## Sheet1
Activity ID | Activity Name | Original Duration | Remaining Duration | Schedule % Complete | Start | Finish | BL Project Start | BL Project Finish | Total Float | Critical | Predecessors | Successors | Variance - BL Project Start Date | Variance - BL Project Finish Date | WBS Name
DHBL DUKHAN HOUSING PROJECT PHASE IX |  | 881 | 881 | 0% | 2012-11-01 | 2015-03-31 | 2012-11-01 | 2015-03-31 | 0 |  |  |  | 0 | 0
DHBL.K10 KEY DATES & MILESTONES |  | 881 | 881 | 0% | 2012-11-01 | 2015-03-31 | 2012-11-01 | 2015-03-31 | 0 |  |  |  | 0 | 0
DHBL.K10.L10 GENERAL |  | 881 | 881 | 0% | 2012-11-01 | 2015-03-31 | 2012-11-01 | 2015-03-31 | 0 |  |  |  | 0 | 0
DUKHKYDGEN0000001000 | Project Commencement | 0 | 0 | 100% | 2012-11-01 |  | 2012-11-01 |  | 0 | Yes |  | DUKHMOBGEN0000003005, DUKHMOBGEN0000003020, DUKHMOBGEN0000003025, DUKHMOBP1APS00002000, DUKHMOBGEN0000003000, DUKHMOBP03PS00002280, DUKHMOBP2BPS00002210, DUKHMOBGEN0000003010, DUKHPROGEN00PQSM1000, DUKHMOBP010000004000, DUKHMOBP020000004000, DUKHMOBP1BPS00002070, DUKHMOBP2APS00002140, DUKHMOBGEN0000003015, DUKHMOBP030000004000, DUKHMOBGEN0000003030 | 0 | 0 | GENERAL
DUKHKYDGEN0000002000 | Project Completion Date | 0 | 0 | 0% |  | 2015-03-31 |  | 2015-03-31 | 0 | Yes | DUKHKYDP030000003000, DUKHKYDP010000001000, DUKHKYDP020000002000 |  | 0 | 0 | GENERAL
DHBL.K10.L15 PACKAGE-1 |  | 0 | 0 | 0% | 2015-03-31 | 2015-03-31 | 2015-03-31 | 2015-03-31 | 0 |  |  |  | 0 | 0
DUKHKYDP010000001000 | Package -1 (Milestone -1) -29 Months | 0 | 0 | 0% |  | 2015-03-31 |  | 2015-03-31 | 0 | Yes | DUKHMOBGEN0000003025, DUKHHANP1BGNDM009020, DUKHHANP1AGNDM009020 | DUKHKYDGEN0000002000 | 0 | 0 | PACKAGE-1
DHBL.K10.L30 PACKAGE-2 |  | 0 | 0 | 0% | 2014-09-30 | 2014-09-30 | 2014-09-30 | 2014-09-30 | 0 |  |  |  | 0 | 0
DUKHKYDP020000002000 | Package -2 (Milestone-2) -23 Months | 0 | 0 | 0% |  | 30-Sep-14* |  | 2014-09-30 | 0 | Yes | DUKHHANP2BGNDM009020, DUKHHANP2AGNDM009020 | DUKHKYDGEN0000002000 | 0 | 0 | PACKAGE-2
DHBL.K10.L45 PACKAGE-3 |  | 0 | 0 | 0% | 2014-11-30 | 2014-11-30 | 2014-11-30 | 2014-11-30 | 0 |  |  |  | 0 | 0
DUKHKYDP030000003000 | Package -3 (Milestone -3) -25 Months | 0 | 0 | 0% |  | 30-Nov-14* |  | 2014-11-30 | 0 | Yes | DUKHHANP03GNDM009020 | DUKHKYDGEN0000002000 | 0 | 0 | PACKAGE-3
DHBL.K15 MOBILIZATION |  | 881 | 881 | 0% | 2012-11-01 | 2015-03-31 | 2012-11-01 | 2015-03-31 | 0 |  |  |  | 0 | 0
DHBL.K15.L05 PROVISIONAL SUM |  | 607 | 607 | 0% | 2012-11-26 | 2014-11-19 | 2012-11-26 | 2014-11-19 | 21 |  |  |  | 0 | 0
DHBL.K15.L05.05 PACKAGE 1A - VILLA |  | 601 | 601 | 0% | 2012-11-26 | 2014-11-12 | 2012-11-26 | 2014-11-12 | 27 |  |  |  | 0 | 0
DUKHMOBP1APS00002015 | Approval of Cost Proposal | 30 | 30 | 0% | 2012-12-30 | 2013-02-02 | 2012-12-30 | 2013-02-02 | 90 | No | DUKHMOBP1APS00002010 | DUKHMOBP1APS00002020 | 0 | 0 | PACKAGE 1A - VILLA
DUKHMOBP1APS00002030 | Commencement of Construction Work | 290 | 290 | 0% | 2013-12-02 | 2014-11-12 | 2013-12-02 | 2014-11-12 | 27 | No | DUKHMOBP1APS00002025, DUKHCONP1AZ1MSEX5000 | DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9PLTC8005 | 0 | 0 | PACKAGE 1A - VILLA
DUKHMOBP1APS00002025 | Engineering & Procurement | 190 | 190 | 0% | 2013-02-03 | 2013-09-16 | 2013-02-03 | 2013-09-16 | 90 | No | DUKHMOBP1APS00002020 | DUKHMOBP1APS00002030 | 0 | 0 | PACKAGE 1A - VILLA
DUKHMOBP1APS00002005 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 90 | No | DUKHMOBP1APS00002000 | DUKHMOBP1APS00002010 | 0 | 0 | PACKAGE 1A - VILLA
DUKHMOBP1APS00002000 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 46 | No | DUKHKYDGEN0000001000 | DUKHMOBI1APS00002035, DUKHMOBP1APS00002005 | 0 | 0 | PACKAGE 1A - VILLA
DUKHMOBP1APS00002020 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-02 |  | 2013-02-02 | 90 | No | DUKHMOBP1APS00002015 | DUKHMOBP1APS00002025 | 0 | 0 | PACKAGE 1A - VILLA
DUKHMOBP1APS00002010 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 90 | No | DUKHMOBP1APS00002005 | DUKHMOBP1APS00002015 | 0 | 0 | PACKAGE 1A - VILLA
DHBL.K15.L05.10 PACKAGE 1A - INFRASTRUCTURE |  | 565 | 565 | 0% | 2012-11-26 | 2014-09-29 | 2012-11-26 | 2014-09-29 | 63 |  |  |  | 0 | 0
DUKHMOBI1APS00002050 | Approval of Cost Proposal | 30 | 30 | 0% | 2013-01-07 | 2013-02-10 | 2013-01-07 | 2013-02-10 | 63 | No | DUKHMOBI1APS00002045 | DUKHMOBI1APS00002055 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00001250 | Approval of Finished Floor Level | 21 | 21 | 0% | 2013-01-20 | 2013-02-13 | 2013-01-20 | 2013-02-13 | 0 | Yes | DUKHMOBI1APS00001225 | DUKHCONP1AZ1STUG1000 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00001200 | Approval of New Site Design Layout | 21 | 21 | 0% | 2012-12-17 | 2013-01-10 | 2012-12-17 | 2013-01-10 | 0 | Yes | DUKHMOBI1APS00001000 | DUKHMOBI1APS00001225, DUKHMOBI1APS00001300 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00001400 | Approval of New Site Design MEP Services Layout | 21 | 21 | 0% | 2013-01-28 | 2013-02-21 | 2013-01-28 | 2013-02-21 | 89 | No | DUKHMOBI1APS00001300 | DUKHENGI1ADWDRSM4250 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00002065 | Commencement of Construction Work | 320 | 320 | 0% | 2013-09-14 | 2014-09-29 | 2013-09-14 | 2014-09-29 | 63 | No | DUKHCONI1AZ1DRGL5115, DUKHMOBI1APS00002060 | DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9ACTC8000 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00002060 | Engineering & Procurement | 180 | 180 | 0% | 2013-02-11 | 2013-09-12 | 2013-02-11 | 2013-09-12 | 63 | No | DUKHMOBI1APS00002055 | DUKHMOBI1APS00002065 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00002040 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 46 | No | DUKHMOBI1APS00002035 | DUKHMOBI1APS00002043 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00002035 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 46 | No | DUKHMOBP1APS00002000 | DUKHMOBI1APS00002040 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00002055 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-10 |  | 2013-02-10 | 63 | No | DUKHMOBI1APS00002050 | DUKHMOBI1APS00002060 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00002043 | Submission & Approval of General Site Layout | 21 | 21 | 0% | 2012-12-04 | 2012-12-29 | 2012-12-04 | 2012-12-29 | 46 | No | DUKHMOBI1APS00002040 | DUKHMOBI1APS00002045, DUKHCONP1AZ1STUG1000 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00002045 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-30 | 2013-01-06 | 2012-12-30 | 2013-01-06 | 63 | No | DUKHMOBI1APS00002043 | DUKHMOBI1APS00002050 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00001225 | Submission of Finished Floor Level | 7 | 7 | 0% | 2013-01-12 | 2013-01-19 | 2013-01-12 | 2013-01-19 | 0 | Yes | DUKHMOBI1APS00001200 | DUKHMOBI1APS00001250 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00001000 | Submission of New Site Design Layout | 14 | 14 | 0% | 2012-12-01 | 2012-12-16 | 2012-12-01 | 2012-12-16 | 0 | Yes | DUKHCONP1AGNSP001000 | DUKHMOBI1APS00001200 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DUKHMOBI1APS00001300 | Submission of New Site Design MEP Services Layout | 14 | 14 | 0% | 2013-01-12 | 2013-01-27 | 2013-01-12 | 2013-01-27 | 89 | No | DUKHMOBI1APS00001200 | DUKHMOBI1APS00001400 | 0 | 0 | PACKAGE 1A - INFRASTRUCTURE
DHBL.K15.L05.15 PACKAGE 1B - VILLA |  | 607 | 607 | 0% | 2012-11-26 | 2014-11-19 | 2012-11-26 | 2014-11-19 | 21 |  |  |  | 0 | 0
DUKHMOBP1BPS00002085 | Approval of Cost Proposal | 30 | 30 | 0% | 2012-12-30 | 2013-02-02 | 2012-12-30 | 2013-02-02 | 80 | No | DUKHMOBP1BPS00002080 | DUKHMOBP1BPS00002090 | 0 | 0 | PACKAGE 1B - VILLA
DUKHMOBP1BPS00002100 | Commencement of Construction Work | 280 | 280 | 0% | 2013-12-22 | 2014-11-19 | 2013-12-22 | 2014-11-19 | 21 | No | DUKHCONP1BZ1MSEX5000, DUKHMOBP1BPS00002095 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6PLTC8005 | 0 | 0 | PACKAGE 1B - VILLA
DUKHMOBP1BPS00002095 | Engineering & Procurement | 210 | 210 | 0% | 2013-02-03 | 2013-10-09 | 2013-02-03 | 2013-10-09 | 80 | No | DUKHMOBP1BPS00002090 | DUKHMOBP1BPS00002100 | 0 | 0 | PACKAGE 1B - VILLA
DUKHMOBP1BPS00002075 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 80 | No | DUKHMOBP1BPS00002070 | DUKHMOBP1BPS00002080 | 0 | 0 | PACKAGE 1B - VILLA
DUKHMOBP1BPS00002070 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 73 | No | DUKHKYDGEN0000001000 | DUKHMOBP1BPS00002075, DUKHMOBI1BPS00002105 | 0 | 0 | PACKAGE 1B - VILLA
DUKHMOBP1BPS00002090 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-02 |  | 2013-02-02 | 80 | No | DUKHMOBP1BPS00002085 | DUKHMOBP1BPS00002095 | 0 | 0 | PACKAGE 1B - VILLA
DUKHMOBP1BPS00002080 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 80 | No | DUKHMOBP1BPS00002075 | DUKHMOBP1BPS00002085 | 0 | 0 | PACKAGE 1B - VILLA
DHBL.K15.L05.20 PACKAGE 1B -INFRASTRUCTURE |  | 585 | 585 | 0% | 2012-11-26 | 2014-10-25 | 2012-11-26 | 2014-10-25 | 43 |  |  |  | 0 | 0
DUKHMOBI1BPS00002120 | Approval of Cost Proposal | 30 | 30 | 0% | 2013-01-07 | 2013-02-10 | 2013-01-07 | 2013-02-10 | 73 | No | DUKHMOBI1BPS00002115 | DUKHMOBI1BPS00002125 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00001250 | Approval of Finished Floor Level | 21 | 21 | 0% | 2013-01-20 | 2013-02-13 | 2013-01-20 | 2013-02-13 | 50 | No | DUKHMOBI1BPS00001225 | DUKHCONP1BZ1STUG1000 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00001200 | Approval of New Site Design Layout | 21 | 21 | 0% | 2012-12-17 | 2013-01-10 | 2012-12-17 | 2013-01-10 | 50 | No | DUKHMOBI1BPS00001000 | DUKHMOBI1BPS00001225, DUKHMOBI1BPS00001300 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00001400 | Approval of New Site Design MEP Services Layout | 21 | 21 | 0% | 2013-01-28 | 2013-02-21 | 2013-01-28 | 2013-02-21 | 89 | No | DUKHMOBI1BPS00001300 | DUKHENGI1BDWDRSM4650 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00002135 | Commencement of Construction Work | 280 | 280 | 0% | 2013-11-25 | 2014-10-25 | 2013-11-25 | 2014-10-25 | 43 | No | DUKHMOBI1BPS00002130, DUKHCONI1BZ1DRGL5115 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6PLTC8005 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00002130 | Engineering & Procurement | 210 | 210 | 0% | 2013-02-11 | 2013-10-20 | 2013-02-11 | 2013-10-20 | 73 | No | DUKHMOBI1BPS00002125 | DUKHMOBI1BPS00002135 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00002110 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 73 | No | DUKHMOBI1BPS00002105 | DUKHMOBI1BPS00002113 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00002105 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 73 | No | DUKHMOBP1BPS00002070 | DUKHMOBI1BPS00002110 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00002125 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-10 |  | 2013-02-10 | 73 | No | DUKHMOBI1BPS00002120 | DUKHMOBI1BPS00002130 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00002113 | Submission & Approval of General Site Layout | 21 | 21 | 0% | 2012-12-04 | 2012-12-29 | 2012-12-04 | 2012-12-29 | 73 | No | DUKHMOBI1BPS00002110 | DUKHMOBI1BPS00002115, DUKHCONP1BZ1STUG1000 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00002115 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-30 | 2013-01-06 | 2012-12-30 | 2013-01-06 | 73 | No | DUKHMOBI1BPS00002113 | DUKHMOBI1BPS00002120 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00001225 | Submission of Finished Floor Level | 7 | 7 | 0% | 2013-01-12 | 2013-01-19 | 2013-01-12 | 2013-01-19 | 50 | No | DUKHMOBI1BPS00001200 | DUKHMOBI1BPS00001250 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00001000 | Submission of New Site Design Layout | 14 | 14 | 0% | 2012-12-01 | 2012-12-16 | 2012-12-01 | 2012-12-16 | 50 | No | DUKHCONP1BGNSP001000 | DUKHMOBI1BPS00001200 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DUKHMOBI1BPS00001300 | Submission of New Site Design MEP Services Layout | 14 | 14 | 0% | 2013-01-12 | 2013-01-27 | 2013-01-12 | 2013-01-27 | 89 | No | DUKHMOBI1BPS00001200 | DUKHMOBI1BPS00001400 | 0 | 0 | PACKAGE 1B -INFRASTRUCTURE
DHBL.K15.L05.25 PACKAGE 2A - VILLA |  | 431 | 431 | 0% | 2012-11-26 | 2014-04-22 | 2012-11-26 | 2014-04-22 | 45 |  |  |  | 0 | 0
DUKHMOBP2APS00002155 | Approval of Cost Proposal | 30 | 30 | 0% | 2012-12-30 | 2013-02-02 | 2012-12-30 | 2013-02-02 | 118 | No | DUKHMOBP2APS00002150 | DUKHMOBP2APS00002160 | 0 | 0 | PACKAGE 2A - VILLA
DUKHMOBP2APS00002170 | Commencement of Construction Work | 180 | 180 | 0% | 2013-09-21 | 2014-04-22 | 2013-09-21 | 2014-04-22 | 45 | No | DUKHCONP2AZ1MSEX5020, DUKHMOBP2APS00002165 | DUKHCONP2AZ2ACTC8000, DUKHCONP2AZ2ELTC8010, DUKHCONP2AZ2PLTC8005 | 0 | 0 | PACKAGE 2A - VILLA
DUKHMOBP2APS00002165 | Engineering & Procurement | 120 | 120 | 0% | 2013-02-03 | 2013-06-23 | 2013-02-03 | 2013-06-23 | 118 | No | DUKHMOBP2APS00002160 | DUKHMOBP2APS00002170 | 0 | 0 | PACKAGE 2A - VILLA
DUKHMOBP2APS00002145 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 118 | No | DUKHMOBP2APS00002140 | DUKHMOBP2APS00002150 | 0 | 0 | PACKAGE 2A - VILLA
DUKHMOBP2APS00002140 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 88 | No | DUKHKYDGEN0000001000 | DUKHMOBI2APS00002175, DUKHMOBP2APS00002145 | 0 | 0 | PACKAGE 2A - VILLA
DUKHMOBP2APS00002160 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-02 |  | 2013-02-02 | 118 | No | DUKHMOBP2APS00002155 | DUKHMOBP2APS00002165 | 0 | 0 | PACKAGE 2A - VILLA
DUKHMOBP2APS00002150 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 118 | No | DUKHMOBP2APS00002145 | DUKHMOBP2APS00002155 | 0 | 0 | PACKAGE 2A - VILLA
DHBL.K15.L05.30 PACKAGE 2A- INFRASTRUCTURE |  | 441 | 441 | 0% | 2012-11-26 | 2014-05-04 | 2012-11-26 | 2014-05-04 | 35 |  |  |  | 0 | 0
DUKHMOBI2APS00002190 | Approval of Cost Proposal | 30 | 30 | 0% | 2012-12-30 | 2013-02-02 | 2012-12-30 | 2013-02-02 | 88 | No | DUKHMOBI2APS00002185 | DUKHMOBI2APS00002195 | 0 | 0 | PACKAGE 2A- INFRASTRUCTURE
DUKHMOBI2APS00002205 | Commencement of Construction Work | 210 | 210 | 0% | 2013-08-28 | 2014-05-04 | 2013-08-28 | 2014-05-04 | 35 | No | DUKHMOBI2APS00002200, DUKHCONI2AZ1DRGL5115 | DUKHCONP2AZ2PLTC8005, DUKHCONP2AZ2ELTC8010, DUKHCONP2AZ2ACTC8000 | 0 | 0 | PACKAGE 2A- INFRASTRUCTURE
DUKHMOBI2APS00002200 | Engineering & Procurement | 120 | 120 | 0% | 2013-02-03 | 2013-06-23 | 2013-02-03 | 2013-06-23 | 88 | No | DUKHMOBI2APS00002195 | DUKHMOBI2APS00002205 | 0 | 0 | PACKAGE 2A- INFRASTRUCTURE
DUKHMOBI2APS00002180 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 88 | No | DUKHMOBI2APS00002175 | DUKHMOBI2APS00002185 | 0 | 0 | PACKAGE 2A- INFRASTRUCTURE
DUKHMOBI2APS00002175 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 88 | No | DUKHMOBP2APS00002140 | DUKHMOBI2APS00002180 | 0 | 0 | PACKAGE 2A- INFRASTRUCTURE
DUKHMOBI2APS00002195 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-02 |  | 2013-02-02 | 88 | No | DUKHMOBI2APS00002190 | DUKHMOBI2APS00002200 | 0 | 0 | PACKAGE 2A- INFRASTRUCTURE
DUKHMOBI2APS00002185 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 88 | No | DUKHMOBI2APS00002180 | DUKHMOBI2APS00002190 | 0 | 0 | PACKAGE 2A- INFRASTRUCTURE
DHBL.K15.L05.35 PACKAGE 2B - VILLA |  | 442 | 442 | 0% | 2012-11-26 | 2014-05-05 | 2012-11-26 | 2014-05-05 | 34 |  |  |  | 0 | 0
DUKHMOBP2BPS00002225 | Approval of Cost Proposal | 30 | 30 | 0% | 2012-12-30 | 2013-02-02 | 2012-12-30 | 2013-02-02 | 88 | No | DUKHMOBP2BPS00002220 | DUKHMOBP2BPS00002230 | 0 | 0 | PACKAGE 2B - VILLA
DUKHMOBP2BPS00002240 | Commencement of Construction Work | 180 | 180 | 0% | 2013-10-03 | 2014-05-05 | 2013-10-03 | 2014-05-05 | 34 | No | DUKHMOBP2BPS00002235, DUKHCONP2BZ3MSEX5000 | DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5PLTC8005, DUKHCONP2BZ5ACTC8000 | 0 | 0 | PACKAGE 2B - VILLA
DUKHMOBP2BPS00002235 | Engineering & Procurement | 150 | 150 | 0% | 2013-02-03 | 2013-07-28 | 2013-02-03 | 2013-07-28 | 88 | No | DUKHMOBP2BPS00002230 | DUKHMOBP2BPS00002240 | 0 | 0 | PACKAGE 2B - VILLA
DUKHMOBP2BPS00002215 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 88 | No | DUKHMOBP2BPS00002210 | DUKHMOBP2BPS00002220 | 0 | 0 | PACKAGE 2B - VILLA
DUKHMOBP2BPS00002210 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 48 | No | DUKHKYDGEN0000001000 | DUKHMOBP2BPS00002215, DUKHMOBI2BPS00002245 | 0 | 0 | PACKAGE 2B - VILLA
DUKHMOBP2BPS00002230 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-02 |  | 2013-02-02 | 88 | No | DUKHMOBP2BPS00002225 | DUKHMOBP2BPS00002235 | 0 | 0 | PACKAGE 2B - VILLA
DUKHMOBP2BPS00002220 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 88 | No | DUKHMOBP2BPS00002215 | DUKHMOBP2BPS00002225 | 0 | 0 | PACKAGE 2B - VILLA
DHBL.K15.L05.40 PACKAGE 2B - INFRASTRUCTURE |  | 440 | 440 | 0% | 2012-11-26 | 2014-05-03 | 2012-11-26 | 2014-05-03 | 36 |  |  |  | 0 | 0
DUKHMOBI2BPS00002260 | Approval of Cost Proposal | 30 | 30 | 0% | 2012-12-30 | 2013-02-02 | 2012-12-30 | 2013-02-02 | 48 | No | DUKHMOBI2BPS00002255 | DUKHMOBI2BPS00002265 | 0 | 0 | PACKAGE 2B - INFRASTRUCTURE
DUKHMOBI2BPS00002275 | Commencement of Construction Work | 230 | 230 | 0% | 2013-07-31 | 2014-05-03 | 2013-07-31 | 2014-05-03 | 36 | No | DUKHMOBI2BPS00002270, DUKHCONI2BZ1DRGL5115 | DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5ACTC8000, DUKHCONP2BZ5PLTC8005 | 0 | 0 | PACKAGE 2B - INFRASTRUCTURE
DUKHMOBI2BPS00002270 | Engineering & Procurement | 140 | 140 | 0% | 2013-02-03 | 2013-07-16 | 2013-02-03 | 2013-07-16 | 48 | No | DUKHMOBI2BPS00002265 | DUKHMOBI2BPS00002275 | 0 | 0 | PACKAGE 2B - INFRASTRUCTURE
DUKHMOBI2BPS00002250 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 48 | No | DUKHMOBI2BPS00002245 | DUKHMOBI2BPS00002255 | 0 | 0 | PACKAGE 2B - INFRASTRUCTURE
DUKHMOBI2BPS00002245 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 48 | No | DUKHMOBP2BPS00002210 | DUKHMOBI2BPS00002250 | 0 | 0 | PACKAGE 2B - INFRASTRUCTURE
DUKHMOBI2BPS00002265 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-02 |  | 2013-02-02 | 48 | No | DUKHMOBI2BPS00002260 | DUKHMOBI2BPS00002270 | 0 | 0 | PACKAGE 2B - INFRASTRUCTURE
DUKHMOBI2BPS00002255 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 48 | No | DUKHMOBI2BPS00002250 | DUKHMOBI2BPS00002260 | 0 | 0 | PACKAGE 2B - INFRASTRUCTURE
DHBL.K15.L05.45 PACKAGE 3 - APARTMENT |  | 423 | 423 | 0% | 2012-11-26 | 2014-04-13 | 2012-11-26 | 2014-04-13 | 3 |  |  |  | 0 | 0
DUKHMOBP03PS00002295 | Approval of Cost Proposal | 30 | 30 | 0% | 2012-12-30 | 2013-02-02 | 2012-12-30 | 2013-02-02 | 98 | No | DUKHMOBP03PS00002290 | DUKHMOBP03PS00002300 | 0 | 0 | PACKAGE 3 - APARTMENT
DUKHMOBP03PS00002310 | Commencement of Construction Work | 120 | 120 | 0% | 2013-11-23 | 2014-04-13 | 2013-11-23 | 2014-04-13 | 3 | No | DUKHMOBP03PS00002305, DUKHCONP03Z1MSEX5000 | DUKHCONP03Z1ACTC8000, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005 | 0 | 0 | PACKAGE 3 - APARTMENT
DUKHMOBP03PS00002305 | Engineering & Procurement | 150 | 150 | 0% | 2013-02-03 | 2013-07-28 | 2013-02-03 | 2013-07-28 | 98 | No | DUKHMOBP03PS00002300 | DUKHMOBP03PS00002310 | 0 | 0 | PACKAGE 3 - APARTMENT
DUKHMOBP03PS00002285 | Finalization of Subcontractor | 21 | 21 | 0% | 2012-11-26 | 2012-12-20 | 2012-11-26 | 2012-12-20 | 98 | No | DUKHMOBP03PS00002280 | DUKHMOBP03PS00002290 | 0 | 0 | PACKAGE 3 - APARTMENT
DUKHMOBP03PS00002280 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 39 | No | DUKHKYDGEN0000001000 | DUKHMOBI03PS00002315, DUKHMOBP03PS00002285 | 0 | 0 | PACKAGE 3 - APARTMENT
DUKHMOBP03PS00002300 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-02 |  | 2013-02-02 | 98 | No | DUKHMOBP03PS00002295 | DUKHMOBP03PS00002305 | 0 | 0 | PACKAGE 3 - APARTMENT
DUKHMOBP03PS00002290 | Submission of Cost Proposal | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 98 | No | DUKHMOBP03PS00002285 | DUKHMOBP03PS00002295 | 0 | 0 | PACKAGE 3 - APARTMENT
DHBL.K15.L05.50 PACKAGE 3 - INFRASTRUCTURE |  | 421 | 421 | 0% | 2012-11-26 | 2014-04-10 | 2012-11-26 | 2014-04-10 | 5 |  |  |  | 0 | 0
DUKHMOBI03PS00002330 | Approval of Cost Proposal | 30 | 30 | 0% | 2013-01-09 | 2013-02-13 | 2013-01-09 | 2013-02-13 | 39 | No | DUKHMOBI03PS00002325 | DUKHMOBI03PS00002335 | 0 | 0 | PACKAGE 3 - INFRASTRUCTURE
DUKHMOBI03PS00002345 | Commencement of Construction Work | 200 | 200 | 0% | 2013-08-17 | 2014-04-10 | 2013-08-17 | 2014-04-10 | 5 | No | DUKHCONI03Z1DRGL5115, DUKHMOBI03PS00002340 | DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1ELTC8010 | 0 | 0 | PACKAGE 3 - INFRASTRUCTURE
DUKHMOBI03PS00002340 | Engineering & Procurement | 120 | 120 | 0% | 2013-02-14 | 2013-07-03 | 2013-02-14 | 2013-07-03 | 39 | No | DUKHMOBI03PS00002335 | DUKHMOBI03PS00002345 | 0 | 0 | PACKAGE 3 - INFRASTRUCTURE
DUKHMOBI03PS00002320 | Finalization of Subcontractor | 30 | 30 | 0% | 2012-11-26 | 2012-12-31 | 2012-11-26 | 2012-12-31 | 39 | No | DUKHMOBI03PS00002315 | DUKHMOBI03PS00002325 | 0 | 0 | PACKAGE 3 - INFRASTRUCTURE
DUKHMOBI03PS00002315 | Receiving of Site Instruction | 0 | 0 | 0% | 2012-11-26 |  | 2012-11-26 |  | 39 | No | DUKHMOBP03PS00002280 | DUKHMOBI03PS00002320 | 0 | 0 | PACKAGE 3 - INFRASTRUCTURE
DUKHMOBI03PS00002335 | Receiving of Variation Order | 0 | 0 | 0% |  | 2013-02-13 |  | 2013-02-13 | 39 | No | DUKHMOBI03PS00002330 | DUKHMOBI03PS00002340 | 0 | 0 | PACKAGE 3 - INFRASTRUCTURE
DUKHMOBI03PS00002325 | Submission of Cost Proposal | 7 | 7 | 0% | 2013-01-01 | 2013-01-08 | 2013-01-01 | 2013-01-08 | 39 | No | DUKHMOBI03PS00002320 | DUKHMOBI03PS00002330 | 0 | 0 | PACKAGE 3 - INFRASTRUCTURE
DHBL.K15.L10 GENERAL |  | 881 | 881 | 0% | 2012-11-01 | 2015-03-31 | 2012-11-01 | 2015-03-31 | 0 |  |  |  | 0 | 0
DUKHMOBGEN0000003015 | Commencement of works (Clause 41) | 30 | 30 | 0% | 2012-11-01 | 2012-12-05 | 2012-11-01 | 2012-12-05 | 57 | No | DUKHKYDGEN0000001000 | DUKHMOBP010000004030 | 0 | 0 | GENERAL
DUKHMOBGEN0000003020 | Construction of plant,Temporary works & material | 30 | 30 | 0% | 2012-11-01 | 2012-12-05 | 2012-11-01 | 2012-12-05 | 42 | No | DUKHKYDGEN0000001000 | DUKHMOBP010000004020 | 0 | 0 | GENERAL
DUKHMOBGEN0000003025 | Construction Running Cost | 881 | 881 | 0% | 2012-11-01 | 2015-03-31 | 2012-11-01 | 2015-03-31 | 0 | Yes | DUKHKYDGEN0000001000 | DUKHKYDP010000001000 | 0 | 0 | GENERAL
DUKHMOBGEN0000003010 | Insurance of works (Clause 21-23) | 30 | 30 | 0% | 2012-11-01 | 2012-12-05 | 2012-11-01 | 2012-12-05 | 72 | No | DUKHKYDGEN0000001000 | DUKHMOBP010000004020 | 0 | 0 | GENERAL
DUKHMOBGEN0000003000 | Performance Bond (Clause 10) | 30 | 30 | 0% | 2012-11-01 | 2012-12-05 | 2012-11-01 | 2012-12-05 | 72 | No | DUKHKYDGEN0000001000 | DUKHMOBP010000004020 | 0 | 0 | GENERAL
DUKHMOBGEN0000003005 | Setting Out (Clause 17) | 30 | 30 | 0% | 2012-11-01 | 2012-12-05 | 2012-11-01 | 2012-12-05 | 72 | No | DUKHKYDGEN0000001000 | DUKHMOBP010000004020 | 0 | 0 | GENERAL
DUKHMOBGEN0000003035 | Sub & App -HSE plan | 60 | 60 | 0% | 2012-11-12 | 2013-01-21 | 2012-11-12 | 2013-01-21 | 89 | No | DUKHMOBGEN0000003030 | DUKHMOBGEN0000003040 | 0 | 0 | GENERAL
DUKHMOBGEN0000003030 | Sub & App -Key Personnel CVs | 60 | 60 | 0% | 2012-11-06 | 2013-01-15 | 2012-11-06 | 2013-01-15 | 89 | No | DUKHKYDGEN0000001000 | DUKHMOBGEN0000003035 | 0 | 0 | GENERAL
DUKHMOBGEN0000003040 | Sub & App -Quality plan | 60 | 60 | 0% | 2012-11-18 | 2013-01-27 | 2012-11-18 | 2013-01-27 | 89 | No | DUKHMOBGEN0000003035 | DUKHMOBP010000004060 | 0 | 0 | GENERAL
DHBL.K15.L15 PACKAGE-1 |  | 85 | 85 | 0% | 2012-11-01 | 2013-02-09 | 2012-11-01 | 2013-02-09 | 52 |  |  |  | 0 | 0
DUKHMOBP010000004080 | Establishment of Labour Mess & Toilets | 20 | 20 | 0% | 2013-01-07 | 2013-01-29 | 2013-01-07 | 2013-01-29 | 61 | No | DUKHMOBP010000004040 | DUKHCONP1AZ1STUG1020 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004060 | Establishment of Security Fences & Gates | 20 | 20 | 0% | 2013-01-07 | 2013-01-29 | 2013-01-07 | 2013-01-29 | 61 | No | DUKHMOBP010000004000, DUKHMOBP010000004040, DUKHMOBGEN0000003040, DUKHMOBP010000004010 | DUKHCONP1AZ1STUG1020 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004070 | Establishment of Site offices | 20 | 20 | 0% | 2013-01-17 | 2013-02-09 | 2013-01-17 | 2013-02-09 | 52 | No | DUKHMOBP010000004030, DUKHMOBP010000004040, DUKHMOBP010000004010 | DUKHCONP1AZ1STUG1020 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004090 | Establishment of Stores & Workshops | 20 | 20 | 0% | 2013-01-07 | 2013-01-29 | 2013-01-07 | 2013-01-29 | 61 | No | DUKHMOBP010000004040 | DUKHCONP1AZ1STUG1020 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004000 | Securing Gate Passes/Access Permit & Courses | 25 | 25 | 0% | 2012-11-01 | 2012-11-29 | 2012-11-01 | 2012-11-29 | 0 | Yes | DUKHKYDGEN0000001000 | DUKHCONP1AGNSP002000, DUKHCONP1AGNSP001000, DUKHMOBP010000004020, DUKHMOBP010000004060, DUKHMOBP010000004010, DUKHCONP1BGNSP001000, DUKHMOBP010000004030, DUKHENGP1ADWSTSM4000 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004040 | Securing Permit To Work | 20 | 20 | 0% | 2012-12-13 | 2013-01-06 | 2012-12-13 | 2013-01-06 | 37 | No | DUKHMOBP010000004010 | DUKHCONP1AZ1STUG1000, DUKHMOBP010000004080, DUKHMOBP010000004090, DUKHMOBP010000004060, DUKHMOBP010000004070, DUKHMOBP010000004050 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004050 | Site Cleaning & Leveling Works | 25 | 25 | 0% | 2012-12-26 | 2013-01-23 | 2012-12-26 | 2013-01-23 | 37 | No | DUKHMOBP010000004040 | DUKHCONP1AZ1STUG1000 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004030 | Sub & App of Layout Drawings-Temporary Struct. | 30 | 30 | 0% | 2012-12-12 | 2013-01-16 | 2012-12-12 | 2013-01-16 | 52 | No | DUKHMOBGEN0000003015, DUKHMOBP010000004020, DUKHMOBP010000004000 | DUKHMOBP010000004070 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004020 | Sub & App of Method Statement-Temporary Struct. | 30 | 30 | 0% | 2012-12-06 | 2013-01-10 | 2012-12-06 | 2013-01-10 | 42 | No | DUKHMOBGEN0000003000, DUKHMOBP010000004000, DUKHMOBP010000004010, DUKHMOBGEN0000003010, DUKHMOBGEN0000003020, DUKHMOBGEN0000003005 | DUKHMOBP010000004030, DUKHENGP1BDWSTSM4400 | 0 | 0 | PACKAGE-1
DUKHMOBP010000004010 | Sub & Approval of Site Logistic Plan | 30 | 30 | 0% | 2012-11-08 | 2012-12-12 | 2012-11-08 | 2012-12-12 | 37 | No | DUKHMOBP010000004000 | DUKHMOBP010000004020, DUKHMOBP010000004040, DUKHMOBP010000004070, DUKHMOBP010000004060 | 0 | 0 | PACKAGE-1
DHBL.K15.L30 PACKAGE-2 |  | 96 | 96 | 0% | 2012-11-01 | 2013-02-23 | 2012-11-01 | 2013-02-23 | 44 |  |  |  | 0 | 0
DUKHMOBP020000004080 | Establishment of Labour Mess & Toilets | 20 | 20 | 0% | 2012-12-20 | 2013-01-12 | 2012-12-20 | 2013-01-12 | 59 | No | DUKHMOBP020000004040 | DUKHCONP2AZ1STUG1020 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004060 | Establishment of Security Fences & Gates | 20 | 20 | 0% | 2013-01-30 | 2013-02-23 | 2013-01-30 | 2013-02-23 | 44 | No | DUKHMOBP020000004010, DUKHMOBP020000004040, DUKHMOBP020000004030, DUKHMOBP020000004000 | DUKHCONP2AZ1STUG1020 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004070 | Establishment of Site offices | 20 | 20 | 0% | 2012-12-20 | 2013-01-12 | 2012-12-20 | 2013-01-12 | 59 | No | DUKHMOBP020000004040, DUKHMOBP020000004010 | DUKHCONP2AZ1STUG1020 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004090 | Establishment of Stores & Workshops | 20 | 20 | 0% | 2012-12-20 | 2013-01-12 | 2012-12-20 | 2013-01-12 | 59 | No | DUKHMOBP020000004040 | DUKHCONP2AZ1STUG1020 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004000 | Securing Gate Passes/Access Permit & Courses | 25 | 25 | 0% | 2012-11-01 | 2012-11-29 | 2012-11-01 | 2012-11-29 | 0 | Yes | DUKHKYDGEN0000001000 | DUKHCONP2AGNSP002000, DUKHCONP2BGNSP001000, DUKHMOBP020000004020, DUKHMOBP020000004060, DUKHMOBP020000004010, DUKHCONP2AGNSP001000, DUKHMOBP020000004030 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004040 | Securing Permit To Work | 20 | 20 | 0% | 2012-11-26 | 2012-12-19 | 2012-11-26 | 2012-12-19 | 39 | No | DUKHMOBP020000004010 | DUKHMOBP020000004070, DUKHMOBP020000004090, DUKHMOBP020000004050, DUKHMOBP020000004060, DUKHMOBP020000004080 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004050 | Site Cleaning & Leveling Works | 25 | 25 | 0% | 2012-12-08 | 2013-01-06 | 2012-12-08 | 2013-01-06 | 39 | No | DUKHMOBP020000004040 | DUKHCONP2AZ1STUG1000 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004030 | Sub & App of Layout Drawings-Temporary Struct. | 30 | 30 | 0% | 2012-12-26 | 2013-01-29 | 2012-12-26 | 2013-01-29 | 44 | No | DUKHMOBP020000004020, DUKHMOBP020000004000 | DUKHMOBP020000004060 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004020 | Sub & App of Method Statement-Temporary Struct. | 30 | 30 | 0% | 2012-11-20 | 2012-12-25 | 2012-11-20 | 2012-12-25 | 44 | No | DUKHMOBP020000004000, DUKHMOBP020000004010 | DUKHMOBP020000004030, DUKHENGP2ADWSTSM4800, DUKHENGP2BDWSTSM5180 | 0 | 0 | PACKAGE-2
DUKHMOBP020000004010 | Sub & Approval of Site Logistic Plan | 30 | 30 | 0% | 2012-11-14 | 2012-12-19 | 2012-11-14 | 2012-12-19 | 39 | No | DUKHMOBP020000004000 | DUKHMOBP020000004060, DUKHMOBP020000004040, DUKHMOBP020000004020, DUKHMOBP020000004070 | 0 | 0 | PACKAGE-2
DHBL.K15.L45 PACKAGE-3 |  | 77 | 77 | 0% | 2012-11-01 | 2013-01-30 | 2012-11-01 | 2013-01-30 | 48 |  |  |  | 0 | 0
DUKHMOBP030000004080 | Establishment of Labour Mess & Toilets | 20 | 20 | 0% | 2013-01-08 | 2013-01-30 | 2013-01-08 | 2013-01-30 | 48 | No | DUKHMOBP030000004040 | DUKHCONP03Z1STUG1020 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004060 | Establishment of Security Fences & Gates | 20 | 20 | 0% | 2013-01-08 | 2013-01-30 | 2013-01-08 | 2013-01-30 | 48 | No | DUKHMOBP030000004010, DUKHMOBP030000004000, DUKHMOBP030000004040 | DUKHCONP03Z1STUG1020 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004070 | Establishment of Site offices | 20 | 20 | 0% | 2013-01-08 | 2013-01-30 | 2013-01-08 | 2013-01-30 | 48 | No | DUKHMOBP030000004040, DUKHMOBP030000004010, DUKHMOBP030000004030 | DUKHCONP03Z1STUG1020 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004090 | Establishment of Stores & Workshops | 20 | 20 | 0% | 2013-01-08 | 2013-01-30 | 2013-01-08 | 2013-01-30 | 28 | No | DUKHMOBP030000004040 | DUKHCONP03Z1STUG1020 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004000 | Securing Gate Passes/Access Permit & Courses | 25 | 25 | 0% | 2012-11-01 | 2012-11-29 | 2012-11-01 | 2012-11-29 | 0 | Yes | DUKHKYDGEN0000001000 | DUKHMOBP030000004030, DUKHMOBP030000004020, DUKHMOBP030000004060, DUKHCONP03GNSP001000, DUKHMOBP030000004010, DUKHENGP03DWSTSM5560 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004040 | Securing Permit To Work | 20 | 20 | 0% | 2012-12-15 | 2013-01-07 | 2012-12-15 | 2013-01-07 | 24 | No | DUKHMOBP030000004010 | DUKHMOBP030000004080, DUKHMOBP030000004070, DUKHMOBP030000004090, DUKHMOBP030000004060, DUKHMOBP030000004050 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004050 | Site Cleaning & Leveling Works | 25 | 25 | 0% | 2012-12-20 | 2013-01-17 | 2012-12-20 | 2013-01-17 | 24 | No | DUKHMOBP030000004040 | DUKHCONP03Z1STUG1000 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004030 | Sub & App of Layout Drawings-Temporary Struct. | 30 | 30 | 0% | 2012-11-17 | 2012-12-22 | 2012-11-17 | 2012-12-22 | 62 | No | DUKHMOBP030000004000, DUKHMOBP030000004020 | DUKHMOBP030000004070 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004020 | Sub & App of Method Statement-Temporary Struct. | 30 | 30 | 0% | 2012-11-17 | 2012-12-22 | 2012-11-17 | 2012-12-22 | 62 | No | DUKHMOBP030000004000, DUKHMOBP030000004010 | DUKHMOBP030000004030 | 0 | 0 | PACKAGE-3
DUKHMOBP030000004010 | Sub & Approval of Site Logistic Plan | 30 | 30 | 0% | 2012-11-10 | 2012-12-13 | 2012-11-10 | 2012-12-13 | 24 | No | DUKHMOBP030000004000 | DUKHMOBP030000004060, DUKHMOBP030000004040, DUKHMOBP030000004070, DUKHMOBP030000004020 | 0 | 0 | PACKAGE-3
DHBL.K20 ENGINEERING |  | 245 | 245 | 0% | 2012-11-26 | 2013-09-12 | 2012-11-26 | 2013-09-12 | 272 |  |  |  | 0 | 0
DHBL.K20.L20 PACKAGE-1A |  | 241 | 241 | 0% | 2012-12-01 | 2013-09-12 | 2012-12-01 | 2013-09-12 | 272 |  |  |  | 0 | 0
DHBL.K20.L20.E05 SHOP DRAWINGS SUBMISSION & APPROVAL |  | 241 | 241 | 0% | 2012-12-01 | 2013-09-12 | 2012-12-01 | 2013-09-12 | 272 |  |  |  | 0 | 0
DHBL.K20.L20.E05.H05 STRUCTURAL DRAWINGS |  | 80 | 80 | 0% | 2012-12-01 | 2013-03-05 | 2012-12-01 | 2013-03-05 | 133 |  |  |  | 0 | 0
DHBL.K20.L20.E05.H05.G10 SUBMISSION OF DRAWINGS |  | 50 | 50 | 0% | 2012-12-01 | 2013-01-28 | 2012-12-01 | 2013-01-28 | 48 |  |  |  | 0 | 0
DUKHENGP1ADWSTSM4020 | Column Drawings-Sub | 15 | 15 | 0% | 2012-12-12 | 2012-12-30 | 2012-12-12 | 2012-12-30 | 48 | No | DUKHENGP1ADWSTSM4010 | DUKHENGP1ADWSTAP4020, DUKHENGP1ADWSTSM4030 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWSTSM4040 | FF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2013-01-12 | 2013-01-28 | 2013-01-12 | 2013-01-28 | 48 | No | DUKHENGP1ADWSTSM4030 | DUKHENGP1ADWARSM4050, DUKHENGP1ADWSTAP4040 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWSTSM4000 | Footing Drawings-Sub | 10 | 10 | 0% | 2012-12-01 | 2012-12-11 | 2012-12-01 | 2012-12-11 | 46 | No | DUKHMOBP010000004000 | DUKHENGP1ADWSTSM4010, DUKHENGP1ADWSTAP4000 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWSTSM4030 | GF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2012-12-25 | 2013-01-10 | 2012-12-25 | 2013-01-10 | 48 | No | DUKHENGP1ADWSTSM4020 | DUKHENGP1ADWSTSM4040, DUKHENGP1ADWSTAP4030 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWSTSM4010 | Grade Beam & Slab Drawings-Sub | 15 | 15 | 0% | 2012-12-06 | 2012-12-24 | 2012-12-06 | 2012-12-24 | 48 | No | DUKHENGP1ADWSTSM4000 | DUKHENGP1ADWSTAP4010, DUKHENGP1ADWSTSM4020 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L20.E05.H05.G20 APPROVAL OF DRAWINGS |  | 70 | 70 | 0% | 2012-12-12 | 2013-03-05 | 2012-12-12 | 2013-03-05 | 133 |  |  |  | 0 | 0
DUKHENGP1ADWSTAP4020 | Column Drawings-App | 30 | 30 | 0% | 2012-12-31 | 2013-02-03 | 2012-12-31 | 2013-02-03 | 123 | No | DUKHENGP1ADWSTSM4020 | DUKHCONP1AZ1STGF2000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWSTAP4040 | FF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-01-29 | 2013-03-05 | 2013-01-29 | 2013-03-05 | 133 | No | DUKHENGP1ADWSTSM4040 | DUKHCONP1AZ1STFF2020 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWSTAP4000 | Footing Drawings-App | 25 | 25 | 0% | 2012-12-12 | 2013-01-10 | 2012-12-12 | 2013-01-10 | 46 | No | DUKHENGP1ADWSTSM4000 | DUKHCONP1AZ1STUG1015 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWSTAP4030 | GF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-01-12 | 2013-02-16 | 2013-01-12 | 2013-02-16 | 133 | No | DUKHENGP1ADWSTSM4030 | DUKHCONP1AZ1STGF2010 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWSTAP4010 | Grade Beam & Slab Drawings-App | 30 | 30 | 0% | 2012-12-25 | 2013-01-28 | 2012-12-25 | 2013-01-28 | 86 | No | DUKHENGP1ADWSTSM4010 | DUKHCONP1AZ1STUG1045, DUKHCONP1AZ1STUG1040 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L20.E05.H10 ARCHITECTURAL DRAWINGS |  | 102 | 102 | 0% | 2013-01-29 | 2013-05-28 | 2013-01-29 | 2013-05-28 | 83 |  |  |  | 0 | 0
DHBL.K20.L20.E05.H10.G10 SUBMISSION OF DRAWINGS |  | 72 | 72 | 0% | 2013-01-29 | 2013-04-23 | 2013-01-29 | 2013-04-23 | 83 |  |  |  | 0 | 0
DUKHENGP1ADWARSM4120 | Aluminum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 82 | No | DUKHPROGEN00PQAP1050, DUKHPROGEN00PQAP2050 | DUKHENGP1ADWARAP4120 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4140 | Carpentry & Joinery Drawings-Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 83 | No | DUKHENGP1ADWARSM4050, DUKHPROGEN00PQAP1150, DUKHPROGEN00PQAP2150 | DUKHENGP1ADWARAP4140 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4080 | Ceramic Flooring & Wall Drawings-Sub | 15 | 15 | 0% | 2013-03-02 | 2013-03-18 | 2013-03-02 | 2013-03-18 | 48 | No | DUKHENGP1ADWARSM4050, DUKHENGP1ADWARSM4060, DUKHENGP1ADWARSM4070 | DUKHENGP1ADWARAP4080, DUKHENGP1ADWARSM4090 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4100 | Cobble & Slate Flooring Drawings-Sub | 15 | 15 | 0% | 2013-03-02 | 2013-03-18 | 2013-03-02 | 2013-03-18 | 88 | No | DUKHENGP1ADWARSM4090 | DUKHENGP1ADWARAP4100 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4130 | Doors & window Drawings-Sub | 15 | 15 | 0% | 2013-03-20 | 2013-04-06 | 2013-03-20 | 2013-04-06 | 61 | No | DUKHPROGEN00PQAP1080, DUKHENGP1ADWARSM4050, DUKHPROGEN00PQAP2080 | DUKHENGP1ADWARAP4130 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4060 | First Floor Plan-Sub | 15 | 15 | 0% | 2013-02-11 | 2013-02-28 | 2013-02-11 | 2013-02-28 | 48 | No | DUKHENGP1ADWARSM4050 | DUKHENGP1ADWARAP4060, DUKHENGP1ADWARSM4080, DUKHENGP1ADWARSM4070 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4050 | Ground Floor Plan-Sub | 15 | 15 | 0% | 2013-01-29 | 2013-02-16 | 2013-01-29 | 2013-02-16 | 48 | No | DUKHENGP1ADWSTSM4040 | DUKHENGP1ADWARSM4080, DUKHENGP1ADWARSM4140, DUKHENGP1ADWARAP4050, DUKHENGP1ADWARSM4130, DUKHENGP1ADWARSM4060 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4110 | Gypsum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 67 | No | DUKHPROGEN00PQAP2050, DUKHPROGEN00PQAP1050 | DUKHENGP1ADWARAP4110 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4090 | Porcelain Floor Drawings-Sub | 15 | 15 | 0% | 2013-03-02 | 2013-03-18 | 2013-03-02 | 2013-03-18 | 57 | No | DUKHENGP1ADWARSM4080 | DUKHENGP1ADWARSM4100, DUKHENGP1ADWARAP4090 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWARSM4070 | Roof Floor Plan-Sub | 15 | 15 | 0% | 2013-02-20 | 2013-03-09 | 2013-02-20 | 2013-03-09 | 53 | No | DUKHENGP1ADWARSM4060 | DUKHENGP1ADWARSM4080, DUKHENGP1ADWARAP4070 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L20.E05.H10.G20 APPROVAL OF DRAWINGS |  | 87 | 87 | 0% | 2013-02-17 | 2013-05-28 | 2013-02-17 | 2013-05-28 | 83 |  |  |  | 0 | 0
DUKHENGP1ADWARAP4120 | Aluminum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 82 | No | DUKHENGP1ADWARSM4120 | DUKHPROGEN00PRDV3310 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4140 | Carpentry & Joinery Drawings-App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 83 | No | DUKHENGP1ADWARSM4140 | DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3570, DUKHPROGEN00PRDV3550 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4080 | Ceramic Flooring & Wall Drawings-App | 30 | 30 | 0% | 2013-03-19 | 2013-04-22 | 2013-03-19 | 2013-04-22 | 48 | No | DUKHENGP1ADWARSM4080 | DUKHPROGEN00PRDV3120 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4100 | Cobble & Slate Flooring Drawings-App | 30 | 30 | 0% | 2013-03-19 | 2013-04-22 | 2013-03-19 | 2013-04-22 | 88 | No | DUKHENGP1ADWARSM4100 | DUKHPROGEN00PRDV3090, DUKHPROGEN00PRDV3100 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4130 | Doors & Window Drawings-App | 30 | 30 | 0% | 2013-04-14 | 2013-05-18 | 2013-04-14 | 2013-05-18 | 55 | No | DUKHENGP1ADWARAP4060, DUKHENGP1ADWARSM4130, DUKHENGP1ADWARAP4070 | DUKHPROGEN00PRDV3450, DUKHPROGEN00PRDV3460, DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3470, DUKHPROGEN00PRDV3440 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4060 | First Floor Plan-App | 30 | 30 | 0% | 2013-03-02 | 2013-04-04 | 2013-03-02 | 2013-04-04 | 62 | No | DUKHENGP1ADWARSM4060 | DUKHENGP1ADWARAP4130, DUKHPROGEN00PRDV3040 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4050 | Ground Floor Plan-App | 30 | 30 | 0% | 2013-02-17 | 2013-03-23 | 2013-02-17 | 2013-03-23 | 92 | No | DUKHENGP1ADWARSM4050 | DUKHPROGEN00PRDV3480, DUKHCONP1AMKARFF3300, DUKHPROGEN00PRDV3110, DUKHPROGEN00PRDV3040, DUKHPROGEN00PRDV3420, DUKHPROGEN00PRDV3320 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4110 | Gypsum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 67 | No | DUKHENGP1ADWARSM4110 | DUKHPROGEN00PRDV3300 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4090 | Porcelain Floor Drawings-App | 30 | 30 | 0% | 2013-03-19 | 2013-04-22 | 2013-03-19 | 2013-04-22 | 57 | No | DUKHENGP1ADWARSM4090 | DUKHPROGEN00PRDV3130 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWARAP4070 | Roof Floor Plan-App | 30 | 30 | 0% | 2013-03-10 | 2013-04-13 | 2013-03-10 | 2013-04-13 | 55 | No | DUKHENGP1ADWARSM4070 | DUKHPROGEN00PRDV3050, DUKHPROGEN00PRDV3140, DUKHENGP1ADWARAP4130 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L20.E05.H20 ELECTRICAL DRAWINGS |  | 100 | 100 | 0% | 2013-02-21 | 2013-06-17 | 2013-02-21 | 2013-06-17 | 70 |  |  |  | 0 | 0
DHBL.K20.L20.E05.H20.G10 SUBMISSION OF DRAWINGS |  | 70 | 70 | 0% | 2013-02-21 | 2013-05-13 | 2013-02-21 | 2013-05-13 | 70 |  |  |  | 0 | 0
DUKHENGP1ADWELSM4190 | Audio Video Intercom System Drawings-Sub | 15 | 15 | 0% | 2013-04-09 | 2013-04-25 | 2013-04-09 | 2013-04-25 | 70 | No | DUKHENGP1ADWELSM4180 | DUKHENGP1ADWELAP4190, DUKHENGP1ADWELSM4200 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWELSM4180 | Central Alarm Monitoring System Drawings-Sub | 15 | 15 | 0% | 2013-03-23 | 2013-04-08 | 2013-03-23 | 2013-04-08 | 70 | No | DUKHENGP1ADWELSM4170 | DUKHENGP1ADWELSM4190, DUKHENGP1ADWELAP4180 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWELSM4160 | Lighting Layout Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 64 | No | DUKHENGP1ADWELSM4150 | DUKHENGP1ADWELAP4160, DUKHENGP1ADWELSM4170 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWELSM4170 | Power Layout Drawings-Sub | 15 | 15 | 0% | 2013-03-05 | 2013-03-21 | 2013-03-05 | 2013-03-21 | 70 | No | DUKHENGP1ADWELSM4150, DUKHENGP1ADWELSM4160 | DUKHENGP1ADWELSM4180, DUKHENGP1ADWELAP4170 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWELSM4150 | Single Line Diagram-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 64 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGP1ADWELAP4150, DUKHENGP1ADWELSM4160, DUKHENGP1ADWELSM4170 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWELSM4200 | Telephone & TV System Drawings-Sub | 15 | 15 | 0% | 2013-04-27 | 2013-05-13 | 2013-04-27 | 2013-05-13 | 70 | No | DUKHENGP1ADWELSM4190 | DUKHENGP1ADWELAP4200 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L20.E05.H20.G20 APPROVAL OF DRAWINGS |  | 85 | 85 | 0% | 2013-03-11 | 2013-06-17 | 2013-03-11 | 2013-06-17 | 70 |  |  |  | 0 | 0
DUKHENGP1ADWELAP4190 | Audio Video Intercom System Drawings-App | 30 | 30 | 0% | 2013-04-27 | 2013-05-30 | 2013-04-27 | 2013-05-30 | 85 | No | DUKHENGP1ADWELSM4190 | DUKHPROGEN00PRDV3270 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWELAP4180 | Central Alarm Monitoring System Drawings-App | 30 | 30 | 0% | 2013-04-09 | 2013-05-13 | 2013-04-09 | 2013-05-13 | 94 | No | DUKHENGP1ADWELSM4180 | DUKHPROGEN00PRDV3360, DUKHPROGEN00PRDV3260, DUKHPROGEN00PRDV3210 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWELAP4160 | Lighting Layout Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 64 | No | DUKHENGP1ADWELSM4160 | DUKHPROGEN00PRDV3180, DUKHPROGEN00PRDV3190 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWELAP4170 | Power Layout Drawings-App | 30 | 30 | 0% | 2013-03-23 | 2013-04-25 | 2013-03-23 | 2013-04-25 | 105 | No | DUKHENGP1ADWELSM4170 | DUKHPROGEN00PRDV3170, DUKHPROGEN00PRDV3200 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWELAP4150 | Single Line Diagram-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 115 | No | DUKHENGP1ADWELSM4150 | DUKHPROGEN00PRDV3170 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWELAP4200 | Telephone & TV System Drawings-App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 70 | No | DUKHENGP1ADWELSM4200 | DUKHPROGEN00PRDV3280, DUKHPROGEN00PRDV3290 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L20.E05.H30 PLUMBING,DRAINAGE,FIREFIGHTING & AC DRAWINGS |  | 75 | 75 | 0% | 2013-02-21 | 2013-05-19 | 2013-02-21 | 2013-05-19 | 130 |  |  |  | 0 | 0
DHBL.K20.L20.E05.H30.G10 SUBMISSION OF DRAWINGS |  | 45 | 45 | 0% | 2013-02-21 | 2013-04-14 | 2013-02-21 | 2013-04-14 | 45 |  |  |  | 0 | 0
DUKHENGP1ADWMESM4240 | AC Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 45 | No | DUKHPROGEN00PQAP1040, DUKHENGP1ADWMESM4230, DUKHPROGEN00PQAP2040 | DUKHENGP1ADWMEAP4240, DUKHENGI1ADWDRSM4250 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWMESM4220 | Drainage Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 45 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP1ADWMEAP4220, DUKHENGP1ADWMESM4230 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWMESM4230 | Fire Fighting Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 45 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040, DUKHENGP1ADWMESM4220 | DUKHENGP1ADWMESM4240, DUKHENGP1ADWMEAP4230 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1ADWMESM4210 | Plumbing Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 53 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP1ADWMEAP4210, DUKHENGP1ADWMEAP4220 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L20.E05.H30.G20 APPROVAL OF DRAWINGS |  | 60 | 60 | 0% | 2013-03-11 | 2013-05-19 | 2013-03-11 | 2013-05-19 | 130 |  |  |  | 0 | 0
DUKHENGP1ADWMEAP4240 | AC Layout & Details Drawings-App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 64 | No | DUKHENGP1ADWMESM4240 | DUKHPROGEN00PRDV3240, DUKHPROGEN00PRDV3340, DUKHPROGEN00PRDV3160, DUKHPROGEN00PRDV3530 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWMEAP4220 | Drainage Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP1ADWMESM4210, DUKHENGP1ADWMESM4220 | DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3330 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWMEAP4230 | Fire Fighting Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 145 | No | DUKHENGP1ADWMESM4230 | DUKHPROGEN00PRDV3370, DUKHPROGEN00PRDV3380 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1ADWMEAP4210 | Plumbing Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP1ADWMESM4210 | DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3680 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L20.E05.H40 INFRA DRAWINGS |  | 127 | 127 | 0% | 2013-04-15 | 2013-09-12 | 2013-04-15 | 2013-09-12 | 272 |  |  |  | 0 | 0
DHBL.K20.L20.E05.H40.G10 SUBMISSION OF DRAWINGS |  | 82 | 82 | 0% | 2013-04-15 | 2013-07-18 | 2013-04-15 | 2013-07-18 | 287 |  |  |  | 0 | 0
DUKHENGI1ADWBWSM4330 | Boundary Wall Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI1ADWSLSM4320 | DUKHENGI1ADWBWAP4330, DUKHENGI1ADWPSSM4340 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWDRSM4250 | Drainage Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHMOBI1APS00001400, DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040, DUKHENGP1ADWMESM4240 | DUKHENGI1ADWWSSM4270, DUKHENGI1ADWDRAP4250 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWELSM4280 | Electrical Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI1ADWFFSM4260, DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGI1ADWELAP4280, DUKHENGI1ADWSTSM4290 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWFFSM4260 | Fire Fighting Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI1ADWWSSM4270 | DUKHENGI1ADWFFAP4260, DUKHENGI1ADWELSM4280 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWGZSM4380 | Gazebo Plan & Details-Sub | 15 | 15 | 0% | 2013-07-02 | 2013-07-18 | 2013-07-02 | 2013-07-18 | 75 | No | DUKHENGI1ADWTRSM4370 | DUKHENGI1ADWGZAP4380 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWGHSM4390 | Guard House Plan & Details-Sub | 15 | 15 | 0% | 2013-07-02 | 2013-07-18 | 2013-07-02 | 2013-07-18 | 287 | No | DUKHENGI1ADWTRSM4370 | DUKHENGI1ADWGHAP4390 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWIRSM4310 | Irrigation Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI1ADWTCSM4300, DUKHENGI1ADWWSSM4270 | DUKHENGI1ADWSLSM4320, DUKHENGI1ADWIRAP4310 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWIWSM4360 | Irrigation Water Tank & Pump Room Details- Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI1ADWRWSM4350 | DUKHENGI1ADWTRSM4370, DUKHENGI1ADWIWAP4360 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWPSSM4340 | Parking Shed Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI1ADWBWSM4330 | DUKHENGI1ADWPSAP4340, DUKHENGI1ADWRWSM4350 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWRWSM4350 | Road Layout & Details-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI1ADWPSSM4340 | DUKHENGI1ADWRWAP4350, DUKHENGI1ADWIWSM4360 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWSLSM4320 | Soft & HardLandscaping Layout & Detail-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI1ADWIRSM4310 | DUKHENGI1ADWBWSM4330, DUKHENGI1ADWSLAP4320 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWSTSM4290 | Street Lighting Layout & details -Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI1ADWELSM4280 | DUKHENGI1ADWSTAP4290, DUKHENGI1ADWTCSM4300 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWTCSM4300 | Telecommunication Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI1ADWSTSM4290 | DUKHENGI1ADWTCAP4300, DUKHENGI1ADWIRSM4310 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWTRSM4370 | Telephone Room Details-Sub | 15 | 15 | 0% | 2013-06-15 | 2013-07-01 | 2013-06-15 | 2013-07-01 | 60 | No | DUKHENGI1ADWIWSM4360 | DUKHENGI1ADWGZSM4380, DUKHENGI1ADWGHSM4390, DUKHENGI1ADWTRAP4370 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1ADWWSSM4270 | Water Supply Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI1ADWDRSM4250 | DUKHENGI1ADWFFSM4260, DUKHENGI1ADWWSAP4270, DUKHENGI1ADWIRSM4310 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L20.E05.H40.G20 APPROVAL OF DRAWINGS |  | 112 | 112 | 0% | 2013-05-02 | 2013-09-12 | 2013-05-02 | 2013-09-12 | 272 |  |  |  | 0 | 0
DUKHENGI1ADWBWAP4330 | Boundary Wall Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 85 | No | DUKHENGI1ADWBWSM4330 | DUKHCONI1AZ1RWGL6000, DUKHPROGEN00PRDV3820, DUKHCONI1AZ1BWGL5315 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWDRAP4250 | Drainage Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 84 | No | DUKHENGI1ADWDRSM4250 | DUKHCONI1AZ1SAGL5135, DUKHPROGEN00PRDV3590, DUKHCONI1AZ1DRGL5115 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWELAP4280 | Electrical Line Layout & Details-App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 60 | No | DUKHENGI1ADWELSM4280 | DUKHCONI1AZ1ELGL5215, DUKHPROGEN00PRDV3350, DUKHPROGEN00PRDV3250, DUKHENGI1ADWSTAP4290 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWFFAP4260 | Fire Fighting Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 45 | No | DUKHENGI1ADWFFSM4260 | DUKHCONI1AZ1FFGL5185, DUKHPROGEN00PRDV3690, DUKHPROGEN00PRDV3650, DUKHPROGEN00PRDV3540 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWGZAP4380 | Gazebo Plan & Details-App | 30 | 30 | 0% | 2013-08-06 | 2013-09-12 | 2013-08-06 | 2013-09-12 | 60 | No | DUKHENGI1ADWGZSM4380, DUKHENGI1ADWTRAP4370 | DUKHPROGEN00PRDV3780, DUKHCONI1ASBGZGL7900 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWGHAP4390 | Guard House Plan & Details-App | 30 | 30 | 0% | 2013-08-06 | 2013-09-12 | 2013-08-06 | 2013-09-12 | 272 | No | DUKHENGI1ADWGHSM4390, DUKHENGI1ADWTRAP4370 | DUKHCONI1ASBGHGL7800 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWIRAP4310 | Irrigation Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 91 | No | DUKHENGI1ADWIRSM4310 | DUKHPROGEN00PRDV3670, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3840, DUKHPROGEN00PRDV3860, DUKHPROGEN00PRDV3870, DUKHCONI1AZ1IRGL5265, DUKHPROGEN00PRDV3830, DUKHPROGEN00PRDV3760 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWIWAP4360 | Irrigation Water Tank & Pump Room Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 49 | No | DUKHENGI1ADWIWSM4360 | DUKHPROGEN00PRDV3590, DUKHPROGEN00PRDV3660, DUKHCONI1ASBIWGL7400 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWPSAP4340 | Parking Shed Layout & Details Drawings-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 150 | No | DUKHENGI1ADWPSSM4340 | DUKHPROGEN00PRDV3730, DUKHCONI1AZ1PSGL7000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWRWAP4350 | Road Layout & Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 149 | No | DUKHENGI1ADWRWSM4350 | DUKHPROGEN00PRDV3720, DUKHPROGEN00PRDV3750, DUKHPROGEN00PRDV3700 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWSLAP4320 | Soft & HardLandscaping Layout & Detail-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 67 | No | DUKHENGI1ADWSLSM4320 | DUKHCONI1AZ1HDGL7020, DUKHPROGEN00PRDV3790, DUKHCONI1AZ1SLGL7200 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWSTAP4290 | Street Lighting Layout & details -App | 30 | 30 | 0% | 2013-06-24 | 2013-07-28 | 2013-06-24 | 2013-07-28 | 60 | No | DUKHENGI1ADWSTSM4290, DUKHENGI1ADWELAP4280 | DUKHENGI1ADWTCAP4300, DUKHCONI1AZ1STGL5235, DUKHPROGEN00PRDV3350, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWTCAP4300 | Telecommunication Line Layout & Details-App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 60 | No | DUKHENGI1ADWTCSM4300, DUKHENGI1ADWSTAP4290 | DUKHCONI1AZ1TCGL5295, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWTRAP4370 | Telephone Room Details-App | 30 | 30 | 0% | 2013-07-02 | 2013-08-05 | 2013-07-02 | 2013-08-05 | 60 | No | DUKHENGI1ADWTRSM4370 | DUKHENGI1ADWGHAP4390, DUKHENGI1ADWGZAP4380, DUKHCONI1ASBTRGL7600 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1ADWWSAP4270 | Water Supply Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 86 | No | DUKHENGI1ADWWSSM4270 | DUKHPROGEN00PRDV3590, DUKHCONI1AZ1WSGL5155 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L30 PACKAGE-1B |  | 224 | 224 | 0% | 2012-12-12 | 2013-09-04 | 2012-12-12 | 2013-09-04 | 279 |  |  |  | 0 | 0
DHBL.K20.L30.E05 SHOP DRAWINGS SUBMISSION & APPROVAL |  | 224 | 224 | 0% | 2012-12-12 | 2013-09-04 | 2012-12-12 | 2013-09-04 | 279 |  |  |  | 0 | 0
DHBL.K20.L30.E05.H05 STRUCTURAL DRAWINGS |  | 80 | 80 | 0% | 2012-12-12 | 2013-03-17 | 2012-12-12 | 2013-03-17 | 167 |  |  |  | 0 | 0
DHBL.K20.L30.E05.H05.G10 SUBMISSION OF DRAWINGS |  | 50 | 50 | 0% | 2012-12-12 | 2013-02-09 | 2012-12-12 | 2013-02-09 | 42 |  |  |  | 0 | 0
DUKHENGP1BDWSTSM4420 | Column Drawings-Sub | 15 | 15 | 0% | 2012-12-25 | 2013-01-10 | 2012-12-25 | 2013-01-10 | 42 | No | DUKHENGP1BDWSTSM4410 | DUKHENGP1BDWSTAP4420, DUKHENGP1BDWSTSM4430 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWSTSM4440 | FF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2013-01-23 | 2013-02-09 | 2013-01-23 | 2013-02-09 | 42 | No | DUKHENGP1BDWSTSM4430 | DUKHENGP1BDWARSM4450, DUKHENGP1BDWSTAP4440 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWSTSM4400 | Footing Drawings-Sub | 15 | 15 | 0% | 2012-12-12 | 2012-12-30 | 2012-12-12 | 2012-12-30 | 42 | No | DUKHMOBP010000004020 | DUKHENGP1BDWSTAP4400, DUKHENGP1BDWSTSM4410 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWSTSM4430 | GF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2013-01-06 | 2013-01-22 | 2013-01-06 | 2013-01-22 | 42 | No | DUKHENGP1BDWSTSM4420 | DUKHENGP1BDWSTAP4430, DUKHENGP1BDWSTSM4440 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWSTSM4410 | Grade Beam & Slab Drawings-Sub | 15 | 15 | 0% | 2012-12-19 | 2013-01-05 | 2012-12-19 | 2013-01-05 | 42 | No | DUKHENGP1BDWSTSM4400 | DUKHENGP1BDWSTSM4420, DUKHENGP1BDWSTAP4410 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L30.E05.H05.G20 APPROVAL OF DRAWINGS |  | 65 | 65 | 0% | 2012-12-31 | 2013-03-17 | 2012-12-31 | 2013-03-17 | 167 |  |  |  | 0 | 0
DUKHENGP1BDWSTAP4420 | Column Drawings-App | 30 | 30 | 0% | 2013-01-12 | 2013-02-16 | 2013-01-12 | 2013-02-16 | 156 | No | DUKHENGP1BDWSTSM4420 | DUKHCONP1BZ1STGF2000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWSTAP4440 | FF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-02-10 | 2013-03-17 | 2013-02-10 | 2013-03-17 | 167 | No | DUKHENGP1BDWSTSM4440 | DUKHCONP1BZ1STFF2020 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWSTAP4400 | Footing Drawings-App | 30 | 30 | 0% | 2012-12-31 | 2013-02-03 | 2012-12-31 | 2013-02-03 | 58 | No | DUKHENGP1BDWSTSM4400 | DUKHCONP1BZ1STUG1000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWSTAP4430 | GF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-01-23 | 2013-02-27 | 2013-01-23 | 2013-02-27 | 166 | No | DUKHENGP1BDWSTSM4430 | DUKHCONP1BZ1STGF2010 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWSTAP4410 | Grade Beam & Slab Drawings-App | 30 | 30 | 0% | 2013-01-06 | 2013-02-09 | 2013-01-06 | 2013-02-09 | 124 | No | DUKHENGP1BDWSTSM4410 | DUKHCONP1BZ1STUG1045, DUKHCONP1BZ1STUG1040 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L30.E05.H10 ARCHITECTURAL DRAWINGS |  | 92 | 92 | 0% | 2013-02-10 | 2013-05-28 | 2013-02-10 | 2013-05-28 | 83 |  |  |  | 0 | 0
DHBL.K20.L30.E05.H10.G10 SUBMISSION OF DRAWINGS |  | 62 | 62 | 0% | 2013-02-10 | 2013-04-23 | 2013-02-10 | 2013-04-23 | 83 |  |  |  | 0 | 0
DUKHENGP1BDWARSM4490 | Aluminum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 82 | No | DUKHPROGEN00PQAP1050, DUKHPROGEN00PQAP2050 | DUKHENGP1BDWARAP4490 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4540 | Carpentry & Joinery Drawings-Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 83 | No | DUKHENGP1BDWARSM4450, DUKHPROGEN00PQAP2150, DUKHPROGEN00PQAP1150 | DUKHENGP1BDWARAP4540 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4500 | Ceramic Flooring & Wall Drawings-Sub | 15 | 15 | 0% | 2013-03-09 | 2013-03-25 | 2013-03-09 | 2013-03-25 | 42 | No | DUKHENGP1BDWARSM4460, DUKHENGP1BDWARSM4450, DUKHENGP1BDWARSM4470 | DUKHENGP1BDWARAP4500, DUKHENGP1BDWARSM4510 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4520 | Cobble & Slate Flooring Drawings-Sub | 15 | 15 | 0% | 2013-03-09 | 2013-03-25 | 2013-03-09 | 2013-03-25 | 82 | No | DUKHENGP1BDWARSM4510 | DUKHENGP1BDWARAP4520 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4530 | Doors & window Drawings-Sub | 15 | 15 | 0% | 2013-03-20 | 2013-04-06 | 2013-03-20 | 2013-04-06 | 61 | No | DUKHPROGEN00PQAP1080, DUKHENGP1BDWARSM4450, DUKHPROGEN00PQAP2080 | DUKHENGP1BDWARAP4530 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4460 | First Floor Plan-Sub | 15 | 15 | 0% | 2013-02-19 | 2013-03-07 | 2013-02-19 | 2013-03-07 | 42 | No | DUKHENGP1BDWARSM4450 | DUKHENGP1BDWARSM4500, DUKHENGP1BDWARAP4460, DUKHENGP1BDWARSM4470 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4450 | Ground Floor Plan-Sub | 15 | 15 | 0% | 2013-02-10 | 2013-02-27 | 2013-02-10 | 2013-02-27 | 42 | No | DUKHENGP1BDWSTSM4440 | DUKHENGP1BDWARAP4450, DUKHENGP1BDWARSM4530, DUKHENGP1BDWARSM4500, DUKHENGP1BDWARSM4460, DUKHENGP1BDWARSM4540 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4480 | Gypsum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 67 | No | DUKHPROGEN00PQAP1050, DUKHPROGEN00PQAP2050 | DUKHENGP1BDWARAP4480 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4510 | Porcelain Floor Drawings-Sub | 15 | 15 | 0% | 2013-03-09 | 2013-03-25 | 2013-03-09 | 2013-03-25 | 51 | No | DUKHENGP1BDWARSM4500 | DUKHENGP1BDWARSM4520, DUKHENGP1BDWARAP4510 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWARSM4470 | Roof Floor Plan-Sub | 15 | 15 | 0% | 2013-02-27 | 2013-03-16 | 2013-02-27 | 2013-03-16 | 47 | No | DUKHENGP1BDWARSM4460 | DUKHENGP1BDWARAP4470, DUKHENGP1BDWARSM4500 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L30.E05.H10.G20 APPROVAL OF DRAWINGS |  | 77 | 77 | 0% | 2013-02-28 | 2013-05-28 | 2013-02-28 | 2013-05-28 | 83 |  |  |  | 0 | 0
DUKHENGP1BDWARAP4490 | Aluminum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 82 | No | DUKHENGP1BDWARSM4490 | DUKHPROGEN00PRDV3310 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4540 | Carpentry & Joinery Drawings-App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 83 | No | DUKHENGP1BDWARSM4540 | DUKHPROGEN00PRDV3570, DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3550 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4500 | Ceramic Flooring & Wall Drawings-App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 42 | No | DUKHENGP1BDWARSM4500 | DUKHPROGEN00PRDV3120 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4520 | Cobble & Slate Flooring Drawings-App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 82 | No | DUKHENGP1BDWARSM4520 | DUKHPROGEN00PRDV3090, DUKHPROGEN00PRDV3100 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4530 | Doors & Window Drawings-App | 30 | 30 | 0% | 2013-04-21 | 2013-05-25 | 2013-04-21 | 2013-05-25 | 49 | No | DUKHENGP1BDWARAP4460, DUKHENGP1BDWARAP4470, DUKHENGP1BDWARSM4530 | DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3470, DUKHPROGEN00PRDV3460, DUKHPROGEN00PRDV3440, DUKHPROGEN00PRDV3450 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4460 | First Floor Plan-App | 30 | 30 | 0% | 2013-03-09 | 2013-04-11 | 2013-03-09 | 2013-04-11 | 56 | No | DUKHENGP1BDWARSM4460 | DUKHPROGEN00PRDV3040, DUKHENGP1BDWARAP4530 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4450 | Ground Floor Plan-App | 30 | 30 | 0% | 2013-02-28 | 2013-04-03 | 2013-02-28 | 2013-04-03 | 82 | No | DUKHENGP1BDWARSM4450 | DUKHCONP1AMKARFF3300, DUKHPROGEN00PRDV3480, DUKHPROGEN00PRDV3040, DUKHPROGEN00PRDV3420, DUKHPROGEN00PRDV3320, DUKHPROGEN00PRDV3110 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4480 | Gypsum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 67 | No | DUKHENGP1BDWARSM4480 | DUKHPROGEN00PRDV3300 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4510 | Porcelain Floor Drawings-App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 51 | No | DUKHENGP1BDWARSM4510 | DUKHPROGEN00PRDV3130 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWARAP4470 | Roof Floor Plan-App | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 49 | No | DUKHENGP1BDWARSM4470 | DUKHPROGEN00PRDV3140, DUKHENGP1BDWARAP4530, DUKHPROGEN00PRDV3050 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L30.E05.H20 ELECTRICAL DRAWINGS |  | 101 | 101 | 0% | 2013-02-21 | 2013-06-18 | 2013-02-21 | 2013-06-18 | 163 |  |  |  | 0 | 0
DHBL.K20.L30.E05.H20.G10 SUBMISSION OF DRAWINGS |  | 71 | 71 | 0% | 2013-02-21 | 2013-05-14 | 2013-02-21 | 2013-05-14 | 69 |  |  |  | 0 | 0
DUKHENGP1BDWELSM4590 | Audio Video Intercom System Drawings-Sub | 15 | 15 | 0% | 2013-04-10 | 2013-04-27 | 2013-04-10 | 2013-04-27 | 69 | No | DUKHENGP1BDWELSM4580 | DUKHENGP1BDWELAP4590, DUKHENGP1BDWELSM4600 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWELSM4580 | Central Alarm Monitoring System Drawings-Sub | 15 | 15 | 0% | 2013-03-24 | 2013-04-09 | 2013-03-24 | 2013-04-09 | 69 | No | DUKHENGP1BDWELSM4570 | DUKHENGP1BDWELAP4580, DUKHENGP1BDWELSM4590 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWELSM4560 | Lighting Layout Drawings-Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 69 | No | DUKHENGP1BDWELSM4550 | DUKHENGP1BDWELSM4570, DUKHENGP1BDWELAP4560 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWELSM4570 | Power Layout Drawings-Sub | 15 | 15 | 0% | 2013-03-16 | 2013-04-01 | 2013-03-16 | 2013-04-01 | 69 | No | DUKHENGP1BDWELSM4550, DUKHENGP1BDWELSM4560 | DUKHENGP1BDWELAP4570, DUKHENGP1BDWELSM4580 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWELSM4550 | Single Line Diagram-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 69 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP1BDWELSM4560, DUKHENGP1BDWELSM4570, DUKHENGP1BDWELAP4550 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWELSM4600 | Telephone & TV System Drawings-Sub | 15 | 15 | 0% | 2013-04-28 | 2013-05-14 | 2013-04-28 | 2013-05-14 | 69 | No | DUKHENGP1BDWELSM4590 | DUKHENGP1BDWELAP4600 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L30.E05.H20.G20 APPROVAL OF DRAWINGS |  | 86 | 86 | 0% | 2013-03-11 | 2013-06-18 | 2013-03-11 | 2013-06-18 | 163 |  |  |  | 0 | 0
DUKHENGP1BDWELAP4590 | Audio Video Intercom System Drawings-App | 30 | 30 | 0% | 2013-04-28 | 2013-06-01 | 2013-04-28 | 2013-06-01 | 84 | No | DUKHENGP1BDWELSM4590 | DUKHPROGEN00PRDV3270 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWELAP4580 | Central Alarm Monitoring System Drawings-App | 30 | 30 | 0% | 2013-04-10 | 2013-05-14 | 2013-04-10 | 2013-05-14 | 193 | No | DUKHENGP1BDWELSM4580 | DUKHPROGEN00PRDV3260, DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3360 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWELAP4560 | Lighting Layout Drawings-App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 147 | No | DUKHENGP1BDWELSM4560 | DUKHPROGEN00PRDV3190, DUKHPROGEN00PRDV3180 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWELAP4570 | Power Layout Drawings-App | 30 | 30 | 0% | 2013-04-02 | 2013-05-06 | 2013-04-02 | 2013-05-06 | 96 | No | DUKHENGP1BDWELSM4570 | DUKHPROGEN00PRDV3200, DUKHPROGEN00PRDV3170 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWELAP4550 | Single Line Diagram-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 115 | No | DUKHENGP1BDWELSM4550 | DUKHPROGEN00PRDV3170 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWELAP4600 | Telephone & TV System Drawings-App | 30 | 30 | 0% | 2013-05-15 | 2013-06-18 | 2013-05-15 | 2013-06-18 | 69 | No | DUKHENGP1BDWELSM4600 | DUKHPROGEN00PRDV3280, DUKHPROGEN00PRDV3290 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L30.E05.H30 PLUMBING,DRAINAGE,FIREFIGHTING & AC DRAWINGS |  | 75 | 75 | 0% | 2013-02-21 | 2013-05-19 | 2013-02-21 | 2013-05-19 | 130 |  |  |  | 0 | 0
DHBL.K20.L30.E05.H30.G10 SUBMISSION OF DRAWINGS |  | 45 | 45 | 0% | 2013-02-21 | 2013-04-14 | 2013-02-21 | 2013-04-14 | 45 |  |  |  | 0 | 0
DUKHENGP1BDWMESM4640 | AC Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 45 | No | DUKHENGP1BDWMESM4630, DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGI1BDWDRSM4650, DUKHENGP1BDWMEAP4640 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWMESM4620 | Drainage Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 45 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP1BDWMEAP4620, DUKHENGP1BDWMESM4630 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWMESM4630 | Fire Fighting Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 45 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040, DUKHENGP1BDWMESM4620 | DUKHENGP1BDWMESM4640, DUKHENGP1BDWMEAP4630 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP1BDWMESM4610 | Plumbing Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 53 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGP1BDWMEAP4620, DUKHENGP1BDWMEAP4610 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L30.E05.H30.G20 APPROVAL OF DRAWINGS |  | 60 | 60 | 0% | 2013-03-11 | 2013-05-19 | 2013-03-11 | 2013-05-19 | 130 |  |  |  | 0 | 0
DUKHENGP1BDWMEAP4640 | AC Layout & Details Drawings-App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 64 | No | DUKHENGP1BDWMESM4640 | DUKHPROGEN00PRDV3160, DUKHPROGEN00PRDV3240, DUKHPROGEN00PRDV3530, DUKHPROGEN00PRDV3340 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWMEAP4620 | Drainage Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP1BDWMESM4610, DUKHENGP1BDWMESM4620 | DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3680 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWMEAP4630 | Fire Fighting Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 145 | No | DUKHENGP1BDWMESM4630 | DUKHPROGEN00PRDV3370, DUKHPROGEN00PRDV3380 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP1BDWMEAP4610 | Plumbing Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP1BDWMESM4610 | DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3770 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L30.E05.H40 INFRA DRAWINGS |  | 120 | 120 | 0% | 2013-04-15 | 2013-09-04 | 2013-04-15 | 2013-09-04 | 279 |  |  |  | 0 | 0
DHBL.K20.L30.E05.H40.G10 SUBMISSION OF DRAWINGS |  | 67 | 67 | 0% | 2013-04-15 | 2013-07-01 | 2013-04-15 | 2013-07-01 | 302 |  |  |  | 0 | 0
DUKHENGI1BDWBWSM4730 | Boundary Wall Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI1BDWSLSM4720 | DUKHENGI1BDWBWAP4730, DUKHENGI1BDWPSSM4740 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWDRSM4650 | Drainage Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGP1BDWMESM4640, DUKHMOBI1BPS00001400, DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGI1BDWWSSM4670, DUKHENGI1BDWDRAP4650 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWELSM4680 | Electrical Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHPROGEN00PQAP1040, DUKHENGI1BDWFFSM4660, DUKHPROGEN00PQAP2040 | DUKHENGI1BDWSTSM4690, DUKHENGI1BDWELAP4680 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWFFSM4660 | Fire Fighting Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI1BDWWSSM4670 | DUKHENGI1BDWFFAP4660, DUKHENGI1BDWELSM4680 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWGZSM4780 | Gazebo Plan & Details-Sub | 15 | 15 | 0% | 2013-06-15 | 2013-07-01 | 2013-06-15 | 2013-07-01 | 90 | No | DUKHENGI1BDWTRSM4770 | DUKHENGI1BDWGZAP4780 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWGHSM4790 | Guard House Plan & Details-Sub | 15 | 15 | 0% | 2013-06-15 | 2013-07-01 | 2013-06-15 | 2013-07-01 | 302 | No | DUKHENGI1BDWTRSM4770 | DUKHENGI1BDWGHAP4790 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWIRSM4710 | Irrigation Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI1BDWTCSM4700, DUKHENGI1BDWWSSM4670 | DUKHENGI1BDWSLSM4720, DUKHENGI1BDWIRAP4710 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWIWSM4760 | Irrigation Water Tank & Pump Room Details- Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI1BDWRWSM4750 | DUKHENGI1BDWIWAP4760, DUKHENGI1BDWTRSM4770 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWPSSM4740 | Parking Shed Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI1BDWBWSM4730 | DUKHENGI1BDWPSAP4740, DUKHENGI1BDWRWSM4750 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWRWSM4750 | Road Layout & Details-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI1BDWPSSM4740 | DUKHENGI1BDWIWSM4760, DUKHENGI1BDWRWAP4750 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWSLSM4720 | Soft & HardLandscaping Layout & Detail-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI1BDWIRSM4710 | DUKHENGI1BDWBWSM4730, DUKHENGI1BDWSLAP4720 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWSTSM4690 | Street Lighting Layout & details -Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI1BDWELSM4680 | DUKHENGI1BDWSTAP4690, DUKHENGI1BDWTCSM4700 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWTCSM4700 | Telecommunication Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI1BDWSTSM4690 | DUKHENGI1BDWIRSM4710, DUKHENGI1BDWTCAP4700 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWTRSM4770 | Telephone Room Details-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 75 | No | DUKHENGI1BDWIWSM4760 | DUKHENGI1BDWGZSM4780, DUKHENGI1BDWTRAP4770, DUKHENGI1BDWGHSM4790 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI1BDWWSSM4670 | Water Supply Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI1BDWDRSM4650 | DUKHENGI1BDWWSAP4670, DUKHENGI1BDWFFSM4660, DUKHENGI1BDWIRSM4710 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L30.E05.H40.G20 APPROVAL OF DRAWINGS |  | 105 | 105 | 0% | 2013-05-02 | 2013-09-04 | 2013-05-02 | 2013-09-04 | 279 |  |  |  | 0 | 0
DUKHENGI1BDWBWAP4730 | Boundary Wall Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 85 | No | DUKHENGI1BDWBWSM4730 | DUKHPROGEN00PRDV3820, DUKHCONI1BZ1RWGL6000, DUKHCONI1BZ1BWGL5315 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWDRAP4650 | Drainage Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 86 | No | DUKHENGI1BDWDRSM4650 | DUKHPROGEN00PRDV3590, DUKHCONI1BZ1DRGL5115, DUKHCONI1BZ1SAGL5135 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWELAP4680 | Electrical Line Layout & Details-App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 60 | No | DUKHENGI1BDWELSM4680 | DUKHCONI1BZ1ELGL5215, DUKHPROGEN00PRDV3350, DUKHPROGEN00PRDV3250, DUKHENGI1BDWSTAP4690 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWFFAP4660 | Fire Fighting Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 45 | No | DUKHENGI1BDWFFSM4660 | DUKHCONI1BZ1FFGL5185, DUKHPROGEN00PRDV3650, DUKHPROGEN00PRDV3540, DUKHPROGEN00PRDV3690 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWGZAP4780 | Gazebo Plan & Details-App | 30 | 30 | 0% | 2013-07-20 | 2013-08-26 | 2013-07-20 | 2013-08-26 | 75 | No | DUKHENGI1BDWGZSM4780, DUKHENGI1BDWTRAP4770 | DUKHCONI1BSBGZGL7900, DUKHPROGEN00PRDV3780 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWGHAP4790 | Guard House Plan & Details-App | 30 | 30 | 0% | 2013-07-20 | 2013-08-26 | 2013-07-20 | 2013-08-26 | 287 | No | DUKHENGI1BDWTRAP4770, DUKHENGI1BDWGHSM4790 | DUKHCONI1BSBGHGL7800 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWIRAP4710 | Irrigation Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 91 | No | DUKHENGI1BDWIRSM4710 | DUKHPROGEN00PRDV3670, DUKHPROGEN00PRDV3870, DUKHPROGEN00PRDV3860, DUKHPROGEN00PRDV3830, DUKHCONI1BZ1IRGL5265, DUKHPROGEN00PRDV3760, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3840 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWIWAP4760 | Irrigation Water Tank & Pump Room Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 49 | No | DUKHENGI1BDWIWSM4760 | DUKHPROGEN00PRDV3590, DUKHPROGEN00PRDV3660, DUKHCONI1BSBIWGL7400 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWPSAP4740 | Parking Shed Layout & Details Drawings-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 150 | No | DUKHENGI1BDWPSSM4740 | DUKHPROGEN00PRDV3730, DUKHCONI1BZ1PSGL7000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWRWAP4750 | Road Layout & Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 149 | No | DUKHENGI1BDWRWSM4750 | DUKHPROGEN00PRDV3700, DUKHPROGEN00PRDV3750, DUKHPROGEN00PRDV3720 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWSLAP4720 | Soft & HardLandscaping Layout & Detail-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 67 | No | DUKHENGI1BDWSLSM4720 | DUKHPROGEN00PRDV3790, DUKHCONI1BZ1HDGL7020, DUKHCONI1BZ1SLGL7200 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWSTAP4690 | Street Lighting Layout & details -App | 30 | 30 | 0% | 2013-06-24 | 2013-07-28 | 2013-06-24 | 2013-07-28 | 60 | No | DUKHENGI1BDWSTSM4690, DUKHENGI1BDWELAP4680 | DUKHENGI1BDWTCAP4700, DUKHPROGEN00PRDV3350, DUKHCONI1BZ1STGL5235, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWTCAP4700 | Telecommunication Line Layout & Details-App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 60 | No | DUKHENGI1BDWTCSM4700, DUKHENGI1BDWSTAP4690 | DUKHCONI1BZ1TCGL5295, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWTRAP4770 | Telephone Room Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 75 | No | DUKHENGI1BDWTRSM4770 | DUKHENGI1BDWGZAP4780, DUKHCONI1BSBTRGL7600, DUKHENGI1BDWGHAP4790 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI1BDWWSAP4670 | Water Supply Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 86 | No | DUKHENGI1BDWWSSM4670 | DUKHCONI1BZ1WSGL5155, DUKHPROGEN00PRDV3590 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L40 PACKAGE-2A |  | 215 | 215 | 0% | 2012-11-26 | 2013-08-05 | 2012-11-26 | 2013-08-05 | 135 |  |  |  | 0 | 0
DHBL.K20.L40.E05 SHOP DRAWINGS SUBMISSION & APPROVAL |  | 215 | 215 | 0% | 2012-11-26 | 2013-08-05 | 2012-11-26 | 2013-08-05 | 135 |  |  |  | 0 | 0
DHBL.K20.L40.E05.H05 STRUCTURAL DRAWINGS |  | 65 | 65 | 0% | 2012-11-26 | 2013-02-10 | 2012-11-26 | 2013-02-10 | 125 |  |  |  | 0 | 0
DHBL.K20.L40.E05.H05.G10 SUBMISSION OF DRAWINGS |  | 35 | 35 | 0% | 2012-11-26 | 2013-01-06 | 2012-11-26 | 2013-01-06 | 78 |  |  |  | 0 | 0
DUKHENGP2ADWSTSM4820 | Column Drawings-Sub | 15 | 15 | 0% | 2012-12-08 | 2012-12-25 | 2012-12-08 | 2012-12-25 | 78 | No | DUKHENGP2ADWSTSM4810 | DUKHENGP2ADWSTSM4830, DUKHENGP2ADWSTAP4820 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWSTSM4800 | Footing Drawings-Sub | 10 | 10 | 0% | 2012-11-26 | 2012-12-06 | 2012-11-26 | 2012-12-06 | 54 | No | DUKHMOBP020000004020 | DUKHENGP2ADWSTSM4810, DUKHENGP2ADWSTAP4800 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWSTSM4830 | GF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2012-12-20 | 2013-01-06 | 2012-12-20 | 2013-01-06 | 78 | No | DUKHENGP2ADWSTSM4820 | DUKHENGP2ADWSTAP4830, DUKHENGP2ADWARSM4850 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWSTSM4810 | Grade Beam & Slab Drawings-Sub | 15 | 15 | 0% | 2012-12-02 | 2012-12-19 | 2012-12-02 | 2012-12-19 | 78 | No | DUKHENGP2ADWSTSM4800 | DUKHENGP2ADWSTAP4810, DUKHENGP2ADWSTSM4820 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L40.E05.H05.G20 APPROVAL OF DRAWINGS |  | 55 | 55 | 0% | 2012-12-08 | 2013-02-10 | 2012-12-08 | 2013-02-10 | 125 |  |  |  | 0 | 0
DUKHENGP2ADWSTAP4820 | Column Drawings-App | 30 | 30 | 0% | 2012-12-26 | 2013-01-29 | 2012-12-26 | 2013-01-29 | 119 | No | DUKHENGP2ADWSTSM4820 | DUKHCONP2AZ1STGF2000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWSTAP4800 | Footing Drawings-App | 25 | 25 | 0% | 2012-12-08 | 2013-01-06 | 2012-12-08 | 2013-01-06 | 54 | No | DUKHENGP2ADWSTSM4800 | DUKHCONP2AZ1STUG1015 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWSTAP4830 | GF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-01-07 | 2013-02-10 | 2013-01-07 | 2013-02-10 | 125 | No | DUKHENGP2ADWSTSM4830 | DUKHCONP2AZ1STGF2010 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWSTAP4810 | Grade Beam & Slab Drawings-App | 30 | 30 | 0% | 2012-12-20 | 2013-01-23 | 2012-12-20 | 2013-01-23 | 85 | No | DUKHENGP2ADWSTSM4810 | DUKHCONP2AZ1STUG1040, DUKHCONP2AZ1STUG1045 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L40.E05.H10 ARCHITECTURAL DRAWINGS |  | 121 | 121 | 0% | 2013-01-07 | 2013-05-28 | 2013-01-07 | 2013-05-28 | 83 |  |  |  | 0 | 0
DHBL.K20.L40.E05.H10.G10 SUBMISSION OF DRAWINGS |  | 91 | 91 | 0% | 2013-01-07 | 2013-04-23 | 2013-01-07 | 2013-04-23 | 83 |  |  |  | 0 | 0
DUKHENGP2ADWARSM4940 | Carpentry & Joinery Drawings-Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 83 | No | DUKHPROGEN00PQAP1150, DUKHPROGEN00PQAP2150, DUKHENGP2ADWARSM4850 | DUKHENGP2ADWARAP4940 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWARSM4880 | Ceramic Flooring & Wall Drawings-Sub | 15 | 15 | 0% | 2013-01-24 | 2013-02-10 | 2013-01-24 | 2013-02-10 | 78 | No | DUKHENGP2ADWARSM4850, DUKHENGP2ADWARSM4870 | DUKHENGP2ADWARSM4890, DUKHENGP2ADWARAP4880 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWARSM4900 | Cobble & Slate Flooring Drawings-Sub | 15 | 15 | 0% | 2013-01-24 | 2013-02-10 | 2013-01-24 | 2013-02-10 | 118 | No | DUKHENGP2ADWARSM4890 | DUKHENGP2ADWARAP4900 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWARSM4930 | Doors & window Drawings-Sub | 15 | 15 | 0% | 2013-03-20 | 2013-04-06 | 2013-03-20 | 2013-04-06 | 61 | No | DUKHENGP2ADWARSM4850, DUKHPROGEN00PQAP2080, DUKHPROGEN00PQAP1080 | DUKHENGP2ADWARAP4930 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWARSM4850 | Ground Floor Plan-Sub | 15 | 15 | 0% | 2013-01-07 | 2013-01-23 | 2013-01-07 | 2013-01-23 | 78 | No | DUKHENGP2ADWSTSM4830 | DUKHENGP2ADWARAP4850, DUKHENGP2ADWARSM4930, DUKHENGP2ADWARSM4880, DUKHENGP2ADWARSM4870, DUKHENGP2ADWARSM4940 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWARSM4910 | Gypsum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 67 | No | DUKHPROGEN00PQAP2050, DUKHPROGEN00PQAP1050 | DUKHENGP2ADWARAP4910 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWARSM4890 | Porcelain Floor Drawings-Sub | 15 | 15 | 0% | 2013-01-24 | 2013-02-10 | 2013-01-24 | 2013-02-10 | 87 | No | DUKHENGP2ADWARSM4880 | DUKHENGP2ADWARSM4900, DUKHENGP2ADWARAP4890 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWARSM4870 | Roof Floor Plan-Sub | 15 | 15 | 0% | 2013-01-15 | 2013-01-31 | 2013-01-15 | 2013-01-31 | 83 | No | DUKHENGP2ADWARSM4850 | DUKHENGP2ADWARAP4870, DUKHENGP2ADWARSM4880 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L40.E05.H10.G20 APPROVAL OF DRAWINGS |  | 106 | 106 | 0% | 2013-01-24 | 2013-05-28 | 2013-01-24 | 2013-05-28 | 83 |  |  |  | 0 | 0
DUKHENGP2ADWARAP4940 | Carpentry & Joinery Drawings-App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 83 | No | DUKHENGP2ADWARSM4940 | DUKHPROGEN00PRDV3550, DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3570 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWARAP4880 | Ceramic Flooring & Wall Drawings-App | 30 | 30 | 0% | 2013-02-11 | 2013-03-18 | 2013-02-11 | 2013-03-18 | 78 | No | DUKHENGP2ADWARSM4880 | DUKHPROGEN00PRDV3120 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWARAP4900 | Cobble & Slate Flooring Drawings-App | 30 | 30 | 0% | 2013-02-11 | 2013-03-18 | 2013-02-11 | 2013-03-18 | 118 | No | DUKHENGP2ADWARSM4900 | DUKHPROGEN00PRDV3090, DUKHPROGEN00PRDV3100 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWARAP4930 | Doors & Window Drawings-App | 30 | 30 | 0% | 2013-04-07 | 2013-05-11 | 2013-04-07 | 2013-05-11 | 61 | No | DUKHENGP2ADWARSM4930, DUKHENGP2ADWARAP4870 | DUKHPROGEN00PRDV3460, DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3450, DUKHPROGEN00PRDV3440, DUKHPROGEN00PRDV3470 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWARAP4850 | Ground Floor Plan-App | 30 | 30 | 0% | 2013-01-24 | 2013-02-28 | 2013-01-24 | 2013-02-28 | 111 | No | DUKHENGP2ADWARSM4850 | DUKHPROGEN00PRDV3480, DUKHPROGEN00PRDV3320, DUKHPROGEN00PRDV3040, DUKHPROGEN00PRDV3420, DUKHPROGEN00PRDV3110, DUKHCONP1AMKARFF3300 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWARAP4910 | Gypsum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 67 | No | DUKHENGP2ADWARSM4910 | DUKHPROGEN00PRDV3300 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWARAP4890 | Porcelain Floor Drawings-App | 30 | 30 | 0% | 2013-02-11 | 2013-03-18 | 2013-02-11 | 2013-03-18 | 87 | No | DUKHENGP2ADWARSM4890 | DUKHPROGEN00PRDV3130 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWARAP4870 | Roof Floor Plan-App | 30 | 30 | 0% | 2013-02-02 | 2013-03-09 | 2013-02-02 | 2013-03-09 | 85 | No | DUKHENGP2ADWARSM4870 | DUKHPROGEN00PRDV3050, DUKHPROGEN00PRDV3140, DUKHENGP2ADWARAP4930 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L40.E05.H20 ELECTRICAL DRAWINGS |  | 95 | 95 | 0% | 2013-02-21 | 2013-06-11 | 2013-02-21 | 2013-06-11 | 75 |  |  |  | 0 | 0
DHBL.K20.L40.E05.H20.G10 SUBMISSION OF DRAWINGS |  | 65 | 65 | 0% | 2013-02-21 | 2013-05-07 | 2013-02-21 | 2013-05-07 | 75 |  |  |  | 0 | 0
DUKHENGP2ADWELSM4990 | Audio Video Intercom System Drawings-Sub | 15 | 15 | 0% | 2013-04-03 | 2013-04-20 | 2013-04-03 | 2013-04-20 | 75 | No | DUKHENGP2ADWELSM4980 | DUKHENGP2ADWELSM5000, DUKHENGP2ADWELAP4990 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWELSM4980 | Central Alarm Monitoring System Drawings-Sub | 15 | 15 | 0% | 2013-03-17 | 2013-04-02 | 2013-03-17 | 2013-04-02 | 75 | No | DUKHENGP2ADWELSM4970 | DUKHENGP2ADWELAP4980, DUKHENGP2ADWELSM4990 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWELSM4960 | Lighting Layout Drawings-Sub | 15 | 15 | 0% | 2013-02-27 | 2013-03-16 | 2013-02-27 | 2013-03-16 | 59 | No | DUKHENGP2ADWELSM4950 | DUKHENGP2ADWELSM4970, DUKHENGP2ADWELAP4960 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWELSM4970 | Power Layout Drawings-Sub | 15 | 15 | 0% | 2013-02-27 | 2013-03-16 | 2013-02-27 | 2013-03-16 | 75 | No | DUKHENGP2ADWELSM4960, DUKHENGP2ADWELSM4950 | DUKHENGP2ADWELSM4980, DUKHENGP2ADWELAP4970 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWELSM4950 | Single Line Diagram-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 59 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP2ADWELSM4960, DUKHENGP2ADWELSM4970, DUKHENGP2ADWELAP4950 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWELSM5000 | Telephone & TV System Drawings-Sub | 15 | 15 | 0% | 2013-04-21 | 2013-05-07 | 2013-04-21 | 2013-05-07 | 75 | No | DUKHENGP2ADWELSM4990 | DUKHENGP2ADWELAP5000 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L40.E05.H20.G20 APPROVAL OF DRAWINGS |  | 80 | 80 | 0% | 2013-03-11 | 2013-06-11 | 2013-03-11 | 2013-06-11 | 75 |  |  |  | 0 | 0
DUKHENGP2ADWELAP4990 | Audio Video Intercom System Drawings-App | 30 | 30 | 0% | 2013-04-21 | 2013-05-25 | 2013-04-21 | 2013-05-25 | 90 | No | DUKHENGP2ADWELSM4990 | DUKHPROGEN00PRDV3270 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWELAP4980 | Central Alarm Monitoring System Drawings-App | 30 | 30 | 0% | 2013-04-03 | 2013-05-07 | 2013-04-03 | 2013-05-07 | 99 | No | DUKHENGP2ADWELSM4980 | DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3260, DUKHPROGEN00PRDV3360 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWELAP4960 | Lighting Layout Drawings-App | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 59 | No | DUKHENGP2ADWELSM4960 | DUKHPROGEN00PRDV3180, DUKHPROGEN00PRDV3190 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWELAP4970 | Power Layout Drawings-App | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 110 | No | DUKHENGP2ADWELSM4970 | DUKHPROGEN00PRDV3170, DUKHPROGEN00PRDV3200 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWELAP4950 | Single Line Diagram-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 115 | No | DUKHENGP2ADWELSM4950 | DUKHPROGEN00PRDV3170 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWELAP5000 | Telephone & TV System Drawings-App | 30 | 30 | 0% | 2013-05-08 | 2013-06-11 | 2013-05-08 | 2013-06-11 | 75 | No | DUKHENGP2ADWELSM5000 | DUKHPROGEN00PRDV3280, DUKHPROGEN00PRDV3290 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L40.E05.H30 PLUMBING,DRAINAGE,FIREFIGHTING & AC DRAWINGS |  | 75 | 75 | 0% | 2013-02-21 | 2013-05-19 | 2013-02-21 | 2013-05-19 | 130 |  |  |  | 0 | 0
DHBL.K20.L40.E05.H30.G10 SUBMISSION OF DRAWINGS |  | 45 | 45 | 0% | 2013-02-21 | 2013-04-14 | 2013-02-21 | 2013-04-14 | 45 |  |  |  | 0 | 0
DUKHENGP2ADWMESM5040 | AC Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 45 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040, DUKHENGP2ADWMESM5030 | DUKHENGP2ADWMEAP5040, DUKHENGI2ADWDRSM5050 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWMESM5020 | Drainage Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 45 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP2ADWMESM5030, DUKHENGP2ADWMEAP5020 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWMESM5030 | Fire Fighting Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 45 | No | DUKHPROGEN00PQAP2040, DUKHENGP2ADWMESM5020, DUKHPROGEN00PQAP1040 | DUKHENGP2ADWMEAP5030, DUKHENGP2ADWMESM5040 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2ADWMESM5010 | Plumbing Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 53 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP2ADWMEAP5020, DUKHENGP2ADWMEAP5010 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L40.E05.H30.G20 APPROVAL OF DRAWINGS |  | 60 | 60 | 0% | 2013-03-11 | 2013-05-19 | 2013-03-11 | 2013-05-19 | 130 |  |  |  | 0 | 0
DUKHENGP2ADWMEAP5040 | AC Layout & Details Drawings-App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 64 | No | DUKHENGP2ADWMESM5040 | DUKHPROGEN00PRDV3530, DUKHPROGEN00PRDV3240, DUKHPROGEN00PRDV3160, DUKHPROGEN00PRDV3340 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWMEAP5020 | Drainage Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP2ADWMESM5010, DUKHENGP2ADWMESM5020 | DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3640 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWMEAP5030 | Fire Fighting Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 145 | No | DUKHENGP2ADWMESM5030 | DUKHPROGEN00PRDV3380, DUKHPROGEN00PRDV3370 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2ADWMEAP5010 | Plumbing Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP2ADWMESM5010 | DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3230 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L40.E05.H40 INFRA DRAWINGS |  | 97 | 97 | 0% | 2013-04-15 | 2013-08-05 | 2013-04-15 | 2013-08-05 | 135 |  |  |  | 0 | 0
DHBL.K20.L40.E05.H40.G10 SUBMISSION OF DRAWINGS |  | 67 | 67 | 0% | 2013-04-15 | 2013-07-01 | 2013-04-15 | 2013-07-01 | 90 |  |  |  | 0 | 0
DUKHENGI2ADWBWSM5130 | Boundary Wall Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI2ADWSLSM5120 | DUKHENGI2ADWPSSM5140, DUKHENGI2ADWBWAP5130 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWDRSM5050 | Drainage Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGP2ADWMESM5040, DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGI2ADWWSSM5070, DUKHENGI2ADWDRAP5050 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWELSM5080 | Electrical Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI2ADWFFSM5060, DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGI2ADWSTSM5090, DUKHENGI2ADWELAP5080 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWFFSM5060 | Fire Fighting Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI2ADWWSSM5070 | DUKHENGI2ADWELSM5080, DUKHENGI2ADWFFAP5060 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWGZSM5170 | Gazebo Plan & Details-Sub | 15 | 15 | 0% | 2013-06-15 | 2013-07-01 | 2013-06-15 | 2013-07-01 | 90 | No | DUKHENGI2ADWIWSM5160 | DUKHENGI2ADWGZAP5170 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWIRSM5110 | Irrigation Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI2ADWTCSM5100, DUKHENGI2ADWWSSM5070 | DUKHENGI2ADWIRAP5110, DUKHENGI2ADWSLSM5120 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWIWSM5160 | Irrigation Water Tank & Pump Room Details- Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI2ADWRWSM5150 | DUKHENGI2ADWGZSM5170, DUKHENGI2ADWIWAP5160 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWPSSM5140 | Parking Shed Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI2ADWBWSM5130 | DUKHENGI2ADWRWSM5150, DUKHENGI2ADWPSAP5140 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWRWSM5150 | Road Layout & Details-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI2ADWPSSM5140 | DUKHENGI2ADWRWAP5150, DUKHENGI2ADWIWSM5160 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWSLSM5120 | Soft & HardLandscaping Layout & Detail-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI2ADWIRSM5110 | DUKHENGI2ADWSLAP5120, DUKHENGI2ADWBWSM5130 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWSTSM5090 | Street Lighting Layout & details -Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI2ADWELSM5080 | DUKHENGI2ADWTCSM5100, DUKHENGI2ADWSTAP5090 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWTCSM5100 | Telecommunication Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI2ADWSTSM5090 | DUKHENGI2ADWIRSM5110, DUKHENGI2ADWTCAP5100 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2ADWWSSM5070 | Water Supply Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI2ADWDRSM5050 | DUKHENGI2ADWFFSM5060, DUKHENGI2ADWWSAP5070, DUKHENGI2ADWIRSM5110 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L40.E05.H40.G20 APPROVAL OF DRAWINGS |  | 82 | 82 | 0% | 2013-05-02 | 2013-08-05 | 2013-05-02 | 2013-08-05 | 135 |  |  |  | 0 | 0
DUKHENGI2ADWBWAP5130 | Boundary Wall Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 85 | No | DUKHENGI2ADWBWSM5130 | DUKHPROGEN00PRDV3820, DUKHCONI2AZ1BWGL5315, DUKHCONI2AZ1RWGL6000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWDRAP5050 | Drainage Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 68 | No | DUKHENGI2ADWDRSM5050 | DUKHCONI2AZ1SAGL5135, DUKHCONI2AZ1DRGL5115, DUKHPROGEN00PRDV3590 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWELAP5080 | Electrical Line Layout & Details-App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 120 | No | DUKHENGI2ADWELSM5080 | DUKHPROGEN00PRDV3350, DUKHPROGEN00PRDV3250, DUKHCONI2AZ1ELGL5215 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWFFAP5060 | Fire Fighting Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 45 | No | DUKHENGI2ADWFFSM5060 | DUKHCONI2AZ1FFGL5185, DUKHPROGEN00PRDV3650, DUKHPROGEN00PRDV3690, DUKHPROGEN00PRDV3540 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWGZAP5170 | Gazebo Plan & Details-App | 30 | 30 | 0% | 2013-07-02 | 2013-08-05 | 2013-07-02 | 2013-08-05 | 90 | No | DUKHENGI2ADWGZSM5170 | DUKHPROGEN00PRDV3780, DUKHCONI2ASBGZGL7900 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWIRAP5110 | Irrigation Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 91 | No | DUKHENGI2ADWIRSM5110 | DUKHPROGEN00PRDV3760, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3830, DUKHCONI2AZ1IRGL5265, DUKHPROGEN00PRDV3870, DUKHPROGEN00PRDV3840, DUKHPROGEN00PRDV3670, DUKHPROGEN00PRDV3860 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWIWAP5160 | Irrigation Water Tank & Pump Room Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 49 | No | DUKHENGI2ADWIWSM5160 | DUKHCONI2ASBIWGL7400, DUKHPROGEN00PRDV3590, DUKHPROGEN00PRDV3660 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWPSAP5140 | Parking Shed Layout & Details Drawings-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 150 | No | DUKHENGI2ADWPSSM5140 | DUKHPROGEN00PRDV3730, DUKHCONI2AZ1PSGL7000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWRWAP5150 | Road Layout & Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 149 | No | DUKHENGI2ADWRWSM5150 | DUKHPROGEN00PRDV3700, DUKHPROGEN00PRDV3720, DUKHPROGEN00PRDV3750 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWSLAP5120 | Soft & HardLandscaping Layout & Detail-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 67 | No | DUKHENGI2ADWSLSM5120 | DUKHCONI2AZ1HDGL7020, DUKHCONI2AZ1SLGL7200, DUKHPROGEN00PRDV3790 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWSTAP5090 | Street Lighting Layout & details -App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 120 | No | DUKHENGI2ADWSTSM5090 | DUKHCONI2AZ1STGL5235, DUKHPROGEN00PRDV3350, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWTCAP5100 | Telecommunication Line Layout & Details-App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 120 | No | DUKHENGI2ADWTCSM5100 | DUKHPROGEN00PRDV3250, DUKHCONI2AZ1TCGL5295 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2ADWWSAP5070 | Water Supply Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 86 | No | DUKHENGI2ADWWSSM5070 | DUKHPROGEN00PRDV3590, DUKHCONI2AZ1WSGL5155 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L50 PACKAGE-2B |  | 215 | 215 | 0% | 2012-11-26 | 2013-08-05 | 2012-11-26 | 2013-08-05 | 135 |  |  |  | 0 | 0
DHBL.K20.L50.E05 SHOP DRAWINGS SUBMISSION & APPROVAL |  | 215 | 215 | 0% | 2012-11-26 | 2013-08-05 | 2012-11-26 | 2013-08-05 | 135 |  |  |  | 0 | 0
DHBL.K20.L50.E05.H05 STRUCTURAL DRAWINGS |  | 65 | 65 | 0% | 2012-11-26 | 2013-02-10 | 2012-11-26 | 2013-02-10 | 136 |  |  |  | 0 | 0
DHBL.K20.L50.E05.H05.G10 SUBMISSION OF DRAWINGS |  | 35 | 35 | 0% | 2012-11-26 | 2013-01-06 | 2012-11-26 | 2013-01-06 | 75 |  |  |  | 0 | 0
DUKHENGP2BDWSTSM5200 | Column Drawings-Sub | 15 | 15 | 0% | 2012-12-08 | 2012-12-25 | 2012-12-08 | 2012-12-25 | 75 | No | DUKHENGP2BDWSTSM5190 | DUKHENGP2BDWSTSM5210, DUKHENGP2BDWSTAP5200 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWSTSM5180 | Footing Drawings-Sub | 10 | 10 | 0% | 2012-11-26 | 2012-12-06 | 2012-11-26 | 2012-12-06 | 70 | No | DUKHMOBP020000004020 | DUKHENGP2BDWSTAP5180, DUKHENGP2BDWSTSM5190 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWSTSM5210 | GF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2012-12-20 | 2013-01-06 | 2012-12-20 | 2013-01-06 | 75 | No | DUKHENGP2BDWSTSM5200 | DUKHENGP2BDWSTAP5210, DUKHENGP2BDWARSM5230 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWSTSM5190 | Grade Beam & Slab Drawings-Sub | 15 | 15 | 0% | 2012-12-02 | 2012-12-19 | 2012-12-02 | 2012-12-19 | 75 | No | DUKHENGP2BDWSTSM5180 | DUKHENGP2BDWSTAP5190, DUKHENGP2BDWSTSM5200 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L50.E05.H05.G20 APPROVAL OF DRAWINGS |  | 55 | 55 | 0% | 2012-12-08 | 2013-02-10 | 2012-12-08 | 2013-02-10 | 136 |  |  |  | 0 | 0
DUKHENGP2BDWSTAP5200 | Column Drawings-App | 30 | 30 | 0% | 2012-12-26 | 2013-01-29 | 2012-12-26 | 2013-01-29 | 130 | No | DUKHENGP2BDWSTSM5200 | DUKHCONP2BZ3STGF2000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWSTAP5180 | Footing Drawings-App | 25 | 25 | 0% | 2012-12-08 | 2013-01-06 | 2012-12-08 | 2013-01-06 | 70 | No | DUKHENGP2BDWSTSM5180 | DUKHCONP2BZ3STUG1015 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWSTAP5210 | GF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-01-07 | 2013-02-10 | 2013-01-07 | 2013-02-10 | 136 | No | DUKHENGP2BDWSTSM5210 | DUKHCONP2BZ3STGF2010 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWSTAP5190 | Grade Beam & Slab Drawings-App | 30 | 30 | 0% | 2012-12-20 | 2013-01-23 | 2012-12-20 | 2013-01-23 | 99 | No | DUKHENGP2BDWSTSM5190 | DUKHCONP2BZ3STUG1040, DUKHCONP2BZ3STUG1045 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L50.E05.H10 ARCHITECTURAL DRAWINGS |  | 121 | 121 | 0% | 2013-01-07 | 2013-05-28 | 2013-01-07 | 2013-05-28 | 83 |  |  |  | 0 | 0
DHBL.K20.L50.E05.H10.G10 SUBMISSION OF DRAWINGS |  | 91 | 91 | 0% | 2013-01-07 | 2013-04-23 | 2013-01-07 | 2013-04-23 | 83 |  |  |  | 0 | 0
DUKHENGP2BDWARSM5320 | Carpentry & Joinery Drawings-Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 83 | No | DUKHENGP2BDWARSM5230, DUKHPROGEN00PQAP2150, DUKHPROGEN00PQAP1150 | DUKHENGP2BDWARAP5320 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWARSM5260 | Ceramic Flooring & Wall Drawings-Sub | 15 | 15 | 0% | 2013-01-28 | 2013-02-14 | 2013-01-28 | 2013-02-14 | 75 | No | DUKHENGP2BDWARSM5250, DUKHENGP2BDWARSM5230 | DUKHENGP2BDWARSM5270, DUKHENGP2BDWARAP5260 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWARSM5280 | Cobble & Slate Flooring Drawings-Sub | 15 | 15 | 0% | 2013-01-28 | 2013-02-14 | 2013-01-28 | 2013-02-14 | 115 | No | DUKHENGP2BDWARSM5270 | DUKHENGP2BDWARAP5280 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWARSM5310 | Doors & window Drawings-Sub | 15 | 15 | 0% | 2013-03-20 | 2013-04-06 | 2013-03-20 | 2013-04-06 | 61 | No | DUKHPROGEN00PQAP1080, DUKHENGP2BDWARSM5230, DUKHPROGEN00PQAP2080 | DUKHENGP2BDWARAP5310 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWARSM5230 | Ground Floor Plan-Sub | 15 | 15 | 0% | 2013-01-07 | 2013-01-23 | 2013-01-07 | 2013-01-23 | 75 | No | DUKHENGP2BDWSTSM5210 | DUKHENGP2BDWARSM5320, DUKHENGP2BDWARSM5250, DUKHENGP2BDWARSM5310, DUKHENGP2BDWARSM5260, DUKHENGP2BDWARAP5230 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWARSM5290 | Gypsum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 67 | No | DUKHPROGEN00PQAP2050, DUKHPROGEN00PQAP1050 | DUKHENGP2BDWARAP5290 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWARSM5270 | Porcelain Floor Drawings-Sub | 15 | 15 | 0% | 2013-01-28 | 2013-02-14 | 2013-01-28 | 2013-02-14 | 84 | No | DUKHENGP2BDWARSM5260 | DUKHENGP2BDWARAP5270, DUKHENGP2BDWARSM5280 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWARSM5250 | Roof Floor Plan-Sub | 15 | 15 | 0% | 2013-01-24 | 2013-02-10 | 2013-01-24 | 2013-02-10 | 75 | No | DUKHENGP2BDWARSM5230 | DUKHENGP2BDWARSM5260, DUKHENGP2BDWARAP5250 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L50.E05.H10.G20 APPROVAL OF DRAWINGS |  | 106 | 106 | 0% | 2013-01-24 | 2013-05-28 | 2013-01-24 | 2013-05-28 | 83 |  |  |  | 0 | 0
DUKHENGP2BDWARAP5320 | Carpentry & Joinery Drawings-App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 83 | No | DUKHENGP2BDWARSM5320 | DUKHPROGEN00PRDV3570, DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3550 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWARAP5260 | Ceramic Flooring & Wall Drawings-App | 30 | 30 | 0% | 2013-02-16 | 2013-03-21 | 2013-02-16 | 2013-03-21 | 75 | No | DUKHENGP2BDWARSM5260 | DUKHPROGEN00PRDV3120 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWARAP5280 | Cobble & Slate Flooring Drawings-App | 30 | 30 | 0% | 2013-02-16 | 2013-03-21 | 2013-02-16 | 2013-03-21 | 115 | No | DUKHENGP2BDWARSM5280 | DUKHPROGEN00PRDV3090, DUKHPROGEN00PRDV3100 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWARAP5310 | Doors & Window Drawings-App | 30 | 30 | 0% | 2013-04-07 | 2013-05-11 | 2013-04-07 | 2013-05-11 | 61 | No | DUKHENGP2BDWARAP5250, DUKHENGP2BDWARSM5310 | DUKHPROGEN00PRDV3460, DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3450, DUKHPROGEN00PRDV3470, DUKHPROGEN00PRDV3440 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWARAP5230 | Ground Floor Plan-App | 30 | 30 | 0% | 2013-01-24 | 2013-02-28 | 2013-01-24 | 2013-02-28 | 111 | No | DUKHENGP2BDWARSM5230 | DUKHCONP1AMKARFF3300, DUKHPROGEN00PRDV3110, DUKHPROGEN00PRDV3040, DUKHPROGEN00PRDV3420, DUKHPROGEN00PRDV3320, DUKHPROGEN00PRDV3480 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWARAP5290 | Gypsum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 67 | No | DUKHENGP2BDWARSM5290 | DUKHPROGEN00PRDV3300 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWARAP5270 | Porcelain Floor Drawings-App | 30 | 30 | 0% | 2013-02-16 | 2013-03-21 | 2013-02-16 | 2013-03-21 | 84 | No | DUKHENGP2BDWARSM5270 | DUKHPROGEN00PRDV3130 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWARAP5250 | Roof Floor Plan-App | 30 | 30 | 0% | 2013-02-11 | 2013-03-18 | 2013-02-11 | 2013-03-18 | 77 | No | DUKHENGP2BDWARSM5250 | DUKHENGP2BDWARAP5310, DUKHPROGEN00PRDV3050, DUKHPROGEN00PRDV3140 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L50.E05.H20 ELECTRICAL DRAWINGS |  | 95 | 95 | 0% | 2013-02-21 | 2013-06-11 | 2013-02-21 | 2013-06-11 | 75 |  |  |  | 0 | 0
DHBL.K20.L50.E05.H20.G10 SUBMISSION OF DRAWINGS |  | 65 | 65 | 0% | 2013-02-21 | 2013-05-07 | 2013-02-21 | 2013-05-07 | 75 |  |  |  | 0 | 0
DUKHENGP2BDWELSM5370 | Audio Video Intercom System Drawings-Sub | 15 | 15 | 0% | 2013-04-03 | 2013-04-20 | 2013-04-03 | 2013-04-20 | 75 | No | DUKHENGP2BDWELSM5360 | DUKHENGP2BDWELAP5370, DUKHENGP2BDWELSM5380 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWELSM5360 | Central Alarm Monitoring System Drawings-Sub | 15 | 15 | 0% | 2013-03-17 | 2013-04-02 | 2013-03-17 | 2013-04-02 | 75 | No | DUKHENGP2BDWELSM5350 | DUKHENGP2BDWELAP5360, DUKHENGP2BDWELSM5370 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWELSM5340 | Lighting Layout Drawings-Sub | 15 | 15 | 0% | 2013-02-27 | 2013-03-16 | 2013-02-27 | 2013-03-16 | 59 | No | DUKHENGP2BDWELSM5330 | DUKHENGP2BDWELAP5340, DUKHENGP2BDWELSM5350 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWELSM5350 | Power Layout Drawings-Sub | 15 | 15 | 0% | 2013-02-27 | 2013-03-16 | 2013-02-27 | 2013-03-16 | 75 | No | DUKHENGP2BDWELSM5330, DUKHENGP2BDWELSM5340 | DUKHENGP2BDWELAP5350, DUKHENGP2BDWELSM5360 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWELSM5330 | Single Line Diagram-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 59 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGP2BDWELAP5330, DUKHENGP2BDWELSM5340, DUKHENGP2BDWELSM5350 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWELSM5380 | Telephone & TV System Drawings-Sub | 15 | 15 | 0% | 2013-04-21 | 2013-05-07 | 2013-04-21 | 2013-05-07 | 75 | No | DUKHENGP2BDWELSM5370 | DUKHENGP2BDWELAP5380 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L50.E05.H20.G20 APPROVAL OF DRAWINGS |  | 80 | 80 | 0% | 2013-03-11 | 2013-06-11 | 2013-03-11 | 2013-06-11 | 75 |  |  |  | 0 | 0
DUKHENGP2BDWELAP5370 | Audio Video Intercom System Drawings-App | 30 | 30 | 0% | 2013-04-21 | 2013-05-25 | 2013-04-21 | 2013-05-25 | 90 | No | DUKHENGP2BDWELSM5370 | DUKHPROGEN00PRDV3270 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWELAP5360 | Central Alarm Monitoring System Drawings-App | 30 | 30 | 0% | 2013-04-03 | 2013-05-07 | 2013-04-03 | 2013-05-07 | 99 | No | DUKHENGP2BDWELSM5360 | DUKHPROGEN00PRDV3260, DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3360 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWELAP5340 | Lighting Layout Drawings-App | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 59 | No | DUKHENGP2BDWELSM5340 | DUKHPROGEN00PRDV3180, DUKHPROGEN00PRDV3190 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWELAP5350 | Power Layout Drawings-App | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 110 | No | DUKHENGP2BDWELSM5350 | DUKHPROGEN00PRDV3200, DUKHPROGEN00PRDV3170 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWELAP5330 | Single Line Diagram-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 115 | No | DUKHENGP2BDWELSM5330 | DUKHPROGEN00PRDV3170 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWELAP5380 | Telephone & TV System Drawings-App | 30 | 30 | 0% | 2013-05-08 | 2013-06-11 | 2013-05-08 | 2013-06-11 | 75 | No | DUKHENGP2BDWELSM5380 | DUKHPROGEN00PRDV3280, DUKHPROGEN00PRDV3290 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L50.E05.H30 PLUMBING,DRAINAGE,FIREFIGHTING & AC DRAWINGS |  | 75 | 75 | 0% | 2013-02-21 | 2013-05-19 | 2013-02-21 | 2013-05-19 | 130 |  |  |  | 0 | 0
DHBL.K20.L50.E05.H30.G10 SUBMISSION OF DRAWINGS |  | 45 | 45 | 0% | 2013-02-21 | 2013-04-14 | 2013-02-21 | 2013-04-14 | 45 |  |  |  | 0 | 0
DUKHENGP2BDWMESM5420 | AC Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 45 | No | DUKHENGP2BDWMESM5410, DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGI2BDWDRSM5430, DUKHENGP2BDWMEAP5420 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWMESM5400 | Drainage Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 45 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP2BDWMEAP5400, DUKHENGP2BDWMESM5410 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWMESM5410 | Fire Fighting Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 45 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040, DUKHENGP2BDWMESM5400 | DUKHENGP2BDWMEAP5410, DUKHENGP2BDWMESM5420 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP2BDWMESM5390 | Plumbing Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 53 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGP2BDWMEAP5390, DUKHENGP2BDWMEAP5400 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L50.E05.H30.G20 APPROVAL OF DRAWINGS |  | 60 | 60 | 0% | 2013-03-11 | 2013-05-19 | 2013-03-11 | 2013-05-19 | 130 |  |  |  | 0 | 0
DUKHENGP2BDWMEAP5420 | AC Layout & Details Drawings-App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 64 | No | DUKHENGP2BDWMESM5420 | DUKHPROGEN00PRDV3340, DUKHPROGEN00PRDV3240, DUKHPROGEN00PRDV3160, DUKHPROGEN00PRDV3530 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWMEAP5400 | Drainage Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP2BDWMESM5390, DUKHENGP2BDWMESM5400 | DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3150 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWMEAP5410 | Fire Fighting Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 145 | No | DUKHENGP2BDWMESM5410 | DUKHPROGEN00PRDV3370, DUKHPROGEN00PRDV3380 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP2BDWMEAP5390 | Plumbing Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP2BDWMESM5390 | DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3520 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L50.E05.H40 INFRA DRAWINGS |  | 97 | 97 | 0% | 2013-04-15 | 2013-08-05 | 2013-04-15 | 2013-08-05 | 135 |  |  |  | 0 | 0
DHBL.K20.L50.E05.H40.G10 SUBMISSION OF DRAWINGS |  | 67 | 67 | 0% | 2013-04-15 | 2013-07-01 | 2013-04-15 | 2013-07-01 | 90 |  |  |  | 0 | 0
DUKHENGI2BDWBWSM5510 | Boundary Wall Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI2BDWSLSM5500 | DUKHENGI2BDWPSSM5520, DUKHENGI2BDWBWAP5510 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWDRSM5430 | Drainage Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGP2BDWMESM5420, DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGI2BDWWSSM5450, DUKHENGI2BDWDRAP5430 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWELSM5460 | Electrical Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI2BDWFFSM5440, DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGI2BDWSTSM5470, DUKHENGI2BDWELAP5460 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWFFSM5440 | Fire Fighting Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI2BDWWSSM5450 | DUKHENGI2BDWELSM5460, DUKHENGI2BDWFFAP5440 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWGZSM5550 | Gazebo Plan & Details-Sub | 15 | 15 | 0% | 2013-06-15 | 2013-07-01 | 2013-06-15 | 2013-07-01 | 90 | No | DUKHENGI2BDWIWSM5540 | DUKHENGI2BDWGZAP5550 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWIRSM5490 | Irrigation Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI2BDWTCSM5480, DUKHENGI2BDWWSSM5450 | DUKHENGI2BDWIRAP5490, DUKHENGI2BDWSLSM5500 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWIWSM5540 | Irrigation Water Tank & Pump Room Details- Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI2BDWRWSM5530 | DUKHENGI2BDWIWAP5540, DUKHENGI2BDWGZSM5550 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWPSSM5520 | Parking Shed Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI2BDWBWSM5510 | DUKHENGI2BDWPSAP5520, DUKHENGI2BDWRWSM5530 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWRWSM5530 | Road Layout & Details-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI2BDWPSSM5520 | DUKHENGI2BDWRWAP5530, DUKHENGI2BDWIWSM5540 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWSLSM5500 | Soft & HardLandscaping Layout & Detail-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI2BDWIRSM5490 | DUKHENGI2BDWSLAP5500, DUKHENGI2BDWBWSM5510 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWSTSM5470 | Street Lighting Layout & details -Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI2BDWELSM5460 | DUKHENGI2BDWSTAP5470, DUKHENGI2BDWTCSM5480 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWTCSM5480 | Telecommunication Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI2BDWSTSM5470 | DUKHENGI2BDWIRSM5490, DUKHENGI2BDWTCAP5480 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI2BDWWSSM5450 | Water Supply Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI2BDWDRSM5430 | DUKHENGI2BDWFFSM5440, DUKHENGI2BDWIRSM5490, DUKHENGI2BDWWSAP5450 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L50.E05.H40.G20 APPROVAL OF DRAWINGS |  | 82 | 82 | 0% | 2013-05-02 | 2013-08-05 | 2013-05-02 | 2013-08-05 | 135 |  |  |  | 0 | 0
DUKHENGI2BDWBWAP5510 | Boundary Wall Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 85 | No | DUKHENGI2BDWBWSM5510 | DUKHCONI2BZ1RWGL6000, DUKHPROGEN00PRDV3820, DUKHCONI2BZ1BWGL5315 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWDRAP5430 | Drainage Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 64 | No | DUKHENGI2BDWDRSM5430 | DUKHPROGEN00PRDV3590, DUKHCONI2BZ1SAGL5135, DUKHCONI2BZ1DRGL5115 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWELAP5460 | Electrical Line Layout & Details-App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 120 | No | DUKHENGI2BDWELSM5460 | DUKHCONI2BZ1ELGL5215, DUKHPROGEN00PRDV3250, DUKHPROGEN00PRDV3350 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWFFAP5440 | Fire Fighting Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 45 | No | DUKHENGI2BDWFFSM5440 | DUKHPROGEN00PRDV3690, DUKHPROGEN00PRDV3540, DUKHCONI2BZ1FFGL5185, DUKHPROGEN00PRDV3650 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWGZAP5550 | Gazebo Plan & Details-App | 30 | 30 | 0% | 2013-07-02 | 2013-08-05 | 2013-07-02 | 2013-08-05 | 90 | No | DUKHENGI2BDWGZSM5550 | DUKHCONI2BSBGZGL7900, DUKHPROGEN00PRDV3780 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWIRAP5490 | Irrigation Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 91 | No | DUKHENGI2BDWIRSM5490 | DUKHPROGEN00PRDV3860, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3670, DUKHCONI2BZ1IRGL5265, DUKHPROGEN00PRDV3870, DUKHPROGEN00PRDV3840, DUKHPROGEN00PRDV3760, DUKHPROGEN00PRDV3830 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWIWAP5540 | Irrigation Water Tank & Pump Room Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 49 | No | DUKHENGI2BDWIWSM5540 | DUKHCONI2BSBIWGL7400, DUKHPROGEN00PRDV3590, DUKHPROGEN00PRDV3660 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWPSAP5520 | Parking Shed Layout & Details Drawings-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 150 | No | DUKHENGI2BDWPSSM5520 | DUKHCONI2BZ1PSGL7000, DUKHPROGEN00PRDV3730 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWRWAP5530 | Road Layout & Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 149 | No | DUKHENGI2BDWRWSM5530 | DUKHPROGEN00PRDV3750, DUKHPROGEN00PRDV3720, DUKHPROGEN00PRDV3700 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWSLAP5500 | Soft & HardLandscaping Layout & Detail-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 67 | No | DUKHENGI2BDWSLSM5500 | DUKHCONI2BZ1HDGL7020, DUKHPROGEN00PRDV3790, DUKHCONI2BZ1SLGL7200 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWSTAP5470 | Street Lighting Layout & details -App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 120 | No | DUKHENGI2BDWSTSM5470 | DUKHPROGEN00PRDV3350, DUKHCONI2BZ1STGL5235, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWTCAP5480 | Telecommunication Line Layout & Details-App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 120 | No | DUKHENGI2BDWTCSM5480 | DUKHCONI2BZ1TCGL5295, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI2BDWWSAP5450 | Water Supply Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 86 | No | DUKHENGI2BDWWSSM5450 | DUKHPROGEN00PRDV3590, DUKHCONI2BZ1WSGL5155 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L60 PACKAGE-3 |  | 241 | 241 | 0% | 2012-12-01 | 2013-09-12 | 2012-12-01 | 2013-09-12 | 170 |  |  |  | 0 | 0
DHBL.K20.L60.E05 SHOP DRAWINGS SUBMISSION & APPROVAL |  | 241 | 241 | 0% | 2012-12-01 | 2013-09-12 | 2012-12-01 | 2013-09-12 | 170 |  |  |  | 0 | 0
DHBL.K20.L60.E05.H05 STRUCTURAL DRAWINGS |  | 82 | 82 | 0% | 2012-12-01 | 2013-03-07 | 2012-12-01 | 2013-03-07 | 110 |  |  |  | 0 | 0
DHBL.K20.L60.E05.H05.G10 SUBMISSION OF DRAWINGS |  | 52 | 52 | 0% | 2012-12-01 | 2013-01-30 | 2012-12-01 | 2013-01-30 | 48 |  |  |  | 0 | 0
DUKHENGP03DWSTSM5580 | Column Drawings-Sub | 15 | 15 | 0% | 2012-12-15 | 2013-01-01 | 2012-12-15 | 2013-01-01 | 48 | No | DUKHENGP03DWSTSM5570 | DUKHENGP03DWSTSM5590, DUKHENGP03DWSTAP5580 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWSTSM5600 | FF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2013-01-14 | 2013-01-30 | 2013-01-14 | 2013-01-30 | 48 | No | DUKHENGP03DWSTSM5590 | DUKHENGP03DWSTAP5600, DUKHENGP03DWARSM5610 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWSTSM5560 | Footing Drawings-Sub | 10 | 10 | 0% | 2012-12-01 | 2012-12-11 | 2012-12-01 | 2012-12-11 | 32 | No | DUKHMOBP030000004000 | DUKHENGP03DWSTSM5570, DUKHENGP03DWSTAP5560 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWSTSM5590 | GF Beams & Slabs Drawings-Sub | 15 | 15 | 0% | 2012-12-27 | 2013-01-13 | 2012-12-27 | 2013-01-13 | 48 | No | DUKHENGP03DWSTSM5580 | DUKHENGP03DWSTAP5590, DUKHENGP03DWSTSM5600 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWSTSM5570 | Grade Beam & Slab Drawings-Sub | 15 | 15 | 0% | 2012-12-08 | 2012-12-25 | 2012-12-08 | 2012-12-25 | 48 | No | DUKHENGP03DWSTSM5560 | DUKHENGP03DWSTAP5570, DUKHENGP03DWSTSM5580 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L60.E05.H05.G20 APPROVAL OF DRAWINGS |  | 72 | 72 | 0% | 2012-12-12 | 2013-03-07 | 2012-12-12 | 2013-03-07 | 110 |  |  |  | 0 | 0
DUKHENGP03DWSTAP5580 | Column Drawings-App | 30 | 30 | 0% | 2013-01-02 | 2013-02-05 | 2013-01-02 | 2013-02-05 | 99 | No | DUKHENGP03DWSTSM5580 | DUKHCONP03Z1STGF2000 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWSTAP5600 | FF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-01-31 | 2013-03-07 | 2013-01-31 | 2013-03-07 | 110 | No | DUKHENGP03DWSTSM5600 | DUKHCONP03Z1STFF2020 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWSTAP5560 | Footing Drawings-App | 25 | 25 | 0% | 2012-12-12 | 2013-01-10 | 2012-12-12 | 2013-01-10 | 32 | No | DUKHENGP03DWSTSM5560 | DUKHCONP03Z1STUG1015 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWSTAP5590 | GF Beams & Slabs Drawings-App | 30 | 30 | 0% | 2013-01-14 | 2013-02-18 | 2013-01-14 | 2013-02-18 | 110 | No | DUKHENGP03DWSTSM5590 | DUKHCONP03Z1STGF2010 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWSTAP5570 | Grade Beam & Slab Drawings-App | 30 | 30 | 0% | 2012-12-26 | 2013-01-29 | 2012-12-26 | 2013-01-29 | 68 | No | DUKHENGP03DWSTSM5570 | DUKHCONP03Z1STUG1040, DUKHCONP03Z1STUG1045 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L60.E05.H10 ARCHITECTURAL DRAWINGS |  | 100 | 100 | 0% | 2013-01-31 | 2013-05-28 | 2013-01-31 | 2013-05-28 | 83 |  |  |  | 0 | 0
DHBL.K20.L60.E05.H10.G10 SUBMISSION OF DRAWINGS |  | 70 | 70 | 0% | 2013-01-31 | 2013-04-23 | 2013-01-31 | 2013-04-23 | 83 |  |  |  | 0 | 0
DUKHENGP03DWARSM5680 | Aluminum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 82 | No | DUKHPROGEN00PQAP1050, DUKHPROGEN00PQAP2050 | DUKHENGP03DWARAP5680 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5700 | Carpentry & Joinery Drawings-Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 83 | No | DUKHENGP03DWARSM5610, DUKHPROGEN00PQAP1150, DUKHPROGEN00PQAP2150 | DUKHENGP03DWARAP5700 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5640 | Ceramic Flooring & Wall Drawings-Sub | 15 | 15 | 0% | 2013-03-02 | 2013-03-18 | 2013-03-02 | 2013-03-18 | 48 | No | DUKHENGP03DWARSM5630, DUKHENGP03DWARSM5620, DUKHENGP03DWARSM5610 | DUKHENGP03DWARAP5640, DUKHENGP03DWARSM5650 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5660 | Cobble & Slate Flooring Drawings-Sub | 15 | 15 | 0% | 2013-03-02 | 2013-03-18 | 2013-03-02 | 2013-03-18 | 88 | No | DUKHENGP03DWARSM5650 | DUKHENGP03DWARAP5660 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5690 | Doors & window Drawings-Sub | 15 | 15 | 0% | 2013-03-20 | 2013-04-06 | 2013-03-20 | 2013-04-06 | 61 | No | DUKHENGP03DWARSM5610, DUKHPROGEN00PQAP2080, DUKHPROGEN00PQAP1080 | DUKHENGP03DWARAP5690 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5620 | First Floor Plan-Sub | 15 | 15 | 0% | 2013-02-11 | 2013-02-28 | 2013-02-11 | 2013-02-28 | 48 | No | DUKHENGP03DWARSM5610 | DUKHENGP03DWARAP5620, DUKHENGP03DWARSM5630, DUKHENGP03DWARSM5640 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5610 | Ground Floor Plan-Sub | 15 | 15 | 0% | 2013-01-31 | 2013-02-18 | 2013-01-31 | 2013-02-18 | 48 | No | DUKHENGP03DWSTSM5600 | DUKHENGP03DWARSM5700, DUKHENGP03DWARAP5610, DUKHENGP03DWARSM5640, DUKHENGP03DWARSM5690, DUKHENGP03DWARSM5620 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5670 | Gypsum False Ceiling Drawings-Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 67 | No | DUKHPROGEN00PQAP2050, DUKHPROGEN00PQAP1050 | DUKHENGP03DWARAP5670 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5650 | Porcelain Floor Drawings-Sub | 15 | 15 | 0% | 2013-03-02 | 2013-03-18 | 2013-03-02 | 2013-03-18 | 57 | No | DUKHENGP03DWARSM5640 | DUKHENGP03DWARAP5650, DUKHENGP03DWARSM5660 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWARSM5630 | Roof Floor Plan-Sub | 15 | 15 | 0% | 2013-02-20 | 2013-03-09 | 2013-02-20 | 2013-03-09 | 53 | No | DUKHENGP03DWARSM5620 | DUKHENGP03DWARSM5640, DUKHENGP03DWARAP5630 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L60.E05.H10.G20 APPROVAL OF DRAWINGS |  | 85 | 85 | 0% | 2013-02-19 | 2013-05-28 | 2013-02-19 | 2013-05-28 | 83 |  |  |  | 0 | 0
DUKHENGP03DWARAP5680 | Aluminum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 82 | No | DUKHENGP03DWARSM5680 | DUKHPROGEN00PRDV3310 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5700 | Carpentry & Joinery Drawings-App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 83 | No | DUKHENGP03DWARSM5700 | DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3570, DUKHPROGEN00PRDV3550 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5640 | Ceramic Flooring & Wall Drawings-App | 30 | 30 | 0% | 2013-03-19 | 2013-04-22 | 2013-03-19 | 2013-04-22 | 48 | No | DUKHENGP03DWARSM5640 | DUKHPROGEN00PRDV3120 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5660 | Cobble & Slate Flooring Drawings-App | 30 | 30 | 0% | 2013-03-19 | 2013-04-22 | 2013-03-19 | 2013-04-22 | 88 | No | DUKHENGP03DWARSM5660 | DUKHPROGEN00PRDV3100, DUKHPROGEN00PRDV3090 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5690 | Doors & Window Drawings-App | 30 | 30 | 0% | 2013-04-14 | 2013-05-18 | 2013-04-14 | 2013-05-18 | 55 | No | DUKHENGP03DWARSM5690, DUKHENGP03DWARAP5630, DUKHENGP03DWARAP5620 | DUKHPROGEN00PRDV3470, DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3450, DUKHPROGEN00PRDV3440, DUKHPROGEN00PRDV3460 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5620 | First Floor Plan-App | 30 | 30 | 0% | 2013-03-02 | 2013-04-04 | 2013-03-02 | 2013-04-04 | 62 | No | DUKHENGP03DWARSM5620 | DUKHPROGEN00PRDV3040, DUKHENGP03DWARAP5690 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5610 | Ground Floor Plan-App | 30 | 30 | 0% | 2013-02-19 | 2013-03-25 | 2013-02-19 | 2013-03-25 | 90 | No | DUKHENGP03DWARSM5610 | DUKHPROGEN00PRDV3110, DUKHCONP1AMKARFF3300, DUKHPROGEN00PRDV3040, DUKHPROGEN00PRDV3420, DUKHPROGEN00PRDV3320, DUKHCONP03MKARFF3300, DUKHPROGEN00PRDV3480 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5670 | Gypsum False Ceiling Drawings-App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 67 | No | DUKHENGP03DWARSM5670 | DUKHPROGEN00PRDV3300 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5650 | Porcelain Floor Drawings-App | 30 | 30 | 0% | 2013-03-19 | 2013-04-22 | 2013-03-19 | 2013-04-22 | 57 | No | DUKHENGP03DWARSM5650 | DUKHPROGEN00PRDV3130 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWARAP5630 | Roof Floor Plan-App | 30 | 30 | 0% | 2013-03-10 | 2013-04-13 | 2013-03-10 | 2013-04-13 | 55 | No | DUKHENGP03DWARSM5630 | DUKHPROGEN00PRDV3050, DUKHPROGEN00PRDV3140, DUKHENGP03DWARAP5690 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L60.E05.H20 ELECTRICAL DRAWINGS |  | 95 | 95 | 0% | 2013-02-21 | 2013-06-11 | 2013-02-21 | 2013-06-11 | 75 |  |  |  | 0 | 0
DHBL.K20.L60.E05.H20.G10 SUBMISSION OF DRAWINGS |  | 65 | 65 | 0% | 2013-02-21 | 2013-05-07 | 2013-02-21 | 2013-05-07 | 75 |  |  |  | 0 | 0
DUKHENGP03DWELSM5750 | Audio Video Intercom System Drawings-Sub | 15 | 15 | 0% | 2013-04-03 | 2013-04-20 | 2013-04-03 | 2013-04-20 | 75 | No | DUKHENGP03DWELSM5740 | DUKHENGP03DWELAP5750, DUKHENGP03DWELSM5760 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWELSM5740 | Central Alarm Monitoring System Drawings-Sub | 15 | 15 | 0% | 2013-03-17 | 2013-04-02 | 2013-03-17 | 2013-04-02 | 75 | No | DUKHENGP03DWELSM5730 | DUKHENGP03DWELAP5740, DUKHENGP03DWELSM5750 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWELSM5720 | Lighting Layout Drawings-Sub | 15 | 15 | 0% | 2013-02-27 | 2013-03-16 | 2013-02-27 | 2013-03-16 | 59 | No | DUKHENGP03DWELSM5710 | DUKHENGP03DWELSM5730, DUKHENGP03DWELAP5720 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWELSM5730 | Power Layout Drawings-Sub | 15 | 15 | 0% | 2013-02-27 | 2013-03-16 | 2013-02-27 | 2013-03-16 | 75 | No | DUKHENGP03DWELSM5710, DUKHENGP03DWELSM5720 | DUKHENGP03DWELSM5740, DUKHENGP03DWELAP5730 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWELSM5710 | Single Line Diagram-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 59 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040 | DUKHENGP03DWELSM5730, DUKHENGP03DWELSM5720, DUKHENGP03DWELAP5710 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWELSM5760 | Telephone & TV System Drawings-Sub | 15 | 15 | 0% | 2013-04-21 | 2013-05-07 | 2013-04-21 | 2013-05-07 | 75 | No | DUKHENGP03DWELSM5750 | DUKHENGP03DWELAP5760 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L60.E05.H20.G20 APPROVAL OF DRAWINGS |  | 80 | 80 | 0% | 2013-03-11 | 2013-06-11 | 2013-03-11 | 2013-06-11 | 75 |  |  |  | 0 | 0
DUKHENGP03DWELAP5750 | Audio Video Intercom System Drawings-App | 30 | 30 | 0% | 2013-04-21 | 2013-05-25 | 2013-04-21 | 2013-05-25 | 90 | No | DUKHENGP03DWELSM5750 | DUKHPROGEN00PRDV3270 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWELAP5740 | Central Alarm Monitoring System Drawings-App | 30 | 30 | 0% | 2013-04-03 | 2013-05-07 | 2013-04-03 | 2013-05-07 | 99 | No | DUKHENGP03DWELSM5740 | DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3360, DUKHPROGEN00PRDV3260 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWELAP5720 | Lighting Layout Drawings-App | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 59 | No | DUKHENGP03DWELSM5720 | DUKHPROGEN00PRDV3190, DUKHPROGEN00PRDV3180 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWELAP5730 | Power Layout Drawings-App | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 110 | No | DUKHENGP03DWELSM5730 | DUKHPROGEN00PRDV3170, DUKHPROGEN00PRDV3200 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWELAP5710 | Single Line Diagram-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 115 | No | DUKHENGP03DWELSM5710 | DUKHPROGEN00PRDV3170 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWELAP5760 | Telephone & TV System Drawings-App | 30 | 30 | 0% | 2013-05-08 | 2013-06-11 | 2013-05-08 | 2013-06-11 | 75 | No | DUKHENGP03DWELSM5760 | DUKHPROGEN00PRDV3280, DUKHPROGEN00PRDV3290 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L60.E05.H30 PLUMBING,DRAINAGE,FIREFIGHTING & AC DRAWINGS |  | 75 | 75 | 0% | 2013-02-21 | 2013-05-19 | 2013-02-21 | 2013-05-19 | 130 |  |  |  | 0 | 0
DHBL.K20.L60.E05.H30.G10 SUBMISSION OF DRAWINGS |  | 45 | 45 | 0% | 2013-02-21 | 2013-04-14 | 2013-02-21 | 2013-04-14 | 45 |  |  |  | 0 | 0
DUKHENGP03DWMESM5800 | AC Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 45 | No | DUKHENGP03DWMESM5790, DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGI03DWDRSM5810, DUKHENGP03DWMEAP5800 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWMESM5780 | Drainage Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 45 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGP03DWMESM5790, DUKHENGP03DWMEAP5780 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWMESM5790 | Fire Fighting Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 45 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00PQAP1040, DUKHENGP03DWMESM5780 | DUKHENGP03DWMEAP5790, DUKHENGP03DWMESM5800 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGP03DWMESM5770 | Plumbing Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 53 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00PQAP2040 | DUKHENGP03DWMEAP5780, DUKHENGP03DWMEAP5770 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L60.E05.H30.G20 APPROVAL OF DRAWINGS |  | 60 | 60 | 0% | 2013-03-11 | 2013-05-19 | 2013-03-11 | 2013-05-19 | 130 |  |  |  | 0 | 0
DUKHENGP03DWMEAP5800 | AC Layout & Details Drawings-App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 64 | No | DUKHENGP03DWMESM5800 | DUKHPROGEN00PRDV3340, DUKHPROGEN00PRDV3160, DUKHPROGEN00PRDV3530, DUKHPROGEN00PRDV3240 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWMEAP5780 | Drainage Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP03DWMESM5770, DUKHENGP03DWMESM5780 | DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3080 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWMEAP5790 | Fire Fighting Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 145 | No | DUKHENGP03DWMESM5790 | DUKHPROGEN00PRDV3380, DUKHPROGEN00PRDV3370 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGP03DWMEAP5770 | Plumbing Layout & Details Drawings-App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 53 | No | DUKHENGP03DWMESM5770 | DUKHPROGEN00PRDV3680, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3230, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3640, DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3080, DUKHPROGEN00PRDV3520 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K20.L60.E05.H40 INFRA DRAWINGS |  | 127 | 127 | 0% | 2013-04-15 | 2013-09-12 | 2013-04-15 | 2013-09-12 | 170 |  |  |  | 0 | 0
DHBL.K20.L60.E05.H40.G10 SUBMISSION OF DRAWINGS |  | 82 | 82 | 0% | 2013-04-15 | 2013-07-18 | 2013-04-15 | 2013-07-18 | 185 |  |  |  | 0 | 0
DUKHENGI03DWBWSM5890 | Boundary Wall Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI03DWSLSM5880 | DUKHENGI03DWPSSM5900, DUKHENGI03DWBWAP5890 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWDRSM5810 | Drainage Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHPROGEN00PQAP1040, DUKHENGP03DWMESM5800, DUKHPROGEN00PQAP2040 | DUKHENGI03DWDRAP5810, DUKHENGI03DWWSSM5830 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWELSM5840 | Electrical Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHPROGEN00PQAP1040, DUKHENGI03DWFFSM5820, DUKHPROGEN00PQAP2040 | DUKHENGI03DWSTSM5850, DUKHENGI03DWELAP5840 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWFFSM5820 | Fire Fighting Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI03DWWSSM5830 | DUKHENGI03DWFFAP5820, DUKHENGI03DWELSM5840 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWGZSM5940 | Gazebo Plan & Details-Sub | 15 | 15 | 0% | 2013-07-02 | 2013-07-18 | 2013-07-02 | 2013-07-18 | 75 | No | DUKHENGI03DWTRSM5930 | DUKHENGI03DWGZAP5940 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWGHSM5950 | Guard House Plan & Details-Sub | 15 | 15 | 0% | 2013-07-02 | 2013-07-18 | 2013-07-02 | 2013-07-18 | 185 | No | DUKHENGI03DWTRSM5930 | DUKHENGI03DWGHAP5950 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWIRSM5870 | Irrigation Layout & Details-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI03DWWSSM5830, DUKHENGI03DWTCSM5860 | DUKHENGI03DWSLSM5880, DUKHENGI03DWIRAP5870 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWIWSM5920 | Irrigation Water Tank & Pump Room Details- Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI03DWRWSM5910 | DUKHENGI03DWIWAP5920, DUKHENGI03DWTRSM5930 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWPSSM5900 | Parking Shed Layout & Details Drawings-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI03DWBWSM5890 | DUKHENGI03DWPSAP5900, DUKHENGI03DWRWSM5910 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWRWSM5910 | Road Layout & Details-Sub | 15 | 15 | 0% | 2013-05-28 | 2013-06-13 | 2013-05-28 | 2013-06-13 | 49 | No | DUKHENGI03DWPSSM5900 | DUKHENGI03DWRWAP5910, DUKHENGI03DWIWSM5920 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWSLSM5880 | Soft & HardLandscaping Layout & Detail-Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 49 | No | DUKHENGI03DWIRSM5870 | DUKHENGI03DWSLAP5880, DUKHENGI03DWBWSM5890 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWSTSM5850 | Street Lighting Layout & details -Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI03DWELSM5840 | DUKHENGI03DWSTAP5850, DUKHENGI03DWTCSM5860 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWTCSM5860 | Telecommunication Line Layout & Details-Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 49 | No | DUKHENGI03DWSTSM5850 | DUKHENGI03DWTCAP5860, DUKHENGI03DWIRSM5870 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWTRSM5930 | Telephone Room Details-Sub | 15 | 15 | 0% | 2013-06-15 | 2013-07-01 | 2013-06-15 | 2013-07-01 | 60 | No | DUKHENGI03DWIWSM5920 | DUKHENGI03DWTRAP5930, DUKHENGI03DWGZSM5940, DUKHENGI03DWGHSM5950 | 0 | 0 | SUBMISSION OF DRAWINGS
DUKHENGI03DWWSSM5830 | Water Supply Line Layout & Details-Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 45 | No | DUKHENGI03DWDRSM5810 | DUKHENGI03DWIRSM5870, DUKHENGI03DWFFSM5820, DUKHENGI03DWWSAP5830 | 0 | 0 | SUBMISSION OF DRAWINGS
DHBL.K20.L60.E05.H40.G20 APPROVAL OF DRAWINGS |  | 112 | 112 | 0% | 2013-05-02 | 2013-09-12 | 2013-05-02 | 2013-09-12 | 170 |  |  |  | 0 | 0
DUKHENGI03DWBWAP5890 | Boundary Wall Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 85 | No | DUKHENGI03DWBWSM5890 | DUKHCONI03Z1BWGL5315, DUKHCONI03Z1RWGL6000, DUKHPROGEN00PRDV3820 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWDRAP5810 | Drainage Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 63 | No | DUKHENGI03DWDRSM5810 | DUKHPROGEN00PRDV3590, DUKHCONI03Z1DRGL5115, DUKHCONI1AZ1SAGL5135 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWELAP5840 | Electrical Line Layout & Details-App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 60 | No | DUKHENGI03DWELSM5840 | DUKHPROGEN00PRDV3350, DUKHENGI03DWSTAP5850, DUKHPROGEN00PRDV3250, DUKHCONI03Z1ELGL5215 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWFFAP5820 | Fire Fighting Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 45 | No | DUKHENGI03DWFFSM5820 | DUKHCONI03Z1FFGL5185, DUKHPROGEN00PRDV3690, DUKHPROGEN00PRDV3650, DUKHPROGEN00PRDV3540 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWGZAP5940 | Gazebo Plan & Details-App | 30 | 30 | 0% | 2013-08-06 | 2013-09-12 | 2013-08-06 | 2013-09-12 | 60 | No | DUKHENGI03DWGZSM5940, DUKHENGI03DWTRAP5930 | DUKHCONI03SBGZGL7900, DUKHPROGEN00PRDV3780 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWGHAP5950 | Guard House Plan & Details-App | 30 | 30 | 0% | 2013-08-06 | 2013-09-12 | 2013-08-06 | 2013-09-12 | 170 | No | DUKHENGI03DWTRAP5930, DUKHENGI03DWGHSM5950 | DUKHCONI03SBGHGL7800 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWIRAP5870 | Irrigation Layout & Details-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 91 | No | DUKHENGI03DWIRSM5870 | DUKHPROGEN00PRDV3840, DUKHPROGEN00PRDV3870, DUKHPROGEN00PRDV3760, DUKHCONI03Z1IRGL5265, DUKHPROGEN00PRDV3830, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3860, DUKHPROGEN00PRDV3670 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWIWAP5920 | Irrigation Water Tank & Pump Room Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 49 | No | DUKHENGI03DWIWSM5920 | DUKHPROGEN00PRDV3660, DUKHCONI03SBIWGL7400, DUKHPROGEN00PRDV3590 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWPSAP5900 | Parking Shed Layout & Details Drawings-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 150 | No | DUKHENGI03DWPSSM5900 | DUKHCONI03Z1PSGL7000, DUKHPROGEN00PRDV3730 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWRWAP5910 | Road Layout & Details-App | 30 | 30 | 0% | 2013-06-15 | 2013-07-18 | 2013-06-15 | 2013-07-18 | 149 | No | DUKHENGI03DWRWSM5910 | DUKHPROGEN00PRDV3700, DUKHPROGEN00PRDV3720, DUKHPROGEN00PRDV3750 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWSLAP5880 | Soft & HardLandscaping Layout & Detail-App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 67 | No | DUKHENGI03DWSLSM5880 | DUKHPROGEN00PRDV3790, DUKHCONI03Z1SLGL7200, DUKHCONI03Z1HDGL7020 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWSTAP5850 | Street Lighting Layout & details -App | 30 | 30 | 0% | 2013-06-24 | 2013-07-28 | 2013-06-24 | 2013-07-28 | 60 | No | DUKHENGI03DWSTSM5850, DUKHENGI03DWELAP5840 | DUKHENGI03DWTCAP5860, DUKHPROGEN00PRDV3350, DUKHCONI03Z1STGL5235, DUKHPROGEN00PRDV3250 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWTCAP5860 | Telecommunication Line Layout & Details-App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 60 | No | DUKHENGI03DWSTAP5850, DUKHENGI03DWTCSM5860 | DUKHPROGEN00PRDV3250, DUKHCONI03Z1TCGL5295 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWTRAP5930 | Telephone Room Details-App | 30 | 30 | 0% | 2013-07-02 | 2013-08-05 | 2013-07-02 | 2013-08-05 | 60 | No | DUKHENGI03DWTRSM5930 | DUKHENGI03DWGHAP5950, DUKHENGI03DWGZAP5940, DUKHCONI03SBTRGL7600 | 0 | 0 | APPROVAL OF DRAWINGS
DUKHENGI03DWWSAP5830 | Water Supply Line Layout & Details-App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 86 | No | DUKHENGI03DWWSSM5830 | DUKHPROGEN00PRDV3590, DUKHCONI03Z1WSGL5155 | 0 | 0 | APPROVAL OF DRAWINGS
DHBL.K25 PROCUREMENT |  | 471 | 471 | 0% | 2012-11-01 | 2014-02-14 | 2012-11-01 | 2014-02-14 | 140 |  |  |  | 0 | 0
DHBL.K25.L15 PREQUALIFICATION, SUBMITTAL AND APPROVAL |  | 159 | 159 | 0% | 2012-11-01 | 2013-05-07 | 2012-11-01 | 2013-05-07 | 55 |  |  |  | 0 | 0
DHBL.K25.L15.10 1ST SUBMISSION OF PREQUALIFICATION |  | 89 | 89 | 0% | 2012-11-01 | 2013-02-14 | 2012-11-01 | 2013-02-14 | 55 |  |  |  | 0 | 0
DUKHPROGEN00PQSM1080 | Aluminum Doors & Windows_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-09 | 2012-12-26 | 2012-12-09 | 2012-12-26 | 26 | No | DUKHPROGEN00PQSM1050 | DUKHPROGEN00PQSM1070, DUKHPROGEN00PQAP1080, DUKHPROGEN00PQSM1090, DUKHPROGEN00PQSM1150 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1000 | Anti Termite Treatment_Prequa. 1st Sub. | 7 | 7 | 0% | 2012-11-01 | 2012-11-08 | 2012-11-01 | 2012-11-08 | 4 | No | DUKHKYDGEN0000001000 | DUKHPROGEN00PQAP1000, DUKHPROGEN00PQSM1010 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1120 | Car Parking Shed_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-24 | 2013-01-09 | 2012-12-24 | 2013-01-09 | 22 | No | DUKHPROGEN00PQSM1110 | DUKHPROGEN00PQSM1160, DUKHPROGEN00PQAP1120 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1150 | Carpentry & Joinery Works_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-27 | 2013-01-13 | 2012-12-27 | 2013-01-13 | 43 | No | DUKHPROGEN00PQSM1080 | DUKHPROGEN00PQAP1150 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1050 | Ceiling Works_Prequa. 1st Sub. | 16 | 16 | 0% | 2012-11-27 | 2012-12-15 | 2012-11-27 | 2012-12-15 | 10 | No | DUKHPROGEN00PQSM1030 | DUKHPROGEN00PQAP1080, DUKHPROGEN00PQAP1050, DUKHPROGEN00PQSM1080, DUKHPROGEN00PQAP1070 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1010 | Concrete_Prequa. 1st Sub. | 8 | 8 | 0% | 2012-11-01 | 2012-11-10 | 2012-11-01 | 2012-11-10 | 4 | No | DUKHPROGEN00PQSM1000 | DUKHPROGEN00PQSM1020, DUKHPROGEN00PQSM1040, DUKHPROGEN00PQAP1010 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1090 | Granite_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-09 | 2012-12-26 | 2012-12-09 | 2012-12-26 | 46 | No | DUKHPROGEN00PQSM1080 | DUKHPROGEN00PQAP1090 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1060 | GRC Panels_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-11-27 | 2012-12-13 | 2012-11-27 | 2012-12-13 | 22 | No | DUKHPROGEN00PQSM1040 | DUKHPROGEN00PQSM1100, DUKHPROGEN00PQAP1060 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1040 | MEPD_Prequa. 1st Sub. | 14 | 14 | 0% | 2012-11-11 | 2012-11-26 | 2012-11-11 | 2012-11-26 | 4 | No | DUKHPROGEN00PQSM1010 | DUKHPROGEN00PQSM1060, DUKHPROGEN00PQAP1040 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1170 | Pre-cast Boundary Wall _Prequa. 1st Sub. | 15 | 15 | 0% | 2013-01-10 | 2013-01-27 | 2013-01-10 | 2013-01-27 | 70 | No | DUKHPROGEN00PQSM1160 | DUKHPROGEN00PQAP1170 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1140 | PVC Tent_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-24 | 2013-01-09 | 2012-12-24 | 2013-01-09 | 28 | No | DUKHPROGEN00PQSM1110 | DUKHPROGEN00PQAP1140 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1180 | Road Works _Prequa. 1st Sub. | 15 | 15 | 0% | 2013-01-28 | 2013-02-14 | 2013-01-28 | 2013-02-14 | 22 | No | DUKHPROGEN00PQSM1160 | DUKHPROGEN00PQAP1180 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1100 | Roller Shutter_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-05 | 2012-12-23 | 2012-12-05 | 2012-12-23 | 22 | No | DUKHPROGEN00PQSM1060 | DUKHPROGEN00PQAP1100, DUKHPROGEN00PQSM1130, DUKHPROGEN00PQSM1110 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1160 | Soft landscaping /Irrigation _Prequa. 1st Sub. | 15 | 15 | 0% | 2013-01-10 | 2013-01-27 | 2013-01-10 | 2013-01-27 | 22 | No | DUKHPROGEN00PQSM1120 | DUKHPROGEN00PQSM1170, DUKHPROGEN00PQSM1180, DUKHPROGEN00PQAP1160 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1130 | Steel Door_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-24 | 2013-01-09 | 2012-12-24 | 2013-01-09 | 85 | No | DUKHPROGEN00PQSM1110, DUKHPROGEN00PQSM1100 | DUKHPROGEN00PQAP1130 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1110 | Structural Steel works_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-24 | 2013-01-09 | 2012-12-24 | 2013-01-09 | 22 | No | DUKHPROGEN00PQSM1100 | DUKHPROGEN00PQSM1140, DUKHPROGEN00PQAP1110, DUKHPROGEN00PQSM1130, DUKHPROGEN00PQSM1120 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1030 | Waterproofing -Roof_Prequa. 1st Sub. | 14 | 14 | 0% | 2012-11-11 | 2012-11-26 | 2012-11-11 | 2012-11-26 | 10 | No | DUKHPROGEN00PQSM1020 | DUKHPROGEN00PQAP1030, DUKHPROGEN00PQSM1050 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1020 | Waterproofing -Wet Area _Prequa. 1st Sub. | 14 | 14 | 0% | 2012-11-11 | 2012-11-26 | 2012-11-11 | 2012-11-26 | 10 | No | DUKHPROGEN00PQSM1010 | DUKHPROGEN00PQSM1030, DUKHPROGEN00PQAP1020 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM1070 | Wooden Doors_Prequa. 1st Sub. | 15 | 15 | 0% | 2012-12-09 | 2012-12-26 | 2012-12-09 | 2012-12-26 | 26 | No | DUKHPROGEN00PQSM1080 | DUKHPROGEN00PQAP1070 | 0 | 0 | 1ST SUBMISSION OF PREQUALIFICATION
DHBL.K25.L15.15 1ST APPROVAL OF PREQUALIFICATION |  | 112 | 112 | 0% | 2012-11-10 | 2013-03-21 | 2012-11-10 | 2013-03-21 | 55 |  |  |  | 0 | 0
DUKHPROGEN00PQAP1080 | Aluminum Doors & Windows_Prequa. 1st App. | 30 | 30 | 0% | 2012-12-27 | 2013-01-30 | 2012-12-27 | 2013-01-30 | 26 | No | DUKHPROGEN00PQSM1050, DUKHPROGEN00PQSM1080 | DUKHPROGEN00PQSM2080, DUKHENGP1BDWARSM4530, DUKHENGP2BDWARSM5310, DUKHENGP1ADWARSM4130, DUKHENGP2ADWARSM4930, DUKHENGP03DWARSM5690 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1000 | Anti Termite Treatment_Prequa. 1st App. | 15 | 15 | 0% | 2012-11-10 | 2012-11-26 | 2012-11-10 | 2012-11-26 | 45 | No | DUKHPROGEN00PQSM1000 | DUKHPROGEN00MTSM1000 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1120 | Car Parking Shed_Prequa. 1st App. | 30 | 30 | 0% | 2013-01-10 | 2013-02-14 | 2013-01-10 | 2013-02-14 | 70 | No | DUKHPROGEN00PQSM1120 | DUKHPROGEN00PQSM2120 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1150 | Carpentry & Joinery Works_Prequa. 1st App. | 30 | 30 | 0% | 2013-01-14 | 2013-02-18 | 2013-01-14 | 2013-02-18 | 43 | No | DUKHPROGEN00PQSM1150 | DUKHENGP03DWARSM5700, DUKHENGP2ADWARSM4940, DUKHPROGEN00PQSM2150, DUKHENGP1ADWARSM4140, DUKHENGP2BDWARSM5320, DUKHENGP1BDWARSM4540 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1050 | Ceiling Works_Prequa. 1st App. | 30 | 30 | 0% | 2012-12-16 | 2013-01-20 | 2012-12-16 | 2013-01-20 | 10 | No | DUKHPROGEN00PQSM1050 | DUKHENGP03DWARSM5680, DUKHPROGEN00PQSM2050, DUKHENGP1BDWARSM4490, DUKHENGP1BDWARSM4480, DUKHENGP1ADWARSM4120, DUKHENGP1ADWARSM4110, DUKHENGP2BDWARSM5290, DUKHENGP03DWARSM5670, DUKHENGP2ADWARSM4910 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1010 | Concrete_Prequa. 1st App. | 15 | 15 | 0% | 2012-11-11 | 2012-11-27 | 2012-11-11 | 2012-11-27 | 39 | No | DUKHPROGEN00PQSM1010 | DUKHPROGEN00MTSM1020 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1090 | Granite_Prequa. 1st App. | 30 | 30 | 0% | 2012-12-27 | 2013-01-30 | 2012-12-27 | 2013-01-30 | 46 | No | DUKHPROGEN00PQSM1090 | DUKHPROGEN00PQSM2090 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1060 | GRC Panels_Prequa. 1st App. | 30 | 30 | 0% | 2012-12-15 | 2013-01-19 | 2012-12-15 | 2013-01-19 | 63 | No | DUKHPROGEN00PQSM1060 | DUKHPROGEN00PQSM2060 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1040 | MEPD_Prequa. 1st App. | 30 | 30 | 0% | 2012-11-27 | 2013-01-01 | 2012-11-27 | 2013-01-01 | 4 | No | DUKHPROGEN00PQSM1040 | DUKHENGP1ADWELSM4150, DUKHENGI1ADWELSM4280, DUKHENGP2BDWMESM5390, DUKHENGP1BDWMESM4610, DUKHENGI1ADWDRSM4250, DUKHENGP2ADWMESM5040, DUKHENGI03DWDRSM5810, DUKHENGP2BDWMESM5410, DUKHENGP1ADWMESM4240, DUKHENGI1BDWELSM4680, DUKHENGI03DWELSM5840, DUKHENGP2ADWMESM5010, DUKHENGP03DWMESM5790, DUKHPROGEN00MTSM1070, DUKHENGI2ADWDRSM5050, DUKHENGP1ADWMESM4230, DUKHENGI2ADWELSM5080, DUKHENGP03DWMESM5770, DUKHENGI2BDWELSM5460, DUKHENGP2BDWELSM5330, DUKHENGP1BDWELSM4550, DUKHPROGEN00MTSM1060, DUKHENGP1ADWMESM4210, DUKHENGP03DWMESM5780, DUKHENGP03DWELSM5710, DUKHENGP2BDWMESM5400, DUKHENGP1BDWMESM4630, DUKHENGP03DWMESM5800, DUKHENGP2ADWELSM4950, DUKHPROGEN00MTSM1080, DUKHENGI2BDWDRSM5430, DUKHENGP2BDWMESM5420, DUKHPROGEN00PQSM2040, DUKHENGP2ADWMESM5020, DUKHENGP1BDWMESM4620, DUKHENGP1BDWMESM4640, DUKHENGP1ADWMESM4220, DUKHENGP2ADWMESM5030, DUKHENGI1BDWDRSM4650 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1170 | Pre-cast Boundary Wall _Prequa. 1st App. | 30 | 30 | 0% | 2013-01-28 | 2013-03-04 | 2013-01-28 | 2013-03-04 | 70 | No | DUKHPROGEN00PQSM1170 | DUKHPROGEN00PQSM2170 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1140 | PVC Tent_Prequa. 1st App. | 30 | 30 | 0% | 2013-01-10 | 2013-02-14 | 2013-01-10 | 2013-02-14 | 28 | No | DUKHPROGEN00PQSM1140 | DUKHPROGEN00PQSM2140 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1180 | Road Works _Prequa. 1st App. | 30 | 30 | 0% | 2013-02-16 | 2013-03-21 | 2013-02-16 | 2013-03-21 | 22 | No | DUKHPROGEN00PQSM1180 | DUKHPROGEN00PQSM2180 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1100 | Roller Shutter_Prequa. 1st App. | 30 | 30 | 0% | 2012-12-24 | 2013-01-27 | 2012-12-24 | 2013-01-27 | 29 | No | DUKHPROGEN00PQSM1100 | DUKHPROGEN00PQSM2100 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1160 | Soft landscaping /Irrigation _Prequa. 1st App. | 30 | 30 | 0% | 2013-01-28 | 2013-03-04 | 2013-01-28 | 2013-03-04 | 37 | No | DUKHPROGEN00PQSM1160 | DUKHPROGEN00PQSM2160 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1130 | Steel Door_Prequa. 1st App. | 30 | 30 | 0% | 2013-01-10 | 2013-02-14 | 2013-01-10 | 2013-02-14 | 85 | No | DUKHPROGEN00PQSM1130 | DUKHPROGEN00PQSM2130 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1110 | Structural Steel works_Prequa. 1st App. | 30 | 30 | 0% | 2013-01-10 | 2013-02-14 | 2013-01-10 | 2013-02-14 | 40 | No | DUKHPROGEN00PQSM1110 | DUKHPROGEN00PQSM2110 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1030 | Waterproofing -Roof_Prequa. 1st App. | 15 | 15 | 0% | 2012-11-27 | 2012-12-13 | 2012-11-27 | 2012-12-13 | 38 | No | DUKHPROGEN00PQSM1030 | DUKHPROGEN00MTSM1030 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1020 | Waterproofing -Wet Area _Prequa. 1st App. | 15 | 15 | 0% | 2012-11-27 | 2012-12-13 | 2012-11-27 | 2012-12-13 | 38 | No | DUKHPROGEN00PQSM1020 | DUKHPROGEN00MTSM1030 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP1070 | Wooden Doors_Prequa. 1st App. | 30 | 30 | 0% | 2012-12-27 | 2013-01-30 | 2012-12-27 | 2013-01-30 | 26 | No | DUKHPROGEN00PQSM1070, DUKHPROGEN00PQSM1050 | DUKHPROGEN00PQSM2070 | 0 | 0 | 1ST APPROVAL OF PREQUALIFICATION
DHBL.K25.L15.20 2ND SUBMISSION OF PREQUALIFICATION |  | 77 | 77 | 0% | 2013-01-02 | 2013-04-02 | 2013-01-02 | 2013-04-02 | 55 |  |  |  | 0 | 0
DUKHPROGEN00PQSM2080 | Aluminum Doors & Windows_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-01-31 | 2013-02-11 | 2013-01-31 | 2013-02-11 | 26 | No | DUKHPROGEN00PQAP1080 | DUKHPROGEN00PQAP2080 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2120 | Car Parking Shed_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-02-16 | 2013-02-26 | 2013-02-16 | 2013-02-26 | 70 | No | DUKHPROGEN00PQAP1120 | DUKHPROGEN00PQAP2120 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2150 | Carpentry & Joinery Works_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-02-19 | 2013-03-02 | 2013-02-19 | 2013-03-02 | 43 | No | DUKHPROGEN00PQAP1150 | DUKHPROGEN00PQAP2150 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2050 | Ceiling Works_Prequa. 2nd Sub. | 14 | 14 | 0% | 2013-01-21 | 2013-02-05 | 2013-01-21 | 2013-02-05 | 10 | No | DUKHPROGEN00PQAP1050 | DUKHPROGEN00PQAP2050 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2090 | Granite_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-01-31 | 2013-02-11 | 2013-01-31 | 2013-02-11 | 46 | No | DUKHPROGEN00PQAP1090 | DUKHPROGEN00PQAP2090 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2060 | GRC Panels_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-01-20 | 2013-01-30 | 2013-01-20 | 2013-01-30 | 63 | No | DUKHPROGEN00PQAP1060 | DUKHPROGEN00PQAP2060 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2040 | MEPD_Prequa. 2nd Sub. | 12 | 12 | 0% | 2013-01-02 | 2013-01-15 | 2013-01-02 | 2013-01-15 | 4 | No | DUKHPROGEN00PQAP1040 | DUKHPROGEN00PQAP2040 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2170 | Pre-cast Boundary Wall _Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-03-05 | 2013-03-16 | 2013-03-05 | 2013-03-16 | 70 | No | DUKHPROGEN00PQAP1170 | DUKHPROGEN00PQAP2170 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2140 | PVC Tent_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-02-16 | 2013-02-26 | 2013-02-16 | 2013-02-26 | 28 | No | DUKHPROGEN00PQAP1140 | DUKHPROGEN00PQAP2140 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2180 | Road Works _Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-03-23 | 2013-04-02 | 2013-03-23 | 2013-04-02 | 22 | No | DUKHPROGEN00PQAP1180 | DUKHPROGEN00PQAP2180 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2100 | Roller Shutter_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-01-28 | 2013-02-07 | 2013-01-28 | 2013-02-07 | 29 | No | DUKHPROGEN00PQAP1100 | DUKHPROGEN00PQAP2100 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2160 | Soft landscaping /Irrigation _Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-03-05 | 2013-03-16 | 2013-03-05 | 2013-03-16 | 37 | No | DUKHPROGEN00PQAP1160 | DUKHPROGEN00PQAP2160 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2130 | Steel Door_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-02-16 | 2013-02-26 | 2013-02-16 | 2013-02-26 | 85 | No | DUKHPROGEN00PQAP1130 | DUKHPROGEN00PQAP2130 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2110 | Structural Steel works_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-02-16 | 2013-02-26 | 2013-02-16 | 2013-02-26 | 40 | No | DUKHPROGEN00PQAP1110 | DUKHPROGEN00PQAP2110 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DUKHPROGEN00PQSM2070 | Wooden Doors_Prequa. 2nd Sub. | 10 | 10 | 0% | 2013-01-31 | 2013-02-11 | 2013-01-31 | 2013-02-11 | 26 | No | DUKHPROGEN00PQAP1070 | DUKHPROGEN00PQAP2070 | 0 | 0 | 2ND SUBMISSION OF PREQUALIFICATION
DHBL.K25.L15.25 2ND APPROVAL OF PREQUALIFICATION |  | 95 | 95 | 0% | 2013-01-16 | 2013-05-07 | 2013-01-16 | 2013-05-07 | 55 |  |  |  | 0 | 0
DUKHPROGEN00PQAP2080 | Aluminum Doors & Windows_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-13 | 2013-03-19 | 2013-02-13 | 2013-03-19 | 26 | No | DUKHPROGEN00PQSM2080 | DUKHENGP1BDWARSM4530, DUKHENGP2ADWARSM4930, DUKHENGP2BDWARSM5310, DUKHPROGEN00MTSM1450, DUKHENGP03DWARSM5690, DUKHPROGEN00MTSM1470, DUKHPROGEN00MTSM1460, DUKHENGP1ADWARSM4130, DUKHPROGEN00MTSM1440 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2120 | Car Parking Shed_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-27 | 2013-04-02 | 2013-02-27 | 2013-04-02 | 70 | No | DUKHPROGEN00PQSM2120 | DUKHPROGEN00MTSM1730 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2150 | Carpentry & Joinery Works_Prequa. 2nd App. | 30 | 30 | 0% | 2013-03-03 | 2013-04-06 | 2013-03-03 | 2013-04-06 | 43 | No | DUKHPROGEN00PQSM2150 | DUKHPROGEN00MTSM1570, DUKHPROGEN00MTSM1560, DUKHENGP03DWARSM5700, DUKHENGP2BDWARSM5320, DUKHENGP2ADWARSM4940, DUKHENGP1BDWARSM4540, DUKHENGP1ADWARSM4140, DUKHPROGEN00MTSM1550 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2050 | Ceiling Works_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-06 | 2013-03-13 | 2013-02-06 | 2013-03-13 | 10 | No | DUKHPROGEN00PQSM2050 | DUKHENGP03DWARSM5680, DUKHENGP03DWARSM5670, DUKHENGP1ADWARSM4110, DUKHENGP2BDWARSM5290, DUKHENGP2ADWARSM4910, DUKHENGP1BDWARSM4480, DUKHENGP1ADWARSM4120, DUKHENGP1BDWARSM4490, DUKHPROGEN00MTSM1310, DUKHPROGEN00MTSM1300 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2090 | Granite_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-13 | 2013-03-19 | 2013-02-13 | 2013-03-19 | 46 | No | DUKHPROGEN00PQSM2090 | DUKHPROGEN00MTSM1480 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2060 | GRC Panels_Prequa. 2nd App. | 30 | 30 | 0% | 2013-01-31 | 2013-03-07 | 2013-01-31 | 2013-03-07 | 63 | No | DUKHPROGEN00PQSM2060 | DUKHPROGEN00MTSM1390 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2040 | MEPD_Prequa. 2nd App. | 30 | 30 | 0% | 2013-01-16 | 2013-02-20 | 2013-01-16 | 2013-02-20 | 4 | No | DUKHPROGEN00PQSM2040 | DUKHPROGEN00MTSM1180, DUKHPROGEN00MTSM1680, DUKHENGP1ADWMESM4210, DUKHPROGEN00MTSM1340, DUKHENGI1ADWDRSM4250, DUKHENGP03DWMESM5790, DUKHENGP2BDWMESM5390, DUKHENGP2ADWMESM5040, DUKHPROGEN00MTSM1270, DUKHPROGEN00MTSM1330, DUKHENGP1ADWMESM4230, DUKHENGP2ADWMESM5010, DUKHENGP2BDWMESM5400, DUKHENGI2BDWDRSM5430, DUKHENGP2ADWELSM4950, DUKHPROGEN00MTSM1240, DUKHPROGEN00MTSM1160, DUKHPROGEN00MTSM1530, DUKHPROGEN00MTSM1380, DUKHENGP1BDWMESM4620, DUKHENGI2BDWELSM5460, DUKHENGP1ADWELSM4150, DUKHPROGEN00MTSM1290, DUKHENGI1BDWDRSM4650, DUKHENGP1BDWELSM4550, DUKHPROGEN00MTSM1190, DUKHPROGEN00MTSM1690, DUKHPROGEN00MTSM1520, DUKHPROGEN00MTSM1220, DUKHENGI1ADWELSM4280, DUKHENGI03DWELSM5840, DUKHENGP03DWELSM5710, DUKHPROGEN00MTSM1640, DUKHPROGEN00MTSM1200, DUKHENGP2ADWMESM5030, DUKHENGP1ADWMESM4240, DUKHPROGEN00MTSM1350, DUKHPROGEN00MTSM1370, DUKHENGP2BDWMESM5410, DUKHENGP2ADWMESM5020, DUKHENGP2BDWELSM5330, DUKHPROGEN00MTSM1280, DUKHENGI1BDWELSM4680, DUKHENGI03DWDRSM5810, DUKHENGI2ADWELSM5080, DUKHPROGEN00MTSM1210, DUKHPROGEN00MTSM1770, DUKHENGP03DWMESM5770, DUKHPROGEN00MTSM1150, DUKHENGP1BDWMESM4630, DUKHPROGEN00MTSM1540, DUKHENGP1ADWMESM4220, DUKHPROGEN00MTSM1260, DUKHENGI2ADWDRSM5050, DUKHPROGEN00MTSM1170, DUKHENGP1BDWMESM4610, DUKHENGP03DWMESM5800, DUKHENGP1BDWMESM4640, DUKHENGP2BDWMESM5420, DUKHPROGEN00MTSM1230, DUKHPROGEN00MTSM1250, DUKHPROGEN00MTSM1360, DUKHENGP03DWMESM5780, DUKHPROGEN00MTSM1650 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2170 | Pre-cast Boundary Wall _Prequa. 2nd App. | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 70 | No | DUKHPROGEN00PQSM2170 | DUKHPROGEN00MTSM1820 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2140 | PVC Tent_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-27 | 2013-04-02 | 2013-02-27 | 2013-04-02 | 28 | No | DUKHPROGEN00PQSM2140 | DUKHPROGEN00MTSM1610 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2180 | Road Works _Prequa. 2nd App. | 30 | 30 | 0% | 2013-04-03 | 2013-05-07 | 2013-04-03 | 2013-05-07 | 22 | No | DUKHPROGEN00PQSM2180 | DUKHPROGEN00MTSM1700 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2100 | Roller Shutter_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-09 | 2013-03-16 | 2013-02-09 | 2013-03-16 | 29 | No | DUKHPROGEN00PQSM2100 | DUKHPROGEN00MTSM1430 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2160 | Soft landscaping /Irrigation _Prequa. 2nd App. | 30 | 30 | 0% | 2013-03-17 | 2013-04-20 | 2013-03-17 | 2013-04-20 | 37 | No | DUKHPROGEN00PQSM2160 | DUKHPROGEN00MTSM1870, DUKHPROGEN00MTSM1830, DUKHPROGEN00MTSM1840, DUKHPROGEN00MTSM1860, DUKHPROGEN00MTSM1760, DUKHPROGEN00MTSM1810, DUKHPROGEN00MTSM1670, DUKHPROGEN00MTSM1790 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2130 | Steel Door_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-27 | 2013-04-02 | 2013-02-27 | 2013-04-02 | 85 | No | DUKHPROGEN00PQSM2130 | DUKHPROGEN00MTSM1800 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2110 | Structural Steel works_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-27 | 2013-04-02 | 2013-02-27 | 2013-04-02 | 40 | No | DUKHPROGEN00PQSM2110 | DUKHPROGEN00MTSM1600 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DUKHPROGEN00PQAP2070 | Wooden Doors_Prequa. 2nd App. | 30 | 30 | 0% | 2013-02-13 | 2013-03-19 | 2013-02-13 | 2013-03-19 | 26 | No | DUKHPROGEN00PQSM2070 | DUKHPROGEN00MTSM1490 | 0 | 0 | 2ND APPROVAL OF PREQUALIFICATION
DHBL.K25.L20 MATERIAL SUBMITTAL AND APPROVAL |  | 297 | 297 | 0% | 2012-11-27 | 2013-11-16 | 2012-11-27 | 2013-11-16 | 114 |  |  |  | 0 | 0
DHBL.K25.L20.10 1ST SUBMISSION OF MATERIAL |  | 227 | 227 | 0% | 2012-11-27 | 2013-08-24 | 2012-11-27 | 2013-08-24 | 97 |  |  |  | 0 | 0
DUKHPROGEN00MTSM1400 | Access Ladder_1st_Sub | 15 | 15 | 0% | 2013-03-09 | 2013-03-25 | 2013-03-09 | 2013-03-25 | 63 | No | DUKHPROGEN00MTSM1390 | DUKHPROGEN00MTAP1400, DUKHPROGEN00MTSM1590 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1470 | Aluminum Windows_1st_Sub | 10 | 10 | 0% | 2013-03-20 | 2013-03-31 | 2013-03-20 | 2013-03-31 | 71 | No | DUKHPROGEN00PQAP2080 | DUKHPROGEN00MTAP1470 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1460 | Aluminum Doors _1st_Sub | 10 | 10 | 0% | 2013-03-20 | 2013-03-31 | 2013-03-20 | 2013-03-31 | 65 | No | DUKHPROGEN00PQAP2080 | DUKHPROGEN00MTAP1460 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1410 | Aluminum Slat Screen_1st_Sub | 15 | 15 | 0% | 2013-03-09 | 2013-03-25 | 2013-03-09 | 2013-03-25 | 81 | No | DUKHPROGEN00MTSM1390 | DUKHPROGEN00MTAP1410 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1310 | Aluminum Tile false ceiling_1st_Sub | 15 | 15 | 0% | 2013-03-14 | 2013-03-31 | 2013-03-14 | 2013-03-31 | 42 | No | DUKHPROGEN00PQAP2050 | DUKHPROGEN00MTAP1310 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1000 | Anti Termite _1st_Sub | 10 | 10 | 0% | 2012-11-27 | 2012-12-08 | 2012-11-27 | 2012-12-08 | 45 | No | DUKHPROGEN00PQAP1000 | DUKHPROGEN00MTAP1000, DUKHPROGEN00MTSM1010 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1010 | Block Work_1st_Sub | 10 | 10 | 0% | 2012-11-27 | 2012-12-08 | 2012-11-27 | 2012-12-08 | 59 | No | DUKHPROGEN00MTSM1000 | DUKHPROGEN00MTAP1010, DUKHPROGEN00MTSM1040 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1350 | Bollard Lamp_1st_Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 110 | No | DUKHPROGEN00MTSM1250, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1350 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1330 | Booster Pump_1st_Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 9 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1150, DUKHPROGEN00MTSM1220 | DUKHPROGEN00MTAP1330, DUKHPROGEN00MTSM1520 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1180 | Cables & Wires_1st_Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 49 | No | DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1180, DUKHPROGEN00MTSM1250, DUKHPROGEN00MTSM1210 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1730 | Car Parking Shed_1st_Sub | 15 | 15 | 0% | 2013-05-08 | 2013-05-25 | 2013-05-08 | 2013-05-25 | 40 | No | DUKHPROGEN00PQAP2120, DUKHPROGEN00MTSM1660 | DUKHPROGEN00MTAP1730, DUKHPROGEN00MTSM1800 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1120 | Ceramic Tile_1st_Sub | 15 | 15 | 0% | 2012-12-13 | 2012-12-31 | 2012-12-13 | 2012-12-31 | 73 | No | DUKHPROGEN00MTSM1110 | DUKHPROGEN00MTSM1130, DUKHPROGEN00MTAP1120 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1550 | Closets /wardrobe& Pelmets_1st_Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 43 | No | DUKHPROGEN00PQAP2150 | DUKHPROGEN00MTAP1550 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1090 | Cobble stone finish _1st_Sub | 15 | 15 | 0% | 2012-12-13 | 2012-12-31 | 2012-12-13 | 2012-12-31 | 73 | No | DUKHPROGEN00MTSM1040 | DUKHPROGEN00MTAP1090, DUKHPROGEN00MTSM1100 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1020 | Concrete_1st_Sub | 10 | 10 | 0% | 2012-11-28 | 2012-12-09 | 2012-11-28 | 2012-12-09 | 39 | No | DUKHPROGEN00PQAP1010 | DUKHPROGEN00MTAP1020 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1160 | Copper Pipes_1st_Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 54 | No | DUKHPROGEN00MTSM1080, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1160, DUKHPROGEN00MTSM1340, DUKHPROGEN00MTSM1240, DUKHPROGEN00MTSM1530 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1560 | Counters, Cabinets & Shelves_1st_Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 43 | No | DUKHPROGEN00PQAP2150 | DUKHPROGEN00MTAP1560 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1360 | Digital Alarm Communicator Panel_1st_Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 49 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1260 | DUKHPROGEN00MTAP1360 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1540 | Ductile Iron Pipes_1st_Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 4 | No | DUKHPROGEN00MTSM1380, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTSM1650, DUKHPROGEN00MTAP1540 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1420 | Epoxy_1st_Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 134 | No | DUKHPROGEN00MTSM1320 | DUKHPROGEN00MTAP1420 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1340 | Exhaust Air louver_1st_Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 61 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1240, DUKHPROGEN00MTSM1160 | DUKHPROGEN00MTSM1530, DUKHPROGEN00MTAP1340 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1530 | Exhaust Fan_1st_Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 61 | No | DUKHPROGEN00MTSM1340, DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1160 | DUKHPROGEN00MTAP1530 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1710 | External signage _1st_Sub | 15 | 15 | 0% | 2013-05-08 | 2013-05-25 | 2013-05-08 | 2013-05-25 | 172 | No | DUKHPROGEN00MTSM1700 | DUKHPROGEN00MTAP1710 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1850 | Fences_1st_Sub | 15 | 15 | 0% | 2013-06-12 | 2013-06-29 | 2013-06-12 | 2013-06-29 | 126 | No | DUKHPROGEN00MTSM1820, DUKHPROGEN00MTSM1820 | DUKHPROGEN00MTAP1850 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1370 | Fire Blanket_1st_Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 4 | No | DUKHPROGEN00MTSM1230, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1370, DUKHPROGEN00MTSM1380 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1380 | Fire Extinguisher_1st_Sub | 15 | 15 | 0% | 2013-03-28 | 2013-04-14 | 2013-03-28 | 2013-04-14 | 4 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1370 | DUKHPROGEN00MTSM1540, DUKHPROGEN00MTAP1380 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1690 | Fire Hydrant_1st_Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 15 | No | DUKHPROGEN00MTSM1650, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1690 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1210 | Fire Resistant Cables_1st_Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 49 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1180 | DUKHPROGEN00MTSM1270, DUKHPROGEN00MTAP1210, DUKHPROGEN00MTSM1260 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1070 | Floor drains & Cleanouts_1st_Sub | 15 | 15 | 0% | 2013-01-02 | 2013-01-19 | 2013-01-02 | 2013-01-19 | 28 | No | DUKHPROGEN00MTSM1060, DUKHPROGEN00PQAP1040 | DUKHPROGEN00MTAP1070, DUKHPROGEN00MTSM1080 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1840 | Gate Values_1st_Sub | 15 | 15 | 0% | 2013-06-30 | 2013-07-16 | 2013-06-30 | 2013-07-16 | 37 | No | DUKHPROGEN00PQAP2160, DUKHPROGEN00MTSM1830 | DUKHPROGEN00MTAP1840, DUKHPROGEN00MTSM1860 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1780 | Gazebo Structure_1st_Sub | 15 | 15 | 0% | 2013-05-26 | 2013-06-11 | 2013-05-26 | 2013-06-11 | 67 | No | DUKHPROGEN00MTSM1700 | DUKHPROGEN00MTAP1780 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1480 | Granite_1st_Sub | 10 | 10 | 0% | 2013-03-20 | 2013-03-31 | 2013-03-20 | 2013-03-31 | 46 | No | DUKHPROGEN00MTSM1130, DUKHPROGEN00PQAP2090 | DUKHPROGEN00MTAP1480 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1390 | GRC Panels_1st_Sub | 15 | 15 | 0% | 2013-03-09 | 2013-03-25 | 2013-03-09 | 2013-03-25 | 63 | No | DUKHPROGEN00PQAP2060 | DUKHPROGEN00MTAP1390, DUKHPROGEN00MTSM1410, DUKHPROGEN00MTSM1400 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1300 | Gypsum Board false ceiling_1st_Sub | 10 | 10 | 0% | 2013-03-14 | 2013-03-25 | 2013-03-14 | 2013-03-25 | 10 | No | DUKHPROGEN00PQAP2050 | DUKHPROGEN00MTAP1300, DUKHPROGEN00MTSM1320 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1660 | Interlock works_1st_Sub | 15 | 15 | 0% | 2013-04-21 | 2013-05-07 | 2013-04-21 | 2013-05-07 | 40 | No | DUKHPROGEN00MTSM1600, DUKHPROGEN00MTSM1600 | DUKHPROGEN00MTSM1730, DUKHPROGEN00MTAP1660 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1450 | Ironmongeries_1st_Sub | 10 | 10 | 0% | 2013-03-20 | 2013-03-31 | 2013-03-20 | 2013-03-31 | 26 | No | DUKHPROGEN00PQAP2080 | DUKHPROGEN00MTAP1450 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1870 | Irrigation Controller_1st_Sub | 15 | 15 | 0% | 2013-08-04 | 2013-08-24 | 2013-08-04 | 2013-08-24 | 37 | No | DUKHPROGEN00PQAP2160, DUKHPROGEN00MTSM1860 | DUKHPROGEN00MTAP1870 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1670 | Irrigation Pipes_1st_Sub | 15 | 15 | 0% | 2013-04-21 | 2013-05-07 | 2013-04-21 | 2013-05-07 | 37 | No | DUKHPROGEN00PQAP2160 | DUKHPROGEN00MTAP1670, DUKHPROGEN00MTSM1760 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1650 | Isolating Values_1st_Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 4 | No | DUKHPROGEN00MTSM1540, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTSM1690, DUKHPROGEN00MTAP1650 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1200 | Isolators_1st_Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 108 | No | DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1200 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1600 | kerb works_1st_Sub | 15 | 15 | 0% | 2013-04-03 | 2013-04-20 | 2013-04-03 | 2013-04-20 | 40 | No | DUKHPROGEN00PQAP2110 | DUKHPROGEN00MTAP1600, DUKHPROGEN00MTSM1660, DUKHPROGEN00MTSM1660 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1770 | Kitchen Water Filter_1st_Sub | 15 | 15 | 0% | 2013-06-06 | 2013-06-23 | 2013-06-06 | 2013-06-23 | 9 | No | DUKHPROGEN00MTSM1680, DUKHPROGEN00MTSM1150, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1770 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1520 | Lift Pump_1st_Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 9 | No | DUKHPROGEN00MTSM1150, DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1330 | DUKHPROGEN00MTAP1520, DUKHPROGEN00MTSM1640 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1190 | Lights & Fixtures_1st_Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 87 | No | DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1190 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1590 | Manhole Covers and Frames_1st_Sub | 15 | 15 | 0% | 2013-03-26 | 2013-04-11 | 2013-03-26 | 2013-04-11 | 63 | No | DUKHPROGEN00MTSM1400 | DUKHPROGEN00MTAP1590 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1810 | Nozzle Jet_1st_Sub | 15 | 15 | 0% | 2013-05-26 | 2013-06-11 | 2013-05-26 | 2013-06-11 | 37 | No | DUKHPROGEN00MTSM1760, DUKHPROGEN00PQAP2160 | DUKHPROGEN00MTSM1830, DUKHPROGEN00MTAP1810 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1320 | Paints_1st_Sub | 15 | 15 | 0% | 2013-03-20 | 2013-04-06 | 2013-03-20 | 2013-04-06 | 10 | No | DUKHPROGEN00MTSM1300 | DUKHPROGEN00MTSM1420, DUKHPROGEN00MTAP1320 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1140 | Pitch roofing_1st_Sub | 15 | 15 | 0% | 2013-01-14 | 2013-01-30 | 2013-01-14 | 2013-01-30 | 87 | No | DUKHPROGEN00MTSM1050 | DUKHPROGEN00MTAP1140 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1790 | Plantation(Grass,Trees)_1st_Sub | 15 | 15 | 0% | 2013-05-26 | 2013-06-11 | 2013-05-26 | 2013-06-11 | 22 | No | DUKHPROGEN00PQAP2160, DUKHPROGEN00MTSM1740 | DUKHPROGEN00MTAP1790 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1040 | Plastering & Accessories_1st_Sub | 10 | 10 | 0% | 2012-12-02 | 2012-12-12 | 2012-12-02 | 2012-12-12 | 73 | No | DUKHPROGEN00MTSM1010 | DUKHPROGEN00MTAP1040, DUKHPROGEN00MTSM1090 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1080 | Polyethylene Pipes_1st_Sub | 15 | 15 | 0% | 2013-01-02 | 2013-01-19 | 2013-01-02 | 2013-01-19 | 55 | No | DUKHPROGEN00PQAP1040, DUKHPROGEN00MTSM1070 | DUKHPROGEN00MTSM1160, DUKHPROGEN00MTAP1080 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1130 | Porcelain Tile_1st_Sub | 15 | 15 | 0% | 2012-12-13 | 2012-12-31 | 2012-12-13 | 2012-12-31 | 82 | No | DUKHPROGEN00MTSM1120 | DUKHPROGEN00MTAP1130, DUKHPROGEN00MTSM1480 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1820 | Pre-cast Boundary Wall _1st_Sub | 15 | 15 | 0% | 2013-05-26 | 2013-06-11 | 2013-05-26 | 2013-06-11 | 40 | No | DUKHPROGEN00MTSM1800, DUKHPROGEN00PQAP2170 | DUKHPROGEN00MTSM1850, DUKHPROGEN00MTAP1820, DUKHPROGEN00MTSM1850 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1440 | PVC Doors_1st_Sub | 10 | 10 | 0% | 2013-03-20 | 2013-03-31 | 2013-03-20 | 2013-03-31 | 92 | No | DUKHPROGEN00PQAP2080 | DUKHPROGEN00MTAP1440 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1610 | PVC Tent_1st_Sub | 10 | 10 | 0% | 2013-04-03 | 2013-04-14 | 2013-04-03 | 2013-04-14 | 28 | No | DUKHPROGEN00PQAP2140 | DUKHPROGEN00MTSM1630, DUKHPROGEN00MTSM1620, DUKHPROGEN00MTAP1610 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1860 | Remote Control Value_1st_Sub | 15 | 15 | 0% | 2013-07-17 | 2013-08-03 | 2013-07-17 | 2013-08-03 | 37 | No | DUKHPROGEN00PQAP2160, DUKHPROGEN00MTSM1840 | DUKHPROGEN00MTAP1860, DUKHPROGEN00MTSM1870 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1720 | Road Marking_1st_Sub | 15 | 15 | 0% | 2013-05-08 | 2013-05-25 | 2013-05-08 | 2013-05-25 | 172 | No | DUKHPROGEN00MTSM1700 | DUKHPROGEN00MTAP1720 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1700 | Road Works Materials _1st_Sub | 15 | 15 | 0% | 2013-05-08 | 2013-05-25 | 2013-05-08 | 2013-05-25 | 22 | No | DUKHPROGEN00PQAP2180 | DUKHPROGEN00MTSM1720, DUKHPROGEN00MTSM1750, DUKHPROGEN00MTAP1700, DUKHPROGEN00MTSM1780, DUKHPROGEN00MTSM1710 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1430 | Roller Shutter_1st_Sub | 10 | 10 | 0% | 2013-03-17 | 2013-03-27 | 2013-03-17 | 2013-03-27 | 29 | No | DUKHPROGEN00PQAP2100 | DUKHPROGEN00MTAP1430, DUKHPROGEN00MTSM1500 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1150 | Sanitary Fittings_1st_Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 4 | No | DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTSM1520, DUKHPROGEN00MTSM1220, DUKHPROGEN00MTSM1230, DUKHPROGEN00MTSM1680, DUKHPROGEN00MTSM1770, DUKHPROGEN00MTSM1330, DUKHPROGEN00MTSM1640, DUKHPROGEN00MTAP1150 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1100 | Slate Tile_1st_Sub | 15 | 15 | 0% | 2012-12-13 | 2012-12-31 | 2012-12-13 | 2012-12-31 | 73 | No | DUKHPROGEN00MTSM1090 | DUKHPROGEN00MTAP1100, DUKHPROGEN00MTSM1110 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1170 | SMDB_1st_Sub | 15 | 15 | 0% | 2013-02-21 | 2013-03-10 | 2013-02-21 | 2013-03-10 | 75 | No | DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1170 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1260 | Smoke Detector_1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 49 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1210 | DUKHPROGEN00MTAP1260, DUKHPROGEN00MTSM1360 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1830 | Solenoid Values_1st_Sub | 15 | 15 | 0% | 2013-06-12 | 2013-06-29 | 2013-06-12 | 2013-06-29 | 37 | No | DUKHPROGEN00PQAP2160, DUKHPROGEN00MTSM1810 | DUKHPROGEN00MTAP1830, DUKHPROGEN00MTSM1840 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1750 | Speed Humps _1st_Sub | 15 | 15 | 0% | 2013-05-08 | 2013-05-25 | 2013-05-08 | 2013-05-25 | 22 | No | DUKHPROGEN00MTSM1700 | DUKHPROGEN00MTSM1740, DUKHPROGEN00MTAP1750 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1240 | Split AC_1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 61 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1160 | DUKHPROGEN00MTSM1340, DUKHPROGEN00MTAP1240 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1760 | Sprinklers_1st_Sub | 15 | 15 | 0% | 2013-05-08 | 2013-05-25 | 2013-05-08 | 2013-05-25 | 37 | No | DUKHPROGEN00PQAP2160, DUKHPROGEN00MTSM1670 | DUKHPROGEN00MTSM1810, DUKHPROGEN00MTAP1760 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1510 | Stainless Steel Cover_1st_Sub | 10 | 10 | 0% | 2013-03-28 | 2013-04-08 | 2013-03-28 | 2013-04-08 | 29 | No | DUKHPROGEN00MTSM1500 | DUKHPROGEN00MTAP1510 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1580 | Stainless Steel Handrail_1st_Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 61 | No | DUKHPROGEN00MTSM1570 | DUKHPROGEN00MTAP1580 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1500 | Steel Door_1st_Sub | 10 | 10 | 0% | 2013-03-28 | 2013-04-08 | 2013-03-28 | 2013-04-08 | 29 | No | DUKHPROGEN00MTSM1430 | DUKHPROGEN00MTSM1510, DUKHPROGEN00MTAP1500 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1800 | Steel Gate & Barrier gates_1st_Sub | 15 | 15 | 0% | 2013-05-26 | 2013-06-11 | 2013-05-26 | 2013-06-11 | 40 | No | DUKHPROGEN00PQAP2130, DUKHPROGEN00MTSM1730 | DUKHPROGEN00MTSM1820, DUKHPROGEN00MTAP1800 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1630 | Steel Ladder_1st_Sub | 15 | 15 | 0% | 2013-04-15 | 2013-05-01 | 2013-04-15 | 2013-05-01 | 36 | No | DUKHPROGEN00MTSM1610 | DUKHPROGEN00MTAP1630 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1740 | Stone Boulders_1st_Sub | 15 | 15 | 0% | 2013-05-08 | 2013-05-25 | 2013-05-08 | 2013-05-25 | 22 | No | DUKHPROGEN00MTSM1750 | DUKHPROGEN00MTAP1740, DUKHPROGEN00MTSM1790 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1110 | Stone Cladding_1st_Sub | 15 | 15 | 0% | 2012-12-13 | 2012-12-31 | 2012-12-13 | 2012-12-31 | 73 | No | DUKHPROGEN00MTSM1100 | DUKHPROGEN00MTAP1110, DUKHPROGEN00MTSM1120 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1250 | Street Light Post Set_1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 110 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1180 | DUKHPROGEN00MTSM1350, DUKHPROGEN00MTAP1250 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1620 | Structural Steel_1st_Sub | 10 | 10 | 0% | 2013-04-03 | 2013-04-14 | 2013-04-03 | 2013-04-14 | 28 | No | DUKHPROGEN00MTSM1610 | DUKHPROGEN00MTAP1620 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1280 | Telephone Fittings & Accessories_1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 70 | No | DUKHPROGEN00MTSM1270, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1280, DUKHPROGEN00MTSM1290 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1290 | Television devices,Fittings & Access._1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 99 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1280 | DUKHPROGEN00MTAP1290 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1050 | Thermal Insulation_1st_Sub | 15 | 15 | 0% | 2012-12-27 | 2013-01-13 | 2012-12-27 | 2013-01-13 | 87 | No | DUKHPROGEN00MTSM1030 | DUKHPROGEN00MTSM1140, DUKHPROGEN00MTAP1050 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1060 | UPVC Pipes_1st_Sub | 15 | 15 | 0% | 2013-01-02 | 2013-01-19 | 2013-01-02 | 2013-01-19 | 28 | No | DUKHPROGEN00PQAP1040 | DUKHPROGEN00MTSM1070, DUKHPROGEN00MTAP1060 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1270 | Video Com System_1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 70 | No | DUKHPROGEN00MTSM1210, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTSM1280, DUKHPROGEN00MTAP1270 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1220 | Water Chiller_1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 9 | No | DUKHPROGEN00MTSM1150, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTAP1220, DUKHPROGEN00MTSM1330 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1230 | Water Heater_1st_Sub | 15 | 15 | 0% | 2013-03-11 | 2013-03-27 | 2013-03-11 | 2013-03-27 | 4 | No | DUKHPROGEN00MTSM1150, DUKHPROGEN00PQAP2040 | DUKHPROGEN00MTSM1370, DUKHPROGEN00MTAP1230 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1640 | Water meter_1st_Sub | 15 | 15 | 0% | 2013-05-02 | 2013-05-19 | 2013-05-02 | 2013-05-19 | 9 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1520, DUKHPROGEN00MTSM1150 | DUKHPROGEN00MTSM1680, DUKHPROGEN00MTAP1640 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1680 | Water Tank_1st_Sub | 15 | 15 | 0% | 2013-05-20 | 2013-06-05 | 2013-05-20 | 2013-06-05 | 9 | No | DUKHPROGEN00PQAP2040, DUKHPROGEN00MTSM1640, DUKHPROGEN00MTSM1150 | DUKHPROGEN00MTSM1770, DUKHPROGEN00MTAP1680 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1030 | Waterproofing_1st_Sub | 10 | 10 | 0% | 2012-12-15 | 2012-12-26 | 2012-12-15 | 2012-12-26 | 38 | No | DUKHPROGEN00PQAP1030, DUKHPROGEN00PQAP1020 | DUKHPROGEN00MTSM1050, DUKHPROGEN00MTAP1030 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1490 | Wooden Doors_1st_Sub | 10 | 10 | 0% | 2013-03-20 | 2013-03-31 | 2013-03-20 | 2013-03-31 | 26 | No | DUKHPROGEN00PQAP2070 | DUKHPROGEN00MTAP1490 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM1570 | Wooden Hand Rails _1st_Sub | 15 | 15 | 0% | 2013-04-07 | 2013-04-23 | 2013-04-07 | 2013-04-23 | 61 | No | DUKHPROGEN00PQAP2150 | DUKHPROGEN00MTAP1570, DUKHPROGEN00MTSM1580 | 0 | 0 | 1ST SUBMISSION OF MATERIAL
DHBL.K25.L20.15 1ST APPROVAL OF MATERIAL |  | 252 | 252 | 0% | 2012-12-03 | 2013-09-28 | 2012-12-03 | 2013-09-28 | 114 |  |  |  | 0 | 0
DUKHPROGEN00MTAP1400 | Access Ladder_1st_App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 91 | No | DUKHPROGEN00MTSM1400 | DUKHPROGEN00MTSM2400 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1470 | Aluminum Windows_1st_App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 71 | No | DUKHPROGEN00MTSM1470 | DUKHPROGEN00MTSM2470 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1460 | Aluminum Doors_1st_App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 65 | No | DUKHPROGEN00MTSM1460 | DUKHPROGEN00MTSM2460 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1410 | Aluminum Slat Screen_1st_App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 81 | No | DUKHPROGEN00MTSM1410 | DUKHPROGEN00MTSM2410 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1310 | Aluminum Tile false ceiling_1st_App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 42 | No | DUKHPROGEN00MTSM1310 | DUKHPROGEN00MTSM2310 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1000 | Anti Termite _1st_App | 15 | 15 | 0% | 2012-12-09 | 2012-12-26 | 2012-12-09 | 2012-12-26 | 45 | No | DUKHPROGEN00MTSM1000 | DUKHPROGEN00PRDV3000 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1010 | Block Work_1st_App | 25 | 25 | 0% | 2012-12-03 | 2013-01-01 | 2012-12-03 | 2013-01-01 | 59 | No | DUKHPROGEN00MTSM1010 | DUKHPROGEN00PRDV3010 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1350 | Bollard Lamp_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 110 | No | DUKHPROGEN00MTSM1350 | DUKHPROGEN00MTSM2350 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1330 | Booster Pump_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 35 | No | DUKHPROGEN00MTSM1330 | DUKHPROGEN00MTSM2330 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1180 | Cables & Wires_1st_App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 64 | No | DUKHPROGEN00MTSM1180 | DUKHPROGEN00PRDV3180 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1730 | Car Parking Shed_1st_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 127 | No | DUKHPROGEN00MTSM1730 | DUKHPROGEN00MTSM2730 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1120 | Ceramic Tile_1st_App | 30 | 30 | 0% | 2013-01-01 | 2013-02-04 | 2013-01-01 | 2013-02-04 | 73 | No | DUKHPROGEN00MTSM1120 | DUKHPROGEN00MTSM2120 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1550 | Closets /wardrobe& Pelmets_1st_App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 43 | No | DUKHPROGEN00MTSM1550 | DUKHPROGEN00MTSM2550 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1090 | Cobble stone finish _1st_App | 30 | 30 | 0% | 2013-01-01 | 2013-02-04 | 2013-01-01 | 2013-02-04 | 113 | No | DUKHPROGEN00MTSM1090 | DUKHPROGEN00MTSM2090 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1020 | Concrete_1st_App | 15 | 15 | 0% | 2012-12-10 | 2012-12-27 | 2012-12-10 | 2012-12-27 | 39 | No | DUKHPROGEN00MTSM1020 | DUKHPROGEN00PRDV3020 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1160 | Copper Pipes_1st_App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 54 | No | DUKHPROGEN00MTSM1160 | DUKHPROGEN00MTSM2160 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1560 | Counters, Cabinets & Shelves_1st_App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 43 | No | DUKHPROGEN00MTSM1560 | DUKHPROGEN00MTSM2560 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1360 | Digital Alarm Communicator Panel_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 49 | No | DUKHPROGEN00MTSM1360 | DUKHPROGEN00MTSM2360 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1540 | Ductile Iron Pipes_1st_App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 5 | No | DUKHPROGEN00MTSM1540 | DUKHPROGEN00MTSM2540 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1420 | Epoxy_1st_App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 134 | No | DUKHPROGEN00MTSM1420 | DUKHPROGEN00MTSM2420 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1340 | Exhaust Air louver_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 76 | No | DUKHPROGEN00MTSM1340 | DUKHPROGEN00MTSM2340 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1530 | Exhaust Fan_1st_App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 61 | No | DUKHPROGEN00MTSM1530 | DUKHPROGEN00MTSM2530 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1710 | External signage _1st_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 172 | No | DUKHPROGEN00MTSM1710 | DUKHPROGEN00MTSM2710 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1850 | Fences_1st_App | 30 | 30 | 0% | 2013-06-30 | 2013-08-03 | 2013-06-30 | 2013-08-03 | 126 | No | DUKHPROGEN00MTSM1850 | DUKHPROGEN00MTSM2850 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1370 | Fire Blanket_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 98 | No | DUKHPROGEN00MTSM1370 | DUKHPROGEN00MTSM2370 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1380 | Fire Extinguisher_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 90 | No | DUKHPROGEN00MTSM1380 | DUKHPROGEN00MTSM2380 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1690 | Fire Hydrant_1st_App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 15 | No | DUKHPROGEN00MTSM1690 | DUKHPROGEN00MTSM2690 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1210 | Fire Resistant Cables_1st_App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 105 | No | DUKHPROGEN00MTSM1210 | DUKHPROGEN00MTSM2210 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1070 | Floor drains & Cleanouts_1st_App | 30 | 30 | 0% | 2013-01-20 | 2013-02-24 | 2013-01-20 | 2013-02-24 | 28 | No | DUKHPROGEN00MTSM1070 | DUKHPROGEN00PRDV3070 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1840 | Gate Values_1st_App | 30 | 30 | 0% | 2013-07-17 | 2013-08-24 | 2013-07-17 | 2013-08-24 | 67 | No | DUKHPROGEN00MTSM1840 | DUKHPROGEN00MTSM2840 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1780 | Gazebo Structure_1st_App | 30 | 30 | 0% | 2013-06-12 | 2013-07-16 | 2013-06-12 | 2013-07-16 | 67 | No | DUKHPROGEN00MTSM1780 | DUKHPROGEN00MTSM2780 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1480 | Granite_1st_App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 46 | No | DUKHPROGEN00MTSM1480 | DUKHPROGEN00MTSM2480 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1390 | GRC Panels_1st_App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 74 | No | DUKHPROGEN00MTSM1390 | DUKHPROGEN00MTSM2390 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1300 | Gypsum Board false ceiling_1st_App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 32 | No | DUKHPROGEN00MTSM1300 | DUKHPROGEN00MTSM2300 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1660 | Interlock works_1st_App | 30 | 30 | 0% | 2013-05-08 | 2013-06-11 | 2013-05-08 | 2013-06-11 | 85 | No | DUKHPROGEN00MTSM1660 | DUKHPROGEN00MTSM2660 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1450 | Ironmongeries_1st_App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 26 | No | DUKHPROGEN00MTSM1450 | DUKHPROGEN00MTSM2450 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1870 | Irrigation Controller_1st_App | 30 | 30 | 0% | 2013-08-25 | 2013-09-28 | 2013-08-25 | 2013-09-28 | 37 | No | DUKHPROGEN00MTSM1870 | DUKHPROGEN00MTSM2870 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1670 | Irrigation Pipes_1st_App | 30 | 30 | 0% | 2013-05-08 | 2013-06-11 | 2013-05-08 | 2013-06-11 | 76 | No | DUKHPROGEN00MTSM1670 | DUKHPROGEN00MTSM2670 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1650 | Isolating Values_1st_App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 4 | No | DUKHPROGEN00MTSM1650 | DUKHPROGEN00MTSM2650 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1200 | Isolators_1st_App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 108 | No | DUKHPROGEN00MTSM1200 | DUKHPROGEN00MTSM2200 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1600 | kerb works_1st_App | 30 | 30 | 0% | 2013-04-21 | 2013-05-25 | 2013-04-21 | 2013-05-25 | 78 | No | DUKHPROGEN00MTSM1600 | DUKHPROGEN00MTSM2600 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1770 | Kitchen Water Filter_1st_App | 30 | 30 | 0% | 2013-06-24 | 2013-07-28 | 2013-06-24 | 2013-07-28 | 9 | No | DUKHPROGEN00MTSM1770 | DUKHPROGEN00MTSM2770 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1520 | Lift Pump_1st_App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 20 | No | DUKHPROGEN00MTSM1520 | DUKHPROGEN00MTSM2520 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1190 | Lights & Fixtures_1st_App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 87 | No | DUKHPROGEN00MTSM1190 | DUKHPROGEN00MTSM2190 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1590 | Manhole Covers and Frames_1st_App | 30 | 30 | 0% | 2013-04-13 | 2013-05-16 | 2013-04-13 | 2013-05-16 | 63 | No | DUKHPROGEN00MTSM1590 | DUKHPROGEN00MTSM2590 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1810 | Nozzle Jet_1st_App | 30 | 30 | 0% | 2013-06-12 | 2013-07-16 | 2013-06-12 | 2013-07-16 | 97 | No | DUKHPROGEN00MTSM1810 | DUKHPROGEN00MTSM2810 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1320 | Paints_1st_App | 30 | 30 | 0% | 2013-04-07 | 2013-05-11 | 2013-04-07 | 2013-05-11 | 10 | No | DUKHPROGEN00MTSM1320 | DUKHPROGEN00MTSM2320 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1140 | Pitch roofing_1st_App | 30 | 30 | 0% | 2013-01-31 | 2013-03-07 | 2013-01-31 | 2013-03-07 | 87 | No | DUKHPROGEN00MTSM1140 | DUKHPROGEN00MTSM2140 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1790 | Plantation(Grass,Trees)_1st_App | 30 | 30 | 0% | 2013-06-12 | 2013-07-16 | 2013-06-12 | 2013-07-16 | 22 | No | DUKHPROGEN00MTSM1790 | DUKHPROGEN00MTSM2790 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1040 | Plastering & Accessories_1st_App | 30 | 30 | 0% | 2012-12-13 | 2013-01-17 | 2012-12-13 | 2013-01-17 | 115 | No | DUKHPROGEN00MTSM1040 | DUKHPROGEN00MTSM2040 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1080 | Polyethylene Pipes_1st_App | 30 | 30 | 0% | 2013-01-20 | 2013-02-24 | 2013-01-20 | 2013-02-24 | 55 | No | DUKHPROGEN00MTSM1080 | DUKHPROGEN00MTSM2080 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1130 | Porcelain Tile_1st_App | 30 | 30 | 0% | 2013-01-01 | 2013-02-04 | 2013-01-01 | 2013-02-04 | 82 | No | DUKHPROGEN00MTSM1130 | DUKHPROGEN00MTSM2130 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1820 | Pre-cast Boundary Wall _1st_App | 30 | 30 | 0% | 2013-06-12 | 2013-07-16 | 2013-06-12 | 2013-07-16 | 40 | No | DUKHPROGEN00MTSM1820 | DUKHPROGEN00MTSM2820 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1440 | PVC Doors_1st_App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 92 | No | DUKHPROGEN00MTSM1440 | DUKHPROGEN00MTSM2440 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1610 | PVC Tent_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 30 | No | DUKHPROGEN00MTSM1610 | DUKHPROGEN00MTSM2610 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1860 | Remote Control Value_1st_App | 30 | 30 | 0% | 2013-08-04 | 2013-09-10 | 2013-08-04 | 2013-09-10 | 52 | No | DUKHPROGEN00MTSM1860 | DUKHPROGEN00MTSM2860 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1720 | Road Marking_1st_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 172 | No | DUKHPROGEN00MTSM1720 | DUKHPROGEN00MTSM2720 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1700 | Road Works Materials _1st_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 189 | No | DUKHPROGEN00MTSM1700 | DUKHPROGEN00MTSM2700 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1430 | Roller Shutter_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 218 | No | DUKHPROGEN00MTSM1430 | DUKHPROGEN00MTSM2430 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1150 | Sanitary Fittings_1st_App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 51 | No | DUKHPROGEN00MTSM1150 | DUKHPROGEN00MTSM2150 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1100 | Slate Tile_1st_App | 30 | 30 | 0% | 2013-01-01 | 2013-02-04 | 2013-01-01 | 2013-02-04 | 118 | No | DUKHPROGEN00MTSM1100 | DUKHPROGEN00MTSM2100 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1170 | SMDB_1st_App | 30 | 30 | 0% | 2013-03-11 | 2013-04-14 | 2013-03-11 | 2013-04-14 | 75 | No | DUKHPROGEN00MTSM1170 | DUKHPROGEN00MTSM2170 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1260 | Smoke Detector_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 90 | No | DUKHPROGEN00MTSM1260 | DUKHPROGEN00MTSM2260 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1830 | Solenoid Values_1st_App | 30 | 30 | 0% | 2013-06-30 | 2013-08-03 | 2013-06-30 | 2013-08-03 | 82 | No | DUKHPROGEN00MTSM1830 | DUKHPROGEN00MTSM2830 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1750 | Speed Humps _1st_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 126 | No | DUKHPROGEN00MTSM1750 | DUKHPROGEN00MTSM2750 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1240 | Split AC_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 84 | No | DUKHPROGEN00MTSM1240 | DUKHPROGEN00MTSM2240 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1760 | Sprinklers_1st_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 138 | No | DUKHPROGEN00MTSM1760 | DUKHPROGEN00MTSM2760 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1510 | Stainless Steel Cover_1st_App | 30 | 30 | 0% | 2013-04-09 | 2013-05-13 | 2013-04-09 | 2013-05-13 | 29 | No | DUKHPROGEN00MTSM1510 | DUKHPROGEN00MTSM2510 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1580 | Stainless Steel Handrail_1st_App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 61 | No | DUKHPROGEN00MTSM1580 | DUKHPROGEN00MTSM2580 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1500 | Steel Door_1st_App | 30 | 30 | 0% | 2013-04-09 | 2013-05-13 | 2013-04-09 | 2013-05-13 | 29 | No | DUKHPROGEN00MTSM1500 | DUKHPROGEN00MTSM2500 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1800 | Steel Gate & Barrier gates_1st_App | 30 | 30 | 0% | 2013-06-12 | 2013-07-16 | 2013-06-12 | 2013-07-16 | 63 | No | DUKHPROGEN00MTSM1800 | DUKHPROGEN00MTSM2800 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1630 | Steel Ladder_1st_App | 30 | 30 | 0% | 2013-05-02 | 2013-06-05 | 2013-05-02 | 2013-06-05 | 36 | No | DUKHPROGEN00MTSM1630 | DUKHPROGEN00MTSM2630 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1740 | Stone Boulders_1st_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 127 | No | DUKHPROGEN00MTSM1740 | DUKHPROGEN00MTSM2740 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1110 | Stone Cladding_1st_App | 30 | 30 | 0% | 2013-01-01 | 2013-02-04 | 2013-01-01 | 2013-02-04 | 125 | No | DUKHPROGEN00MTSM1110 | DUKHPROGEN00MTSM2110 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1250 | Street Light Post Set_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 125 | No | DUKHPROGEN00MTSM1250 | DUKHPROGEN00MTSM2250 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1620 | Structural Steel_1st_App | 30 | 30 | 0% | 2013-04-15 | 2013-05-19 | 2013-04-15 | 2013-05-19 | 28 | No | DUKHPROGEN00MTSM1620 | DUKHPROGEN00MTSM2620 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1280 | Telephone Fittings & Accessories_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 70 | No | DUKHPROGEN00MTSM1280 | DUKHPROGEN00MTSM2280 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1290 | Television devices,Fittings & Access._1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 99 | No | DUKHPROGEN00MTSM1290 | DUKHPROGEN00MTSM2290 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1050 | Thermal Insulation_1st_App | 30 | 30 | 0% | 2013-01-14 | 2013-02-18 | 2013-01-14 | 2013-02-18 | 116 | No | DUKHPROGEN00MTSM1050 | DUKHPROGEN00MTSM2050 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1060 | UPVC Pipes_1st_App | 30 | 30 | 0% | 2013-01-20 | 2013-02-24 | 2013-01-20 | 2013-02-24 | 28 | No | DUKHPROGEN00MTSM1060 | DUKHPROGEN00PRDV3060 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1270 | Video Com System_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 70 | No | DUKHPROGEN00MTSM1270 | DUKHPROGEN00MTSM2270 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1220 | Water Chiller_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 50 | No | DUKHPROGEN00MTSM1220 | DUKHPROGEN00MTSM2220 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1230 | Water Heater_1st_App | 30 | 30 | 0% | 2013-03-28 | 2013-05-01 | 2013-03-28 | 2013-05-01 | 59 | No | DUKHPROGEN00MTSM1230 | DUKHPROGEN00MTSM2230 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1640 | Water meter_1st_App | 30 | 30 | 0% | 2013-05-20 | 2013-06-23 | 2013-05-20 | 2013-06-23 | 56 | No | DUKHPROGEN00MTSM1640 | DUKHPROGEN00MTSM2640 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1680 | Water Tank_1st_App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 41 | No | DUKHPROGEN00MTSM1680 | DUKHPROGEN00MTSM2680 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1030 | Waterproofing_1st_App | 15 | 15 | 0% | 2012-12-27 | 2013-01-13 | 2012-12-27 | 2013-01-13 | 38 | No | DUKHPROGEN00MTSM1030 | DUKHPROGEN00PRDV3030 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1490 | Wooden Doors_1st_App | 30 | 30 | 0% | 2013-04-01 | 2013-05-05 | 2013-04-01 | 2013-05-05 | 26 | No | DUKHPROGEN00MTSM1490 | DUKHPROGEN00MTSM2490 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DUKHPROGEN00MTAP1570 | Wooden Hand Rails _1st_App | 30 | 30 | 0% | 2013-04-24 | 2013-05-28 | 2013-04-24 | 2013-05-28 | 61 | No | DUKHPROGEN00MTSM1570 | DUKHPROGEN00MTSM2570 | 0 | 0 | 1ST APPROVAL OF MATERIAL
DHBL.K25.L20.20 2ND SUBMISSION OF MATERIAL |  | 223 | 223 | 0% | 2013-01-19 | 2013-10-09 | 2013-01-19 | 2013-10-09 | 114 |  |  |  | 0 | 0
DUKHPROGEN00MTSM2400 | Access Ladder_2nd_Sub | 10 | 10 | 0% | 2013-04-30 | 2013-05-11 | 2013-04-30 | 2013-05-11 | 91 | No | DUKHPROGEN00MTAP1400 | DUKHPROGEN00MTAP2400 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2470 | Aluminum Windows_2nd_Sub | 10 | 10 | 0% | 2013-05-06 | 2013-05-16 | 2013-05-06 | 2013-05-16 | 71 | No | DUKHPROGEN00MTAP1470 | DUKHPROGEN00MTAP2470 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2460 | Aluminum Doors_2nd_Sub | 10 | 10 | 0% | 2013-05-06 | 2013-05-16 | 2013-05-06 | 2013-05-16 | 65 | No | DUKHPROGEN00MTAP1460 | DUKHPROGEN00MTAP2460 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2410 | Aluminum Slat Screen_2nd_Sub | 10 | 10 | 0% | 2013-04-30 | 2013-05-11 | 2013-04-30 | 2013-05-11 | 81 | No | DUKHPROGEN00MTAP1410 | DUKHPROGEN00MTAP2410 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2310 | Aluminum Tile false ceiling_2nd_Sub | 10 | 10 | 0% | 2013-05-06 | 2013-05-16 | 2013-05-06 | 2013-05-16 | 42 | No | DUKHPROGEN00MTAP1310 | DUKHPROGEN00MTAP2310 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2350 | Bollard Lamp_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 110 | No | DUKHPROGEN00MTAP1350 | DUKHPROGEN00MTAP2350 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2330 | Booster Pump_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 35 | No | DUKHPROGEN00MTAP1330 | DUKHPROGEN00MTAP2330 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2730 | Car Parking Shed_2nd_Sub | 10 | 10 | 0% | 2013-06-30 | 2013-07-10 | 2013-06-30 | 2013-07-10 | 127 | No | DUKHPROGEN00MTAP1730 | DUKHPROGEN00MTAP2730 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2120 | Ceramic Tile_2nd_Sub | 10 | 10 | 0% | 2013-02-05 | 2013-02-17 | 2013-02-05 | 2013-02-17 | 73 | No | DUKHPROGEN00MTAP1120 | DUKHPROGEN00MTAP2120 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2550 | Closets /wardrobe& Pelmets_2nd_Sub | 10 | 10 | 0% | 2013-05-29 | 2013-06-09 | 2013-05-29 | 2013-06-09 | 43 | No | DUKHPROGEN00MTAP1550 | DUKHPROGEN00MTAP2550 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2090 | Cobble stone finish _2nd_Sub | 10 | 10 | 0% | 2013-02-05 | 2013-02-17 | 2013-02-05 | 2013-02-17 | 113 | No | DUKHPROGEN00MTAP1090 | DUKHPROGEN00MTAP2090 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2160 | Copper Pipes_2nd_Sub | 10 | 10 | 0% | 2013-04-15 | 2013-04-25 | 2013-04-15 | 2013-04-25 | 54 | No | DUKHPROGEN00MTAP1160 | DUKHPROGEN00MTAP2160 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2560 | Counters, Cabinets & Shelves_2nd_Sub | 10 | 10 | 0% | 2013-05-29 | 2013-06-09 | 2013-05-29 | 2013-06-09 | 43 | No | DUKHPROGEN00MTAP1560 | DUKHPROGEN00MTAP2560 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2360 | Digital Alarm Communicator Panel_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 49 | No | DUKHPROGEN00MTAP1360 | DUKHPROGEN00MTAP2360 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2540 | Ductile Iron Pipes_2nd_Sub | 10 | 10 | 0% | 2013-06-06 | 2013-06-17 | 2013-06-06 | 2013-06-17 | 5 | No | DUKHPROGEN00MTAP1540 | DUKHPROGEN00MTAP2540 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2420 | Epoxy_2nd_Sub | 10 | 10 | 0% | 2013-05-29 | 2013-06-09 | 2013-05-29 | 2013-06-09 | 134 | No | DUKHPROGEN00MTAP1420 | DUKHPROGEN00MTAP2420 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2340 | Exhaust Air louver_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 76 | No | DUKHPROGEN00MTAP1340 | DUKHPROGEN00MTAP2340 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2530 | Exhaust Fan_2nd_Sub | 10 | 10 | 0% | 2013-06-06 | 2013-06-17 | 2013-06-06 | 2013-06-17 | 61 | No | DUKHPROGEN00MTAP1530 | DUKHPROGEN00MTAP2530 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2710 | External signage _2nd_Sub | 10 | 10 | 0% | 2013-06-30 | 2013-07-10 | 2013-06-30 | 2013-07-10 | 172 | No | DUKHPROGEN00MTAP1710 | DUKHPROGEN00MTAP2710 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2850 | Fences_2nd_Sub | 10 | 10 | 0% | 2013-08-04 | 2013-08-18 | 2013-08-04 | 2013-08-18 | 126 | No | DUKHPROGEN00MTAP1850 | DUKHPROGEN00MTAP2850 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2370 | Fire Blanket_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 98 | No | DUKHPROGEN00MTAP1370 | DUKHPROGEN00MTAP2370 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2380 | Fire Extinguisher_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 90 | No | DUKHPROGEN00MTAP1380 | DUKHPROGEN00MTAP2380 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2690 | Fire Hydrant_2nd_Sub | 10 | 10 | 0% | 2013-07-11 | 2013-07-22 | 2013-07-11 | 2013-07-22 | 15 | No | DUKHPROGEN00MTAP1690 | DUKHPROGEN00MTAP2690 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2210 | Fire Resistant Cables_2nd_Sub | 10 | 10 | 0% | 2013-04-15 | 2013-04-25 | 2013-04-15 | 2013-04-25 | 105 | No | DUKHPROGEN00MTAP1210 | DUKHPROGEN00MTAP2210 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2840 | Gate Values_2nd_Sub | 10 | 10 | 0% | 2013-08-25 | 2013-09-04 | 2013-08-25 | 2013-09-04 | 67 | No | DUKHPROGEN00MTAP1840 | DUKHPROGEN00MTAP2840 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2780 | Gazebo Structure_2nd_Sub | 10 | 10 | 0% | 2013-07-17 | 2013-07-28 | 2013-07-17 | 2013-07-28 | 67 | No | DUKHPROGEN00MTAP1780 | DUKHPROGEN00MTAP2780 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2480 | Granite_2nd_Sub | 10 | 10 | 0% | 2013-05-06 | 2013-05-16 | 2013-05-06 | 2013-05-16 | 46 | No | DUKHPROGEN00MTAP1480 | DUKHPROGEN00MTAP2480 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2390 | GRC Panels_2nd_Sub | 10 | 10 | 0% | 2013-04-30 | 2013-05-11 | 2013-04-30 | 2013-05-11 | 74 | No | DUKHPROGEN00MTAP1390 | DUKHPROGEN00MTAP2390 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2300 | Gypsum Board false ceiling_2nd_Sub | 10 | 10 | 0% | 2013-04-30 | 2013-05-11 | 2013-04-30 | 2013-05-11 | 32 | No | DUKHPROGEN00MTAP1300 | DUKHPROGEN00MTAP2300 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2660 | Interlock works_2nd_Sub | 10 | 10 | 0% | 2013-06-12 | 2013-06-23 | 2013-06-12 | 2013-06-23 | 85 | No | DUKHPROGEN00MTAP1660 | DUKHPROGEN00MTAP2660 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2450 | Ironmongeries_2nd_Sub | 10 | 10 | 0% | 2013-05-06 | 2013-05-16 | 2013-05-06 | 2013-05-16 | 26 | No | DUKHPROGEN00MTAP1450 | DUKHPROGEN00MTAP2450 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2870 | Irrigation Controller_2nd_Sub | 10 | 10 | 0% | 2013-09-29 | 2013-10-09 | 2013-09-29 | 2013-10-09 | 37 | No | DUKHPROGEN00MTAP1870 | DUKHPROGEN00MTAP2870 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2670 | Irrigation Pipes_2nd_Sub | 10 | 10 | 0% | 2013-06-12 | 2013-06-23 | 2013-06-12 | 2013-06-23 | 76 | No | DUKHPROGEN00MTAP1670 | DUKHPROGEN00MTAP2670 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2650 | Isolating Values_2nd_Sub | 10 | 10 | 0% | 2013-06-24 | 2013-07-04 | 2013-06-24 | 2013-07-04 | 4 | No | DUKHPROGEN00MTAP1650 | DUKHPROGEN00MTAP2650 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2200 | Isolators_2nd_Sub | 10 | 10 | 0% | 2013-04-15 | 2013-04-25 | 2013-04-15 | 2013-04-25 | 108 | No | DUKHPROGEN00MTAP1200 | DUKHPROGEN00MTAP2200 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2600 | kerb works_2nd_Sub | 10 | 10 | 0% | 2013-05-26 | 2013-06-05 | 2013-05-26 | 2013-06-05 | 78 | No | DUKHPROGEN00MTAP1600 | DUKHPROGEN00MTAP2600 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2770 | Kitchen Water Filter_2nd_Sub | 10 | 10 | 0% | 2013-07-29 | 2013-08-08 | 2013-07-29 | 2013-08-08 | 9 | No | DUKHPROGEN00MTAP1770 | DUKHPROGEN00MTAP2770 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2520 | Lift Pump_2nd_Sub | 10 | 10 | 0% | 2013-06-06 | 2013-06-17 | 2013-06-06 | 2013-06-17 | 20 | No | DUKHPROGEN00MTAP1520 | DUKHPROGEN00MTAP2520 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2190 | Lights & Fixtures_2nd_Sub | 10 | 10 | 0% | 2013-04-15 | 2013-04-25 | 2013-04-15 | 2013-04-25 | 87 | No | DUKHPROGEN00MTAP1190 | DUKHPROGEN00MTAP2190 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2590 | Manhole Covers and Frames_2nd_Sub | 10 | 10 | 0% | 2013-05-18 | 2013-05-28 | 2013-05-18 | 2013-05-28 | 63 | No | DUKHPROGEN00MTAP1590 | DUKHPROGEN00MTAP2590 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2810 | Nozzle Jet_2nd_Sub | 10 | 10 | 0% | 2013-07-17 | 2013-07-28 | 2013-07-17 | 2013-07-28 | 97 | No | DUKHPROGEN00MTAP1810 | DUKHPROGEN00MTAP2810 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2320 | Paints_2nd_Sub | 10 | 10 | 0% | 2013-05-12 | 2013-05-22 | 2013-05-12 | 2013-05-22 | 10 | No | DUKHPROGEN00MTAP1320 | DUKHPROGEN00MTAP2320 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2140 | Pitch roofing_2nd_Sub | 15 | 15 | 0% | 2013-03-09 | 2013-03-25 | 2013-03-09 | 2013-03-25 | 87 | No | DUKHPROGEN00MTAP1140 | DUKHPROGEN00MTAP2140 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2790 | Plantation(Grass,Trees)_2nd_Sub | 10 | 10 | 0% | 2013-07-17 | 2013-07-28 | 2013-07-17 | 2013-07-28 | 22 | No | DUKHPROGEN00MTAP1790 | DUKHPROGEN00MTAP2790 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2040 | Plastering & Accessories_2nd_Sub | 10 | 10 | 0% | 2013-01-19 | 2013-01-29 | 2013-01-19 | 2013-01-29 | 115 | No | DUKHPROGEN00MTAP1040 | DUKHPROGEN00MTAP2040 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2080 | Polyethylene Pipes_2nd_Sub | 10 | 10 | 0% | 2013-02-25 | 2013-03-07 | 2013-02-25 | 2013-03-07 | 55 | No | DUKHPROGEN00MTAP1080 | DUKHPROGEN00MTAP2080 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2130 | Porcelain Tile_2nd_Sub | 10 | 10 | 0% | 2013-02-05 | 2013-02-17 | 2013-02-05 | 2013-02-17 | 82 | No | DUKHPROGEN00MTAP1130 | DUKHPROGEN00MTAP2130 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2820 | Pre-cast Boundary Wall _2nd_Sub | 10 | 10 | 0% | 2013-07-17 | 2013-07-28 | 2013-07-17 | 2013-07-28 | 40 | No | DUKHPROGEN00MTAP1820 | DUKHPROGEN00MTAP2820 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2440 | PVC Doors_2nd_Sub | 10 | 10 | 0% | 2013-05-06 | 2013-05-16 | 2013-05-06 | 2013-05-16 | 92 | No | DUKHPROGEN00MTAP1440 | DUKHPROGEN00MTAP2440 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2610 | PVC Tent_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 30 | No | DUKHPROGEN00MTAP1610 | DUKHPROGEN00MTAP2610 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2860 | Remote Control Value_2nd_Sub | 10 | 10 | 0% | 2013-09-11 | 2013-09-22 | 2013-09-11 | 2013-09-22 | 52 | No | DUKHPROGEN00MTAP1860 | DUKHPROGEN00MTAP2860 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2720 | Road Marking_2nd_Sub | 10 | 10 | 0% | 2013-06-30 | 2013-07-10 | 2013-06-30 | 2013-07-10 | 172 | No | DUKHPROGEN00MTAP1720 | DUKHPROGEN00MTAP2720 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2700 | Road Works Materials _2nd_Sub | 10 | 10 | 0% | 2013-06-30 | 2013-07-10 | 2013-06-30 | 2013-07-10 | 189 | No | DUKHPROGEN00MTAP1700 | DUKHPROGEN00MTAP2700 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2430 | Roller Shutter_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 218 | No | DUKHPROGEN00MTAP1430 | DUKHPROGEN00MTAP2430 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2150 | Sanitary Fittings_2nd_Sub | 10 | 10 | 0% | 2013-04-15 | 2013-04-25 | 2013-04-15 | 2013-04-25 | 51 | No | DUKHPROGEN00MTAP1150 | DUKHPROGEN00MTAP2150 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2100 | Slate Tile_2nd_Sub | 10 | 10 | 0% | 2013-02-05 | 2013-02-17 | 2013-02-05 | 2013-02-17 | 118 | No | DUKHPROGEN00MTAP1100 | DUKHPROGEN00MTAP2100 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2170 | SMDB_2nd_Sub | 10 | 10 | 0% | 2013-04-15 | 2013-04-25 | 2013-04-15 | 2013-04-25 | 75 | No | DUKHPROGEN00MTAP1170 | DUKHPROGEN00MTAP2170 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2260 | Smoke Detector_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 90 | No | DUKHPROGEN00MTAP1260 | DUKHPROGEN00MTAP2260 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2830 | Solenoid Values_2nd_Sub | 10 | 10 | 0% | 2013-08-04 | 2013-08-18 | 2013-08-04 | 2013-08-18 | 82 | No | DUKHPROGEN00MTAP1830 | DUKHPROGEN00MTAP2830 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2750 | Speed Humps _2nd_Sub | 10 | 10 | 0% | 2013-06-30 | 2013-07-10 | 2013-06-30 | 2013-07-10 | 126 | No | DUKHPROGEN00MTAP1750 | DUKHPROGEN00MTAP2750 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2240 | Split AC_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 84 | No | DUKHPROGEN00MTAP1240 | DUKHPROGEN00MTAP2240 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2760 | Sprinklers_2nd_Sub | 10 | 10 | 0% | 2013-06-30 | 2013-07-10 | 2013-06-30 | 2013-07-10 | 138 | No | DUKHPROGEN00MTAP1760 | DUKHPROGEN00MTAP2760 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2510 | Stainless Steel Cover_2nd_Sub | 10 | 10 | 0% | 2013-05-14 | 2013-05-25 | 2013-05-14 | 2013-05-25 | 29 | No | DUKHPROGEN00MTAP1510 | DUKHPROGEN00MTAP2510 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2580 | Stainless Steel Handrail_2nd_Sub | 10 | 10 | 0% | 2013-05-29 | 2013-06-09 | 2013-05-29 | 2013-06-09 | 61 | No | DUKHPROGEN00MTSM2570, DUKHPROGEN00MTAP1580 | DUKHPROGEN00MTAP2580 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2500 | Steel Door_2nd_Sub | 10 | 10 | 0% | 2013-05-14 | 2013-05-25 | 2013-05-14 | 2013-05-25 | 29 | No | DUKHPROGEN00MTAP1500 | DUKHPROGEN00MTAP2500 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2800 | Steel Gate & Barrier gates_2nd_Sub | 10 | 10 | 0% | 2013-07-17 | 2013-07-28 | 2013-07-17 | 2013-07-28 | 63 | No | DUKHPROGEN00MTAP1800 | DUKHPROGEN00MTAP2800 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2630 | Steel Ladder_2nd_Sub | 10 | 10 | 0% | 2013-06-06 | 2013-06-17 | 2013-06-06 | 2013-06-17 | 36 | No | DUKHPROGEN00MTAP1630 | DUKHPROGEN00MTAP2630 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2740 | Stone Boulders_2nd_Sub | 10 | 10 | 0% | 2013-06-30 | 2013-07-10 | 2013-06-30 | 2013-07-10 | 127 | No | DUKHPROGEN00MTAP1740 | DUKHPROGEN00MTAP2740 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2110 | Stone Cladding_2nd_Sub | 10 | 10 | 0% | 2013-02-05 | 2013-02-17 | 2013-02-05 | 2013-02-17 | 125 | No | DUKHPROGEN00MTAP1110 | DUKHPROGEN00MTAP2110 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2250 | Street Light Post Set_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 125 | No | DUKHPROGEN00MTAP1250 | DUKHPROGEN00MTAP2250 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2620 | Structural Steel_2nd_Sub | 10 | 10 | 0% | 2013-05-20 | 2013-05-30 | 2013-05-20 | 2013-05-30 | 28 | No | DUKHPROGEN00MTAP1620 | DUKHPROGEN00MTAP2620 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2280 | Telephone Fittings & Accessories_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 70 | No | DUKHPROGEN00MTAP1280 | DUKHPROGEN00MTAP2280 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2290 | Television devices,Fittings & Access._2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 99 | No | DUKHPROGEN00MTAP1290 | DUKHPROGEN00MTAP2290 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2050 | Thermal Insulation_2nd_Sub | 15 | 15 | 0% | 2013-02-19 | 2013-03-07 | 2013-02-19 | 2013-03-07 | 116 | No | DUKHPROGEN00MTAP1050 | DUKHPROGEN00MTAP2050 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2270 | Video Com System_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 70 | No | DUKHPROGEN00MTAP1270 | DUKHPROGEN00MTAP2270 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2220 | Water Chiller_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 50 | No | DUKHPROGEN00MTAP1220 | DUKHPROGEN00MTAP2220 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2230 | Water Heater_2nd_Sub | 10 | 10 | 0% | 2013-05-02 | 2013-05-13 | 2013-05-02 | 2013-05-13 | 59 | No | DUKHPROGEN00MTAP1230 | DUKHPROGEN00MTAP2230 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2640 | Water meter_2nd_Sub | 10 | 10 | 0% | 2013-06-24 | 2013-07-04 | 2013-06-24 | 2013-07-04 | 56 | No | DUKHPROGEN00MTAP1640 | DUKHPROGEN00MTAP2640 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2680 | Water Tank_2nd_Sub | 10 | 10 | 0% | 2013-07-11 | 2013-07-22 | 2013-07-11 | 2013-07-22 | 41 | No | DUKHPROGEN00MTAP1680 | DUKHPROGEN00MTAP2680 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2490 | Wooden Doors_2nd_Sub | 10 | 10 | 0% | 2013-05-06 | 2013-05-16 | 2013-05-06 | 2013-05-16 | 26 | No | DUKHPROGEN00MTAP1490 | DUKHPROGEN00MTAP2490 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DUKHPROGEN00MTSM2570 | Wooden Hand Rails _2nd_Sub | 10 | 10 | 0% | 2013-05-29 | 2013-06-09 | 2013-05-29 | 2013-06-09 | 61 | No | DUKHPROGEN00MTAP1570 | DUKHPROGEN00MTSM2580, DUKHPROGEN00MTAP2570 | 0 | 0 | 2ND SUBMISSION OF MATERIAL
DHBL.K25.L20.25 2ND APPROVAL OF MATERIAL |  | 243 | 243 | 0% | 2013-01-30 | 2013-11-16 | 2013-01-30 | 2013-11-16 | 114 |  |  |  | 0 | 0
DUKHPROGEN00MTAP2400 | Access Ladder_2nd_App | 30 | 30 | 0% | 2013-05-12 | 2013-06-15 | 2013-05-12 | 2013-06-15 | 91 | No | DUKHPROGEN00MTSM2400 | DUKHPROGEN00PRDV3400 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2470 | Aluminum Windows_2nd_App | 30 | 30 | 0% | 2013-05-18 | 2013-06-20 | 2013-05-18 | 2013-06-20 | 71 | No | DUKHPROGEN00MTSM2470 | DUKHPROGEN00PRDV3470 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2460 | Aluminum Doors_2nd_App | 30 | 30 | 0% | 2013-05-18 | 2013-06-20 | 2013-05-18 | 2013-06-20 | 65 | No | DUKHPROGEN00MTSM2460 | DUKHPROGEN00PRDV3460 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2410 | Aluminum Slat Screen_2nd_App | 30 | 30 | 0% | 2013-05-12 | 2013-06-15 | 2013-05-12 | 2013-06-15 | 81 | No | DUKHPROGEN00MTSM2410 | DUKHPROGEN00PRDV3410 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2310 | Aluminum Tile false ceiling_2nd_App | 30 | 30 | 0% | 2013-05-18 | 2013-06-20 | 2013-05-18 | 2013-06-20 | 42 | No | DUKHPROGEN00MTSM2310 | DUKHPROGEN00PRDV3310 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2350 | Bollard Lamp_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 110 | No | DUKHPROGEN00MTSM2350 | DUKHPROGEN00PRDV3350 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2330 | Booster Pump_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 35 | No | DUKHPROGEN00MTSM2330 | DUKHPROGEN00PRDV3330 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2730 | Car Parking Shed_2nd_App | 30 | 30 | 0% | 2013-07-11 | 2013-08-18 | 2013-07-11 | 2013-08-18 | 127 | No | DUKHPROGEN00MTSM2730 | DUKHPROGEN00PRDV3730 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2120 | Ceramic Tile_2nd_App | 30 | 30 | 0% | 2013-02-18 | 2013-03-24 | 2013-02-18 | 2013-03-24 | 73 | No | DUKHPROGEN00MTSM2120 | DUKHPROGEN00PRDV3120 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2550 | Closets /wardrobe& Pelmets_2nd_App | 30 | 30 | 0% | 2013-06-10 | 2013-07-14 | 2013-06-10 | 2013-07-14 | 43 | No | DUKHPROGEN00MTSM2550 | DUKHPROGEN00PRDV3550 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2090 | Cobble stone finish _2nd_App | 30 | 30 | 0% | 2013-02-18 | 2013-03-24 | 2013-02-18 | 2013-03-24 | 113 | No | DUKHPROGEN00MTSM2090 | DUKHPROGEN00PRDV3090 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2160 | Copper Pipes_2nd_App | 30 | 30 | 0% | 2013-04-27 | 2013-05-30 | 2013-04-27 | 2013-05-30 | 54 | No | DUKHPROGEN00MTSM2160 | DUKHPROGEN00PRDV3160 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2560 | Counters, Cabinets & Shelves_2nd_App | 30 | 30 | 0% | 2013-06-10 | 2013-07-14 | 2013-06-10 | 2013-07-14 | 43 | No | DUKHPROGEN00MTSM2560 | DUKHPROGEN00PRDV3560 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2360 | Digital Alarm Communicator Panel_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 49 | No | DUKHPROGEN00MTSM2360 | DUKHPROGEN00PRDV3360 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2540 | Ductile Iron Pipes_2nd_App | 30 | 30 | 0% | 2013-06-18 | 2013-07-22 | 2013-06-18 | 2013-07-22 | 5 | No | DUKHPROGEN00MTSM2540 | DUKHPROGEN00PRDV3540 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2420 | Epoxy_2nd_App | 30 | 30 | 0% | 2013-06-10 | 2013-07-14 | 2013-06-10 | 2013-07-14 | 134 | No | DUKHPROGEN00MTSM2420 | DUKHPROGEN00PRDV3420 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2340 | Exhaust Air louver_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 76 | No | DUKHPROGEN00MTSM2340 | DUKHPROGEN00PRDV3340 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2530 | Exhaust Fan_2nd_App | 30 | 30 | 0% | 2013-06-18 | 2013-07-22 | 2013-06-18 | 2013-07-22 | 61 | No | DUKHPROGEN00MTSM2530 | DUKHPROGEN00PRDV3530 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2710 | External signage _2nd_App | 30 | 30 | 0% | 2013-07-11 | 2013-08-18 | 2013-07-11 | 2013-08-18 | 172 | No | DUKHPROGEN00MTSM2710 | DUKHPROGEN00PRDV3710 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2850 | Fences_2nd_App | 30 | 30 | 0% | 2013-08-19 | 2013-09-22 | 2013-08-19 | 2013-09-22 | 126 | No | DUKHPROGEN00MTSM2850 | DUKHPROGEN00PRDV3850 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2370 | Fire Blanket_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 98 | No | DUKHPROGEN00MTSM2370 | DUKHPROGEN00PRDV3370 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2380 | Fire Extinguisher_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 90 | No | DUKHPROGEN00MTSM2380 | DUKHPROGEN00PRDV3380 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2690 | Fire Hydrant_2nd_App | 30 | 30 | 0% | 2013-07-23 | 2013-08-29 | 2013-07-23 | 2013-08-29 | 15 | No | DUKHPROGEN00MTSM2690 | DUKHPROGEN00PRDV3690 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2210 | Fire Resistant Cables_2nd_App | 30 | 30 | 0% | 2013-04-27 | 2013-05-30 | 2013-04-27 | 2013-05-30 | 105 | No | DUKHPROGEN00MTSM2210 | DUKHPROGEN00PRDV3210 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2840 | Gate Values_2nd_App | 30 | 30 | 0% | 2013-09-05 | 2013-10-09 | 2013-09-05 | 2013-10-09 | 67 | No | DUKHPROGEN00MTSM2840 | DUKHPROGEN00PRDV3840 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2780 | Gazebo Structure_2nd_App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 67 | No | DUKHPROGEN00MTSM2780 | DUKHPROGEN00PRDV3780 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2480 | Granite_2nd_App | 30 | 30 | 0% | 2013-05-18 | 2013-06-20 | 2013-05-18 | 2013-06-20 | 46 | No | DUKHPROGEN00MTSM2480 | DUKHPROGEN00PRDV3480 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2390 | GRC Panels_2nd_App | 30 | 30 | 0% | 2013-05-12 | 2013-06-15 | 2013-05-12 | 2013-06-15 | 74 | No | DUKHPROGEN00MTSM2390 | DUKHPROGEN00PRDV3390 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2300 | Gypsum Board false ceiling_2nd_App | 30 | 30 | 0% | 2013-05-12 | 2013-06-15 | 2013-05-12 | 2013-06-15 | 32 | No | DUKHPROGEN00MTSM2300 | DUKHPROGEN00PRDV3300 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2660 | Interlock works_2nd_App | 30 | 30 | 0% | 2013-06-24 | 2013-07-28 | 2013-06-24 | 2013-07-28 | 85 | No | DUKHPROGEN00MTSM2660 | DUKHPROGEN00PRDV3660 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2450 | Ironmongeries_2nd_App | 30 | 30 | 0% | 2013-05-18 | 2013-06-20 | 2013-05-18 | 2013-06-20 | 26 | No | DUKHPROGEN00MTSM2450 | DUKHPROGEN00PRDV3450 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2870 | Irrigation Controller_2nd_App | 30 | 30 | 0% | 2013-10-10 | 2013-11-16 | 2013-10-10 | 2013-11-16 | 37 | No | DUKHPROGEN00MTSM2870 | DUKHPROGEN00PRDV3870 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2670 | Irrigation Pipes_2nd_App | 30 | 30 | 0% | 2013-06-24 | 2013-07-28 | 2013-06-24 | 2013-07-28 | 76 | No | DUKHPROGEN00MTSM2670 | DUKHPROGEN00PRDV3670 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2650 | Isolating Values_2nd_App | 30 | 30 | 0% | 2013-07-06 | 2013-08-08 | 2013-07-06 | 2013-08-08 | 4 | No | DUKHPROGEN00MTSM2650 | DUKHPROGEN00PRDV3650 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2200 | Isolators_2nd_App | 30 | 30 | 0% | 2013-04-27 | 2013-05-30 | 2013-04-27 | 2013-05-30 | 108 | No | DUKHPROGEN00MTSM2200 | DUKHPROGEN00PRDV3200 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2600 | kerb works_2nd_App | 30 | 30 | 0% | 2013-06-06 | 2013-07-10 | 2013-06-06 | 2013-07-10 | 78 | No | DUKHPROGEN00MTSM2600 | DUKHPROGEN00PRDV3600 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2770 | Kitchen Water Filter_2nd_App | 30 | 30 | 0% | 2013-08-13 | 2013-09-16 | 2013-08-13 | 2013-09-16 | 9 | No | DUKHPROGEN00MTSM2770 | DUKHPROGEN00PRDV3770 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2520 | Lift Pump_2nd_App | 30 | 30 | 0% | 2013-06-18 | 2013-07-22 | 2013-06-18 | 2013-07-22 | 20 | No | DUKHPROGEN00MTSM2520 | DUKHPROGEN00PRDV3520 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2190 | Lights & Fixtures_2nd_App | 30 | 30 | 0% | 2013-04-27 | 2013-05-30 | 2013-04-27 | 2013-05-30 | 87 | No | DUKHPROGEN00MTSM2190 | DUKHPROGEN00PRDV3190 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2590 | Manhole Covers and Frames_2nd_App | 30 | 30 | 0% | 2013-05-29 | 2013-07-02 | 2013-05-29 | 2013-07-02 | 63 | No | DUKHPROGEN00MTSM2590 | DUKHPROGEN00PRDV3590 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2810 | Nozzle Jet_2nd_App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 97 | No | DUKHPROGEN00MTSM2810 | DUKHPROGEN00PRDV3810 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2320 | Paints_2nd_App | 30 | 30 | 0% | 2013-05-23 | 2013-06-26 | 2013-05-23 | 2013-06-26 | 10 | No | DUKHPROGEN00MTSM2320 | DUKHPROGEN00PRDV3320 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2140 | Pitch roofing_2nd_App | 30 | 30 | 0% | 2013-03-26 | 2013-04-29 | 2013-03-26 | 2013-04-29 | 87 | No | DUKHPROGEN00MTSM2140 | DUKHPROGEN00PRDV3140 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2790 | Plantation(Grass,Trees)_2nd_App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 22 | No | DUKHPROGEN00MTSM2790 | DUKHPROGEN00PRDV3790 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2040 | Plastering & Accessories_2nd_App | 30 | 30 | 0% | 2013-01-30 | 2013-03-06 | 2013-01-30 | 2013-03-06 | 115 | No | DUKHPROGEN00MTSM2040 | DUKHPROGEN00PRDV3040 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2080 | Polyethylene Pipes_2nd_App | 30 | 30 | 0% | 2013-03-09 | 2013-04-11 | 2013-03-09 | 2013-04-11 | 55 | No | DUKHPROGEN00MTSM2080 | DUKHPROGEN00PRDV3080 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2130 | Porcelain Tile_2nd_App | 30 | 30 | 0% | 2013-02-18 | 2013-03-24 | 2013-02-18 | 2013-03-24 | 82 | No | DUKHPROGEN00MTSM2130 | DUKHPROGEN00PRDV3130 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2820 | Pre-cast Boundary Wall _2nd_App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 40 | No | DUKHPROGEN00MTSM2820 | DUKHPROGEN00PRDV3820 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2440 | PVC Doors_2nd_App | 30 | 30 | 0% | 2013-05-18 | 2013-06-20 | 2013-05-18 | 2013-06-20 | 92 | No | DUKHPROGEN00MTSM2440 | DUKHPROGEN00PRDV3440 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2610 | PVC Tent_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 30 | No | DUKHPROGEN00MTSM2610 | DUKHPROGEN00PRDV3610 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2860 | Remote Control Value_2nd_App | 30 | 30 | 0% | 2013-09-23 | 2013-10-29 | 2013-09-23 | 2013-10-29 | 52 | No | DUKHPROGEN00MTSM2860 | DUKHPROGEN00PRDV3860 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2720 | Road Marking_2nd_App | 30 | 30 | 0% | 2013-07-11 | 2013-08-18 | 2013-07-11 | 2013-08-18 | 172 | No | DUKHPROGEN00MTSM2720 | DUKHPROGEN00PRDV3720 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2700 | Road Works Materials_2nd_App | 30 | 30 | 0% | 2013-07-11 | 2013-08-18 | 2013-07-11 | 2013-08-18 | 189 | No | DUKHPROGEN00MTSM2700 | DUKHPROGEN00PRDV3700 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2430 | Roller Shutter_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 218 | No | DUKHPROGEN00MTSM2430 | DUKHPROGEN00PRDV3430 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2150 | Sanitary Fittings_2nd_App | 30 | 30 | 0% | 2013-04-27 | 2013-05-30 | 2013-04-27 | 2013-05-30 | 51 | No | DUKHPROGEN00MTSM2150 | DUKHPROGEN00PRDV3150 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2100 | Slate Tile_2nd_App | 30 | 30 | 0% | 2013-02-18 | 2013-03-24 | 2013-02-18 | 2013-03-24 | 118 | No | DUKHPROGEN00MTSM2100 | DUKHPROGEN00PRDV3100 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2170 | SMDB_2nd_App | 30 | 30 | 0% | 2013-04-27 | 2013-05-30 | 2013-04-27 | 2013-05-30 | 75 | No | DUKHPROGEN00MTSM2170 | DUKHPROGEN00PRDV3170 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2260 | Smoke Detector_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 90 | No | DUKHPROGEN00MTSM2260 | DUKHPROGEN00PRDV3260 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2830 | Solenoid Values_2nd_App | 30 | 30 | 0% | 2013-08-19 | 2013-09-22 | 2013-08-19 | 2013-09-22 | 82 | No | DUKHPROGEN00MTSM2830 | DUKHPROGEN00PRDV3830 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2750 | Speed Humps _2nd_App | 30 | 30 | 0% | 2013-07-11 | 2013-08-18 | 2013-07-11 | 2013-08-18 | 126 | No | DUKHPROGEN00MTSM2750 | DUKHPROGEN00PRDV3750 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2240 | Split AC_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 84 | No | DUKHPROGEN00MTSM2240 | DUKHPROGEN00PRDV3240 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2760 | Sprinklers_2nd_App | 30 | 30 | 0% | 2013-07-11 | 2013-08-18 | 2013-07-11 | 2013-08-18 | 138 | No | DUKHPROGEN00MTSM2760 | DUKHPROGEN00PRDV3760 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2510 | Stainless Steel Cover_2nd_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 29 | No | DUKHPROGEN00MTSM2510 | DUKHPROGEN00PRDV3510 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2580 | Stainless Steel Handrail_2nd_App | 30 | 30 | 0% | 2013-06-10 | 2013-07-14 | 2013-06-10 | 2013-07-14 | 61 | No | DUKHPROGEN00MTSM2580 | DUKHPROGEN00PRDV3580 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2500 | Steel Door_2nd_App | 30 | 30 | 0% | 2013-05-26 | 2013-06-29 | 2013-05-26 | 2013-06-29 | 29 | No | DUKHPROGEN00MTSM2500 | DUKHPROGEN00PRDV3500 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2800 | Steel Gate & Barrier gates_2nd_App | 30 | 30 | 0% | 2013-07-29 | 2013-09-04 | 2013-07-29 | 2013-09-04 | 63 | No | DUKHPROGEN00MTSM2800 | DUKHPROGEN00PRDV3800 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2630 | Steel Ladder_2nd_App | 30 | 30 | 0% | 2013-06-18 | 2013-07-22 | 2013-06-18 | 2013-07-22 | 36 | No | DUKHPROGEN00MTSM2630 | DUKHPROGEN00PRDV3630 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2740 | Stone Boulders_2nd_App | 30 | 30 | 0% | 2013-07-11 | 2013-08-18 | 2013-07-11 | 2013-08-18 | 127 | No | DUKHPROGEN00MTSM2740 | DUKHPROGEN00PRDV3740 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2110 | Stone Cladding_2nd_App | 30 | 30 | 0% | 2013-02-18 | 2013-03-24 | 2013-02-18 | 2013-03-24 | 125 | No | DUKHPROGEN00MTSM2110 | DUKHPROGEN00PRDV3110 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2250 | Street Light Post Set_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 125 | No | DUKHPROGEN00MTSM2250 | DUKHPROGEN00PRDV3250 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2620 | Structural Steel_2nd_App | 30 | 30 | 0% | 2013-06-01 | 2013-07-04 | 2013-06-01 | 2013-07-04 | 28 | No | DUKHPROGEN00MTSM2620 | DUKHPROGEN00PRDV3620 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2280 | Telephone Fittings & Accessories_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 70 | No | DUKHPROGEN00MTSM2280 | DUKHPROGEN00PRDV3280 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2290 | Television devices,Fittings & Access._2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 99 | No | DUKHPROGEN00MTSM2290 | DUKHPROGEN00PRDV3290 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2050 | Thermal Insulation_2nd_App | 30 | 30 | 0% | 2013-03-09 | 2013-04-11 | 2013-03-09 | 2013-04-11 | 116 | No | DUKHPROGEN00MTSM2050 | DUKHPROGEN00PRDV3050 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2270 | Video Com System_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 70 | No | DUKHPROGEN00MTSM2270 | DUKHPROGEN00PRDV3270 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2220 | Water Chiller_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 50 | No | DUKHPROGEN00MTSM2220 | DUKHPROGEN00PRDV3220 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2230 | Water Heater_2nd_App | 30 | 30 | 0% | 2013-05-14 | 2013-06-17 | 2013-05-14 | 2013-06-17 | 59 | No | DUKHPROGEN00MTSM2230 | DUKHPROGEN00PRDV3230 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2640 | Water meter_2nd_App | 30 | 30 | 0% | 2013-07-06 | 2013-08-08 | 2013-07-06 | 2013-08-08 | 56 | No | DUKHPROGEN00MTSM2640 | DUKHPROGEN00PRDV3640 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2680 | Water Tank_2nd_App | 30 | 30 | 0% | 2013-07-23 | 2013-08-29 | 2013-07-23 | 2013-08-29 | 41 | No | DUKHPROGEN00MTSM2680 | DUKHPROGEN00PRDV3680 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2490 | Wooden Doors_2nd_App | 30 | 30 | 0% | 2013-05-18 | 2013-06-20 | 2013-05-18 | 2013-06-20 | 26 | No | DUKHPROGEN00MTSM2490 | DUKHPROGEN00PRDV3490 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DUKHPROGEN00MTAP2570 | Wooden Hand Rails _2nd_App | 30 | 30 | 0% | 2013-06-10 | 2013-07-14 | 2013-06-10 | 2013-07-14 | 61 | No | DUKHPROGEN00MTSM2570 | DUKHPROGEN00PRDV3570 | 0 | 0 | 2ND APPROVAL OF MATERIAL
DHBL.K25.L25 MANUFACTURING, PROCUREMENT & DELIVERY |  | 415 | 415 | 0% | 2012-12-27 | 2014-02-14 | 2012-12-27 | 2014-02-14 | 140 |  |  |  | 0 | 0
DUKHPROGEN00PRDV3400 | Proc & Del Access Ladder | 90 | 90 | 0% | 2013-06-16 | 2013-09-13 | 2013-06-16 | 2013-09-13 | 109 | No | DUKHPROGEN00MTAP2400 | DUKHCONP2AMKARRF3660, DUKHCONP1AMKARRF3660, DUKHCONP1AZ1ARRF3660, DUKHCONP03MKARRF3660 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3410 | Proc & Del Aluminium Slat Screen | 120 | 120 | 0% | 2013-06-16 | 2013-10-13 | 2013-06-16 | 2013-10-13 | 98 | No | DUKHPROGEN00MTAP2410 | DUKHCONP03MKARRF3650, DUKHCONP1AZ1ARRF3650, DUKHCONP1AMKARRF3650 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3460 | Proc & Del Aluminum Doors | 120 | 120 | 0% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18 | 80 | No | DUKHENGP2ADWARAP4930, DUKHENGP2BDWARAP5310, DUKHENGP1ADWARAP4130, DUKHENGP1BDWARAP4530, DUKHPROGEN00MTAP2460, DUKHENGP03DWARAP5690 | DUKHCONP1AZ1ARGF3070, DUKHCONP03MKARFF3370, DUKHCONP03MKARGF3070, DUKHCONP1AMKARGF3070, DUKHCONP1AMKARFF3370 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3310 | Proc & Del Aluminum Tile false ceiling | 120 | 120 | 0% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18 | 53 | No | DUKHENGP03DWARAP5680, DUKHPROGEN00MTAP2310, DUKHENGP1ADWARAP4120, DUKHENGP1BDWARAP4490 | DUKHCONP1AMKARGF3055, DUKHCONP1AZ1ARGF3055, DUKHCONP03MKARGF3055, DUKHCONP03MKARFF3355 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3470 | Proc & Del Aluminum Windows | 120 | 120 | 0% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18 | 87 | No | DUKHPROGEN00MTAP2470, DUKHENGP1BDWARAP4530, DUKHENGP03DWARAP5690, DUKHENGP1ADWARAP4130, DUKHENGP2BDWARAP5310, DUKHENGP2ADWARAP4930 | DUKHCONP1AMKARFF3380, DUKHCONP1AZ1ARGF3080, DUKHCONP2AMKARGF3080, DUKHCONP1AMKARGF3080, DUKHCONP03MKARGF3080, DUKHCONP03MKARFF3380 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3000 | Proc & Del Anti Termite | 7 | 7 | 0% | 2012-12-27 | 2013-01-02 | 2012-12-27 | 2013-01-02 | 54 | No | DUKHPROGEN00MTAP1000 | DUKHCONP1AZ1STUG1005 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3010 | Proc & Del Block Work | 10 | 10 | 0% | 2013-01-02 | 2013-01-11 | 2013-01-02 | 2013-01-11 | 70 | No | DUKHPROGEN00MTAP1010 | DUKHCONP1AZ1STUG1020, DUKHCONP03MKARFF3300, DUKHCONP1AZ1ARGF3000, DUKHCONP2AMKARGF3000, DUKHCONP1AMKARFF3300 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3350 | Proc & Del Bollard Lamp | 120 | 120 | 0% | 2013-07-29 | 2013-11-25 | 2013-07-29 | 2013-11-25 | 111 | No | DUKHENGI03DWELAP5840, DUKHENGI03DWSTAP5850, DUKHENGI2ADWSTAP5090, DUKHENGI1BDWELAP4680, DUKHENGI1ADWELAP4280, DUKHENGI1BDWSTAP4690, DUKHENGI2BDWSTAP5470, DUKHENGI2ADWELAP5080, DUKHPROGEN00MTAP2350, DUKHENGI1ADWSTAP4290, DUKHENGI2BDWELAP5460 | DUKHCONI2AZ1STGL5255, DUKHCONI03Z1STGL5255, DUKHCONI1AZ1STGL5255 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3330 | Proc & Del Booster Pump | 120 | 120 | 0% | 2013-07-05 | 2013-11-01 | 2013-07-05 | 2013-11-01 | 45 | No | DUKHENGP1BDWMEAP4620, DUKHENGP2BDWMEAP5400, DUKHENGP2ADWMEAP5010, DUKHENGP2BDWMEAP5390, DUKHPROGEN00MTAP2330, DUKHENGP1BDWMEAP4610, DUKHENGP2ADWMEAP5020, DUKHENGP1ADWMEAP4210, DUKHENGP1ADWMEAP4220, DUKHENGP03DWMEAP5770, DUKHENGP03DWMEAP5780 | DUKHCONP2AMKWEEX5065, DUKHCONP03Z1WTEX5065, DUKHCONP1AZ1WEEX5065, DUKHCONP1AMKWEEX5065 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3180 | Proc & Del Cables & Wires | 120 | 120 | 0% | 2013-04-21 | 2013-08-18 | 2013-04-21 | 2013-08-18 | 69 | No | DUKHENGP1ADWELAP4160, DUKHENGP1BDWELAP4560, DUKHENGP2BDWELAP5340, DUKHPROGEN00MTAP1180, DUKHENGP2ADWELAP4960, DUKHENGP03DWELAP5720 | DUKHCONP03MKELFF4045, DUKHCONP03MKELGF4010, DUKHCONP2AMKELGF4010, DUKHCONP1AMKELFF4045, DUKHCONP1AMKELGF4010, DUKHCONP1AZ1ELGF4005 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3730 | Proc & Del Car Parking Shed | 90 | 90 | 0% | 2013-08-19 | 2013-11-16 | 2013-08-19 | 2013-11-16 | 151 | No | DUKHPROGEN00MTAP2730, DUKHENGI2ADWPSAP5140, DUKHENGI1ADWPSAP4340, DUKHENGI1BDWPSAP4740, DUKHENGI03DWPSAP5900, DUKHENGI2BDWPSAP5520 | DUKHCONI1AZ1PSGL7010, DUKHCONI2AZ1PSGL7010, DUKHCONI03Z1PSGL7010 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3120 | Proc & Del Ceramic Tile | 120 | 120 | 0% | 2013-04-30 | 2013-08-27 | 2013-04-30 | 2013-08-27 | 49 | No | DUKHENGP03DWARAP5640, DUKHPROGEN00MTAP2120, DUKHENGP1BDWARAP4500, DUKHENGP2BDWARAP5260, DUKHENGP2ADWARAP4880, DUKHENGP1ADWARAP4080 | DUKHCONP1AMKARGF3020, DUKHCONP03MKARGF3020, DUKHCONP2AMKARGF3020, DUKHCONP1AZ1ARGF3020, DUKHCONP1AMKARFF3320, DUKHCONP03MKARFF3320 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3550 | Proc & Del Closets /wardrobe& Pelmets | 120 | 120 | 0% | 2013-07-15 | 2013-11-11 | 2013-07-15 | 2013-11-11 | 54 | No | DUKHPROGEN00MTAP2550, DUKHENGP2ADWARAP4940, DUKHENGP03DWARAP5700, DUKHENGP2BDWARAP5320, DUKHENGP1ADWARAP4140, DUKHENGP1BDWARAP4540 | DUKHCONP1AZ1ARGF3075, DUKHCONP03MKARFF3375, DUKHCONP1AMKARGF3075, DUKHCONP1AMKARFF3375, DUKHCONP2AMKARGF3075, DUKHCONP03MKARGF3075 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3090 | Proc & Del Cobble stone finish | 120 | 120 | 0% | 2013-04-30 | 2013-08-27 | 2013-04-30 | 2013-08-27 | 96 | No | DUKHENGP2ADWARAP4900, DUKHENGP1ADWARAP4100, DUKHPROGEN00MTAP2090, DUKHENGP1BDWARAP4520, DUKHENGP2BDWARAP5280, DUKHENGP03DWARAP5660 | DUKHCONP03MKARGF3040, DUKHCONP1AMKARGF3040, DUKHCONP1AZ1ARGF3040, DUKHCONP2AMKARGF3040 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3020 | Proc & Del Concrete | 7 | 7 | 0% | 2012-12-28 | 2013-01-03 | 2012-12-28 | 2013-01-03 | 46 | No | DUKHPROGEN00MTAP1020 | DUKHCONP2AZ1STUG1015, DUKHCONP03Z1STUG1015, DUKHCONP1AZ1STUG1010, DUKHCONP1AZ1STUG1015 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3160 | Proc & Del Copper Pipes | 90 | 90 | 0% | 2013-05-31 | 2013-08-28 | 2013-05-31 | 2013-08-28 | 63 | No | DUKHPROGEN00MTAP2160, DUKHENGP2ADWMEAP5040, DUKHENGP1BDWMEAP4640, DUKHENGP03DWMEAP5800, DUKHENGP1ADWMEAP4240, DUKHENGP2BDWMEAP5420 | DUKHCONP1AMKACFF4615, DUKHCONP03MKACFF4615, DUKHCONP03MKACGF4600, DUKHCONP1AZ1ACGF4600, DUKHCONP1AMKACGF4600, DUKHCONP2AMKACGF4600 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3560 | Proc & Del Counters, Cabinets & Shelves | 120 | 120 | 0% | 2013-07-15 | 2013-11-11 | 2013-07-15 | 2013-11-11 | 54 | No | DUKHENGP03DWARAP5700, DUKHENGP1ADWARAP4140, DUKHENGP2ADWARAP4940, DUKHENGP1BDWARAP4540, DUKHENGP2BDWARAP5320, DUKHPROGEN00MTAP2560 | DUKHCONP1AMKARGF3075, DUKHCONP1AMKARFF3375, DUKHCONP2AMKARGF3075, DUKHCONP03MKARFF3375, DUKHCONP1AZ1ARGF3075, DUKHCONP03MKARGF3075 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3360 | Proc & Del Digital Alarm Communicator Panel | 120 | 120 | 0% | 2013-07-05 | 2013-11-01 | 2013-07-05 | 2013-11-01 | 61 | No | DUKHENGP1ADWELAP4180, DUKHENGP03DWELAP5740, DUKHPROGEN00MTAP2360, DUKHENGP2BDWELAP5360, DUKHENGP2ADWELAP4980, DUKHENGP1BDWELAP4580 | DUKHCONP2AMKELGF4015, DUKHCONP1AMKELFF4055, DUKHCONP03MKELGF4015, DUKHCONP1AZ1ELGF4015, DUKHCONP1AMKELGF4015, DUKHCONP03MKELFF4055 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3540 | Proc & Del Ductile Iron Pipes | 110 | 110 | 0% | 2013-07-23 | 2013-11-09 | 2013-07-23 | 2013-11-09 | 6 | No | DUKHENGI2BDWFFAP5440, DUKHPROGEN00MTAP2540, DUKHENGI1BDWFFAP4660, DUKHENGI2ADWFFAP5060, DUKHENGI1ADWFFAP4260, DUKHENGI03DWFFAP5820 | DUKHCONI1AZ1FFGL5190, DUKHCONI2AZ1FFGL5190, DUKHCONI03Z1FFGL5190 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3420 | Proc & Del Epoxy | 40 | 40 | 0% | 2013-07-15 | 2013-08-23 | 2013-07-15 | 2013-08-23 | 163 | No | DUKHENGP1BDWARAP4450, DUKHENGP03DWARAP5610, DUKHPROGEN00MTAP2420, DUKHENGP2ADWARAP4850, DUKHENGP1ADWARAP4050, DUKHENGP2BDWARAP5230 | DUKHCONP1AMKARRF3620, DUKHCONP1AMKARGF3095, DUKHCONP1AZ1ARRF3620, DUKHCONP2AMKARGF3095, DUKHCONP03MKARRF3620, DUKHCONP03MKARGF3095 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3340 | Proc & Del Exhaust Air louver | 90 | 90 | 0% | 2013-07-05 | 2013-10-02 | 2013-07-05 | 2013-10-02 | 93 | No | DUKHPROGEN00MTAP2340, DUKHENGP1ADWMEAP4240, DUKHENGP03DWMEAP5800, DUKHENGP2BDWMEAP5420, DUKHENGP2ADWMEAP5040, DUKHENGP1BDWMEAP4640 | DUKHCONP1AZ1ACGF4605, DUKHCONP03MKACGF4605, DUKHCONP1AMKACFF4620, DUKHCONP1AMKACGF4605, DUKHCONP03MKACFF4620, DUKHCONP2AMKACGF4605 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3530 | Proc & Del Exhaust Fan | 90 | 90 | 0% | 2013-07-23 | 2013-10-20 | 2013-07-23 | 2013-10-20 | 75 | No | DUKHENGP2ADWMEAP5040, DUKHENGP1BDWMEAP4640, DUKHPROGEN00MTAP2530, DUKHENGP03DWMEAP5800, DUKHENGP1ADWMEAP4240, DUKHENGP2BDWMEAP5420 | DUKHCONP1AMKACGF4605, DUKHCONP1AZ1ACGF4605, DUKHCONP03MKACGF4605, DUKHCONP2AMKACGF4605 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3710 | Proc & Del External signage | 60 | 60 | 0% | 2013-08-19 | 2013-10-17 | 2013-08-19 | 2013-10-17 | 205 | No | DUKHPROGEN00MTAP2710 | DUKHCONI1AZ1RWGL6030, DUKHCONI2AZ1RWGL6030, DUKHCONI03Z1RWGL6030 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3850 | Proc & Del Fences | 90 | 90 | 0% | 2013-09-23 | 2013-12-21 | 2013-09-23 | 2013-12-21 | 151 | No | DUKHPROGEN00MTAP2850 | DUKHCONI1ASBIWGL7435, DUKHCONI2ASBIWGL7435, DUKHCONI03SBIWGL7435 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3370 | Proc & Del Fire Blanket | 60 | 60 | 0% | 2013-07-05 | 2013-09-02 | 2013-07-05 | 2013-09-02 | 121 | No | DUKHENGP1BDWMEAP4630, DUKHENGP1ADWMEAP4230, DUKHPROGEN00MTAP2370, DUKHENGP2ADWMEAP5030, DUKHENGP2BDWMEAP5410, DUKHENGP03DWMEAP5790 | DUKHCONP03MKELGF4015, DUKHCONP1AMKELGF4015, DUKHCONP2AMKELGF4015, DUKHCONP1AZ1ELGF4015 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3380 | Proc & Del Fire Extinguisher | 70 | 70 | 0% | 2013-07-05 | 2013-09-12 | 2013-07-05 | 2013-09-12 | 111 | No | DUKHENGP1BDWMEAP4630, DUKHENGP2ADWMEAP5030, DUKHENGP03DWMEAP5790, DUKHPROGEN00MTAP2380, DUKHENGP1ADWMEAP4230, DUKHENGP2BDWMEAP5410 | DUKHCONP03MKELGF4015, DUKHCONP1AMKELGF4015, DUKHCONP2AMKELGF4015, DUKHCONP1AZ1ELGF4015 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3690 | Proc & Del Fire Hydrant | 100 | 100 | 0% | 2013-08-30 | 2013-12-07 | 2013-08-30 | 2013-12-07 | 18 | No | DUKHENGI2BDWFFAP5440, DUKHENGI1ADWFFAP4260, DUKHENGI03DWFFAP5820, DUKHENGI2ADWFFAP5060, DUKHPROGEN00MTAP2690, DUKHENGI1BDWFFAP4660 | DUKHCONI1AZ1FFGL5205, DUKHCONI2AZ1FFGL5205, DUKHCONI03Z1FFGL5205 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3210 | Proc & Del Fire Resistant Cables | 90 | 90 | 0% | 2013-05-31 | 2013-08-28 | 2013-05-31 | 2013-08-28 | 126 | No | DUKHENGP03DWELAP5740, DUKHPROGEN00MTAP2210, DUKHENGP2ADWELAP4980, DUKHENGP1BDWELAP4580, DUKHENGP2BDWELAP5360, DUKHENGP1ADWELAP4180 | DUKHCONP03MKELGF4015, DUKHCONP1AZ1ELGF4015, DUKHCONP1AMKELFF4055, DUKHCONP03MKELFF4055, DUKHCONP2AMKELGF4015, DUKHCONP1AMKELGF4015 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3070 | Proc & Del Floor drains & Cleanouts | 40 | 40 | 0% | 2013-02-25 | 2013-04-05 | 2013-02-25 | 2013-04-05 | 32 | No | DUKHPROGEN00MTAP1070 | DUKHCONP1AZ1PLUG4300, DUKHCONP03Z1PLUG4300, DUKHCONP2AZ1PLUG4300 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3840 | Proc & Del Gate Values | 90 | 90 | 0% | 2013-10-10 | 2014-01-07 | 2013-10-10 | 2014-01-07 | 82 | No | DUKHENGI03DWIRAP5870, DUKHENGI1ADWIRAP4310, DUKHENGI2BDWIRAP5490, DUKHENGI2ADWIRAP5110, DUKHPROGEN00MTAP2840, DUKHENGI1BDWIRAP4710 | DUKHCONI03Z1IRGL5290, DUKHCONI1AZ1IRGL5290, DUKHCONI2AZ1IRGL5290 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3780 | Proc & Del Gazebo Structure | 120 | 120 | 0% | 2013-09-13 | 2014-01-10 | 2013-09-13 | 2014-01-10 | 73 | No | DUKHENGI1ADWGZAP4380, DUKHENGI2ADWGZAP5170, DUKHPROGEN00MTAP2780, DUKHENGI1BDWGZAP4780, DUKHENGI03DWGZAP5940, DUKHENGI2BDWGZAP5550 | DUKHCONI1ASBGZGL7900, DUKHCONI2ASBGZGL7900, DUKHCONI03SBGZGL7900 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3480 | Proc & Del Granite | 120 | 120 | 0% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18 | 58 | No | DUKHENGP2ADWARAP4850, DUKHENGP1ADWARAP4050, DUKHENGP1BDWARAP4450, DUKHPROGEN00MTAP2480, DUKHENGP2BDWARAP5230, DUKHENGP03DWARAP5610 | DUKHCONP03MKARGF3050, DUKHCONP1AMKARFF3350, DUKHCONP03MKARFF3350, DUKHCONP1AMKARGF3050, DUKHCONP1AZ1ARGF3050 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3390 | Proc & Del GRC Panels | 90 | 90 | 0% | 2013-06-16 | 2013-09-13 | 2013-06-16 | 2013-09-13 | 89 | No | DUKHPROGEN00MTAP2390 | DUKHCONP03Z1AREL3675, DUKHCONP03MKAREL3675 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3300 | Proc & Del Gypsum Board false ceiling | 110 | 110 | 0% | 2013-06-16 | 2013-10-03 | 2013-06-16 | 2013-10-03 | 37 | No | DUKHENGP2BDWARAP5290, DUKHENGP2ADWARAP4910, DUKHENGP03DWARAP5670, DUKHPROGEN00MTAP2300, DUKHENGP1BDWARAP4480, DUKHENGP1ADWARAP4110 | DUKHCONP1AMKARFF3360, DUKHCONP03MKARFF3360, DUKHCONP2AMKARGF3060, DUKHCONP03MKARGF3060, DUKHCONP1AZ1ARGF3060, DUKHCONP1AMKARGF3060 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3660 | Proc & Del Interlock works | 40 | 40 | 0% | 2013-07-29 | 2013-09-06 | 2013-07-29 | 2013-09-06 | 105 | No | DUKHENGI1BDWIWAP4760, DUKHENGI03DWIWAP5920, DUKHPROGEN00MTAP2660, DUKHENGI1ADWIWAP4360, DUKHENGI2ADWIWAP5160, DUKHENGI2BDWIWAP5540 | DUKHCONP1AZ1HDEX5100, DUKHCONP1AMKHDEX5100, DUKHCONP2AMKHDEX5100 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3450 | Proc & Del Ironmogeries | 120 | 120 | 0% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18 | 31 | No | DUKHENGP1ADWARAP4130, DUKHENGP2ADWARAP4930, DUKHPROGEN00MTAP2450, DUKHENGP2BDWARAP5310, DUKHENGP03DWARAP5690, DUKHENGP1BDWARAP4530 | DUKHCONP1AMKARFF3365, DUKHCONP03MKARFF3365, DUKHCONP03MKARGF3065, DUKHCONP1AMKARGF3065, DUKHCONP1AZ1ARGF3070, DUKHCONP2AMKARGF3065 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3870 | Proc & Del Irrigation Controller | 90 | 90 | 0% | 2013-11-17 | 2014-02-14 | 2013-11-17 | 2014-02-14 | 44 | No | DUKHENGI03DWIRAP5870, DUKHENGI2ADWIRAP5110, DUKHENGI1ADWIRAP4310, DUKHENGI1BDWIRAP4710, DUKHENGI2BDWIRAP5490, DUKHPROGEN00MTAP2870 | DUKHCONI03Z1IRGL5290, DUKHCONI1AZ1IRGL5290, DUKHCONI2AZ1IRGL5290 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3670 | Proc & Del Irrigation Pipes | 60 | 60 | 0% | 2013-07-29 | 2013-09-26 | 2013-07-29 | 2013-09-26 | 94 | No | DUKHENGI1BDWIRAP4710, DUKHPROGEN00MTAP2670, DUKHENGI1ADWIRAP4310, DUKHENGI2BDWIRAP5490, DUKHENGI03DWIRAP5870, DUKHENGI2ADWIRAP5110 | DUKHCONP2AMKSLEX5105, DUKHCONI1AZ1IRGL5270, DUKHCONP1AMKSLEX5105 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3650 | Proc & Del Isolating Values | 90 | 90 | 0% | 2013-08-09 | 2013-11-06 | 2013-08-09 | 2013-11-06 | 9 | No | DUKHENGI1BDWFFAP4660, DUKHENGI03DWFFAP5820, DUKHENGI2ADWFFAP5060, DUKHPROGEN00MTAP2650, DUKHENGI2BDWFFAP5440, DUKHENGI1ADWFFAP4260 | DUKHCONI1AZ1FFGL5190, DUKHCONI2AZ1FFGL5190, DUKHCONI03Z1FFGL5190 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3200 | Proc & Del Isolators | 120 | 120 | 0% | 2013-05-31 | 2013-09-27 | 2013-05-31 | 2013-09-27 | 130 | No | DUKHENGP2ADWELAP4970, DUKHENGP1BDWELAP4570, DUKHENGP2BDWELAP5350, DUKHENGP03DWELAP5730, DUKHPROGEN00MTAP2200, DUKHENGP1ADWELAP4170 | DUKHCONP1AMKELRF4070, DUKHCONP2AMKELRF4070, DUKHCONP1AZ1ELRF4070, DUKHCONP03MKELRF4070 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3600 | Proc & Del kerb works | 40 | 40 | 0% | 2013-07-11 | 2013-08-19 | 2013-07-11 | 2013-08-19 | 95 | No | DUKHPROGEN00MTAP2600 | DUKHCONP2AMKHDEX5090, DUKHCONP1AMKHDEX5090, DUKHCONP1AZ1HDEX5090, DUKHCONI03Z1HDGL7025 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3770 | Proc & Del Kitchen Water Filter | 60 | 60 | 0% | 2013-09-17 | 2013-11-15 | 2013-09-17 | 2013-11-15 | 11 | No | DUKHENGP1ADWMEAP4210, DUKHENGP03DWMEAP5780, DUKHPROGEN00MTAP2770, DUKHENGP2BDWMEAP5400, DUKHENGP2ADWMEAP5010, DUKHENGP1BDWMEAP4620, DUKHENGP1ADWMEAP4220, DUKHENGP03DWMEAP5770, DUKHENGP2BDWMEAP5390, DUKHENGP2ADWMEAP5020, DUKHENGP1BDWMEAP4610 | DUKHCONP2AMKPLGF4315, DUKHCONP1AZ1PLGF4315, DUKHCONP1AMKPLGF4315, DUKHCONP03MKPLGF4315 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3520 | Proc & Del Lift Pump | 120 | 120 | 0% | 2013-07-23 | 2013-11-19 | 2013-07-23 | 2013-11-19 | 27 | No | DUKHENGP2ADWMEAP5020, DUKHENGP2ADWMEAP5010, DUKHENGP1ADWMEAP4220, DUKHENGP1BDWMEAP4610, DUKHENGP2BDWMEAP5400, DUKHENGP03DWMEAP5780, DUKHENGP1BDWMEAP4620, DUKHENGP1ADWMEAP4210, DUKHPROGEN00MTAP2520, DUKHENGP03DWMEAP5770, DUKHENGP2BDWMEAP5390 | DUKHCONP1AMKWEEX5065, DUKHCONP2AMKWEEX5065, DUKHCONP1AZ1WEEX5065 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3190 | Proc & Del Lights & Fixtures | 120 | 120 | 0% | 2013-05-31 | 2013-09-27 | 2013-05-31 | 2013-09-27 | 105 | No | DUKHENGP1BDWELAP4560, DUKHENGP1ADWELAP4160, DUKHENGP2BDWELAP5340, DUKHPROGEN00MTAP2190, DUKHENGP03DWELAP5720, DUKHENGP2ADWELAP4960 | DUKHCONP2AMKELGF4025, DUKHCONP03MKELFF4065, DUKHCONP1AMKELGF4025, DUKHCONP1AMKELFF4065, DUKHCONP03MKELGF4025, DUKHCONP1AZ1ELGF4025 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3590 | Proc & Del Manhole Covers and Frames | 90 | 90 | 0% | 2013-07-19 | 2013-10-16 | 2013-07-19 | 2013-10-16 | 61 | No | DUKHENGI2ADWWSAP5070, DUKHENGI2ADWIWAP5160, DUKHENGI1ADWIWAP4360, DUKHENGI1BDWDRAP4650, DUKHENGI1BDWIWAP4760, DUKHENGI2BDWWSAP5450, DUKHENGI1ADWWSAP4270, DUKHENGI03DWWSAP5830, DUKHENGI1ADWDRAP4250, DUKHENGI03DWDRAP5810, DUKHENGI2BDWDRAP5430, DUKHPROGEN00MTAP2590, DUKHENGI03DWIWAP5920, DUKHENGI2ADWDRAP5050, DUKHENGI1BDWWSAP4670, DUKHENGI2BDWIWAP5540 | DUKHCONP1AZ1MSEX5000 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3810 | Proc & Del Nozzle Jet | 90 | 90 | 0% | 2013-09-05 | 2013-12-03 | 2013-09-05 | 2013-12-03 | 117 | No | DUKHENGI2ADWIRAP5110, DUKHENGI2BDWIRAP5490, DUKHENGI03DWIRAP5870, DUKHPROGEN00MTAP2810, DUKHENGI1ADWIRAP4310, DUKHENGI1BDWIRAP4710 | DUKHCONI2AZ1IRGL5290, DUKHCONI1AZ1IRGL5290, DUKHCONI03Z1IRGL5290 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3320 | Proc & Del Paints | 90 | 90 | 0% | 2013-06-27 | 2013-09-24 | 2013-06-27 | 2013-09-24 | 12 | No | DUKHPROGEN00MTAP2320, DUKHENGP2ADWARAP4850, DUKHENGP1BDWARAP4450, DUKHENGP2BDWARAP5230, DUKHENGP03DWARAP5610, DUKHENGP1ADWARAP4050 | DUKHCONP2AMKARGF3030, DUKHCONP1AMKARGF3030, DUKHCONP1AMKARFF3330, DUKHCONP1AZ1ARGF3030, DUKHCONP03MKARFF3330, DUKHCONP03MKARGF3030 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3140 | Proc & Del Pitch roofing | 40 | 40 | 0% | 2013-04-30 | 2013-06-08 | 2013-04-30 | 2013-06-08 | 105 | No | DUKHENGP2ADWARAP4870, DUKHENGP1ADWARAP4070, DUKHENGP1BDWARAP4470, DUKHENGP03DWARAP5630, DUKHPROGEN00MTAP2140, DUKHENGP2BDWARAP5250 | DUKHCONP2AMKARRF3625, DUKHCONP2AZ1ARRF3625 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3790 | Proc & Del Plantation(Grass,Trees) | 90 | 90 | 0% | 2013-09-05 | 2013-12-03 | 2013-09-05 | 2013-12-03 | 26 | No | DUKHPROGEN00MTAP2790, DUKHENGI1BDWSLAP4720, DUKHENGI2BDWSLAP5500, DUKHENGI03DWSLAP5880, DUKHENGI1ADWSLAP4320, DUKHENGI2ADWSLAP5120 | DUKHCONP1AZ1SLEX5105, DUKHCONP1AMKSLEX5105, DUKHCONP2AMKSLEX5105, DUKHCONI1AZ1SLGL7205 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3040 | Proc & Del Plastering & Accessories | 60 | 60 | 0% | 2013-04-12 | 2013-06-10 | 2013-04-12 | 2013-06-10 | 98 | No | DUKHENGP1BDWARAP4460, DUKHENGP03DWARAP5610, DUKHENGP03DWARAP5620, DUKHENGP2ADWARAP4850, DUKHENGP1ADWARAP4060, DUKHENGP1BDWARAP4450, DUKHENGP2BDWARAP5230, DUKHENGP1ADWARAP4050, DUKHPROGEN00MTAP2040 | DUKHCONP1AZ1ARGF3005, DUKHCONP1AMKARGF3005, DUKHCONP03MKARGF3005, DUKHCONP1AMKARFF3305, DUKHCONP03MKARFF3305, DUKHCONP2AMKARGF3005 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3080 | Proc & Del Polyethylene Pipes | 90 | 90 | 0% | 2013-04-15 | 2013-07-13 | 2013-04-15 | 2013-07-13 | 62 | No | DUKHENGP1ADWMEAP4210, DUKHENGP1BDWMEAP4610, DUKHENGP1BDWMEAP4620, DUKHENGP2ADWMEAP5020, DUKHENGP2BDWMEAP5400, DUKHPROGEN00MTAP2080, DUKHENGP1ADWMEAP4220, DUKHENGP2ADWMEAP5010, DUKHENGP2BDWMEAP5390, DUKHENGP03DWMEAP5770, DUKHENGP03DWMEAP5780 | DUKHCONP1AZ1PLFF4325, DUKHCONP1AMKPLFF4325, DUKHCONP2AMKPLGF4305, DUKHCONP03MKPLFF4325 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3130 | Proc & Del Porcelain Tile | 120 | 120 | 0% | 2013-04-30 | 2013-08-27 | 2013-04-30 | 2013-08-27 | 59 | No | DUKHENGP1BDWARAP4510, DUKHENGP2BDWARAP5270, DUKHENGP2ADWARAP4890, DUKHENGP03DWARAP5650, DUKHENGP1ADWARAP4090, DUKHPROGEN00MTAP2130 | DUKHCONP1AMKARGF3025, DUKHCONP03MKARFF3325, DUKHCONP03MKARGF3025, DUKHCONP2AMKARGF3025, DUKHCONP1AZ1ARGF3025, DUKHCONP1AMKARFF3325 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3820 | Proc & Del Pre-cast Boundry Wall | 100 | 100 | 0% | 2013-09-05 | 2013-12-13 | 2013-09-05 | 2013-12-13 | 49 | No | DUKHENGI2ADWBWAP5130, DUKHENGI1BDWBWAP4730, DUKHENGI2BDWBWAP5510, DUKHPROGEN00MTAP2820, DUKHENGI1ADWBWAP4330, DUKHENGI03DWBWAP5890 | DUKHCONI1AZ1BWGL5315, DUKHCONI2AZ1BWGL5315, DUKHCONI03Z1BWGL5315 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3440 | Proc & Del PVC Doors | 90 | 90 | 0% | 2013-06-21 | 2013-09-18 | 2013-06-21 | 2013-09-18 | 111 | No | DUKHENGP2ADWARAP4930, DUKHPROGEN00MTAP2440, DUKHENGP1ADWARAP4130, DUKHENGP1BDWARAP4530, DUKHENGP2BDWARAP5310, DUKHENGP03DWARAP5690 | DUKHCONP03MKARGF3070, DUKHCONP1AZ1ARGF3070, DUKHCONP1AMKARGF3070 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3610 | Proc & Del PVC Tent | 110 | 110 | 0% | 2013-07-05 | 2013-10-22 | 2013-07-05 | 2013-10-22 | 38 | No | DUKHPROGEN00MTAP2610 | DUKHCONP1AZ1WEEX5060, DUKHCONP1AMKWEEX5050, DUKHCONP03Z1WTEX5060, DUKHCONP2AMKWEEX5050 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3860 | Proc & Del Remote Control Value | 90 | 90 | 0% | 2013-10-30 | 2014-01-27 | 2013-10-30 | 2014-01-27 | 62 | No | DUKHPROGEN00MTAP2860, DUKHENGI2BDWIRAP5490, DUKHENGI1ADWIRAP4310, DUKHENGI1BDWIRAP4710, DUKHENGI03DWIRAP5870, DUKHENGI2ADWIRAP5110 | DUKHCONI1AZ1IRGL5290, DUKHCONI03Z1IRGL5290, DUKHCONI2AZ1IRGL5290 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3720 | Proc & Del Road Marking | 60 | 60 | 0% | 2013-08-19 | 2013-10-17 | 2013-08-19 | 2013-10-17 | 205 | No | DUKHENGI2BDWRWAP5530, DUKHPROGEN00MTAP2720, DUKHENGI1ADWRWAP4350, DUKHENGI2ADWRWAP5150, DUKHENGI03DWRWAP5910, DUKHENGI1BDWRWAP4750 | DUKHCONI2AZ1RWGL6030, DUKHCONI1AZ1RWGL6030, DUKHCONI03Z1RWGL6030 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3700 | Proc & Del Road Works Materials | 40 | 40 | 0% | 2013-08-19 | 2013-09-27 | 2013-08-19 | 2013-09-27 | 225 | No | DUKHENGI1BDWRWAP4750, DUKHENGI2ADWRWAP5150, DUKHPROGEN00MTAP2700, DUKHENGI03DWRWAP5910, DUKHENGI2BDWRWAP5530, DUKHENGI1ADWRWAP4350 | DUKHCONI03Z1RWGL6030, DUKHCONI1AZ1RWGL6030, DUKHCONI2AZ1RWGL6030 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3430 | Proc & Del Roller Shutter | 120 | 120 | 0% | 2013-06-18 | 2013-10-15 | 2013-06-18 | 2013-10-15 | 262 | No | DUKHPROGEN00MTAP2430 | DUKHCONP1AZ1MSEX5335, DUKHCONP1AZ2MSEX5335 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3150 | Proc & Del Sanitary Fittings | 120 | 120 | 0% | 2013-05-31 | 2013-09-27 | 2013-05-31 | 2013-09-27 | 60 | No | DUKHENGP1ADWMEAP4220, DUKHENGP1ADWMEAP4210, DUKHENGP2BDWMEAP5390, DUKHENGP2ADWMEAP5020, DUKHENGP1BDWMEAP4620, DUKHENGP03DWMEAP5780, DUKHENGP2ADWMEAP5010, DUKHPROGEN00MTAP2150, DUKHENGP1BDWMEAP4610, DUKHENGP03DWMEAP5770, DUKHENGP2BDWMEAP5400 | DUKHCONP2AMKPLGF4315, DUKHCONP03MKPLGF4315, DUKHCONP1AZ1PLGF4315, DUKHCONP1AMKPLGF4315 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3100 | Proc & Del Slate Tile | 120 | 120 | 0% | 2013-04-30 | 2013-08-27 | 2013-04-30 | 2013-08-27 | 102 | No | DUKHENGP1ADWARAP4100, DUKHENGP03DWARAP5660, DUKHENGP1BDWARAP4520, DUKHPROGEN00MTAP2100, DUKHENGP2ADWARAP4900, DUKHENGP2BDWARAP5280 | DUKHCONP1AMKARGF3035, DUKHCONP1AMKARFF3335, DUKHCONP1AZ1ARGF3035, DUKHCONP2AMKARGF3035, DUKHCONP03MKARFF3335, DUKHCONP03MKARGF3035 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3170 | Proc & Del SMDB | 120 | 120 | 0% | 2013-05-31 | 2013-09-27 | 2013-05-31 | 2013-09-27 | 92 | No | DUKHENGP2ADWELAP4970, DUKHENGP03DWELAP5730, DUKHENGP1ADWELAP4170, DUKHENGP1BDWELAP4570, DUKHENGP1ADWELAP4150, DUKHENGP2BDWELAP5350, DUKHENGP1BDWELAP4550, DUKHENGP2BDWELAP5330, DUKHPROGEN00MTAP2170, DUKHENGP03DWELAP5710, DUKHENGP2ADWELAP4950 | DUKHCONP03MKELGF4020, DUKHCONP1AMKELGF4020, DUKHCONP1AMKELFF4060, DUKHCONP1AZ1ELGF4020, DUKHCONP03MKELFF4060, DUKHCONP2AMKELGF4020 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3260 | Proc & Del Smoke Detector | 90 | 90 | 0% | 2013-06-18 | 2013-09-15 | 2013-06-18 | 2013-09-15 | 108 | No | DUKHENGP1ADWELAP4180, DUKHENGP2BDWELAP5360, DUKHPROGEN00MTAP2260, DUKHENGP2ADWELAP4980, DUKHENGP03DWELAP5740, DUKHENGP1BDWELAP4580 | DUKHCONP03MKELGF4015, DUKHCONP1AZ1ELGF4015, DUKHCONP1AMKELFF4055, DUKHCONP1AMKELGF4015, DUKHCONP03MKELFF4055, DUKHCONP2AMKELGF4015 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3830 | Proc & Del Solenoid Values | 90 | 90 | 0% | 2013-09-23 | 2013-12-21 | 2013-09-23 | 2013-12-21 | 99 | No | DUKHENGI2ADWIRAP5110, DUKHENGI03DWIRAP5870, DUKHENGI1ADWIRAP4310, DUKHENGI1BDWIRAP4710, DUKHPROGEN00MTAP2830, DUKHENGI2BDWIRAP5490 | DUKHCONI2AZ1IRGL5290, DUKHCONI1AZ1IRGL5290, DUKHCONI03Z1IRGL5290 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3750 | Proc & Del Speed Humps | 60 | 60 | 0% | 2013-08-19 | 2013-10-17 | 2013-08-19 | 2013-10-17 | 150 | No | DUKHENGI2BDWRWAP5530, DUKHENGI2ADWRWAP5150, DUKHPROGEN00MTAP2750, DUKHENGI1ADWRWAP4350, DUKHENGI1BDWRWAP4750, DUKHENGI03DWRWAP5910 | DUKHCONI2AZ1HDGL7040, DUKHCONI1AZ1HDGL7040, DUKHCONI1AZ1RWGL6000, DUKHCONI03Z1HDGL7040 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3240 | Proc & Del Split AC | 120 | 120 | 0% | 2013-06-18 | 2013-10-15 | 2013-06-18 | 2013-10-15 | 101 | No | DUKHENGP2ADWMEAP5040, DUKHENGP1ADWMEAP4240, DUKHPROGEN00MTAP2240, DUKHENGP1BDWMEAP4640, DUKHENGP2BDWMEAP5420, DUKHENGP03DWMEAP5800 | DUKHCONP03MKACGF4610, DUKHCONP1AMKACGF4610, DUKHCONP1AZ1ACGF4610, DUKHCONP1AMKACFF4625, DUKHCONP03MKACFF4625, DUKHCONP2AMKACGF4610 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3760 | Proc & Del Sprinklers | 60 | 60 | 0% | 2013-08-19 | 2013-10-17 | 2013-08-19 | 2013-10-17 | 164 | No | DUKHPROGEN00MTAP2760, DUKHENGI2ADWIRAP5110, DUKHENGI03DWIRAP5870, DUKHENGI2BDWIRAP5490, DUKHENGI1ADWIRAP4310, DUKHENGI1BDWIRAP4710 | DUKHCONI2AZ1IRGL5290, DUKHCONI03Z1IRGL5290, DUKHCONI1AZ1IRGL5290 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3510 | Proc & Del Stainless Steel Cover | 120 | 120 | 0% | 2013-06-30 | 2013-10-27 | 2013-06-30 | 2013-10-27 | 33 | No | DUKHPROGEN00MTAP2510 | DUKHCONP1AZ1ARRF3655, DUKHCONP1AMKWEEX5050, DUKHCONP2AMKWEEX5050 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3580 | Proc & Del Stainless Steel Handrail | 120 | 120 | 0% | 2013-07-15 | 2013-11-11 | 2013-07-15 | 2013-11-11 | 75 | No | DUKHPROGEN00MTAP2580 | DUKHCONP1AZ1MSEX5025, DUKHCONP03MKARFF3385, DUKHCONP1AMKARFF3385 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3500 | Proc & Del Steel Door | 120 | 120 | 0% | 2013-06-30 | 2013-10-27 | 2013-06-30 | 2013-10-27 | 33 | No | DUKHPROGEN00MTAP2500 | DUKHCONP03Z1WTEX5050, DUKHCONP1AZ1WEEX5050, DUKHCONP2AMKWEEX5050, DUKHCONP1AMKWEEX5050 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3800 | Proc & Del Steel Gate & Barrier gates | 90 | 90 | 0% | 2013-09-05 | 2013-12-03 | 2013-09-05 | 2013-12-03 | 76 | No | DUKHPROGEN00MTAP2800 | DUKHCONI2AZ1BWGL5320, DUKHCONI03Z1BWGL5320, DUKHCONI1AZ1BWGL5320 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3630 | Proc & Del Steel Ladder | 90 | 90 | 0% | 2013-07-23 | 2013-10-20 | 2013-07-23 | 2013-10-20 | 45 | No | DUKHPROGEN00MTAP2630 | DUKHCONI1ASBIWGL7460, DUKHCONP1AMKWEEX5060, DUKHCONP2AMKWEEX5060 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3740 | Proc & Del Stone Boulders | 60 | 60 | 0% | 2013-08-19 | 2013-10-17 | 2013-08-19 | 2013-10-17 | 152 | No | DUKHPROGEN00MTAP2740 | DUKHCONI2AZ1HDGL7035, DUKHCONI03Z1HDGL7035, DUKHCONI1AZ1HDGL7035 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3110 | Proc & Del Stone Cladding | 120 | 120 | 0% | 2013-04-04 | 2013-08-01 | 2013-04-04 | 2013-08-01 | 139 | No | DUKHENGP03DWARAP5610, DUKHENGP2BDWARAP5230, DUKHENGP1ADWARAP4050, DUKHPROGEN00MTAP2110, DUKHENGP2ADWARAP4850, DUKHENGP1BDWARAP4450 | DUKHCONP1AZ1AREL3670, DUKHCONP1AMKAREL3670 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3250 | Proc & Del Street Light Post Set | 120 | 120 | 0% | 2013-09-05 | 2014-01-02 | 2013-09-05 | 2014-01-02 | 73 | No | DUKHENGI2ADWTCAP5100, DUKHENGI03DWELAP5840, DUKHPROGEN00MTAP2250, DUKHENGI2ADWSTAP5090, DUKHENGI1ADWELAP4280, DUKHENGI2BDWTCAP5480, DUKHENGI03DWTCAP5860, DUKHENGI1BDWELAP4680, DUKHENGI1BDWTCAP4700, DUKHENGI03DWSTAP5850, DUKHENGI2ADWELAP5080, DUKHENGI1ADWTCAP4300, DUKHENGI2BDWELAP5460, DUKHENGI2BDWSTAP5470, DUKHENGI1ADWSTAP4290, DUKHENGI1BDWSTAP4690 | DUKHCONI1AZ1STGL5255, DUKHCONI03Z1STGL5255, DUKHCONI2AZ1STGL5255 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3620 | Proc & Del Strutural Steel | 120 | 120 | 0% | 2013-07-05 | 2013-11-01 | 2013-07-05 | 2013-11-01 | 33 | No | DUKHPROGEN00MTAP2620 | DUKHCONP2AMKWEEX5060, DUKHCONP1AMKWEEX5060, DUKHCONP1AZ1WEEX5060 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3280 | Proc & Del Telephone Fittings & Accessories | 120 | 120 | 0% | 2013-06-19 | 2013-10-16 | 2013-06-19 | 2013-10-16 | 84 | No | DUKHENGP2BDWELAP5380, DUKHENGP03DWELAP5760, DUKHENGP1BDWELAP4600, DUKHPROGEN00MTAP2280, DUKHENGP2ADWELAP5000, DUKHENGP1ADWELAP4200 | DUKHCONP1AZ1ELGF4030, DUKHCONP1AMKELFF4050, DUKHCONP2AMKELGF4030, DUKHCONP03MKELFF4050, DUKHCONP1AMKELGF4030, DUKHCONP03MKELGF4030 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3290 | Proc & Del Television devices,Fit. & Access. | 120 | 120 | 0% | 2013-06-19 | 2013-10-16 | 2013-06-19 | 2013-10-16 | 118 | No | DUKHPROGEN00MTAP2290, DUKHENGP2BDWELAP5380, DUKHENGP2ADWELAP5000, DUKHENGP1ADWELAP4200, DUKHENGP1BDWELAP4600, DUKHENGP03DWELAP5760 | DUKHCONP1AZ1ELRF4075, DUKHCONP1AMKELRF4075, DUKHCONP2AMKELRF4075, DUKHCONP03MKELRF4075 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3050 | Proc & Del Thermal Insulation | 60 | 60 | 0% | 2013-04-21 | 2013-06-19 | 2013-04-21 | 2013-06-19 | 130 | No | DUKHENGP2ADWARAP4870, DUKHENGP1ADWARAP4070, DUKHENGP03DWARAP5630, DUKHPROGEN00MTAP2050, DUKHENGP1BDWARAP4470, DUKHENGP2BDWARAP5250 | DUKHCONP03Z1ARRF3635, DUKHCONP1AZ1ARRF3635, DUKHCONP2AZ1ARRF3635 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3060 | Proc & Del UPVC Pipes | 40 | 40 | 0% | 2013-02-25 | 2013-04-05 | 2013-02-25 | 2013-04-05 | 32 | No | DUKHPROGEN00MTAP1060 | DUKHCONP1AZ1PLUG4300, DUKHCONP03Z1PLUG4300, DUKHCONP2AZ1PLUG4300 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3270 | Proc & Del Video Com System | 120 | 120 | 0% | 2013-06-18 | 2013-10-15 | 2013-06-18 | 2013-10-15 | 85 | No | DUKHENGP2BDWELAP5370, DUKHENGP1BDWELAP4590, DUKHENGP2ADWELAP4990, DUKHPROGEN00MTAP2270, DUKHENGP1ADWELAP4190, DUKHENGP03DWELAP5750 | DUKHCONP1AZ1ELGF4030, DUKHCONP1AMKELGF4030, DUKHCONP2AMKELGF4030, DUKHCONP1AMKELFF4050, DUKHCONP03MKELGF4030, DUKHCONP03MKELFF4050 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3220 | Proc & Del Water Chiller | 120 | 120 | 0% | 2013-06-18 | 2013-10-15 | 2013-06-18 | 2013-10-15 | 62 | No | DUKHENGP1ADWMEAP4210, DUKHENGP1BDWMEAP4620, DUKHENGP2ADWMEAP5010, DUKHENGP1ADWMEAP4220, DUKHENGP2BDWMEAP5390, DUKHENGP2BDWMEAP5400, DUKHENGP03DWMEAP5770, DUKHENGP03DWMEAP5780, DUKHPROGEN00MTAP2220, DUKHENGP2ADWMEAP5020, DUKHENGP1BDWMEAP4610 | DUKHCONP2AMKWEEX5065, DUKHCONP1AMKWEEX5065, DUKHCONP1AZ1WEEX5065, DUKHCONP03Z1WTEX5065 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3230 | Proc & Del Water Heater | 90 | 90 | 0% | 2013-06-18 | 2013-09-15 | 2013-06-18 | 2013-09-15 | 72 | No | DUKHENGP1ADWMEAP4220, DUKHENGP03DWMEAP5780, DUKHENGP1BDWMEAP4610, DUKHENGP1BDWMEAP4620, DUKHENGP2ADWMEAP5020, DUKHENGP2BDWMEAP5390, DUKHENGP2BDWMEAP5400, DUKHENGP03DWMEAP5770, DUKHENGP1ADWMEAP4210, DUKHPROGEN00MTAP2230, DUKHENGP2ADWMEAP5010 | DUKHCONP1AZ1PLGF4320, DUKHCONP03MKPLGF4315, DUKHCONP1AMKPLGF4315, DUKHCONP2AMKPLGF4315 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3640 | Proc & Del Water meter | 60 | 60 | 0% | 2013-08-09 | 2013-10-07 | 2013-08-09 | 2013-10-07 | 70 | No | DUKHENGP1ADWMEAP4220, DUKHENGP1BDWMEAP4610, DUKHENGP03DWMEAP5780, DUKHENGP1BDWMEAP4620, DUKHENGP2ADWMEAP5010, DUKHENGP2BDWMEAP5390, DUKHENGP1ADWMEAP4210, DUKHENGP2BDWMEAP5400, DUKHENGP03DWMEAP5770, DUKHPROGEN00MTAP2640, DUKHENGP2ADWMEAP5020 | DUKHCONP1AZ1WEEX5065, DUKHCONP2AMKWEEX5065, DUKHCONP1AMKWEEX5065 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3680 | Proc & Del Water Tank | 60 | 60 | 0% | 2013-08-30 | 2013-10-28 | 2013-08-30 | 2013-10-28 | 49 | No | DUKHENGP2ADWMEAP5020, DUKHENGP2ADWMEAP5010, DUKHENGP1ADWMEAP4220, DUKHENGP2BDWMEAP5390, DUKHENGP03DWMEAP5780, DUKHENGP2BDWMEAP5400, DUKHENGP03DWMEAP5770, DUKHENGP1ADWMEAP4210, DUKHPROGEN00MTAP2680, DUKHENGP1BDWMEAP4620, DUKHENGP1BDWMEAP4610 | DUKHCONP1AMKWEEX5065, DUKHCONP1AZ1WEEX5065, DUKHCONP2AMKWEEX5065 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3030 | Proc & Del Waterproofing | 7 | 7 | 0% | 2013-01-14 | 2013-01-20 | 2013-01-14 | 2013-01-20 | 45 | No | DUKHPROGEN00MTAP1030 | DUKHCONP1AZ1STUG1015 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3490 | Proc & Del Wooden Doors | 120 | 120 | 0% | 2013-06-21 | 2013-10-18 | 2013-06-21 | 2013-10-18 | 31 | No | DUKHENGP2ADWARAP4930, DUKHENGP1BDWARAP4530, DUKHENGP1ADWARAP4130, DUKHENGP2BDWARAP5310, DUKHPROGEN00MTAP2490, DUKHENGP03DWARAP5690 | DUKHCONP1AMKARFF3365, DUKHCONP03MKARFF3365, DUKHCONP03MKARGF3065, DUKHCONP1AMKARGF3065, DUKHCONP1AZ1ARGF3065, DUKHCONP2AMKARGF3065 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DUKHPROGEN00PRDV3570 | Proc & Del Wooden Hand Rails | 100 | 100 | 0% | 2013-07-15 | 2013-10-22 | 2013-07-15 | 2013-10-22 | 74 | No | DUKHPROGEN00MTAP2570, DUKHENGP2BDWARAP5320, DUKHENGP1BDWARAP4540, DUKHENGP03DWARAP5700, DUKHENGP1ADWARAP4140, DUKHENGP2ADWARAP4940 | DUKHCONP2AMKARGF3075, DUKHCONP1AZ1ARGF3085, DUKHCONP1AMKARFF3385, DUKHCONP03MKARFF3385, DUKHCONP03MKARGF3075, DUKHCONP1AMKARGF3075 | 0 | 0 | MANUFACTURING, PROCUREMENT & DELIVERY
DHBL.K30 CONSTRUCTION |  | 657 | 657 | 0% | 2012-11-10 | 2015-01-01 | 2012-11-10 | 2015-01-01 | 6 |  |  |  | 0 | 0
DHBL.K30.L15 PACKAGE-1A |  | 642 | 642 | 0% | 2012-11-10 | 2014-12-14 | 2012-11-10 | 2014-12-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.03 SITE PREPARATORY WORKS |  | 81 | 81 | 0% | 2012-11-10 | 2013-02-13 | 2012-11-10 | 2013-02-13 | 15 |  |  |  | 0 | 0
DUKHCONP1AGNSP002400 | Approval for new Layout for rerouting | 14 | 14 | 0% | 2012-12-30 | 2013-01-14 | 2012-12-30 | 2013-01-14 | 0 | Yes | DUKHCONP1AGNSP002300 | DUKHCONP1AGNSP002500 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP004000 | Demolition of Existing building & landscaping | 20 | 20 | 0% | 2012-11-22 | 2012-12-15 | 2012-11-22 | 2012-12-15 | 60 | No | DUKHCONP1AGNSP003000 | DUKHCONP1AGNSP005000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP005000 | Demolition of existing services works | 20 | 20 | 0% | 2012-11-28 | 2012-12-22 | 2012-11-28 | 2012-12-22 | 60 | No | DUKHCONP1AGNSP004000 | DUKHCONP1AZ5STUG1000, DUKHCONP1AZ9STUG1000, DUKHCONP1AZ6STUG1000, DUKHCONP1AZ2STUG1000, DUKHCONP1AZ3STUG1000, DUKHCONP1AZ8STUG1000, DUKHCONP1AZ4STUG1000, DUKHCONP1AZ7STUG1000, DUKHCONP1AZ1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP002200 | Information Required for Rerouting | 14 | 14 | 0% | 2012-12-04 | 2012-12-20 | 2012-12-04 | 2012-12-20 | 0 | Yes | DUKHCONP1AGNSP002100 | DUKHCONP1AGNSP002300 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP002300 | Preparation & Submission for new Layout for rerouting | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 0 | Yes | DUKHCONP1AGNSP002200 | DUKHCONP1AGNSP002400 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP002500 | Rerouting Works | 25 | 25 | 0% | 2013-01-15 | 2013-02-13 | 2013-01-15 | 2013-02-13 | 0 | Yes | DUKHCONP1AGNSP002400 | DUKHCONP1AZ1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP002000 | Scanning for Existing Services for rerouting | 16 | 16 | 0% | 2012-11-10 | 2012-11-27 | 2012-11-10 | 2012-11-27 | 0 | Yes | DUKHMOBP010000004000 | DUKHCONP1AGNSP003000, DUKHCONP1AGNSP002100 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP003000 | Site stripping | 20 | 20 | 0% | 2012-11-17 | 2012-12-09 | 2012-11-17 | 2012-12-09 | 60 | No | DUKHCONP1AGNSP002000 | DUKHCONP1AGNSP004000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP002100 | Submission of Scanning Reports | 5 | 5 | 0% | 2012-11-28 | 2012-12-03 | 2012-11-28 | 2012-12-03 | 0 | Yes | DUKHCONP1AGNSP002000 | DUKHCONP1AGNSP002200 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1AGNSP001000 | Survey works, | 20 | 20 | 0% | 2012-12-01 | 2012-12-24 | 2012-12-01 | 2012-12-24 | 0 | Yes | DUKHMOBP010000004000 | DUKHMOBI1APS00001000 | 0 | 0 | SITE PREPARATORY WORKS
DHBL.K30.L15.05 MOCK UP VILLA |  | 133 | 133 | 0% | 2013-09-03 | 2014-02-08 | 2013-09-03 | 2014-02-08 | 19 |  |  |  | 0 | 0
DHBL.K30.L15.05 .15 FINISHING WORKS |  | 118 | 118 | 0% | 2013-09-03 | 2014-01-21 | 2013-09-03 | 2014-01-21 | 34 |  |  |  | 0 | 0
DHBL.K30.L15.05 .15 .10 INTERNAL FINISHES |  | 118 | 118 | 0% | 2013-09-03 | 2014-01-21 | 2013-09-03 | 2014-01-21 | 24 |  |  |  | 0 | 0
DHBL.K30.L15.05 .15 .10 .10 GROUND FLOOR |  | 82 | 82 | 0% | 2013-09-03 | 2013-12-09 | 2013-09-03 | 2013-12-09 | 60 |  |  |  | 0 | 0
DUKHCONP1AMKARGF3070 | Aluminum doors | 5 | 5 | 0% | 2013-11-06 | 2013-11-11 | 2013-11-06 | 2013-11-11 | 55 | No | DUKHPROGEN00PRDV3460, DUKHPROGEN00PRDV3440, DUKHCONP1AMKARGF3065 | DUKHCONP1AMKARGF3080, DUKHCONP1AZ1ARGF3070, DUKHCONP1AMKARGF3075, DUKHCONP1AMKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3055 | Aluminum tile false ceiling | 7 | 7 | 0% | 2013-10-23 | 2013-10-30 | 2013-10-23 | 2013-10-30 | 45 | No | DUKHPROGEN00PRDV3310, DUKHCONP1AMKACGF4600, DUKHCONP1AMKARGF3045 | DUKHCONP1AMKPLGF4320, DUKHCONP1AMKELGF4020, DUKHCONP1AMKELGF4030, DUKHCONP1AMKELGF4025, DUKHCONP1AMKELGF4015, DUKHCONP1AZ1ARGF3055, DUKHCONP1AMKACGF4605, DUKHCONP1AMKARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3080 | Aluminum windows | 5 | 5 | 0% | 2013-11-12 | 2013-11-17 | 2013-11-12 | 2013-11-17 | 71 | No | DUKHCONP1AMKARGF3070, DUKHPROGEN00PRDV3470 | DUKHCONP1AZ1ARGF3080, DUKHCONP1AMKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3000 | Block work | 6 | 6 | 0% | 2013-09-03 | 2013-09-09 | 2013-09-03 | 2013-09-09 | 18 | No | DUKHCONP1AZ1STGF2015, DUKHCONP1AZ1STGF2015 | DUKHCONP1AMKELGF4000, DUKHCONP1AMKARGF3005, DUKHCONP1AZ1ARGF3000, DUKHCONP1AMKPLGF4305, DUKHCONP1AMKPLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3075 | Carpentry & Joinery Works | 10 | 10 | 0% | 2013-11-12 | 2013-11-23 | 2013-11-12 | 2013-11-23 | 55 | No | DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3550, DUKHPROGEN00PRDV3570, DUKHCONP1AMKARGF3070 | DUKHCONP1AMKARGF3090, DUKHCONP1AZ1ARGF3075, DUKHCONP1AMKARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3020 | Ceramic Wall Tiling | 6 | 6 | 0% | 2013-09-29 | 2013-10-05 | 2013-09-29 | 2013-10-05 | 34 | No | DUKHCONP1AMKARGF3015, DUKHPROGEN00PRDV3120, DUKHCONP1AMKPLGF4310 | DUKHCONP1AZ1ARGF3020, DUKHCONP1AMKARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3040 | Cobble Tile flooring | 5 | 5 | 0% | 2013-10-13 | 2013-10-20 | 2013-10-13 | 2013-10-20 | 46 | No | DUKHPROGEN00PRDV3090, DUKHCONP1AMKARGF3010, DUKHCONP1AMKARGF3025 | DUKHCONP1AMKARGF3035, DUKHCONP1AZ1ARGF3040, DUKHCONP1AMKARGF3050, DUKHCONP1AMKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3095 | Final Painting | 7 | 7 | 0% | 2013-12-02 | 2013-12-09 | 2013-12-02 | 2013-12-09 | 60 | No | DUKHPROGEN00PRDV3420, DUKHCONP1AMKARGF3030, DUKHCONP1AMKARGF3035, DUKHCONP1AMKARGF3040, DUKHCONP1AMKARGF3085, DUKHCONP1AMKARGF3060, DUKHCONP1AMKARGF3080, DUKHCONP1AMKARGF3070, DUKHCONP1AMKARGF3090 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3045 | Fixing of Suspension systems | 7 | 7 | 0% | 2013-10-13 | 2013-10-22 | 2013-10-13 | 2013-10-22 | 42 | No | DUKHCONP1AMKARGF3030, DUKHCONP1AMKELGF4010, DUKHCONP1AMKARGF3025 | DUKHCONP1AMKARGF3060, DUKHCONP1AZ1ARGF3045, DUKHCONP1AMKARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3010 | Flooring screed | 7 | 7 | 0% | 2013-09-19 | 2013-09-26 | 2013-09-19 | 2013-09-26 | 34 | No | DUKHCONP1AMKARGF3005 | DUKHCONP1AMKARGF3040, DUKHCONP1AZ1ARGF3010, DUKHCONP1AMKARGF3025, DUKHCONP1AMKARGF3035, DUKHCONP1AMKARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3050 | Granite - Stair case flooring & Skirting | 7 | 7 | 0% | 2013-10-21 | 2013-10-28 | 2013-10-21 | 2013-10-28 | 55 | No | DUKHCONP1AMKARGF3025, DUKHCONP1AMKARGF3040, DUKHPROGEN00PRDV3480 | DUKHCONP1AZ1ARGF3050, DUKHCONP1AMKARGF3065, DUKHCONP1AMKARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3060 | Gypsum board false ceiling | 7 | 7 | 0% | 2013-10-23 | 2013-10-30 | 2013-10-23 | 2013-10-30 | 45 | No | DUKHCONP1AMKARGF3045, DUKHCONP1AMKACGF4600, DUKHPROGEN00PRDV3300 | DUKHCONP1AZ1ARGF3060, DUKHCONP1AMKELGF4030, DUKHCONP1AMKPLGF4320, DUKHCONP1AMKARGF3065, DUKHCONP1AMKELGF4020, DUKHCONP1AMKACGF4605, DUKHCONP1AMKELGF4015, DUKHCONP1AMKARGF3095, DUKHCONP1AMKELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3090 | Installation of Granite Counter Top | 7 | 7 | 0% | 2013-11-24 | 2013-12-01 | 2013-11-24 | 2013-12-01 | 59 | No | DUKHCONP1AMKARGF3075 | DUKHCONP1AZ1ARGF3090, DUKHCONP1AMKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3030 | Paint First coat | 5 | 5 | 0% | 2013-10-02 | 2013-10-07 | 2013-10-02 | 2013-10-07 | 41 | No | DUKHPROGEN00PRDV3320, DUKHCONP1AMKARGF3005 | DUKHCONP1AZ1ARGF3030, DUKHCONP1AMKARGF3095, DUKHCONP1AMKARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3005 | Plastering work | 7 | 7 | 0% | 2013-09-16 | 2013-09-23 | 2013-09-16 | 2013-09-23 | 25 | No | DUKHPROGEN00PRDV3040, DUKHCONP1AMKARGF3000, DUKHCONP1AMKELGF4000 | DUKHCONP1AMKACGF4600, DUKHCONP1AMKARGF3010, DUKHCONP1AMKARGF3030, DUKHCONP1AZ1ARGF3005, DUKHCONP1AMKELGF4005, DUKHCONP1AMKARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3025 | Porcelain Tile flooring | 6 | 6 | 0% | 2013-10-06 | 2013-10-12 | 2013-10-06 | 2013-10-12 | 34 | No | DUKHPROGEN00PRDV3130, DUKHCONP1AMKARGF3010, DUKHCONP1AMKARGF3020 | DUKHCONP1AMKARGF3050, DUKHCONP1AZ1ARGF3025, DUKHCONP1AMKARGF3040, DUKHCONP1AMKARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3085 | S.S.Handrails & Balustrade | 7 | 7 | 0% | 2013-11-24 | 2013-12-01 | 2013-11-24 | 2013-12-01 | 60 | No | DUKHCONP1AMKARGF3075, DUKHCONP1AMKARGF3050 | DUKHCONP1AZ1ARGF3085, DUKHCONP1AMKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3035 | Slate Tile Flooring & Skirting | 5 | 5 | 0% | 2013-10-21 | 2013-10-26 | 2013-10-21 | 2013-10-26 | 46 | No | DUKHCONP1AMKARGF3040, DUKHPROGEN00PRDV3100, DUKHCONP1AMKARGF3010 | DUKHCONP1AMKARGF3095, DUKHCONP1AZ1ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3015 | Wet area waterproofing & Protection Screed | 5 | 5 | 0% | 2013-09-23 | 2013-09-28 | 2013-09-23 | 2013-09-28 | 34 | No | DUKHCONP1AMKARGF3005, DUKHCONP1AMKARGF3010 | DUKHCONP1AZ1ARGF3015, DUKHCONP1AMKARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKARGF3065 | Wooden door & PVC Door | 5 | 5 | 0% | 2013-10-31 | 2013-11-05 | 2013-10-31 | 2013-11-05 | 55 | No | DUKHPROGEN00PRDV3490, DUKHCONP1AMKARGF3050, DUKHCONP1AMKARGF3060, DUKHPROGEN00PRDV3450, DUKHCONP1AMKARGF3055 | DUKHCONP1AZ1ARGF3065, DUKHCONP1AMKPLGF4315, DUKHCONP1AMKARGF3070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.05 .15 .10 .15 FIRST FLOORS |  | 82 | 82 | 0% | 2013-10-15 | 2014-01-21 | 2013-10-15 | 2014-01-21 | 24 |  |  |  | 0 | 0
DUKHCONP1AMKARFF3370 | Aluminum doors | 5 | 5 | 0% | 2013-12-19 | 2013-12-24 | 2013-12-19 | 2013-12-24 | 22 | No | DUKHCONP1AMKARFF3365, DUKHPROGEN00PRDV3460 | DUKHCONP1AMKARFF3380, DUKHCONP1AZ1ARFF3370, DUKHCONP1AMKARFF3395, DUKHCONP1AMKARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3380 | Aluminum windows | 5 | 5 | 0% | 2013-12-25 | 2013-12-30 | 2013-12-25 | 2013-12-30 | 33 | No | DUKHPROGEN00PRDV3470, DUKHCONP1AMKARFF3370 | DUKHCONP1AZ1ARFF3380, DUKHCONP1AMKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3300 | Block work | 6 | 6 | 0% | 2013-10-15 | 2013-10-23 | 2013-10-15 | 2013-10-23 | 0 | Yes | DUKHENGP2BDWARAP5230, DUKHENGP03DWARAP5610, DUKHENGP1ADWARAP4050, DUKHENGP1BDWARAP4450, DUKHENGP2ADWARAP4850, DUKHPROGEN00PRDV3010, DUKHCONP1AZ1STFF2035 | DUKHCONP1AZ1ARFF3300, DUKHCONP1AMKARFF3305, DUKHCONP1AMKELFF4035, DUKHCONP1AMKPLFF4325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3375 | Carpentry & Joinery Works | 10 | 10 | 0% | 2013-12-25 | 2014-01-05 | 2013-12-25 | 2014-01-05 | 22 | No | DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3550, DUKHCONP1AMKARFF3370 | DUKHCONP1AMKARFF3390, DUKHCONP1AZ1ARFF3375, DUKHCONP1AMKARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3320 | Ceramic Wall Tiling | 6 | 6 | 0% | 2013-11-12 | 2013-11-18 | 2013-11-12 | 2013-11-18 | 21 | No | DUKHCONP1AMKPLFF4325, DUKHCONP1AMKARFF3315, DUKHPROGEN00PRDV3120, DUKHCONP1AMKPLFF4330 | DUKHCONP1AZ1ARFF3320, DUKHCONP1AMKARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3395 | Final Painting | 7 | 7 | 0% | 2014-01-14 | 2014-01-21 | 2014-01-14 | 2014-01-21 | 24 | No | DUKHCONP1AMKARFF3390, DUKHCONP1AMKARFF3325, DUKHCONP1AMKARFF3335, DUKHCONP1AMKARFF3385, DUKHCONP1AMKARFF3310, DUKHCONP1AMKARRF3620, DUKHCONP1AMKARFF3370, DUKHCONP1AMKARFF3330, DUKHCONP1AMKARFF3380, DUKHCONP1AMKARFF3360 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3345 | Fixing of Suspension systems | 7 | 7 | 0% | 2013-11-26 | 2013-12-03 | 2013-11-26 | 2013-12-03 | 22 | No | DUKHCONP1AMKARFF3325, DUKHCONP1AMKELFF4045, DUKHCONP1AMKARFF3330 | DUKHCONP1AMKARFF3360, DUKHCONP1AZ1ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3310 | Flooring screed | 7 | 7 | 0% | 2013-11-03 | 2013-11-10 | 2013-11-03 | 2013-11-10 | 21 | No | DUKHCONP1AMKARFF3305 | DUKHCONP1AMKARFF3315, DUKHCONP1AZ1ARFF3310, DUKHCONP1AMKARFF3395, DUKHCONP1AMKARFF3325, DUKHCONP1AMKARFF3350, DUKHCONP1AMKARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3350 | Granite - Stair case flooring & Skirting | 7 | 7 | 0% | 2013-11-26 | 2013-12-03 | 2013-11-26 | 2013-12-03 | 29 | No | DUKHPROGEN00PRDV3480, DUKHCONP1AMKARFF3325, DUKHCONP1AMKARFF3310 | DUKHCONP1AZ1ARFF3350, DUKHCONP1AMKARFF3385, DUKHCONP1AMKARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3360 | Gypsum board false ceiling | 7 | 7 | 0% | 2013-12-04 | 2013-12-11 | 2013-12-04 | 2013-12-11 | 22 | No | DUKHPROGEN00PRDV3300, DUKHCONP1AMKARFF3345, DUKHCONP1AMKACFF4615 | DUKHCONP1AMKPLFF4340, DUKHCONP1AZ1ARFF3360, DUKHCONP1AMKELFF4065, DUKHCONP1AMKELFF4060, DUKHCONP1AMKELFF4050, DUKHCONP1AMKACFF4620, DUKHCONP1AMKELFF4055, DUKHCONP1AMKARFF3395, DUKHCONP1AMKARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3390 | Installation of Granite Counter Top | 7 | 7 | 0% | 2014-01-06 | 2014-01-13 | 2014-01-06 | 2014-01-13 | 24 | No | DUKHCONP1AMKARFF3375 | DUKHCONP1AMKARFF3395, DUKHCONP1AZ1ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3330 | Paint First coat | 5 | 5 | 0% | 2013-11-16 | 2013-11-20 | 2013-11-16 | 2013-11-20 | 24 | No | DUKHCONP1AMKARFF3305, DUKHPROGEN00PRDV3320 | DUKHCONP1AZ1ARFF3330, DUKHCONP1AMKARFF3395, DUKHCONP1AMKARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3305 | Plastering work | 7 | 7 | 0% | 2013-10-30 | 2013-11-06 | 2013-10-30 | 2013-11-06 | 8 | No | DUKHCONP1AMKARFF3300, DUKHCONP1AMKELFF4035, DUKHPROGEN00PRDV3040 | DUKHCONP1AMKARFF3330, DUKHCONP1AMKACFF4615, DUKHCONP1AZ1ARFF3305, DUKHCONP1AMKELFF4040, DUKHCONP1AMKARFF3310, DUKHCONP1AMKARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3325 | Porcelain Tile flooring | 6 | 6 | 0% | 2013-11-19 | 2013-11-25 | 2013-11-19 | 2013-11-25 | 21 | No | DUKHCONP1AMKARFF3310, DUKHPROGEN00PRDV3130, DUKHCONP1AMKARFF3320 | DUKHCONP1AMKARFF3335, DUKHCONP1AMKARFF3395, DUKHCONP1AMKARFF3345, DUKHCONP1AMKARFF3350, DUKHCONP1AZ1ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3385 | S.S.Handrails & Balustrade | 7 | 7 | 0% | 2014-01-06 | 2014-01-13 | 2014-01-06 | 2014-01-13 | 24 | No | DUKHPROGEN00PRDV3570, DUKHCONP1AMKARFF3375, DUKHCONP1AMKARFF3350, DUKHPROGEN00PRDV3580 | DUKHCONP1AZ1ARFF3385, DUKHCONP1AMKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3335 | Slate Tile Flooring & Skirting | 5 | 5 | 0% | 2013-11-26 | 2013-12-01 | 2013-11-26 | 2013-12-01 | 39 | No | DUKHCONP1AMKARFF3325, DUKHPROGEN00PRDV3100, DUKHCONP1AMKARFF3310 | DUKHCONP1AZ1ARFF3335, DUKHCONP1AMKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3315 | Wet area waterproofing & Protection Screed | 5 | 5 | 0% | 2013-11-06 | 2013-11-11 | 2013-11-06 | 2013-11-11 | 21 | No | DUKHCONP1AMKARFF3310, DUKHCONP1AMKARFF3305 | DUKHCONP1AZ1ARFF3315, DUKHCONP1AMKARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKARFF3365 | Wooden door | 5 | 5 | 0% | 2013-12-12 | 2013-12-17 | 2013-12-12 | 2013-12-17 | 22 | No | DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3450, DUKHCONP1AMKARFF3350, DUKHCONP1AMKARFF3360 | DUKHCONP1AZ1ARFF3365, DUKHCONP1AMKARFF3370, DUKHCONP1AMKPLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.05 .15 .10 .20 ROOF |  | 28 | 28 | 0% | 2013-09-21 | 2013-10-24 | 2013-09-21 | 2013-10-24 | 91 |  |  |  | 0 | 0
DUKHCONP1AMKARRF3600 | Block work | 6 | 6 | 0% | 2013-09-21 | 2013-09-26 | 2013-09-21 | 2013-09-26 | 36 | No | DUKHCONP1AZ1STGF2015 | DUKHCONP1AMKARRF3605, DUKHCONP1AMKARRF3605, DUKHCONP1AZ1ARRF3600 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3620 | Epoxy Painting -Storage area | 6 | 6 | 0% | 2013-10-16 | 2013-10-24 | 2013-10-16 | 2013-10-24 | 91 | No | DUKHPROGEN00PRDV3420, DUKHCONP1AMKARRF3695 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ARRF3620, DUKHCONP1AZ1PLTC8005, DUKHCONP1AMKARFF3395, DUKHCONP1AMKARRF3660, DUKHCONP1AZ1ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3610 | Flooring screed | 6 | 6 | 0% | 2013-10-01 | 2013-10-07 | 2013-10-01 | 2013-10-07 | 92 | No | DUKHCONP1AMKARRF3605 | DUKHCONP1AZ1ARRF3610 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3695 | Painting -Storage area | 6 | 6 | 0% | 2013-10-09 | 2013-10-15 | 2013-10-09 | 2013-10-15 | 91 | No | DUKHCONP1AMKARRF3605 | DUKHCONP1AMKARRF3620, DUKHCONP1AZ1ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3605 | Plastering work | 6 | 6 | 0% | 2013-09-24 | 2013-09-30 | 2013-09-24 | 2013-09-30 | 36 | No | DUKHCONP1AMKARRF3600, DUKHCONP1AMKARRF3600 | DUKHCONP1AMKARRF3610, DUKHCONP1AMKARRF3695, DUKHCONP1AMKARRF3630, DUKHCONP1AMKAREL3665, DUKHCONP1AZ1ARRF3605, DUKHCONP1AMKPLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.05 .15 .15 EXTERNAL FINISHES |  | 36 | 36 | 0% | 2013-11-04 | 2013-12-15 | 2013-11-04 | 2013-12-15 | 65 |  |  |  | 0 | 0
DHBL.K30.L15.05 .15 .15 .10 ROOF |  | 28 | 28 | 0% | 2013-11-04 | 2013-12-05 | 2013-11-04 | 2013-12-05 | 73 |  |  |  | 0 | 0
DUKHCONP1AMKARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 5 | 5 | 0% | 2013-11-18 | 2013-11-23 | 2013-11-18 | 2013-11-23 | 55 | No | DUKHCONP1AMKARRF3645, DUKHPROGEN00PRDV3410 | DUKHCONP1AZ1ARRF3650, DUKHCONP1AMKARRF3655 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3660 | Installation of Access Ladder | 6 | 6 | 0% | 2013-11-30 | 2013-12-05 | 2013-11-30 | 2013-12-05 | 73 | No | DUKHCONP1AMKARRF3655, DUKHPROGEN00PRDV3400, DUKHCONP1AMKARRF3620 | DUKHCONP1AZ1ARRF3660 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3640 | Installation of Insulation & Protection | 4 | 4 | 0% | 2013-11-11 | 2013-11-14 | 2013-11-11 | 2013-11-14 | 9 | No | DUKHCONP1AMKARRF3635 | DUKHCONP1AMKARRF3645, DUKHCONP1AZ1ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3655 | Installation of Pumps Protection cabinets | 5 | 5 | 0% | 2013-11-24 | 2013-11-28 | 2013-11-24 | 2013-11-28 | 55 | No | DUKHCONP1AMKARRF3650, DUKHCONP1AMKARRF3645 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AMKARRF3660, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1ARRF3655, DUKHCONP1AMKPLRF4355 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3635 | Laying of Waterproofing Membrane | 4 | 4 | 0% | 2013-11-06 | 2013-11-10 | 2013-11-06 | 2013-11-10 | 9 | No | DUKHCONP1AMKARRF3630 | DUKHCONP1AZ1ARRF3635, DUKHCONP1AMKARRF3640 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3630 | Leveling Screed for Waterproofing | 2 | 2 | 0% | 2013-11-04 | 2013-11-05 | 2013-11-04 | 2013-11-05 | 9 | No | DUKHCONP1AZ1STRF2055, DUKHCONP1AZ1STRF2065, DUKHCONP1AZ1STRF2060, DUKHCONP1AMKARRF3605 | DUKHCONP1AMKARRF3635, DUKHCONP1AZ1ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AMKARRF3645 | Lime Stone Chips & Paving slab Installation | 2 | 2 | 0% | 2013-11-16 | 2013-11-17 | 2013-11-16 | 2013-11-17 | 9 | No | DUKHCONP1AMKARRF3640 | DUKHCONP1AZ1ARRF3645, DUKHCONP1AMKAREL3665, DUKHCONP1AMKARRF3650, DUKHCONP1AMKACRF4635, DUKHCONP1AMKARRF3655, DUKHCONP1AMKPLRF4345, DUKHCONP1AMKELRF4070, DUKHCONP1AMKPLRF4355, DUKHCONP1AMKACRF4630 | 0 | 0 | ROOF
DHBL.K30.L15.05 .15 .15 .15 ELEVATION |  | 24 | 24 | 0% | 2013-11-18 | 2013-12-15 | 2013-11-18 | 2013-12-15 | 60 |  |  |  | 0 | 0
DUKHCONP1AMKAREL3680 | External Painting | 7 | 7 | 0% | 2013-12-08 | 2013-12-15 | 2013-12-08 | 2013-12-15 | 60 | No | DUKHCONP1AMKAREL3665, DUKHCONP1AMKAREL3670 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1AMKAREL3665 | External Plastering | 10 | 10 | 0% | 2013-11-18 | 2013-11-28 | 2013-11-18 | 2013-11-28 | 16 | No | DUKHCONP1AMKARRF3645, DUKHCONP1AZ1STRF2060, DUKHCONP1AMKARRF3605 | DUKHCONP1AMKAREL3680, DUKHCONP1AZ1AREL3665, DUKHCONP1AMKMSEX5020, DUKHCONP1AMKAREL3670 | 0 | 0 | ELEVATION
DUKHCONP1AMKAREL3670 | External stone cladding works | 7 | 7 | 0% | 2013-11-30 | 2013-12-07 | 2013-11-30 | 2013-12-07 | 16 | No | DUKHPROGEN00PRDV3110, DUKHCONP1AMKAREL3665 | DUKHCONP1AZ1AREL3670, DUKHCONP1AMKAREL3680, DUKHCONP1AMKMSEX5020 | 0 | 0 | ELEVATION
DHBL.K30.L15.05 .20 MEP WORKS |  | 102 | 102 | 0% | 2013-09-10 | 2014-01-09 | 2013-09-10 | 2014-01-09 | 44 |  |  |  | 0 | 0
DHBL.K30.L15.05 .20 .10 ELECTRICAL WORKS |  | 100 | 100 | 0% | 2013-09-10 | 2014-01-07 | 2013-09-10 | 2014-01-07 | 38 |  |  |  | 0 | 0
DHBL.K30.L15.05 .20 .10 .10 GROUND FLOOR |  | 52 | 52 | 0% | 2013-09-10 | 2013-11-11 | 2013-09-10 | 2013-11-11 | 64 |  |  |  | 0 | 0
DUKHCONP1AMKELGF4005 | Cable tray & trunking installation | 5 | 5 | 0% | 2013-09-24 | 2013-09-29 | 2013-09-24 | 2013-09-29 | 43 | No | DUKHCONP1AMKELGF4000, DUKHCONP1AMKARGF3005 | DUKHCONP1AZ1ELGF4005, DUKHCONP1AMKELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKELGF4000 | Fixing of wall conduits & switch socket boxes | 5 | 5 | 0% | 2013-09-10 | 2013-09-15 | 2013-09-10 | 2013-09-15 | 25 | No | DUKHCONP1AMKARGF3000 | DUKHCONP1AMKELGF4005, DUKHCONP1AZ1ELGF4000, DUKHCONP1AMKARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKELGF4015 | Install. of CAMS & Fire Fighting Accessories | 7 | 7 | 0% | 2013-11-02 | 2013-11-09 | 2013-11-02 | 2013-11-09 | 54 | No | DUKHPROGEN00PRDV3380, DUKHPROGEN00PRDV3370, DUKHCONP1AMKARGF3055, DUKHPROGEN00PRDV3360, DUKHCONP1AMKARGF3060, DUKHPROGEN00PRDV3260, DUKHPROGEN00PRDV3210 | DUKHCONP1AMKELFF4055, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKELGF4020 | Installation of DBS,MCCB Accessories. | 5 | 5 | 0% | 2013-10-31 | 2013-11-05 | 2013-10-31 | 2013-11-05 | 52 | No | DUKHPROGEN00PRDV3170, DUKHCONP1AMKARGF3055, DUKHCONP1AMKELGF4010, DUKHCONP1AMKARGF3060 | DUKHCONP1AMKELGF4030, DUKHCONP1AMKELGF4025, DUKHCONP1AZ1ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKELGF4025 | Installation of Lighting fixtures & Accessories | 5 | 5 | 0% | 2013-11-06 | 2013-11-11 | 2013-11-06 | 2013-11-11 | 64 | No | DUKHCONP1AMKELGF4020, DUKHPROGEN00PRDV3190, DUKHCONP1AMKARGF3055, DUKHCONP1AMKARGF3060 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1ELTC8010, DUKHCONP1AMKELFF4065, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKELGF4030 | Installation of Telephone System | 5 | 5 | 0% | 2013-11-06 | 2013-11-11 | 2013-11-06 | 2013-11-11 | 57 | No | DUKHCONP1AMKELGF4020, DUKHPROGEN00PRDV3270, DUKHCONP1AMKARGF3055, DUKHCONP1AMKARGF3060, DUKHPROGEN00PRDV3280 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1PLTC8005, DUKHCONP1AMKELFF4050, DUKHCONP1AZ1ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKELGF4010 | Installation of wiring & Main Cabling | 5 | 5 | 0% | 2013-09-30 | 2013-10-05 | 2013-09-30 | 2013-10-05 | 45 | No | DUKHCONP1AMKELGF4005, DUKHPROGEN00PRDV3180 | DUKHCONP1AMKELGF4020, DUKHCONP1AZ1ELGF4010, DUKHCONP1AMKARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.05 .20 .10 .15 FIRST FLOORS |  | 52 | 52 | 0% | 2013-10-24 | 2013-12-24 | 2013-10-24 | 2013-12-24 | 33 |  |  |  | 0 | 0
DUKHCONP1AMKELFF4040 | Cable tray & trunking installation | 5 | 5 | 0% | 2013-11-07 | 2013-11-12 | 2013-11-07 | 2013-11-12 | 26 | No | DUKHCONP1AMKELFF4035, DUKHCONP1AMKARFF3305 | DUKHCONP1AZ1ELFF4040, DUKHCONP1AMKELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKELFF4035 | Fixing of wall conduits & switch socket boxes | 5 | 5 | 0% | 2013-10-24 | 2013-10-29 | 2013-10-24 | 2013-10-29 | 8 | No | DUKHCONP1AMKARFF3300 | DUKHCONP1AZ1ELFF4035, DUKHCONP1AMKELFF4040, DUKHCONP1AMKARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKELFF4055 | Install. of CAMS & Fire Fighting Accessories | 7 | 7 | 0% | 2013-12-12 | 2013-12-21 | 2013-12-12 | 2013-12-21 | 26 | No | DUKHPROGEN00PRDV3360, DUKHCONP1AMKELGF4015, DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3260, DUKHCONP1AMKARFF3360 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKELFF4060 | Installation of DBS,MCCB Accessories. | 5 | 5 | 0% | 2013-12-12 | 2013-12-17 | 2013-12-12 | 2013-12-17 | 31 | No | DUKHCONP1AMKELFF4045, DUKHPROGEN00PRDV3170, DUKHCONP1AMKARFF3360 | DUKHCONP1AMKELFF4065, DUKHCONP1AMKELFF4050, DUKHCONP1AZ1ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKELFF4065 | Installation of Lighting fixtures & Accessories | 5 | 5 | 0% | 2013-12-19 | 2013-12-24 | 2013-12-19 | 2013-12-24 | 33 | No | DUKHPROGEN00PRDV3190, DUKHCONP1AMKARFF3360, DUKHCONP1AMKELGF4025, DUKHCONP1AMKELFF4060 | DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ACTC8000, DUKHCONP1AMKELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKELFF4050 | Installation of Telephone System | 5 | 5 | 0% | 2013-12-19 | 2013-12-24 | 2013-12-19 | 2013-12-24 | 31 | No | DUKHPROGEN00PRDV3280, DUKHCONP1AMKELFF4060, DUKHPROGEN00PRDV3270, DUKHCONP1AMKARFF3360, DUKHCONP1AMKELGF4030 | DUKHCONP1AMKELRF4070, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ELFF4050 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKELFF4045 | Installation of wiring & Main Cabling | 5 | 5 | 0% | 2013-11-13 | 2013-11-18 | 2013-11-13 | 2013-11-18 | 28 | No | DUKHCONP1AMKELFF4040, DUKHPROGEN00PRDV3180 | DUKHCONP1AZ1ELFF4045, DUKHCONP1AMKELRF4070, DUKHCONP1AMKELFF4060, DUKHCONP1AMKARFF3345 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.05 .20 .10 .20 ROOF |  | 12 | 12 | 0% | 2013-12-25 | 2014-01-07 | 2013-12-25 | 2014-01-07 | 38 |  |  |  | 0 | 0
DUKHCONP1AMKELRF4070 | Installation of Isolator | 5 | 5 | 0% | 2013-12-25 | 2013-12-30 | 2013-12-25 | 2013-12-30 | 38 | No | DUKHPROGEN00PRDV3200, DUKHCONP1AMKELFF4045, DUKHCONP1AMKELFF4050, DUKHCONP1AMKARRF3645, DUKHCONP1AMKELFF4065 | DUKHCONP1AZ1ELRF4070, DUKHCONP1AMKELRF4075 | 0 | 0 | ROOF
DUKHCONP1AMKELRF4075 | Installation of TV Dish Antenna | 7 | 7 | 0% | 2013-12-31 | 2014-01-07 | 2013-12-31 | 2014-01-07 | 38 | No | DUKHPROGEN00PRDV3290, DUKHCONP1AMKELRF4070 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ELRF4075, DUKHCONP1AZ1PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L15.05 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 102 | 102 | 0% | 2013-09-10 | 2014-01-09 | 2013-09-10 | 2014-01-09 | 44 |  |  |  | 0 | 0
DHBL.K30.L15.05 .20 .15 .10 GROUND FLOOR |  | 67 | 67 | 0% | 2013-09-10 | 2013-11-28 | 2013-09-10 | 2013-11-28 | 79 |  |  |  | 0 | 0
DUKHCONP1AMKPLGF4310 | Installation of Drainage pipes &testing | 5 | 5 | 0% | 2013-09-10 | 2013-09-15 | 2013-09-10 | 2013-09-15 | 45 | No | DUKHCONP1AMKPLGF4305, DUKHCONP1AMKARGF3000 | DUKHCONP1AMKMSEX5000, DUKHCONP1AZ1PLGF4310, DUKHCONP1AMKPLGF4315, DUKHCONP1AMKARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKPLGF4305 | Installation of Plumbing pipes & testing | 5 | 5 | 0% | 2013-09-10 | 2013-09-15 | 2013-09-10 | 2013-09-15 | 27 | No | DUKHCONP1AMKARGF3000 | DUKHCONP1AZ1PLGF4305, DUKHCONP1AMKPLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKPLGF4320 | Installation of Water Heater | 5 | 5 | 0% | 2013-11-24 | 2013-11-28 | 2013-11-24 | 2013-11-28 | 79 | No | DUKHCONP1AMKARGF3055, DUKHCONP1AMKARGF3060, DUKHCONP1AMKPLGF4315 | DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLGF4320, DUKHCONP1AZ1ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKPLGF4315 | Sanitary Fittings & Accessories | 7 | 7 | 0% | 2013-11-16 | 2013-11-23 | 2013-11-16 | 2013-11-23 | 48 | No | DUKHCONP1AMKPLGF4310, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3150, DUKHCONP1AMKARGF3065, DUKHPROGEN00PRDV3230 | DUKHCONP1AMKPLGF4320, DUKHCONP1AZ1PLGF4315, DUKHCONP1AMKPLFF4335 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.05 .20 .15 .15 FIRST FLOORS |  | 59 | 59 | 0% | 2013-10-24 | 2014-01-01 | 2013-10-24 | 2014-01-01 | 27 |  |  |  | 0 | 0
DUKHCONP1AMKPLFF4330 | Installation of Drainage pipes & testing | 5 | 5 | 0% | 2013-10-24 | 2013-10-29 | 2013-10-24 | 2013-10-29 | 30 | No | DUKHCONP1AMKPLFF4325 | DUKHCONP1AMKPLFF4335, DUKHCONP1AMKPLRF4350, DUKHCONP1AMKMSEX5000, DUKHCONP1AZ1PLFF4330, DUKHCONP1AMKARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKPLFF4325 | Installation of Plumbing pipes & testing | 5 | 5 | 0% | 2013-10-24 | 2013-10-29 | 2013-10-24 | 2013-10-29 | 9 | No | DUKHPROGEN00PRDV3080, DUKHCONP1AMKARFF3300 | DUKHCONP1AMKARFF3320, DUKHCONP1AZ1PLFF4325, DUKHCONP1AMKPLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKPLFF4340 | Installation of Water Heater | 5 | 5 | 0% | 2013-12-28 | 2014-01-01 | 2013-12-28 | 2014-01-01 | 27 | No | DUKHCONP1AMKARFF3360, DUKHCONP1AMKPLFF4335 | DUKHCONP1AZ1PLFF4340, DUKHCONP1AMKPLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKPLFF4335 | Sanitary Fittings & Accessories | 7 | 7 | 0% | 2013-12-19 | 2013-12-26 | 2013-12-19 | 2013-12-26 | 27 | No | DUKHCONP1AMKPLFF4330, DUKHCONP1AMKARFF3365, DUKHCONP1AMKPLGF4315 | DUKHCONP1AMKPLFF4340, DUKHCONP1AZ1PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.05 .20 .15 .20 ROOF |  | 45 | 45 | 0% | 2013-11-18 | 2014-01-09 | 2013-11-18 | 2014-01-09 | 27 |  |  |  | 0 | 0
DUKHCONP1AMKPLRF4345 | Installation of Plumbing pipes & fittings | 5 | 5 | 0% | 2013-11-18 | 2013-11-23 | 2013-11-18 | 2013-11-23 | 9 | No | DUKHCONP1AMKARRF3645, DUKHCONP1AMKARRF3605 | DUKHCONP1AMKWEEX5030, DUKHCONP1AMKPLRF4355, DUKHCONP1AZ1PLRF4345, DUKHCONP1AMKMSEX5000, DUKHCONP1AMKPLRF4350 | 0 | 0 | ROOF
DUKHCONP1AMKPLRF4350 | Installation of Rain water Pipes | 5 | 5 | 0% | 2013-11-24 | 2013-11-28 | 2013-11-24 | 2013-11-28 | 55 | No | DUKHCONP1AMKPLFF4330, DUKHCONP1AMKPLRF4345 | DUKHCONP1AMKWEEX5065, DUKHCONP1AZ1PLTC8005, DUKHCONP1AMKPLRF4355, DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AMKPLRF4355 | Roof Water Tank Installation & Connections | 7 | 7 | 0% | 2014-01-02 | 2014-01-09 | 2014-01-02 | 2014-01-09 | 27 | No | DUKHCONP1AMKPLRF4345, DUKHCONP1AMKPLFF4340, DUKHCONP1AMKARRF3655, DUKHCONP1AMKPLRF4350, DUKHCONP1AMKARRF3645 | DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1PLRF4355, DUKHCONP1AMKWEEX5065, DUKHCONP1AZ1ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.05 .20 .20 AC WORKS |  | 81 | 81 | 0% | 2013-09-24 | 2013-12-30 | 2013-09-24 | 2013-12-30 | 43 |  |  |  | 0 | 0
DHBL.K30.L15.05 .20 .20 .10 GROUND FLOOR |  | 40 | 40 | 0% | 2013-09-24 | 2013-11-11 | 2013-09-24 | 2013-11-11 | 73 |  |  |  | 0 | 0
DUKHCONP1AMKACGF4610 | Fixing of Split AC | 5 | 5 | 0% | 2013-11-06 | 2013-11-11 | 2013-11-06 | 2013-11-11 | 73 | No | DUKHCONP1AMKACGF4605, DUKHPROGEN00PRDV3240 | DUKHCONP1AMKACFF4625, DUKHCONP1AMKACRF4635, DUKHCONP1AZ1ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKACGF4605 | Fixing of Ventilation Equipments | 5 | 5 | 0% | 2013-10-31 | 2013-11-05 | 2013-10-31 | 2013-11-05 | 60 | No | DUKHPROGEN00PRDV3530, DUKHCONP1AMKACGF4600, DUKHCONP1AMKARGF3060, DUKHPROGEN00PRDV3340, DUKHCONP1AMKARGF3055 | DUKHCONP1AMKACGF4610, DUKHCONP1AMKACFF4620, DUKHCONP1AZ1ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AMKACGF4600 | Installation AC Pipes | 5 | 5 | 0% | 2013-09-24 | 2013-09-29 | 2013-09-24 | 2013-09-29 | 63 | No | DUKHCONP1AMKARGF3005, DUKHPROGEN00PRDV3160 | DUKHCONP1AMKACGF4605, DUKHCONP1AMKACFF4615, DUKHCONP1AMKARGF3055, DUKHCONP1AMKARGF3060, DUKHCONP1AMKACRF4630, DUKHCONP1AZ1ACGF4600 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.05 .20 .20 .15 FIRST FLOORS |  | 40 | 40 | 0% | 2013-11-07 | 2013-12-24 | 2013-11-07 | 2013-12-24 | 42 |  |  |  | 0 | 0
DUKHCONP1AMKACFF4625 | Fixing of Split AC | 5 | 5 | 0% | 2013-12-19 | 2013-12-24 | 2013-12-19 | 2013-12-24 | 42 | No | DUKHCONP1AMKACGF4610, DUKHCONP1AMKACFF4620, DUKHPROGEN00PRDV3240 | DUKHCONP1AMKACRF4635, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ACFF4625, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKACFF4620 | Fixing of Ventilation Equipments | 5 | 5 | 0% | 2013-12-12 | 2013-12-17 | 2013-12-12 | 2013-12-17 | 29 | No | DUKHPROGEN00PRDV3340, DUKHCONP1AMKACFF4615, DUKHCONP1AMKACGF4605, DUKHCONP1AMKARFF3360 | DUKHCONP1AZ1ACFF4620, DUKHCONP1AMKACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1AMKACFF4615 | Installation AC Pipes | 5 | 5 | 0% | 2013-11-07 | 2013-11-12 | 2013-11-07 | 2013-11-12 | 40 | No | DUKHPROGEN00PRDV3160, DUKHCONP1AMKARFF3305, DUKHCONP1AMKACGF4600 | DUKHCONP1AZ1ACFF4615, DUKHCONP1AMKACRF4630, DUKHCONP1AMKACFF4620, DUKHCONP1AMKARFF3360 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.05 .20 .20 .20 ROOF |  | 36 | 36 | 0% | 2013-11-18 | 2013-12-30 | 2013-11-18 | 2013-12-30 | 43 |  |  |  | 0 | 0
DUKHCONP1AMKACRF4635 | Installation of Condensing Unit | 5 | 5 | 0% | 2013-12-25 | 2013-12-30 | 2013-12-25 | 2013-12-30 | 43 | No | DUKHCONP1AMKACFF4625, DUKHCONP1AMKACRF4630, DUKHCONP1AMKARRF3645, DUKHCONP1AMKACGF4610 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1ACRF4635, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AMKACRF4630 | Installation of Refrigerant Pipes | 5 | 5 | 0% | 2013-11-18 | 2013-11-23 | 2013-11-18 | 2013-11-23 | 69 | No | DUKHCONP1AMKACFF4615, DUKHCONP1AMKACGF4600, DUKHCONP1AMKARRF3645 | DUKHCONP1AMKACRF4635, DUKHCONP1AZ1ACRF4630 | 0 | 0 | ROOF
DHBL.K30.L15.05 .25 EXTERNAL WORKS |  | 65 | 65 | 0% | 2013-11-24 | 2014-02-08 | 2013-11-24 | 2014-02-08 | 9 |  |  |  | 0 | 0
DHBL.K30.L15.05 .25 .10 MISCELLANEOUS |  | 24 | 24 | 0% | 2013-11-24 | 2013-12-22 | 2013-11-24 | 2013-12-22 | 18 |  |  |  | 0 | 0
DUKHCONP1AMKMSEX5005 | Construction of Soak pit, Chambers | 7 | 7 | 0% | 2013-12-02 | 2013-12-09 | 2013-12-02 | 2013-12-09 | 9 | No | DUKHCONP1AMKMSEX5000 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1MSEX5005, DUKHCONP1AMKMSEX5015, DUKHCONP1AZ1ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AMKMSEX5020 | Construction Entrance Ramp | 7 | 7 | 0% | 2013-12-08 | 2013-12-15 | 2013-12-08 | 2013-12-15 | 16 | No | DUKHCONP1AMKAREL3670, DUKHCONP1AMKAREL3665 | DUKHCONP1AZ1MSEX5020, DUKHCONP1AMKMSEX5025, DUKHCONP1AMKHDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AMKMSEX5015 | Construction of grease Trap | 7 | 7 | 0% | 2013-12-10 | 2013-12-17 | 2013-12-10 | 2013-12-17 | 9 | No | DUKHCONP1AMKMSEX5005 | DUKHCONP1AZ1MSEX5015, DUKHCONP1AMKWEEX5030, DUKHCONP1AMKWEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AMKMSEX5000 | Construction of Manholes | 7 | 7 | 0% | 2013-11-24 | 2013-12-01 | 2013-11-24 | 2013-12-01 | 9 | No | DUKHCONP1AMKPLGF4310, DUKHCONP1AMKPLFF4330, DUKHCONP1AMKPLRF4345 | DUKHCONP1AMKMSEX5005, DUKHCONP1AZ1MSEX5000 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AMKMSEX5025 | SS.Handrails and Balustrades | 5 | 5 | 0% | 2013-12-16 | 2013-12-22 | 2013-12-16 | 2013-12-22 | 18 | No | DUKHCONP1AMKMSEX5020 | DUKHCONP1AMKWEEX5060, DUKHCONP1AZ1MSEX5025, DUKHCONP1AMKHDEX5090 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.05 .25 .15 WATER TANK ENCLOSURE |  | 44 | 44 | 0% | 2013-12-19 | 2014-02-08 | 2013-12-19 | 2014-02-08 | 9 |  |  |  | 0 | 0
DUKHCONP1AMKWEEX5040 | Block works & Plastering | 7 | 7 | 0% | 2014-01-01 | 2014-01-08 | 2014-01-01 | 2014-01-08 | 9 | No | DUKHCONP1AMKWEEX5035 | DUKHCONP1AMKWEEX5045, DUKHCONP1AZ1WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AMKWEEX5035 | Construction of Raft | 7 | 7 | 0% | 2013-12-24 | 2013-12-31 | 2013-12-24 | 2013-12-31 | 9 | No | DUKHCONP1AMKWEEX5030 | DUKHCONP1AMKWEEX5040, DUKHCONP1AZ1WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AMKWEEX5030 | Excavation | 4 | 4 | 0% | 2013-12-19 | 2013-12-23 | 2013-12-19 | 2013-12-23 | 9 | No | DUKHCONP1AMKPLRF4345, DUKHCONP1AMKMSEX5015 | DUKHCONP1AZ1WEEX5030, DUKHCONP1AMKWEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AMKWEEX5045 | Flooring & Painting | 7 | 7 | 0% | 2014-01-09 | 2014-01-16 | 2014-01-09 | 2014-01-16 | 9 | No | DUKHCONP1AMKWEEX5040 | DUKHCONP1AMKWEEX5050, DUKHCONP1AZ1WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AMKWEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 7 | 7 | 0% | 2014-02-01 | 2014-02-08 | 2014-02-01 | 2014-02-08 | 9 | No | DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3680, DUKHCONP1AMKPLRF4350, DUKHPROGEN00PRDV3640, DUKHCONP1AMKPLRF4355, DUKHCONP1AMKMSEX5015, DUKHPROGEN00PRDV3330, DUKHCONP1AMKWEEX5060 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1WEEX5065, DUKHCONP1AZ1ACTC8000 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AMKWEEX5050 | Installation of Steel Gate | 5 | 5 | 0% | 2014-01-18 | 2014-01-22 | 2014-01-18 | 2014-01-22 | 9 | No | DUKHPROGEN00PRDV3510, DUKHCONP1AMKWEEX5045, DUKHPROGEN00PRDV3500, DUKHPROGEN00PRDV3610 | DUKHCONP1AZ1WEEX5050, DUKHCONP1AMKWEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AMKWEEX5060 | Structural steel & SS Shed cover installation | 7 | 7 | 0% | 2014-01-23 | 2014-01-30 | 2014-01-23 | 2014-01-30 | 9 | No | DUKHPROGEN00PRDV3630, DUKHCONP1AMKMSEX5025, DUKHPROGEN00PRDV3620, DUKHCONP1AMKWEEX5050 | DUKHCONP1AZ1WEEX5060, DUKHCONP1AMKWEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.05 .25 .20 HARD LANDSCAPING |  | 15 | 15 | 0% | 2013-12-23 | 2014-01-08 | 2013-12-23 | 2014-01-08 | 21 |  |  |  | 0 | 0
DUKHCONP1AMKHDEX5095 | Cobble Stone Works | 5 | 5 | 0% | 2013-12-29 | 2014-01-02 | 2013-12-29 | 2014-01-02 | 21 | No | DUKHCONP1AMKHDEX5090 | DUKHCONP1AZ1HDEX5095, DUKHCONP1AMKHDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AMKHDEX5100 | Interlock works | 5 | 5 | 0% | 2014-01-04 | 2014-01-08 | 2014-01-04 | 2014-01-08 | 21 | No | DUKHPROGEN00PRDV3660, DUKHCONP1AMKHDEX5095 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AMKSLEX5105, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1HDEX5100, DUKHCONP1AZ1PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AMKHDEX5090 | kerb works | 5 | 5 | 0% | 2013-12-23 | 2013-12-28 | 2013-12-23 | 2013-12-28 | 18 | No | DUKHPROGEN00PRDV3600, DUKHCONP1AMKMSEX5020, DUKHCONP1AMKMSEX5025 | DUKHCONP1AZ1HDEX5090, DUKHCONP1AMKHDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.05 .25 .25 SOFT LANDSCAPING |  | 14 | 14 | 0% | 2014-01-09 | 2014-01-25 | 2014-01-09 | 2014-01-25 | 21 |  |  |  | 0 | 0
DUKHCONP1AMKSLEX5105 | Laying of Grass/ green area | 7 | 7 | 0% | 2014-01-09 | 2014-01-16 | 2014-01-09 | 2014-01-16 | 21 | No | DUKHCONP1AMKHDEX5100, DUKHPROGEN00PRDV3790, DUKHPROGEN00PRDV3670 | DUKHCONP1AMKSLEX5110, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1SLEX5105, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AMKSLEX5110 | Laying of Palm tree | 7 | 7 | 0% | 2014-01-18 | 2014-01-25 | 2014-01-18 | 2014-01-25 | 21 | No | DUKHCONP1AMKSLEX5105 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1SLEX5110, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.10 ZONE - 1 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-02-14 | 2014-04-19 | 2013-02-14 | 2014-04-19 | 90 |  |  |  | 0 | 0
DHBL.K30.L15.10 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-02-14 | 2013-11-24 | 2013-02-14 | 2013-11-24 | 9 |  |  |  | 0 | 0
DHBL.K30.L15.10 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-02-14 | 2013-07-10 | 2013-02-14 | 2013-07-10 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.10 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-02-14 | 2013-07-10 | 2013-02-14 | 2013-07-10 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ1STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-04-24 | 2013-05-22 | 2013-04-24 | 2013-05-22 | 0 | Yes | DUKHCONP1AZ1STUG1030, DUKHCONP1AZ1STUG1030 | DUKHCONP1AZ1STUG1040, DUKHCONP1AZ2STUG1035, DUKHCONP1AZ1STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-03-23 | 2013-04-14 | 2013-03-23 | 2013-04-14 | 0 | Yes | DUKHMOBP010000004060, DUKHMOBP010000004080, DUKHPROGEN00PRDV3010, DUKHMOBP010000004090, DUKHCONP1AZ1STUG1015, DUKHCONP1AZ1STUG1015, DUKHMOBP010000004070 | DUKHCONP1AZ1STUG1025, DUKHCONP1AZ1STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1040 | Construction of Grade Beams | 26 | 26 | 0% | 2013-05-11 | 2013-06-09 | 2013-05-11 | 2013-06-09 | 0 | Yes | DUKHENGP1ADWSTAP4010, DUKHCONP1AZ1STUG1035, DUKHCONP1AZ1STUG1035 | DUKHCONP1AZ1PLUG4300, DUKHCONP1AZ1PLUG4300, DUKHCONP1AZ1STUG1045, DUKHCONP1AZ1STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-04-01 | 2013-04-29 | 2013-04-01 | 2013-04-29 | 0 | Yes | DUKHCONP1AZ1STUG1020, DUKHCONP1AZ1STUG1020 | DUKHCONP1AZ1STUG1030, DUKHCONP1AZ1STUG1030, DUKHCONP1AZ2STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-06-12 | 2013-07-10 | 2013-06-12 | 2013-07-10 | 0 | Yes | DUKHCONP1AZ1PLUG4300, DUKHENGP1ADWSTAP4010, DUKHCONP1AZ1STUG1040, DUKHCONP1AZ1PLUG4300, DUKHCONP1AZ1STUG1040 | DUKHCONP1AZ1STGF2000, DUKHCONP1AZ1STGF2000, DUKHCONP1AZ2STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-02-26 | 2013-03-24 | 2013-02-26 | 2013-03-24 | 0 | Yes | DUKHCONP1AZ1STUG1000, DUKHPROGEN00PRDV3000, DUKHCONP1AZ1STUG1000 | DUKHCONP1AZ1STUG1010, DUKHCONP1AZ1STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-03-02 | 2013-03-27 | 2013-03-02 | 2013-03-27 | 0 | Yes | DUKHCONP1AZ1STUG1005, DUKHCONP1AZ1STUG1005, DUKHPROGEN00PRDV3020 | DUKHCONP1AZ1STUG1015, DUKHCONP1AZ1STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-02-14 | 2013-03-14 | 2013-02-14 | 2013-03-14 | 0 | Yes | DUKHMOBP010000004040, DUKHMOBP010000004050, DUKHMOBI1APS00001250, DUKHMOBI1APS00002043, DUKHCONP1AGNSP005000, DUKHCONP1AGNSP002500 | DUKHCONP1AZ1STUG1005, DUKHCONP1AZ2STUG1000, DUKHCONP1AZ1STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-03-07 | 2013-04-04 | 2013-03-07 | 2013-04-04 | 0 | Yes | DUKHCONP1AZ1STUG1010, DUKHPROGEN00PRDV3030, DUKHPROGEN00PRDV3020, DUKHCONP1AZ1STUG1010, DUKHENGP1ADWSTAP4000 | DUKHCONP1AZ1STUG1020, DUKHCONP1AZ1STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ1STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-04-10 | 2013-05-08 | 2013-04-10 | 2013-05-08 | 0 | Yes | DUKHCONP1AZ1STUG1025, DUKHCONP1AZ1STUG1025 | DUKHCONP1AZ1STUG1035, DUKHCONP1AZ1STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.10 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2013-06-29 | 2013-11-24 | 2013-06-29 | 2013-11-24 | 9 |  |  |  | 0 | 0
DHBL.K30.L15.10 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-06-29 | 2013-08-26 | 2013-06-29 | 2013-08-26 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ1STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-08-06 | 2013-08-26 | 2013-08-06 | 2013-08-26 | 0 | Yes | DUKHCONP1AZ1STGF2010, DUKHCONP1AZ1STGF2010 | DUKHCONP1AZ2STGF2015, DUKHCONP1AZ1ARGF3000, DUKHCONP1AMKARRF3600, DUKHCONP1AZ1STFF2020, DUKHCONP1AMKARGF3000, DUKHCONP1AZ1STFF2020, DUKHCONP1AMKARGF3000, DUKHCONP1AZ1ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-07-22 | 2013-08-22 | 2013-07-22 | 2013-08-22 | 0 | Yes | DUKHENGP1ADWSTAP4030, DUKHCONP1AZ1STGF2005, DUKHCONP1AZ1STGF2005 | DUKHCONP1AZ1STGF2015, DUKHCONP1AZ1STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-07-07 | 2013-08-03 | 2013-07-07 | 2013-08-03 | 0 | Yes | DUKHCONP1AZ1STGF2000, DUKHCONP1AZ1STGF2000 | DUKHCONI1AZ4DRGL5115, DUKHCONP1AZ1STGF2010, DUKHCONP1AZ1STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-06-29 | 2013-07-27 | 2013-06-29 | 2013-07-27 | 0 | Yes | DUKHCONP1AZ1STUG1045, DUKHCONP1AZ1STUG1045, DUKHENGP1ADWSTAP4020 | DUKHCONP1AZ1STGF2005, DUKHCONP1AZ2STGF2000, DUKHCONP1AZ1STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.10 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2013-08-08 | 2013-10-07 | 2013-08-08 | 2013-10-07 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ1STFF2035 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-09-21 | 2013-10-07 | 2013-09-21 | 2013-10-07 | 0 | Yes | DUKHCONP1AZ1STFF2030, DUKHCONP1AZ1STFF2030 | DUKHCONP1AZ1STRF2040, DUKHCONP1AZ1STRF2040, DUKHCONP1AZ1ARFF3300, DUKHCONP1AZ2STFF2035, DUKHCONP1AZ1ARFF3300, DUKHCONP1AMKARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-09-05 | 2013-10-03 | 2013-09-05 | 2013-10-03 | 0 | Yes | DUKHCONP1AZ1STFF2025, DUKHCONP1AZ1STFF2025 | DUKHCONP1AZ1STFF2035, DUKHCONP1AZ1STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-08-21 | 2013-09-17 | 2013-08-21 | 2013-09-17 | 0 | Yes | DUKHCONP1AZ1STFF2020, DUKHCONP1AZ1STFF2020 | DUKHCONP1AZ1STFF2030, DUKHCONP1AZ1STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-08-08 | 2013-09-09 | 2013-08-08 | 2013-09-09 | 0 | Yes | DUKHCONP1AZ1STGF2015, DUKHCONP1AZ1STGF2015, DUKHENGP1ADWSTAP4040 | DUKHCONP1AZ1STFF2025, DUKHCONP1AZ1ARFF3300, DUKHCONP1AZ2STFF2020, DUKHCONP1AZ1ARFF3300, DUKHCONP1AZ1STFF2025 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.10 .10 .15 .20 ROOF |  | 51 | 51 | 0% | 2013-09-24 | 2013-11-24 | 2013-09-24 | 2013-11-24 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ1STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-09-29 | 2013-10-20 | 2013-09-29 | 2013-10-20 | 9 | No | DUKHCONP1AZ1STRF2040, DUKHCONP1AZ1STRF2040 | DUKHCONP1AZ1STRF2050, DUKHCONP1AZ1STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ1STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-09-24 | 2013-10-14 | 2013-09-24 | 2013-10-14 | 9 | No | DUKHCONP1AZ1STFF2035, DUKHCONP1AZ1STFF2035 | DUKHCONP1AZ1STRF2045, DUKHCONP1AZ2STRF2040, DUKHCONP1AZ1STRF2045 | 0 | 0 | ROOF
DUKHCONP1AZ1STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-10-21 | 2013-11-18 | 2013-10-21 | 2013-11-18 | 9 | No | DUKHCONP1AZ1STRF2055, DUKHCONP1AZ1STRF2055 | DUKHCONP1AZ1ARRF3630, DUKHCONP1AZ1STRF2065, DUKHCONP1AZ1ARRF3630, DUKHCONP1AMKAREL3665, DUKHCONP1AMKARRF3630, DUKHCONP1AZ1STRF2065 | 0 | 0 | ROOF
DUKHCONP1AZ1STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-10-27 | 2013-11-24 | 2013-10-27 | 2013-11-24 | 9 | No | DUKHCONP1AZ1STRF2060, DUKHCONP1AZ1STRF2060 | DUKHCONP1AZ1AREL3665, DUKHCONP1AZ1AREL3665, DUKHCONP1AZ1ARRF3630, DUKHCONP1AMKARRF3630, DUKHCONP1AZ2STRF2065, DUKHCONP1AZ1ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ1STRF2055 | Slab-Concrete-Head room | 10 | 10 | 0% | 2013-10-16 | 2013-10-29 | 2013-10-16 | 2013-10-29 | 9 | No | DUKHCONP1AZ1STRF2050, DUKHCONP1AZ1STRF2050 | DUKHCONP1AZ1WEEX5030, DUKHCONP1AZ2STRF2055, DUKHCONP1AZ1MSEX5000, DUKHCONP1AZ1MSEX5020, DUKHCONP1AMKARRF3630, DUKHCONP1AZ1MSEX5020, DUKHCONP1AZ1STRF2060, DUKHCONP1AZ1MSEX5000, DUKHCONP1AZ1ARRF3600, DUKHCONP1AZ1WEEX5030, DUKHCONP1AZ1STRF2060, DUKHCONP1AZ1ARRF3600 | 0 | 0 | ROOF
DUKHCONP1AZ1STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2013-10-02 | 2013-10-27 | 2013-10-02 | 2013-10-27 | 9 | No | DUKHCONP1AZ1STRF2045, DUKHCONP1AZ1STRF2045 | DUKHCONP1AZ1STRF2055, DUKHCONP1AZ1STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.10 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2013-09-10 | 2014-03-20 | 2013-09-10 | 2014-03-20 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.10 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2013-09-10 | 2014-03-20 | 2013-09-10 | 2014-03-20 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.10 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-09-10 | 2014-02-24 | 2013-09-10 | 2014-02-24 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ1ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2013-12-29 | 2014-01-14 | 2013-12-29 | 2014-01-14 | 21 | No | DUKHPROGEN00PRDV3460, DUKHCONP1AMKARGF3070, DUKHCONP1AZ1ARGF3065, DUKHPROGEN00PRDV3450, DUKHPROGEN00PRDV3440, DUKHCONP1AZ1ARGF3065 | DUKHCONP1AZ1ARGF3080, DUKHCONP1AZ1ARGF3075, DUKHCONP1AZ1ARGF3080, DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2013-11-28 | 2013-12-28 | 2013-11-28 | 2013-12-28 | 21 | No | DUKHCONP1AZ1ACGF4600, DUKHCONP1AZ1ARGF3045, DUKHPROGEN00PRDV3310, DUKHCONP1AZ1ARGF3045, DUKHCONP1AMKARGF3055, DUKHCONP1AZ1ACGF4600 | DUKHCONP1AZ1ELGF4015, DUKHCONP1AZ1ACGF4605, DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ1ELGF4015, DUKHCONP1AZ1ELGF4020, DUKHCONP1AZ1ELGF4020, DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ1ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-01-05 | 2014-01-27 | 2014-01-05 | 2014-01-27 | 31 | No | DUKHCONP1AZ1ARGF3070, DUKHPROGEN00PRDV3470, DUKHCONP1AZ1ARGF3070, DUKHCONP1AMKARGF3080 | DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ2ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3000 | Block work | 25 | 25 | 0% | 2013-09-10 | 2013-10-08 | 2013-09-10 | 2013-10-08 | 18 | No | DUKHCONP1AZ1STGF2015, DUKHCONP1AMKARGF3000, DUKHPROGEN00PRDV3010, DUKHCONP1AZ1STGF2015 | DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ1PLGF4310, DUKHCONP1AZ1ELGF4000, DUKHCONP1AZ1PLGF4305, DUKHCONP1AZ1ELGF4000, DUKHCONP1AZ1PLGF4305, DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ1PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-01-04 | 2014-01-26 | 2014-01-04 | 2014-01-26 | 21 | No | DUKHCONP1AZ1ARGF3070, DUKHPROGEN00PRDV3550, DUKHCONP1AMKARGF3075, DUKHPROGEN00PRDV3560, DUKHCONP1AZ1ARGF3070 | DUKHCONP1AZ1ARGF3090, DUKHCONP1AZ1ARGF3090, DUKHCONP1AZ1ARGF3085, DUKHCONP1AZ1ARGF3085, DUKHCONP1AZ2ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-10-28 | 2013-11-25 | 2013-10-28 | 2013-11-25 | 18 | No | DUKHCONP1AZ1ARGF3015, DUKHCONP1AZ1PLGF4305, DUKHCONP1AZ1PLGF4305, DUKHCONP1AMKARGF3020, DUKHPROGEN00PRDV3120, DUKHCONP1AZ1PLGF4310, DUKHCONP1AZ1ARGF3015, DUKHCONP1AZ1PLGF4310 | DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ1ARGF3025, DUKHCONP1AZ1ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2013-11-30 | 2013-12-16 | 2013-11-30 | 2013-12-16 | 21 | No | DUKHCONP1AZ1ARGF3010, DUKHCONP1AZ1ARGF3035, DUKHPROGEN00PRDV3090, DUKHCONP1AMKARGF3040, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3025, DUKHCONP1AZ1ARGF3010, DUKHCONP1AZ1ARGF3025 | DUKHCONP1AZ1ARGF3050, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 21 | No | DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ARGF3090, DUKHCONP1AZ1ACGF4610, DUKHCONP1AZ1ARGF3030, DUKHCONP1AZ1ARGF3080, DUKHCONP1AZ1ARGF3070, DUKHCONP1AZ1ARGF3085, DUKHCONP1AZ1ACGF4610, DUKHCONP1AZ1ARGF3030, DUKHCONP1AZ1ARGF3040, DUKHCONP1AZ1ARGF3040, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3070, DUKHCONP1AZ1ARGF3080, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ARGF3090, DUKHCONP1AZ1ARGF3085, DUKHCONP1AMKARGF3095 | DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2013-11-20 | 2013-12-12 | 2013-11-20 | 2013-12-12 | 18 | No | DUKHCONP1AZ1ELGF4010, DUKHCONP1AZ1ELGF4010, DUKHCONP1AZ1ARGF3025, DUKHCONP1AMKARGF3045, DUKHCONP1AZ1ARGF3030, DUKHCONP1AZ1ARGF3025, DUKHCONP1AZ1ARGF3030 | DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ1ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-10-10 | 2013-11-05 | 2013-10-10 | 2013-11-05 | 26 | No | DUKHCONP1AMKARGF3010, DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ1ARGF3005 | DUKHCONP1AZ1ARGF3040, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3025, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3040, DUKHCONP1AZ1ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2013-12-08 | 2013-12-31 | 2013-12-08 | 2013-12-31 | 21 | No | DUKHCONP1AZ1ARGF3025, DUKHCONP1AZ1ARGF3040, DUKHCONP1AMKARGF3050, DUKHCONP1AZ1ARGF3025, DUKHPROGEN00PRDV3480, DUKHCONP1AZ1ARGF3040 | DUKHCONP1AZ1ARGF3065, DUKHCONP1AZ1ARGF3085, DUKHCONP1AZ1ARGF3085, DUKHCONP1AZ1ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2013-12-02 | 2013-12-31 | 2013-12-02 | 2013-12-31 | 18 | No | DUKHCONP1AZ1ACGF4600, DUKHCONP1AMKARGF3060, DUKHCONP1AZ1ARGF3045, DUKHPROGEN00PRDV3300, DUKHCONP1AZ1ACGF4600, DUKHCONP1AZ1ARGF3045 | DUKHCONP1AZ1ELGF4020, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ1ACGF4605, DUKHCONP1AZ1ELGF4030, DUKHCONP1AZ1ELGF4015, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ1ELGF4015, DUKHCONP1AZ1PLGF4320, DUKHCONP1AZ1ELGF4020, DUKHCONP1AZ1PLGF4320, DUKHCONP1AZ1ACGF4605, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-01-16 | 2014-02-02 | 2014-01-16 | 2014-02-02 | 21 | No | DUKHCONP1AZ1ARGF3075, DUKHCONP1AZ1ARGF3075, DUKHCONP1AMKARGF3090 | DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-10-21 | 2013-11-18 | 2013-10-21 | 2013-11-18 | 32 | No | DUKHCONP1AMKARGF3030, DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ1ARGF3005, DUKHPROGEN00PRDV3320 | DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ2ARGF3030, DUKHCONP1AZ1ARGF3045, DUKHCONP1AZ1ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-10-02 | 2013-11-02 | 2013-10-02 | 2013-11-02 | 18 | No | DUKHCONP1AZ1ARGF3000, DUKHPROGEN00PRDV3040, DUKHCONP1AZ1ELGF4000, DUKHCONP1AZ1ELGF4000, DUKHCONP1AZ1PLGF4305, DUKHCONP1AZ1PLGF4305, DUKHCONP1AMKARGF3005, DUKHCONP1AZ1ARGF3000 | DUKHCONP1AZ1ARGF3030, DUKHCONP1AZ1ARGF3015, DUKHCONP1AZ1ACGF4600, DUKHCONP1AZ1ARGF3030, DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ1ARGF3015, DUKHCONP1AZ1ARGF3010, DUKHCONP1AZ1ACGF4600, DUKHCONP1AZ1ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-11-03 | 2013-12-01 | 2013-11-03 | 2013-12-01 | 18 | No | DUKHPROGEN00PRDV3130, DUKHCONP1AMKARGF3025, DUKHCONP1AZ1ARGF3020, DUKHCONP1AZ1ARGF3010, DUKHCONP1AZ1ARGF3020, DUKHCONP1AZ1ARGF3010 | DUKHCONP1AZ1ARGF3050, DUKHCONP1AZ1ARGF3050, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ1ARGF3045, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3045, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3040, DUKHCONP1AZ1ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-01-12 | 2014-02-03 | 2014-01-12 | 2014-02-03 | 26 | No | DUKHPROGEN00PRDV3570, DUKHCONP1AMKARGF3085, DUKHCONP1AZ1ARGF3075, DUKHCONP1AZ1ARGF3050, DUKHCONP1AZ1ARGF3050, DUKHCONP1AZ1ARGF3075 | DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2013-11-23 | 2013-12-09 | 2013-11-23 | 2013-12-09 | 23 | No | DUKHCONP1AZ1ARGF3010, DUKHCONP1AZ1ARGF3025, DUKHCONP1AZ1ARGF3010, DUKHPROGEN00PRDV3100, DUKHCONP1AMKARGF3035, DUKHCONP1AZ1ARGF3025 | DUKHCONP1AZ1ARGF3040, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3040, DUKHCONP1AZ1ARGF3065, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-10-22 | 2013-11-07 | 2013-10-22 | 2013-11-07 | 18 | No | DUKHCONP1AZ1ARGF3005, DUKHCONP1AMKARGF3015, DUKHCONP1AZ1ARGF3005 | DUKHCONP1AZ1ARGF3020, DUKHCONP1AZ2ARGF3015, DUKHCONP1AZ1ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2013-12-23 | 2014-01-08 | 2013-12-23 | 2014-01-08 | 21 | No | DUKHCONP1AMKARGF3065, DUKHCONP1AZ1ARGF3050, DUKHPROGEN00PRDV3490, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3035, DUKHCONP1AZ1ARGF3050 | DUKHCONP1AZ1PLGF4315, DUKHCONP1AZ2ARGF3065, DUKHCONP1AZ1ARGF3070, DUKHCONP1AZ1PLGF4315, DUKHCONP1AZ1ARGF3070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.10 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2013-10-24 | 2014-03-20 | 2013-10-24 | 2014-03-20 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ1ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-01-26 | 2014-02-18 | 2014-01-26 | 2014-02-18 | 0 | Yes | DUKHCONP1AMKARFF3370, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ARFF3365 | DUKHCONP1AZ1ARFF3375, DUKHCONP1AZ2ARFF3370, DUKHCONP1AZ1ARFF3380, DUKHCONP1AZ1ARFF3380, DUKHCONP1AZ1ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-02-02 | 2014-02-25 | 2014-02-02 | 2014-02-25 | 5 | No | DUKHCONP1AZ1ARFF3370, DUKHCONP1AMKARFF3380, DUKHCONP1AZ1ARFF3370 | DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3300 | Block work | 25 | 25 | 0% | 2013-10-24 | 2013-11-21 | 2013-10-24 | 2013-11-21 | 0 | Yes | DUKHCONP1AZ1STFF2020, DUKHCONP1AMKARFF3300, DUKHCONP1AZ1STFF2020, DUKHCONP1AZ1STFF2035, DUKHCONP1AZ1STFF2035 | DUKHCONP1AZ1PLFF4325, DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ1ELFF4035, DUKHCONP1AZ1PLFF4325, DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1ELFF4035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 0 | Yes | DUKHCONP1AMKARFF3375, DUKHCONP1AZ1ARFF3370, DUKHCONP1AZ1ARFF3370 | DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ1ARFF3385, DUKHCONP1AZ1ARFF3390, DUKHCONP1AZ1ARFF3385, DUKHCONP1AZ1ARFF3390, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 0 | Yes | DUKHCONP1AZ1PLFF4325, DUKHCONP1AZ1ARFF3315, DUKHCONP1AMKARFF3320, DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ1ARFF3315, DUKHCONP1AZ1PLFF4325, DUKHCONP1AZ1PLFF4330 | DUKHCONP1AZ1ARFF3325, DUKHCONP1AZ2ARFF3320, DUKHCONP1AZ1ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 0 | Yes | DUKHCONP1AZ1ARFF3335, DUKHCONP1AZ1ARFF3380, DUKHCONP1AZ1ARFF3385, DUKHCONP1AZ1ARRF3620, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ARFF3330, DUKHCONP1AZ1ARFF3335, DUKHCONP1AZ1ARFF3380, DUKHCONP1AZ1ARFF3385, DUKHCONP1AZ1ARFF3350, DUKHCONP1AZ1ARFF3350, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ACFF4625, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ARFF3375, DUKHCONP1AZ1ACFF4625, DUKHCONP1AMKARFF3395, DUKHCONP1AZ1ARFF3390, DUKHCONP1AZ1ARFF3330, DUKHCONP1AZ1ARFF3375, DUKHCONP1AZ1ARFF3390 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ1ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-01-04 | 2014-01-26 | 2014-01-04 | 2014-01-26 | 0 | Yes | DUKHCONP1AZ1ARFF3330, DUKHCONP1AZ1ELFF4045, DUKHCONP1AZ1ELFF4045, DUKHCONP1AZ1ARFF3325, DUKHCONP1AZ1ARFF3330, DUKHCONP1AZ1ARFF3325, DUKHCONP1AMKARFF3345 | DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ2ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3310 | Flooring screed | 21 | 21 | 0% | 2013-11-25 | 2013-12-19 | 2013-11-25 | 2013-12-19 | 12 | No | DUKHCONP1AMKARFF3310, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1ARFF3305 | DUKHCONP1AZ1ARFF3335, DUKHCONP1AZ1ARFF3325, DUKHCONP1AZ1ARFF3325, DUKHCONP1AZ1ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-01-12 | 2014-02-03 | 2014-01-12 | 2014-02-03 | 2 | No | DUKHCONP1AMKARFF3350, DUKHCONP1AZ1ARFF3325, DUKHCONP1AZ1ARFF3325 | DUKHCONP1AZ1ARFF3385, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3385, DUKHCONP1AZ1ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 0 | Yes | DUKHCONP1AZ1ACFF4615, DUKHCONP1AMKARFF3360, DUKHCONP1AZ1ACFF4615, DUKHCONP1AZ1ARFF3345, DUKHCONP1AZ1ARFF3345 | DUKHCONP1AZ1ACFF4620, DUKHCONP1AZ1ELFF4060, DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ELFF4050, DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ1ELFF4060, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ELFF4055, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ELFF4055, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ELFF4050, DUKHCONP1AZ1PLFF4340, DUKHCONP1AZ1ACFF4620, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ1PLFF4340 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3385 | Handrail & S.S.Balustrade | 20 | 20 | 0% | 2014-02-15 | 2014-03-09 | 2014-02-15 | 2014-03-09 | 0 | Yes | DUKHCONP1AZ1ARFF3350, DUKHCONP1AMKARFF3385, DUKHCONP1AZ1ARFF3375, DUKHCONP1AZ1ARFF3375, DUKHCONP1AZ1ARFF3350 | DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-02-15 | 2014-03-09 | 2014-02-15 | 2014-03-09 | 1 | No | DUKHCONP1AZ1ARFF3375, DUKHCONP1AMKARFF3390, DUKHCONP1AZ1ARFF3375 | DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3330 | Paint First coat | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 14 | No | DUKHCONP1AMKARFF3330, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1ARFF3305 | DUKHCONP1AZ1ARFF3345, DUKHCONP1AZ1ARFF3345, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3305 | Plastering work | 25 | 25 | 0% | 2013-11-17 | 2013-12-15 | 2013-11-17 | 2013-12-15 | 0 | Yes | DUKHCONP1AZ1PLFF4325, DUKHCONP1AZ1ELFF4035, DUKHCONP1AMKARFF3305, DUKHCONP1AZ1PLFF4325, DUKHCONP1AZ1ARFF3300, DUKHCONP1AZ1ELFF4035, DUKHCONP1AZ1ARFF3300 | DUKHCONP1AZ1ACFF4615, DUKHCONP1AZ1AREL3665, DUKHCONP1AZ1ARFF3330, DUKHCONP1AZ1ARFF3310, DUKHCONP1AZ1AREL3665, DUKHCONP1AZ1ARFF3310, DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ1ARFF3330, DUKHCONP1AZ1ACFF4615, DUKHCONP1AZ1ARFF3315, DUKHCONP1AZ1ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 0 | Yes | DUKHCONP1AZ1ARFF3310, DUKHCONP1AZ1ARFF3310, DUKHCONP1AZ1ARFF3320, DUKHCONP1AZ1ARFF3320, DUKHCONP1AMKARFF3325 | DUKHCONP1AZ1ARFF3345, DUKHCONP1AZ1ARFF3345, DUKHCONP1AZ1ARFF3350, DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ1ARFF3350, DUKHCONP1AZ1ARFF3335, DUKHCONP1AZ1ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-01-08 | 2014-01-25 | 2014-01-08 | 2014-01-25 | 8 | No | DUKHCONP1AZ1ARFF3310, DUKHCONP1AMKARFF3335, DUKHCONP1AZ1ARFF3310, DUKHCONP1AZ1ARFF3325, DUKHCONP1AZ1ARFF3325 | DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2013-12-07 | 2013-12-24 | 2013-12-07 | 2013-12-24 | 0 | Yes | DUKHCONP1AMKARFF3315, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1ARFF3305 | DUKHCONP1AZ1ARFF3320, DUKHCONP1AZ1ARFF3320, DUKHCONP1AZ2ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-01-26 | 2014-02-12 | 2014-01-26 | 2014-02-12 | 0 | Yes | DUKHCONP1AZ1ARFF3360, DUKHCONP1AMKARFF3365, DUKHCONP1AZ1ARFF3350, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ARFF3335, DUKHCONP1AZ1ARFF3335, DUKHCONP1AZ1ARFF3350 | DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1PLFF4335, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ1PLFF4335, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3370, DUKHCONP1AZ1ARFF3370 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.10 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2013-11-12 | 2014-01-16 | 2013-11-12 | 2014-01-16 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ1ARRF3600 | Block work | 20 | 20 | 0% | 2013-11-12 | 2013-12-04 | 2013-11-12 | 2013-12-04 | 21 | No | DUKHCONP1AZ1STRF2055, DUKHCONP1AMKARRF3600, DUKHCONP1AZ1STRF2055 | DUKHCONP1AZ1ARRF3605, DUKHCONP1AZ2ARRF3600, DUKHCONP1AZ1ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2013-12-31 | 2014-01-16 | 2013-12-31 | 2014-01-16 | 45 | No | DUKHPROGEN00PRDV3420, DUKHCONP1AMKARRF3620, DUKHCONP1AZ1ARRF3695, DUKHCONP1AZ1ARRF3695 | DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3610 | Flooring screed | 15 | 15 | 0% | 2013-12-04 | 2013-12-22 | 2013-12-04 | 2013-12-22 | 45 | No | DUKHCONP1AZ1ARRF3605, DUKHCONP1AZ1ARRF3605, DUKHCONP1AMKARRF3610 | DUKHCONP1AZ1ARRF3695, DUKHCONP1AZ1ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2013-12-12 | 2014-01-05 | 2013-12-12 | 2014-01-05 | 45 | No | DUKHCONP1AZ1ARRF3610, DUKHCONP1AMKARRF3695, DUKHCONP1AZ1ARRF3610 | DUKHCONP1AZ1AREL3680, DUKHCONP1AZ1ARRF3620, DUKHCONP1AZ1AREL3680, DUKHCONP1AZ1ARRF3620 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3605 | Plastering work | 20 | 20 | 0% | 2013-11-20 | 2013-12-12 | 2013-11-20 | 2013-12-12 | 21 | No | DUKHCONP1AZ1ARRF3600, DUKHCONP1AZ1ARRF3600, DUKHCONP1AMKARRF3605 | DUKHCONP1AZ1ARRF3610, DUKHCONP1AZ1PLRF4345, DUKHCONP1AZ1PLRF4345, DUKHCONP1AZ1ARRF3630, DUKHCONP1AZ1ARRF3610, DUKHCONP1AZ1AREL3665 | 0 | 0 | ROOF
DHBL.K30.L15.10 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2013-11-30 | 2014-02-18 | 2013-11-30 | 2014-02-18 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.10 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2013-12-14 | 2014-02-18 | 2013-12-14 | 2014-02-18 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ1ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 21 | No | DUKHCONP1AMKARRF3650, DUKHCONP1AZ1ARRF3645, DUKHPROGEN00PRDV3410, DUKHCONP1AZ1ARRF3645 | DUKHCONP1AZ1ARRF3655, DUKHCONP1AZ1ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-02-01 | 2014-02-18 | 2014-02-01 | 2014-02-18 | 26 | No | DUKHCONP1AZ1ARRF3655, DUKHCONP1AMKARRF3660, DUKHCONP1AZ1ARRF3655, DUKHPROGEN00PRDV3400 | DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2013-12-23 | 2014-01-20 | 2013-12-23 | 2014-01-20 | 21 | No | DUKHCONP1AZ1ARRF3635, DUKHCONP1AZ1ARRF3635, DUKHCONP1AMKARRF3640 | DUKHCONP1AZ1ARRF3645, DUKHCONP1AZ1ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-01-20 | 2014-02-12 | 2014-01-20 | 2014-02-12 | 21 | No | DUKHPROGEN00PRDV3510, DUKHCONP1AMKARRF3655, DUKHCONP1AZ1ARRF3645, DUKHCONP1AZ1ARRF3650, DUKHCONP1AZ1ARRF3650, DUKHCONP1AZ1ARRF3645 | DUKHCONP1AZ1ARRF3660, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ARRF3660, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ1PLRF4355, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 21 | No | DUKHPROGEN00PRDV3050, DUKHCONP1AMKARRF3635, DUKHCONP1AZ1ARRF3630, DUKHCONP1AZ1ARRF3630 | DUKHCONP1AZ1ARRF3640, DUKHCONP1AZ1ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 21 | No | DUKHCONP1AZ1STRF2065, DUKHCONP1AZ1STRF2060, DUKHCONP1AZ1STRF2060, DUKHCONP1AZ1ARRF3605, DUKHCONP1AZ1STRF2065, DUKHCONP1AMKARRF3630 | DUKHCONP1AZ1ARRF3635, DUKHCONP1AZ2ARRF3630, DUKHCONP1AZ1ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ1ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 21 | No | DUKHCONP1AMKARRF3645, DUKHCONP1AZ1ARRF3640, DUKHCONP1AZ1ARRF3640 | DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1ELRF4070, DUKHCONP1AZ1ARRF3655, DUKHCONP1AZ1ARRF3650, DUKHCONP1AZ1ARRF3650, DUKHCONP1AZ1ELRF4070, DUKHCONP1AZ1ARRF3655, DUKHCONP1AZ1PLRF4350 | 0 | 0 | ROOF
DHBL.K30.L15.10 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2013-11-30 | 2014-01-21 | 2013-11-30 | 2014-01-21 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ1AREL3680 | External Painting | 20 | 20 | 0% | 2013-12-30 | 2014-01-21 | 2013-12-30 | 2014-01-21 | 49 | No | DUKHCONP1AZ1ARRF3695, DUKHCONP1AZ1AREL3670, DUKHCONP1AZ1ARRF3695, DUKHCONP1AZ1AREL3670, DUKHCONP1AMKAREL3680 | DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ2AREL3680, DUKHCONP1AZ1ELTC8010 | 0 | 0 | ELEVATION
DUKHCONP1AZ1AREL3665 | External Plastering | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 47 | No | DUKHCONP1AZ1STRF2065, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1STRF2065, DUKHCONP1AZ1ARFF3305, DUKHCONP1AMKAREL3665, DUKHCONP1AZ1ARRF3605 | DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1AREL3670, DUKHCONP1AZ1AREL3670, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ1PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP1AZ1AREL3670 | External stone cladding works | 20 | 20 | 0% | 2013-12-17 | 2014-01-09 | 2013-12-17 | 2014-01-09 | 49 | No | DUKHPROGEN00PRDV3110, DUKHCONP1AZ1AREL3665, DUKHCONP1AZ1AREL3665, DUKHCONP1AMKAREL3670 | DUKHCONP1AZ2AREL3670, DUKHCONP1AZ1AREL3680, DUKHCONP1AZ1AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L15.10 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-06-03 | 2014-03-19 | 2013-06-03 | 2014-03-19 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.10 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2013-09-16 | 2014-03-19 | 2013-09-16 | 2014-03-19 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.10 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-09-16 | 2014-01-26 | 2013-09-16 | 2014-01-26 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ1ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-09-30 | 2013-10-24 | 2013-09-30 | 2013-10-24 | 43 | No | DUKHCONP1AMKELGF4005, DUKHCONP1AZ1ELGF4000, DUKHCONP1AZ1ELGF4000, DUKHPROGEN00PRDV3180 | DUKHCONP1AZ1ELGF4010, DUKHCONP1AZ2ELGF4005, DUKHCONP1AZ1ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-09-16 | 2013-10-14 | 2013-09-16 | 2013-10-14 | 27 | No | DUKHCONP1AZ1ARGF3000, DUKHCONP1AMKELGF4000, DUKHCONP1AZ1ARGF3000 | DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ1ELGF4005, DUKHCONP1AZ1ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 30 | No | DUKHPROGEN00PRDV3210, DUKHCONP1AZ1ARGF3055, DUKHPROGEN00PRDV3360, DUKHCONP1AZ1ARGF3060, DUKHPROGEN00PRDV3260, DUKHCONP1AZ1ARGF3060, DUKHPROGEN00PRDV3380, DUKHCONP1AZ1ARGF3055, DUKHCONP1AMKELGF4015, DUKHPROGEN00PRDV3370 | DUKHCONP1AZ1ELFF4055, DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2013-12-16 | 2014-01-08 | 2013-12-16 | 2014-01-08 | 18 | No | DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ELGF4010, DUKHPROGEN00PRDV3170, DUKHCONP1AMKELGF4020, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ELGF4010, DUKHCONP1AZ1ARGF3055 | DUKHCONP1AZ1ELGF4030, DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ1ELGF4030, DUKHCONP1AZ1ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 25 | No | DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ1ARGF3060, DUKHPROGEN00PRDV3190, DUKHCONP1AZ1ELGF4020, DUKHCONP1AZ1ELGF4020, DUKHCONP1AMKELGF4025, DUKHCONP1AZ1ARGF3055 | DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2013-12-29 | 2014-01-20 | 2013-12-29 | 2014-01-20 | 18 | No | DUKHCONP1AZ1ELGF4020, DUKHPROGEN00PRDV3270, DUKHPROGEN00PRDV3280, DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ELGF4020, DUKHCONP1AZ1ARGF3060, DUKHCONP1AMKELGF4030 | DUKHCONP1AZ1ELFF4050, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-10-08 | 2013-11-07 | 2013-10-08 | 2013-11-07 | 43 | No | DUKHCONP1AMKELGF4010, DUKHCONP1AZ1ELGF4005, DUKHCONP1AZ1ELGF4005 | DUKHCONP1AZ1ARGF3045, DUKHCONP1AZ1ELGF4020, DUKHCONP1AZ1ARGF3045, DUKHCONP1AZ1ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.10 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2013-10-30 | 2014-03-02 | 2013-10-30 | 2014-03-02 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ1ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-11-13 | 2013-12-05 | 2013-11-13 | 2013-12-05 | 26 | No | DUKHCONP1AMKELFF4040, DUKHCONP1AZ1ELFF4035, DUKHCONP1AZ1ELFF4035 | DUKHCONP1AZ1ELFF4045, DUKHCONP1AZ1ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-10-30 | 2013-11-27 | 2013-10-30 | 2013-11-27 | 10 | No | DUKHCONP1AMKELFF4035, DUKHCONP1AZ1ARFF3300, DUKHCONP1AZ1ARFF3300 | DUKHCONP1AZ1ELFF4040, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1ELFF4040, DUKHCONP1AZ1ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 2 | No | DUKHCONP1AZ1ELGF4015, DUKHCONP1AMKELFF4055, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ELGF4015 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ2ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-01-26 | 2014-02-18 | 2014-01-26 | 2014-02-18 | 1 | No | DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ELFF4045, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ELFF4045, DUKHCONP1AMKELFF4060 | DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ2ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 1 | No | DUKHCONP1AZ1ARFF3360, DUKHCONP1AMKELFF4065, DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ELFF4060, DUKHCONP1AZ1ELFF4060, DUKHCONP1AZ1ELGF4025 | DUKHCONP1AZ1ELRF4070, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ1ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 12 | No | DUKHCONP1AZ1ELGF4030, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1MSEX5010, DUKHCONP1AMKELFF4050, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ELGF4030 | DUKHCONP1AZ1ELRF4070, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 26 | No | DUKHCONP1AMKELFF4045, DUKHCONP1AZ1ELFF4040, DUKHCONP1AZ1ELFF4040 | DUKHCONP1AZ1ELRF4070, DUKHCONP1AZ1ARFF3345, DUKHCONP1AZ1ELRF4070, DUKHCONP1AZ1ARFF3345, DUKHCONP1AZ1ELFF4060, DUKHCONP1AZ1ELFF4060, DUKHCONP1AZ2ELFF4045 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.10 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-02-16 | 2014-03-19 | 2014-02-16 | 2014-03-19 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ1ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-02-16 | 2014-03-08 | 2014-02-16 | 2014-03-08 | 1 | No | DUKHCONP1AZ1ELFF4045, DUKHCONP1AZ1ELFF4045, DUKHCONP1AZ1ARRF3645, DUKHCONP1AMKELRF4070, DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ1ELFF4050, DUKHPROGEN00PRDV3200, DUKHCONP1AZ1ARRF3645, DUKHCONP1AZ1ELFF4050, DUKHCONP1AZ1ELFF4065 | DUKHCONP1AZ1ELRF4075, DUKHCONP1AZ1ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ1ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-02-22 | 2014-03-19 | 2014-02-22 | 2014-03-19 | 1 | No | DUKHPROGEN00PRDV3290, DUKHCONP1AZ1ELRF4070, DUKHCONP1AZ1ELRF4070, DUKHCONP1AMKELRF4075 | DUKHCONP1AZ1ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.10 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-06-03 | 2014-03-19 | 2013-06-03 | 2014-03-19 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.10 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-06-03 | 2014-01-26 | 2013-06-03 | 2014-01-26 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-06-03 | 2013-06-20 | 2013-06-03 | 2013-06-20 | 0 | Yes | DUKHCONP1AZ1STUG1040, DUKHPROGEN00PRDV3070, DUKHPROGEN00PRDV3060, DUKHCONP1AZ1STUG1040 | DUKHCONP1AZ1STUG1045, DUKHCONP1AZ1STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-09-26 | 2013-10-16 | 2013-09-26 | 2013-10-16 | 39 | No | DUKHCONP1AZ1PLGF4305, DUKHCONP1AZ1ARGF3000, DUKHCONP1AMKPLGF4310, DUKHCONP1AZ1PLGF4305, DUKHCONP1AZ1ARGF3000 | DUKHCONP1AZ1PLGF4315, DUKHCONP1AZ1MSEX5000, DUKHCONP1AZ1PLGF4315, DUKHCONP1AZ1MSEX5000, DUKHCONP1AZ1ARGF3020, DUKHCONP1AZ1ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-09-26 | 2013-10-16 | 2013-09-26 | 2013-10-16 | 18 | No | DUKHCONP1AMKPLGF4305, DUKHCONP1AZ1ARGF3000, DUKHCONP1AZ1ARGF3000 | DUKHCONP1AZ1PLGF4310, DUKHCONP1AZ1ARGF3020, DUKHCONP1AZ1ARGF3020, DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ1PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-01-09 | 2014-01-26 | 2014-01-09 | 2014-01-26 | 45 | No | DUKHPROGEN00PRDV3230, DUKHCONP1AZ1PLGF4315, DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1PLGF4315, DUKHCONP1AZ1ARGF3060, DUKHCONP1AMKPLGF4320 | DUKHCONP1AZ2PLGF4320, DUKHCONP1AZ1PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2013-12-29 | 2014-01-20 | 2013-12-29 | 2014-01-20 | 45 | No | DUKHCONP1AZ1ARGF3065, DUKHCONP1AZ1PLGF4310, DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3150, DUKHCONP1AZ1PLGF4310, DUKHCONP1AZ1ARGF3065, DUKHCONP1AMKPLGF4315 | DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ1PLGF4320, DUKHCONP1AZ1PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.10 .20 .15 .15 FIRST FLOORS |  | 95 | 95 | 0% | 2013-11-10 | 2014-03-02 | 2013-11-10 | 2014-03-02 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ1PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2013-11-10 | 2013-11-30 | 2013-11-10 | 2013-11-30 | 22 | No | DUKHCONP1AZ1ARFF3300, DUKHCONP1AZ1PLFF4325, DUKHCONP1AZ1PLFF4325, DUKHCONP1AMKPLFF4330, DUKHCONP1AZ1ARFF3300 | DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1PLFF4335, DUKHCONP1AZ1ARFF3320, DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1PLFF4335, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ1ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-11-10 | 2013-11-30 | 2013-11-10 | 2013-11-30 | 0 | Yes | DUKHPROGEN00PRDV3080, DUKHCONP1AZ1ARFF3300, DUKHCONP1AZ1ARFF3300, DUKHCONP1AMKPLFF4325 | DUKHCONP1AZ1ARFF3320, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ1ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-02-13 | 2014-03-02 | 2014-02-13 | 2014-03-02 | 1 | No | DUKHCONP1AZ1PLFF4335, DUKHCONP1AZ1PLFF4335, DUKHCONP1AMKPLFF4340, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ARFF3360 | DUKHCONP1AZ1PLRF4355, DUKHCONP1AZ2PLFF4340, DUKHCONP1AZ1PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-02-01 | 2014-02-24 | 2014-02-01 | 2014-02-24 | 1 | No | DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ1ARFF3365, DUKHCONP1AMKPLFF4335, DUKHCONP1AZ1PLFF4330 | DUKHCONP1AZ1PLFF4340, DUKHCONP1AZ1PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.10 .20 .15 .20 ROOF |  | 89 | 89 | 0% | 2013-12-04 | 2014-03-19 | 2013-12-04 | 2014-03-19 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ1PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2013-12-04 | 2013-12-22 | 2013-12-04 | 2013-12-22 | 52 | No | DUKHCONP1AMKPLRF4345, DUKHCONP1AZ1ARRF3605, DUKHCONP1AZ1ARRF3605 | DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1PLRF4355, DUKHCONP1AZ1PLRF4355, DUKHCONP1AZ1PLRF4350 | 0 | 0 | ROOF
DUKHCONP1AZ1PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-01-14 | 2014-01-30 | 2014-01-14 | 2014-01-30 | 26 | No | DUKHCONP1AZ1AREL3665, DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ1ARRF3645, DUKHCONP1AZ1PLRF4345, DUKHCONP1AMKPLRF4350, DUKHCONP1AZ1AREL3665, DUKHCONP1AZ1PLRF4345, DUKHCONP1AZ1ARRF3645, DUKHCONP1AZ1PLFF4330 | DUKHCONP1AZ1PLRF4355, DUKHCONP1AZ1WEEX5065, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1PLRF4355, DUKHCONP1AZ1WEEX5065, DUKHCONP1AZ2PLRF4350 | 0 | 0 | ROOF
DUKHCONP1AZ1PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-02-19 | 2014-03-19 | 2014-02-19 | 2014-03-19 | 1 | No | DUKHCONP1AZ1PLFF4340, DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1PLRF4345, DUKHCONP1AZ1PLRF4350, DUKHCONP1AMKPLRF4355, DUKHCONP1AZ1ARRF3655, DUKHCONP1AZ1PLRF4345, DUKHCONP1AZ1ARRF3655, DUKHCONP1AZ1PLFF4340 | DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ1PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L15.10 .20 .20 AC WORKS |  | 126 | 126 | 0% | 2013-10-16 | 2014-03-16 | 2013-10-16 | 2014-03-16 | 4 |  |  |  | 0 | 0
DHBL.K30.L15.10 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-10-16 | 2014-01-23 | 2013-10-16 | 2014-01-23 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ1ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-01-01 | 2014-01-23 | 2014-01-01 | 2014-01-23 | 32 | No | DUKHPROGEN00PRDV3240, DUKHCONP1AMKACGF4610, DUKHCONP1AZ1ACGF4605, DUKHCONP1AZ1ACGF4605 | DUKHCONP1AZ2ACGF4610, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ACRF4635, DUKHCONP1AZ1ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 32 | No | DUKHPROGEN00PRDV3340, DUKHCONP1AZ1ACGF4600, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ1ARGF3060, DUKHPROGEN00PRDV3530, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ACGF4600, DUKHCONP1AMKACGF4605 | DUKHCONP1AZ2ACGF4605, DUKHCONP1AZ1ACGF4610, DUKHCONP1AZ1ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ1ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-10-16 | 2013-11-10 | 2013-10-16 | 2013-11-10 | 49 | No | DUKHCONP1AZ1ARGF3005, DUKHPROGEN00PRDV3160, DUKHCONP1AZ1ARGF3005, DUKHCONP1AMKACGF4600 | DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ACGF4605, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ1ARGF3055, DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ1ACGF4605 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.10 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2013-12-01 | 2014-03-04 | 2013-12-01 | 2014-03-04 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ1ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-02-09 | 2014-03-04 | 2014-02-09 | 2014-03-04 | 3 | No | DUKHCONP1AMKACFF4625, DUKHCONP1AZ1ACFF4620, DUKHCONP1AZ1ACFF4620 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ2ACFF4625, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ACRF4635, DUKHCONP1AZ1ACRF4635 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 3 | No | DUKHCONP1AZ1ACFF4615, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ACFF4615, DUKHCONP1AMKACFF4620, DUKHCONP1AZ1ARFF3360 | DUKHCONP1AZ1ACFF4625, DUKHCONP1AZ2ACFF4620, DUKHCONP1AZ1ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ1ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2013-12-01 | 2013-12-24 | 2013-12-01 | 2013-12-24 | 27 | No | DUKHCONP1AMKACFF4615, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ1ARFF3305 | DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ACFF4620, DUKHCONP1AZ1ACFF4620, DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ1ARFF3360, DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ1ACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.10 .20 .20 .20 ROOF |  | 60 | 60 | 0% | 2014-01-05 | 2014-03-16 | 2014-01-05 | 2014-03-16 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ1ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 4 | No | DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ1ACGF4610, DUKHCONP1AMKACRF4635, DUKHCONP1AZ1ACGF4610, DUKHCONP1AZ1ACFF4625, DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ1ACFF4625 | DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ2ACRF4635 | 0 | 0 | ROOF
DUKHCONP1AZ1ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 34 | No | DUKHCONP1AZ1ARRF3645, DUKHCONP1AZ1ARRF3645, DUKHCONP1AZ1ACGF4600, DUKHCONP1AZ1ACFF4615, DUKHCONP1AMKACRF4630, DUKHCONP1AZ1ACFF4615, DUKHCONP1AZ1ACGF4600 | DUKHCONP1AZ1ACRF4635, DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ1ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.10 .25 EXTERNAL WORKS |  | 104 | 104 | 0% | 2013-12-02 | 2014-04-03 | 2013-12-02 | 2014-04-03 | 103 |  |  |  | 0 | 0
DHBL.K30.L15.10 .25 .10 MISCELLANEOUS |  | 104 | 104 | 0% | 2013-12-02 | 2014-04-03 | 2013-12-02 | 2014-04-03 | 103 |  |  |  | 0 | 0
DUKHCONP1AZ1MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 103 | No | DUKHPROGEN00PRDV3430, DUKHCONI1AZ1BWGL5325 | DUKHCONP1AZ2MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ1MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-12-16 | 2014-01-14 | 2013-12-16 | 2014-01-14 | 13 | No | DUKHCONP1AZ1MSEX5000, DUKHCONP1AMKMSEX5005, DUKHCONP1AZ1MSEX5000 | DUKHCONP1AZ1MSEX5015, DUKHCONP1AZ1MSEX5010, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ1MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2013-12-16 | 2014-01-14 | 2013-12-16 | 2014-01-14 | 16 | No | DUKHCONP1AZ1STRF2055, DUKHCONP1AMKMSEX5020, DUKHCONP1AZ1STRF2055 | DUKHCONP1AZ1HDEX5090, DUKHCONP1AZ1HDEX5090, DUKHCONP1AZ2MSEX5020, DUKHCONP1AZ1MSEX5025, DUKHCONP1AZ1MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ1MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-01-06 | 2014-01-28 | 2014-01-06 | 2014-01-28 | 33 | No | DUKHCONP1AZ1MSEX5005, DUKHCONP1AMKMSEX5015, DUKHCONP1AZ1MSEX5005 | DUKHCONP1AZ1WEEX5065, DUKHCONP1AZ1WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ1MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-12-02 | 2013-12-31 | 2013-12-02 | 2013-12-31 | 13 | No | DUKHCONP1AZ1PLGF4310, DUKHCONP1AZ1STRF2055, DUKHCONP1AZ1STRF2055, DUKHCONP1AMKMSEX5000, DUKHCONP1AZ1PLGF4310, DUKHPROGEN00PRDV3590 | DUKHCONP1AZ1MSEX5005, DUKHCONP1AZ1MSEX5005, DUKHMOBP1APS00002030 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ1MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-01-06 | 2014-01-28 | 2014-01-06 | 2014-01-28 | 22 | No | DUKHCONP1AZ1MSEX5020, DUKHCONP1AZ1MSEX5020, DUKHCONP1AMKMSEX5025, DUKHPROGEN00PRDV3580 | DUKHCONP1AZ1WEEX5050, DUKHCONP1AZ1WEEX5060 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ1MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-01-15 | 2014-02-13 | 2014-01-15 | 2014-02-13 | 13 | No | DUKHCONP1AZ1MSEX5005 | DUKHCONP1AZ1ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.10 .25 .15 WATER TANK ENCLOSURE |  | 65 | 65 | 0% | 2013-12-24 | 2014-03-10 | 2013-12-24 | 2014-03-10 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ1WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 11 | No | DUKHCONP1AZ1WEEX5035, DUKHCONP1AZ1WEEX5035, DUKHCONP1AMKWEEX5040 | DUKHCONP1AZ1WEEX5045, DUKHCONP1AZ1WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ1WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-01-01 | 2014-01-29 | 2014-01-01 | 2014-01-29 | 11 | No | DUKHCONP1AZ1WEEX5030, DUKHCONP1AMKWEEX5035, DUKHCONP1AZ1WEEX5030 | DUKHCONP1AZ1WEEX5040, DUKHCONP1AZ1WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ1WEEX5030 | Excavation | 20 | 20 | 0% | 2013-12-24 | 2014-01-15 | 2013-12-24 | 2014-01-15 | 13 | No | DUKHCONP1AZ1STRF2055, DUKHCONP1AMKWEEX5030, DUKHCONP1AZ1STRF2055 | DUKHCONP1AZ1WEEX5035, DUKHCONP1AZ2WEEX5030, DUKHCONP1AZ1WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ1WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-01-18 | 2014-02-16 | 2014-01-18 | 2014-02-16 | 11 | No | DUKHCONP1AZ1WEEX5040, DUKHCONP1AZ1WEEX5040, DUKHCONP1AMKWEEX5045 | DUKHCONP1AZ1WEEX5050, DUKHCONP1AZ1WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ1WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 9 | No | DUKHPROGEN00PRDV3640, DUKHCONP1AZ1WEEX5060, DUKHPROGEN00PRDV3330, DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1MSEX5015, DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3680, DUKHCONP1AZ1PLRF4350, DUKHCONP1AMKWEEX5065, DUKHCONP1AZ1MSEX5015, DUKHCONP1AZ1WEEX5060 | DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ1PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ1WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 11 | No | DUKHCONP1AZ1WEEX5045, DUKHCONP1AMKWEEX5050, DUKHPROGEN00PRDV3500, DUKHCONP1AZ1MSEX5025, DUKHCONP1AZ1WEEX5045 | DUKHCONP1AZ1WEEX5060, DUKHCONP1AZ1WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ1WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 10 | No | DUKHCONP1AMKWEEX5060, DUKHPROGEN00PRDV3610, DUKHCONP1AZ1MSEX5025, DUKHCONP1AZ1WEEX5050, DUKHCONP1AZ1WEEX5050, DUKHPROGEN00PRDV3620 | DUKHCONP1AZ1WEEX5065, DUKHCONP1AZ1WEEX5065, DUKHCONP1AZ2WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.10 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2013-12-31 | 2014-02-10 | 2013-12-31 | 2014-02-10 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ1HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-01-12 | 2014-02-03 | 2014-01-12 | 2014-02-03 | 16 | No | DUKHCONP1AMKHDEX5095, DUKHCONP1AZ1HDEX5090, DUKHCONP1AZ1HDEX5090 | DUKHCONP1AZ1HDEX5100, DUKHCONP1AZ1HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ1HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 16 | No | DUKHPROGEN00PRDV3660, DUKHCONP1AZ1HDEX5095, DUKHCONP1AZ1HDEX5095, DUKHCONP1AMKHDEX5100 | DUKHCONP1AZ1SLEX5105, DUKHCONP1AZ1SLEX5105, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ1HDEX5090 | kerb works | 20 | 20 | 0% | 2013-12-31 | 2014-01-22 | 2013-12-31 | 2014-01-22 | 16 | No | DUKHCONP1AZ1MSEX5020, DUKHCONP1AZ1MSEX5020, DUKHCONP1AMKHDEX5090, DUKHPROGEN00PRDV3600 | DUKHCONP1AZ2HDEX5090, DUKHCONP1AZ1HDEX5095, DUKHCONP1AZ1HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.10 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-01-25 | 2014-03-02 | 2014-01-25 | 2014-03-02 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ1SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 16 | No | DUKHPROGEN00PRDV3790, DUKHCONP1AZ1HDEX5100, DUKHCONP1AMKSLEX5105, DUKHCONP1AZ1HDEX5100 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1SLEX5110, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ1SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ1SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 16 | No | DUKHCONP1AMKSLEX5110, DUKHCONP1AZ1SLEX5105, DUKHCONP1AZ1SLEX5105 | DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ1PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.10 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ1ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONP1AMKELFF4055, DUKHCONP1AMKELRF4075, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ACFF4625, DUKHCONP1AMKHDEX5100, DUKHCONP1AMKACRF4635, DUKHCONP1AMKELGF4025, DUKHCONP1AZ1ACRF4635, DUKHCONP1AMKARRF3655, DUKHCONP1AMKPLRF4355, DUKHCONP1AMKELFF4050, DUKHCONP1AMKELGF4030, DUKHCONP1AMKAREL3680, DUKHCONP1AMKARFF3395, DUKHCONP1AMKMSEX5005, DUKHCONP1AMKACFF4625, DUKHCONP1AZ1AREL3680, DUKHCONP1AMKSLEX5110, DUKHCONP1AMKARRF3620, DUKHCONP1AMKELFF4065, DUKHCONP1AMKELGF4015, DUKHCONP1AZ1ARGF3095, DUKHCONP1AMKWEEX5065, DUKHCONP1AMKSLEX5105, DUKHCONP1AMKARGF3095, DUKHCONP1AMKPLGF4320, DUKHCONP1AMKPLRF4350 | DUKHHANP1AGNACTC9000, DUKHCONP1AZ2ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONP1AZ1SLEX5105, DUKHCONP1AMKACFF4625, DUKHCONP1AZ1ELFF4055, DUKHCONP1AMKMSEX5005, DUKHCONP1AMKWEEX5065, DUKHCONP1AMKARRF3655, DUKHCONP1AMKARRF3620, DUKHCONP1AMKELFF4055, DUKHCONP1AMKELGF4030, DUKHCONP1AMKAREL3680, DUKHCONP1AMKARGF3095, DUKHCONP1AMKELGF4025, DUKHCONP1AZ1ARRF3660, DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ1ELFF4050, DUKHCONP1AMKSLEX5110, DUKHCONP1AMKPLGF4320, DUKHCONP1AMKELGF4015, DUKHCONP1AZ1ARRF3620, DUKHCONP1AZ1ELRF4075, DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ1SLEX5110, DUKHCONP1AMKSLEX5105, DUKHCONP1AMKHDEX5100, DUKHCONP1AMKELFF4065, DUKHCONP1AMKELFF4050, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ1ELGF4015, DUKHCONP1AZ1ELGF4030, DUKHCONP1AZ1HDEX5100, DUKHCONP1AZ1MSEX5005, DUKHCONP1AMKELRF4075, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1ARRF3655, DUKHCONP1AMKPLRF4355, DUKHCONP1AZ1AREL3680, DUKHCONP1AMKARFF3395, DUKHCONP1AMKPLRF4350, DUKHCONP1AMKACRF4635 | DUKHHANP1AGNPLTC9005, DUKHCONP1AZ2ELTC8010, DUKHHANP1AGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONP1AZ1AREL3680, DUKHCONP1AZ1ARFF3395, DUKHCONP1AMKWEEX5065, DUKHCONP1AMKELFF4055, DUKHCONP1AZ1ARRF3655, DUKHCONP1AZ1ARRF3660, DUKHCONP1AMKMSEX5005, DUKHCONP1AMKSLEX5105, DUKHCONP1AMKARRF3655, DUKHCONP1AMKPLGF4320, DUKHCONP1AMKPLRF4350, DUKHCONP1AMKPLRF4355, DUKHCONP1AMKACFF4625, DUKHCONP1AMKELGF4015, DUKHCONP1AMKELGF4030, DUKHCONP1AMKARFF3395, DUKHCONP1AMKACRF4635, DUKHCONP1AMKELFF4065, DUKHCONP1AMKELGF4025, DUKHCONP1AZ1ARRF3620, DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ1WEEX5065, DUKHCONP1AMKARGF3095, DUKHCONP1AMKARRF3620, DUKHCONP1AMKELFF4050, DUKHCONP1AZ1PLGF4320, DUKHCONP1AZ1MSEX5005, DUKHCONP1AZ1SLEX5105, DUKHCONP1AMKAREL3680, DUKHCONP1AZ1PLRF4355, DUKHCONP1AMKSLEX5110, DUKHCONP1AMKELRF4075, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ1HDEX5100, DUKHCONP1AZ1SLEX5110, DUKHCONP1AMKHDEX5100 | DUKHHANP1AGNPLTC9005, DUKHCONP1AZ2PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.15 ZONE - 2 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-03-16 | 2014-05-18 | 2013-03-16 | 2014-05-18 | 90 |  |  |  | 0 | 0
DHBL.K30.L15.15 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-03-16 | 2013-12-24 | 2013-03-16 | 2013-12-24 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.15 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-03-16 | 2013-08-08 | 2013-03-16 | 2013-08-08 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.15 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-03-16 | 2013-08-08 | 2013-03-16 | 2013-08-08 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ2STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-05-23 | 2013-06-20 | 2013-05-23 | 2013-06-20 | 0 | Yes | DUKHCONP1AZ2STUG1030, DUKHCONP1AZ2STUG1030, DUKHCONP1AZ1STUG1035 | DUKHCONP1AZ2STUG1040, DUKHCONP1AZ3STUG1035, DUKHCONP1AZ2STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-04-21 | 2013-05-13 | 2013-04-21 | 2013-05-13 | 0 | Yes | DUKHCONP1AZ2STUG1015, DUKHCONP1AZ2STUG1015 | DUKHCONP1AZ2STUG1025, DUKHCONP1AZ2STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-06-09 | 2013-07-07 | 2013-06-09 | 2013-07-07 | 0 | Yes | DUKHCONP1AZ2STUG1035, DUKHCONP1AZ2STUG1035 | DUKHCONP1AZ2STUG1045, DUKHCONP1AZ2PLUG4300, DUKHCONP1AZ2STUG1045, DUKHCONP1AZ2PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-04-30 | 2013-05-28 | 2013-04-30 | 2013-05-28 | 0 | Yes | DUKHCONP1AZ2STUG1020, DUKHCONP1AZ1STUG1025, DUKHCONP1AZ2STUG1020 | DUKHCONP1AZ3STUG1025, DUKHCONP1AZ2STUG1030, DUKHCONP1AZ2STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-07-11 | 2013-08-08 | 2013-07-11 | 2013-08-08 | 0 | Yes | DUKHCONP1AZ2PLUG4300, DUKHCONP1AZ2STUG1040, DUKHCONP1AZ2PLUG4300, DUKHCONP1AZ1STUG1045, DUKHCONP1AZ2STUG1040 | DUKHCONP1AZ3STUG1045, DUKHCONP1AZ2STGF2000, DUKHCONP1AZ2STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-03-27 | 2013-04-22 | 2013-03-27 | 2013-04-22 | 0 | Yes | DUKHCONP1AZ2STUG1000, DUKHCONP1AZ2STUG1000 | DUKHCONP1AZ2STUG1010, DUKHCONP1AZ2STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-03-31 | 2013-04-25 | 2013-03-31 | 2013-04-25 | 0 | Yes | DUKHCONP1AZ2STUG1005, DUKHCONP1AZ2STUG1005 | DUKHCONP1AZ2STUG1015, DUKHCONP1AZ2STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-03-16 | 2013-04-13 | 2013-03-16 | 2013-04-13 | 0 | Yes | DUKHCONP1AZ1STUG1000, DUKHCONP1AGNSP005000 | DUKHCONP1AZ2STUG1005, DUKHCONP1BZ1STUG1000, DUKHCONP1AZ2STUG1005, DUKHCONP1AZ3STUG1000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-04-06 | 2013-05-04 | 2013-04-06 | 2013-05-04 | 0 | Yes | DUKHCONP1AZ2STUG1010, DUKHCONP1AZ2STUG1010 | DUKHCONP1AZ2STUG1020, DUKHCONP1AZ2STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ2STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-05-09 | 2013-06-06 | 2013-05-09 | 2013-06-06 | 0 | Yes | DUKHCONP1AZ2STUG1025, DUKHCONP1AZ2STUG1025 | DUKHCONP1AZ2STUG1035, DUKHCONP1AZ2STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.15 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2013-07-28 | 2013-12-24 | 2013-07-28 | 2013-12-24 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.15 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-07-28 | 2013-09-24 | 2013-07-28 | 2013-09-24 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ2STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-09-09 | 2013-09-24 | 2013-09-09 | 2013-09-24 | 2 | No | DUKHCONP1AZ1STGF2015, DUKHCONP1AZ2STGF2010, DUKHCONP1AZ2STGF2010 | DUKHCONP1AZ3STGF2015, DUKHCONP1AZ2STFF2020, DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ2STFF2020, DUKHCONP1AZ2ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-08-24 | 2013-09-21 | 2013-08-24 | 2013-09-21 | 2 | No | DUKHCONP1AZ2STGF2005, DUKHCONP1AZ2STGF2005 | DUKHCONP1AZ2STGF2015, DUKHCONI1AZ1DRGL5115, DUKHCONP1AZ2STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-08-05 | 2013-09-04 | 2013-08-05 | 2013-09-04 | 2 | No | DUKHCONP1AZ2STGF2000, DUKHCONP1AZ2STGF2000 | DUKHCONP1AZ2STGF2010, DUKHCONP1AZ2STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-07-28 | 2013-08-28 | 2013-07-28 | 2013-08-28 | 0 | Yes | DUKHCONP1AZ1STGF2000, DUKHCONP1AZ2STUG1045, DUKHCONP1AZ2STUG1045 | DUKHCONP1AZ2STGF2005, DUKHCONP1AZ3STGF2000, DUKHCONP1AZ2STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.15 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2013-09-11 | 2013-11-09 | 2013-09-11 | 2013-11-09 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ2STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-10-24 | 2013-11-09 | 2013-10-24 | 2013-11-09 | 4 | No | DUKHCONP1AZ2STFF2030, DUKHCONP1AZ1STFF2035, DUKHCONP1AZ2STFF2030 | DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2STRF2040, DUKHCONP1AZ3STFF2035, DUKHCONP1AZ2STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-10-06 | 2013-11-05 | 2013-10-06 | 2013-11-05 | 4 | No | DUKHCONP1AZ2STFF2025, DUKHCONP1AZ2STFF2025 | DUKHCONP1AZ2STFF2035, DUKHCONP1AZ2STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-09-21 | 2013-10-20 | 2013-09-21 | 2013-10-20 | 4 | No | DUKHCONP1AZ2STFF2020, DUKHCONP1AZ2STFF2020 | DUKHCONP1AZ2STFF2030, DUKHCONP1AZ2STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-09-11 | 2013-10-09 | 2013-09-11 | 2013-10-09 | 2 | No | DUKHCONP1AZ2STGF2015, DUKHCONP1AZ1STFF2020, DUKHCONP1AZ2STGF2015 | DUKHCONP1AZ2STFF2025, DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2STFF2025, DUKHCONP1AZ3STFF2020, DUKHCONP1AZ2ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.15 .10 .15 .20 ROOF |  | 50 | 50 | 0% | 2013-10-27 | 2013-12-24 | 2013-10-27 | 2013-12-24 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ2STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-10-30 | 2013-11-18 | 2013-10-30 | 2013-11-18 | 32 | No | DUKHCONP1AZ2STRF2040, DUKHCONP1AZ2STRF2040 | DUKHCONP1AZ2STRF2050, DUKHCONP1AZ2STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ2STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-10-27 | 2013-11-16 | 2013-10-27 | 2013-11-16 | 22 | No | DUKHCONP1AZ2STFF2035, DUKHCONP1AZ1STRF2040, DUKHCONP1AZ2STFF2035 | DUKHCONP1AZ3STRF2040, DUKHCONP1AZ2STRF2045, DUKHCONP1AZ2STRF2045 | 0 | 0 | ROOF
DUKHCONP1AZ2STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-11-14 | 2013-12-12 | 2013-11-14 | 2013-12-12 | 56 | No | DUKHCONP1AZ2STRF2055, DUKHCONP1AZ2STRF2055 | DUKHCONP1AZ2ARRF3630, DUKHCONP1AZ2STRF2065, DUKHCONP1AZ2ARRF3630, DUKHCONP1AZ2STRF2065 | 0 | 0 | ROOF
DUKHCONP1AZ2STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-11-25 | 2013-12-24 | 2013-11-25 | 2013-12-24 | 52 | No | DUKHCONP1AZ1STRF2065, DUKHCONP1AZ2STRF2060, DUKHCONP1AZ2STRF2060 | DUKHCONP1AZ2ARRF3630, DUKHCONP1AZ2ARRF3630, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ3STRF2065, DUKHCONP1AZ2AREL3665 | 0 | 0 | ROOF
DUKHCONP1AZ2STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2013-11-12 | 2013-11-26 | 2013-11-12 | 2013-11-26 | 32 | No | DUKHCONP1AZ1STRF2055, DUKHCONP1AZ2STRF2050, DUKHCONP1AZ2STRF2050 | DUKHCONP1AZ2ARRF3600, DUKHCONP1AZ2ARRF3600, DUKHCONP1AZ2MSEX5000, DUKHCONP1AZ2MSEX5000, DUKHCONP1AZ2WEEX5030, DUKHCONP1AZ2STRF2060, DUKHCONP1AZ2WEEX5030, DUKHCONP1AZ2MSEX5020, DUKHCONP1AZ2MSEX5020, DUKHCONP1AZ3STRF2055, DUKHCONP1AZ2STRF2060 | 0 | 0 | ROOF
DUKHCONP1AZ2STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2013-11-02 | 2013-11-24 | 2013-11-02 | 2013-11-24 | 32 | No | DUKHCONP1AZ2STRF2045, DUKHCONP1AZ2STRF2045 | DUKHCONP1AZ2STRF2055, DUKHCONP1AZ2STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.15 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2013-10-09 | 2014-04-19 | 2013-10-09 | 2014-04-19 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.15 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2013-10-09 | 2014-04-19 | 2013-10-09 | 2014-04-19 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.15 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-10-09 | 2014-03-25 | 2013-10-09 | 2014-03-25 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ2ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-01-27 | 2014-02-13 | 2014-01-27 | 2014-02-13 | 21 | No | DUKHCONP1AZ2ARGF3065, DUKHCONP1AZ1ARGF3070, DUKHCONP1AZ2ARGF3065 | DUKHCONP1AZ2ARGF3075, DUKHCONP1AZ2ARGF3080, DUKHCONP1AZ2ARGF3080, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3075, DUKHCONP1AZ3ARGF3070 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 21 | No | DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ2ACGF4600 | DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ2ACGF4605, DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ2ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-02-03 | 2014-02-26 | 2014-02-03 | 2014-02-26 | 31 | No | DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ1ARGF3080 | DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ3ARGF3080, DUKHCONP1AZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3000 | Block work | 25 | 25 | 0% | 2013-10-09 | 2013-11-09 | 2013-10-09 | 2013-11-09 | 18 | No | DUKHCONP1AZ2STGF2015, DUKHCONP1AZ2STGF2015, DUKHCONP1AZ1ARGF3000 | DUKHCONP1AZ2ELGF4000, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ3ARGF3000, DUKHCONP1AZ2ELGF4000, DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ2ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-02-02 | 2014-02-25 | 2014-02-02 | 2014-02-25 | 21 | No | DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ1ARGF3075 | DUKHCONP1AZ2ARGF3090, DUKHCONP1AZ2ARGF3085, DUKHCONP1AZ3ARGF3075, DUKHCONP1AZ2ARGF3085, DUKHCONP1AZ2ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-11-26 | 2013-12-25 | 2013-11-26 | 2013-12-25 | 18 | No | DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ1ARGF3020, DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ2ARGF3015, DUKHCONP1AZ2ARGF3015, DUKHCONP1AZ2PLGF4310 | DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2013-12-30 | 2014-01-15 | 2013-12-30 | 2014-01-15 | 21 | No | DUKHCONP1AZ2ARGF3010, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3010, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3035 | DUKHCONP1AZ2ARGF3050, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 21 | No | DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3080, DUKHCONP1AZ1ARGF3095, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ2ACGF4610, DUKHCONP1AZ2ARGF3090, DUKHCONP1AZ2ARGF3030, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ2ARGF3090, DUKHCONP1AZ2ARGF3085, DUKHCONP1AZ2ARGF3030, DUKHCONP1AZ2ARGF3080, DUKHCONP1AZ2ACGF4610, DUKHCONP1AZ2ARGF3085, DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3060 | DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2013-12-21 | 2014-01-12 | 2013-12-21 | 2014-01-12 | 18 | No | DUKHCONP1AZ2ARGF3030, DUKHCONP1AZ1ARGF3045, DUKHCONP1AZ2ELGF4010, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3030, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ELGF4010 | DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ2ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-11-11 | 2013-12-04 | 2013-11-11 | 2013-12-04 | 26 | No | DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ2ARGF3005 | DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 21 | No | DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3040 | DUKHCONP1AZ2ARGF3065, DUKHCONP1AZ2ARGF3065, DUKHCONP1AZ2ARGF3085, DUKHCONP1AZ2ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-01-01 | 2014-01-29 | 2014-01-01 | 2014-01-29 | 18 | No | DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ1ARGF3060, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ2ARGF3045 | DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ2PLGF4320, DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2PLGF4320, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ACGF4605, DUKHCONP1AZ2ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-02-16 | 2014-03-04 | 2014-02-16 | 2014-03-04 | 21 | No | DUKHCONP1AZ2ARGF3075, DUKHCONP1AZ2ARGF3075 | DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-11-19 | 2013-12-17 | 2013-11-19 | 2013-12-17 | 32 | No | DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ1ARGF3030, DUKHCONP1AZ2ARGF3005 | DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-11-03 | 2013-12-01 | 2013-11-03 | 2013-12-01 | 18 | No | DUKHCONP1AZ1ARGF3005, DUKHCONP1AZ2ELGF4000, DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ2ELGF4000, DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ2PLGF4305 | DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ2ARGF3030, DUKHCONP1AZ2ARGF3015, DUKHCONP1AZ2ARGF3010, DUKHCONP1AZ2ARGF3015, DUKHCONP1AZ2ARGF3010, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ2ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-12-02 | 2013-12-31 | 2013-12-02 | 2013-12-31 | 18 | No | DUKHCONP1AZ1ARGF3025, DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ2ARGF3010, DUKHCONP1AZ2ARGF3010, DUKHCONP1AZ2ARGF3020 | DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3050, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ2ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-02-10 | 2014-03-05 | 2014-02-10 | 2014-03-05 | 26 | No | DUKHCONP1AZ2ARGF3075, DUKHCONP1AZ2ARGF3075, DUKHCONP1AZ2ARGF3050, DUKHCONP1AZ2ARGF3050 | DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2013-12-23 | 2014-01-08 | 2013-12-23 | 2014-01-08 | 23 | No | DUKHCONP1AZ2ARGF3010, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3025, DUKHCONP1AZ2ARGF3010 | DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3040, DUKHCONP1AZ2ARGF3065, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-11-20 | 2013-12-07 | 2013-11-20 | 2013-12-07 | 18 | No | DUKHCONP1AZ1ARGF3015, DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ2ARGF3005 | DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ3ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-01-21 | 2014-02-06 | 2014-01-21 | 2014-02-06 | 21 | No | DUKHCONP1AZ1ARGF3065, DUKHCONP1AZ2ARGF3050, DUKHCONP1AZ2ARGF3035, DUKHCONP1AZ2ARGF3050, DUKHCONP1AZ2ARGF3035 | DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ2ARGF3070, DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ3ARGF3065 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.15 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2013-11-23 | 2014-04-19 | 2013-11-23 | 2014-04-19 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ2ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 0 | Yes | DUKHCONP1AZ1ARFF3370, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ARFF3365 | DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ2ARFF3380, DUKHCONP1AZ2ARFF3380, DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ3ARFF3370 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-03-05 | 2014-03-27 | 2014-03-05 | 2014-03-27 | 4 | No | DUKHCONP1AZ2ARFF3370, DUKHCONP1AZ2ARFF3370 | DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3300 | Block work | 25 | 25 | 0% | 2013-11-23 | 2013-12-22 | 2013-11-23 | 2013-12-22 | 0 | Yes | DUKHCONP1AZ2STFF2020, DUKHCONP1AZ2STFF2035, DUKHCONP1AZ2STFF2035, DUKHCONP1AZ2STFF2020, DUKHCONP1AZ1ARFF3300 | DUKHCONP1AZ2PLFF4325, DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2ELFF4035, DUKHCONP1AZ2PLFF4325, DUKHCONP1AZ2ELFF4035, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ2ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 0 | Yes | DUKHCONP1AZ2ARFF3370, DUKHCONP1AZ1ARFF3375, DUKHCONP1AZ2ARFF3370 | DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3390, DUKHCONP1AZ2ARFF3385, DUKHCONP1AZ2ARFF3390, DUKHCONP1AZ2ARFF3385, DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 0 | Yes | DUKHCONP1AZ2ARFF3315, DUKHCONP1AZ1ARFF3320, DUKHCONP1AZ2ARFF3315, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2PLFF4325, DUKHCONP1AZ2PLFF4325, DUKHCONP1AZ2PLFF4330 | DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ2ACFF4625, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ1ARFF3395, DUKHCONP1AZ2ARFF3330, DUKHCONP1AZ2ARFF3335, DUKHCONP1AZ2ARFF3350, DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ2ARFF3390, DUKHCONP1AZ2ARFF3390, DUKHCONP1AZ2ARFF3385, DUKHCONP1AZ2ARFF3385, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ARFF3335, DUKHCONP1AZ2ARFF3380, DUKHCONP1AZ2ARFF3330, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ACFF4625, DUKHCONP1AZ2ARFF3380, DUKHCONP1AZ2ARFF3350, DUKHCONP1AZ2ARFF3360 | DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2ACTC8000, DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-02-03 | 2014-02-26 | 2014-02-03 | 2014-02-26 | 0 | Yes | DUKHCONP1AZ2ARFF3330, DUKHCONP1AZ2ARFF3330, DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ1ARFF3345 | DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3310 | Flooring screed | 21 | 21 | 0% | 2013-12-26 | 2014-01-19 | 2013-12-26 | 2014-01-19 | 12 | No | DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ARFF3305 | DUKHCONP1AZ2ARFF3335, DUKHCONP1AZ2ARFF3335, DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ2ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-02-12 | 2014-03-06 | 2014-02-12 | 2014-03-06 | 2 | No | DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ2ARFF3325 | DUKHCONP1AZ2ARFF3385, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ARFF3385, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-02-10 | 2014-03-11 | 2014-02-10 | 2014-03-11 | 0 | Yes | DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ1ARFF3360 | DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ELFF4050, DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ2ELFF4060, DUKHCONP1AZ2ACFF4620, DUKHCONP1AZ2ELFF4050, DUKHCONP1AZ2PLFF4340, DUKHCONP1AZ2ACFF4620, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ELFF4055, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ELFF4060, DUKHCONP1AZ2ELFF4055, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ2PLFF4340 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-03-16 | 2014-04-07 | 2014-03-16 | 2014-04-07 | 0 | Yes | DUKHCONP1AZ2ARFF3350, DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ2ARFF3350 | DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-03-16 | 2014-04-07 | 2014-03-16 | 2014-04-07 | 1 | No | DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ2ARFF3375 | DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-01-04 | 2014-02-01 | 2014-01-04 | 2014-02-01 | 14 | No | DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ARFF3305 | DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3305 | Plastering work | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 0 | Yes | DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2ELFF4035, DUKHCONP1AZ2ELFF4035, DUKHCONP1AZ2PLFF4325, DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ1ARFF3305, DUKHCONP1AZ2PLFF4325 | DUKHCONP1AZ2ARFF3330, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ2ARFF3330, DUKHCONP1AZ2ARFF3310, DUKHCONP1AZ2ARFF3315, DUKHCONP1AZ2ARFF3315, DUKHCONP1AZ2ARFF3310, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ2ACFF4615 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 0 | Yes | DUKHCONP1AZ2ARFF3320, DUKHCONP1AZ2ARFF3320, DUKHCONP1AZ2ARFF3310, DUKHCONP1AZ2ARFF3310, DUKHCONP1AZ1ARFF3325 | DUKHCONP1AZ3ARFF3325, DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ2ARFF3335, DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ2ARFF3350, DUKHCONP1AZ2ARFF3350, DUKHCONP1AZ2ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-02-08 | 2014-02-25 | 2014-02-08 | 2014-02-25 | 8 | No | DUKHCONP1AZ2ARFF3310, DUKHCONP1AZ2ARFF3310, DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ2ARFF3325 | DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-01-07 | 2014-01-23 | 2014-01-07 | 2014-01-23 | 0 | Yes | DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ1ARFF3315 | DUKHCONP1AZ3ARFF3315, DUKHCONP1AZ2ARFF3320, DUKHCONP1AZ2ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-02-26 | 2014-03-15 | 2014-02-26 | 2014-03-15 | 0 | Yes | DUKHCONP1AZ2ARFF3350, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ARFF3335, DUKHCONP1AZ2ARFF3335, DUKHCONP1AZ1ARFF3365, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ARFF3350 | DUKHCONP1AZ2PLFF4335, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3370, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ARFF3370, DUKHCONP1AZ2PLFF4335, DUKHCONP1AZ3ARFF3365 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.15 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2013-12-07 | 2014-02-10 | 2013-12-07 | 2014-02-10 | 57 |  |  |  | 0 | 0
DUKHCONP1AZ2ARRF3600 | Block work | 20 | 20 | 0% | 2013-12-07 | 2013-12-30 | 2013-12-07 | 2013-12-30 | 52 | No | DUKHCONP1AZ2STRF2055, DUKHCONP1AZ2STRF2055, DUKHCONP1AZ1ARRF3600 | DUKHCONP1AZ3ARRF3600, DUKHCONP1AZ2ARRF3605, DUKHCONP1AZ2ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-01-25 | 2014-02-10 | 2014-01-25 | 2014-02-10 | 57 | No | DUKHCONP1AZ2ARRF3695, DUKHCONP1AZ2ARRF3695 | DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3610 | Flooring screed | 15 | 15 | 0% | 2013-12-30 | 2014-01-15 | 2013-12-30 | 2014-01-15 | 57 | No | DUKHCONP1AZ2ARRF3605, DUKHCONP1AZ2ARRF3605 | DUKHCONP1AZ2ARRF3695, DUKHCONP1AZ2ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 57 | No | DUKHCONP1AZ2ARRF3610, DUKHCONP1AZ2ARRF3610 | DUKHCONP1AZ2AREL3680, DUKHCONP1AZ2AREL3680, DUKHCONP1AZ2ARRF3620, DUKHCONP1AZ2ARRF3620 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3605 | Plastering work | 20 | 20 | 0% | 2013-12-15 | 2014-01-07 | 2013-12-15 | 2014-01-07 | 52 | No | DUKHCONP1AZ2ARRF3600, DUKHCONP1AZ2ARRF3600 | DUKHCONP1AZ2PLRF4345, DUKHCONP1AZ2ARRF3610, DUKHCONP1AZ2PLRF4345, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ2ARRF3610 | 0 | 0 | ROOF
DHBL.K30.L15.15 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2013-12-30 | 2014-03-19 | 2013-12-30 | 2014-03-19 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.15 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-01-13 | 2014-03-19 | 2014-01-13 | 2014-03-19 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ2ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 21 | No | DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2ARRF3645 | DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-03-03 | 2014-03-19 | 2014-03-03 | 2014-03-19 | 26 | No | DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2ARRF3655 | DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 21 | No | DUKHCONP1AZ2ARRF3635, DUKHCONP1AZ2ARRF3635 | DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-02-19 | 2014-03-13 | 2014-02-19 | 2014-03-13 | 21 | No | DUKHCONP1AZ2ARRF3650, DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ1ARRF3655, DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2ARRF3650 | DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2ARRF3660, DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2ARRF3660, DUKHCONP1AZ3ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 21 | No | DUKHCONP1AZ2ARRF3630, DUKHCONP1AZ2ARRF3630 | DUKHCONP1AZ2ARRF3640, DUKHCONP1AZ2ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 21 | No | DUKHCONP1AZ2STRF2060, DUKHCONP1AZ2STRF2065, DUKHCONP1AZ2STRF2065, DUKHCONP1AZ1ARRF3630, DUKHCONP1AZ2STRF2060 | DUKHCONP1AZ3ARRF3630, DUKHCONP1AZ2ARRF3635, DUKHCONP1AZ2ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ2ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 21 | No | DUKHCONP1AZ2ARRF3640, DUKHCONP1AZ2ARRF3640 | DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ELRF4070, DUKHCONP1AZ2ARRF3650, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2ELRF4070, DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ARRF3650 | 0 | 0 | ROOF
DHBL.K30.L15.15 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2013-12-30 | 2014-02-20 | 2013-12-30 | 2014-02-20 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ2AREL3680 | External Painting | 20 | 20 | 0% | 2014-01-28 | 2014-02-20 | 2014-01-28 | 2014-02-20 | 49 | No | DUKHCONP1AZ2ARRF3695, DUKHCONP1AZ2AREL3670, DUKHCONP1AZ2ARRF3695, DUKHCONP1AZ2AREL3670, DUKHCONP1AZ1AREL3680 | DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ3AREL3680, DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2ACTC8000 | 0 | 0 | ELEVATION
DUKHCONP1AZ2AREL3665 | External Plastering | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 47 | No | DUKHCONP1AZ2STRF2065, DUKHCONP1AZ2STRF2065, DUKHCONP1AZ1AREL3665, DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ARRF3605, DUKHCONP1AZ2ARFF3305 | DUKHCONP1AZ2AREL3670, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2AREL3670, DUKHCONP1AZ3AREL3665 | 0 | 0 | ELEVATION
DUKHCONP1AZ2AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-01-16 | 2014-02-08 | 2014-01-16 | 2014-02-08 | 49 | No | DUKHCONP1AZ2AREL3665, DUKHCONP1AZ1AREL3670, DUKHCONP1AZ2AREL3665 | DUKHCONP1AZ3AREL3670, DUKHCONP1AZ2AREL3680, DUKHCONP1AZ2AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L15.15 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-07-02 | 2014-04-17 | 2013-07-02 | 2014-04-17 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.15 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2013-10-15 | 2014-04-17 | 2013-10-15 | 2014-04-17 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.15 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-10-15 | 2014-02-25 | 2013-10-15 | 2014-02-25 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ2ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-10-29 | 2013-11-20 | 2013-10-29 | 2013-11-20 | 45 | No | DUKHCONP1AZ2ELGF4000, DUKHCONP1AZ1ELGF4005, DUKHCONP1AZ2ELGF4000 | DUKHCONP1AZ2ELGF4010, DUKHCONP1AZ3ELGF4005, DUKHCONP1AZ2ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-10-15 | 2013-11-14 | 2013-10-15 | 2013-11-14 | 27 | No | DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ2ARGF3000 | DUKHCONP1AZ2ELGF4005, DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ2ELGF4005, DUKHCONP1AZ2ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-01-09 | 2014-02-06 | 2014-01-09 | 2014-02-06 | 30 | No | DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ1ELGF4015, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ARGF3055 | DUKHCONP1AZ2ELFF4055, DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ2ELFF4055, DUKHCONP1AZ2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-01-15 | 2014-02-06 | 2014-01-15 | 2014-02-06 | 18 | No | DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ELGF4010, DUKHCONP1AZ2ELGF4010, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ARGF3060 | DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ2ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 25 | No | DUKHCONP1AZ1ELGF4025, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ARGF3060 | DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 18 | No | DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ1ELGF4030, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ELGF4020 | DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ3ELGF4030, DUKHCONP1AZ2ELFF4050, DUKHCONP1AZ2ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-11-06 | 2013-12-04 | 2013-11-06 | 2013-12-04 | 45 | No | DUKHCONP1AZ2ELGF4005, DUKHCONP1AZ2ELGF4005 | DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ELGF4020, DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ2ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.15 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2013-11-28 | 2014-03-31 | 2013-11-28 | 2014-03-31 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ2ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-10 | 2014-01-02 | 2013-12-10 | 2014-01-02 | 29 | No | DUKHCONP1AZ2ELFF4035, DUKHCONP1AZ2ELFF4035 | DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ2ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-11-28 | 2013-12-28 | 2013-11-28 | 2013-12-28 | 11 | No | DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2ARFF3300 | DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ELFF4040, DUKHCONP1AZ2ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-02-19 | 2014-03-19 | 2014-02-19 | 2014-03-19 | 1 | No | DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ1ELFF4055, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ2ARFF3360 | DUKHCONP1AZ3ELFF4055, DUKHCONP1AZ2ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-02-23 | 2014-03-17 | 2014-02-23 | 2014-03-17 | 3 | No | DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ1ELFF4060, DUKHCONP1AZ2ARFF3360 | DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ2ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 1 | No | DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ1ELFF4065, DUKHCONP1AZ2ELFF4060, DUKHCONP1AZ2ELFF4060, DUKHCONP1AZ2ELGF4025 | DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ2ELRF4070, DUKHCONP1AZ2ELRF4070, DUKHCONP1AZ2ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 11 | No | DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ2MSEX5010 | DUKHCONP1AZ2ELRF4070, DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 27 | No | DUKHCONP1AZ2ELFF4040, DUKHCONP1AZ1ELFF4045, DUKHCONP1AZ2ELFF4040 | DUKHCONP1AZ2ELFF4060, DUKHCONP1AZ2ELFF4060, DUKHCONP1AZ3ELFF4045, DUKHCONP1AZ2ELRF4070, DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ2ELRF4070 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.15 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-03-17 | 2014-04-17 | 2014-03-17 | 2014-04-17 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ2ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-03-17 | 2014-04-06 | 2014-03-17 | 2014-04-06 | 1 | No | DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2ELFF4050, DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ2ELFF4050 | DUKHCONP1AZ2ELRF4075, DUKHCONP1AZ2ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ2ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-03-23 | 2014-04-17 | 2014-03-23 | 2014-04-17 | 1 | No | DUKHCONP1AZ2ELRF4070, DUKHCONP1AZ2ELRF4070 | DUKHCONP1AZ2ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.15 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-07-02 | 2014-04-17 | 2013-07-02 | 2014-04-17 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.15 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-07-02 | 2014-02-25 | 2013-07-02 | 2014-02-25 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-07-02 | 2013-07-20 | 2013-07-02 | 2013-07-20 | 0 | Yes | DUKHCONP1AZ2STUG1040, DUKHCONP1AZ2STUG1040 | DUKHCONP1AZ2STUG1045, DUKHCONP1AZ2STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-10-28 | 2013-11-17 | 2013-10-28 | 2013-11-17 | 39 | No | DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ2PLGF4305 | DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ2MSEX5000, DUKHCONP1AZ2MSEX5000, DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ2ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-10-28 | 2013-11-17 | 2013-10-28 | 2013-11-17 | 18 | No | DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ1PLGF4305 | DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ2ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-02-08 | 2014-02-25 | 2014-02-08 | 2014-02-25 | 45 | No | DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ1PLGF4320, DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ARGF3060 | DUKHCONP1AZ3PLGF4320, DUKHCONP1AZ2PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 45 | No | DUKHCONP1AZ1PLGF4315, DUKHCONP1AZ2ARGF3065, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ2ARGF3065 | DUKHCONP1AZ2PLGF4320, DUKHCONP1AZ3PLGF4315, DUKHCONP1AZ2PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.15 .20 .15 .15 FIRST FLOORS |  | 90 | 90 | 0% | 2013-12-10 | 2014-03-26 | 2013-12-10 | 2014-03-26 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ2PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2013-12-10 | 2013-12-31 | 2013-12-10 | 2013-12-31 | 22 | No | DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2PLFF4325, DUKHCONP1AZ1PLFF4330, DUKHCONP1AZ2PLFF4325 | DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2PLFF4335, DUKHCONP1AZ2PLFF4335, DUKHCONP1AZ2ARFF3320, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ2ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-12-10 | 2013-12-31 | 2013-12-10 | 2013-12-31 | 0 | Yes | DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ2ARFF3300 | DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ARFF3320, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-03-10 | 2014-03-26 | 2014-03-10 | 2014-03-26 | 5 | No | DUKHCONP1AZ2PLFF4335, DUKHCONP1AZ2PLFF4335, DUKHCONP1AZ1PLFF4340, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ARFF3360 | DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ3PLFF4340 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 5 | No | DUKHCONP1AZ2ARFF3365, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2ARFF3365 | DUKHCONP1AZ2PLFF4340, DUKHCONP1AZ2PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.15 .20 .15 .20 ROOF |  | 93 | 93 | 0% | 2013-12-30 | 2014-04-17 | 2013-12-30 | 2014-04-17 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ2PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2013-12-30 | 2014-01-15 | 2013-12-30 | 2014-01-15 | 56 | No | DUKHCONP1AZ2ARRF3605, DUKHCONP1AZ2ARRF3605 | DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2PLRF4350 | 0 | 0 | ROOF
DUKHCONP1AZ2PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-02-13 | 2014-03-02 | 2014-02-13 | 2014-03-02 | 26 | No | DUKHCONP1AZ2PLRF4345, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ1PLRF4350, DUKHCONP1AZ2PLFF4330, DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2PLRF4345 | DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ3PLRF4350 | 0 | 0 | ROOF
DUKHCONP1AZ2PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-03-20 | 2014-04-17 | 2014-03-20 | 2014-04-17 | 1 | No | DUKHCONP1AZ2PLRF4345, DUKHCONP1AZ2PLRF4345, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2PLFF4340, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ1PLRF4355, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2PLFF4340, DUKHCONP1AZ2PLRF4350 | DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ2PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L15.15 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2013-11-17 | 2014-04-15 | 2013-11-17 | 2014-04-15 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.15 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-11-17 | 2014-02-23 | 2013-11-17 | 2014-02-23 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ2ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 32 | No | DUKHCONP1AZ1ACGF4610, DUKHCONP1AZ2ACGF4605, DUKHCONP1AZ2ACGF4605 | DUKHCONP1AZ3ACGF4610, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ACRF4635, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-09 | 2014-02-06 | 2014-01-09 | 2014-02-06 | 32 | No | DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ1ACGF4605, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ARGF3060 | DUKHCONP1AZ2ACGF4610, DUKHCONP1AZ2ACGF4610, DUKHCONP1AZ3ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ2ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-11-17 | 2013-12-09 | 2013-11-17 | 2013-12-09 | 49 | No | DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ1ACGF4600 | DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ2ACGF4605, DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ARGF3055, DUKHCONP1AZ2ACGF4605, DUKHCONP1AZ3ACGF4600 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.15 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-01-01 | 2014-04-03 | 2014-01-01 | 2014-04-03 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ2ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-03-12 | 2014-04-03 | 2014-03-12 | 2014-04-03 | 2 | No | DUKHCONP1AZ2ACFF4620, DUKHCONP1AZ2ACFF4620, DUKHCONP1AZ1ACFF4625 | DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ACRF4635, DUKHCONP1AZ2ACRF4635, DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-02-19 | 2014-03-19 | 2014-02-19 | 2014-03-19 | 2 | No | DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ1ACFF4620, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ACFF4615 | DUKHCONP1AZ2ACFF4625, DUKHCONP1AZ2ACFF4625, DUKHCONP1AZ3ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ2ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-01 | 2014-01-23 | 2014-01-01 | 2014-01-23 | 27 | No | DUKHCONP1AZ1ACFF4615, DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ2ARFF3305 | DUKHCONP1AZ3ACFF4615, DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ACFF4620, DUKHCONP1AZ2ARFF3360, DUKHCONP1AZ2ACFF4620 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.15 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-02-03 | 2014-04-15 | 2014-02-03 | 2014-04-15 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ2ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 3 | No | DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ACFF4625, DUKHCONP1AZ2ACFF4625, DUKHCONP1AZ1ACRF4635, DUKHCONP1AZ2ACGF4610, DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ2ACGF4610 | DUKHCONP1AZ3ACRF4635, DUKHCONP1AZ2ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ2ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 34 | No | DUKHCONP1AZ2ARRF3645, DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ1ACRF4630, DUKHCONP1AZ2ARRF3645 | DUKHCONP1AZ2ACRF4635, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ2ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.15 .25 EXTERNAL WORKS |  | 136 | 136 | 0% | 2013-11-24 | 2014-05-03 | 2013-11-24 | 2014-05-03 | 103 |  |  |  | 0 | 0
DHBL.K30.L15.15 .25 .10 MISCELLANEOUS |  | 136 | 136 | 0% | 2013-11-24 | 2014-05-03 | 2013-11-24 | 2014-05-03 | 103 |  |  |  | 0 | 0
DUKHCONP1AZ2MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-04-05 | 2014-05-03 | 2014-04-05 | 2014-05-03 | 103 | No | DUKHCONP1AZ1MSEX5335, DUKHPROGEN00PRDV3430, DUKHCONI1AZ1BWGL5325 | DUKHCONP1AZ3MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ2MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-12-08 | 2014-01-06 | 2013-12-08 | 2014-01-06 | 33 | No | DUKHCONP1AZ2MSEX5000, DUKHCONP1AZ2MSEX5000 | DUKHCONP1AZ2MSEX5010, DUKHCONP1AZ2MSEX5015, DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2MSEX5015, DUKHCONP1AZ2ELTC8010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ2MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-01-15 | 2014-02-13 | 2014-01-15 | 2014-02-13 | 16 | No | DUKHCONP1AZ1MSEX5020, DUKHCONP1AZ2STRF2055, DUKHCONP1AZ2STRF2055 | DUKHCONP1AZ2HDEX5090, DUKHCONP1AZ2MSEX5025, DUKHCONP1AZ2HDEX5090, DUKHCONP1AZ3MSEX5020, DUKHCONP1AZ2MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ2MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2013-12-29 | 2014-01-20 | 2013-12-29 | 2014-01-20 | 33 | No | DUKHCONP1AZ2MSEX5005, DUKHCONP1AZ2MSEX5005 | DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ2MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ2MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-11-24 | 2013-12-23 | 2013-11-24 | 2013-12-23 | 33 | No | DUKHCONP1AZ2STRF2055, DUKHCONP1AZ2STRF2055, DUKHCONP1AZ2PLGF4310, DUKHCONP1AZ2PLGF4310 | DUKHCONP1AZ2MSEX5005, DUKHCONP1AZ2MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ2MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-02-02 | 2014-02-25 | 2014-02-02 | 2014-02-25 | 19 | No | DUKHCONP1AZ2MSEX5020, DUKHCONP1AZ2MSEX5020 | DUKHCONP1AZ2WEEX5050, DUKHCONP1AZ2WEEX5060 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ2MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 33 | No | DUKHCONP1AZ2MSEX5005, DUKHCONP1AZ2MSEX5015 | DUKHCONP1AZ2ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.15 .25 .15 WATER TANK ENCLOSURE |  | 70 | 70 | 0% | 2014-01-16 | 2014-04-08 | 2014-01-16 | 2014-04-08 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ2WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 13 | No | DUKHCONP1AZ2WEEX5035, DUKHCONP1AZ2WEEX5035 | DUKHCONP1AZ2WEEX5045, DUKHCONP1AZ2WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ2WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 13 | No | DUKHCONP1AZ2WEEX5030, DUKHCONP1AZ2WEEX5030 | DUKHCONP1AZ2WEEX5040, DUKHCONP1AZ2WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ2WEEX5030 | Excavation | 20 | 20 | 0% | 2014-01-16 | 2014-02-08 | 2014-01-16 | 2014-02-08 | 13 | No | DUKHCONP1AZ2STRF2055, DUKHCONP1AZ1WEEX5030, DUKHCONP1AZ2STRF2055 | DUKHCONP1AZ2WEEX5035, DUKHCONP1AZ3WEEX5030, DUKHCONP1AZ2WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ2WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 13 | No | DUKHCONP1AZ2WEEX5040, DUKHCONP1AZ2WEEX5040 | DUKHCONP1AZ2WEEX5050, DUKHCONP1AZ2WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ2WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-03-11 | 2014-04-08 | 2014-03-11 | 2014-04-08 | 9 | No | DUKHCONP1AZ2WEEX5060, DUKHCONP1AZ2MSEX5015, DUKHCONP1AZ1WEEX5065, DUKHCONP1AZ2WEEX5060, DUKHCONP1AZ2MSEX5015, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2PLRF4350 | DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ2PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ2WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-02-22 | 2014-03-16 | 2014-02-22 | 2014-03-16 | 13 | No | DUKHCONP1AZ2MSEX5025, DUKHCONP1AZ2WEEX5045, DUKHCONP1AZ2WEEX5045 | DUKHCONP1AZ2WEEX5060, DUKHCONP1AZ2WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ2WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 10 | No | DUKHCONP1AZ2MSEX5025, DUKHCONP1AZ2WEEX5050, DUKHCONP1AZ1WEEX5060, DUKHCONP1AZ2WEEX5050 | DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ3WEEX5060, DUKHCONP1AZ2WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.15 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-01-29 | 2014-03-12 | 2014-01-29 | 2014-03-12 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ2HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-02-10 | 2014-03-05 | 2014-02-10 | 2014-03-05 | 16 | No | DUKHCONP1AZ2HDEX5090, DUKHCONP1AZ2HDEX5090 | DUKHCONP1AZ2HDEX5100, DUKHCONP1AZ2HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ2HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 16 | No | DUKHCONP1AZ2HDEX5095, DUKHCONP1AZ2HDEX5095 | DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2SLEX5105, DUKHCONP1AZ2SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ2HDEX5090 | kerb works | 20 | 20 | 0% | 2014-01-29 | 2014-02-22 | 2014-01-29 | 2014-02-22 | 16 | No | DUKHCONP1AZ2MSEX5020, DUKHCONP1AZ1HDEX5090, DUKHCONP1AZ2MSEX5020 | DUKHCONP1AZ2HDEX5095, DUKHCONP1AZ2HDEX5095, DUKHCONP1AZ3HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.15 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-02-24 | 2014-03-31 | 2014-02-24 | 2014-03-31 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ2SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 16 | No | DUKHCONP1AZ2HDEX5100, DUKHCONP1AZ2HDEX5100 | DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2SLEX5110, DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ2SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ2SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 16 | No | DUKHCONP1AZ2SLEX5105, DUKHCONP1AZ2SLEX5105 | DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ2PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.15 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ2ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 | Yes | DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2AREL3680, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ACRF4635, DUKHCONP1AZ2ACFF4625 | DUKHHANP1AGNACTC9000, DUKHCONP1AZ3ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 | Yes | DUKHCONP1AZ2SLEX5105, DUKHCONP1AZ2SLEX5110, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ2HDEX5100, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ2AREL3680, DUKHCONP1AZ2ELRF4075, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ2ARRF3620, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2ELFF4055, DUKHCONP1AZ2MSEX5005, DUKHCONP1AZ2ARRF3660, DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ2ELFF4050, DUKHCONP1AZ2ELGF4015 | DUKHHANP1AGNELTC9010, DUKHCONP1AZ3ELTC8010, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 | Yes | DUKHCONP1AZ2HDEX5100, DUKHCONP1AZ2ARRF3620, DUKHCONP1AZ2AREL3680, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ2ARRF3660, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ2PLRF4350, DUKHCONP1AZ2PLGF4320, DUKHCONP1AZ1PLTC8005, DUKHCONP1AZ2SLEX5110, DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ2MSEX5005, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ2SLEX5105 | DUKHCONP1AZ3PLTC8005, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.20 ZONE - 3 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-04-14 | 2014-06-16 | 2013-04-14 | 2014-06-16 | 90 |  |  |  | 0 | 0
DHBL.K30.L15.20 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-04-14 | 2014-01-22 | 2013-04-14 | 2014-01-22 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.20 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-04-14 | 2013-09-10 | 2013-04-14 | 2013-09-10 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.20 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-04-14 | 2013-09-10 | 2013-04-14 | 2013-09-10 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ3STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-06-22 | 2013-07-20 | 2013-06-22 | 2013-07-20 | 0 | Yes | DUKHCONP1AZ3STUG1030, DUKHCONP1AZ3STUG1030, DUKHCONP1AZ2STUG1035 | DUKHCONP1AZ3STUG1040, DUKHCONP1AZ4STUG1035, DUKHCONP1AZ3STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-05-20 | 2013-06-11 | 2013-05-20 | 2013-06-11 | 0 | Yes | DUKHCONP1AZ3STUG1015, DUKHCONP1AZ3STUG1015 | DUKHCONP1AZ3STUG1025, DUKHCONP1AZ3STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-07-08 | 2013-08-05 | 2013-07-08 | 2013-08-05 | 0 | Yes | DUKHCONP1AZ3STUG1035, DUKHCONP1AZ3STUG1035 | DUKHCONP1AZ3STUG1045, DUKHCONP1AZ3STUG1045, DUKHCONP1AZ3PLUG4300, DUKHCONP1AZ3PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-05-29 | 2013-06-26 | 2013-05-29 | 2013-06-26 | 0 | Yes | DUKHCONP1AZ2STUG1025, DUKHCONP1AZ3STUG1020, DUKHCONP1AZ3STUG1020 | DUKHCONP1AZ3STUG1030, DUKHCONP1AZ4STUG1025, DUKHCONP1AZ3STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-08-13 | 2013-09-10 | 2013-08-13 | 2013-09-10 | 0 | Yes | DUKHCONP1AZ3PLUG4300, DUKHCONP1AZ3STUG1040, DUKHCONP1AZ3STUG1040, DUKHCONP1AZ2STUG1045, DUKHCONP1AZ3PLUG4300 | DUKHCONP1AZ4STUG1045, DUKHCONP1AZ3STGF2000, DUKHCONP1AZ3STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-04-25 | 2013-05-21 | 2013-04-25 | 2013-05-21 | 0 | Yes | DUKHCONP1AZ3STUG1000, DUKHCONP1AZ3STUG1000 | DUKHCONP1AZ3STUG1010, DUKHCONP1AZ3STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-04-29 | 2013-05-25 | 2013-04-29 | 2013-05-25 | 0 | Yes | DUKHCONP1AZ3STUG1005, DUKHCONP1AZ3STUG1005 | DUKHCONP1AZ3STUG1015, DUKHCONP1AZ3STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-04-14 | 2013-05-12 | 2013-04-14 | 2013-05-12 | 0 | Yes | DUKHCONP1AGNSP005000, DUKHCONP1AZ2STUG1000 | DUKHCONP1AZ4STUG1000, DUKHCONP1AZ3STUG1005, DUKHCONP1AZ3STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-05-05 | 2013-06-02 | 2013-05-05 | 2013-06-02 | 0 | Yes | DUKHCONP1AZ3STUG1010, DUKHCONP1AZ3STUG1010 | DUKHCONP1AZ3STUG1020, DUKHCONP1AZ3STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ3STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-06-08 | 2013-07-06 | 2013-06-08 | 2013-07-06 | 0 | Yes | DUKHCONP1AZ3STUG1025, DUKHCONP1AZ3STUG1025 | DUKHCONP1AZ3STUG1035, DUKHCONP1AZ3STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.20 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2013-08-29 | 2014-01-22 | 2013-08-29 | 2014-01-22 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.20 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-08-29 | 2013-10-26 | 2013-08-29 | 2013-10-26 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ3STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-10-08 | 2013-10-26 | 2013-10-08 | 2013-10-26 | 2 | No | DUKHCONP1AZ2STGF2015, DUKHCONP1AZ3STGF2010, DUKHCONP1AZ3STGF2010 | DUKHCONP1AZ3STFF2020, DUKHCONP1AZ3ARGF3000, DUKHCONP1AZ3STFF2020, DUKHCONP1AZ4STGF2015, DUKHCONP1AZ3ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-09-22 | 2013-10-22 | 2013-09-22 | 2013-10-22 | 2 | No | DUKHCONP1AZ3STGF2005, DUKHCONP1AZ3STGF2005 | DUKHCONP1AZ3STGF2015, DUKHCONP1AZ3STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-09-07 | 2013-10-03 | 2013-09-07 | 2013-10-03 | 2 | No | DUKHCONP1AZ3STGF2000, DUKHCONP1AZ3STGF2000 | DUKHCONP1AZ3STGF2010, DUKHCONP1AZ3STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-08-29 | 2013-09-26 | 2013-08-29 | 2013-09-26 | 0 | Yes | DUKHCONP1AZ3STUG1045, DUKHCONP1AZ2STGF2000, DUKHCONP1AZ3STUG1045 | DUKHCONP1AZ4STGF2000, DUKHCONP1AZ3STGF2005, DUKHCONP1AZ3STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.20 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2013-10-10 | 2013-12-08 | 2013-10-10 | 2013-12-08 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ3STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-11-23 | 2013-12-08 | 2013-11-23 | 2013-12-08 | 4 | No | DUKHCONP1AZ3STFF2030, DUKHCONP1AZ3STFF2030, DUKHCONP1AZ2STFF2035 | DUKHCONP1AZ3STRF2040, DUKHCONP1AZ4STFF2035, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ3STRF2040, DUKHCONP1AZ3ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-11-06 | 2013-12-04 | 2013-11-06 | 2013-12-04 | 4 | No | DUKHCONP1AZ3STFF2025, DUKHCONP1AZ3STFF2025 | DUKHCONP1AZ3STFF2035, DUKHCONP1AZ3STFF2035, DUKHCONI1AZ2DRGL5115 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-10-22 | 2013-11-18 | 2013-10-22 | 2013-11-18 | 4 | No | DUKHCONP1AZ3STFF2020, DUKHCONP1AZ3STFF2020 | DUKHCONP1AZ3STFF2030, DUKHCONP1AZ3STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-10-10 | 2013-11-10 | 2013-10-10 | 2013-11-10 | 2 | No | DUKHCONP1AZ2STFF2020, DUKHCONP1AZ3STGF2015, DUKHCONP1AZ3STGF2015 | DUKHCONP1AZ3STFF2025, DUKHCONP1AZ4STFF2020, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ3STFF2025, DUKHCONP1AZ3ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.20 .10 .15 .20 ROOF |  | 50 | 50 | 0% | 2013-11-25 | 2014-01-22 | 2013-11-25 | 2014-01-22 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ3STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-11-28 | 2013-12-17 | 2013-11-28 | 2013-12-17 | 20 | No | DUKHCONP1AZ3STRF2040, DUKHCONP1AZ3STRF2040 | DUKHCONP1AZ3STRF2050, DUKHCONP1AZ3STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ3STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-11-25 | 2013-12-15 | 2013-11-25 | 2013-12-15 | 15 | No | DUKHCONP1AZ3STFF2035, DUKHCONP1AZ2STRF2040, DUKHCONP1AZ3STFF2035 | DUKHCONP1AZ4STRF2040, DUKHCONP1AZ3STRF2045, DUKHCONP1AZ3STRF2045 | 0 | 0 | ROOF
DUKHCONP1AZ3STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 56 | No | DUKHCONP1AZ3STRF2055, DUKHCONP1AZ3STRF2055 | DUKHCONP1AZ3STRF2065, DUKHCONP1AZ3ARRF3630, DUKHCONP1AZ3STRF2065, DUKHCONP1AZ3ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ3STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-12-25 | 2014-01-22 | 2013-12-25 | 2014-01-22 | 52 | No | DUKHCONP1AZ3STRF2060, DUKHCONP1AZ3STRF2060, DUKHCONP1AZ2STRF2065 | DUKHCONP1AZ3ARRF3630, DUKHCONP1AZ4STRF2065, DUKHCONP1AZ3ARRF3630, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ3AREL3665 | 0 | 0 | ROOF
DUKHCONP1AZ3STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2013-12-11 | 2013-12-26 | 2013-12-11 | 2013-12-26 | 20 | No | DUKHCONP1AZ3STRF2050, DUKHCONP1AZ2STRF2055, DUKHCONP1AZ3STRF2050 | DUKHCONP1AZ3MSEX5000, DUKHCONP1AZ3MSEX5020, DUKHCONP1AZ3ARRF3600, DUKHCONP1AZ4STRF2055, DUKHCONP1AZ3STRF2060, DUKHCONP1AZ3WEEX5030, DUKHCONP1AZ3ARRF3600, DUKHCONP1AZ3WEEX5030, DUKHCONP1AZ3MSEX5000, DUKHCONP1AZ3STRF2060, DUKHCONP1AZ3MSEX5020 | 0 | 0 | ROOF
DUKHCONP1AZ3STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2013-12-01 | 2013-12-24 | 2013-12-01 | 2013-12-24 | 20 | No | DUKHCONP1AZ3STRF2045, DUKHCONP1AZ3STRF2045 | DUKHCONP1AZ3STRF2055, DUKHCONP1AZ3STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.20 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2013-11-10 | 2014-05-18 | 2013-11-10 | 2014-05-18 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.20 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2013-11-10 | 2014-05-18 | 2013-11-10 | 2014-05-18 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.20 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-11-10 | 2014-04-23 | 2013-11-10 | 2014-04-23 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ3ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-02-26 | 2014-03-15 | 2014-02-26 | 2014-03-15 | 21 | No | DUKHCONP1AZ3ARGF3065, DUKHCONP1AZ3ARGF3065, DUKHCONP1AZ2ARGF3070 | DUKHCONP1AZ3ARGF3075, DUKHCONP1AZ3ARGF3080, DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3080, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 21 | No | DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ACGF4600, DUKHCONP1AZ3ACGF4600 | DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ3ELGF4020, DUKHCONP1AZ3ACGF4605, DUKHCONP1AZ3ACGF4605, DUKHCONP1AZ3ELGF4020, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ3ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-03-05 | 2014-03-27 | 2014-03-05 | 2014-03-27 | 31 | No | DUKHCONP1AZ3ARGF3070, DUKHCONP1AZ2ARGF3080, DUKHCONP1AZ3ARGF3070 | DUKHCONP1AZ4ARGF3080, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3000 | Block work | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 18 | No | DUKHCONP1AZ2ARGF3000, DUKHCONP1AZ3STGF2015, DUKHCONP1AZ3STGF2015 | DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3ELGF4000, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3ELGF4000, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-03-04 | 2014-03-26 | 2014-03-04 | 2014-03-26 | 21 | No | DUKHCONP1AZ3ARGF3070, DUKHCONP1AZ2ARGF3075, DUKHCONP1AZ3ARGF3070 | DUKHCONP1AZ3ARGF3090, DUKHCONP1AZ4ARGF3075, DUKHCONP1AZ3ARGF3085, DUKHCONP1AZ3ARGF3090, DUKHCONP1AZ3ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-12-26 | 2014-01-23 | 2013-12-26 | 2014-01-23 | 18 | No | DUKHCONP1AZ2ARGF3020, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3ARGF3015, DUKHCONP1AZ3ARGF3015 | DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-01-28 | 2014-02-15 | 2014-01-28 | 2014-02-15 | 21 | No | DUKHCONP1AZ3ARGF3010, DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3010, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3025 | DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 21 | No | DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3090, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ARGF3070, DUKHCONP1AZ3ARGF3080, DUKHCONP1AZ3ACGF4610, DUKHCONP1AZ2ARGF3095, DUKHCONP1AZ3ACGF4610, DUKHCONP1AZ3ARGF3085, DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3070, DUKHCONP1AZ3ARGF3080, DUKHCONP1AZ3ARGF3090, DUKHCONP1AZ3ARGF3085 | DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 18 | No | DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ELGF4010, DUKHCONP1AZ2ARGF3045, DUKHCONP1AZ3ELGF4010, DUKHCONP1AZ3ARGF3025 | DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ4ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-12-10 | 2014-01-04 | 2013-12-10 | 2014-01-04 | 26 | No | DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ3ARGF3005 | DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-02-05 | 2014-03-01 | 2014-02-05 | 2014-03-01 | 21 | No | DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3025 | DUKHCONP1AZ3ARGF3065, DUKHCONP1AZ3ARGF3085, DUKHCONP1AZ3ARGF3065, DUKHCONP1AZ3ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 18 | No | DUKHCONP1AZ2ARGF3060, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ACGF4600, DUKHCONP1AZ3ACGF4600 | DUKHCONP1AZ3ELGF4030, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ3ELGF4030, DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3PLGF4320, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ACGF4605, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ3PLGF4320, DUKHCONP1AZ3ELGF4020, DUKHCONP1AZ3ACGF4605, DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ3ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-03-17 | 2014-04-02 | 2014-03-17 | 2014-04-02 | 21 | No | DUKHCONP1AZ3ARGF3075, DUKHCONP1AZ3ARGF3075 | DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-12-19 | 2014-01-16 | 2013-12-19 | 2014-01-16 | 32 | No | DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ2ARGF3030, DUKHCONP1AZ3ARGF3005 | DUKHCONP1AZ4ARGF3030, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-12-02 | 2013-12-31 | 2013-12-02 | 2013-12-31 | 18 | No | DUKHCONP1AZ3ARGF3000, DUKHCONP1AZ2ARGF3005, DUKHCONP1AZ3ELGF4000, DUKHCONP1AZ3ELGF4000, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3ARGF3000 | DUKHCONP1AZ3ARGF3015, DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ3ARGF3010, DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ3ACGF4600, DUKHCONP1AZ3ARGF3015, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ3ACGF4600, DUKHCONP1AZ3ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-01-01 | 2014-01-29 | 2014-01-01 | 2014-01-29 | 18 | No | DUKHCONP1AZ3ARGF3010, DUKHCONP1AZ3ARGF3010, DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ2ARGF3025 | DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-03-12 | 2014-04-03 | 2014-03-12 | 2014-04-03 | 26 | No | DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ3ARGF3075, DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ3ARGF3075 | DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-01-21 | 2014-02-06 | 2014-01-21 | 2014-02-06 | 23 | No | DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ3ARGF3010, DUKHCONP1AZ3ARGF3010 | DUKHCONP1AZ3ARGF3065, DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3040, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-12-21 | 2014-01-06 | 2013-12-21 | 2014-01-06 | 18 | No | DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ2ARGF3015, DUKHCONP1AZ3ARGF3005 | DUKHCONP1AZ4ARGF3015, DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-02-20 | 2014-03-09 | 2014-02-20 | 2014-03-09 | 21 | No | DUKHCONP1AZ3ARGF3035, DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ3ARGF3050, DUKHCONP1AZ2ARGF3065, DUKHCONP1AZ3ARGF3035 | DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ3ARGF3070, DUKHCONP1AZ3ARGF3070, DUKHCONP1AZ3PLGF4315, DUKHCONP1AZ3PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.20 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2013-12-23 | 2014-05-18 | 2013-12-23 | 2014-05-18 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ3ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-03-27 | 2014-04-19 | 2014-03-27 | 2014-04-19 | 0 | Yes | DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ2ARFF3370 | DUKHCONP1AZ4ARFF3370, DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ3ARFF3380, DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ3ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-04-03 | 2014-04-26 | 2014-04-03 | 2014-04-26 | 4 | No | DUKHCONP1AZ3ARFF3370, DUKHCONP1AZ3ARFF3370 | DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3300 | Block work | 25 | 25 | 0% | 2013-12-23 | 2014-01-20 | 2013-12-23 | 2014-01-20 | 0 | Yes | DUKHCONP1AZ3STFF2035, DUKHCONP1AZ2ARFF3300, DUKHCONP1AZ3STFF2020, DUKHCONP1AZ3STFF2020, DUKHCONP1AZ3STFF2035 | DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ3ELFF4035, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ELFF4035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 0 | Yes | DUKHCONP1AZ2ARFF3375, DUKHCONP1AZ3ARFF3370, DUKHCONP1AZ3ARFF3370 | DUKHCONP1AZ3ARFF3385, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3385, DUKHCONP1AZ4ARFF3375, DUKHCONP1AZ3ARFF3390, DUKHCONP1AZ3ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 0 | Yes | DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ3ARFF3315, DUKHCONP1AZ3ARFF3315, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ2ARFF3320, DUKHCONP1AZ3PLFF4330 | DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ3ARFF3325, DUKHCONP1AZ3ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 | Yes | DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3380, DUKHCONP1AZ3ARFF3390, DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3380, DUKHCONP1AZ3ARFF3330, DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ3ARFF3385, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3390, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ2ARFF3395, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ARFF3385, DUKHCONP1AZ3ARFF3330 | DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-03-05 | 2014-03-27 | 2014-03-05 | 2014-03-27 | 0 | Yes | DUKHCONP1AZ2ARFF3345, DUKHCONP1AZ3ELFF4045, DUKHCONP1AZ3ARFF3330, DUKHCONP1AZ3ARFF3330, DUKHCONP1AZ3ARFF3325, DUKHCONP1AZ3ARFF3325, DUKHCONP1AZ3ELFF4045 | DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ4ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-01-25 | 2014-02-18 | 2014-01-25 | 2014-02-18 | 12 | No | DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ARFF3305 | DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ3ARFF3325, DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ3ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-03-13 | 2014-04-05 | 2014-03-13 | 2014-04-05 | 2 | No | DUKHCONP1AZ3ARFF3325, DUKHCONP1AZ3ARFF3325 | DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3385, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-03-12 | 2014-04-09 | 2014-03-12 | 2014-04-09 | 0 | Yes | DUKHCONP1AZ3ACFF4615, DUKHCONP1AZ3ACFF4615, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ2ARFF3360 | DUKHCONP1AZ3PLFF4340, DUKHCONP1AZ3ELFF4055, DUKHCONP1AZ3ELFF4055, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ3PLFF4340, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ACFF4620, DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ3ELFF4050, DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ3ELFF4050, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ3ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-04-14 | 2014-05-06 | 2014-04-14 | 2014-05-06 | 0 | Yes | DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3375 | DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-04-14 | 2014-05-06 | 2014-04-14 | 2014-05-06 | 1 | No | DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ3ARFF3375 | DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 14 | No | DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ARFF3305 | DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 0 | Yes | DUKHCONP1AZ2ARFF3305, DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ3ELFF4035, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ3ELFF4035 | DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ3ARFF3310, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ3ARFF3330, DUKHCONP1AZ3ARFF3315, DUKHCONP1AZ3ACFF4615, DUKHCONP1AZ3ARFF3315, DUKHCONP1AZ3ARFF3330, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ3ARFF3310, DUKHCONP1AZ3ACFF4615 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 0 | Yes | DUKHCONP1AZ2ARFF3325, DUKHCONP1AZ3ARFF3320, DUKHCONP1AZ3ARFF3310, DUKHCONP1AZ3ARFF3310, DUKHCONP1AZ3ARFF3320 | DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ4ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-03-10 | 2014-03-26 | 2014-03-10 | 2014-03-26 | 8 | No | DUKHCONP1AZ3ARFF3310, DUKHCONP1AZ3ARFF3325, DUKHCONP1AZ3ARFF3310, DUKHCONP1AZ3ARFF3325 | DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-02-05 | 2014-02-23 | 2014-02-05 | 2014-02-23 | 0 | Yes | DUKHCONP1AZ2ARFF3315, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ARFF3305 | DUKHCONP1AZ4ARFF3315, DUKHCONP1AZ3ARFF3320, DUKHCONP1AZ3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-03-27 | 2014-04-13 | 2014-03-27 | 2014-04-13 | 0 | Yes | DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3350, DUKHCONP1AZ3ARFF3335, DUKHCONP1AZ2ARFF3365 | DUKHCONP1AZ3PLFF4335, DUKHCONP1AZ3ARFF3370, DUKHCONP1AZ3ARFF3370, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3PLFF4335, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ4ARFF3365 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.20 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-01-06 | 2014-03-12 | 2014-01-06 | 2014-03-12 | 57 |  |  |  | 0 | 0
DUKHCONP1AZ3ARRF3600 | Block work | 20 | 20 | 0% | 2014-01-06 | 2014-01-28 | 2014-01-06 | 2014-01-28 | 52 | No | DUKHCONP1AZ2ARRF3600, DUKHCONP1AZ3STRF2055, DUKHCONP1AZ3STRF2055 | DUKHCONP1AZ4ARRF3600, DUKHCONP1AZ3ARRF3605, DUKHCONP1AZ3ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-02-24 | 2014-03-12 | 2014-02-24 | 2014-03-12 | 57 | No | DUKHCONP1AZ3ARRF3695, DUKHCONP1AZ3ARRF3695 | DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-01-28 | 2014-02-15 | 2014-01-28 | 2014-02-15 | 57 | No | DUKHCONP1AZ3ARRF3605, DUKHCONP1AZ3ARRF3605 | DUKHCONP1AZ3ARRF3695, DUKHCONP1AZ3ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-02-05 | 2014-03-01 | 2014-02-05 | 2014-03-01 | 57 | No | DUKHCONP1AZ3ARRF3610, DUKHCONP1AZ3ARRF3610 | DUKHCONP1AZ3ARRF3620, DUKHCONP1AZ3AREL3680, DUKHCONP1AZ3AREL3680, DUKHCONP1AZ3ARRF3620 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-01-14 | 2014-02-05 | 2014-01-14 | 2014-02-05 | 52 | No | DUKHCONP1AZ3ARRF3600, DUKHCONP1AZ3ARRF3600 | DUKHCONP1AZ3ARRF3610, DUKHCONP1AZ3PLRF4345, DUKHCONP1AZ3ARRF3610, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ3PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.20 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-01-28 | 2014-04-17 | 2014-01-28 | 2014-04-17 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.20 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-02-12 | 2014-04-17 | 2014-02-12 | 2014-04-17 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ3ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 21 | No | DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3ARRF3645 | DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-04-01 | 2014-04-17 | 2014-04-01 | 2014-04-17 | 26 | No | DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3ARRF3655 | DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 21 | No | DUKHCONP1AZ3ARRF3635, DUKHCONP1AZ3ARRF3635 | DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-03-20 | 2014-04-12 | 2014-03-20 | 2014-04-12 | 21 | No | DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3ARRF3650, DUKHCONP1AZ3ARRF3650, DUKHCONP1AZ2ARRF3655, DUKHCONP1AZ3ARRF3645 | DUKHCONP1AZ3ARRF3660, DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3ARRF3660, DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 21 | No | DUKHCONP1AZ3ARRF3630, DUKHCONP1AZ3ARRF3630 | DUKHCONP1AZ3ARRF3640, DUKHCONP1AZ3ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 21 | No | DUKHCONP1AZ3STRF2065, DUKHCONP1AZ2ARRF3630, DUKHCONP1AZ3STRF2060, DUKHCONP1AZ3STRF2065, DUKHCONP1AZ3STRF2060 | DUKHCONP1AZ4ARRF3630, DUKHCONP1AZ3ARRF3635, DUKHCONP1AZ3ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ3ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 21 | No | DUKHCONP1AZ3ARRF3640, DUKHCONP1AZ3ARRF3640 | DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ3ARRF3650, DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3ARRF3650, DUKHCONP1AZ3ARRF3655 | 0 | 0 | ROOF
DHBL.K30.L15.20 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-01-28 | 2014-03-22 | 2014-01-28 | 2014-03-22 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ3AREL3680 | External Painting | 20 | 20 | 0% | 2014-02-27 | 2014-03-22 | 2014-02-27 | 2014-03-22 | 49 | No | DUKHCONP1AZ3AREL3670, DUKHCONP1AZ2AREL3680, DUKHCONP1AZ3ARRF3695, DUKHCONP1AZ3AREL3670, DUKHCONP1AZ3ARRF3695 | DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ4AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1AZ3AREL3665 | External Plastering | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 47 | No | DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ARRF3605, DUKHCONP1AZ3STRF2065, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ2AREL3665, DUKHCONP1AZ3STRF2065 | DUKHCONP1AZ3AREL3670, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ4AREL3665, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3AREL3670 | 0 | 0 | ELEVATION
DUKHCONP1AZ3AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 49 | No | DUKHCONP1AZ2AREL3670, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ3AREL3665 | DUKHCONP1AZ3AREL3680, DUKHCONP1AZ3AREL3680, DUKHCONP1AZ4AREL3670 | 0 | 0 | ELEVATION
DHBL.K30.L15.20 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-07-31 | 2014-05-17 | 2013-07-31 | 2014-05-17 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.20 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2013-11-16 | 2014-05-17 | 2013-11-16 | 2014-05-17 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.20 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-11-16 | 2014-03-26 | 2013-11-16 | 2014-03-26 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ3ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-11-27 | 2013-12-21 | 2013-11-27 | 2013-12-21 | 45 | No | DUKHCONP1AZ3ELGF4000, DUKHCONP1AZ2ELGF4005, DUKHCONP1AZ3ELGF4000 | DUKHCONP1AZ4ELGF4005, DUKHCONP1AZ3ELGF4010, DUKHCONP1AZ3ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 27 | No | DUKHCONP1AZ3ARGF3000, DUKHCONP1AZ3ARGF3000 | DUKHCONP1AZ3ELGF4005, DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ3ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 30 | No | DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ2ELGF4015, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3060 | DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3ELFF4055, DUKHCONP1AZ3ELFF4055, DUKHCONP1AZ4ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-02-15 | 2014-03-09 | 2014-02-15 | 2014-03-09 | 18 | No | DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ELGF4010, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ELGF4010 | DUKHCONP1AZ3ELGF4030, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ3ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 25 | No | DUKHCONP1AZ2ELGF4025, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ELGF4020, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ELGF4020 | DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ3ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 18 | No | DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ELGF4020, DUKHCONP1AZ2ELGF4030, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ELGF4020 | DUKHCONP1AZ4ELGF4030, DUKHCONP1AZ3ELFF4050, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 45 | No | DUKHCONP1AZ3ELGF4005, DUKHCONP1AZ3ELGF4005 | DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ARGF3045, DUKHCONP1AZ3ELGF4020, DUKHCONP1AZ3ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.20 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2013-12-29 | 2014-04-29 | 2013-12-29 | 2014-04-29 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ3ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-01-09 | 2014-02-01 | 2014-01-09 | 2014-02-01 | 29 | No | DUKHCONP1AZ3ELFF4035, DUKHCONP1AZ3ELFF4035 | DUKHCONP1AZ3ELFF4045, DUKHCONP1AZ3ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 11 | No | DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ3ARFF3300 | DUKHCONP1AZ3ELFF4040, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ELFF4040, DUKHCONP1AZ3ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-03-20 | 2014-04-17 | 2014-03-20 | 2014-04-17 | 1 | No | DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ2ELFF4055 | DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ4ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-03-24 | 2014-04-15 | 2014-03-24 | 2014-04-15 | 3 | No | DUKHCONP1AZ3ELFF4045, DUKHCONP1AZ3ELFF4045, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ2ELFF4060, DUKHCONP1AZ3ARFF3360 | DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ4ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 1 | No | DUKHCONP1AZ2ELFF4065, DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ELGF4025 | DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 11 | No | DUKHCONP1AZ3ELGF4030, DUKHCONP1AZ3MSEX5010, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ELGF4030 | DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 27 | No | DUKHCONP1AZ3ELFF4040, DUKHCONP1AZ2ELFF4045, DUKHCONP1AZ3ELFF4040 | DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3ARFF3345, DUKHCONP1AZ4ELFF4045 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.20 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-04-15 | 2014-05-17 | 2014-04-15 | 2014-05-17 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ3ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-04-15 | 2014-05-05 | 2014-04-15 | 2014-05-05 | 1 | No | DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3ELFF4045, DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3ELFF4045, DUKHCONP1AZ3ELFF4050, DUKHCONP1AZ3ELFF4050 | DUKHCONP1AZ3ELRF4075, DUKHCONP1AZ3ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ3ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-04-21 | 2014-05-17 | 2014-04-21 | 2014-05-17 | 1 | No | DUKHCONP1AZ3ELRF4070, DUKHCONP1AZ3ELRF4070 | DUKHCONP1AZ3ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.20 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-07-31 | 2014-05-17 | 2013-07-31 | 2014-05-17 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.20 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-07-31 | 2014-03-26 | 2013-07-31 | 2014-03-26 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-07-31 | 2013-08-21 | 2013-07-31 | 2013-08-21 | 0 | Yes | DUKHCONP1AZ3STUG1040, DUKHCONP1AZ3STUG1040 | DUKHCONP1AZ3STUG1045, DUKHCONP1AZ3STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-11-26 | 2013-12-16 | 2013-11-26 | 2013-12-16 | 39 | No | DUKHCONP1AZ3ARGF3000, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ3ARGF3000 | DUKHCONP1AZ3PLGF4315, DUKHCONP1AZ3MSEX5000, DUKHCONP1AZ3MSEX5000, DUKHCONP1AZ3PLGF4315, DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-11-26 | 2013-12-16 | 2013-11-26 | 2013-12-16 | 18 | No | DUKHCONP1AZ3ARGF3000, DUKHCONP1AZ2PLGF4305, DUKHCONP1AZ3ARGF3000 | DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ3ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-03-10 | 2014-03-26 | 2014-03-10 | 2014-03-26 | 45 | No | DUKHCONP1AZ2PLGF4320, DUKHCONP1AZ3PLGF4315, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3PLGF4315, DUKHCONP1AZ3ARGF3060 | DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ4PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 45 | No | DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ2PLGF4315, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3ARGF3065, DUKHCONP1AZ3ARGF3065 | DUKHCONP1AZ3PLGF4320, DUKHCONP1AZ4PLGF4315, DUKHCONP1AZ3PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.20 .20 .15 .15 FIRST FLOORS |  | 90 | 90 | 0% | 2014-01-09 | 2014-04-24 | 2014-01-09 | 2014-04-24 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ3PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-01-09 | 2014-01-29 | 2014-01-09 | 2014-01-29 | 22 | No | DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ3PLFF4325, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ2PLFF4330 | DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3PLFF4335, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ3ARFF3320, DUKHCONP1AZ3PLFF4335, DUKHCONP1AZ3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-01-09 | 2014-01-29 | 2014-01-09 | 2014-01-29 | 0 | Yes | DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ3ARFF3300 | DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ARFF3320, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-04-08 | 2014-04-24 | 2014-04-08 | 2014-04-24 | 5 | No | DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3PLFF4335, DUKHCONP1AZ2PLFF4340, DUKHCONP1AZ3PLFF4335 | DUKHCONP1AZ4PLFF4340, DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ3PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-03-27 | 2014-04-19 | 2014-03-27 | 2014-04-19 | 5 | No | DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3ARFF3365, DUKHCONP1AZ3PLFF4330 | DUKHCONP1AZ3PLFF4340, DUKHCONP1AZ3PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.20 .20 .15 .20 ROOF |  | 93 | 93 | 0% | 2014-01-28 | 2014-05-17 | 2014-01-28 | 2014-05-17 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ3PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-01-28 | 2014-02-15 | 2014-01-28 | 2014-02-15 | 56 | No | DUKHCONP1AZ3ARRF3605, DUKHCONP1AZ3ARRF3605 | DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ3PLRF4350 | 0 | 0 | ROOF
DUKHCONP1AZ3PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-03-15 | 2014-03-31 | 2014-03-15 | 2014-03-31 | 26 | No | DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ3PLRF4345, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3PLRF4345, DUKHCONP1AZ2PLRF4350 | DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ3PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ3PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 1 | No | DUKHCONP1AZ2PLRF4355, DUKHCONP1AZ3PLRF4345, DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3PLRF4345, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3PLFF4340, DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3PLFF4340 | DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ3PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L15.20 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2013-12-16 | 2014-05-14 | 2013-12-16 | 2014-05-14 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.20 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-12-16 | 2014-03-24 | 2013-12-16 | 2014-03-24 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ3ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-03-02 | 2014-03-24 | 2014-03-02 | 2014-03-24 | 32 | No | DUKHCONP1AZ3ACGF4605, DUKHCONP1AZ2ACGF4610, DUKHCONP1AZ3ACGF4605 | DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ3ACRF4635, DUKHCONP1AZ3ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 32 | No | DUKHCONP1AZ2ACGF4605, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ACGF4600, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ACGF4600 | DUKHCONP1AZ3ACGF4610, DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ3ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ3ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-12-16 | 2014-01-08 | 2013-12-16 | 2014-01-08 | 49 | No | DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ2ACGF4600, DUKHCONP1AZ3ARGF3005 | DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ3ACGF4605, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ARGF3055, DUKHCONP1AZ3ACGF4605, DUKHCONP1AZ3ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.20 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-01-30 | 2014-05-03 | 2014-01-30 | 2014-05-03 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ3ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-04-10 | 2014-05-03 | 2014-04-10 | 2014-05-03 | 2 | No | DUKHCONP1AZ3ACFF4620, DUKHCONP1AZ3ACFF4620, DUKHCONP1AZ2ACFF4625 | DUKHCONP1AZ3ACRF4635, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ3ACRF4635 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-03-20 | 2014-04-17 | 2014-03-20 | 2014-04-17 | 2 | No | DUKHCONP1AZ3ACFF4615, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ACFF4615, DUKHCONP1AZ2ACFF4620, DUKHCONP1AZ3ARFF3360 | DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ4ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ3ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 27 | No | DUKHCONP1AZ2ACFF4615, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ3ARFF3305 | DUKHCONP1AZ3ACFF4620, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ARFF3360, DUKHCONP1AZ3ACFF4620, DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ3ACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.20 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-03-05 | 2014-05-14 | 2014-03-05 | 2014-05-14 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ3ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 3 | No | DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ2ACRF4635, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ3ACGF4610, DUKHCONP1AZ3ACGF4610, DUKHCONP1AZ3ACFF4625 | DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ4ACRF4635 | 0 | 0 | ROOF
DUKHCONP1AZ3ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 34 | No | DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3ACGF4600, DUKHCONP1AZ3ACFF4615, DUKHCONP1AZ3ACGF4600, DUKHCONP1AZ2ACRF4630, DUKHCONP1AZ3ARRF3645, DUKHCONP1AZ3ACFF4615 | DUKHCONP1AZ3ACRF4635, DUKHCONP1AZ3ACRF4635, DUKHCONP1AZ4ACRF4630 | 0 | 0 | ROOF
DHBL.K30.L15.20 .25 EXTERNAL WORKS |  | 136 | 136 | 0% | 2013-12-24 | 2014-06-01 | 2013-12-24 | 2014-06-01 | 103 |  |  |  | 0 | 0
DHBL.K30.L15.20 .25 .10 MISCELLANEOUS |  | 136 | 136 | 0% | 2013-12-24 | 2014-06-01 | 2013-12-24 | 2014-06-01 | 103 |  |  |  | 0 | 0
DUKHCONP1AZ3MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 103 | No | DUKHCONI1AZ2BWGL5325, DUKHCONP1AZ2MSEX5335 | DUKHCONP1AZ4MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ3MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-01-07 | 2014-02-04 | 2014-01-07 | 2014-02-04 | 33 | No | DUKHCONP1AZ3MSEX5000, DUKHCONP1AZ3MSEX5000 | DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3MSEX5015, DUKHCONP1AZ3MSEX5015, DUKHCONP1AZ3PLTC8005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ3MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 16 | No | DUKHCONP1AZ3STRF2055, DUKHCONP1AZ2MSEX5020, DUKHCONP1AZ3STRF2055 | DUKHCONP1AZ4MSEX5020, DUKHCONP1AZ3HDEX5090, DUKHCONP1AZ3HDEX5090, DUKHCONP1AZ3MSEX5025, DUKHCONP1AZ3MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ3MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 33 | No | DUKHCONP1AZ3MSEX5005, DUKHCONP1AZ3MSEX5005 | DUKHCONP1AZ3MSEX5010, DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ3WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ3MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 33 | No | DUKHCONP1AZ3STRF2055, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3PLGF4310, DUKHCONP1AZ3STRF2055 | DUKHCONP1AZ3MSEX5005, DUKHCONP1AZ3MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ3MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-03-04 | 2014-03-26 | 2014-03-04 | 2014-03-26 | 19 | No | DUKHCONP1AZ3MSEX5020, DUKHCONP1AZ3MSEX5020 | DUKHCONP1AZ3WEEX5050, DUKHCONP1AZ3WEEX5060 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ3MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 33 | No | DUKHCONP1AZ3MSEX5015 | DUKHCONP1AZ3ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.20 .25 .15 WATER TANK ENCLOSURE |  | 75 | 75 | 0% | 2014-02-09 | 2014-05-07 | 2014-02-09 | 2014-05-07 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ3WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 18 | No | DUKHCONP1AZ3WEEX5035, DUKHCONP1AZ3WEEX5035 | DUKHCONP1AZ3WEEX5045, DUKHCONP1AZ3WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ3WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 18 | No | DUKHCONP1AZ3WEEX5030, DUKHCONP1AZ3WEEX5030 | DUKHCONP1AZ3WEEX5040, DUKHCONP1AZ3WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ3WEEX5030 | Excavation | 20 | 20 | 0% | 2014-02-09 | 2014-03-04 | 2014-02-09 | 2014-03-04 | 18 | No | DUKHCONP1AZ2WEEX5030, DUKHCONP1AZ3STRF2055, DUKHCONP1AZ3STRF2055 | DUKHCONP1AZ3WEEX5035, DUKHCONP1AZ4WEEX5030, DUKHCONP1AZ3WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ3WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 18 | No | DUKHCONP1AZ3WEEX5040, DUKHCONP1AZ3WEEX5040 | DUKHCONP1AZ3WEEX5050, DUKHCONP1AZ3WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ3WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-04-09 | 2014-05-07 | 2014-04-09 | 2014-05-07 | 9 | No | DUKHCONP1AZ2WEEX5065, DUKHCONP1AZ3WEEX5060, DUKHCONP1AZ3MSEX5015, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3WEEX5060, DUKHCONP1AZ3MSEX5015 | DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ4WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ3WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 18 | No | DUKHCONP1AZ3WEEX5045, DUKHCONP1AZ3MSEX5025, DUKHCONP1AZ3WEEX5045 | DUKHCONP1AZ3WEEX5060, DUKHCONP1AZ3WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ3WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 10 | No | DUKHCONP1AZ3WEEX5050, DUKHCONP1AZ2WEEX5060, DUKHCONP1AZ3WEEX5050, DUKHCONP1AZ3MSEX5025 | DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ4WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.20 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-03-01 | 2014-04-10 | 2014-03-01 | 2014-04-10 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ3HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-03-12 | 2014-04-03 | 2014-03-12 | 2014-04-03 | 16 | No | DUKHCONP1AZ3HDEX5090, DUKHCONP1AZ3HDEX5090 | DUKHCONP1AZ3HDEX5100, DUKHCONP1AZ3HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ3HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 16 | No | DUKHCONP1AZ3HDEX5095, DUKHCONP1AZ3HDEX5095 | DUKHCONP1AZ3SLEX5105, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3SLEX5105, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ3ELTC8010 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ3HDEX5090 | kerb works | 20 | 20 | 0% | 2014-03-01 | 2014-03-23 | 2014-03-01 | 2014-03-23 | 16 | No | DUKHCONP1AZ3MSEX5020, DUKHCONP1AZ3MSEX5020, DUKHCONP1AZ2HDEX5090 | DUKHCONP1AZ3HDEX5095, DUKHCONP1AZ4HDEX5090, DUKHCONP1AZ3HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.20 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-03-25 | 2014-04-29 | 2014-03-25 | 2014-04-29 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ3SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-03-25 | 2014-04-22 | 2014-03-25 | 2014-04-22 | 16 | No | DUKHCONP1AZ3HDEX5100, DUKHCONP1AZ3HDEX5100 | DUKHCONP1AZ3SLEX5110, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ3SLEX5110, DUKHCONP1AZ3ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ3SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 16 | No | DUKHCONP1AZ3SLEX5105, DUKHCONP1AZ3SLEX5105 | DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ3ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.20 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ3ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 0 | Yes | DUKHCONP1AZ3ARRF3660, DUKHCONP1AZ3SLEX5110, DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ3AREL3680, DUKHCONP1AZ3ARRF3620, DUKHCONP1AZ3MSEX5005, DUKHCONP1AZ3ACRF4635, DUKHCONP1AZ3HDEX5100, DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3SLEX5105, DUKHCONP1AZ2ACTC8000, DUKHCONP1AZ3ARFF3395 | DUKHCONP1AZ4ACTC8000, DUKHHANP1AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 0 | Yes | DUKHCONP1AZ3ARRF3660, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ3ELGF4015, DUKHCONP1AZ3ELFF4055, DUKHCONP1AZ3ELFF4050, DUKHCONP1AZ3SLEX5105, DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ3ARRF3620, DUKHCONP1AZ3AREL3680, DUKHCONP1AZ3SLEX5110, DUKHCONP1AZ3ELRF4075, DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3MSEX5005, DUKHCONP1AZ3ELGF4030, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3HDEX5100, DUKHCONP1AZ3ELFF4065 | DUKHCONP1AZ4ELTC8010, DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 0 | Yes | DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ3ARRF3620, DUKHCONP1AZ3SLEX5105, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ3SLEX5110, DUKHCONP1AZ3PLGF4320, DUKHCONP1AZ3ARRF3660, DUKHCONP1AZ2PLTC8005, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ3AREL3680, DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ3HDEX5100, DUKHCONP1AZ3MSEX5005 | DUKHCONP1AZ4PLTC8005, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.25 ZONE - 4 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-05-13 | 2014-07-15 | 2013-05-13 | 2014-07-15 | 72 |  |  |  | 0 | 0
DHBL.K30.L15.25 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-05-13 | 2014-02-22 | 2013-05-13 | 2014-02-22 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.25 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-05-13 | 2013-10-09 | 2013-05-13 | 2013-10-09 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.25 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-05-13 | 2013-10-09 | 2013-05-13 | 2013-10-09 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ4STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-07-21 | 2013-08-21 | 2013-07-21 | 2013-08-21 | 0 | Yes | DUKHCONP1AZ4STUG1030, DUKHCONP1AZ4STUG1030, DUKHCONP1AZ3STUG1035 | DUKHCONP1AZ4STUG1040, DUKHCONP1AZ5STUG1035, DUKHCONP1AZ4STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-06-18 | 2013-07-10 | 2013-06-18 | 2013-07-10 | 0 | Yes | DUKHCONP1AZ4STUG1015, DUKHCONP1AZ4STUG1015 | DUKHCONP1AZ4STUG1025, DUKHCONP1AZ4STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-08-06 | 2013-09-07 | 2013-08-06 | 2013-09-07 | 0 | Yes | DUKHCONP1AZ4STUG1035, DUKHCONP1AZ4STUG1035 | DUKHCONP1AZ4STUG1045, DUKHCONP1AZ4PLUG4300, DUKHCONP1AZ4STUG1045, DUKHCONP1AZ4PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-06-27 | 2013-07-25 | 2013-06-27 | 2013-07-25 | 0 | Yes | DUKHCONP1AZ4STUG1020, DUKHCONP1AZ3STUG1025, DUKHCONP1AZ4STUG1020 | DUKHCONP1AZ4STUG1030, DUKHCONP1AZ4STUG1030, DUKHCONP1AZ5STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-09-11 | 2013-10-09 | 2013-09-11 | 2013-10-09 | 0 | Yes | DUKHCONP1AZ3STUG1045, DUKHCONP1AZ4PLUG4300, DUKHCONP1AZ4STUG1040, DUKHCONP1AZ4STUG1040, DUKHCONP1AZ4PLUG4300 | DUKHCONP1AZ5STUG1045, DUKHCONP1AZ4STGF2000, DUKHCONP1AZ4STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-05-25 | 2013-06-19 | 2013-05-25 | 2013-06-19 | 0 | Yes | DUKHCONP1AZ4STUG1000, DUKHCONP1AZ4STUG1000 | DUKHCONP1AZ4STUG1010, DUKHCONP1AZ4STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-05-28 | 2013-06-23 | 2013-05-28 | 2013-06-23 | 0 | Yes | DUKHCONP1AZ4STUG1005, DUKHCONP1AZ4STUG1005 | DUKHCONP1AZ4STUG1015, DUKHCONP1AZ4STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-05-13 | 2013-06-10 | 2013-05-13 | 2013-06-10 | 0 | Yes | DUKHCONP1AZ3STUG1000, DUKHCONP1AGNSP005000 | DUKHCONP1AZ4STUG1005, DUKHCONP1AZ5STUG1000, DUKHCONP1AZ4STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-06-03 | 2013-07-01 | 2013-06-03 | 2013-07-01 | 0 | Yes | DUKHCONP1AZ4STUG1010, DUKHCONP1AZ4STUG1010 | DUKHCONP1AZ4STUG1020, DUKHCONP1AZ4STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ4STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-07-07 | 2013-08-04 | 2013-07-07 | 2013-08-04 | 0 | Yes | DUKHCONP1AZ4STUG1025, DUKHCONP1AZ4STUG1025 | DUKHCONP1AZ4STUG1035, DUKHCONP1AZ4STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.25 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2013-09-28 | 2014-02-22 | 2013-09-28 | 2014-02-22 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.25 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-09-28 | 2013-11-24 | 2013-09-28 | 2013-11-24 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ4STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-11-09 | 2013-11-24 | 2013-11-09 | 2013-11-24 | 2 | No | DUKHCONP1AZ4STGF2010, DUKHCONP1AZ4STGF2010, DUKHCONP1AZ3STGF2015 | DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ4STFF2020, DUKHCONP1AZ5STGF2015, DUKHCONP1AZ4STFF2020, DUKHCONP1AZ4ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-10-23 | 2013-11-20 | 2013-10-23 | 2013-11-20 | 2 | No | DUKHCONP1AZ4STGF2005, DUKHCONP1AZ4STGF2005 | DUKHCONP1AZ4STGF2015, DUKHCONP1AZ4STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-10-06 | 2013-11-04 | 2013-10-06 | 2013-11-04 | 2 | No | DUKHCONP1AZ4STGF2000, DUKHCONP1AZ4STGF2000 | DUKHCONP1AZ4STGF2010, DUKHCONP1AZ4STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-09-28 | 2013-10-28 | 2013-09-28 | 2013-10-28 | 0 | Yes | DUKHCONP1AZ3STGF2000, DUKHCONP1AZ4STUG1045, DUKHCONP1AZ4STUG1045 | DUKHCONP1AZ4STGF2005, DUKHCONP1AZ4STGF2005, DUKHCONP1AZ5STGF2000 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.25 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2013-11-11 | 2014-01-07 | 2013-11-11 | 2014-01-07 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ4STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-12-23 | 2014-01-07 | 2013-12-23 | 2014-01-07 | 4 | No | DUKHCONP1AZ3STFF2035, DUKHCONP1AZ4STFF2030, DUKHCONP1AZ4STFF2030 | DUKHCONP1AZ4STRF2040, DUKHCONP1AZ5STFF2035, DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ4STRF2040, DUKHCONP1AZ4ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 4 | No | DUKHCONP1AZ4STFF2025, DUKHCONP1AZ4STFF2025 | DUKHCONP1AZ4STFF2035, DUKHCONP1AZ4STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-11-20 | 2013-12-17 | 2013-11-20 | 2013-12-17 | 4 | No | DUKHCONP1AZ4STFF2020, DUKHCONP1AZ4STFF2020 | DUKHCONP1AZ4STFF2030, DUKHCONP1AZ4STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-11-11 | 2013-12-09 | 2013-11-11 | 2013-12-09 | 2 | No | DUKHCONP1AZ4STGF2015, DUKHCONP1AZ4STGF2015, DUKHCONP1AZ3STFF2020 | DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ5STFF2020, DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ4STFF2025, DUKHCONP1AZ4STFF2025 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.25 .10 .15 .20 ROOF |  | 50 | 50 | 0% | 2013-12-25 | 2014-02-22 | 2013-12-25 | 2014-02-22 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ4STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-12-29 | 2014-01-16 | 2013-12-29 | 2014-01-16 | 8 | No | DUKHCONP1AZ4STRF2040, DUKHCONP1AZ4STRF2040 | DUKHCONP1AZ4STRF2050, DUKHCONP1AZ4STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ4STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-12-25 | 2014-01-14 | 2013-12-25 | 2014-01-14 | 8 | No | DUKHCONP1AZ4STFF2035, DUKHCONP1AZ3STRF2040, DUKHCONP1AZ4STFF2035 | DUKHCONP1AZ5STRF2040, DUKHCONP1AZ4STRF2045, DUKHCONP1AZ4STRF2045 | 0 | 0 | ROOF
DUKHCONP1AZ4STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 56 | No | DUKHCONP1AZ4STRF2055, DUKHCONP1AZ4STRF2055 | DUKHCONP1AZ4STRF2065, DUKHCONP1AZ4ARRF3630, DUKHCONP1AZ4STRF2065, DUKHCONP1AZ4ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ4STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-01-23 | 2014-02-22 | 2014-01-23 | 2014-02-22 | 52 | No | DUKHCONP1AZ3STRF2065, DUKHCONP1AZ4STRF2060, DUKHCONP1AZ4STRF2060 | DUKHCONP1AZ5STRF2065, DUKHCONP1AZ4ARRF3630, DUKHCONP1AZ4AREL3665, DUKHCONP1AZ4ARRF3630, DUKHCONP1AZ4AREL3665 | 0 | 0 | ROOF
DUKHCONP1AZ4STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-01-11 | 2014-01-25 | 2014-01-11 | 2014-01-25 | 8 | No | DUKHCONP1AZ4STRF2050, DUKHCONP1AZ3STRF2055, DUKHCONP1AZ4STRF2050 | DUKHCONP1AZ4MSEX5000, DUKHCONP1AZ4MSEX5020, DUKHCONP1AZ4WEEX5030, DUKHCONP1AZ4ARRF3600, DUKHCONP1AZ4MSEX5000, DUKHCONP1AZ4STRF2060, DUKHCONP1AZ4MSEX5020, DUKHCONP1AZ4STRF2060, DUKHCONP1AZ4ARRF3600, DUKHCONP1AZ5STRF2055, DUKHCONP1AZ4WEEX5030 | 0 | 0 | ROOF
DUKHCONP1AZ4STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2013-12-31 | 2014-01-22 | 2013-12-31 | 2014-01-22 | 8 | No | DUKHCONP1AZ4STRF2045, DUKHCONP1AZ4STRF2045 | DUKHCONP1AZ4STRF2055, DUKHCONP1AZ4STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.25 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2013-12-09 | 2014-06-16 | 2013-12-09 | 2014-06-16 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.25 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2013-12-09 | 2014-06-16 | 2013-12-09 | 2014-06-16 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.25 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-12-09 | 2014-05-22 | 2013-12-09 | 2014-05-22 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ4ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-03-27 | 2014-04-13 | 2014-03-27 | 2014-04-13 | 21 | No | DUKHCONP1AZ3ARGF3070, DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ4ARGF3065 | DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3080, DUKHCONP1AZ5ARGF3070, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3075, DUKHCONP1AZ4ARGF3080, DUKHCONP1AZ4ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 21 | No | DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ4ARGF3045 | DUKHCONP1AZ4ELGF4020, DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ4ELGF4015, DUKHCONP1AZ4ELGF4020, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-04-03 | 2014-04-26 | 2014-04-03 | 2014-04-26 | 31 | No | DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ3ARGF3080, DUKHCONP1AZ4ARGF3070 | DUKHCONP1AZ5ARGF3080, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3000 | Block work | 25 | 25 | 0% | 2013-12-09 | 2014-01-07 | 2013-12-09 | 2014-01-07 | 18 | No | DUKHCONP1AZ4STGF2015, DUKHCONP1AZ3ARGF3000, DUKHCONP1AZ4STGF2015 | DUKHCONP1AZ4ELGF4000, DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ4PLGF4310, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ELGF4000, DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ4PLGF4310, DUKHCONP1AZ5ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-04-02 | 2014-04-24 | 2014-04-02 | 2014-04-24 | 21 | No | DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ3ARGF3075, DUKHCONP1AZ4ARGF3070 | DUKHCONP1AZ5ARGF3075, DUKHCONP1AZ4ARGF3090, DUKHCONP1AZ4ARGF3090, DUKHCONP1AZ4ARGF3085, DUKHCONP1AZ4ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 18 | No | DUKHCONP1AZ4ARGF3015, DUKHCONP1AZ4ARGF3015, DUKHCONP1AZ4PLGF4310, DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ3ARGF3020, DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ4PLGF4310 | DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-02-27 | 2014-03-16 | 2014-02-27 | 2014-03-16 | 21 | No | DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3010, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3010 | DUKHCONP1AZ4ARGF3050, DUKHCONP1AZ4ARGF3050, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 21 | No | DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ4ARGF3080, DUKHCONP1AZ4ARGF3085, DUKHCONP1AZ4ARGF3090, DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ4ARGF3080, DUKHCONP1AZ4ARGF3085, DUKHCONP1AZ4ARGF3030, DUKHCONP1AZ4ARGF3030, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ3ARGF3095, DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ARGF3090 | DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 18 | No | DUKHCONP1AZ4ARGF3030, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ELGF4010, DUKHCONP1AZ4ELGF4010, DUKHCONP1AZ4ARGF3030, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ3ARGF3045 | DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-01-09 | 2014-02-02 | 2014-01-09 | 2014-02-02 | 26 | No | DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ARGF3005 | DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 21 | No | DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3040 | DUKHCONP1AZ4ARGF3085, DUKHCONP1AZ4ARGF3085, DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ4ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 18 | No | DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ3ARGF3060, DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ4ACGF4600 | DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ4ELGF4030, DUKHCONP1AZ4ELGF4030, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ELGF4015, DUKHCONP1AZ4ELGF4020, DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ4PLGF4320, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ4PLGF4320, DUKHCONP1AZ4ELGF4015, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-04-15 | 2014-05-01 | 2014-04-15 | 2014-05-01 | 21 | No | DUKHCONP1AZ4ARGF3075, DUKHCONP1AZ4ARGF3075 | DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-01-18 | 2014-02-16 | 2014-01-18 | 2014-02-16 | 32 | No | DUKHCONP1AZ3ARGF3030, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ARGF3005 | DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ5ARGF3030, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-01-01 | 2014-01-29 | 2014-01-01 | 2014-01-29 | 18 | No | DUKHCONP1AZ4ELGF4000, DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ3ARGF3005, DUKHCONP1AZ4ELGF4000 | DUKHCONP1AZ4ARGF3010, DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ4ARGF3030, DUKHCONP1AZ4ARGF3015, DUKHCONP1AZ4ARGF3010, DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ4ARGF3030, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ4ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 18 | No | DUKHCONP1AZ4ARGF3010, DUKHCONP1AZ4ARGF3020, DUKHCONP1AZ3ARGF3025, DUKHCONP1AZ4ARGF3010, DUKHCONP1AZ4ARGF3020 | DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ4ARGF3050, DUKHCONP1AZ4ARGF3050, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-04-10 | 2014-05-03 | 2014-04-10 | 2014-05-03 | 26 | No | DUKHCONP1AZ4ARGF3050, DUKHCONP1AZ4ARGF3050, DUKHCONP1AZ4ARGF3075, DUKHCONP1AZ4ARGF3075 | DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-02-20 | 2014-03-09 | 2014-02-20 | 2014-03-09 | 23 | No | DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ4ARGF3010, DUKHCONP1AZ4ARGF3010, DUKHCONP1AZ4ARGF3025 | DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARGF3040, DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-01-19 | 2014-02-04 | 2014-01-19 | 2014-02-04 | 18 | No | DUKHCONP1AZ3ARGF3015, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ARGF3005 | DUKHCONP1AZ4ARGF3020, DUKHCONP1AZ4ARGF3020, DUKHCONP1AZ5ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-03-22 | 2014-04-07 | 2014-03-22 | 2014-04-07 | 21 | No | DUKHCONP1AZ3ARGF3065, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3050, DUKHCONP1AZ4ARGF3035, DUKHCONP1AZ4ARGF3050 | DUKHCONP1AZ4PLGF4315, DUKHCONP1AZ5ARGF3065, DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ4PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.25 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2014-01-21 | 2014-06-16 | 2014-01-21 | 2014-06-16 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ4ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-04-26 | 2014-05-18 | 2014-04-26 | 2014-05-18 | 0 | Yes | DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ3ARFF3370 | DUKHCONP1AZ4ARFF3380, DUKHCONP1AZ5ARFF3370, DUKHCONP1AZ4ARFF3380, DUKHCONP1AZ4ARFF3375, DUKHCONP1AZ4ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-05-03 | 2014-05-25 | 2014-05-03 | 2014-05-25 | 4 | No | DUKHCONP1AZ4ARFF3370, DUKHCONP1AZ4ARFF3370 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3300 | Block work | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 0 | Yes | DUKHCONP1AZ4STFF2020, DUKHCONP1AZ4STFF2020, DUKHCONP1AZ3ARFF3300, DUKHCONP1AZ4STFF2035, DUKHCONP1AZ4STFF2035 | DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4PLFF4325, DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4PLFF4325, DUKHCONP1AZ4ELFF4035, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4ELFF4035, DUKHCONP1AZ5ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-05-01 | 2014-05-29 | 2014-05-01 | 2014-05-29 | 0 | Yes | DUKHCONP1AZ3ARFF3375, DUKHCONP1AZ4ARFF3370, DUKHCONP1AZ4ARFF3370 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3390, DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ4ARFF3390, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3385, DUKHCONP1AZ4ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 0 | Yes | DUKHCONP1AZ4ARFF3315, DUKHCONP1AZ3ARFF3320, DUKHCONP1AZ4PLFF4325, DUKHCONP1AZ4PLFF4325, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4ARFF3315, DUKHCONP1AZ4PLFF4330 | DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ5ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 0 | Yes | DUKHCONP1AZ4ARFF3350, DUKHCONP1AZ4ARFF3350, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ARFF3375, DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ4ARFF3390, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ARFF3385, DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ4ARFF3380, DUKHCONP1AZ3ARFF3395, DUKHCONP1AZ4ARFF3330, DUKHCONP1AZ4ARFF3380, DUKHCONP1AZ4ARFF3375, DUKHCONP1AZ4ARFF3390, DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ4ARFF3330, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ARFF3385, DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ4ARFF3360 | DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-04-03 | 2014-04-26 | 2014-04-03 | 2014-04-26 | 0 | Yes | DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ4ELFF4045, DUKHCONP1AZ4ELFF4045, DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ4ARFF3330, DUKHCONP1AZ4ARFF3330, DUKHCONP1AZ3ARFF3345 | DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-02-24 | 2014-03-19 | 2014-02-24 | 2014-03-19 | 12 | No | DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4ARFF3305 | DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ4ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-04-12 | 2014-05-04 | 2014-04-12 | 2014-05-04 | 2 | No | DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ4ARFF3325 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ARFF3385, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-04-10 | 2014-05-08 | 2014-04-10 | 2014-05-08 | 0 | Yes | DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ3ARFF3360 | DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ELFF4060, DUKHCONP1AZ4ELFF4055, DUKHCONP1AZ4PLFF4340, DUKHCONP1AZ4PLFF4340, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ4ACFF4620, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ELFF4050, DUKHCONP1AZ4ELFF4055, DUKHCONP1AZ4ACFF4620, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ELFF4050, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ4ELFF4060, DUKHCONP1AZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-05-13 | 2014-06-04 | 2014-05-13 | 2014-06-04 | 0 | Yes | DUKHCONP1AZ4ARFF3350, DUKHCONP1AZ4ARFF3375, DUKHCONP1AZ4ARFF3350, DUKHCONP1AZ4ARFF3375 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-05-13 | 2014-06-04 | 2014-05-13 | 2014-06-04 | 1 | No | DUKHCONP1AZ4ARFF3375, DUKHCONP1AZ4ARFF3375 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 14 | No | DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4ARFF3305 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 0 | Yes | DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ4ELFF4035, DUKHCONP1AZ3ARFF3305, DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ4PLFF4325, DUKHCONP1AZ4ELFF4035, DUKHCONP1AZ4PLFF4325 | DUKHCONP1AZ4AREL3665, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ4ARFF3315, DUKHCONP1AZ4ARFF3330, DUKHCONP1AZ4ARFF3310, DUKHCONP1AZ4ARFF3330, DUKHCONP1AZ4ARFF3315, DUKHCONP1AZ4ARFF3310, DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ4AREL3665 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ4ARFF3310, DUKHCONP1AZ4ARFF3310, DUKHCONP1AZ3ARFF3325 | DUKHCONP1AZ4ARFF3350, DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ4ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-04-08 | 2014-04-24 | 2014-04-08 | 2014-04-24 | 8 | No | DUKHCONP1AZ4ARFF3310, DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ4ARFF3310 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-03-08 | 2014-03-24 | 2014-03-08 | 2014-03-24 | 0 | Yes | DUKHCONP1AZ3ARFF3315, DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4ARFF3305 | DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ5ARFF3315, DUKHCONP1AZ4ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-04-26 | 2014-05-12 | 2014-04-26 | 2014-05-12 | 0 | Yes | DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ARFF3350, DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ4ARFF3350, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ARFF3335, DUKHCONP1AZ3ARFF3365 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ARFF3370, DUKHCONP1AZ4ARFF3370, DUKHCONP1AZ4PLFF4335, DUKHCONP1AZ4PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.25 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-02-04 | 2014-04-10 | 2014-02-04 | 2014-04-10 | 57 |  |  |  | 0 | 0
DUKHCONP1AZ4ARRF3600 | Block work | 20 | 20 | 0% | 2014-02-04 | 2014-02-27 | 2014-02-04 | 2014-02-27 | 52 | No | DUKHCONP1AZ3ARRF3600, DUKHCONP1AZ4STRF2055, DUKHCONP1AZ4STRF2055 | DUKHCONP1AZ4ARRF3605, DUKHCONP1AZ4ARRF3605, DUKHCONP1AZ5ARRF3600 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-03-25 | 2014-04-10 | 2014-03-25 | 2014-04-10 | 57 | No | DUKHCONP1AZ4ARRF3695, DUKHCONP1AZ4ARRF3695 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ4PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-02-27 | 2014-03-16 | 2014-02-27 | 2014-03-16 | 57 | No | DUKHCONP1AZ4ARRF3605, DUKHCONP1AZ4ARRF3605 | DUKHCONP1AZ4ARRF3695, DUKHCONP1AZ4ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 57 | No | DUKHCONP1AZ4ARRF3610, DUKHCONP1AZ4ARRF3610 | DUKHCONP1AZ4ARRF3620, DUKHCONP1AZ4AREL3680, DUKHCONP1AZ4AREL3680, DUKHCONP1AZ4ARRF3620 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-02-13 | 2014-03-08 | 2014-02-13 | 2014-03-08 | 52 | No | DUKHCONP1AZ4ARRF3600, DUKHCONP1AZ4ARRF3600 | DUKHCONP1AZ4AREL3665, DUKHCONP1AZ4PLRF4345, DUKHCONP1AZ4ARRF3610, DUKHCONP1AZ4ARRF3610, DUKHCONP1AZ4PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.25 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-02-27 | 2014-05-17 | 2014-02-27 | 2014-05-17 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.25 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-03-13 | 2014-05-17 | 2014-03-13 | 2014-05-17 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ4ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 21 | No | DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4ARRF3645 | DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-04-30 | 2014-05-17 | 2014-04-30 | 2014-05-17 | 26 | No | DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4ARRF3655 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ4PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 21 | No | DUKHCONP1AZ4ARRF3635, DUKHCONP1AZ4ARRF3635 | DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-04-19 | 2014-05-11 | 2014-04-19 | 2014-05-11 | 21 | No | DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4ARRF3650, DUKHCONP1AZ3ARRF3655, DUKHCONP1AZ4ARRF3650, DUKHCONP1AZ4ARRF3645 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ4ARRF3660, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ4ARRF3660 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-03-17 | 2014-04-14 | 2014-03-17 | 2014-04-14 | 21 | No | DUKHCONP1AZ4ARRF3630, DUKHCONP1AZ4ARRF3630 | DUKHCONP1AZ4ARRF3640, DUKHCONP1AZ4ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 21 | No | DUKHCONP1AZ4STRF2065, DUKHCONP1AZ3ARRF3630, DUKHCONP1AZ4STRF2065, DUKHCONP1AZ4STRF2060, DUKHCONP1AZ4STRF2060 | DUKHCONP1AZ4ARRF3635, DUKHCONP1AZ4ARRF3635, DUKHCONP1AZ5ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ4ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 21 | No | DUKHCONP1AZ4ARRF3640, DUKHCONP1AZ4ARRF3640 | DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4ELRF4070, DUKHCONP1AZ4ARRF3650, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4ELRF4070, DUKHCONP1AZ4ARRF3650 | 0 | 0 | ROOF
DHBL.K30.L15.25 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-02-27 | 2014-04-20 | 2014-02-27 | 2014-04-20 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ4AREL3680 | External Painting | 20 | 20 | 0% | 2014-03-29 | 2014-04-20 | 2014-03-29 | 2014-04-20 | 49 | No | DUKHCONP1AZ4AREL3670, DUKHCONP1AZ4AREL3670, DUKHCONP1AZ4ARRF3695, DUKHCONP1AZ4ARRF3695, DUKHCONP1AZ3AREL3680 | DUKHCONP1AZ5AREL3680, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4PLTC8005 | 0 | 0 | ELEVATION
DUKHCONP1AZ4AREL3665 | External Plastering | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 47 | No | DUKHCONP1AZ4ARRF3605, DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4STRF2065, DUKHCONP1AZ4STRF2065, DUKHCONP1AZ3AREL3665, DUKHCONP1AZ4ARFF3305 | DUKHCONP1AZ5AREL3665, DUKHCONP1AZ4AREL3670, DUKHCONP1AZ4AREL3670, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP1AZ4AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 49 | No | DUKHCONP1AZ4AREL3665, DUKHCONP1AZ4AREL3665, DUKHCONP1AZ3AREL3670 | DUKHCONP1AZ4AREL3680, DUKHCONP1AZ4AREL3680, DUKHCONP1AZ5AREL3670 | 0 | 0 | ELEVATION
DHBL.K30.L15.25 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-09-02 | 2014-06-15 | 2013-09-02 | 2014-06-15 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.25 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2013-12-15 | 2014-06-15 | 2013-12-15 | 2014-06-15 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.25 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-12-15 | 2014-04-24 | 2013-12-15 | 2014-04-24 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ4ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-28 | 2014-01-19 | 2013-12-28 | 2014-01-19 | 45 | No | DUKHCONP1AZ4ELGF4000, DUKHCONP1AZ4ELGF4000, DUKHCONP1AZ3ELGF4005 | DUKHCONP1AZ4ELGF4010, DUKHCONP1AZ5ELGF4005, DUKHCONP1AZ4ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-12-15 | 2014-01-13 | 2013-12-15 | 2014-01-13 | 27 | No | DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ4ARGF3000 | DUKHCONP1AZ4ELGF4005, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ELGF4005, DUKHCONP1AZ4ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 30 | No | DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ3ELGF4015 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ELFF4055, DUKHCONP1AZ4ELFF4055, DUKHCONP1AZ5ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-03-16 | 2014-04-07 | 2014-03-16 | 2014-04-07 | 18 | No | DUKHCONP1AZ4ELGF4010, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ELGF4010 | DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ELGF4030, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 25 | No | DUKHCONP1AZ4ELGF4020, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ELGF4020, DUKHCONP1AZ3ELGF4025, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ARGF3060 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ5ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-03-27 | 2014-04-19 | 2014-03-27 | 2014-04-19 | 18 | No | DUKHCONP1AZ4ELGF4020, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ3ELGF4030, DUKHCONP1AZ4ELGF4020 | DUKHCONP1AZ5ELGF4030, DUKHCONP1AZ4ELFF4050, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 45 | No | DUKHCONP1AZ4ELGF4005, DUKHCONP1AZ4ELGF4005 | DUKHCONP1AZ4ELGF4020, DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ4ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.25 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2014-01-27 | 2014-05-28 | 2014-01-27 | 2014-05-28 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ4ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-02-08 | 2014-03-03 | 2014-02-08 | 2014-03-03 | 29 | No | DUKHCONP1AZ4ELFF4035, DUKHCONP1AZ4ELFF4035 | DUKHCONP1AZ4ELFF4045, DUKHCONP1AZ4ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 11 | No | DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ4ARFF3300 | DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4ELFF4040, DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 1 | No | DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ3ELFF4055, DUKHCONP1AZ4ELGF4015, DUKHCONP1AZ4ELGF4015 | DUKHCONP1AZ5ELFF4055, DUKHCONP1AZ4ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-04-22 | 2014-05-14 | 2014-04-22 | 2014-05-14 | 3 | No | DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ELFF4045, DUKHCONP1AZ3ELFF4060, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ELFF4045 | DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ5ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 1 | No | DUKHCONP1AZ4ELFF4060, DUKHCONP1AZ3ELFF4065, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ELFF4060, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ4ARFF3360 | DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ELRF4070, DUKHCONP1AZ4ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 8 | No | DUKHCONP1AZ4MSEX5010, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ELGF4030, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ELGF4030 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ELRF4070, DUKHCONP1AZ4ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-02-19 | 2014-03-19 | 2014-02-19 | 2014-03-19 | 27 | No | DUKHCONP1AZ4ELFF4040, DUKHCONP1AZ4ELFF4040, DUKHCONP1AZ3ELFF4045 | DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ4ELRF4070, DUKHCONP1AZ4ELRF4070, DUKHCONP1AZ5ELFF4045, DUKHCONP1AZ4ELFF4060, DUKHCONP1AZ4ELFF4060 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.25 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-05-14 | 2014-06-15 | 2014-05-14 | 2014-06-15 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ4ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-05-14 | 2014-06-03 | 2014-05-14 | 2014-06-03 | 1 | No | DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4ELFF4045, DUKHCONP1AZ4ELFF4045, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ4ELFF4050, DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ4ELFF4050 | DUKHCONP1AZ4ELRF4075, DUKHCONP1AZ4ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ4ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-05-20 | 2014-06-15 | 2014-05-20 | 2014-06-15 | 1 | No | DUKHCONP1AZ4ELRF4070, DUKHCONP1AZ4ELRF4070 | DUKHCONP1AZ4ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.25 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-09-02 | 2014-06-15 | 2013-09-02 | 2014-06-15 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.25 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-09-02 | 2014-04-24 | 2013-09-02 | 2014-04-24 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-09-02 | 2013-09-19 | 2013-09-02 | 2013-09-19 | 0 | Yes | DUKHCONP1AZ4STUG1040, DUKHCONP1AZ4STUG1040 | DUKHCONP1AZ4STUG1045, DUKHCONP1AZ4STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-12-26 | 2014-01-15 | 2013-12-26 | 2014-01-15 | 21 | No | DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ4PLGF4305, DUKHCONP1AZ4ARGF3000 | DUKHCONP1AZ4MSEX5000, DUKHCONP1AZ4ARGF3020, DUKHCONP1AZ4PLGF4315, DUKHCONP1AZ4PLGF4315, DUKHCONP1AZ4MSEX5000, DUKHCONP1AZ4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-12-26 | 2014-01-15 | 2013-12-26 | 2014-01-15 | 18 | No | DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ3PLGF4305, DUKHCONP1AZ4ARGF3000 | DUKHCONP1AZ4PLGF4310, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ARGF3020, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4PLGF4310, DUKHCONP1AZ4ARGF3020, DUKHCONP1AZ5PLGF4305 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-04-08 | 2014-04-24 | 2014-04-08 | 2014-04-24 | 45 | No | DUKHCONP1AZ4PLGF4315, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ3PLGF4320, DUKHCONP1AZ4PLGF4315 | DUKHCONP1AZ5PLGF4320, DUKHCONP1AZ4PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-03-27 | 2014-04-19 | 2014-03-27 | 2014-04-19 | 45 | No | DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ3PLGF4315, DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ4PLGF4310, DUKHCONP1AZ4PLGF4310 | DUKHCONP1AZ4PLGF4320, DUKHCONP1AZ5PLGF4315, DUKHCONP1AZ4PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.25 .20 .15 .15 FIRST FLOORS |  | 91 | 91 | 0% | 2014-02-06 | 2014-05-24 | 2014-02-06 | 2014-05-24 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ4PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-02-06 | 2014-02-27 | 2014-02-06 | 2014-02-27 | 23 | No | DUKHCONP1AZ4PLFF4325, DUKHCONP1AZ4PLFF4325, DUKHCONP1AZ3PLFF4330, DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ4ARFF3300 | DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ4PLFF4335, DUKHCONP1AZ4PLFF4335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-02-06 | 2014-02-27 | 2014-02-06 | 2014-02-27 | 1 | No | DUKHCONP1AZ4ARFF3300, DUKHCONP1AZ4ARFF3300 | DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ4ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-05-07 | 2014-05-24 | 2014-05-07 | 2014-05-24 | 5 | No | DUKHCONP1AZ4PLFF4335, DUKHCONP1AZ3PLFF4340, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4PLFF4335 | DUKHCONP1AZ5PLFF4340, DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ4PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-04-26 | 2014-05-18 | 2014-04-26 | 2014-05-18 | 5 | No | DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4PLFF4330 | DUKHCONP1AZ4PLFF4340, DUKHCONP1AZ4PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.25 .20 .15 .20 ROOF |  | 93 | 93 | 0% | 2014-02-27 | 2014-06-15 | 2014-02-27 | 2014-06-15 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ4PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-02-27 | 2014-03-16 | 2014-02-27 | 2014-03-16 | 56 | No | DUKHCONP1AZ4ARRF3605, DUKHCONP1AZ4ARRF3605 | DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ4PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-04-13 | 2014-04-29 | 2014-04-13 | 2014-04-29 | 26 | No | DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4PLRF4345, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ4AREL3665, DUKHCONP1AZ3PLRF4350, DUKHCONP1AZ4PLRF4345, DUKHCONP1AZ4AREL3665 | DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ4WEEX5065, DUKHCONP1AZ4WEEX5065, DUKHCONP1AZ4PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ4PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-05-18 | 2014-06-15 | 2014-05-18 | 2014-06-15 | 1 | No | DUKHCONP1AZ3PLRF4355, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4PLFF4340, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4PLFF4340, DUKHCONP1AZ4PLRF4345, DUKHCONP1AZ4PLRF4345 | DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ5PLRF4355 | 0 | 0 | ROOF
DHBL.K30.L15.25 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2014-01-15 | 2014-06-12 | 2014-01-15 | 2014-06-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.25 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-01-15 | 2014-04-22 | 2014-01-15 | 2014-04-22 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ4ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-03-31 | 2014-04-22 | 2014-03-31 | 2014-04-22 | 32 | No | DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ3ACGF4610 | DUKHCONP1AZ5ACGF4610, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ACRF4635, DUKHCONP1AZ4ACRF4635, DUKHCONP1AZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 32 | No | DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ3ACGF4605 | DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ5ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ4ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-15 | 2014-02-06 | 2014-01-15 | 2014-02-06 | 49 | No | DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ3ACGF4600 | DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ4ARGF3055, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ4ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.25 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-03-02 | 2014-06-01 | 2014-03-02 | 2014-06-01 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ4ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-05-10 | 2014-06-01 | 2014-05-10 | 2014-06-01 | 2 | No | DUKHCONP1AZ4ACFF4620, DUKHCONP1AZ3ACFF4625, DUKHCONP1AZ4ACFF4620 | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ACRF4635, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4ACRF4635, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ5ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 2 | No | DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ3ACFF4620, DUKHCONP1AZ4ACFF4615 | DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ5ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ4ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-03-02 | 2014-03-24 | 2014-03-02 | 2014-03-24 | 27 | No | DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ3ACFF4615 | DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ4ACFF4620, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ4ACFF4620 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.25 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-04-03 | 2014-06-12 | 2014-04-03 | 2014-06-12 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ4ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 3 | No | DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ3ACRF4635 | DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ5ACRF4635 | 0 | 0 | ROOF
DUKHCONP1AZ4ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 34 | No | DUKHCONP1AZ4ACGF4600, DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ3ACRF4630, DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4ARRF3645, DUKHCONP1AZ4ACGF4600 | DUKHCONP1AZ5ACRF4630, DUKHCONP1AZ4ACRF4635, DUKHCONP1AZ4ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.25 .25 EXTERNAL WORKS |  | 126 | 126 | 0% | 2014-01-22 | 2014-06-18 | 2014-01-22 | 2014-06-18 | 95 |  |  |  | 0 | 0
DHBL.K30.L15.25 .25 .10 MISCELLANEOUS |  | 126 | 126 | 0% | 2014-01-22 | 2014-06-18 | 2014-01-22 | 2014-06-18 | 95 |  |  |  | 0 | 0
DUKHCONP1AZ4MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-05-21 | 2014-06-18 | 2014-05-21 | 2014-06-18 | 95 | No | DUKHCONP1AZ3MSEX5335, DUKHCONI1AZ2BWGL5325 | DUKHCONP1AZ5MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ4MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-02-05 | 2014-03-06 | 2014-02-05 | 2014-03-06 | 8 | No | DUKHCONP1AZ4MSEX5000, DUKHCONP1AZ4MSEX5000 | DUKHCONP1AZ4MSEX5015, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ4MSEX5015, DUKHCONP1AZ4ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ4MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 16 | No | DUKHCONP1AZ3MSEX5020, DUKHCONP1AZ4STRF2055, DUKHCONP1AZ4STRF2055 | DUKHCONP1AZ4HDEX5090, DUKHCONP1AZ5MSEX5020, DUKHCONP1AZ4MSEX5025, DUKHCONP1AZ4MSEX5025, DUKHCONP1AZ4HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ4MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 8 | No | DUKHCONP1AZ4MSEX5005, DUKHCONP1AZ4MSEX5005 | DUKHCONP1AZ4WEEX5065, DUKHCONP1AZ4WEEX5065, DUKHCONP1AZ4MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ4MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 8 | No | DUKHCONP1AZ4STRF2055, DUKHCONP1AZ4PLGF4310, DUKHCONP1AZ4STRF2055, DUKHCONP1AZ4PLGF4310 | DUKHCONP1AZ4MSEX5005, DUKHCONP1AZ4MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ4MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-04-02 | 2014-04-24 | 2014-04-02 | 2014-04-24 | 19 | No | DUKHCONP1AZ4MSEX5020, DUKHCONP1AZ4MSEX5020 | DUKHCONP1AZ4WEEX5060, DUKHCONP1AZ4WEEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ4MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 8 | No | DUKHCONP1AZ4MSEX5015 | DUKHCONP1AZ4ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.25 .25 .15 WATER TANK ENCLOSURE |  | 80 | 80 | 0% | 2014-03-05 | 2014-06-05 | 2014-03-05 | 2014-06-05 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ4WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-03-20 | 2014-04-17 | 2014-03-20 | 2014-04-17 | 23 | No | DUKHCONP1AZ4WEEX5035, DUKHCONP1AZ4WEEX5035 | DUKHCONP1AZ4WEEX5045, DUKHCONP1AZ4WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ4WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-03-11 | 2014-04-08 | 2014-03-11 | 2014-04-08 | 23 | No | DUKHCONP1AZ4WEEX5030, DUKHCONP1AZ4WEEX5030 | DUKHCONP1AZ4WEEX5040, DUKHCONP1AZ4WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ4WEEX5030 | Excavation | 20 | 20 | 0% | 2014-03-05 | 2014-03-27 | 2014-03-05 | 2014-03-27 | 23 | No | DUKHCONP1AZ4STRF2055, DUKHCONP1AZ3WEEX5030, DUKHCONP1AZ4STRF2055 | DUKHCONP1AZ5WEEX5030, DUKHCONP1AZ4WEEX5035, DUKHCONP1AZ4WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ4WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 23 | No | DUKHCONP1AZ4WEEX5040, DUKHCONP1AZ4WEEX5040 | DUKHCONP1AZ4WEEX5050, DUKHCONP1AZ4WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ4WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-05-08 | 2014-06-05 | 2014-05-08 | 2014-06-05 | 9 | No | DUKHCONP1AZ4MSEX5015, DUKHCONP1AZ4MSEX5015, DUKHCONP1AZ4WEEX5060, DUKHCONP1AZ4WEEX5060, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ3WEEX5065, DUKHCONP1AZ4PLRF4350 | DUKHCONP1AZ5WEEX5065, DUKHCONP1AZ4PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ4WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-04-14 | 2014-05-06 | 2014-04-14 | 2014-05-06 | 19 | No | DUKHCONP1AZ4WEEX5045, DUKHCONP1AZ4WEEX5045, DUKHCONP1AZ4MSEX5025 | DUKHCONP1AZ4WEEX5060, DUKHCONP1AZ4WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ4WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 10 | No | DUKHCONP1AZ4WEEX5050, DUKHCONP1AZ4MSEX5025, DUKHCONP1AZ3WEEX5060, DUKHCONP1AZ4WEEX5050 | DUKHCONP1AZ5WEEX5060, DUKHCONP1AZ4WEEX5065, DUKHCONP1AZ4WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.25 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-03-30 | 2014-05-10 | 2014-03-30 | 2014-05-10 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ4HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-04-10 | 2014-05-03 | 2014-04-10 | 2014-05-03 | 16 | No | DUKHCONP1AZ4HDEX5090, DUKHCONP1AZ4HDEX5090 | DUKHCONP1AZ4HDEX5100, DUKHCONP1AZ4HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ4HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-04-17 | 2014-05-10 | 2014-04-17 | 2014-05-10 | 16 | No | DUKHCONP1AZ4HDEX5095, DUKHCONP1AZ4HDEX5095 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ4SLEX5105, DUKHCONP1AZ4SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ4HDEX5090 | kerb works | 20 | 20 | 0% | 2014-03-30 | 2014-04-21 | 2014-03-30 | 2014-04-21 | 16 | No | DUKHCONP1AZ4MSEX5020, DUKHCONP1AZ3HDEX5090, DUKHCONP1AZ4MSEX5020 | DUKHCONP1AZ4HDEX5095, DUKHCONP1AZ5HDEX5090, DUKHCONP1AZ4HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.25 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-04-23 | 2014-05-28 | 2014-04-23 | 2014-05-28 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ4SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 16 | No | DUKHCONP1AZ4HDEX5100, DUKHCONP1AZ4HDEX5100 | DUKHCONP1AZ4SLEX5110, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ4SLEX5110, DUKHCONP1AZ4PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ4SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 16 | No | DUKHCONP1AZ4SLEX5105, DUKHCONP1AZ4SLEX5105 | DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ4PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.25 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ4ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 | Yes | DUKHCONP1AZ4HDEX5100, DUKHCONP1AZ4AREL3680, DUKHCONP1AZ4ARRF3620, DUKHCONP1AZ4ACRF4635, DUKHCONP1AZ4ARRF3660, DUKHCONP1AZ4SLEX5105, DUKHCONP1AZ4SLEX5110, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4MSEX5005, DUKHCONP1AZ4ACFF4625, DUKHCONP1AZ4ARGF3095 | DUKHCONP1AZ5ACTC8000, DUKHHANP1AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 | Yes | DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4ARRF3620, DUKHCONP1AZ4HDEX5100, DUKHCONP1AZ4MSEX5005, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ4ARRF3660, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4SLEX5110, DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ4ELRF4075, DUKHCONP1AZ4SLEX5105, DUKHCONP1AZ4ELGF4015, DUKHCONP1AZ4ELGF4030, DUKHCONP1AZ4ELFF4050, DUKHCONP1AZ4AREL3680, DUKHCONP1AZ4ELFF4055, DUKHCONP1AZ4ARGF3095 | DUKHCONP1AZ5ELTC8010, DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 | Yes | DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ4HDEX5100, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ4MSEX5005, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ4SLEX5110, DUKHCONP1AZ4WEEX5065, DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ4ARRF3660, DUKHCONP1AZ4ARRF3620, DUKHCONP1AZ4SLEX5105, DUKHCONP1AZ4PLGF4320, DUKHCONP1AZ4AREL3680, DUKHCONP1AZ4PLRF4350 | DUKHCONP1AZ5PLTC8005, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.30 ZONE - 5 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-06-11 | 2014-08-17 | 2013-06-11 | 2014-08-17 | 72 |  |  |  | 0 | 0
DHBL.K30.L15.30 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-06-11 | 2014-03-23 | 2013-06-11 | 2014-03-23 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.30 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-06-11 | 2013-11-10 | 2013-06-11 | 2013-11-10 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.30 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-06-11 | 2013-11-10 | 2013-06-11 | 2013-11-10 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ5STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-08-22 | 2013-09-19 | 2013-08-22 | 2013-09-19 | 0 | Yes | DUKHCONP1AZ5STUG1030, DUKHCONP1AZ4STUG1035, DUKHCONP1AZ5STUG1030 | DUKHCONP1AZ6STUG1035, DUKHCONP1AZ5STUG1040, DUKHCONP1AZ5STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-07-17 | 2013-08-08 | 2013-07-17 | 2013-08-08 | 0 | Yes | DUKHCONP1AZ5STUG1015, DUKHCONP1AZ5STUG1015 | DUKHCONP1AZ5STUG1025, DUKHCONP1AZ5STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-09-08 | 2013-10-06 | 2013-09-08 | 2013-10-06 | 0 | Yes | DUKHCONP1AZ5STUG1035, DUKHCONP1AZ5STUG1035 | DUKHCONP1AZ5STUG1045, DUKHCONP1AZ5PLUG4300, DUKHCONP1AZ5STUG1045, DUKHCONP1AZ5PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-07-27 | 2013-08-27 | 2013-07-27 | 2013-08-27 | 0 | Yes | DUKHCONP1AZ5STUG1020, DUKHCONP1AZ5STUG1020, DUKHCONP1AZ4STUG1025 | DUKHCONP1AZ6STUG1025, DUKHCONP1AZ5STUG1030, DUKHCONP1AZ5STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-10-10 | 2013-11-10 | 2013-10-10 | 2013-11-10 | 0 | Yes | DUKHCONP1AZ5STUG1040, DUKHCONP1AZ4STUG1045, DUKHCONP1AZ5PLUG4300, DUKHCONP1AZ5PLUG4300, DUKHCONP1AZ5STUG1040 | DUKHCONP1AZ6STUG1045, DUKHCONP1AZ5STGF2000, DUKHCONP1AZ5STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-06-23 | 2013-07-18 | 2013-06-23 | 2013-07-18 | 0 | Yes | DUKHCONP1AZ5STUG1000, DUKHCONP1AZ5STUG1000 | DUKHCONP1AZ5STUG1010, DUKHCONP1AZ5STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-06-26 | 2013-07-22 | 2013-06-26 | 2013-07-22 | 0 | Yes | DUKHCONP1AZ5STUG1005, DUKHCONP1AZ5STUG1005 | DUKHCONP1AZ5STUG1015, DUKHCONP1AZ5STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-06-11 | 2013-07-09 | 2013-06-11 | 2013-07-09 | 0 | Yes | DUKHCONP1AGNSP005000, DUKHCONP1AZ4STUG1000 | DUKHCONP1AZ5STUG1005, DUKHCONP1AZ6STUG1000, DUKHCONP1AZ5STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-07-02 | 2013-07-30 | 2013-07-02 | 2013-07-30 | 0 | Yes | DUKHCONP1AZ5STUG1010, DUKHCONP1AZ5STUG1010 | DUKHCONP1AZ5STUG1020, DUKHCONP1AZ5STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ5STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-08-05 | 2013-09-05 | 2013-08-05 | 2013-09-05 | 0 | Yes | DUKHCONP1AZ5STUG1025, DUKHCONP1AZ5STUG1025 | DUKHCONP1AZ5STUG1035, DUKHCONP1AZ5STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.30 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2013-10-29 | 2014-03-23 | 2013-10-29 | 2014-03-23 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.30 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-10-29 | 2013-12-24 | 2013-10-29 | 2013-12-24 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ5STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-12-08 | 2013-12-24 | 2013-12-08 | 2013-12-24 | 2 | No | DUKHCONP1AZ4STGF2015, DUKHCONP1AZ5STGF2010, DUKHCONP1AZ5STGF2010 | DUKHCONP1AZ5STFF2020, DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ5STFF2020, DUKHCONP1AZ6STGF2015, DUKHCONP1AZ5ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 2 | No | DUKHCONP1AZ5STGF2005, DUKHCONP1AZ5STGF2005 | DUKHCONP1AZ5STGF2015, DUKHCONP1AZ5STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-11-06 | 2013-12-03 | 2013-11-06 | 2013-12-03 | 2 | No | DUKHCONP1AZ5STGF2000, DUKHCONP1AZ5STGF2000 | DUKHCONP1AZ5STGF2010, DUKHCONP1AZ5STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-10-29 | 2013-11-26 | 2013-10-29 | 2013-11-26 | 0 | Yes | DUKHCONP1AZ5STUG1045, DUKHCONP1AZ4STGF2000, DUKHCONP1AZ5STUG1045 | DUKHCONP1AZ5STGF2005, DUKHCONP1AZ5STGF2005, DUKHCONP1AZ6STGF2000 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.30 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2013-12-10 | 2014-02-05 | 2013-12-10 | 2014-02-05 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ5STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-01-21 | 2014-02-05 | 2014-01-21 | 2014-02-05 | 4 | No | DUKHCONP1AZ4STFF2035, DUKHCONP1AZ5STFF2030, DUKHCONP1AZ5STFF2030 | DUKHCONP1AZ6STFF2035, DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ5STRF2040, DUKHCONP1AZ5STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 4 | No | DUKHCONP1AZ5STFF2025, DUKHCONP1AZ5STFF2025 | DUKHCONP1AZ5STFF2035, DUKHCONP1AZ5STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-12-21 | 2014-01-16 | 2013-12-21 | 2014-01-16 | 4 | No | DUKHCONP1AZ5STFF2020, DUKHCONP1AZ5STFF2020 | DUKHCONP1AZ5STFF2030, DUKHCONI1AZ3DRGL5115, DUKHCONP1AZ5STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 2 | No | DUKHCONP1AZ4STFF2020, DUKHCONP1AZ5STGF2015, DUKHCONP1AZ5STGF2015 | DUKHCONP1AZ5STFF2025, DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ5STFF2025, DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ6STFF2020 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.30 .10 .15 .20 ROOF |  | 50 | 50 | 0% | 2014-01-23 | 2014-03-23 | 2014-01-23 | 2014-03-23 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ5STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-01-27 | 2014-02-16 | 2014-01-27 | 2014-02-16 | 8 | No | DUKHCONP1AZ5STRF2040, DUKHCONP1AZ5STRF2040 | DUKHCONP1AZ5STRF2050, DUKHCONP1AZ5STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ5STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-01-23 | 2014-02-13 | 2014-01-23 | 2014-02-13 | 8 | No | DUKHCONP1AZ4STRF2040, DUKHCONP1AZ5STFF2035, DUKHCONP1AZ5STFF2035 | DUKHCONP1AZ5STRF2045, DUKHCONP1AZ5STRF2045, DUKHCONP1AZ6STRF2040 | 0 | 0 | ROOF
DUKHCONP1AZ5STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 56 | No | DUKHCONP1AZ5STRF2055, DUKHCONP1AZ5STRF2055 | DUKHCONP1AZ5STRF2065, DUKHCONP1AZ5ARRF3630, DUKHCONP1AZ5ARRF3630, DUKHCONP1AZ5STRF2065 | 0 | 0 | ROOF
DUKHCONP1AZ5STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-02-23 | 2014-03-23 | 2014-02-23 | 2014-03-23 | 52 | No | DUKHCONP1AZ4STRF2065, DUKHCONP1AZ5STRF2060, DUKHCONP1AZ5STRF2060 | DUKHCONP1AZ5ARRF3630, DUKHCONP1AZ5AREL3665, DUKHCONP1AZ6STRF2065, DUKHCONP1AZ5AREL3665, DUKHCONP1AZ5ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ5STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-02-09 | 2014-02-24 | 2014-02-09 | 2014-02-24 | 8 | No | DUKHCONP1AZ5STRF2050, DUKHCONP1AZ5STRF2050, DUKHCONP1AZ4STRF2055 | DUKHCONP1AZ5MSEX5020, DUKHCONP1AZ5MSEX5000, DUKHCONP1AZ6STRF2055, DUKHCONP1AZ5STRF2060, DUKHCONP1AZ5MSEX5020, DUKHCONP1AZ5ARRF3600, DUKHCONP1AZ5STRF2060, DUKHCONP1AZ5ARRF3600, DUKHCONP1AZ5MSEX5000, DUKHCONP1AZ5WEEX5030, DUKHCONP1AZ5WEEX5030 | 0 | 0 | ROOF
DUKHCONP1AZ5STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-01-29 | 2014-02-22 | 2014-01-29 | 2014-02-22 | 8 | No | DUKHCONP1AZ5STRF2045, DUKHCONP1AZ5STRF2045 | DUKHCONP1AZ5STRF2055, DUKHCONP1AZ5STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.30 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2014-01-08 | 2014-07-15 | 2014-01-08 | 2014-07-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.30 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2014-01-08 | 2014-07-15 | 2014-01-08 | 2014-07-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.30 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-01-08 | 2014-06-21 | 2014-01-08 | 2014-06-21 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ5ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-04-26 | 2014-05-12 | 2014-04-26 | 2014-05-12 | 21 | No | DUKHCONP1AZ5ARGF3065, DUKHCONP1AZ4ARGF3070, DUKHCONP1AZ5ARGF3065 | DUKHCONP1AZ5ARGF3080, DUKHCONP1AZ5ARGF3080, DUKHCONP1AZ5ARGF3075, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3075, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ6ARGF3070 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 21 | No | DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ5ARGF3045 | DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5ACGF4605, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-05-03 | 2014-05-25 | 2014-05-03 | 2014-05-25 | 31 | No | DUKHCONP1AZ4ARGF3080, DUKHCONP1AZ5ARGF3070, DUKHCONP1AZ5ARGF3070 | DUKHCONP1AZ6ARGF3080, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3000 | Block work | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 18 | No | DUKHCONP1AZ5STGF2015, DUKHCONP1AZ4ARGF3000, DUKHCONP1AZ5STGF2015 | DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ5ELGF4000, DUKHCONP1AZ5PLGF4305, DUKHCONP1AZ5ELGF4000, DUKHCONP1AZ5PLGF4305, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ6ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-05-01 | 2014-05-24 | 2014-05-01 | 2014-05-24 | 21 | No | DUKHCONP1AZ5ARGF3070, DUKHCONP1AZ4ARGF3075, DUKHCONP1AZ5ARGF3070 | DUKHCONP1AZ5ARGF3090, DUKHCONP1AZ6ARGF3075, DUKHCONP1AZ5ARGF3085, DUKHCONP1AZ5ARGF3090, DUKHCONP1AZ5ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 18 | No | DUKHCONP1AZ5PLGF4305, DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5ARGF3015, DUKHCONP1AZ4ARGF3020, DUKHCONP1AZ5PLGF4305, DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5ARGF3015 | DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ5ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-03-29 | 2014-04-14 | 2014-03-29 | 2014-04-14 | 21 | No | DUKHCONP1AZ5ARGF3010, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ARGF3010 | DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3050, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 21 | No | DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3085, DUKHCONP1AZ5ACGF4610, DUKHCONP1AZ5ARGF3030, DUKHCONP1AZ5ARGF3070, DUKHCONP1AZ4ARGF3095, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3090, DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3085, DUKHCONP1AZ5ARGF3030, DUKHCONP1AZ5ARGF3080, DUKHCONP1AZ5ARGF3090, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ACGF4610, DUKHCONP1AZ5ARGF3070, DUKHCONP1AZ5ARGF3080 | DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ5PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 18 | No | DUKHCONP1AZ4ARGF3045, DUKHCONP1AZ5ARGF3030, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ELGF4010, DUKHCONP1AZ5ELGF4010, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ARGF3030 | DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-02-08 | 2014-03-04 | 2014-02-08 | 2014-03-04 | 26 | No | DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ5ARGF3005 | DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-04-06 | 2014-04-28 | 2014-04-06 | 2014-04-28 | 21 | No | DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3025 | DUKHCONP1AZ5ARGF3065, DUKHCONP1AZ5ARGF3085, DUKHCONP1AZ5ARGF3065, DUKHCONP1AZ5ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 18 | No | DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ4ARGF3060, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ5ACGF4600 | DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5PLGF4320, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5ELGF4030, DUKHCONP1AZ5ELGF4030, DUKHCONP1AZ5PLGF4320, DUKHCONP1AZ5ACGF4605, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5ACGF4605, DUKHCONP1AZ5ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-05-14 | 2014-05-31 | 2014-05-14 | 2014-05-31 | 21 | No | DUKHCONP1AZ5ARGF3075, DUKHCONP1AZ5ARGF3075 | DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 32 | No | DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ4ARGF3030 | DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ6ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 18 | No | DUKHCONP1AZ5PLGF4305, DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ4ARGF3005, DUKHCONP1AZ5ELGF4000, DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ5ELGF4000, DUKHCONP1AZ5PLGF4305 | DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ARGF3030, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ARGF3010, DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ5ARGF3015, DUKHCONP1AZ5ARGF3030, DUKHCONP1AZ5ARGF3010, DUKHCONP1AZ5ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 18 | No | DUKHCONP1AZ5ARGF3010, DUKHCONP1AZ5ARGF3020, DUKHCONP1AZ5ARGF3010, DUKHCONP1AZ4ARGF3025, DUKHCONP1AZ5ARGF3020 | DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ5ARGF3050, DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ARGF3050, DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-05-10 | 2014-06-01 | 2014-05-10 | 2014-06-01 | 26 | No | DUKHCONP1AZ5ARGF3050, DUKHCONP1AZ5ARGF3075, DUKHCONP1AZ5ARGF3050, DUKHCONP1AZ5ARGF3075 | DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-03-22 | 2014-04-07 | 2014-03-22 | 2014-04-07 | 23 | No | DUKHCONP1AZ5ARGF3010, DUKHCONP1AZ5ARGF3010, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ5ARGF3025 | DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3065, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARGF3040, DUKHCONP1AZ5ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-02-18 | 2014-03-06 | 2014-02-18 | 2014-03-06 | 18 | No | DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ4ARGF3015, DUKHCONP1AZ5ARGF3005 | DUKHCONP1AZ6ARGF3015, DUKHCONP1AZ5ARGF3020, DUKHCONP1AZ5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-04-20 | 2014-05-06 | 2014-04-20 | 2014-05-06 | 21 | No | DUKHCONP1AZ5ARGF3050, DUKHCONP1AZ4ARGF3065, DUKHCONP1AZ5ARGF3050, DUKHCONP1AZ5ARGF3035, DUKHCONP1AZ5ARGF3035 | DUKHCONP1AZ5ARGF3070, DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ5PLGF4315, DUKHCONP1AZ5PLGF4315, DUKHCONP1AZ5ARGF3070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.30 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2014-02-20 | 2014-07-15 | 2014-02-20 | 2014-07-15 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ5ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-05-25 | 2014-06-16 | 2014-05-25 | 2014-06-16 | 0 | Yes | DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ4ARFF3370, DUKHCONP1AZ5ARFF3365 | DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ5ARFF3380, DUKHCONP1AZ6ARFF3370, DUKHCONP1AZ5ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-06-01 | 2014-06-23 | 2014-06-01 | 2014-06-23 | 4 | No | DUKHCONP1AZ5ARFF3370, DUKHCONP1AZ5ARFF3370 | DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3300 | Block work | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 0 | Yes | DUKHCONP1AZ5STFF2020, DUKHCONP1AZ5STFF2020, DUKHCONP1AZ5STFF2035, DUKHCONP1AZ5STFF2035, DUKHCONP1AZ4ARFF3300 | DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ELFF4035, DUKHCONP1AZ5PLFF4325, DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ5ELFF4035, DUKHCONP1AZ5PLFF4325, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-05-31 | 2014-06-28 | 2014-05-31 | 2014-06-28 | 0 | Yes | DUKHCONP1AZ5ARFF3370, DUKHCONP1AZ5ARFF3370, DUKHCONP1AZ4ARFF3375 | DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3390, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3385, DUKHCONP1AZ5ARFF3385, DUKHCONP1AZ5ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-04-13 | 2014-05-11 | 2014-04-13 | 2014-05-11 | 0 | Yes | DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5PLFF4325, DUKHCONP1AZ4ARFF3320, DUKHCONP1AZ5ARFF3315, DUKHCONP1AZ5PLFF4325, DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5ARFF3315 | DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ5ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 | Yes | DUKHCONP1AZ5ARFF3390, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ARFF3380, DUKHCONP1AZ5ARFF3390, DUKHCONP1AZ5ACFF4625, DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ5ARFF3330, DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3350, DUKHCONP1AZ5ARFF3385, DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ5ARFF3385, DUKHCONP1AZ4ARFF3395, DUKHCONP1AZ5ACFF4625, DUKHCONP1AZ5ARFF3330, DUKHCONP1AZ5ARFF3350, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ5ARFF3380 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-05-03 | 2014-05-25 | 2014-05-03 | 2014-05-25 | 0 | Yes | DUKHCONP1AZ5ARFF3330, DUKHCONP1AZ4ARFF3345, DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ5ELFF4045, DUKHCONP1AZ5ELFF4045, DUKHCONP1AZ5ARFF3330 | DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ5ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-03-25 | 2014-04-17 | 2014-03-25 | 2014-04-17 | 12 | No | DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ARFF3305 | DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-05-11 | 2014-06-02 | 2014-05-11 | 2014-06-02 | 2 | No | DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ5ARFF3325 | DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ5ARFF3385, DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ5ARFF3385, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-05-10 | 2014-06-07 | 2014-05-10 | 2014-06-07 | 0 | Yes | DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ4ARFF3360, DUKHCONP1AZ5ARFF3345 | DUKHCONP1AZ5PLFF4340, DUKHCONP1AZ5ELFF4050, DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ5ELFF4055, DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ5ELFF4060, DUKHCONP1AZ5ELFF4060, DUKHCONP1AZ5ACFF4620, DUKHCONP1AZ5ELFF4050, DUKHCONP1AZ5ELFF4055, DUKHCONP1AZ5PLFF4340, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ACFF4620, DUKHCONP1AZ5ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-06-11 | 2014-07-03 | 2014-06-11 | 2014-07-03 | 0 | Yes | DUKHCONP1AZ5ARFF3350, DUKHCONP1AZ5ARFF3350, DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ5ARFF3375 | DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-06-11 | 2014-07-03 | 2014-06-11 | 2014-07-03 | 1 | No | DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ5ARFF3375 | DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 14 | No | DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ARFF3305 | DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-03-17 | 2014-04-14 | 2014-03-17 | 2014-04-14 | 0 | Yes | DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ4ARFF3305, DUKHCONP1AZ5PLFF4325, DUKHCONP1AZ5ELFF4035, DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ5ELFF4035, DUKHCONP1AZ5PLFF4325 | DUKHCONP1AZ5ARFF3310, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ5AREL3665, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ5AREL3665, DUKHCONP1AZ5ARFF3330, DUKHCONP1AZ5ARFF3315, DUKHCONP1AZ5ARFF3310, DUKHCONP1AZ5ARFF3315, DUKHCONP1AZ5ARFF3330 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 | Yes | DUKHCONP1AZ4ARFF3325, DUKHCONP1AZ5ARFF3310, DUKHCONP1AZ5ARFF3320, DUKHCONP1AZ5ARFF3320, DUKHCONP1AZ5ARFF3310 | DUKHCONP1AZ5ARFF3350, DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ5ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-05-07 | 2014-05-24 | 2014-05-07 | 2014-05-24 | 8 | No | DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ5ARFF3310, DUKHCONP1AZ5ARFF3325, DUKHCONP1AZ5ARFF3310 | DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-04-06 | 2014-04-22 | 2014-04-06 | 2014-04-22 | 0 | Yes | DUKHCONP1AZ4ARFF3315, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ARFF3305 | DUKHCONP1AZ6ARFF3315, DUKHCONP1AZ5ARFF3320, DUKHCONP1AZ5ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-05-25 | 2014-06-10 | 2014-05-25 | 2014-06-10 | 0 | Yes | DUKHCONP1AZ4ARFF3365, DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3350, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ARFF3350, DUKHCONP1AZ5ARFF3335, DUKHCONP1AZ5ARFF3360 | DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ5ARFF3370, DUKHCONP1AZ5PLFF4335, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ARFF3370, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.30 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-03-06 | 2014-05-10 | 2014-03-06 | 2014-05-10 | 57 |  |  |  | 0 | 0
DUKHCONP1AZ5ARRF3600 | Block work | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 52 | No | DUKHCONP1AZ5STRF2055, DUKHCONP1AZ5STRF2055, DUKHCONP1AZ4ARRF3600 | DUKHCONP1AZ6ARRF3600, DUKHCONP1AZ5ARRF3605, DUKHCONP1AZ5ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-04-23 | 2014-05-10 | 2014-04-23 | 2014-05-10 | 57 | No | DUKHCONP1AZ5ARRF3695, DUKHCONP1AZ5ARRF3695 | DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-03-29 | 2014-04-14 | 2014-03-29 | 2014-04-14 | 57 | No | DUKHCONP1AZ5ARRF3605, DUKHCONP1AZ5ARRF3605 | DUKHCONP1AZ5ARRF3695, DUKHCONP1AZ5ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-04-06 | 2014-04-28 | 2014-04-06 | 2014-04-28 | 57 | No | DUKHCONP1AZ5ARRF3610, DUKHCONP1AZ5ARRF3610 | DUKHCONP1AZ5ARRF3620, DUKHCONP1AZ5AREL3680, DUKHCONP1AZ5ARRF3620, DUKHCONP1AZ5AREL3680 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-03-15 | 2014-04-06 | 2014-03-15 | 2014-04-06 | 52 | No | DUKHCONP1AZ5ARRF3600, DUKHCONP1AZ5ARRF3600 | DUKHCONP1AZ5PLRF4345, DUKHCONP1AZ5AREL3665, DUKHCONP1AZ5ARRF3610, DUKHCONP1AZ5ARRF3610, DUKHCONP1AZ5PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.30 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-03-29 | 2014-06-15 | 2014-03-29 | 2014-06-15 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.30 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-04-12 | 2014-06-15 | 2014-04-12 | 2014-06-15 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ5ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 21 | No | DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5ARRF3645 | DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ5ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-05-29 | 2014-06-15 | 2014-05-29 | 2014-06-15 | 26 | No | DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ5ARRF3655 | DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 21 | No | DUKHCONP1AZ5ARRF3635, DUKHCONP1AZ5ARRF3635 | DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-05-18 | 2014-06-09 | 2014-05-18 | 2014-06-09 | 21 | No | DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ4ARRF3655, DUKHCONP1AZ5ARRF3650, DUKHCONP1AZ5ARRF3650 | DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ5ARRF3660, DUKHCONP1AZ5ARRF3660, DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ5PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 21 | No | DUKHCONP1AZ5ARRF3630, DUKHCONP1AZ5ARRF3630 | DUKHCONP1AZ5ARRF3640, DUKHCONP1AZ5ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 21 | No | DUKHCONP1AZ5STRF2065, DUKHCONP1AZ5STRF2060, DUKHCONP1AZ5STRF2060, DUKHCONP1AZ5STRF2065, DUKHCONP1AZ4ARRF3630 | DUKHCONP1AZ5ARRF3635, DUKHCONP1AZ6ARRF3630, DUKHCONP1AZ5ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ5ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 21 | No | DUKHCONP1AZ5ARRF3640, DUKHCONP1AZ5ARRF3640 | DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5ACRF4630, DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ5ACRF4630, DUKHCONP1AZ5ARRF3650, DUKHCONP1AZ5ARRF3650 | 0 | 0 | ROOF
DHBL.K30.L15.30 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-03-29 | 2014-05-19 | 2014-03-29 | 2014-05-19 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ5AREL3680 | External Painting | 20 | 20 | 0% | 2014-04-27 | 2014-05-19 | 2014-04-27 | 2014-05-19 | 49 | No | DUKHCONP1AZ5AREL3670, DUKHCONP1AZ5ARRF3695, DUKHCONP1AZ4AREL3680, DUKHCONP1AZ5ARRF3695, DUKHCONP1AZ5AREL3670 | DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ6AREL3680, DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ELTC8010 | 0 | 0 | ELEVATION
DUKHCONP1AZ5AREL3665 | External Plastering | 25 | 25 | 0% | 2014-03-29 | 2014-04-26 | 2014-03-29 | 2014-04-26 | 47 | No | DUKHCONP1AZ5ARRF3605, DUKHCONP1AZ4AREL3665, DUKHCONP1AZ5STRF2065, DUKHCONP1AZ5STRF2065, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ARFF3305 | DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5AREL3670, DUKHCONP1AZ6AREL3665, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5AREL3670 | 0 | 0 | ELEVATION
DUKHCONP1AZ5AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-04-15 | 2014-05-07 | 2014-04-15 | 2014-05-07 | 49 | No | DUKHCONP1AZ4AREL3670, DUKHCONP1AZ5AREL3665, DUKHCONP1AZ5AREL3665 | DUKHCONP1AZ5AREL3680, DUKHCONP1AZ6AREL3670, DUKHCONP1AZ5AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L15.30 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-10-01 | 2014-07-14 | 2013-10-01 | 2014-07-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.30 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2014-01-14 | 2014-07-14 | 2014-01-14 | 2014-07-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.30 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-01-14 | 2014-05-24 | 2014-01-14 | 2014-05-24 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ5ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-01-26 | 2014-02-18 | 2014-01-26 | 2014-02-18 | 45 | No | DUKHCONP1AZ5ELGF4000, DUKHCONP1AZ4ELGF4005, DUKHCONP1AZ5ELGF4000 | DUKHCONP1AZ5ELGF4010, DUKHCONP1AZ6ELGF4005, DUKHCONP1AZ5ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 27 | No | DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ5ARGF3000 | DUKHCONP1AZ5ELGF4005, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ5ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 30 | No | DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ4ELGF4015 | DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5ELFF4055, DUKHCONP1AZ5ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-04-14 | 2014-05-06 | 2014-04-14 | 2014-05-06 | 18 | No | DUKHCONP1AZ5ELGF4010, DUKHCONP1AZ5ELGF4010, DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ARGF3060 | DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5ELGF4030, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 25 | No | DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ4ELGF4025, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3055 | DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-04-26 | 2014-05-18 | 2014-04-26 | 2014-05-18 | 18 | No | DUKHCONP1AZ4ELGF4030, DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3060 | DUKHCONP1AZ5ELFF4050, DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 45 | No | DUKHCONP1AZ5ELGF4005, DUKHCONP1AZ5ELGF4005 | DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ELGF4020, DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ5ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.30 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2014-02-26 | 2014-06-26 | 2014-02-26 | 2014-06-26 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ5ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-03-10 | 2014-04-01 | 2014-03-10 | 2014-04-01 | 29 | No | DUKHCONP1AZ5ELFF4035, DUKHCONP1AZ5ELFF4035 | DUKHCONP1AZ5ELFF4045, DUKHCONP1AZ5ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 11 | No | DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ5ARFF3300 | DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ELFF4040, DUKHCONP1AZ5ELFF4040, DUKHCONP1AZ5ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-05-18 | 2014-06-15 | 2014-05-18 | 2014-06-15 | 1 | No | DUKHCONP1AZ4ELFF4055, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ5ARFF3360 | DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ6ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-05-21 | 2014-06-12 | 2014-05-21 | 2014-06-12 | 3 | No | DUKHCONP1AZ4ELFF4060, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ELFF4045, DUKHCONP1AZ5ELFF4045 | DUKHCONP1AZ6ELFF4060, DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ5ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 1 | No | DUKHCONP1AZ4ELFF4065, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ELFF4060, DUKHCONP1AZ5ELFF4060, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ELGF4025 | DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ5ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 8 | No | DUKHCONP1AZ5ELGF4030, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5MSEX5010, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ELGF4030 | DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ5ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-03-20 | 2014-04-17 | 2014-03-20 | 2014-04-17 | 27 | No | DUKHCONP1AZ4ELFF4045, DUKHCONP1AZ5ELFF4040, DUKHCONP1AZ5ELFF4040 | DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ5ELFF4060, DUKHCONP1AZ5ELFF4060, DUKHCONP1AZ5ARFF3345 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.30 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-06-12 | 2014-07-14 | 2014-06-12 | 2014-07-14 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ5ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-06-12 | 2014-07-02 | 2014-06-12 | 2014-07-02 | 1 | No | DUKHCONP1AZ5ELFF4045, DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5ELFF4045, DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5ELFF4050, DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ5ELFF4050 | DUKHCONP1AZ5ELRF4075, DUKHCONP1AZ5ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ5ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-06-18 | 2014-07-14 | 2014-06-18 | 2014-07-14 | 1 | No | DUKHCONP1AZ5ELRF4070, DUKHCONP1AZ5ELRF4070 | DUKHCONP1AZ5ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.30 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-10-01 | 2014-07-14 | 2013-10-01 | 2014-07-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.30 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-10-01 | 2014-05-24 | 2013-10-01 | 2014-05-24 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-10-01 | 2013-10-21 | 2013-10-01 | 2013-10-21 | 0 | Yes | DUKHCONP1AZ5STUG1040, DUKHCONP1AZ5STUG1040 | DUKHCONP1AZ5STUG1045, DUKHCONP1AZ5STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-01-25 | 2014-02-15 | 2014-01-25 | 2014-02-15 | 21 | No | DUKHCONP1AZ5PLGF4305, DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ5PLGF4305 | DUKHCONP1AZ5MSEX5000, DUKHCONP1AZ5PLGF4315, DUKHCONP1AZ5ARGF3020, DUKHCONP1AZ5PLGF4315, DUKHCONP1AZ5MSEX5000, DUKHCONP1AZ5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-01-25 | 2014-02-15 | 2014-01-25 | 2014-02-15 | 18 | No | DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ5ARGF3000, DUKHCONP1AZ4PLGF4305 | DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5ARGF3020, DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ5ARGF3020, DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-05-07 | 2014-05-24 | 2014-05-07 | 2014-05-24 | 45 | No | DUKHCONP1AZ5PLGF4315, DUKHCONP1AZ5PLGF4315, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ4PLGF4320, DUKHCONP1AZ5ARGF3060 | DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ6PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-04-26 | 2014-05-18 | 2014-04-26 | 2014-05-18 | 45 | No | DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5ARGF3065, DUKHCONP1AZ4PLGF4315, DUKHCONP1AZ5ARGF3065 | DUKHCONP1AZ5PLGF4320, DUKHCONP1AZ5PLGF4320, DUKHCONP1AZ6PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.30 .20 .15 .15 FIRST FLOORS |  | 90 | 90 | 0% | 2014-03-10 | 2014-06-22 | 2014-03-10 | 2014-06-22 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ5PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-03-10 | 2014-03-30 | 2014-03-10 | 2014-03-30 | 22 | No | DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ4PLFF4330, DUKHCONP1AZ5PLFF4325, DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ5PLFF4325 | DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5PLFF4335, DUKHCONP1AZ5PLFF4335, DUKHCONP1AZ5ARFF3320, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ5ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-03-10 | 2014-03-30 | 2014-03-10 | 2014-03-30 | 0 | Yes | DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ5ARFF3300 | DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ARFF3320, DUKHCONP1AZ5ARFF3320, DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-06-05 | 2014-06-22 | 2014-06-05 | 2014-06-22 | 5 | No | DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ4PLFF4340, DUKHCONP1AZ5PLFF4335, DUKHCONP1AZ5PLFF4335, DUKHCONP1AZ5ARFF3360 | DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ6PLFF4340 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-05-25 | 2014-06-16 | 2014-05-25 | 2014-06-16 | 5 | No | DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ5ARFF3365 | DUKHCONP1AZ5PLFF4340, DUKHCONP1AZ5PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.30 .20 .15 .20 ROOF |  | 93 | 93 | 0% | 2014-03-29 | 2014-07-14 | 2014-03-29 | 2014-07-14 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ5PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-03-29 | 2014-04-14 | 2014-03-29 | 2014-04-14 | 56 | No | DUKHCONP1AZ5ARRF3605, DUKHCONP1AZ5ARRF3605 | DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ5PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-05-12 | 2014-05-28 | 2014-05-12 | 2014-05-28 | 26 | No | DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5PLRF4345, DUKHCONP1AZ5AREL3665, DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5PLRF4345, DUKHCONP1AZ4PLRF4350, DUKHCONP1AZ5PLFF4330, DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5AREL3665 | DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ5WEEX5065, DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ5WEEX5065, DUKHCONP1AZ5PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ5PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 1 | No | DUKHCONP1AZ5PLRF4345, DUKHCONP1AZ5PLFF4340, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ4PLRF4355, DUKHCONP1AZ5PLFF4340, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ5PLRF4345, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5PLRF4350 | DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ6PLRF4355 | 0 | 0 | ROOF
DHBL.K30.L15.30 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2014-02-15 | 2014-07-12 | 2014-02-15 | 2014-07-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.30 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-02-15 | 2014-05-21 | 2014-02-15 | 2014-05-21 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ5ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-04-29 | 2014-05-21 | 2014-04-29 | 2014-05-21 | 32 | No | DUKHCONP1AZ5ACGF4605, DUKHCONP1AZ4ACGF4610, DUKHCONP1AZ5ACGF4605 | DUKHCONP1AZ6ACGF4610, DUKHCONP1AZ5ACRF4635, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ACRF4635, DUKHCONP1AZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 32 | No | DUKHCONP1AZ4ACGF4605, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ARGF3055 | DUKHCONP1AZ5ACGF4610, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ5ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ5ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-02-15 | 2014-03-09 | 2014-02-15 | 2014-03-09 | 49 | No | DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ4ACGF4600 | DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ACRF4630, DUKHCONP1AZ5ACGF4605, DUKHCONP1AZ5ACGF4605, DUKHCONP1AZ5ARGF3055, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ5ACRF4630 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.30 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-03-31 | 2014-06-30 | 2014-03-31 | 2014-06-30 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ5ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-06-08 | 2014-06-30 | 2014-06-08 | 2014-06-30 | 2 | No | DUKHCONP1AZ5ACFF4620, DUKHCONP1AZ5ACFF4620, DUKHCONP1AZ4ACFF4625 | DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ACRF4635, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5ACRF4635, DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-05-18 | 2014-06-15 | 2014-05-18 | 2014-06-15 | 2 | No | DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ4ACFF4620, DUKHCONP1AZ5ARFF3360 | DUKHCONP1AZ5ACFF4625, DUKHCONP1AZ6ACFF4620, DUKHCONP1AZ5ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ5ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-03-31 | 2014-04-22 | 2014-03-31 | 2014-04-22 | 27 | No | DUKHCONP1AZ4ACFF4615, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ5ARFF3305 | DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ5ACFF4620, DUKHCONP1AZ5ACRF4630, DUKHCONP1AZ5ACFF4620, DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ5ACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.30 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-05-03 | 2014-07-12 | 2014-05-03 | 2014-07-12 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ5ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 3 | No | DUKHCONP1AZ5ACGF4610, DUKHCONP1AZ5ACGF4610, DUKHCONP1AZ5ACFF4625, DUKHCONP1AZ4ACRF4635, DUKHCONP1AZ5ACFF4625, DUKHCONP1AZ5ACRF4630, DUKHCONP1AZ5ACRF4630 | DUKHCONP1AZ6ACRF4635, DUKHCONP1AZ5ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ5ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 34 | No | DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ4ACRF4630, DUKHCONP1AZ5ARRF3645, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ5ACFF4615, DUKHCONP1AZ5ACGF4600 | DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ5ACRF4635, DUKHCONP1AZ5ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.30 .25 EXTERNAL WORKS |  | 129 | 129 | 0% | 2014-02-22 | 2014-07-21 | 2014-02-22 | 2014-07-21 | 92 |  |  |  | 0 | 0
DHBL.K30.L15.30 .25 .10 MISCELLANEOUS |  | 129 | 129 | 0% | 2014-02-22 | 2014-07-21 | 2014-02-22 | 2014-07-21 | 92 |  |  |  | 0 | 0
DUKHCONP1AZ5MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 92 | No | DUKHCONI1AZ3BWGL5325, DUKHCONP1AZ4MSEX5335 | DUKHCONP1AZ6MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ5MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-03-08 | 2014-04-05 | 2014-03-08 | 2014-04-05 | 8 | No | DUKHCONP1AZ5MSEX5000, DUKHCONP1AZ5MSEX5000 | DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ5MSEX5015, DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ5MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-04-14 | 2014-05-12 | 2014-04-14 | 2014-05-12 | 16 | No | DUKHCONP1AZ5STRF2055, DUKHCONP1AZ4MSEX5020, DUKHCONP1AZ5STRF2055 | DUKHCONP1AZ5MSEX5025, DUKHCONP1AZ6MSEX5020, DUKHCONP1AZ5HDEX5090, DUKHCONP1AZ5MSEX5025, DUKHCONP1AZ5HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ5MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-03-27 | 2014-04-19 | 2014-03-27 | 2014-04-19 | 8 | No | DUKHCONP1AZ5MSEX5005, DUKHCONP1AZ5MSEX5005 | DUKHCONP1AZ5WEEX5065, DUKHCONP1AZ5MSEX5010, DUKHCONP1AZ5WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ5MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-02-22 | 2014-03-22 | 2014-02-22 | 2014-03-22 | 8 | No | DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5STRF2055, DUKHCONP1AZ5PLGF4310, DUKHCONP1AZ5STRF2055 | DUKHCONP1AZ5MSEX5005, DUKHCONP1AZ5MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ5MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-05-01 | 2014-05-24 | 2014-05-01 | 2014-05-24 | 19 | No | DUKHCONP1AZ5MSEX5020, DUKHCONP1AZ5MSEX5020 | DUKHCONP1AZ5WEEX5060, DUKHCONP1AZ5WEEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ5MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 8 | No | DUKHCONP1AZ5MSEX5015 | DUKHCONP1AZ5ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.30 .25 .15 WATER TANK ENCLOSURE |  | 85 | 85 | 0% | 2014-03-29 | 2014-07-05 | 2014-03-29 | 2014-07-05 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ5WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-04-13 | 2014-05-11 | 2014-04-13 | 2014-05-11 | 28 | No | DUKHCONP1AZ5WEEX5035, DUKHCONP1AZ5WEEX5035 | DUKHCONP1AZ5WEEX5045, DUKHCONP1AZ5WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ5WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 28 | No | DUKHCONP1AZ5WEEX5030, DUKHCONP1AZ5WEEX5030 | DUKHCONP1AZ5WEEX5040, DUKHCONP1AZ5WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ5WEEX5030 | Excavation | 20 | 20 | 0% | 2014-03-29 | 2014-04-20 | 2014-03-29 | 2014-04-20 | 28 | No | DUKHCONP1AZ4WEEX5030, DUKHCONP1AZ5STRF2055, DUKHCONP1AZ5STRF2055 | DUKHCONP1AZ6WEEX5030, DUKHCONP1AZ5WEEX5035, DUKHCONP1AZ5WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ5WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 28 | No | DUKHCONP1AZ5WEEX5040, DUKHCONP1AZ5WEEX5040 | DUKHCONP1AZ5WEEX5050, DUKHCONP1AZ5WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ5WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-06-07 | 2014-07-05 | 2014-06-07 | 2014-07-05 | 9 | No | DUKHCONP1AZ5MSEX5015, DUKHCONP1AZ4WEEX5065, DUKHCONP1AZ5MSEX5015, DUKHCONP1AZ5WEEX5060, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5WEEX5060, DUKHCONP1AZ5PLRF4350 | DUKHCONP1AZ6WEEX5065, DUKHCONP1AZ5PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ5WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-05-13 | 2014-06-04 | 2014-05-13 | 2014-06-04 | 19 | No | DUKHCONP1AZ5WEEX5045, DUKHCONP1AZ5WEEX5045, DUKHCONP1AZ5MSEX5025 | DUKHCONP1AZ5WEEX5060, DUKHCONP1AZ5WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ5WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 10 | No | DUKHCONP1AZ5MSEX5025, DUKHCONP1AZ4WEEX5060, DUKHCONP1AZ5WEEX5050, DUKHCONP1AZ5WEEX5050 | DUKHCONP1AZ6WEEX5060, DUKHCONP1AZ5WEEX5065, DUKHCONP1AZ5WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.30 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-04-28 | 2014-06-08 | 2014-04-28 | 2014-06-08 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ5HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-05-10 | 2014-06-01 | 2014-05-10 | 2014-06-01 | 16 | No | DUKHCONP1AZ5HDEX5090, DUKHCONP1AZ5HDEX5090 | DUKHCONP1AZ5HDEX5100, DUKHCONP1AZ5HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ5HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-05-17 | 2014-06-08 | 2014-05-17 | 2014-06-08 | 16 | No | DUKHCONP1AZ5HDEX5095, DUKHCONP1AZ5HDEX5095 | DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5SLEX5105, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5SLEX5105, DUKHCONP1AZ5PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ5HDEX5090 | kerb works | 20 | 20 | 0% | 2014-04-28 | 2014-05-20 | 2014-04-28 | 2014-05-20 | 16 | No | DUKHCONP1AZ4HDEX5090, DUKHCONP1AZ5MSEX5020, DUKHCONP1AZ5MSEX5020 | DUKHCONP1AZ5HDEX5095, DUKHCONP1AZ5HDEX5095, DUKHCONP1AZ6HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.30 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-05-22 | 2014-06-26 | 2014-05-22 | 2014-06-26 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ5SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 16 | No | DUKHCONP1AZ5HDEX5100, DUKHCONP1AZ5HDEX5100 | DUKHCONP1AZ5SLEX5110, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ5SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 16 | No | DUKHCONP1AZ5SLEX5105, DUKHCONP1AZ5SLEX5105 | DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ5PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.30 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ5ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 0 | Yes | DUKHCONP1AZ5SLEX5110, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ5HDEX5100, DUKHCONP1AZ5ARRF3660, DUKHCONP1AZ5SLEX5105, DUKHCONP1AZ5ACFF4625, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5ARRF3620, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5MSEX5005, DUKHCONP1AZ5AREL3680, DUKHCONP1AZ5ACRF4635 | DUKHHANP1AGNACTC9000, DUKHCONP1AZ6ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 0 | Yes | DUKHCONP1AZ5SLEX5105, DUKHCONP1AZ5ELRF4075, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ5ELFF4050, DUKHCONP1AZ4ELTC8010, DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ5ELFF4055, DUKHCONP1AZ5ARRF3660, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5SLEX5110, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ5HDEX5100, DUKHCONP1AZ5ARRF3620, DUKHCONP1AZ5MSEX5005, DUKHCONP1AZ5ELGF4030, DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ5AREL3680, DUKHCONP1AZ5ARFF3395 | DUKHCONP1AZ6ELTC8010, DUKHHANP1AGNPLTC9005, DUKHHANP1AGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 0 | Yes | DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ5SLEX5105, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ5MSEX5005, DUKHCONP1AZ5PLGF4320, DUKHCONP1AZ5AREL3680, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ5SLEX5110, DUKHCONP1AZ5WEEX5065, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ5ARRF3660, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ5HDEX5100, DUKHCONP1AZ5ARRF3620 | DUKHCONP1AZ6PLTC8005, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.35 ZONE - 6 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-07-10 | 2014-09-15 | 2013-07-10 | 2014-09-15 | 54 |  |  |  | 0 | 0
DHBL.K30.L15.35 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-07-10 | 2014-04-21 | 2013-07-10 | 2014-04-21 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.35 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-07-10 | 2013-12-09 | 2013-07-10 | 2013-12-09 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.35 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-07-10 | 2013-12-09 | 2013-07-10 | 2013-12-09 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ6STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-09-21 | 2013-10-21 | 2013-09-21 | 2013-10-21 | 0 | Yes | DUKHCONP1AZ6STUG1030, DUKHCONP1AZ5STUG1035, DUKHCONP1AZ6STUG1030 | DUKHCONP1AZ6STUG1040, DUKHCONP1AZ7STUG1035, DUKHCONP1AZ6STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-08-19 | 2013-09-10 | 2013-08-19 | 2013-09-10 | 0 | Yes | DUKHCONP1AZ6STUG1015, DUKHCONP1AZ6STUG1015 | DUKHCONP1AZ6STUG1025, DUKHCONP1AZ6STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-10-07 | 2013-11-06 | 2013-10-07 | 2013-11-06 | 0 | Yes | DUKHCONP1AZ6STUG1035, DUKHCONP1AZ6STUG1035 | DUKHCONP1AZ6STUG1045, DUKHCONP1AZ6PLUG4300, DUKHCONP1AZ6STUG1045, DUKHCONP1AZ6PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-08-28 | 2013-09-25 | 2013-08-28 | 2013-09-25 | 0 | Yes | DUKHCONP1AZ6STUG1020, DUKHCONP1AZ5STUG1025, DUKHCONP1AZ6STUG1020 | DUKHCONP1AZ6STUG1030, DUKHCONP1AZ6STUG1030, DUKHCONP1AZ7STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-11-11 | 2013-12-09 | 2013-11-11 | 2013-12-09 | 0 | Yes | DUKHCONP1AZ5STUG1045, DUKHCONP1AZ6STUG1040, DUKHCONP1AZ6PLUG4300, DUKHCONP1AZ6STUG1040, DUKHCONP1AZ6PLUG4300 | DUKHCONP1AZ6STGF2000, DUKHCONP1AZ7STUG1045, DUKHCONP1AZ6STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-07-22 | 2013-08-20 | 2013-07-22 | 2013-08-20 | 0 | Yes | DUKHCONP1AZ6STUG1000, DUKHCONP1AZ6STUG1000 | DUKHCONP1AZ6STUG1010, DUKHCONP1AZ6STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-07-25 | 2013-08-24 | 2013-07-25 | 2013-08-24 | 0 | Yes | DUKHCONP1AZ6STUG1005, DUKHCONP1AZ6STUG1005 | DUKHCONP1AZ6STUG1015, DUKHCONP1AZ6STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-07-10 | 2013-08-07 | 2013-07-10 | 2013-08-07 | 0 | Yes | DUKHCONP1AGNSP005000, DUKHCONP1AZ5STUG1000 | DUKHCONP1AZ6STUG1005, DUKHCONP1AZ6STUG1005, DUKHCONP1AZ7STUG1000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-07-31 | 2013-09-01 | 2013-07-31 | 2013-09-01 | 0 | Yes | DUKHCONP1AZ6STUG1010, DUKHCONP1AZ6STUG1010 | DUKHCONP1AZ6STUG1020, DUKHCONP1AZ6STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ6STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-09-07 | 2013-10-05 | 2013-09-07 | 2013-10-05 | 0 | Yes | DUKHCONP1AZ6STUG1025, DUKHCONP1AZ6STUG1025 | DUKHCONP1AZ6STUG1035, DUKHCONP1AZ6STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.35 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2013-11-27 | 2014-04-21 | 2013-11-27 | 2014-04-21 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.35 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-11-27 | 2014-01-22 | 2013-11-27 | 2014-01-22 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ6STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-01-07 | 2014-01-22 | 2014-01-07 | 2014-01-22 | 2 | No | DUKHCONP1AZ6STGF2010, DUKHCONP1AZ6STGF2010, DUKHCONP1AZ5STGF2015 | DUKHCONP1AZ6STFF2020, DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ6STFF2020, DUKHCONP1AZ7STGF2015, DUKHCONP1AZ6ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 2 | No | DUKHCONP1AZ6STGF2005, DUKHCONP1AZ6STGF2005 | DUKHCONP1AZ6STGF2015, DUKHCONP1AZ6STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-12-05 | 2014-01-02 | 2013-12-05 | 2014-01-02 | 2 | No | DUKHCONP1AZ6STGF2000, DUKHCONP1AZ6STGF2000 | DUKHCONP1AZ6STGF2010, DUKHCONP1AZ6STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-11-27 | 2013-12-26 | 2013-11-27 | 2013-12-26 | 0 | Yes | DUKHCONP1AZ6STUG1045, DUKHCONP1AZ5STGF2000, DUKHCONP1AZ6STUG1045 | DUKHCONP1AZ6STGF2005, DUKHCONP1AZ7STGF2000, DUKHCONP1AZ6STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.35 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2014-01-09 | 2014-03-08 | 2014-01-09 | 2014-03-08 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ6STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-02-20 | 2014-03-08 | 2014-02-20 | 2014-03-08 | 4 | No | DUKHCONP1AZ5STFF2035, DUKHCONP1AZ6STFF2030, DUKHCONP1AZ6STFF2030 | DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ7STFF2035, DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6STRF2040, DUKHCONP1AZ6STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 4 | No | DUKHCONP1AZ6STFF2025, DUKHCONP1AZ6STFF2025 | DUKHCONP1AZ6STFF2035, DUKHCONP1AZ6STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6STFF2025 | Column-Concrete | 24 | 24 | 0% | 2014-01-19 | 2014-02-16 | 2014-01-19 | 2014-02-16 | 4 | No | DUKHCONP1AZ6STFF2020, DUKHCONP1AZ6STFF2020 | DUKHCONP1AZ6STFF2030, DUKHCONP1AZ6STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-01-09 | 2014-02-06 | 2014-01-09 | 2014-02-06 | 2 | No | DUKHCONP1AZ6STGF2015, DUKHCONP1AZ5STFF2020, DUKHCONP1AZ6STGF2015 | DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6STFF2025, DUKHCONP1AZ7STFF2020, DUKHCONP1AZ6STFF2025, DUKHCONP1AZ6ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.35 .10 .15 .20 ROOF |  | 50 | 50 | 0% | 2014-02-23 | 2014-04-21 | 2014-02-23 | 2014-04-21 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ6STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-02-26 | 2014-03-17 | 2014-02-26 | 2014-03-17 | 8 | No | DUKHCONP1AZ6STRF2040, DUKHCONP1AZ6STRF2040 | DUKHCONP1AZ6STRF2050, DUKHCONP1AZ6STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ6STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-02-23 | 2014-03-15 | 2014-02-23 | 2014-03-15 | 8 | No | DUKHCONP1AZ5STRF2040, DUKHCONP1AZ6STFF2035, DUKHCONP1AZ6STFF2035 | DUKHCONP1AZ6STRF2045, DUKHCONP1AZ6STRF2045, DUKHCONP1AZ7STRF2040 | 0 | 0 | ROOF
DUKHCONP1AZ6STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 56 | No | DUKHCONP1AZ6STRF2055, DUKHCONP1AZ6STRF2055 | DUKHCONP1AZ6STRF2065, DUKHCONP1AZ6ARRF3630, DUKHCONP1AZ6STRF2065, DUKHCONP1AZ6ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ6STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-03-24 | 2014-04-21 | 2014-03-24 | 2014-04-21 | 52 | No | DUKHCONP1AZ6STRF2060, DUKHCONP1AZ6STRF2060, DUKHCONP1AZ5STRF2065 | DUKHCONP1AZ6ARRF3630, DUKHCONP1AZ6AREL3665, DUKHCONP1AZ7STRF2065, DUKHCONP1AZ6AREL3665, DUKHCONP1AZ6ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ6STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-03-11 | 2014-03-25 | 2014-03-11 | 2014-03-25 | 8 | No | DUKHCONP1AZ6STRF2050, DUKHCONP1AZ5STRF2055, DUKHCONP1AZ6STRF2050 | DUKHCONP1AZ6MSEX5000, DUKHCONP1AZ6ARRF3600, DUKHCONP1AZ6MSEX5020, DUKHCONP1AZ6ARRF3600, DUKHCONP1AZ6MSEX5000, DUKHCONP1AZ6STRF2060, DUKHCONP1AZ6MSEX5020, DUKHCONP1AZ6STRF2060, DUKHCONP1AZ6WEEX5030, DUKHCONP1AZ6WEEX5030, DUKHCONP1AZ7STRF2055 | 0 | 0 | ROOF
DUKHCONP1AZ6STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-03-01 | 2014-03-23 | 2014-03-01 | 2014-03-23 | 8 | No | DUKHCONP1AZ6STRF2045, DUKHCONP1AZ6STRF2045 | DUKHCONP1AZ6STRF2055, DUKHCONP1AZ6STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.35 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2014-02-06 | 2014-08-17 | 2014-02-06 | 2014-08-17 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.35 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2014-02-06 | 2014-08-17 | 2014-02-06 | 2014-08-17 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.35 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-02-06 | 2014-07-20 | 2014-02-06 | 2014-07-20 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ6ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-05-25 | 2014-06-10 | 2014-05-25 | 2014-06-10 | 21 | No | DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ5ARGF3070 | DUKHCONP1AZ7ARGF3070, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3080, DUKHCONP1AZ6ARGF3080, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3075, DUKHCONP1AZ6ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 21 | No | DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ARGF3045 | DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-06-01 | 2014-06-23 | 2014-06-01 | 2014-06-23 | 31 | No | DUKHCONP1AZ6ARGF3070, DUKHCONP1AZ5ARGF3080, DUKHCONP1AZ6ARGF3070 | DUKHCONP1AZ7ARGF3080, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3000 | Block work | 25 | 25 | 0% | 2014-02-06 | 2014-03-08 | 2014-02-06 | 2014-03-08 | 18 | No | DUKHCONP1AZ6STGF2015, DUKHCONP1AZ6STGF2015, DUKHCONP1AZ5ARGF3000 | DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ6ELGF4000, DUKHCONP1AZ6ELGF4000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-05-31 | 2014-06-22 | 2014-05-31 | 2014-06-22 | 21 | No | DUKHCONP1AZ5ARGF3075, DUKHCONP1AZ6ARGF3070, DUKHCONP1AZ6ARGF3070 | DUKHCONP1AZ6ARGF3090, DUKHCONP1AZ6ARGF3085, DUKHCONP1AZ6ARGF3090, DUKHCONP1AZ7ARGF3075, DUKHCONP1AZ6ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-03-25 | 2014-04-22 | 2014-03-25 | 2014-04-22 | 18 | No | DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ5ARGF3020, DUKHCONP1AZ6ARGF3015, DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ6ARGF3015 | DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ6ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-04-27 | 2014-05-13 | 2014-04-27 | 2014-05-13 | 21 | No | DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3010, DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3010 | DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3050, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-06-22 | 2014-07-20 | 2014-06-22 | 2014-07-20 | 21 | No | DUKHCONP1AZ6ARGF3070, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3080, DUKHCONP1AZ6ACGF4610, DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ARGF3070, DUKHCONP1AZ6ACGF4610, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3080, DUKHCONP1AZ5ARGF3095, DUKHCONP1AZ6ARGF3090, DUKHCONP1AZ6ARGF3085, DUKHCONP1AZ6ARGF3030, DUKHCONP1AZ6ARGF3030, DUKHCONP1AZ6ARGF3090, DUKHCONP1AZ6ARGF3085 | DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ7ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-04-17 | 2014-05-10 | 2014-04-17 | 2014-05-10 | 18 | No | DUKHCONP1AZ6ELGF4010, DUKHCONP1AZ6ARGF3030, DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ5ARGF3045, DUKHCONP1AZ6ELGF4010, DUKHCONP1AZ6ARGF3030, DUKHCONP1AZ6ARGF3025 | DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-03-10 | 2014-04-02 | 2014-03-10 | 2014-04-02 | 26 | No | DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ6ARGF3005 | DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-05-05 | 2014-05-27 | 2014-05-05 | 2014-05-27 | 21 | No | DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3040 | DUKHCONP1AZ6ARGF3085, DUKHCONP1AZ6ARGF3085, DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ6ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-04-29 | 2014-05-27 | 2014-04-29 | 2014-05-27 | 18 | No | DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ5ARGF3060, DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ6ARGF3045 | DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6PLGF4320, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ6PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-06-12 | 2014-06-29 | 2014-06-12 | 2014-06-29 | 21 | No | DUKHCONP1AZ6ARGF3075, DUKHCONP1AZ6ARGF3075 | DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 32 | No | DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ5ARGF3030 | DUKHCONP1AZ7ARGF3030, DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 18 | No | DUKHCONP1AZ6ELGF4000, DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ5ARGF3005, DUKHCONP1AZ6ELGF4000, DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ6PLGF4305 | DUKHCONP1AZ6ARGF3010, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ6ARGF3015, DUKHCONP1AZ6ARGF3010, DUKHCONP1AZ6ARGF3030, DUKHCONP1AZ6ARGF3015, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 18 | No | DUKHCONP1AZ6ARGF3010, DUKHCONP1AZ6ARGF3010, DUKHCONP1AZ5ARGF3025, DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ6ARGF3020 | DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3050, DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3050, DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-06-08 | 2014-06-30 | 2014-06-08 | 2014-06-30 | 26 | No | DUKHCONP1AZ6ARGF3050, DUKHCONP1AZ6ARGF3075, DUKHCONP1AZ6ARGF3050, DUKHCONP1AZ6ARGF3075 | DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-04-20 | 2014-05-06 | 2014-04-20 | 2014-05-06 | 23 | No | DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ6ARGF3010, DUKHCONP1AZ6ARGF3010 | DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3040, DUKHCONP1AZ6ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-03-19 | 2014-04-05 | 2014-03-19 | 2014-04-05 | 18 | No | DUKHCONP1AZ5ARGF3015, DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ6ARGF3005 | DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ7ARGF3015, DUKHCONP1AZ6ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-05-19 | 2014-06-04 | 2014-05-19 | 2014-06-04 | 21 | No | DUKHCONP1AZ5ARGF3065, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3050, DUKHCONP1AZ6ARGF3035, DUKHCONP1AZ6ARGF3050 | DUKHCONP1AZ6ARGF3070, DUKHCONP1AZ6PLGF4315, DUKHCONP1AZ6ARGF3070, DUKHCONP1AZ7ARGF3065, DUKHCONP1AZ6PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.35 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2014-03-22 | 2014-08-17 | 2014-03-22 | 2014-08-17 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ6ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-06-23 | 2014-07-15 | 2014-06-23 | 2014-07-15 | 0 | Yes | DUKHCONP1AZ5ARFF3370, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3365 | DUKHCONP1AZ6ARFF3380, DUKHCONP1AZ6ARFF3380, DUKHCONP1AZ7ARFF3370, DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ6ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-06-30 | 2014-07-22 | 2014-06-30 | 2014-07-22 | 4 | No | DUKHCONP1AZ6ARFF3370, DUKHCONP1AZ6ARFF3370 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3300 | Block work | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONP1AZ6STFF2020, DUKHCONP1AZ6STFF2035, DUKHCONP1AZ5ARFF3300, DUKHCONP1AZ6STFF2035, DUKHCONP1AZ6STFF2020 | DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6PLFF4325, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ELFF4035, DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ6ELFF4035, DUKHCONP1AZ6PLFF4325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-06-29 | 2014-07-27 | 2014-06-29 | 2014-07-27 | 0 | Yes | DUKHCONP1AZ5ARFF3375, DUKHCONP1AZ6ARFF3370, DUKHCONP1AZ6ARFF3370 | DUKHCONP1AZ7ARFF3375, DUKHCONP1AZ6ARFF3385, DUKHCONP1AZ6ARFF3385, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3390, DUKHCONP1AZ6ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 0 | Yes | DUKHCONP1AZ5ARFF3320, DUKHCONP1AZ6PLFF4325, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6PLFF4325, DUKHCONP1AZ6ARFF3315, DUKHCONP1AZ6ARFF3315 | DUKHCONP1AZ7ARFF3320, DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ6ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 0 | Yes | DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ6ARFF3350, DUKHCONP1AZ6ARFF3330, DUKHCONP1AZ6ARFF3335, DUKHCONP1AZ6ARFF3350, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3380, DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ6ARFF3385, DUKHCONP1AZ5ARFF3395, DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ARFF3330, DUKHCONP1AZ6ARFF3335, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ARFF3390, DUKHCONP1AZ6ARFF3390, DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ6ARFF3380, DUKHCONP1AZ6ARFF3385 | DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-06-01 | 2014-06-23 | 2014-06-01 | 2014-06-23 | 0 | Yes | DUKHCONP1AZ5ARFF3345, DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ6ARFF3330, DUKHCONP1AZ6ARFF3330, DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ6ELFF4045 | DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ7ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-04-23 | 2014-05-17 | 2014-04-23 | 2014-05-17 | 12 | No | DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ARFF3305 | DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ6ARFF3335, DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ6ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-06-09 | 2014-07-01 | 2014-06-09 | 2014-07-01 | 2 | No | DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ6ARFF3325 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3385, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-06-08 | 2014-07-06 | 2014-06-08 | 2014-07-06 | 0 | Yes | DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ5ARFF3360, DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ6ACFF4615 | DUKHCONP1AZ6ELFF4055, DUKHCONP1AZ6PLFF4340, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ACFF4620, DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6PLFF4340, DUKHCONP1AZ6ACFF4620, DUKHCONP1AZ6ELFF4055, DUKHCONP1AZ6ELFF4050, DUKHCONP1AZ6ELFF4060, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ6ELFF4060, DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ6ELFF4050 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-07-10 | 2014-08-05 | 2014-07-10 | 2014-08-05 | 0 | Yes | DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ6ARFF3350, DUKHCONP1AZ6ARFF3350 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-07-10 | 2014-08-05 | 2014-07-10 | 2014-08-05 | 1 | No | DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ6ARFF3375 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-05-01 | 2014-05-29 | 2014-05-01 | 2014-05-29 | 14 | No | DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ARFF3305 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ6ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 0 | Yes | DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6ELFF4035, DUKHCONP1AZ6PLFF4325, DUKHCONP1AZ6ELFF4035, DUKHCONP1AZ5ARFF3305, DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6PLFF4325 | DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ6ARFF3330, DUKHCONP1AZ6ARFF3310, DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ6AREL3665, DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ6ARFF3315, DUKHCONP1AZ6AREL3665, DUKHCONP1AZ6ARFF3330, DUKHCONP1AZ6ARFF3315, DUKHCONP1AZ6ARFF3310 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 0 | Yes | DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ6ARFF3310, DUKHCONP1AZ6ARFF3310, DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ5ARFF3325 | DUKHCONP1AZ6ARFF3350, DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ6ARFF3335, DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ6ARFF3350, DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ6ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-06-05 | 2014-06-22 | 2014-06-05 | 2014-06-22 | 8 | No | DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ6ARFF3310, DUKHCONP1AZ6ARFF3310, DUKHCONP1AZ6ARFF3325 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-05-05 | 2014-05-21 | 2014-05-05 | 2014-05-21 | 0 | Yes | DUKHCONP1AZ5ARFF3315, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ARFF3305 | DUKHCONP1AZ7ARFF3315, DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ6ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-06-23 | 2014-07-09 | 2014-06-23 | 2014-07-09 | 0 | Yes | DUKHCONP1AZ5ARFF3365, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ARFF3335, DUKHCONP1AZ6ARFF3350, DUKHCONP1AZ6ARFF3350, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ARFF3335 | DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARFF3370, DUKHCONP1AZ6ARFF3370, DUKHCONP1AZ6PLFF4335, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.35 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-04-05 | 2014-06-08 | 2014-04-05 | 2014-06-08 | 57 |  |  |  | 0 | 0
DUKHCONP1AZ6ARRF3600 | Block work | 20 | 20 | 0% | 2014-04-05 | 2014-04-27 | 2014-04-05 | 2014-04-27 | 52 | No | DUKHCONP1AZ6STRF2055, DUKHCONP1AZ5ARRF3600, DUKHCONP1AZ6STRF2055 | DUKHCONP1AZ7ARRF3600, DUKHCONP1AZ6ARRF3605, DUKHCONP1AZ6ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-05-22 | 2014-06-08 | 2014-05-22 | 2014-06-08 | 57 | No | DUKHCONP1AZ6ARRF3695, DUKHCONP1AZ6ARRF3695 | DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-04-27 | 2014-05-13 | 2014-04-27 | 2014-05-13 | 57 | No | DUKHCONP1AZ6ARRF3605, DUKHCONP1AZ6ARRF3605 | DUKHCONP1AZ6ARRF3695, DUKHCONP1AZ6ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-05-05 | 2014-05-27 | 2014-05-05 | 2014-05-27 | 57 | No | DUKHCONP1AZ6ARRF3610, DUKHCONP1AZ6ARRF3610 | DUKHCONP1AZ6ARRF3620, DUKHCONP1AZ6AREL3680, DUKHCONP1AZ6ARRF3620, DUKHCONP1AZ6AREL3680 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 52 | No | DUKHCONP1AZ6ARRF3600, DUKHCONP1AZ6ARRF3600 | DUKHCONP1AZ6AREL3665, DUKHCONP1AZ6ARRF3610, DUKHCONP1AZ6PLRF4345, DUKHCONP1AZ6ARRF3610, DUKHCONP1AZ6PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.35 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-04-27 | 2014-07-14 | 2014-04-27 | 2014-07-14 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.35 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-05-11 | 2014-07-14 | 2014-05-11 | 2014-07-14 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ6ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 21 | No | DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ6ARRF3645 | DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ6ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-06-28 | 2014-07-14 | 2014-06-28 | 2014-07-14 | 26 | No | DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ6ARRF3655 | DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 21 | No | DUKHCONP1AZ6ARRF3635, DUKHCONP1AZ6ARRF3635 | DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ6ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-06-16 | 2014-07-08 | 2014-06-16 | 2014-07-08 | 21 | No | DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ5ARRF3655, DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ6ARRF3650, DUKHCONP1AZ6ARRF3650 | DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6ARRF3660, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ARRF3660, DUKHCONP1AZ6PLRF4355, DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ6PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-05-14 | 2014-06-11 | 2014-05-14 | 2014-06-11 | 21 | No | DUKHCONP1AZ6ARRF3630, DUKHCONP1AZ6ARRF3630 | DUKHCONP1AZ6ARRF3640, DUKHCONP1AZ6ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 21 | No | DUKHCONP1AZ6STRF2065, DUKHCONP1AZ6STRF2060, DUKHCONP1AZ5ARRF3630, DUKHCONP1AZ6STRF2060, DUKHCONP1AZ6STRF2065 | DUKHCONP1AZ7ARRF3630, DUKHCONP1AZ6ARRF3635, DUKHCONP1AZ6ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ6ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 21 | No | DUKHCONP1AZ6ARRF3640, DUKHCONP1AZ6ARRF3640 | DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6ELRF4070, DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ6ARRF3650, DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ6ARRF3650, DUKHCONP1AZ6ELRF4070 | 0 | 0 | ROOF
DHBL.K30.L15.35 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-04-27 | 2014-06-17 | 2014-04-27 | 2014-06-17 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ6AREL3680 | External Painting | 20 | 20 | 0% | 2014-05-26 | 2014-06-17 | 2014-05-26 | 2014-06-17 | 49 | No | DUKHCONP1AZ6AREL3670, DUKHCONP1AZ6AREL3670, DUKHCONP1AZ6ARRF3695, DUKHCONP1AZ5AREL3680, DUKHCONP1AZ6ARRF3695 | DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ7AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1AZ6AREL3665 | External Plastering | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 47 | No | DUKHCONP1AZ6ARRF3605, DUKHCONP1AZ6STRF2065, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6STRF2065, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ5AREL3665 | DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6AREL3670, DUKHCONP1AZ6AREL3670, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ7AREL3665 | 0 | 0 | ELEVATION
DUKHCONP1AZ6AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-05-14 | 2014-06-05 | 2014-05-14 | 2014-06-05 | 49 | No | DUKHCONP1AZ6AREL3665, DUKHCONP1AZ6AREL3665, DUKHCONP1AZ5AREL3670 | DUKHCONP1AZ6AREL3680, DUKHCONP1AZ6AREL3680, DUKHCONP1AZ7AREL3670 | 0 | 0 | ELEVATION
DHBL.K30.L15.35 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-11-02 | 2014-08-16 | 2013-11-02 | 2014-08-16 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.35 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2014-02-13 | 2014-08-16 | 2014-02-13 | 2014-08-16 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.35 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-02-13 | 2014-06-22 | 2014-02-13 | 2014-06-22 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ6ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-02-25 | 2014-03-19 | 2014-02-25 | 2014-03-19 | 45 | No | DUKHCONP1AZ6ELGF4000, DUKHCONP1AZ6ELGF4000, DUKHCONP1AZ5ELGF4005 | DUKHCONP1AZ6ELGF4010, DUKHCONP1AZ7ELGF4005, DUKHCONP1AZ6ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 27 | No | DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ6ARGF3000 | DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ6ELGF4005, DUKHCONP1AZ6ELGF4005, DUKHCONP1AZ6ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-05-07 | 2014-06-04 | 2014-05-07 | 2014-06-04 | 30 | No | DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ5ELGF4015, DUKHCONP1AZ6ARGF3055 | DUKHCONP1AZ6ELFF4055, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ELFF4055, DUKHCONP1AZ7ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-05-13 | 2014-06-04 | 2014-05-13 | 2014-06-04 | 18 | No | DUKHCONP1AZ6ELGF4010, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ELGF4010, DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ARGF3060 | DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ6ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-05-25 | 2014-06-22 | 2014-05-25 | 2014-06-22 | 25 | No | DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ5ELGF4025, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ELGF4020 | DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ7ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-05-25 | 2014-06-16 | 2014-05-25 | 2014-06-16 | 18 | No | DUKHCONP1AZ5ELGF4030, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ARGF3060 | DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ELFF4050, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ6ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 45 | No | DUKHCONP1AZ6ELGF4005, DUKHCONP1AZ6ELGF4005 | DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ6ELGF4020, DUKHCONP1AZ6ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.35 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2014-03-27 | 2014-07-26 | 2014-03-27 | 2014-07-26 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ6ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-04-08 | 2014-04-30 | 2014-04-08 | 2014-04-30 | 29 | No | DUKHCONP1AZ6ELFF4035, DUKHCONP1AZ6ELFF4035 | DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ6ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 11 | No | DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6ARFF3300 | DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ELFF4040, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 1 | No | DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ5ELFF4055 | DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ7ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-06-19 | 2014-07-12 | 2014-06-19 | 2014-07-12 | 3 | No | DUKHCONP1AZ5ELFF4060, DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ6ARFF3360 | DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ6ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 1 | No | DUKHCONP1AZ5ELFF4065, DUKHCONP1AZ6ELFF4060, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ6ELFF4060, DUKHCONP1AZ6ARFF3360 | DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ELRF4070, DUKHCONP1AZ7ELFF4065, DUKHCONP1AZ6ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 8 | No | DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6MSEX5010, DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ6ARFF3360 | DUKHCONP1AZ6ELRF4070, DUKHCONP1AZ6ELRF4070, DUKHCONP1AZ6ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 27 | No | DUKHCONP1AZ6ELFF4040, DUKHCONP1AZ6ELFF4040, DUKHCONP1AZ5ELFF4045 | DUKHCONP1AZ6ELRF4070, DUKHCONP1AZ7ELFF4045, DUKHCONP1AZ6ELFF4060, DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ6ELRF4070, DUKHCONP1AZ6ELFF4060, DUKHCONP1AZ6ARFF3345 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.35 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-07-12 | 2014-08-16 | 2014-07-12 | 2014-08-16 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ6ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-07-12 | 2014-07-31 | 2014-07-12 | 2014-07-31 | 1 | No | DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ6ELFF4050, DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ6ELFF4050, DUKHCONP1AZ6ARRF3645 | DUKHCONP1AZ6ELRF4075, DUKHCONP1AZ6ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ6ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-07-17 | 2014-08-16 | 2014-07-17 | 2014-08-16 | 1 | No | DUKHCONP1AZ6ELRF4070, DUKHCONP1AZ6ELRF4070 | DUKHCONP1AZ6ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.35 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-11-02 | 2014-08-16 | 2013-11-02 | 2014-08-16 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.35 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-11-02 | 2014-06-22 | 2013-11-02 | 2014-06-22 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ6PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-11-02 | 2013-11-19 | 2013-11-02 | 2013-11-19 | 0 | Yes | DUKHCONP1AZ6STUG1040, DUKHCONP1AZ6STUG1040 | DUKHCONP1AZ6STUG1045, DUKHCONP1AZ6STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-02-24 | 2014-03-16 | 2014-02-24 | 2014-03-16 | 21 | No | DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ6PLGF4305 | DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ6MSEX5000, DUKHCONP1AZ6MSEX5000, DUKHCONP1AZ6PLGF4315, DUKHCONP1AZ6PLGF4315 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-02-24 | 2014-03-16 | 2014-02-24 | 2014-03-16 | 18 | No | DUKHCONP1AZ5PLGF4305, DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ6ARGF3000 | DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ6ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-06-05 | 2014-06-22 | 2014-06-05 | 2014-06-22 | 45 | No | DUKHCONP1AZ6PLGF4315, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ5PLGF4320, DUKHCONP1AZ6PLGF4315, DUKHCONP1AZ6ARGF3060 | DUKHCONP1AZ7PLGF4320, DUKHCONP1AZ6PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-05-25 | 2014-06-16 | 2014-05-25 | 2014-06-16 | 45 | No | DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ5PLGF4315 | DUKHCONP1AZ7PLGF4315, DUKHCONP1AZ6PLGF4320, DUKHCONP1AZ6PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.35 .20 .15 .15 FIRST FLOORS |  | 90 | 90 | 0% | 2014-04-08 | 2014-07-21 | 2014-04-08 | 2014-07-21 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ6PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-04-08 | 2014-04-28 | 2014-04-08 | 2014-04-28 | 22 | No | DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6PLFF4325, DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6PLFF4325, DUKHCONP1AZ5PLFF4330 | DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ6PLFF4335, DUKHCONP1AZ6PLFF4335, DUKHCONP1AZ7PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-04-08 | 2014-04-28 | 2014-04-08 | 2014-04-28 | 0 | Yes | DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ6ARFF3300 | DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-07-05 | 2014-07-21 | 2014-07-05 | 2014-07-21 | 5 | No | DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6PLFF4335, DUKHCONP1AZ6PLFF4335, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ5PLFF4340 | DUKHCONP1AZ6PLRF4355, DUKHCONP1AZ7PLFF4340, DUKHCONP1AZ6PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-06-23 | 2014-07-15 | 2014-06-23 | 2014-07-15 | 5 | No | DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ6PLFF4330 | DUKHCONP1AZ6PLFF4340, DUKHCONP1AZ6PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.35 .20 .15 .20 ROOF |  | 93 | 93 | 0% | 2014-04-27 | 2014-08-16 | 2014-04-27 | 2014-08-16 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ6PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-04-27 | 2014-05-13 | 2014-04-27 | 2014-05-13 | 56 | No | DUKHCONP1AZ6ARRF3605, DUKHCONP1AZ6ARRF3605 | DUKHCONP1AZ6PLRF4355, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ6PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-06-10 | 2014-06-26 | 2014-06-10 | 2014-06-26 | 26 | No | DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ6PLFF4330, DUKHCONP1AZ6AREL3665, DUKHCONP1AZ6PLRF4345, DUKHCONP1AZ5PLRF4350, DUKHCONP1AZ6PLRF4345, DUKHCONP1AZ6AREL3665 | DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6PLRF4355, DUKHCONP1AZ6PLRF4355, DUKHCONP1AZ6WEEX5065, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ6WEEX5065 | 0 | 0 | ROOF
DUKHCONP1AZ6PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-07-15 | 2014-08-16 | 2014-07-15 | 2014-08-16 | 1 | No | DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ5PLRF4355, DUKHCONP1AZ6PLRF4345, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6PLFF4340, DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ6PLRF4345, DUKHCONP1AZ6PLFF4340, DUKHCONP1AZ6ARRF3655 | DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ6PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L15.35 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2014-03-16 | 2014-08-13 | 2014-03-16 | 2014-08-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.35 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-03-16 | 2014-06-19 | 2014-03-16 | 2014-06-19 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ6ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-05-28 | 2014-06-19 | 2014-05-28 | 2014-06-19 | 32 | No | DUKHCONP1AZ5ACGF4610, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ6ACGF4605 | DUKHCONP1AZ6ACRF4635, DUKHCONP1AZ7ACGF4610, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-05-07 | 2014-06-04 | 2014-05-07 | 2014-06-04 | 32 | No | DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ5ACGF4605, DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ARGF3060 | DUKHCONP1AZ6ACGF4610, DUKHCONP1AZ7ACGF4605, DUKHCONP1AZ6ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ6ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-03-16 | 2014-04-07 | 2014-03-16 | 2014-04-07 | 49 | No | DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ5ACGF4600, DUKHCONP1AZ6ARGF3005 | DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ARGF3060, DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ6ARGF3055, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ6ARGF3055 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.35 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-04-29 | 2014-07-29 | 2014-04-29 | 2014-07-29 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ6ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-07-07 | 2014-07-29 | 2014-07-07 | 2014-07-29 | 2 | No | DUKHCONP1AZ6ACFF4620, DUKHCONP1AZ6ACFF4620, DUKHCONP1AZ5ACFF4625 | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ7ACFF4625, DUKHCONP1AZ6ACRF4635, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ACRF4635 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 2 | No | DUKHCONP1AZ5ACFF4620, DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ACFF4615 | DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ7ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ6ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-04-29 | 2014-05-21 | 2014-04-29 | 2014-05-21 | 27 | No | DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ5ACFF4615 | DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ARFF3360, DUKHCONP1AZ6ACFF4620, DUKHCONP1AZ6ACFF4620 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.35 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-06-01 | 2014-08-13 | 2014-06-01 | 2014-08-13 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ6ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 3 | No | DUKHCONP1AZ6ACGF4610, DUKHCONP1AZ5ACRF4635, DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ6ACGF4610, DUKHCONP1AZ6ACFF4625 | DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ7ACRF4635 | 0 | 0 | ROOF
DUKHCONP1AZ6ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 34 | No | DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ6ARRF3645, DUKHCONP1AZ5ACRF4630, DUKHCONP1AZ6ARRF3645 | DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ6ACRF4635, DUKHCONP1AZ6ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.35 .25 EXTERNAL WORKS |  | 119 | 119 | 0% | 2014-03-23 | 2014-08-11 | 2014-03-23 | 2014-08-11 | 84 |  |  |  | 0 | 0
DHBL.K30.L15.35 .25 .10 MISCELLANEOUS |  | 119 | 119 | 0% | 2014-03-23 | 2014-08-11 | 2014-03-23 | 2014-08-11 | 84 |  |  |  | 0 | 0
DUKHCONP1AZ6MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-07-10 | 2014-08-11 | 2014-07-10 | 2014-08-11 | 84 | No | DUKHCONI1AZ3BWGL5325, DUKHCONP1AZ5MSEX5335 | DUKHCONP1AZ7MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ6MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-04-06 | 2014-05-04 | 2014-04-06 | 2014-05-04 | 8 | No | DUKHCONP1AZ6MSEX5000, DUKHCONP1AZ6MSEX5000 | DUKHCONP1AZ6MSEX5015, DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ6MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-05-13 | 2014-06-10 | 2014-05-13 | 2014-06-10 | 16 | No | DUKHCONP1AZ6STRF2055, DUKHCONP1AZ5MSEX5020, DUKHCONP1AZ6STRF2055 | DUKHCONP1AZ6MSEX5025, DUKHCONP1AZ6HDEX5090, DUKHCONP1AZ6MSEX5025, DUKHCONP1AZ7MSEX5020, DUKHCONP1AZ6HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ6MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-04-26 | 2014-05-18 | 2014-04-26 | 2014-05-18 | 8 | No | DUKHCONP1AZ6MSEX5005, DUKHCONP1AZ6MSEX5005 | DUKHCONP1AZ6MSEX5010, DUKHCONP1AZ6WEEX5065, DUKHCONP1AZ6WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ6MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-03-23 | 2014-04-20 | 2014-03-23 | 2014-04-20 | 8 | No | DUKHCONP1AZ6STRF2055, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6PLGF4310, DUKHCONP1AZ6STRF2055 | DUKHCONP1AZ6MSEX5005, DUKHCONP1AZ6MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ6MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-05-31 | 2014-06-22 | 2014-05-31 | 2014-06-22 | 19 | No | DUKHCONP1AZ6MSEX5020, DUKHCONP1AZ6MSEX5020 | DUKHCONP1AZ6WEEX5060, DUKHCONP1AZ6WEEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ6MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 8 | No | DUKHCONP1AZ6MSEX5015 | DUKHCONP1AZ6ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.35 .25 .15 WATER TANK ENCLOSURE |  | 90 | 90 | 0% | 2014-04-21 | 2014-08-06 | 2014-04-21 | 2014-08-06 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ6WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-05-06 | 2014-06-03 | 2014-05-06 | 2014-06-03 | 33 | No | DUKHCONP1AZ6WEEX5035, DUKHCONP1AZ6WEEX5035 | DUKHCONP1AZ6WEEX5045, DUKHCONP1AZ6WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ6WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 33 | No | DUKHCONP1AZ6WEEX5030, DUKHCONP1AZ6WEEX5030 | DUKHCONP1AZ6WEEX5040, DUKHCONP1AZ6WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ6WEEX5030 | Excavation | 20 | 20 | 0% | 2014-04-21 | 2014-05-13 | 2014-04-21 | 2014-05-13 | 33 | No | DUKHCONP1AZ5WEEX5030, DUKHCONP1AZ6STRF2055, DUKHCONP1AZ6STRF2055 | DUKHCONP1AZ7WEEX5030, DUKHCONP1AZ6WEEX5035, DUKHCONP1AZ6WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ6WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-05-13 | 2014-06-10 | 2014-05-13 | 2014-06-10 | 33 | No | DUKHCONP1AZ6WEEX5040, DUKHCONP1AZ6WEEX5040 | DUKHCONP1AZ6WEEX5050, DUKHCONP1AZ6WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ6WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-07-06 | 2014-08-06 | 2014-07-06 | 2014-08-06 | 9 | No | DUKHCONP1AZ5WEEX5065, DUKHCONP1AZ6WEEX5060, DUKHCONP1AZ6MSEX5015, DUKHCONP1AZ6WEEX5060, DUKHCONP1AZ6MSEX5015, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6PLRF4350 | DUKHCONP1AZ7WEEX5065, DUKHCONP1AZ6PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ6WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-06-11 | 2014-07-03 | 2014-06-11 | 2014-07-03 | 19 | No | DUKHCONP1AZ6WEEX5045, DUKHCONP1AZ6WEEX5045, DUKHCONP1AZ6MSEX5025 | DUKHCONP1AZ6WEEX5060, DUKHCONP1AZ6WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ6WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 10 | No | DUKHCONP1AZ5WEEX5060, DUKHCONP1AZ6WEEX5050, DUKHCONP1AZ6MSEX5025, DUKHCONP1AZ6WEEX5050 | DUKHCONP1AZ6WEEX5065, DUKHCONP1AZ6WEEX5065, DUKHCONP1AZ7WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.35 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-05-27 | 2014-07-07 | 2014-05-27 | 2014-07-07 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ6HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-06-08 | 2014-06-30 | 2014-06-08 | 2014-06-30 | 16 | No | DUKHCONP1AZ6HDEX5090, DUKHCONP1AZ6HDEX5090 | DUKHCONP1AZ6HDEX5100, DUKHCONP1AZ6HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ6HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-06-15 | 2014-07-07 | 2014-06-15 | 2014-07-07 | 16 | No | DUKHCONP1AZ6HDEX5095, DUKHCONP1AZ6HDEX5095 | DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6SLEX5105, DUKHCONP1AZ6SLEX5105, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ6HDEX5090 | kerb works | 20 | 20 | 0% | 2014-05-27 | 2014-06-18 | 2014-05-27 | 2014-06-18 | 16 | No | DUKHCONP1AZ6MSEX5020, DUKHCONP1AZ6MSEX5020, DUKHCONP1AZ5HDEX5090 | DUKHCONP1AZ6HDEX5095, DUKHCONP1AZ6HDEX5095, DUKHCONP1AZ7HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.35 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-06-21 | 2014-07-26 | 2014-06-21 | 2014-07-26 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ6SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-06-21 | 2014-07-19 | 2014-06-21 | 2014-07-19 | 16 | No | DUKHCONP1AZ6HDEX5100, DUKHCONP1AZ6HDEX5100 | DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6SLEX5110, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ6SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 16 | No | DUKHCONP1AZ6SLEX5105, DUKHCONP1AZ6SLEX5105 | DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ6ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.35 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ6ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 0 | Yes | DUKHCONP1AZ6HDEX5100, DUKHCONP1AZ6ACRF4635, DUKHCONP1AZ6ARRF3620, DUKHCONP1AZ6AREL3680, DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ6MSEX5005, DUKHCONP1AZ6SLEX5105, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARRF3660, DUKHCONP1AZ5ACTC8000, DUKHCONP1AZ6SLEX5110, DUKHCONP1AZ6ARFF3395 | DUKHHANP1AGNACTC9000, DUKHCONP1AZ7ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ6ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 0 | Yes | DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ6ELGF4030, DUKHCONP1AZ6AREL3680, DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ6MSEX5005, DUKHCONP1AZ6SLEX5105, DUKHCONP1AZ6ELRF4075, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ6HDEX5100, DUKHCONP1AZ6ELFF4055, DUKHCONP1AZ6ELFF4050, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6ARRF3660, DUKHCONP1AZ6SLEX5110, DUKHCONP1AZ6ARRF3620, DUKHCONP1AZ6ARFF3395 | DUKHCONP1AZ7ELTC8010, DUKHHANP1AGNPLTC9005, DUKHHANP1AGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ6PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 0 | Yes | DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ6PLRF4355, DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ6MSEX5005, DUKHCONP1AZ6SLEX5110, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ6SLEX5105, DUKHCONP1AZ6WEEX5065, DUKHCONP1AZ6HDEX5100, DUKHCONP1AZ6PLGF4320, DUKHCONP1AZ6ARRF3620, DUKHCONP1AZ6ARRF3660, DUKHCONP1AZ6AREL3680 | DUKHCONP1AZ7PLTC8005, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.40 ZONE - 7 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-08-08 | 2014-10-16 | 2013-08-08 | 2014-10-16 | 36 |  |  |  | 0 | 0
DHBL.K30.L15.40 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-08-08 | 2014-05-20 | 2013-08-08 | 2014-05-20 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.40 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-08-08 | 2014-01-08 | 2013-08-08 | 2014-01-08 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.40 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-08-08 | 2014-01-08 | 2013-08-08 | 2014-01-08 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ7STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-10-22 | 2013-11-19 | 2013-10-22 | 2013-11-19 | 0 | Yes | DUKHCONP1AZ7STUG1030, DUKHCONP1AZ7STUG1030, DUKHCONP1AZ6STUG1035 | DUKHCONP1AZ7STUG1040, DUKHCONP1AZ8STUG1035, DUKHCONP1AZ7STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-09-17 | 2013-10-09 | 2013-09-17 | 2013-10-09 | 0 | Yes | DUKHCONP1AZ7STUG1015, DUKHCONP1AZ7STUG1015 | DUKHCONP1AZ7STUG1025, DUKHCONP1AZ7STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-11-07 | 2013-12-05 | 2013-11-07 | 2013-12-05 | 0 | Yes | DUKHCONP1AZ7STUG1035, DUKHCONP1AZ7STUG1035 | DUKHCONP1AZ7PLUG4300, DUKHCONP1AZ7PLUG4300, DUKHCONP1AZ7STUG1045, DUKHCONP1AZ7STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-09-26 | 2013-10-27 | 2013-09-26 | 2013-10-27 | 0 | Yes | DUKHCONP1AZ7STUG1020, DUKHCONP1AZ7STUG1020, DUKHCONP1AZ6STUG1025 | DUKHCONP1AZ8STUG1025, DUKHCONP1AZ7STUG1030, DUKHCONP1AZ7STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 0 | Yes | DUKHCONP1AZ7PLUG4300, DUKHCONP1AZ6STUG1045, DUKHCONP1AZ7STUG1040, DUKHCONP1AZ7PLUG4300, DUKHCONP1AZ7STUG1040 | DUKHCONP1AZ8STUG1045, DUKHCONP1AZ7STGF2000, DUKHCONP1AZ7STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-08-24 | 2013-09-18 | 2013-08-24 | 2013-09-18 | 0 | Yes | DUKHCONP1AZ7STUG1000, DUKHCONP1AZ7STUG1000 | DUKHCONP1AZ7STUG1010, DUKHCONP1AZ7STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-08-27 | 2013-09-22 | 2013-08-27 | 2013-09-22 | 0 | Yes | DUKHCONP1AZ7STUG1005, DUKHCONP1AZ7STUG1005 | DUKHCONP1AZ7STUG1015, DUKHCONP1AZ7STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-08-08 | 2013-09-09 | 2013-08-08 | 2013-09-09 | 0 | Yes | DUKHCONP1AGNSP005000, DUKHCONP1AZ6STUG1000 | DUKHCONP1AZ8STUG1000, DUKHCONP1AZ7STUG1005, DUKHCONP1AZ7STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-09-02 | 2013-09-30 | 2013-09-02 | 2013-09-30 | 0 | Yes | DUKHCONP1AZ7STUG1010, DUKHCONP1AZ7STUG1010 | DUKHCONP1AZ7STUG1020, DUKHCONP1AZ7STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ7STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-10-06 | 2013-11-05 | 2013-10-06 | 2013-11-05 | 0 | Yes | DUKHCONP1AZ7STUG1025, DUKHCONP1AZ7STUG1025 | DUKHCONP1AZ7STUG1035, DUKHCONP1AZ7STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.40 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2013-12-28 | 2014-05-20 | 2013-12-28 | 2014-05-20 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.40 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-12-28 | 2014-02-22 | 2013-12-28 | 2014-02-22 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ7STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-02-05 | 2014-02-22 | 2014-02-05 | 2014-02-22 | 2 | No | DUKHCONP1AZ7STGF2010, DUKHCONP1AZ6STGF2015, DUKHCONP1AZ7STGF2010 | DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ8STGF2015, DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ7STFF2020, DUKHCONP1AZ7STFF2020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 2 | No | DUKHCONP1AZ7STGF2005, DUKHCONP1AZ7STGF2005 | DUKHCONP1AZ7STGF2015, DUKHCONP1AZ7STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7STGF2005 | Column-Concrete | 24 | 24 | 0% | 2014-01-05 | 2014-02-01 | 2014-01-05 | 2014-02-01 | 2 | No | DUKHCONP1AZ7STGF2000, DUKHCONP1AZ7STGF2000 | DUKHCONP1AZ7STGF2010, DUKHCONP1AZ7STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 0 | Yes | DUKHCONP1AZ6STGF2000, DUKHCONP1AZ7STUG1045, DUKHCONP1AZ7STUG1045 | DUKHCONP1AZ7STGF2005, DUKHCONP1AZ7STGF2005, DUKHCONP1AZ8STGF2000 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.40 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2014-02-08 | 2014-04-06 | 2014-02-08 | 2014-04-06 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ7STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-03-22 | 2014-04-06 | 2014-03-22 | 2014-04-06 | 4 | No | DUKHCONP1AZ6STFF2035, DUKHCONP1AZ7STFF2030, DUKHCONP1AZ7STFF2030 | DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ7STRF2040, DUKHCONP1AZ7STRF2040, DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ8STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 4 | No | DUKHCONP1AZ7STFF2025, DUKHCONP1AZ7STFF2025 | DUKHCONP1AZ7STFF2035, DUKHCONP1AZ7STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7STFF2025 | Column-Concrete | 24 | 24 | 0% | 2014-02-18 | 2014-03-17 | 2014-02-18 | 2014-03-17 | 4 | No | DUKHCONP1AZ7STFF2020, DUKHCONP1AZ7STFF2020 | DUKHCONP1AZ7STFF2030, DUKHCONP1AZ7STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 2 | No | DUKHCONP1AZ6STFF2020, DUKHCONP1AZ7STGF2015, DUKHCONP1AZ7STGF2015 | DUKHCONP1AZ7STFF2025, DUKHCONP1AZ7STFF2025, DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ8STFF2020, DUKHCONP1AZ7ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.40 .10 .15 .20 ROOF |  | 50 | 50 | 0% | 2014-03-24 | 2014-05-20 | 2014-03-24 | 2014-05-20 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ7STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-03-27 | 2014-04-15 | 2014-03-27 | 2014-04-15 | 8 | No | DUKHCONP1AZ7STRF2040, DUKHCONP1AZ7STRF2040 | DUKHCONP1AZ7STRF2050, DUKHCONP1AZ7STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ7STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-03-24 | 2014-04-13 | 2014-03-24 | 2014-04-13 | 8 | No | DUKHCONP1AZ7STFF2035, DUKHCONP1AZ7STFF2035, DUKHCONP1AZ6STRF2040 | DUKHCONP1AZ7STRF2045, DUKHCONP1AZ8STRF2040, DUKHCONP1AZ7STRF2045 | 0 | 0 | ROOF
DUKHCONP1AZ7STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 56 | No | DUKHCONP1AZ7STRF2055, DUKHCONP1AZ7STRF2055 | DUKHCONP1AZ7STRF2065, DUKHCONP1AZ7STRF2065, DUKHCONP1AZ7ARRF3630, DUKHCONP1AZ7ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ7STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-04-22 | 2014-05-20 | 2014-04-22 | 2014-05-20 | 52 | No | DUKHCONP1AZ7STRF2060, DUKHCONP1AZ7STRF2060, DUKHCONP1AZ6STRF2065 | DUKHCONP1AZ8STRF2065, DUKHCONP1AZ7ARRF3630, DUKHCONP1AZ7AREL3665, DUKHCONP1AZ7ARRF3630, DUKHCONP1AZ7AREL3665 | 0 | 0 | ROOF
DUKHCONP1AZ7STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-04-09 | 2014-04-23 | 2014-04-09 | 2014-04-23 | 8 | No | DUKHCONP1AZ7STRF2050, DUKHCONP1AZ7STRF2050, DUKHCONP1AZ6STRF2055 | DUKHCONP1AZ8STRF2055, DUKHCONP1AZ7ARRF3600, DUKHCONP1AZ7ARRF3600, DUKHCONP1AZ7MSEX5020, DUKHCONP1AZ7MSEX5000, DUKHCONP1AZ7WEEX5030, DUKHCONP1AZ7MSEX5020, DUKHCONP1AZ7STRF2060, DUKHCONP1AZ7MSEX5000, DUKHCONP1AZ7WEEX5030, DUKHCONP1AZ7STRF2060 | 0 | 0 | ROOF
DUKHCONP1AZ7STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-03-30 | 2014-04-21 | 2014-03-30 | 2014-04-21 | 8 | No | DUKHCONP1AZ7STRF2045, DUKHCONP1AZ7STRF2045 | DUKHCONP1AZ7STRF2055, DUKHCONP1AZ7STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.40 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2014-03-09 | 2014-09-15 | 2014-03-09 | 2014-09-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.40 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2014-03-09 | 2014-09-15 | 2014-03-09 | 2014-09-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.40 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-03-09 | 2014-08-21 | 2014-03-09 | 2014-08-21 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ7ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-06-23 | 2014-07-09 | 2014-06-23 | 2014-07-09 | 21 | No | DUKHCONP1AZ6ARGF3070, DUKHCONP1AZ7ARGF3065, DUKHCONP1AZ7ARGF3065 | DUKHCONP1AZ7ARGF3080, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ7ARGF3075, DUKHCONP1AZ7ARGF3080, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-05-25 | 2014-06-22 | 2014-05-25 | 2014-06-22 | 21 | No | DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ARGF3045 | DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ7ELGF4025, DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ7ELGF4025, DUKHCONP1AZ7ELGF4015, DUKHCONP1AZ7ACGF4605, DUKHCONP1AZ7ELGF4015, DUKHCONP1AZ7ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-06-30 | 2014-07-22 | 2014-06-30 | 2014-07-22 | 31 | No | DUKHCONP1AZ6ARGF3080, DUKHCONP1AZ7ARGF3070, DUKHCONP1AZ7ARGF3070 | DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ8ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3000 | Block work | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 18 | No | DUKHCONP1AZ6ARGF3000, DUKHCONP1AZ7STGF2015, DUKHCONP1AZ7STGF2015 | DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ELGF4000, DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ7ELGF4000, DUKHCONP1AZ7PLGF4310, DUKHCONP1AZ7PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-06-29 | 2014-07-21 | 2014-06-29 | 2014-07-21 | 21 | No | DUKHCONP1AZ7ARGF3070, DUKHCONP1AZ6ARGF3075, DUKHCONP1AZ7ARGF3070 | DUKHCONP1AZ7ARGF3085, DUKHCONP1AZ7ARGF3090, DUKHCONP1AZ7ARGF3090, DUKHCONP1AZ7ARGF3085, DUKHCONP1AZ8ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 18 | No | DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ7PLGF4310, DUKHCONP1AZ7ARGF3015, DUKHCONP1AZ6ARGF3020, DUKHCONP1AZ7ARGF3015, DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ7PLGF4310 | DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ8ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-05-26 | 2014-06-11 | 2014-05-26 | 2014-06-11 | 21 | No | DUKHCONP1AZ7ARGF3010, DUKHCONP1AZ7ARGF3010, DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ARGF3035 | DUKHCONP1AZ7ARGF3050, DUKHCONP1AZ7ARGF3050, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-07-21 | 2014-08-21 | 2014-07-21 | 2014-08-21 | 21 | No | DUKHCONP1AZ7ARGF3030, DUKHCONP1AZ7ARGF3085, DUKHCONP1AZ7ARGF3080, DUKHCONP1AZ7ARGF3090, DUKHCONP1AZ7ARGF3085, DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ7ARGF3070, DUKHCONP1AZ7ARGF3080, DUKHCONP1AZ7ARGF3090, DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ARGF3030, DUKHCONP1AZ7ARGF3070, DUKHCONP1AZ7ACGF4610, DUKHCONP1AZ6ARGF3095, DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ACGF4610 | DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-05-17 | 2014-06-08 | 2014-05-17 | 2014-06-08 | 18 | No | DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ARGF3030, DUKHCONP1AZ7ELGF4010, DUKHCONP1AZ7ARGF3030, DUKHCONP1AZ6ARGF3045, DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ELGF4010 | DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ7ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-04-08 | 2014-05-01 | 2014-04-08 | 2014-05-01 | 26 | No | DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ARGF3005 | DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-06-03 | 2014-06-25 | 2014-06-03 | 2014-06-25 | 21 | No | DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3025 | DUKHCONP1AZ7ARGF3065, DUKHCONP1AZ7ARGF3065, DUKHCONP1AZ7ARGF3085, DUKHCONP1AZ7ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 18 | No | DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ6ARGF3060 | DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ7ELGF4025, DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ7ACGF4605, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ7ELGF4025, DUKHCONP1AZ7PLGF4320, DUKHCONP1AZ7ELGF4015, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ7PLGF4320, DUKHCONP1AZ7ACGF4605, DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ7ELGF4015, DUKHCONP1AZ7ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-07-12 | 2014-07-28 | 2014-07-12 | 2014-07-28 | 21 | No | DUKHCONP1AZ7ARGF3075, DUKHCONP1AZ7ARGF3075 | DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 32 | No | DUKHCONP1AZ6ARGF3030, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ARGF3005 | DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 18 | No | DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ6ARGF3005, DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ7ELGF4000, DUKHCONP1AZ7ELGF4000 | DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ7ARGF3030, DUKHCONP1AZ7ARGF3015, DUKHCONP1AZ7ARGF3010, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ7ARGF3015, DUKHCONP1AZ7ARGF3010, DUKHCONP1AZ7ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-04-29 | 2014-05-27 | 2014-04-29 | 2014-05-27 | 18 | No | DUKHCONP1AZ6ARGF3025, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ7ARGF3010, DUKHCONP1AZ7ARGF3010 | DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ARGF3050, DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ7ARGF3050, DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-07-07 | 2014-07-29 | 2014-07-07 | 2014-07-29 | 26 | No | DUKHCONP1AZ7ARGF3075, DUKHCONP1AZ7ARGF3075, DUKHCONP1AZ7ARGF3050, DUKHCONP1AZ7ARGF3050 | DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-05-19 | 2014-06-04 | 2014-05-19 | 2014-06-04 | 23 | No | DUKHCONP1AZ7ARGF3010, DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ7ARGF3010, DUKHCONP1AZ7ARGF3025 | DUKHCONP1AZ7ARGF3065, DUKHCONP1AZ7ARGF3040, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3065, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-04-17 | 2014-05-04 | 2014-04-17 | 2014-05-04 | 18 | No | DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ6ARGF3015 | DUKHCONP1AZ8ARGF3015, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ7ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-06-17 | 2014-07-03 | 2014-06-17 | 2014-07-03 | 21 | No | DUKHCONP1AZ7ARGF3035, DUKHCONP1AZ6ARGF3065, DUKHCONP1AZ7ARGF3050, DUKHCONP1AZ7ARGF3050, DUKHCONP1AZ7ARGF3035 | DUKHCONP1AZ7PLGF4315, DUKHCONP1AZ7ARGF3070, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ7ARGF3070, DUKHCONP1AZ7PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.40 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2014-04-20 | 2014-09-15 | 2014-04-20 | 2014-09-15 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ7ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-07-22 | 2014-08-17 | 2014-07-22 | 2014-08-17 | 0 | Yes | DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ6ARFF3370 | DUKHCONP1AZ7ARFF3375, DUKHCONP1AZ7ARFF3380, DUKHCONP1AZ8ARFF3370, DUKHCONP1AZ7ARFF3380, DUKHCONP1AZ7ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-07-29 | 2014-08-24 | 2014-07-29 | 2014-08-24 | 4 | No | DUKHCONP1AZ7ARFF3370, DUKHCONP1AZ7ARFF3370 | DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3300 | Block work | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 | Yes | DUKHCONP1AZ7STFF2035, DUKHCONP1AZ7STFF2035, DUKHCONP1AZ7STFF2020, DUKHCONP1AZ6ARFF3300, DUKHCONP1AZ7STFF2020 | DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ7ELFF4035, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ7ELFF4035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-07-28 | 2014-08-28 | 2014-07-28 | 2014-08-28 | 0 | Yes | DUKHCONP1AZ6ARFF3375, DUKHCONP1AZ7ARFF3370, DUKHCONP1AZ7ARFF3370 | DUKHCONP1AZ7ARFF3390, DUKHCONP1AZ8ARFF3375, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3385, DUKHCONP1AZ7ARFF3385, DUKHCONP1AZ7ARFF3390, DUKHCONP1AZ7ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-06-10 | 2014-07-08 | 2014-06-10 | 2014-07-08 | 0 | Yes | DUKHCONP1AZ6ARFF3320, DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ7ARFF3315, DUKHCONP1AZ7ARFF3315, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ7PLFF4330 | DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ8ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 0 | Yes | DUKHCONP1AZ6ARFF3395, DUKHCONP1AZ7ARFF3335, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ARFF3380, DUKHCONP1AZ7ARFF3375, DUKHCONP1AZ7ARFF3390, DUKHCONP1AZ7ARFF3385, DUKHCONP1AZ7ARFF3330, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ARFF3390, DUKHCONP1AZ7ARFF3350, DUKHCONP1AZ7ARFF3385, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7ARFF3330, DUKHCONP1AZ7ARFF3335, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7ARFF3380, DUKHCONP1AZ7ARFF3350, DUKHCONP1AZ7ARFF3375, DUKHCONP1AZ7ACFF4625, DUKHCONP1AZ7ACFF4625 | DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ7ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-06-30 | 2014-07-22 | 2014-06-30 | 2014-07-22 | 0 | Yes | DUKHCONP1AZ7ELFF4045, DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ7ARFF3330, DUKHCONP1AZ7ARFF3330, DUKHCONP1AZ6ARFF3345, DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ7ELFF4045 | DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-05-22 | 2014-06-15 | 2014-05-22 | 2014-06-15 | 12 | No | DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7ARFF3305 | DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ7ARFF3335, DUKHCONP1AZ7ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-07-08 | 2014-07-30 | 2014-07-08 | 2014-07-30 | 2 | No | DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ7ARFF3325 | DUKHCONP1AZ7ARFF3385, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7ARFF3385, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-07-07 | 2014-08-07 | 2014-07-07 | 2014-08-07 | 0 | Yes | DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ7ARFF3345, DUKHCONP1AZ7ARFF3345, DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ6ARFF3360 | DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ7ELFF4055, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ELFF4050, DUKHCONP1AZ7ELFF4065, DUKHCONP1AZ7ELFF4055, DUKHCONP1AZ7PLFF4340, DUKHCONP1AZ7PLFF4340, DUKHCONP1AZ7ACFF4620, DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ7ELFF4050, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7ACFF4620, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ7ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-08-12 | 2014-09-03 | 2014-08-12 | 2014-09-03 | 0 | Yes | DUKHCONP1AZ7ARFF3350, DUKHCONP1AZ7ARFF3350, DUKHCONP1AZ7ARFF3375, DUKHCONP1AZ7ARFF3375 | DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-08-12 | 2014-09-03 | 2014-08-12 | 2014-09-03 | 1 | No | DUKHCONP1AZ7ARFF3375, DUKHCONP1AZ7ARFF3375 | DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-05-31 | 2014-06-28 | 2014-05-31 | 2014-06-28 | 14 | No | DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7ARFF3305 | DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3345, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-05-14 | 2014-06-11 | 2014-05-14 | 2014-06-11 | 0 | Yes | DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ6ARFF3305, DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ7ELFF4035, DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ7ELFF4035 | DUKHCONP1AZ7AREL3665, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ7AREL3665, DUKHCONP1AZ7ARFF3315, DUKHCONP1AZ7ARFF3330, DUKHCONP1AZ7ARFF3315, DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ7ARFF3310, DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ7ARFF3310, DUKHCONP1AZ7ARFF3330 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 | Yes | DUKHCONP1AZ7ARFF3320, DUKHCONP1AZ6ARFF3325, DUKHCONP1AZ7ARFF3310, DUKHCONP1AZ7ARFF3310, DUKHCONP1AZ7ARFF3320 | DUKHCONP1AZ7ARFF3350, DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ7ARFF3335, DUKHCONP1AZ7ARFF3350, DUKHCONP1AZ7ARFF3345, DUKHCONP1AZ7ARFF3335, DUKHCONP1AZ7ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-07-05 | 2014-07-21 | 2014-07-05 | 2014-07-21 | 8 | No | DUKHCONP1AZ7ARFF3310, DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ7ARFF3310, DUKHCONP1AZ7ARFF3325 | DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-06-03 | 2014-06-19 | 2014-06-03 | 2014-06-19 | 0 | Yes | DUKHCONP1AZ6ARFF3315, DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7ARFF3305 | DUKHCONP1AZ8ARFF3315, DUKHCONP1AZ7ARFF3320, DUKHCONP1AZ7ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-07-22 | 2014-08-11 | 2014-07-22 | 2014-08-11 | 0 | Yes | DUKHCONP1AZ6ARFF3365, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ARFF3335, DUKHCONP1AZ7ARFF3350, DUKHCONP1AZ7ARFF3335, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ARFF3350 | DUKHCONP1AZ7PLFF4335, DUKHCONP1AZ7ARFF3370, DUKHCONP1AZ7ARFF3370, DUKHCONP1AZ7PLFF4335, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ8ARFF3365 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.40 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-05-04 | 2014-07-07 | 2014-05-04 | 2014-07-07 | 57 |  |  |  | 0 | 0
DUKHCONP1AZ7ARRF3600 | Block work | 20 | 20 | 0% | 2014-05-04 | 2014-05-26 | 2014-05-04 | 2014-05-26 | 52 | No | DUKHCONP1AZ7STRF2055, DUKHCONP1AZ7STRF2055, DUKHCONP1AZ6ARRF3600 | DUKHCONP1AZ7ARRF3605, DUKHCONP1AZ8ARRF3600, DUKHCONP1AZ7ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-06-21 | 2014-07-07 | 2014-06-21 | 2014-07-07 | 57 | No | DUKHCONP1AZ7ARRF3695, DUKHCONP1AZ7ARRF3695 | DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7PLTC8005 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-05-26 | 2014-06-11 | 2014-05-26 | 2014-06-11 | 57 | No | DUKHCONP1AZ7ARRF3605, DUKHCONP1AZ7ARRF3605 | DUKHCONP1AZ7ARRF3695, DUKHCONP1AZ7ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-06-03 | 2014-06-25 | 2014-06-03 | 2014-06-25 | 57 | No | DUKHCONP1AZ7ARRF3610, DUKHCONP1AZ7ARRF3610 | DUKHCONP1AZ7AREL3680, DUKHCONP1AZ7ARRF3620, DUKHCONP1AZ7AREL3680, DUKHCONP1AZ7ARRF3620 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-05-12 | 2014-06-03 | 2014-05-12 | 2014-06-03 | 52 | No | DUKHCONP1AZ7ARRF3600, DUKHCONP1AZ7ARRF3600 | DUKHCONP1AZ7ARRF3610, DUKHCONP1AZ7PLRF4345, DUKHCONP1AZ7AREL3665, DUKHCONP1AZ7ARRF3610, DUKHCONP1AZ7PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.40 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-05-26 | 2014-08-16 | 2014-05-26 | 2014-08-16 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.40 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-06-09 | 2014-08-16 | 2014-06-09 | 2014-08-16 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ7ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-06-30 | 2014-07-28 | 2014-06-30 | 2014-07-28 | 21 | No | DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ARRF3645 | DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-07-27 | 2014-08-16 | 2014-07-27 | 2014-08-16 | 26 | No | DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7ARRF3655 | DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 21 | No | DUKHCONP1AZ7ARRF3635, DUKHCONP1AZ7ARRF3635 | DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-07-15 | 2014-08-10 | 2014-07-15 | 2014-08-10 | 21 | No | DUKHCONP1AZ7ARRF3650, DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ6ARRF3655, DUKHCONP1AZ7ARRF3650 | DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ARRF3660, DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ7ARRF3660, DUKHCONP1AZ8ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 21 | No | DUKHCONP1AZ7ARRF3630, DUKHCONP1AZ7ARRF3630 | DUKHCONP1AZ7ARRF3640, DUKHCONP1AZ7ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 21 | No | DUKHCONP1AZ7STRF2060, DUKHCONP1AZ6ARRF3630, DUKHCONP1AZ7STRF2065, DUKHCONP1AZ7STRF2065, DUKHCONP1AZ7STRF2060 | DUKHCONP1AZ8ARRF3630, DUKHCONP1AZ7ARRF3635, DUKHCONP1AZ7ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ7ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-06-22 | 2014-07-20 | 2014-06-22 | 2014-07-20 | 21 | No | DUKHCONP1AZ7ARRF3640, DUKHCONP1AZ7ARRF3640 | DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7ARRF3650, DUKHCONP1AZ7ARRF3650, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7ELRF4070, DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ7ELRF4070 | 0 | 0 | ROOF
DHBL.K30.L15.40 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-05-26 | 2014-07-16 | 2014-05-26 | 2014-07-16 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ7AREL3680 | External Painting | 20 | 20 | 0% | 2014-06-24 | 2014-07-16 | 2014-06-24 | 2014-07-16 | 49 | No | DUKHCONP1AZ7AREL3670, DUKHCONP1AZ7ARRF3695, DUKHCONP1AZ7AREL3670, DUKHCONP1AZ7ARRF3695, DUKHCONP1AZ6AREL3680 | DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ8AREL3680, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ACTC8000 | 0 | 0 | ELEVATION
DUKHCONP1AZ7AREL3665 | External Plastering | 25 | 25 | 0% | 2014-05-26 | 2014-06-23 | 2014-05-26 | 2014-06-23 | 47 | No | DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7STRF2065, DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7STRF2065, DUKHCONP1AZ7ARRF3605, DUKHCONP1AZ6AREL3665 | DUKHCONP1AZ7AREL3670, DUKHCONP1AZ7AREL3670, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP1AZ7AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-06-12 | 2014-07-05 | 2014-06-12 | 2014-07-05 | 49 | No | DUKHCONP1AZ7AREL3665, DUKHCONP1AZ7AREL3665, DUKHCONP1AZ6AREL3670 | DUKHCONP1AZ7AREL3680, DUKHCONP1AZ7AREL3680, DUKHCONP1AZ8AREL3670 | 0 | 0 | ELEVATION
DHBL.K30.L15.40 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-12-01 | 2014-09-14 | 2013-12-01 | 2014-09-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.40 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2014-03-15 | 2014-09-14 | 2014-03-15 | 2014-09-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.40 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-03-15 | 2014-07-21 | 2014-03-15 | 2014-07-21 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ7ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-03-26 | 2014-04-17 | 2014-03-26 | 2014-04-17 | 45 | No | DUKHCONP1AZ7ELGF4000, DUKHCONP1AZ7ELGF4000, DUKHCONP1AZ6ELGF4005 | DUKHCONP1AZ7ELGF4010, DUKHCONP1AZ7ELGF4010, DUKHCONP1AZ8ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 27 | No | DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ7ARGF3000 | DUKHCONP1AZ7ELGF4005, DUKHCONP1AZ7ELGF4005, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-06-05 | 2014-07-03 | 2014-06-05 | 2014-07-03 | 30 | No | DUKHCONP1AZ6ELGF4015, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3060 | DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ELFF4055, DUKHCONP1AZ7ELFF4055, DUKHCONP1AZ8ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-06-11 | 2014-07-03 | 2014-06-11 | 2014-07-03 | 18 | No | DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ELGF4010, DUKHCONP1AZ7ELGF4010, DUKHCONP1AZ7ARGF3060 | DUKHCONP1AZ7ELGF4025, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ7ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 25 | No | DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ6ELGF4025, DUKHCONP1AZ7ELGF4020 | DUKHCONP1AZ7ELFF4065, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ7ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-06-23 | 2014-07-15 | 2014-06-23 | 2014-07-15 | 18 | No | DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ6ELGF4030 | DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ7ELFF4050, DUKHCONP1AZ7ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 45 | No | DUKHCONP1AZ7ELGF4005, DUKHCONP1AZ7ELGF4005 | DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ELGF4020, DUKHCONP1AZ7ARGF3045, DUKHCONP1AZ7ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.40 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2014-04-26 | 2014-08-27 | 2014-04-26 | 2014-08-27 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ7ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-05-07 | 2014-05-29 | 2014-05-07 | 2014-05-29 | 29 | No | DUKHCONP1AZ7ELFF4035, DUKHCONP1AZ7ELFF4035 | DUKHCONP1AZ7ELFF4045, DUKHCONP1AZ7ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 11 | No | DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ7ARFF3300 | DUKHCONP1AZ7ELFF4040, DUKHCONP1AZ7ELFF4040, DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-07-15 | 2014-08-16 | 2014-07-15 | 2014-08-16 | 1 | No | DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ELGF4015, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ6ELFF4055, DUKHCONP1AZ7ELGF4015 | DUKHCONP1AZ8ELFF4055, DUKHCONP1AZ7ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-07-19 | 2014-08-13 | 2014-07-19 | 2014-08-13 | 3 | No | DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ELFF4045, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ELFF4045, DUKHCONP1AZ6ELFF4060 | DUKHCONP1AZ7ELFF4065, DUKHCONP1AZ7ELFF4065, DUKHCONP1AZ8ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-07-27 | 2014-08-27 | 2014-07-27 | 2014-08-27 | 1 | No | DUKHCONP1AZ7ELGF4025, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ6ELFF4065, DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ELGF4025 | DUKHCONP1AZ7ELRF4070, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 8 | No | DUKHCONP1AZ7MSEX5010, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ7ELGF4030 | DUKHCONP1AZ7ELRF4070, DUKHCONP1AZ7ELRF4070, DUKHCONP1AZ7ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-05-18 | 2014-06-15 | 2014-05-18 | 2014-06-15 | 27 | No | DUKHCONP1AZ7ELFF4040, DUKHCONP1AZ6ELFF4045, DUKHCONP1AZ7ELFF4040 | DUKHCONP1AZ7ARFF3345, DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ7ELRF4070, DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ7ELRF4070, DUKHCONP1AZ7ARFF3345 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.40 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-08-13 | 2014-09-14 | 2014-08-13 | 2014-09-14 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ7ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-08-13 | 2014-09-02 | 2014-08-13 | 2014-09-02 | 1 | No | DUKHCONP1AZ7ELFF4050, DUKHCONP1AZ7ELFF4065, DUKHCONP1AZ7ELFF4050, DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ELFF4045, DUKHCONP1AZ7ELFF4045, DUKHCONP1AZ7ELFF4065 | DUKHCONP1AZ7ELRF4075, DUKHCONP1AZ7ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ7ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-08-19 | 2014-09-14 | 2014-08-19 | 2014-09-14 | 1 | No | DUKHCONP1AZ7ELRF4070, DUKHCONP1AZ7ELRF4070 | DUKHCONP1AZ7ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.40 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-12-01 | 2014-09-14 | 2013-12-01 | 2014-09-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.40 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-12-01 | 2014-07-21 | 2013-12-01 | 2014-07-21 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ7PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-12-01 | 2013-12-19 | 2013-12-01 | 2013-12-19 | 0 | Yes | DUKHCONP1AZ7STUG1040, DUKHCONP1AZ7STUG1040 | DUKHCONP1AZ7STUG1045, DUKHCONP1AZ7STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-03-25 | 2014-04-14 | 2014-03-25 | 2014-04-14 | 21 | No | DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ7PLGF4305 | DUKHCONP1AZ7MSEX5000, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ7PLGF4315, DUKHCONP1AZ7MSEX5000, DUKHCONP1AZ7PLGF4315, DUKHCONP1AZ7ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-03-25 | 2014-04-14 | 2014-03-25 | 2014-04-14 | 18 | No | DUKHCONP1AZ6PLGF4305, DUKHCONP1AZ7ARGF3000, DUKHCONP1AZ7ARGF3000 | DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ7PLGF4310, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ7PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-07-05 | 2014-07-21 | 2014-07-05 | 2014-07-21 | 45 | No | DUKHCONP1AZ6PLGF4320, DUKHCONP1AZ7PLGF4315, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7PLGF4315 | DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ8PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-06-23 | 2014-07-15 | 2014-06-23 | 2014-07-15 | 45 | No | DUKHCONP1AZ6PLGF4315, DUKHCONP1AZ7PLGF4310, DUKHCONP1AZ7PLGF4310, DUKHCONP1AZ7ARGF3065, DUKHCONP1AZ7ARGF3065 | DUKHCONP1AZ7PLGF4320, DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ7PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.40 .20 .15 .15 FIRST FLOORS |  | 90 | 90 | 0% | 2014-05-07 | 2014-08-23 | 2014-05-07 | 2014-08-23 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ7PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-05-07 | 2014-05-27 | 2014-05-07 | 2014-05-27 | 22 | No | DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ7PLFF4325, DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ6PLFF4330 | DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ7PLFF4335, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7PLFF4335, DUKHCONP1AZ7ARFF3320, DUKHCONP1AZ7ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-05-07 | 2014-05-27 | 2014-05-07 | 2014-05-27 | 0 | Yes | DUKHCONP1AZ7ARFF3300, DUKHCONP1AZ7ARFF3300 | DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7ARFF3320, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ7ARFF3320, DUKHCONP1AZ7ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-08-06 | 2014-08-23 | 2014-08-06 | 2014-08-23 | 5 | No | DUKHCONP1AZ7PLFF4335, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ6PLFF4340, DUKHCONP1AZ7PLFF4335 | DUKHCONP1AZ8PLFF4340, DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ7PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-07-22 | 2014-08-17 | 2014-07-22 | 2014-08-17 | 5 | No | DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ7ARFF3365, DUKHCONP1AZ7PLFF4330 | DUKHCONP1AZ7PLFF4340, DUKHCONP1AZ7PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.40 .20 .15 .20 ROOF |  | 93 | 93 | 0% | 2014-05-26 | 2014-09-14 | 2014-05-26 | 2014-09-14 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ7PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-05-26 | 2014-06-11 | 2014-05-26 | 2014-06-11 | 56 | No | DUKHCONP1AZ7ARRF3605, DUKHCONP1AZ7ARRF3605 | DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ7PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-07-09 | 2014-07-26 | 2014-07-09 | 2014-07-26 | 26 | No | DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ7PLRF4345, DUKHCONP1AZ7PLRF4345, DUKHCONP1AZ6PLRF4350, DUKHCONP1AZ7AREL3665, DUKHCONP1AZ7AREL3665 | DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ7WEEX5065, DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ7WEEX5065, DUKHCONP1AZ7PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ7PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 1 | No | DUKHCONP1AZ6PLRF4355, DUKHCONP1AZ7PLRF4345, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7PLFF4340, DUKHCONP1AZ7PLFF4340, DUKHCONP1AZ7PLRF4345, DUKHCONP1AZ7PLRF4350 | DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ7PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L15.40 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2014-04-14 | 2014-09-11 | 2014-04-14 | 2014-09-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.40 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-04-14 | 2014-07-19 | 2014-04-14 | 2014-07-19 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ7ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-06-26 | 2014-07-19 | 2014-06-26 | 2014-07-19 | 32 | No | DUKHCONP1AZ6ACGF4610, DUKHCONP1AZ7ACGF4605, DUKHCONP1AZ7ACGF4605 | DUKHCONP1AZ8ACGF4610, DUKHCONP1AZ7ACRF4635, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ACRF4635, DUKHCONP1AZ7ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-06-05 | 2014-07-03 | 2014-06-05 | 2014-07-03 | 32 | No | DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ6ACGF4605, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ7ARGF3055 | DUKHCONP1AZ7ACGF4610, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ7ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ7ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-04-14 | 2014-05-06 | 2014-04-14 | 2014-05-06 | 49 | No | DUKHCONP1AZ6ACGF4600, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ7ARGF3005 | DUKHCONP1AZ7ACGF4605, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3055, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ7ACGF4605, DUKHCONP1AZ7ACRF4630 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.40 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-05-28 | 2014-08-31 | 2014-05-28 | 2014-08-31 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ7ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-08-09 | 2014-08-31 | 2014-08-09 | 2014-08-31 | 2 | No | DUKHCONP1AZ6ACFF4625, DUKHCONP1AZ7ACFF4620, DUKHCONP1AZ7ACFF4620 | DUKHCONP1AZ7ACRF4635, DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ7ACRF4635, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-07-15 | 2014-08-16 | 2014-07-15 | 2014-08-16 | 2 | No | DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ6ACFF4620, DUKHCONP1AZ7ARFF3360 | DUKHCONP1AZ7ACFF4625, DUKHCONP1AZ7ACFF4625, DUKHCONP1AZ8ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ7ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-05-28 | 2014-06-19 | 2014-05-28 | 2014-06-19 | 27 | No | DUKHCONP1AZ6ACFF4615, DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ7ARFF3305 | DUKHCONP1AZ7ACFF4620, DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ7ACFF4620, DUKHCONP1AZ7ARFF3360, DUKHCONP1AZ7ACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.40 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-06-30 | 2014-09-11 | 2014-06-30 | 2014-09-11 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ7ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-08-14 | 2014-09-11 | 2014-08-14 | 2014-09-11 | 3 | No | DUKHCONP1AZ7ACFF4625, DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ7ACGF4610, DUKHCONP1AZ7ACFF4625, DUKHCONP1AZ6ACRF4635, DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ7ACGF4610 | DUKHCONP1AZ8ACRF4635, DUKHCONP1AZ7ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ7ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-06-30 | 2014-07-28 | 2014-06-30 | 2014-07-28 | 34 | No | DUKHCONP1AZ6ACRF4630, DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ7ARRF3645, DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ7ACGF4600 | DUKHCONP1AZ7ACRF4635, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ7ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.40 .25 EXTERNAL WORKS |  | 122 | 122 | 0% | 2014-04-21 | 2014-09-13 | 2014-04-21 | 2014-09-13 | 63 |  |  |  | 0 | 0
DHBL.K30.L15.40 .25 .10 MISCELLANEOUS |  | 122 | 122 | 0% | 2014-04-21 | 2014-09-13 | 2014-04-21 | 2014-09-13 | 63 |  |  |  | 0 | 0
DUKHCONP1AZ7MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-08-16 | 2014-09-13 | 2014-08-16 | 2014-09-13 | 63 | No | DUKHCONP1AZ6MSEX5335, DUKHCONI1AZ4BWGL5325 | DUKHCONP1AZ8MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ7MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-05-05 | 2014-06-02 | 2014-05-05 | 2014-06-02 | 8 | No | DUKHCONP1AZ7MSEX5000, DUKHCONP1AZ7MSEX5000 | DUKHCONP1AZ7MSEX5015, DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ7MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ7MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-06-11 | 2014-07-09 | 2014-06-11 | 2014-07-09 | 16 | No | DUKHCONP1AZ7STRF2055, DUKHCONP1AZ6MSEX5020, DUKHCONP1AZ7STRF2055 | DUKHCONP1AZ8MSEX5020, DUKHCONP1AZ7MSEX5025, DUKHCONP1AZ7MSEX5025, DUKHCONP1AZ7HDEX5090, DUKHCONP1AZ7HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ7MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-05-25 | 2014-06-16 | 2014-05-25 | 2014-06-16 | 8 | No | DUKHCONP1AZ7MSEX5005, DUKHCONP1AZ7MSEX5005 | DUKHCONP1AZ7WEEX5065, DUKHCONP1AZ7MSEX5010, DUKHCONP1AZ7WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ7MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-04-21 | 2014-05-19 | 2014-04-21 | 2014-05-19 | 8 | No | DUKHCONP1AZ7PLGF4310, DUKHCONP1AZ7PLGF4310, DUKHCONP1AZ7STRF2055, DUKHCONP1AZ7STRF2055 | DUKHCONP1AZ7MSEX5005, DUKHCONP1AZ7MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ7MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-06-29 | 2014-07-21 | 2014-06-29 | 2014-07-21 | 19 | No | DUKHCONP1AZ7MSEX5020, DUKHCONP1AZ7MSEX5020 | DUKHCONP1AZ7WEEX5060, DUKHCONP1AZ7WEEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ7MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 8 | No | DUKHCONP1AZ7MSEX5015 | DUKHCONP1AZ7ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.40 .25 .15 WATER TANK ENCLOSURE |  | 95 | 95 | 0% | 2014-05-14 | 2014-09-04 | 2014-05-14 | 2014-09-04 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ7WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 38 | No | DUKHCONP1AZ7WEEX5035, DUKHCONP1AZ7WEEX5035 | DUKHCONP1AZ7WEEX5045, DUKHCONP1AZ7WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ7WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-05-20 | 2014-06-17 | 2014-05-20 | 2014-06-17 | 38 | No | DUKHCONP1AZ7WEEX5030, DUKHCONP1AZ7WEEX5030 | DUKHCONP1AZ7WEEX5040, DUKHCONP1AZ7WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ7WEEX5030 | Excavation | 20 | 20 | 0% | 2014-05-14 | 2014-06-05 | 2014-05-14 | 2014-06-05 | 38 | No | DUKHCONP1AZ6WEEX5030, DUKHCONP1AZ7STRF2055, DUKHCONP1AZ7STRF2055 | DUKHCONP1AZ7WEEX5035, DUKHCONP1AZ7WEEX5035, DUKHCONP1AZ8WEEX5030 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ7WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-06-05 | 2014-07-03 | 2014-06-05 | 2014-07-03 | 38 | No | DUKHCONP1AZ7WEEX5040, DUKHCONP1AZ7WEEX5040 | DUKHCONP1AZ7WEEX5050, DUKHCONP1AZ7WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ7WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-08-07 | 2014-09-04 | 2014-08-07 | 2014-09-04 | 9 | No | DUKHCONP1AZ7WEEX5060, DUKHCONP1AZ6WEEX5065, DUKHCONP1AZ7WEEX5060, DUKHCONP1AZ7MSEX5015, DUKHCONP1AZ7MSEX5015, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7PLRF4350 | DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ8WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ7WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-07-10 | 2014-08-05 | 2014-07-10 | 2014-08-05 | 19 | No | DUKHCONP1AZ7WEEX5045, DUKHCONP1AZ7WEEX5045, DUKHCONP1AZ7MSEX5025 | DUKHCONP1AZ7WEEX5060, DUKHCONP1AZ7WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ7WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-07-27 | 2014-08-27 | 2014-07-27 | 2014-08-27 | 10 | No | DUKHCONP1AZ7WEEX5050, DUKHCONP1AZ7WEEX5050, DUKHCONP1AZ6WEEX5060, DUKHCONP1AZ7MSEX5025 | DUKHCONP1AZ7WEEX5065, DUKHCONP1AZ8WEEX5060, DUKHCONP1AZ7WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.40 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-06-25 | 2014-08-09 | 2014-06-25 | 2014-08-09 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ7HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-07-07 | 2014-07-29 | 2014-07-07 | 2014-07-29 | 16 | No | DUKHCONP1AZ7HDEX5090, DUKHCONP1AZ7HDEX5090 | DUKHCONP1AZ7HDEX5100, DUKHCONP1AZ7HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ7HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-07-14 | 2014-08-09 | 2014-07-14 | 2014-08-09 | 16 | No | DUKHCONP1AZ7HDEX5095, DUKHCONP1AZ7HDEX5095 | DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7SLEX5105, DUKHCONP1AZ7SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ7HDEX5090 | kerb works | 20 | 20 | 0% | 2014-06-25 | 2014-07-17 | 2014-06-25 | 2014-07-17 | 16 | No | DUKHCONP1AZ7MSEX5020, DUKHCONP1AZ6HDEX5090, DUKHCONP1AZ7MSEX5020 | DUKHCONP1AZ7HDEX5095, DUKHCONP1AZ7HDEX5095, DUKHCONP1AZ8HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.40 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-07-20 | 2014-08-27 | 2014-07-20 | 2014-08-27 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ7SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-07-20 | 2014-08-20 | 2014-07-20 | 2014-08-20 | 16 | No | DUKHCONP1AZ7HDEX5100, DUKHCONP1AZ7HDEX5100 | DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ7SLEX5110, DUKHCONP1AZ7SLEX5110, DUKHCONP1AZ7PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ7SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-07-27 | 2014-08-27 | 2014-07-27 | 2014-08-27 | 16 | No | DUKHCONP1AZ7SLEX5105, DUKHCONP1AZ7SLEX5105 | DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ7PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.40 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-09-16 | 2014-10-16 | 2014-09-16 | 2014-10-16 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ7ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-09-16 | 2014-10-16 | 2014-09-16 | 2014-10-16 | 0 | Yes | DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7HDEX5100, DUKHCONP1AZ7SLEX5105, DUKHCONP1AZ7ARRF3660, DUKHCONP1AZ7ACRF4635, DUKHCONP1AZ7SLEX5110, DUKHCONP1AZ7ARRF3620, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ7MSEX5005, DUKHCONP1AZ7AREL3680, DUKHCONP1AZ7ACFF4625 | DUKHHANP1AGNACTC9000, DUKHCONP1AZ8ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ7ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-09-16 | 2014-10-16 | 2014-09-16 | 2014-10-16 | 0 | Yes | DUKHCONP1AZ7ELFF4055, DUKHCONP1AZ7HDEX5100, DUKHCONP1AZ7SLEX5105, DUKHCONP1AZ7SLEX5110, DUKHCONP1AZ7ELGF4015, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7ARRF3660, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ7MSEX5005, DUKHCONP1AZ7ELRF4075, DUKHCONP1AZ7ELFF4050, DUKHCONP1AZ7ELGF4025, DUKHCONP1AZ7AREL3680, DUKHCONP1AZ7ARRF3620, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ7ELFF4065 | DUKHCONP1AZ8ELTC8010, DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ7PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-09-16 | 2014-10-16 | 2014-09-16 | 2014-10-16 | 0 | Yes | DUKHCONP1AZ7HDEX5100, DUKHCONP1AZ7WEEX5065, DUKHCONP1AZ7ARRF3660, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ7AREL3680, DUKHCONP1AZ7PLGF4320, DUKHCONP1AZ7MSEX5005, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ7ARRF3655, DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ7SLEX5110, DUKHCONP1AZ7ARRF3620, DUKHCONP1AZ7SLEX5105 | DUKHCONP1AZ8PLTC8005, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.45 ZONE - 8 (4 Twin Villas) |  | 361 | 361 | 0% | 2013-09-10 | 2014-11-15 | 2013-09-10 | 2014-11-15 | 18 |  |  |  | 0 | 0
DHBL.K30.L15.45 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-09-10 | 2014-06-18 | 2013-09-10 | 2014-06-18 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.45 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-09-10 | 2014-02-06 | 2013-09-10 | 2014-02-06 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.45 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-09-10 | 2014-02-06 | 2013-09-10 | 2014-02-06 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ8STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-11-20 | 2013-12-19 | 2013-11-20 | 2013-12-19 | 0 | Yes | DUKHCONP1AZ8STUG1030, DUKHCONP1AZ8STUG1030, DUKHCONP1AZ7STUG1035 | DUKHCONP1AZ8STUG1040, DUKHCONP1AZ9STUG1035, DUKHCONP1AZ8STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-10-16 | 2013-11-10 | 2013-10-16 | 2013-11-10 | 0 | Yes | DUKHCONP1AZ8STUG1015, DUKHCONP1AZ8STUG1015 | DUKHCONP1AZ8STUG1025, DUKHCONP1AZ8STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-12-07 | 2014-01-05 | 2013-12-07 | 2014-01-05 | 0 | Yes | DUKHCONP1AZ8STUG1035, DUKHCONP1AZ8STUG1035 | DUKHCONP1AZ8STUG1045, DUKHCONP1AZ8PLUG4300, DUKHCONP1AZ8STUG1045, DUKHCONP1AZ8PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-10-28 | 2013-11-25 | 2013-10-28 | 2013-11-25 | 0 | Yes | DUKHCONP1AZ8STUG1020, DUKHCONP1AZ7STUG1025, DUKHCONP1AZ8STUG1020 | DUKHCONP1AZ8STUG1030, DUKHCONP1AZ9STUG1025, DUKHCONP1AZ8STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2014-01-09 | 2014-02-06 | 2014-01-09 | 2014-02-06 | 0 | Yes | DUKHCONP1AZ8STUG1040, DUKHCONP1AZ8PLUG4300, DUKHCONP1AZ7STUG1045, DUKHCONP1AZ8STUG1040, DUKHCONP1AZ8PLUG4300 | DUKHCONP1AZ9STUG1045, DUKHCONP1AZ8STGF2000, DUKHCONP1AZ8STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-09-22 | 2013-10-20 | 2013-09-22 | 2013-10-20 | 0 | Yes | DUKHCONP1AZ8STUG1000, DUKHCONP1AZ8STUG1000 | DUKHCONP1AZ8STUG1010, DUKHCONP1AZ8STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-09-25 | 2013-10-23 | 2013-09-25 | 2013-10-23 | 0 | Yes | DUKHCONP1AZ8STUG1005, DUKHCONP1AZ8STUG1005 | DUKHCONP1AZ8STUG1015, DUKHCONP1AZ8STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-09-10 | 2013-10-08 | 2013-09-10 | 2013-10-08 | 0 | Yes | DUKHCONP1AZ7STUG1000, DUKHCONP1AGNSP005000 | DUKHCONP1AZ8STUG1005, DUKHCONP1AZ8STUG1005, DUKHCONP1AZ9STUG1000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-10-01 | 2013-10-31 | 2013-10-01 | 2013-10-31 | 0 | Yes | DUKHCONP1AZ8STUG1010, DUKHCONP1AZ8STUG1010 | DUKHCONP1AZ8STUG1020, DUKHCONP1AZ8STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ8STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-11-06 | 2013-12-04 | 2013-11-06 | 2013-12-04 | 0 | Yes | DUKHCONP1AZ8STUG1025, DUKHCONP1AZ8STUG1025 | DUKHCONP1AZ8STUG1035, DUKHCONP1AZ8STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.45 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2014-01-26 | 2014-06-18 | 2014-01-26 | 2014-06-18 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.45 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2014-01-26 | 2014-03-23 | 2014-01-26 | 2014-03-23 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ8STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-03-08 | 2014-03-23 | 2014-03-08 | 2014-03-23 | 2 | No | DUKHCONP1AZ8STGF2010, DUKHCONP1AZ7STGF2015, DUKHCONP1AZ8STGF2010 | DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ9STGF2015, DUKHCONP1AZ8STFF2020, DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ8STFF2020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-02-19 | 2014-03-19 | 2014-02-19 | 2014-03-19 | 2 | No | DUKHCONP1AZ8STGF2005, DUKHCONP1AZ8STGF2005 | DUKHCONP1AZ8STGF2015, DUKHCONP1AZ8STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8STGF2005 | Column-Concrete | 24 | 24 | 0% | 2014-02-03 | 2014-03-03 | 2014-02-03 | 2014-03-03 | 2 | No | DUKHCONP1AZ8STGF2000, DUKHCONP1AZ8STGF2000 | DUKHCONP1AZ8STGF2010, DUKHCONP1AZ8STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 0 | Yes | DUKHCONP1AZ8STUG1045, DUKHCONP1AZ8STUG1045, DUKHCONP1AZ7STGF2000 | DUKHCONP1AZ8STGF2005, DUKHCONP1AZ8STGF2005, DUKHCONP1AZ9STGF2000 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.45 .10 .15 .15 FIRST FLOORS |  | 49 | 49 | 0% | 2014-03-10 | 2014-05-05 | 2014-03-10 | 2014-05-05 | 4 |  |  |  | 0 | 0
DUKHCONP1AZ8STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-04-20 | 2014-05-05 | 2014-04-20 | 2014-05-05 | 4 | No | DUKHCONP1AZ8STFF2030, DUKHCONP1AZ8STFF2030, DUKHCONP1AZ7STFF2035 | DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ8STRF2040, DUKHCONP1AZ8STRF2040, DUKHCONP1AZ9STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 4 | No | DUKHCONP1AZ8STFF2025, DUKHCONP1AZ8STFF2025 | DUKHCONP1AZ8STFF2035, DUKHCONI1AZ5DRGL5115, DUKHCONP1AZ8STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8STFF2025 | Column-Concrete | 24 | 24 | 0% | 2014-03-19 | 2014-04-15 | 2014-03-19 | 2014-04-15 | 4 | No | DUKHCONP1AZ8STFF2020, DUKHCONP1AZ8STFF2020 | DUKHCONP1AZ8STFF2030, DUKHCONP1AZ8STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 2 | No | DUKHCONP1AZ8STGF2015, DUKHCONP1AZ8STGF2015, DUKHCONP1AZ7STFF2020 | DUKHCONP1AZ8STFF2025, DUKHCONP1AZ8STFF2025, DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ9STFF2020 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.45 .10 .15 .20 ROOF |  | 50 | 50 | 0% | 2014-04-22 | 2014-06-18 | 2014-04-22 | 2014-06-18 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ8STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-04-26 | 2014-05-14 | 2014-04-26 | 2014-05-14 | 8 | No | DUKHCONP1AZ8STRF2040, DUKHCONP1AZ8STRF2040 | DUKHCONP1AZ8STRF2050, DUKHCONP1AZ8STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ8STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-04-22 | 2014-05-12 | 2014-04-22 | 2014-05-12 | 8 | No | DUKHCONP1AZ7STRF2040, DUKHCONP1AZ8STFF2035, DUKHCONP1AZ8STFF2035 | DUKHCONP1AZ8STRF2045, DUKHCONP1AZ9STRF2040, DUKHCONP1AZ8STRF2045 | 0 | 0 | ROOF
DUKHCONP1AZ8STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 56 | No | DUKHCONP1AZ8STRF2055, DUKHCONP1AZ8STRF2055 | DUKHCONP1AZ8ARRF3630, DUKHCONP1AZ8ARRF3630, DUKHCONP1AZ8STRF2065, DUKHCONP1AZ8STRF2065 | 0 | 0 | ROOF
DUKHCONP1AZ8STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-05-21 | 2014-06-18 | 2014-05-21 | 2014-06-18 | 52 | No | DUKHCONP1AZ7STRF2065, DUKHCONP1AZ8STRF2060, DUKHCONP1AZ8STRF2060 | DUKHCONP1AZ8ARRF3630, DUKHCONP1AZ9STRF2065, DUKHCONP1AZ8ARRF3630, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ8AREL3665 | 0 | 0 | ROOF
DUKHCONP1AZ8STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-05-08 | 2014-05-22 | 2014-05-08 | 2014-05-22 | 8 | No | DUKHCONP1AZ7STRF2055, DUKHCONP1AZ8STRF2050, DUKHCONP1AZ8STRF2050 | DUKHCONP1AZ8STRF2060, DUKHCONP1AZ8MSEX5000, DUKHCONP1AZ8MSEX5020, DUKHCONP1AZ8MSEX5020, DUKHCONP1AZ8WEEX5030, DUKHCONP1AZ8WEEX5030, DUKHCONP1AZ8STRF2060, DUKHCONP1AZ9STRF2055, DUKHCONP1AZ8MSEX5000, DUKHCONP1AZ8ARRF3600, DUKHCONP1AZ8ARRF3600 | 0 | 0 | ROOF
DUKHCONP1AZ8STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-04-28 | 2014-05-20 | 2014-04-28 | 2014-05-20 | 8 | No | DUKHCONP1AZ8STRF2045, DUKHCONP1AZ8STRF2045 | DUKHCONP1AZ8STRF2055, DUKHCONP1AZ8STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.45 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2014-04-07 | 2014-10-16 | 2014-04-07 | 2014-10-16 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.45 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2014-04-07 | 2014-10-16 | 2014-04-07 | 2014-10-16 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.45 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-04-07 | 2014-09-20 | 2014-04-07 | 2014-09-20 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ8ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-07-22 | 2014-08-11 | 2014-07-22 | 2014-08-11 | 21 | No | DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ7ARGF3070 | DUKHCONP1AZ8ARGF3075, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3075, DUKHCONP1AZ9ARGF3070, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3080, DUKHCONP1AZ8ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 21 | No | DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ8ARGF3045 | DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ELGF4015, DUKHCONP1AZ8ELGF4015, DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ8ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-07-29 | 2014-08-24 | 2014-07-29 | 2014-08-24 | 31 | No | DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ7ARGF3080 | DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ9ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3000 | Block work | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 18 | No | DUKHCONP1AZ8STGF2015, DUKHCONP1AZ8STGF2015, DUKHCONP1AZ7ARGF3000 | DUKHCONP1AZ8PLGF4310, DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ8ELGF4000, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8ELGF4000, DUKHCONP1AZ8PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-07-28 | 2014-08-23 | 2014-07-28 | 2014-08-23 | 21 | No | DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ7ARGF3075 | DUKHCONP1AZ8ARGF3085, DUKHCONP1AZ8ARGF3090, DUKHCONP1AZ8ARGF3090, DUKHCONP1AZ9ARGF3075, DUKHCONP1AZ8ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 18 | No | DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8PLGF4310, DUKHCONP1AZ8PLGF4310, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8ARGF3015, DUKHCONP1AZ7ARGF3020, DUKHCONP1AZ8ARGF3015 | DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ8ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-06-24 | 2014-07-10 | 2014-06-24 | 2014-07-10 | 21 | No | DUKHCONP1AZ8ARGF3010, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3010, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3035 | DUKHCONP1AZ8ARGF3050, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-08-23 | 2014-09-20 | 2014-08-23 | 2014-09-20 | 21 | No | DUKHCONP1AZ8ARGF3080, DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3080, DUKHCONP1AZ8ARGF3090, DUKHCONP1AZ7ARGF3095, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ8ARGF3085, DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ACGF4610, DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ8ARGF3090, DUKHCONP1AZ8ACGF4610, DUKHCONP1AZ8ARGF3085 | DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-06-15 | 2014-07-07 | 2014-06-15 | 2014-07-07 | 18 | No | DUKHCONP1AZ8ELGF4010, DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ELGF4010, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ7ARGF3045 | DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-05-07 | 2014-05-31 | 2014-05-07 | 2014-05-31 | 26 | No | DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ8ARGF3005 | DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-07-02 | 2014-07-24 | 2014-07-02 | 2014-07-24 | 21 | No | DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3040 | DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ8ARGF3085, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ8ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-06-26 | 2014-07-24 | 2014-06-26 | 2014-07-24 | 18 | No | DUKHCONP1AZ7ARGF3060, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ8ACGF4600 | DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ8ELGF4015, DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ8PLGF4320, DUKHCONP1AZ8PLGF4320, DUKHCONP1AZ8ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-08-13 | 2014-08-30 | 2014-08-13 | 2014-08-30 | 21 | No | DUKHCONP1AZ8ARGF3075, DUKHCONP1AZ8ARGF3075 | DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 32 | No | DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ7ARGF3030 | DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ9ARGF3030, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-04-29 | 2014-05-27 | 2014-04-29 | 2014-05-27 | 18 | No | DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ7ARGF3005, DUKHCONP1AZ8ELGF4000, DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8ELGF4000 | DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ8ARGF3010, DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ8ARGF3015, DUKHCONP1AZ8ARGF3015, DUKHCONP1AZ8ARGF3010, DUKHCONP1AZ8ACGF4600 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 18 | No | DUKHCONP1AZ7ARGF3025, DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ8ARGF3010, DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ8ARGF3010 | DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ8ARGF3050, DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3050, DUKHCONP1AZ8ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-08-09 | 2014-08-31 | 2014-08-09 | 2014-08-31 | 26 | No | DUKHCONP1AZ8ARGF3075, DUKHCONP1AZ8ARGF3050, DUKHCONP1AZ8ARGF3050, DUKHCONP1AZ8ARGF3075 | DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-06-17 | 2014-07-03 | 2014-06-17 | 2014-07-03 | 23 | No | DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ8ARGF3010, DUKHCONP1AZ8ARGF3010 | DUKHCONP1AZ8ARGF3040, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ8ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-05-17 | 2014-06-02 | 2014-05-17 | 2014-06-02 | 18 | No | DUKHCONP1AZ7ARGF3015, DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ8ARGF3005 | DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ9ARGF3015, DUKHCONP1AZ8ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-07-16 | 2014-08-05 | 2014-07-16 | 2014-08-05 | 21 | No | DUKHCONP1AZ8ARGF3050, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3035, DUKHCONP1AZ8ARGF3050, DUKHCONP1AZ7ARGF3065 | DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ9ARGF3065 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.45 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2014-05-19 | 2014-10-16 | 2014-05-19 | 2014-10-16 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ8ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-08-24 | 2014-09-15 | 2014-08-24 | 2014-09-15 | 0 | Yes | DUKHCONP1AZ7ARFF3370, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8ARFF3365 | DUKHCONP1AZ8ARFF3380, DUKHCONP1AZ8ARFF3380, DUKHCONP1AZ8ARFF3375, DUKHCONP1AZ8ARFF3375, DUKHCONP1AZ9ARFF3370 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-08-31 | 2014-09-22 | 2014-08-31 | 2014-09-22 | 4 | No | DUKHCONP1AZ8ARFF3370, DUKHCONP1AZ8ARFF3370 | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3300 | Block work | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 0 | Yes | DUKHCONP1AZ8STFF2035, DUKHCONP1AZ8STFF2020, DUKHCONP1AZ8STFF2035, DUKHCONP1AZ8STFF2020, DUKHCONP1AZ7ARFF3300 | DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ELFF4035, DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8ELFF4035, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-08-30 | 2014-09-27 | 2014-08-30 | 2014-09-27 | 0 | Yes | DUKHCONP1AZ7ARFF3375, DUKHCONP1AZ8ARFF3370, DUKHCONP1AZ8ARFF3370 | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3390, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3390, DUKHCONP1AZ8ARFF3385, DUKHCONP1AZ9ARFF3375, DUKHCONP1AZ8ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-07-09 | 2014-08-10 | 2014-07-09 | 2014-08-10 | 0 | Yes | DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8ARFF3315, DUKHCONP1AZ8ARFF3315, DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ7ARFF3320, DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8PLFF4330 | DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ9ARFF3320, DUKHCONP1AZ8ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-09-16 | 2014-10-16 | 2014-09-16 | 2014-10-16 | 0 | Yes | DUKHCONP1AZ8ARFF3330, DUKHCONP1AZ8ARFF3375, DUKHCONP1AZ8ARFF3385, DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8ARFF3390, DUKHCONP1AZ8ARFF3335, DUKHCONP1AZ7ARFF3395, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8ARFF3375, DUKHCONP1AZ8ARFF3335, DUKHCONP1AZ8ARFF3350, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8ARFF3380, DUKHCONP1AZ8ARFF3380, DUKHCONP1AZ8ARFF3390, DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ8ARFF3350, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8ARFF3330, DUKHCONP1AZ8ARFF3385 | DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ8ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-07-29 | 2014-08-24 | 2014-07-29 | 2014-08-24 | 0 | Yes | DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ7ARFF3345, DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ8ARFF3330, DUKHCONP1AZ8ARFF3330, DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ8ARFF3325 | DUKHCONP1AZ9ARFF3345, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-06-21 | 2014-07-14 | 2014-06-21 | 2014-07-14 | 12 | No | DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ARFF3305 | DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ8ARFF3335, DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ8ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-08-10 | 2014-09-01 | 2014-08-10 | 2014-09-01 | 2 | No | DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ8ARFF3325 | DUKHCONP1AZ8ARFF3385, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3385, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-08-09 | 2014-09-06 | 2014-08-09 | 2014-09-06 | 0 | Yes | DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ7ARFF3360 | DUKHCONP1AZ8PLFF4340, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8ELFF4060, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ELFF4050, DUKHCONP1AZ8PLFF4340, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ8ACFF4620, DUKHCONP1AZ8ELFF4055, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ8ELFF4055, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ACFF4620, DUKHCONP1AZ8ELFF4050, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-09-10 | 2014-10-02 | 2014-09-10 | 2014-10-02 | 0 | Yes | DUKHCONP1AZ8ARFF3350, DUKHCONP1AZ8ARFF3350, DUKHCONP1AZ8ARFF3375, DUKHCONP1AZ8ARFF3375 | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-09-10 | 2014-10-02 | 2014-09-10 | 2014-10-02 | 1 | No | DUKHCONP1AZ8ARFF3375, DUKHCONP1AZ8ARFF3375 | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-06-29 | 2014-07-27 | 2014-06-29 | 2014-07-27 | 14 | No | DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ARFF3305 | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 0 | Yes | DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ7ARFF3305, DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ8ELFF4035, DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8ELFF4035 | DUKHCONP1AZ8ARFF3330, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ8ARFF3330, DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ8ARFF3310, DUKHCONP1AZ8ARFF3315, DUKHCONP1AZ8ARFF3310, DUKHCONP1AZ8ARFF3315, DUKHCONP1AZ8ACFF4615 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 0 | Yes | DUKHCONP1AZ8ARFF3320, DUKHCONP1AZ7ARFF3325, DUKHCONP1AZ8ARFF3310, DUKHCONP1AZ8ARFF3310, DUKHCONP1AZ8ARFF3320 | DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ARFF3350, DUKHCONP1AZ8ARFF3335, DUKHCONP1AZ9ARFF3325, DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ARFF3335, DUKHCONP1AZ8ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-08-06 | 2014-08-23 | 2014-08-06 | 2014-08-23 | 8 | No | DUKHCONP1AZ8ARFF3310, DUKHCONP1AZ8ARFF3310, DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ8ARFF3325 | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-07-02 | 2014-07-19 | 2014-07-02 | 2014-07-19 | 0 | Yes | DUKHCONP1AZ7ARFF3315, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ARFF3305 | DUKHCONP1AZ9ARFF3315, DUKHCONP1AZ8ARFF3320, DUKHCONP1AZ8ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-08-24 | 2014-09-09 | 2014-08-24 | 2014-09-09 | 0 | Yes | DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8ARFF3350, DUKHCONP1AZ8ARFF3335, DUKHCONP1AZ8ARFF3335, DUKHCONP1AZ8ARFF3350, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ7ARFF3365 | DUKHCONP1AZ8PLFF4335, DUKHCONP1AZ8PLFF4335, DUKHCONP1AZ8ARFF3370, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARFF3370, DUKHCONP1AZ9ARFF3365 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.45 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-06-02 | 2014-08-09 | 2014-06-02 | 2014-08-09 | 57 |  |  |  | 0 | 0
DUKHCONP1AZ8ARRF3600 | Block work | 20 | 20 | 0% | 2014-06-02 | 2014-06-24 | 2014-06-02 | 2014-06-24 | 52 | No | DUKHCONP1AZ7ARRF3600, DUKHCONP1AZ8STRF2055, DUKHCONP1AZ8STRF2055 | DUKHCONP1AZ9ARRF3600, DUKHCONP1AZ8ARRF3605, DUKHCONP1AZ8ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-07-20 | 2014-08-09 | 2014-07-20 | 2014-08-09 | 57 | No | DUKHCONP1AZ8ARRF3695, DUKHCONP1AZ8ARRF3695 | DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-06-24 | 2014-07-10 | 2014-06-24 | 2014-07-10 | 57 | No | DUKHCONP1AZ8ARRF3605, DUKHCONP1AZ8ARRF3605 | DUKHCONP1AZ8ARRF3695, DUKHCONP1AZ8ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-07-02 | 2014-07-24 | 2014-07-02 | 2014-07-24 | 57 | No | DUKHCONP1AZ8ARRF3610, DUKHCONP1AZ8ARRF3610 | DUKHCONP1AZ8ARRF3620, DUKHCONP1AZ8ARRF3620, DUKHCONP1AZ8AREL3680, DUKHCONP1AZ8AREL3680 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-06-10 | 2014-07-02 | 2014-06-10 | 2014-07-02 | 52 | No | DUKHCONP1AZ8ARRF3600, DUKHCONP1AZ8ARRF3600 | DUKHCONP1AZ8AREL3665, DUKHCONP1AZ8ARRF3610, DUKHCONP1AZ8PLRF4345, DUKHCONP1AZ8ARRF3610, DUKHCONP1AZ8PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.45 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-06-24 | 2014-09-14 | 2014-06-24 | 2014-09-14 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.45 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-07-08 | 2014-09-14 | 2014-07-08 | 2014-09-14 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ8ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-07-29 | 2014-08-30 | 2014-07-29 | 2014-08-30 | 21 | No | DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8ARRF3645 | DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ8ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-08-28 | 2014-09-14 | 2014-08-28 | 2014-09-14 | 26 | No | DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ8ARRF3655 | DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 21 | No | DUKHCONP1AZ8ARRF3635, DUKHCONP1AZ8ARRF3635 | DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-08-17 | 2014-09-08 | 2014-08-17 | 2014-09-08 | 21 | No | DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8ARRF3650, DUKHCONP1AZ8ARRF3650, DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ7ARRF3655 | DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ARRF3660, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ8ARRF3660 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-07-12 | 2014-08-12 | 2014-07-12 | 2014-08-12 | 21 | No | DUKHCONP1AZ8ARRF3630, DUKHCONP1AZ8ARRF3630 | DUKHCONP1AZ8ARRF3640, DUKHCONP1AZ8ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-07-08 | 2014-08-09 | 2014-07-08 | 2014-08-09 | 21 | No | DUKHCONP1AZ8STRF2060, DUKHCONP1AZ8STRF2065, DUKHCONP1AZ8STRF2060, DUKHCONP1AZ7ARRF3630, DUKHCONP1AZ8STRF2065 | DUKHCONP1AZ8ARRF3635, DUKHCONP1AZ9ARRF3630, DUKHCONP1AZ8ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ8ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-07-21 | 2014-08-21 | 2014-07-21 | 2014-08-21 | 21 | No | DUKHCONP1AZ8ARRF3640, DUKHCONP1AZ8ARRF3640 | DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8ARRF3650, DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ8ARRF3650 | 0 | 0 | ROOF
DHBL.K30.L15.45 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-06-24 | 2014-08-18 | 2014-06-24 | 2014-08-18 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ8AREL3680 | External Painting | 20 | 20 | 0% | 2014-07-23 | 2014-08-18 | 2014-07-23 | 2014-08-18 | 49 | No | DUKHCONP1AZ8ARRF3695, DUKHCONP1AZ7AREL3680, DUKHCONP1AZ8ARRF3695, DUKHCONP1AZ8AREL3670, DUKHCONP1AZ8AREL3670 | DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ9AREL3680, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8PLTC8005 | 0 | 0 | ELEVATION
DUKHCONP1AZ8AREL3665 | External Plastering | 25 | 25 | 0% | 2014-06-24 | 2014-07-22 | 2014-06-24 | 2014-07-22 | 47 | No | DUKHCONP1AZ8ARRF3605, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ7AREL3665, DUKHCONP1AZ8STRF2065, DUKHCONP1AZ8STRF2065 | DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ9AREL3665, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8AREL3670, DUKHCONP1AZ8AREL3670 | 0 | 0 | ELEVATION
DUKHCONP1AZ8AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-07-12 | 2014-08-06 | 2014-07-12 | 2014-08-06 | 49 | No | DUKHCONP1AZ8AREL3665, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ7AREL3670 | DUKHCONP1AZ8AREL3680, DUKHCONP1AZ9AREL3670, DUKHCONP1AZ8AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L15.45 .20 MEP WORKS |  | 242 | 242 | 0% | 2013-12-31 | 2014-10-15 | 2013-12-31 | 2014-10-15 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.45 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2014-04-13 | 2014-10-15 | 2014-04-13 | 2014-10-15 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.45 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-04-13 | 2014-08-23 | 2014-04-13 | 2014-08-23 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ8ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-04-24 | 2014-05-17 | 2014-04-24 | 2014-05-17 | 45 | No | DUKHCONP1AZ8ELGF4000, DUKHCONP1AZ7ELGF4005, DUKHCONP1AZ8ELGF4000 | DUKHCONP1AZ9ELGF4005, DUKHCONP1AZ8ELGF4010, DUKHCONP1AZ8ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-04-13 | 2014-05-11 | 2014-04-13 | 2014-05-11 | 27 | No | DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ8ARGF3000 | DUKHCONP1AZ8ELGF4005, DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ8ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-07-05 | 2014-08-05 | 2014-07-05 | 2014-08-05 | 30 | No | DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ7ELGF4015 | DUKHCONP1AZ8ELFF4055, DUKHCONP1AZ9ELGF4015, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-07-10 | 2014-08-05 | 2014-07-10 | 2014-08-05 | 18 | No | DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ELGF4010, DUKHCONP1AZ8ELGF4010, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3060 | DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ8ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-07-22 | 2014-08-23 | 2014-07-22 | 2014-08-23 | 25 | No | DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ7ELGF4025 | DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ9ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-07-22 | 2014-08-17 | 2014-07-22 | 2014-08-17 | 18 | No | DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ7ELGF4030, DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ARGF3060 | DUKHCONP1AZ8ELFF4050, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ELFF4050, DUKHCONP1AZ9ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 45 | No | DUKHCONP1AZ8ELGF4005, DUKHCONP1AZ8ELGF4005 | DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ELGF4020, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ8ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.45 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2014-05-25 | 2014-09-25 | 2014-05-25 | 2014-09-25 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ8ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-06-05 | 2014-06-28 | 2014-06-05 | 2014-06-28 | 29 | No | DUKHCONP1AZ8ELFF4035, DUKHCONP1AZ8ELFF4035 | DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ8ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-05-25 | 2014-06-22 | 2014-05-25 | 2014-06-22 | 11 | No | DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ8ARFF3300 | DUKHCONP1AZ8ELFF4040, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ELFF4040, DUKHCONP1AZ8ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 1 | No | DUKHCONP1AZ7ELFF4055, DUKHCONP1AZ8ELGF4015, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8ELGF4015 | DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ9ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-08-20 | 2014-09-11 | 2014-08-20 | 2014-09-11 | 3 | No | DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ7ELFF4060, DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ8ARFF3360 | DUKHCONP1AZ9ELFF4060, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ8ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 1 | No | DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ7ELFF4065, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ8ELFF4060, DUKHCONP1AZ8ELFF4060 | DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ8ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 8 | No | DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8MSEX5010, DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ8ARFF3360 | DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ8ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 27 | No | DUKHCONP1AZ8ELFF4040, DUKHCONP1AZ8ELFF4040, DUKHCONP1AZ7ELFF4045 | DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ8ELFF4060, DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ9ELFF4045, DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ8ELFF4060 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.45 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-09-11 | 2014-10-15 | 2014-09-11 | 2014-10-15 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ8ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-09-11 | 2014-10-01 | 2014-09-11 | 2014-10-01 | 1 | No | DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ8ELFF4050, DUKHCONP1AZ8ELFF4050, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8ARRF3645 | DUKHCONP1AZ8ELRF4075, DUKHCONP1AZ8ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ8ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-09-17 | 2014-10-15 | 2014-09-17 | 2014-10-15 | 1 | No | DUKHCONP1AZ8ELRF4070, DUKHCONP1AZ8ELRF4070 | DUKHCONP1AZ8ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.45 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 242 | 242 | 0% | 2013-12-31 | 2014-10-15 | 2013-12-31 | 2014-10-15 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.45 .20 .15 .10 GROUND FLOOR |  | 198 | 198 | 0% | 2013-12-31 | 2014-08-23 | 2013-12-31 | 2014-08-23 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ8PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2013-12-31 | 2014-01-18 | 2013-12-31 | 2014-01-18 | 0 | Yes | DUKHCONP1AZ8STUG1040, DUKHCONP1AZ8STUG1040 | DUKHCONP1AZ8STUG1045, DUKHCONP1AZ8STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-04-23 | 2014-05-13 | 2014-04-23 | 2014-05-13 | 21 | No | DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ8ARGF3000 | DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ8MSEX5000, DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ8MSEX5000 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-04-23 | 2014-05-13 | 2014-04-23 | 2014-05-13 | 18 | No | DUKHCONP1AZ7PLGF4305, DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ8ARGF3000 | DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ9PLGF4305, DUKHCONP1AZ8PLGF4310, DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ8PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-08-06 | 2014-08-23 | 2014-08-06 | 2014-08-23 | 45 | No | DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ7PLGF4320, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3060 | DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ9PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-07-22 | 2014-08-17 | 2014-07-22 | 2014-08-17 | 45 | No | DUKHCONP1AZ8PLGF4310, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ8PLGF4310, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ7PLGF4315 | DUKHCONP1AZ8PLGF4320, DUKHCONP1AZ9PLGF4315, DUKHCONP1AZ8PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.45 .20 .15 .15 FIRST FLOORS |  | 90 | 90 | 0% | 2014-06-05 | 2014-09-21 | 2014-06-05 | 2014-09-21 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ8PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-06-05 | 2014-06-25 | 2014-06-05 | 2014-06-25 | 22 | No | DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ7PLFF4330, DUKHCONP1AZ8PLFF4325, DUKHCONP1AZ8ARFF3300 | DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8PLFF4335, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ8PLFF4335, DUKHCONP1AZ8ARFF3320, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-06-05 | 2014-06-25 | 2014-06-05 | 2014-06-25 | 0 | Yes | DUKHCONP1AZ8ARFF3300, DUKHCONP1AZ8ARFF3300 | DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ARFF3320, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ8ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-09-04 | 2014-09-21 | 2014-09-04 | 2014-09-21 | 5 | No | DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ7PLFF4340, DUKHCONP1AZ8PLFF4335, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ8PLFF4335 | DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ9PLFF4340 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-08-24 | 2014-09-15 | 2014-08-24 | 2014-09-15 | 5 | No | DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ8ARFF3365, DUKHCONP1AZ8PLFF4330 | DUKHCONP1AZ8PLFF4340, DUKHCONP1AZ8PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.45 .20 .15 .20 ROOF |  | 93 | 93 | 0% | 2014-06-24 | 2014-10-15 | 2014-06-24 | 2014-10-15 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ8PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-06-24 | 2014-07-10 | 2014-06-24 | 2014-07-10 | 56 | No | DUKHCONP1AZ8ARRF3605, DUKHCONP1AZ8ARRF3605 | DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ8PLRF4350 | 0 | 0 | ROOF
DUKHCONP1AZ8PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-08-11 | 2014-08-27 | 2014-08-11 | 2014-08-27 | 26 | No | DUKHCONP1AZ8PLRF4345, DUKHCONP1AZ7PLRF4350, DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ8PLRF4345, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ8PLFF4330 | DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ8WEEX5065, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8WEEX5065 | 0 | 0 | ROOF
DUKHCONP1AZ8PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-09-15 | 2014-10-15 | 2014-09-15 | 2014-10-15 | 1 | No | DUKHCONP1AZ8PLRF4345, DUKHCONP1AZ8PLRF4345, DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ7PLRF4355, DUKHCONP1AZ8PLFF4340, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8PLFF4340, DUKHCONP1AZ8ARRF3655 | DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8ACTC8000 | 0 | 0 | ROOF
DHBL.K30.L15.45 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2014-05-13 | 2014-10-13 | 2014-05-13 | 2014-10-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.45 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-05-13 | 2014-08-20 | 2014-05-13 | 2014-08-20 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ8ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-07-26 | 2014-08-20 | 2014-07-26 | 2014-08-20 | 32 | No | DUKHCONP1AZ7ACGF4610, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ8ACGF4605 | DUKHCONP1AZ9ACGF4610, DUKHCONP1AZ8ACRF4635, DUKHCONP1AZ8ACRF4635, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-07-05 | 2014-08-05 | 2014-07-05 | 2014-08-05 | 32 | No | DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ7ACGF4605 | DUKHCONP1AZ8ACGF4610, DUKHCONP1AZ9ACGF4605, DUKHCONP1AZ8ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ8ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-05-13 | 2014-06-04 | 2014-05-13 | 2014-06-04 | 49 | No | DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ7ACGF4600, DUKHCONP1AZ8ARGF3005 | DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ARGF3055, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ8ACRF4630 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.45 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-06-26 | 2014-09-29 | 2014-06-26 | 2014-09-29 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ8ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-09-07 | 2014-09-29 | 2014-09-07 | 2014-09-29 | 2 | No | DUKHCONP1AZ8ACFF4620, DUKHCONP1AZ8ACFF4620, DUKHCONP1AZ7ACFF4625 | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ACRF4635, DUKHCONP1AZ9ACFF4625, DUKHCONP1AZ8ACRF4635 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 2 | No | DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ7ACFF4620, DUKHCONP1AZ8ARFF3360 | DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ9ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ8ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-06-26 | 2014-07-19 | 2014-06-26 | 2014-07-19 | 27 | No | DUKHCONP1AZ7ACFF4615, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ8ARFF3305 | DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ8ACFF4620, DUKHCONP1AZ8ACFF4620, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ8ARFF3360 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.45 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-07-29 | 2014-10-13 | 2014-07-29 | 2014-10-13 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ8ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-09-13 | 2014-10-13 | 2014-09-13 | 2014-10-13 | 3 | No | DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ7ACRF4635, DUKHCONP1AZ8ACGF4610, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ8ACGF4610, DUKHCONP1AZ8ACFF4625 | DUKHCONP1AZ9ACRF4635, DUKHCONP1AZ8ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ8ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-07-29 | 2014-08-30 | 2014-07-29 | 2014-08-30 | 34 | No | DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ7ACRF4630, DUKHCONP1AZ8ARRF3645, DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ8ACGF4600 | DUKHCONP1AZ8ACRF4635, DUKHCONP1AZ9ACRF4630, DUKHCONP1AZ8ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.45 .25 EXTERNAL WORKS |  | 115 | 115 | 0% | 2014-05-20 | 2014-10-04 | 2014-05-20 | 2014-10-04 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.45 .25 .10 MISCELLANEOUS |  | 112 | 112 | 0% | 2014-05-20 | 2014-09-30 | 2014-05-20 | 2014-09-30 | 55 |  |  |  | 0 | 0
DUKHCONP1AZ8MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-09-02 | 2014-09-30 | 2014-09-02 | 2014-09-30 | 55 | No | DUKHCONP1AZ7MSEX5335, DUKHCONI1AZ4BWGL5325 | DUKHCONP1AZ9MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ8MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-06-03 | 2014-07-01 | 2014-06-03 | 2014-07-01 | 8 | No | DUKHCONP1AZ8MSEX5000, DUKHCONP1AZ8MSEX5000 | DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8MSEX5015, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8MSEX5015, DUKHCONP1AZ8ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ8MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-07-10 | 2014-08-11 | 2014-07-10 | 2014-08-11 | 16 | No | DUKHCONP1AZ7MSEX5020, DUKHCONP1AZ8STRF2055, DUKHCONP1AZ8STRF2055 | DUKHCONP1AZ8HDEX5090, DUKHCONP1AZ8MSEX5025, DUKHCONP1AZ8HDEX5090, DUKHCONP1AZ8MSEX5025, DUKHCONP1AZ9MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ8MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-06-23 | 2014-07-15 | 2014-06-23 | 2014-07-15 | 8 | No | DUKHCONP1AZ8MSEX5005, DUKHCONP1AZ8MSEX5005 | DUKHCONP1AZ8MSEX5010, DUKHCONP1AZ8WEEX5065, DUKHCONP1AZ8WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ8MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-05-20 | 2014-06-17 | 2014-05-20 | 2014-06-17 | 8 | No | DUKHCONP1AZ8STRF2055, DUKHCONP1AZ8PLGF4310, DUKHCONP1AZ8STRF2055, DUKHCONP1AZ8PLGF4310 | DUKHCONP1AZ8MSEX5005, DUKHCONP1AZ8MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ8MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-07-28 | 2014-08-23 | 2014-07-28 | 2014-08-23 | 19 | No | DUKHCONP1AZ8MSEX5020, DUKHCONP1AZ8MSEX5020 | DUKHCONP1AZ8WEEX5060, DUKHCONP1AZ8WEEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ8MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 8 | No | DUKHCONP1AZ8MSEX5015 | DUKHCONP1AZ8ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.45 .25 .15 WATER TANK ENCLOSURE |  | 100 | 100 | 0% | 2014-06-07 | 2014-10-04 | 2014-06-07 | 2014-10-04 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ8WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-06-22 | 2014-07-20 | 2014-06-22 | 2014-07-20 | 43 | No | DUKHCONP1AZ8WEEX5035, DUKHCONP1AZ8WEEX5035 | DUKHCONP1AZ8WEEX5045, DUKHCONP1AZ8WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ8WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 43 | No | DUKHCONP1AZ8WEEX5030, DUKHCONP1AZ8WEEX5030 | DUKHCONP1AZ8WEEX5040, DUKHCONP1AZ8WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ8WEEX5030 | Excavation | 20 | 20 | 0% | 2014-06-07 | 2014-06-29 | 2014-06-07 | 2014-06-29 | 43 | No | DUKHCONP1AZ8STRF2055, DUKHCONP1AZ8STRF2055, DUKHCONP1AZ7WEEX5030 | DUKHCONP1AZ8WEEX5035, DUKHCONP1AZ8WEEX5035, DUKHCONP1AZ9WEEX5030 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ8WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-06-29 | 2014-07-27 | 2014-06-29 | 2014-07-27 | 43 | No | DUKHCONP1AZ8WEEX5040, DUKHCONP1AZ8WEEX5040 | DUKHCONP1AZ8WEEX5050, DUKHCONP1AZ8WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ8WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-09-06 | 2014-10-04 | 2014-09-06 | 2014-10-04 | 9 | No | DUKHCONP1AZ8MSEX5015, DUKHCONP1AZ8MSEX5015, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ7WEEX5065, DUKHCONP1AZ8WEEX5060, DUKHCONP1AZ8WEEX5060, DUKHCONP1AZ8PLRF4350 | DUKHCONP1AZ9WEEX5065, DUKHCONP1AZ8PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ8WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-08-12 | 2014-09-03 | 2014-08-12 | 2014-09-03 | 19 | No | DUKHCONP1AZ8MSEX5025, DUKHCONP1AZ8WEEX5045, DUKHCONP1AZ8WEEX5045 | DUKHCONP1AZ8WEEX5060, DUKHCONP1AZ8WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ8WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 10 | No | DUKHCONP1AZ7WEEX5060, DUKHCONP1AZ8MSEX5025, DUKHCONP1AZ8WEEX5050, DUKHCONP1AZ8WEEX5050 | DUKHCONP1AZ9WEEX5060, DUKHCONP1AZ8WEEX5065, DUKHCONP1AZ8WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.45 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-07-24 | 2014-09-07 | 2014-07-24 | 2014-09-07 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ8HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-08-09 | 2014-08-31 | 2014-08-09 | 2014-08-31 | 16 | No | DUKHCONP1AZ8HDEX5090, DUKHCONP1AZ8HDEX5090 | DUKHCONP1AZ8HDEX5100, DUKHCONP1AZ8HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ8HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-08-16 | 2014-09-07 | 2014-08-16 | 2014-09-07 | 16 | No | DUKHCONP1AZ8HDEX5095, DUKHCONP1AZ8HDEX5095 | DUKHCONP1AZ8SLEX5105, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ8SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ8HDEX5090 | kerb works | 20 | 20 | 0% | 2014-07-24 | 2014-08-19 | 2014-07-24 | 2014-08-19 | 16 | No | DUKHCONP1AZ8MSEX5020, DUKHCONP1AZ8MSEX5020, DUKHCONP1AZ7HDEX5090 | DUKHCONP1AZ9HDEX5090, DUKHCONP1AZ8HDEX5095, DUKHCONP1AZ8HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.45 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-08-21 | 2014-09-25 | 2014-08-21 | 2014-09-25 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ8SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-08-21 | 2014-09-18 | 2014-08-21 | 2014-09-18 | 16 | No | DUKHCONP1AZ8HDEX5100, DUKHCONP1AZ8HDEX5100 | DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8SLEX5110, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ8SLEX5110, DUKHCONP1AZ8ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ8SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 16 | No | DUKHCONP1AZ8SLEX5105, DUKHCONP1AZ8SLEX5105 | DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ8ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.45 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-10-18 | 2014-11-15 | 2014-10-18 | 2014-11-15 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ8ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-10-18 | 2014-11-15 | 2014-10-18 | 2014-11-15 | 0 | Yes | DUKHCONP1AZ8SLEX5110, DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ8HDEX5100, DUKHCONP1AZ8AREL3680, DUKHCONP1AZ8ARRF3620, DUKHCONP1AZ8SLEX5105, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ARRF3660, DUKHCONP1AZ8MSEX5005, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ8ACRF4635 | DUKHCONP1AZ9ACTC8000, DUKHHANP1AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ8ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-10-18 | 2014-11-15 | 2014-10-18 | 2014-11-15 | 0 | Yes | DUKHCONP1AZ8MSEX5005, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ8ELFF4055, DUKHCONP1AZ8HDEX5100, DUKHCONP1AZ8ELGF4025, DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ8ARRF3620, DUKHCONP1AZ8SLEX5110, DUKHCONP1AZ8ARRF3660, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ8ELGF4015, DUKHCONP1AZ8ELRF4075, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8ELGF4030, DUKHCONP1AZ8AREL3680, DUKHCONP1AZ8SLEX5105, DUKHCONP1AZ8ELFF4050 | DUKHHANP1AGNPLTC9005, DUKHCONP1AZ9ELTC8010, DUKHHANP1AGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ8PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-10-18 | 2014-11-15 | 2014-10-18 | 2014-11-15 | 0 | Yes | DUKHCONP1AZ8HDEX5100, DUKHCONP1AZ8SLEX5110, DUKHCONP1AZ8ARRF3620, DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ8SLEX5105, DUKHCONP1AZ8ARRF3660, DUKHCONP1AZ8MSEX5005, DUKHCONP1AZ8PLGF4320, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ7PLTC8005, DUKHCONP1AZ8WEEX5065, DUKHCONP1AZ8AREL3680 | DUKHCONP1AZ9PLTC8005, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L15.50 ZONE - 9 (5 Twin Villas) |  | 361 | 361 | 0% | 2013-10-09 | 2014-12-14 | 2013-10-09 | 2014-12-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.50 .10 STRUCTURAL WORKS |  | 238 | 238 | 0% | 2013-10-09 | 2014-07-17 | 2013-10-09 | 2014-07-17 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.50 .10 .10 SUB STRUCTURE |  | 126 | 126 | 0% | 2013-10-09 | 2014-03-09 | 2013-10-09 | 2014-03-09 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.50 .10 .10 .10 UPTO GRADE SLAB |  | 126 | 126 | 0% | 2013-10-09 | 2014-03-09 | 2013-10-09 | 2014-03-09 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ9STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 0 | Yes | DUKHCONP1AZ9STUG1030, DUKHCONP1AZ8STUG1035, DUKHCONP1AZ9STUG1030 | DUKHCONP1AZ9STUG1040, DUKHCONP1AZ9STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-11-17 | 2013-12-09 | 2013-11-17 | 2013-12-09 | 0 | Yes | DUKHCONP1AZ9STUG1015, DUKHCONP1AZ9STUG1015 | DUKHCONP1AZ9STUG1025, DUKHCONP1AZ9STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 0 | Yes | DUKHCONP1AZ9STUG1035, DUKHCONP1AZ9STUG1035 | DUKHCONP1AZ9PLUG4300, DUKHCONP1AZ9STUG1045, DUKHCONP1AZ9PLUG4300, DUKHCONP1AZ9STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-11-26 | 2013-12-25 | 2013-11-26 | 2013-12-25 | 0 | Yes | DUKHCONP1AZ8STUG1025, DUKHCONP1AZ9STUG1020, DUKHCONP1AZ9STUG1020 | DUKHCONP1AZ9STUG1030, DUKHCONP1AZ9STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 0 | Yes | DUKHCONP1AZ8STUG1045, DUKHCONP1AZ9STUG1040, DUKHCONP1AZ9STUG1040, DUKHCONP1AZ9PLUG4300, DUKHCONP1AZ9PLUG4300 | DUKHCONP1AZ9STGF2000, DUKHCONP1AZ9STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-10-23 | 2013-11-18 | 2013-10-23 | 2013-11-18 | 0 | Yes | DUKHCONP1AZ9STUG1000, DUKHCONP1AZ9STUG1000 | DUKHCONP1AZ9STUG1010, DUKHCONP1AZ9STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-10-27 | 2013-11-21 | 2013-10-27 | 2013-11-21 | 0 | Yes | DUKHCONP1AZ9STUG1005, DUKHCONP1AZ9STUG1005 | DUKHCONP1AZ9STUG1015, DUKHCONP1AZ9STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-10-09 | 2013-11-09 | 2013-10-09 | 2013-11-09 | 0 | Yes | DUKHCONP1AGNSP005000, DUKHCONP1AZ8STUG1000 | DUKHCONP1AZ9STUG1005, DUKHCONP1AZ9STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-11-02 | 2013-11-30 | 2013-11-02 | 2013-11-30 | 0 | Yes | DUKHCONP1AZ9STUG1010, DUKHCONP1AZ9STUG1010 | DUKHCONP1AZ9STUG1020, DUKHCONP1AZ9STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1AZ9STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 0 | Yes | DUKHCONP1AZ9STUG1025, DUKHCONP1AZ9STUG1025 | DUKHCONP1AZ9STUG1035, DUKHCONP1AZ9STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L15.50 .10 .15 SUPERSTRUCTURE |  | 123 | 123 | 0% | 2014-02-25 | 2014-07-17 | 2014-02-25 | 2014-07-17 | 52 |  |  |  | 0 | 0
DHBL.K30.L15.50 .10 .15 .10 GROUND FLOOR |  | 49 | 49 | 0% | 2014-02-25 | 2014-04-22 | 2014-02-25 | 2014-04-22 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ9STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-04-07 | 2014-04-22 | 2014-04-07 | 2014-04-22 | 0 | Yes | DUKHCONP1AZ9STGF2010, DUKHCONP1AZ9STGF2010, DUKHCONP1AZ8STGF2015 | DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ9STFF2020, DUKHCONP1AZ9STFF2020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONP1AZ9STGF2005, DUKHCONP1AZ9STGF2005 | DUKHCONP1AZ9STGF2015, DUKHCONP1AZ9STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9STGF2005 | Column-Concrete | 24 | 24 | 0% | 2014-03-06 | 2014-04-02 | 2014-03-06 | 2014-04-02 | 0 | Yes | DUKHCONP1AZ9STGF2000, DUKHCONP1AZ9STGF2000 | DUKHCONP1AZ9STGF2010, DUKHCONP1AZ9STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 0 | Yes | DUKHCONP1AZ9STUG1045, DUKHCONP1AZ9STUG1045, DUKHCONP1AZ8STGF2000 | DUKHCONP1AZ9STGF2005, DUKHCONP1AZ9STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.50 .10 .15 .15 FIRST FLOORS |  | 51 | 51 | 0% | 2014-04-10 | 2014-06-08 | 2014-04-10 | 2014-06-08 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ9STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-05-24 | 2014-06-08 | 2014-05-24 | 2014-06-08 | 0 | Yes | DUKHCONP1AZ9STFF2030, DUKHCONP1AZ9STFF2030, DUKHCONP1AZ8STFF2035 | DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9STRF2040, DUKHCONP1AZ9STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-05-07 | 2014-06-04 | 2014-05-07 | 2014-06-04 | 0 | Yes | DUKHCONP1AZ9STFF2025, DUKHCONP1AZ9STFF2025 | DUKHCONP1AZ9STFF2035, DUKHCONP1AZ9STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9STFF2025 | Column-Concrete | 24 | 24 | 0% | 2014-04-22 | 2014-05-19 | 2014-04-22 | 2014-05-19 | 0 | Yes | DUKHCONP1AZ9STFF2020, DUKHCONP1AZ9STFF2020 | DUKHCONP1AZ9STFF2030, DUKHCONP1AZ9STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-04-10 | 2014-05-08 | 2014-04-10 | 2014-05-08 | 0 | Yes | DUKHCONP1AZ9STGF2015, DUKHCONP1AZ8STFF2020, DUKHCONP1AZ9STGF2015 | DUKHCONP1AZ9STFF2025, DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9STFF2025, DUKHCONP1AZ9ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.50 .10 .15 .20 ROOF |  | 46 | 46 | 0% | 2014-05-26 | 2014-07-17 | 2014-05-26 | 2014-07-17 | 52 |  |  |  | 0 | 0
DUKHCONP1AZ9STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-05-29 | 2014-06-17 | 2014-05-29 | 2014-06-17 | 9 | No | DUKHCONP1AZ9STRF2040, DUKHCONP1AZ9STRF2040 | DUKHCONP1AZ9STRF2050, DUKHCONP1AZ9STRF2050 | 0 | 0 | ROOF
DUKHCONP1AZ9STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-05-26 | 2014-06-15 | 2014-05-26 | 2014-06-15 | 9 | No | DUKHCONP1AZ8STRF2040, DUKHCONP1AZ9STFF2035, DUKHCONP1AZ9STFF2035 | DUKHCONP1AZ9STRF2045, DUKHCONP1AZ9STRF2045, DUKHCONI1ASBIWGL7400 | 0 | 0 | ROOF
DUKHCONP1AZ9STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 52 | No | DUKHCONP1AZ9STRF2055, DUKHCONP1AZ9STRF2055 | DUKHCONP1AZ9STRF2065, DUKHCONP1AZ9ARRF3630, DUKHCONP1AZ9ARRF3630, DUKHCONP1AZ9STRF2065 | 0 | 0 | ROOF
DUKHCONP1AZ9STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-06-19 | 2014-07-17 | 2014-06-19 | 2014-07-17 | 52 | No | DUKHCONP1AZ9STRF2060, DUKHCONP1AZ8STRF2065, DUKHCONP1AZ9STRF2060 | DUKHCONP1AZ9AREL3665, DUKHCONP1AZ9ARRF3630, DUKHCONP1AZ9AREL3665, DUKHCONP1AZ9ARRF3630 | 0 | 0 | ROOF
DUKHCONP1AZ9STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-06-11 | 2014-06-25 | 2014-06-11 | 2014-06-25 | 9 | No | DUKHCONP1AZ9STRF2050, DUKHCONP1AZ8STRF2055, DUKHCONP1AZ9STRF2050 | DUKHCONP1AZ9MSEX5020, DUKHCONP1AZ9MSEX5000, DUKHCONP1AZ9WEEX5030, DUKHCONP1AZ9STRF2060, DUKHCONP1AZ9MSEX5020, DUKHCONP1AZ9WEEX5030, DUKHCONP1AZ9ARRF3600, DUKHCONP1AZ9STRF2060, DUKHCONP1AZ9ARRF3600, DUKHCONP1AZ9MSEX5000 | 0 | 0 | ROOF
DUKHCONP1AZ9STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-06-01 | 2014-06-23 | 2014-06-01 | 2014-06-23 | 9 | No | DUKHCONP1AZ9STRF2045, DUKHCONP1AZ9STRF2045 | DUKHCONP1AZ9STRF2055, DUKHCONP1AZ9STRF2055 | 0 | 0 | ROOF
DHBL.K30.L15.50 .15 FINISHING WORKS |  | 161 | 161 | 0% | 2014-05-06 | 2014-11-15 | 2014-05-06 | 2014-11-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.50 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2014-05-06 | 2014-11-15 | 2014-05-06 | 2014-11-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L15.50 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-05-06 | 2014-10-21 | 2014-05-06 | 2014-10-21 | 21 |  |  |  | 0 | 0
DUKHCONP1AZ9ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-08-24 | 2014-09-09 | 2014-08-24 | 2014-09-09 | 21 | No | DUKHCONP1AZ8ARGF3070, DUKHCONP1AZ9ARGF3065, DUKHCONP1AZ9ARGF3065 | DUKHCONP1AZ9ARGF3080, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3075, DUKHCONP1AZ9ARGF3080, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-07-22 | 2014-08-23 | 2014-07-22 | 2014-08-23 | 21 | No | DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ9ARGF3045 | DUKHCONP1AZ9ACGF4605, DUKHCONP1AZ9ELGF4015, DUKHCONP1AZ9ACGF4605, DUKHCONP1AZ9ELGF4015, DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-08-31 | 2014-09-22 | 2014-08-31 | 2014-09-22 | 31 | No | DUKHCONP1AZ9ARGF3070, DUKHCONP1AZ8ARGF3080, DUKHCONP1AZ9ARGF3070 | DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3000 | Block work | 25 | 25 | 0% | 2014-05-06 | 2014-06-03 | 2014-05-06 | 2014-06-03 | 18 | No | DUKHCONP1AZ9STGF2015, DUKHCONP1AZ8ARGF3000, DUKHCONP1AZ9STGF2015 | DUKHCONP1AZ9ELGF4000, DUKHCONP1AZ9PLGF4305, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9ELGF4000, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ9PLGF4305 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-08-30 | 2014-09-21 | 2014-08-30 | 2014-09-21 | 21 | No | DUKHCONP1AZ9ARGF3070, DUKHCONP1AZ9ARGF3070, DUKHCONP1AZ8ARGF3075 | DUKHCONP1AZ9ARGF3085, DUKHCONP1AZ9ARGF3090, DUKHCONP1AZ9ARGF3085, DUKHCONP1AZ9ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-06-21 | 2014-07-19 | 2014-06-21 | 2014-07-19 | 18 | No | DUKHCONP1AZ9PLGF4305, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9ARGF3015, DUKHCONP1AZ9PLGF4305, DUKHCONP1AZ8ARGF3020, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9ARGF3015 | DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-07-23 | 2014-08-12 | 2014-07-23 | 2014-08-12 | 21 | No | DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ARGF3010, DUKHCONP1AZ9ARGF3010, DUKHCONP1AZ9ARGF3025 | DUKHCONP1AZ9ARGF3050, DUKHCONP1AZ9ARGF3050, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-09-21 | 2014-10-21 | 2014-09-21 | 2014-10-21 | 21 | No | DUKHCONP1AZ9ACGF4610, DUKHCONP1AZ9ARGF3030, DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3070, DUKHCONP1AZ8ARGF3095, DUKHCONP1AZ9ACGF4610, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3080, DUKHCONP1AZ9ARGF3090, DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3090, DUKHCONP1AZ9ARGF3030, DUKHCONP1AZ9ARGF3070, DUKHCONP1AZ9ARGF3080, DUKHCONP1AZ9ARGF3085, DUKHCONP1AZ9ARGF3085, DUKHCONP1AZ9ARGF3040 | DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-07-14 | 2014-08-09 | 2014-07-14 | 2014-08-09 | 18 | No | DUKHCONP1AZ9ARGF3030, DUKHCONP1AZ9ELGF4010, DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ELGF4010, DUKHCONP1AZ8ARGF3045, DUKHCONP1AZ9ARGF3030, DUKHCONP1AZ9ARGF3025 | DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-06-05 | 2014-06-29 | 2014-06-05 | 2014-06-29 | 26 | No | DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ9ARGF3005 | DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-07-31 | 2014-08-26 | 2014-07-31 | 2014-08-26 | 21 | No | DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ARGF3025 | DUKHCONP1AZ9ARGF3065, DUKHCONP1AZ9ARGF3085, DUKHCONP1AZ9ARGF3065, DUKHCONP1AZ9ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-07-26 | 2014-08-26 | 2014-07-26 | 2014-08-26 | 18 | No | DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ8ARGF3060, DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ARGF3045 | DUKHCONP1AZ9PLGF4320, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ELGF4015, DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELGF4030, DUKHCONP1AZ9ELGF4015, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9PLGF4320, DUKHCONP1AZ9ACGF4605, DUKHCONP1AZ9ACGF4605, DUKHCONP1AZ9ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-09-11 | 2014-09-28 | 2014-09-11 | 2014-09-28 | 21 | No | DUKHCONP1AZ9ARGF3075, DUKHCONP1AZ9ARGF3075 | DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 32 | No | DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ8ARGF3030, DUKHCONP1AZ9ARGF3005 | DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ9ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 18 | No | DUKHCONP1AZ8ARGF3005, DUKHCONP1AZ9PLGF4305, DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ9PLGF4305, DUKHCONP1AZ9ELGF4000, DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ9ELGF4000 | DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ARGF3010, DUKHCONP1AZ9ARGF3030, DUKHCONP1AZ9ARGF3015, DUKHCONP1AZ9ARGF3015, DUKHCONP1AZ9ARGF3010, DUKHCONP1AZ9ARGF3030, DUKHCONP1AZ9ACGF4600 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-06-26 | 2014-07-24 | 2014-06-26 | 2014-07-24 | 18 | No | DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ8ARGF3025, DUKHCONP1AZ9ARGF3010, DUKHCONP1AZ9ARGF3010 | DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3050, DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-09-07 | 2014-09-29 | 2014-09-07 | 2014-09-29 | 26 | No | DUKHCONP1AZ9ARGF3075, DUKHCONP1AZ9ARGF3050, DUKHCONP1AZ9ARGF3075, DUKHCONP1AZ9ARGF3050 | DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-07-16 | 2014-08-05 | 2014-07-16 | 2014-08-05 | 23 | No | DUKHCONP1AZ9ARGF3010, DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ARGF3025, DUKHCONP1AZ9ARGF3010 | DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3065, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3040, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-06-15 | 2014-07-01 | 2014-06-15 | 2014-07-01 | 18 | No | DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ8ARGF3015 | DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ9ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-08-18 | 2014-09-03 | 2014-08-18 | 2014-09-03 | 21 | No | DUKHCONP1AZ9ARGF3035, DUKHCONP1AZ9ARGF3050, DUKHCONP1AZ9ARGF3050, DUKHCONP1AZ8ARGF3065, DUKHCONP1AZ9ARGF3035 | DUKHCONP1AZ9PLGF4315, DUKHCONP1AZ9ARGF3070, DUKHCONP1AZ9PLGF4315, DUKHCONP1AZ9ARGF3070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.50 .15 .10 .15 FIRST FLOORS |  | 125 | 125 | 0% | 2014-06-17 | 2014-11-15 | 2014-06-17 | 2014-11-15 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ9ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-09-22 | 2014-10-16 | 2014-09-22 | 2014-10-16 | 0 | Yes | DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ8ARFF3370, DUKHCONP1AZ9ARFF3365 | DUKHCONP1AZ9ARFF3375, DUKHCONP1AZ9ARFF3375, DUKHCONP1AZ9ARFF3380, DUKHCONP1AZ9ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-09-29 | 2014-10-23 | 2014-09-29 | 2014-10-23 | 4 | No | DUKHCONP1AZ9ARFF3370, DUKHCONP1AZ9ARFF3370 | DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3300 | Block work | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 | Yes | DUKHCONP1AZ9STFF2035, DUKHCONP1AZ9STFF2020, DUKHCONP1AZ9STFF2035, DUKHCONP1AZ9STFF2020, DUKHCONP1AZ8ARFF3300 | DUKHCONP1AZ9PLFF4325, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9ELFF4035, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9PLFF4325, DUKHCONP1AZ9ELFF4035 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-09-28 | 2014-10-28 | 2014-09-28 | 2014-10-28 | 0 | Yes | DUKHCONP1AZ9ARFF3370, DUKHCONP1AZ9ARFF3370, DUKHCONP1AZ8ARFF3375 | DUKHCONP1AZ9ARFF3385, DUKHCONP1AZ9ARFF3390, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3390, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-08-11 | 2014-09-08 | 2014-08-11 | 2014-09-08 | 0 | Yes | DUKHCONP1AZ8ARFF3320, DUKHCONP1AZ9PLFF4325, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9ARFF3315, DUKHCONP1AZ9ARFF3315, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9PLFF4325 | DUKHCONP1AZ9ARFF3325, DUKHCONP1AZ9ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-10-18 | 2014-11-15 | 2014-10-18 | 2014-11-15 | 0 | Yes | DUKHCONP1AZ8ARFF3395, DUKHCONP1AZ9ARFF3390, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ARFF3380, DUKHCONP1AZ9ARFF3335, DUKHCONP1AZ9ARFF3350, DUKHCONP1AZ9ARFF3390, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3350, DUKHCONP1AZ9ACFF4625, DUKHCONP1AZ9ARFF3375, DUKHCONP1AZ9ARFF3375, DUKHCONP1AZ9ARFF3385, DUKHCONP1AZ9ARFF3330, DUKHCONP1AZ9ELFF4055, DUKHCONP1AZ9ARFF3380, DUKHCONP1AZ9ARFF3385, DUKHCONP1AZ9ARFF3330, DUKHCONP1AZ9ACFF4625, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ARFF3335 | DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-08-31 | 2014-09-22 | 2014-08-31 | 2014-09-22 | 0 | Yes | DUKHCONP1AZ8ARFF3345, DUKHCONP1AZ9ARFF3325, DUKHCONP1AZ9ARFF3330, DUKHCONP1AZ9ARFF3325, DUKHCONP1AZ9ELFF4045, DUKHCONP1AZ9ELFF4045, DUKHCONP1AZ9ARFF3330 | DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-07-20 | 2014-08-16 | 2014-07-20 | 2014-08-16 | 12 | No | DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3305 | DUKHCONP1AZ9ARFF3335, DUKHCONP1AZ9ARFF3335, DUKHCONP1AZ9ARFF3325, DUKHCONP1AZ9ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-09-08 | 2014-09-30 | 2014-09-08 | 2014-09-30 | 2 | No | DUKHCONP1AZ9ARFF3325, DUKHCONP1AZ9ARFF3325 | DUKHCONP1AZ9ARFF3385, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3385, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-09-07 | 2014-10-05 | 2014-09-07 | 2014-10-05 | 0 | Yes | DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ8ARFF3360, DUKHCONP1AZ9ARFF3345, DUKHCONP1AZ9ARFF3345 | DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ9ELFF4055, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ELFF4060, DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ9PLFF4340, DUKHCONP1AZ9ACFF4620, DUKHCONP1AZ9ELFF4050, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ELFF4050, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9PLFF4340, DUKHCONP1AZ9ELFF4055, DUKHCONP1AZ9ACFF4620, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-10-12 | 2014-11-03 | 2014-10-12 | 2014-11-03 | 0 | Yes | DUKHCONP1AZ9ARFF3375, DUKHCONP1AZ9ARFF3350, DUKHCONP1AZ9ARFF3350, DUKHCONP1AZ9ARFF3375 | DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-10-12 | 2014-11-03 | 2014-10-12 | 2014-11-03 | 1 | No | DUKHCONP1AZ9ARFF3375, DUKHCONP1AZ9ARFF3375 | DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-07-28 | 2014-08-28 | 2014-07-28 | 2014-08-28 | 14 | No | DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3305 | DUKHCONP1AZ9ARFF3345, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-07-12 | 2014-08-12 | 2014-07-12 | 2014-08-12 | 0 | Yes | DUKHCONP1AZ9PLFF4325, DUKHCONP1AZ8ARFF3305, DUKHCONP1AZ9ELFF4035, DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9PLFF4325, DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9ELFF4035 | DUKHCONP1AZ9ARFF3330, DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ9ARFF3310, DUKHCONP1AZ9ARFF3330, DUKHCONP1AZ9ARFF3315, DUKHCONP1AZ9ARFF3310, DUKHCONP1AZ9ARFF3315, DUKHCONP1AZ9AREL3665, DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ9AREL3665 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 0 | Yes | DUKHCONP1AZ9ARFF3320, DUKHCONP1AZ9ARFF3320, DUKHCONP1AZ9ARFF3310, DUKHCONP1AZ8ARFF3325, DUKHCONP1AZ9ARFF3310 | DUKHCONP1AZ9ARFF3350, DUKHCONP1AZ9ARFF3345, DUKHCONP1AZ9ARFF3335, DUKHCONP1AZ9ARFF3345, DUKHCONP1AZ9ARFF3335, DUKHCONP1AZ9ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-09-04 | 2014-09-21 | 2014-09-04 | 2014-09-21 | 8 | No | DUKHCONP1AZ9ARFF3310, DUKHCONP1AZ9ARFF3310, DUKHCONP1AZ9ARFF3325, DUKHCONP1AZ9ARFF3325 | DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-07-31 | 2014-08-20 | 2014-07-31 | 2014-08-20 | 0 | Yes | DUKHCONP1AZ8ARFF3315, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3305 | DUKHCONP1AZ9ARFF3320, DUKHCONP1AZ9ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-09-22 | 2014-10-08 | 2014-09-22 | 2014-10-08 | 0 | Yes | DUKHCONP1AZ9ARFF3350, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3350, DUKHCONP1AZ9ARFF3335, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3335, DUKHCONP1AZ8ARFF3365 | DUKHCONP1AZ9ARFF3370, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9PLFF4335, DUKHCONP1AZ9PLFF4335, DUKHCONP1AZ9ARFF3370, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.50 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-07-06 | 2014-09-11 | 2014-07-06 | 2014-09-11 | 53 |  |  |  | 0 | 0
DUKHCONP1AZ9ARRF3600 | Block work | 20 | 20 | 0% | 2014-07-06 | 2014-07-28 | 2014-07-06 | 2014-07-28 | 48 | No | DUKHCONP1AZ8ARRF3600, DUKHCONP1AZ9STRF2055, DUKHCONP1AZ9STRF2055 | DUKHCONP1AZ9ARRF3605, DUKHCONP1AZ9ARRF3605 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-08-26 | 2014-09-11 | 2014-08-26 | 2014-09-11 | 53 | No | DUKHCONP1AZ9ARRF3695, DUKHCONP1AZ9ARRF3695 | DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-07-28 | 2014-08-17 | 2014-07-28 | 2014-08-17 | 53 | No | DUKHCONP1AZ9ARRF3605, DUKHCONP1AZ9ARRF3605 | DUKHCONP1AZ9ARRF3695, DUKHCONP1AZ9ARRF3695 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-08-09 | 2014-08-31 | 2014-08-09 | 2014-08-31 | 53 | No | DUKHCONP1AZ9ARRF3610, DUKHCONP1AZ9ARRF3610 | DUKHCONP1AZ9ARRF3620, DUKHCONP1AZ9AREL3680, DUKHCONP1AZ9ARRF3620, DUKHCONP1AZ9AREL3680 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-07-14 | 2014-08-09 | 2014-07-14 | 2014-08-09 | 48 | No | DUKHCONP1AZ9ARRF3600, DUKHCONP1AZ9ARRF3600 | DUKHCONP1AZ9AREL3665, DUKHCONP1AZ9PLRF4345, DUKHCONP1AZ9ARRF3610, DUKHCONP1AZ9ARRF3610, DUKHCONP1AZ9PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L15.50 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-07-23 | 2014-10-15 | 2014-07-23 | 2014-10-15 | 26 |  |  |  | 0 | 0
DHBL.K30.L15.50 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-08-10 | 2014-10-15 | 2014-08-10 | 2014-10-15 | 26 |  |  |  | 0 | 0
DUKHCONP1AZ9ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-08-31 | 2014-09-28 | 2014-08-31 | 2014-09-28 | 21 | No | DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ9ARRF3645 | DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9ARRF3655 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-09-27 | 2014-10-15 | 2014-09-27 | 2014-10-15 | 26 | No | DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9ARRF3655 | DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9ELTC8010 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 21 | No | DUKHCONP1AZ9ARRF3635, DUKHCONP1AZ9ARRF3635 | DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ9ARRF3645 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-09-15 | 2014-10-07 | 2014-09-15 | 2014-10-07 | 21 | No | DUKHCONP1AZ9ARRF3650, DUKHCONP1AZ8ARRF3655, DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ9ARRF3650, DUKHCONP1AZ9ARRF3645 | DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ9ARRF3660, DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ9ARRF3660 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-08-13 | 2014-09-10 | 2014-08-13 | 2014-09-10 | 21 | No | DUKHCONP1AZ9ARRF3630, DUKHCONP1AZ9ARRF3630 | DUKHCONP1AZ9ARRF3640, DUKHCONP1AZ9ARRF3640 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-08-10 | 2014-09-07 | 2014-08-10 | 2014-09-07 | 21 | No | DUKHCONP1AZ9STRF2065, DUKHCONP1AZ8ARRF3630, DUKHCONP1AZ9STRF2060, DUKHCONP1AZ9STRF2060, DUKHCONP1AZ9STRF2065 | DUKHCONP1AZ9ARRF3635, DUKHCONP1AZ9ARRF3635 | 0 | 0 | ROOF
DUKHCONP1AZ9ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-08-23 | 2014-09-20 | 2014-08-23 | 2014-09-20 | 21 | No | DUKHCONP1AZ9ARRF3640, DUKHCONP1AZ9ARRF3640 | DUKHCONP1AZ9ACRF4630, DUKHCONP1AZ9ARRF3650, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9ARRF3650, DUKHCONP1AZ9ACRF4630, DUKHCONP1AZ9ELRF4070, DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9ELRF4070 | 0 | 0 | ROOF
DHBL.K30.L15.50 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-07-23 | 2014-09-16 | 2014-07-23 | 2014-09-16 | 49 |  |  |  | 0 | 0
DUKHCONP1AZ9AREL3680 | External Painting | 20 | 20 | 0% | 2014-08-25 | 2014-09-16 | 2014-08-25 | 2014-09-16 | 49 | No | DUKHCONP1AZ9AREL3670, DUKHCONP1AZ9ARRF3695, DUKHCONP1AZ8AREL3680, DUKHCONP1AZ9AREL3670, DUKHCONP1AZ9ARRF3695 | DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9PLTC8005 | 0 | 0 | ELEVATION
DUKHCONP1AZ9AREL3665 | External Plastering | 25 | 25 | 0% | 2014-07-23 | 2014-08-24 | 2014-07-23 | 2014-08-24 | 47 | No | DUKHCONP1AZ9ARRF3605, DUKHCONP1AZ9STRF2065, DUKHCONP1AZ8AREL3665, DUKHCONP1AZ9STRF2065, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3305 | DUKHCONP1AZ9AREL3670, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9AREL3670, DUKHCONP1AZ9PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP1AZ9AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-08-13 | 2014-09-04 | 2014-08-13 | 2014-09-04 | 49 | No | DUKHCONP1AZ9AREL3665, DUKHCONP1AZ9AREL3665, DUKHCONP1AZ8AREL3670 | DUKHCONP1AZ9AREL3680, DUKHCONP1AZ9AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L15.50 .20 MEP WORKS |  | 243 | 243 | 0% | 2014-01-28 | 2014-11-13 | 2014-01-28 | 2014-11-13 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.50 .20 .10 ELECTRICAL WORKS |  | 155 | 155 | 0% | 2014-05-12 | 2014-11-13 | 2014-05-12 | 2014-11-13 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.50 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-05-12 | 2014-09-21 | 2014-05-12 | 2014-09-21 | 25 |  |  |  | 0 | 0
DUKHCONP1AZ9ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-05-24 | 2014-06-15 | 2014-05-24 | 2014-06-15 | 45 | No | DUKHCONP1AZ8ELGF4005, DUKHCONP1AZ9ELGF4000, DUKHCONP1AZ9ELGF4000 | DUKHCONP1AZ9ELGF4010, DUKHCONP1AZ9ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 27 | No | DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ9ARGF3000 | DUKHCONP1AZ9ELGF4005, DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ9ELGF4005, DUKHCONP1AZ9ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-08-06 | 2014-09-03 | 2014-08-06 | 2014-09-03 | 30 | No | DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ8ELGF4015 | DUKHCONP1AZ9ELFF4055, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-08-12 | 2014-09-03 | 2014-08-12 | 2014-09-03 | 18 | No | DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ELGF4010, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ELGF4010, DUKHCONP1AZ9ARGF3060 | DUKHCONP1AZ9ELGF4030, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-08-24 | 2014-09-21 | 2014-08-24 | 2014-09-21 | 25 | No | DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ8ELGF4025 | DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ9ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-08-24 | 2014-09-15 | 2014-08-24 | 2014-09-15 | 18 | No | DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ8ELGF4030 | DUKHCONP1AZ9ELFF4050, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 45 | No | DUKHCONP1AZ9ELGF4005, DUKHCONP1AZ9ELGF4005 | DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ9ARGF3045, DUKHCONP1AZ9ELGF4020, DUKHCONP1AZ9ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.50 .20 .10 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2014-06-23 | 2014-10-27 | 2014-06-23 | 2014-10-27 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ9ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-07-05 | 2014-07-27 | 2014-07-05 | 2014-07-27 | 29 | No | DUKHCONP1AZ9ELFF4035, DUKHCONP1AZ9ELFF4035 | DUKHCONP1AZ9ELFF4045, DUKHCONP1AZ9ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 11 | No | DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9ARFF3300 | DUKHCONP1AZ9ELFF4040, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ELFF4040, DUKHCONP1AZ9ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-09-15 | 2014-10-15 | 2014-09-15 | 2014-10-15 | 1 | No | DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ELGF4015, DUKHCONP1AZ8ELFF4055, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ELGF4015 | DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-09-18 | 2014-10-13 | 2014-09-18 | 2014-10-13 | 3 | No | DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ8ELFF4060, DUKHCONP1AZ9ELFF4045, DUKHCONP1AZ9ELFF4045, DUKHCONP1AZ9ARFF3360 | DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ9ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 1 | No | DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ8ELFF4065, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELFF4060, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELFF4060 | DUKHCONP1AZ9ELRF4070, DUKHCONP1AZ9ELRF4070, DUKHCONP1AZ9ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-09-15 | 2014-10-15 | 2014-09-15 | 2014-10-15 | 9 | No | DUKHCONP1AZ9ELGF4030, DUKHCONP1AZ9MSEX5010, DUKHCONP1AZ9ELGF4030, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3360 | DUKHCONP1AZ9ELRF4070, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-07-15 | 2014-08-16 | 2014-07-15 | 2014-08-16 | 27 | No | DUKHCONP1AZ8ELFF4045, DUKHCONP1AZ9ELFF4040, DUKHCONP1AZ9ELFF4040 | DUKHCONP1AZ9ELFF4060, DUKHCONP1AZ9ELRF4070, DUKHCONP1AZ9ARFF3345, DUKHCONP1AZ9ARFF3345, DUKHCONP1AZ9ELFF4060, DUKHCONP1AZ9ELRF4070 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.50 .20 .10 .20 ROOF |  | 28 | 28 | 0% | 2014-10-13 | 2014-11-13 | 2014-10-13 | 2014-11-13 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ9ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-10-13 | 2014-11-02 | 2014-10-13 | 2014-11-02 | 1 | No | DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ9ELFF4050, DUKHCONP1AZ9ELFF4065, DUKHCONP1AZ9ELFF4045, DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ9ELFF4050, DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ9ELFF4045 | DUKHCONP1AZ9ELRF4075, DUKHCONP1AZ9ELRF4075 | 0 | 0 | ROOF
DUKHCONP1AZ9ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-10-19 | 2014-11-13 | 2014-10-19 | 2014-11-13 | 1 | No | DUKHCONP1AZ9ELRF4070, DUKHCONP1AZ9ELRF4070 | DUKHCONP1AZ9ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L15.50 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 243 | 243 | 0% | 2014-01-28 | 2014-11-13 | 2014-01-28 | 2014-11-13 | 1 |  |  |  | 0 | 0
DHBL.K30.L15.50 .20 .15 .10 GROUND FLOOR |  | 199 | 199 | 0% | 2014-01-28 | 2014-09-21 | 2014-01-28 | 2014-09-21 | 45 |  |  |  | 0 | 0
DUKHCONP1AZ9PLUG4300 | Drainage / Storm Pipes in Grade Slab | 16 | 16 | 0% | 2014-01-28 | 2014-02-16 | 2014-01-28 | 2014-02-16 | 0 | Yes | DUKHCONP1AZ9STUG1040, DUKHCONP1AZ9STUG1040 | DUKHCONP1AZ9STUG1045, DUKHCONP1AZ9STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-05-22 | 2014-06-11 | 2014-05-22 | 2014-06-11 | 21 | No | DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ9PLGF4305, DUKHCONP1AZ9PLGF4305 | DUKHCONP1AZ9PLGF4315, DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ9MSEX5000, DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ9MSEX5000, DUKHCONP1AZ9PLGF4315 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-05-22 | 2014-06-11 | 2014-05-22 | 2014-06-11 | 18 | No | DUKHCONP1AZ9ARGF3000, DUKHCONP1AZ8PLGF4305, DUKHCONP1AZ9ARGF3000 | DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9ARGF3020, DUKHCONP1AZ9PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-09-04 | 2014-09-21 | 2014-09-04 | 2014-09-21 | 45 | No | DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9PLGF4315, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ8PLGF4320, DUKHCONP1AZ9PLGF4315 | DUKHCONP1AZ9PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-08-24 | 2014-09-15 | 2014-08-24 | 2014-09-15 | 45 | No | DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ8PLGF4315, DUKHCONP1AZ9ARGF3065, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9ARGF3065 | DUKHCONP1AZ9PLGF4320, DUKHCONP1AZ9PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.50 .20 .15 .15 FIRST FLOORS |  | 90 | 90 | 0% | 2014-07-05 | 2014-10-22 | 2014-07-05 | 2014-10-22 | 5 |  |  |  | 0 | 0
DUKHCONP1AZ9PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-07-05 | 2014-07-24 | 2014-07-05 | 2014-07-24 | 22 | No | DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9PLFF4325, DUKHCONP1AZ8PLFF4330, DUKHCONP1AZ9PLFF4325 | DUKHCONP1AZ9PLFF4335, DUKHCONP1AZ9ARFF3320, DUKHCONP1AZ9ARFF3320, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9PLFF4335 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-07-05 | 2014-07-24 | 2014-07-05 | 2014-07-24 | 0 | Yes | DUKHCONP1AZ9ARFF3300, DUKHCONP1AZ9ARFF3300 | DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3320, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-10-04 | 2014-10-22 | 2014-10-04 | 2014-10-22 | 5 | No | DUKHCONP1AZ9PLFF4335, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9PLFF4335, DUKHCONP1AZ8PLFF4340 | DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ9PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-09-22 | 2014-10-16 | 2014-09-22 | 2014-10-16 | 5 | No | DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9ARFF3365, DUKHCONP1AZ9PLFF4330 | DUKHCONP1AZ9PLFF4340, DUKHCONP1AZ9PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.50 .20 .15 .20 ROOF |  | 89 | 89 | 0% | 2014-07-28 | 2014-11-13 | 2014-07-28 | 2014-11-13 | 1 |  |  |  | 0 | 0
DUKHCONP1AZ9PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-07-28 | 2014-08-17 | 2014-07-28 | 2014-08-17 | 52 | No | DUKHCONP1AZ9ARRF3605, DUKHCONP1AZ9ARRF3605 | DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ9PLRF4350 | 0 | 0 | ROOF
DUKHCONP1AZ9PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-09-09 | 2014-09-25 | 2014-09-09 | 2014-09-25 | 26 | No | DUKHCONP1AZ9PLRF4345, DUKHCONP1AZ9AREL3665, DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ8PLRF4350, DUKHCONP1AZ9AREL3665, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9PLFF4330, DUKHCONP1AZ9PLRF4345 | DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9WEEX5065, DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ9WEEX5065, DUKHCONP1AZ9PLRF4355 | 0 | 0 | ROOF
DUKHCONP1AZ9PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-10-16 | 2014-11-13 | 2014-10-16 | 2014-11-13 | 1 | No | DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9PLFF4340, DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9PLRF4345, DUKHCONP1AZ8PLRF4355, DUKHCONP1AZ9PLRF4345, DUKHCONP1AZ9PLFF4340, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9PLRF4350 | DUKHCONP1AZ9PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L15.50 .20 .20 AC WORKS |  | 127 | 127 | 0% | 2014-06-11 | 2014-11-11 | 2014-06-11 | 2014-11-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L15.50 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-06-11 | 2014-09-18 | 2014-06-11 | 2014-09-18 | 32 |  |  |  | 0 | 0
DUKHCONP1AZ9ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-08-27 | 2014-09-18 | 2014-08-27 | 2014-09-18 | 32 | No | DUKHCONP1AZ8ACGF4610, DUKHCONP1AZ9ACGF4605, DUKHCONP1AZ9ACGF4605 | DUKHCONP1AZ9ACRF4635, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ACRF4635, DUKHCONP1AZ9ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-08-06 | 2014-09-03 | 2014-08-06 | 2014-09-03 | 32 | No | DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ8ACGF4605, DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3060 | DUKHCONP1AZ9ACGF4610, DUKHCONP1AZ9ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1AZ9ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-06-11 | 2014-07-03 | 2014-06-11 | 2014-07-03 | 49 | No | DUKHCONP1AZ9ARGF3005, DUKHCONP1AZ8ACGF4600, DUKHCONP1AZ9ARGF3005 | DUKHCONP1AZ9ACRF4630, DUKHCONP1AZ9ACRF4630, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ARGF3055, DUKHCONP1AZ9ACGF4605, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ARGF3060, DUKHCONP1AZ9ACGF4605 | 0 | 0 | GROUND FLOOR
DHBL.K30.L15.50 .20 .20 .15 FIRST FLOORS |  | 79 | 79 | 0% | 2014-07-26 | 2014-10-30 | 2014-07-26 | 2014-10-30 | 2 |  |  |  | 0 | 0
DUKHCONP1AZ9ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-10-06 | 2014-10-30 | 2014-10-06 | 2014-10-30 | 2 | No | DUKHCONP1AZ9ACFF4620, DUKHCONP1AZ8ACFF4625, DUKHCONP1AZ9ACFF4620 | DUKHCONP1AZ9ACRF4635, DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9ACRF4635, DUKHCONP1AZ9ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-09-15 | 2014-10-15 | 2014-09-15 | 2014-10-15 | 2 | No | DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ8ACFF4620, DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3360 | DUKHCONP1AZ9ACFF4625, DUKHCONP1AZ9ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1AZ9ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-07-26 | 2014-08-20 | 2014-07-26 | 2014-08-20 | 27 | No | DUKHCONP1AZ8ACFF4615, DUKHCONP1AZ9ARFF3305, DUKHCONP1AZ9ARFF3305 | DUKHCONP1AZ9ACFF4620, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ARFF3360, DUKHCONP1AZ9ACFF4620, DUKHCONP1AZ9ACRF4630, DUKHCONP1AZ9ACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L15.50 .20 .20 .20 ROOF |  | 61 | 61 | 0% | 2014-08-31 | 2014-11-11 | 2014-08-31 | 2014-11-11 | 3 |  |  |  | 0 | 0
DUKHCONP1AZ9ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-10-14 | 2014-11-11 | 2014-10-14 | 2014-11-11 | 3 | No | DUKHCONP1AZ9ACGF4610, DUKHCONP1AZ9ACFF4625, DUKHCONP1AZ8ACRF4635, DUKHCONP1AZ9ACRF4630, DUKHCONP1AZ9ACGF4610, DUKHCONP1AZ9ACFF4625, DUKHCONP1AZ9ACRF4630 | DUKHCONP1AZ9ACTC8000 | 0 | 0 | ROOF
DUKHCONP1AZ9ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-08-31 | 2014-09-28 | 2014-08-31 | 2014-09-28 | 34 | No | DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ACGF4600, DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ8ACRF4630, DUKHCONP1AZ9ACFF4615, DUKHCONP1AZ9ARRF3645, DUKHCONP1AZ9ACFF4615 | DUKHCONP1AZ9ACRF4635, DUKHCONP1AZ9ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L15.50 .25 EXTERNAL WORKS |  | 116 | 116 | 0% | 2014-06-17 | 2014-11-04 | 2014-06-17 | 2014-11-04 | 34 |  |  |  | 0 | 0
DHBL.K30.L15.50 .25 .10 MISCELLANEOUS |  | 116 | 116 | 0% | 2014-06-17 | 2014-11-04 | 2014-06-17 | 2014-11-04 | 34 |  |  |  | 0 | 0
DUKHCONP1AZ9MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-10-05 | 2014-11-04 | 2014-10-05 | 2014-11-04 | 34 | No | DUKHCONP1AZ8MSEX5335, DUKHCONI1AZ5BWGL5325 | DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ9MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-07-01 | 2014-07-29 | 2014-07-01 | 2014-07-29 | 9 | No | DUKHCONP1AZ9MSEX5000, DUKHCONP1AZ9MSEX5000 | DUKHCONP1AZ9MSEX5015, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ9MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-08-12 | 2014-09-09 | 2014-08-12 | 2014-09-09 | 16 | No | DUKHCONP1AZ9STRF2055, DUKHCONP1AZ9STRF2055, DUKHCONP1AZ8MSEX5020 | DUKHCONP1AZ9MSEX5025, DUKHCONP1AZ9HDEX5090, DUKHCONP1AZ9MSEX5025, DUKHCONP1AZ9HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ9MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-07-21 | 2014-08-16 | 2014-07-21 | 2014-08-16 | 9 | No | DUKHCONP1AZ9MSEX5005, DUKHCONP1AZ9MSEX5005 | DUKHCONP1AZ9WEEX5065, DUKHCONP1AZ9WEEX5065, DUKHCONP1AZ9MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ9MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 9 | No | DUKHCONP1AZ9STRF2055, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9PLGF4310, DUKHCONP1AZ9STRF2055 | DUKHCONP1AZ9MSEX5005, DUKHCONP1AZ9MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ9MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-08-30 | 2014-09-21 | 2014-08-30 | 2014-09-21 | 19 | No | DUKHCONP1AZ9MSEX5020, DUKHCONP1AZ9MSEX5020 | DUKHCONP1AZ9WEEX5060, DUKHCONP1AZ9WEEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP1AZ9MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 9 | No | DUKHCONP1AZ9MSEX5015 | DUKHCONP1AZ9ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L15.50 .25 .15 WATER TANK ENCLOSURE |  | 105 | 105 | 0% | 2014-06-30 | 2014-11-04 | 2014-06-30 | 2014-11-04 | 9 |  |  |  | 0 | 0
DUKHCONP1AZ9WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-07-15 | 2014-08-16 | 2014-07-15 | 2014-08-16 | 48 | No | DUKHCONP1AZ9WEEX5035, DUKHCONP1AZ9WEEX5035 | DUKHCONP1AZ9WEEX5045, DUKHCONP1AZ9WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ9WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-07-06 | 2014-08-06 | 2014-07-06 | 2014-08-06 | 48 | No | DUKHCONP1AZ9WEEX5030, DUKHCONP1AZ9WEEX5030 | DUKHCONP1AZ9WEEX5040, DUKHCONP1AZ9WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ9WEEX5030 | Excavation | 20 | 20 | 0% | 2014-06-30 | 2014-07-22 | 2014-06-30 | 2014-07-22 | 48 | No | DUKHCONP1AZ9STRF2055, DUKHCONP1AZ9STRF2055, DUKHCONP1AZ8WEEX5030 | DUKHCONP1AZ9WEEX5035, DUKHCONP1AZ9WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ9WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-07-22 | 2014-08-23 | 2014-07-22 | 2014-08-23 | 48 | No | DUKHCONP1AZ9WEEX5040, DUKHCONP1AZ9WEEX5040 | DUKHCONP1AZ9WEEX5050, DUKHCONP1AZ9WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ9WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-10-05 | 2014-11-04 | 2014-10-05 | 2014-11-04 | 9 | No | DUKHCONP1AZ9MSEX5015, DUKHCONP1AZ9WEEX5060, DUKHCONP1AZ9MSEX5015, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ8WEEX5065, DUKHCONP1AZ9WEEX5060, DUKHCONP1AZ9PLRF4350 | DUKHCONP1AZ9PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ9WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-09-10 | 2014-10-02 | 2014-09-10 | 2014-10-02 | 19 | No | DUKHCONP1AZ9MSEX5025, DUKHCONP1AZ9WEEX5045, DUKHCONP1AZ9WEEX5045 | DUKHCONP1AZ9WEEX5060, DUKHCONP1AZ9WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1AZ9WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 10 | No | DUKHCONP1AZ9WEEX5050, DUKHCONP1AZ9MSEX5025, DUKHCONP1AZ9WEEX5050, DUKHCONP1AZ8WEEX5060 | DUKHCONP1AZ9WEEX5065, DUKHCONP1AZ9WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L15.50 .25 .20 HARD LANDSCAPING |  | 36 | 36 | 0% | 2014-08-26 | 2014-10-06 | 2014-08-26 | 2014-10-06 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ9HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-09-07 | 2014-09-29 | 2014-09-07 | 2014-09-29 | 16 | No | DUKHCONP1AZ9HDEX5090, DUKHCONP1AZ9HDEX5090 | DUKHCONP1AZ9HDEX5100, DUKHCONP1AZ9HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ9HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-09-14 | 2014-10-06 | 2014-09-14 | 2014-10-06 | 16 | No | DUKHCONP1AZ9HDEX5095, DUKHCONP1AZ9HDEX5095 | DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9SLEX5105, DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1AZ9HDEX5090 | kerb works | 20 | 20 | 0% | 2014-08-26 | 2014-09-17 | 2014-08-26 | 2014-09-17 | 16 | No | DUKHCONP1AZ8HDEX5090, DUKHCONP1AZ9MSEX5020, DUKHCONP1AZ9MSEX5020 | DUKHCONP1AZ9HDEX5095, DUKHCONP1AZ9HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L15.50 .25 .25 SOFT LANDSCAPING |  | 31 | 31 | 0% | 2014-09-20 | 2014-10-27 | 2014-09-20 | 2014-10-27 | 16 |  |  |  | 0 | 0
DUKHCONP1AZ9SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-09-20 | 2014-10-20 | 2014-09-20 | 2014-10-20 | 16 | No | DUKHCONP1AZ9HDEX5100, DUKHCONP1AZ9HDEX5100 | DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9SLEX5110, DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9SLEX5110, DUKHCONP1AZ9PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1AZ9SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 16 | No | DUKHCONP1AZ9SLEX5105, DUKHCONP1AZ9SLEX5105 | DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ9PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L15.50 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-11-16 | 2014-12-14 | 2014-11-16 | 2014-12-14 | 0 |  |  |  | 0 | 0
DUKHCONP1AZ9ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-11-16 | 2014-12-14 | 2014-11-16 | 2014-12-14 | 0 | Yes | DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ8ACTC8000, DUKHCONP1AZ9HDEX5100, DUKHCONP1AZ9SLEX5110, DUKHCONP1AZ9ACFF4625, DUKHCONP1AZ9AREL3680, DUKHCONP1AZ9ACRF4635, DUKHCONP1AZ9ARRF3620, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9MSEX5005, DUKHMOBI1APS00002065, DUKHCONP1AZ9SLEX5105, DUKHMOBP1APS00002030 | DUKHHANP1AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ9ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-11-16 | 2014-12-14 | 2014-11-16 | 2014-12-14 | 0 | Yes | DUKHCONP1AZ9SLEX5105, DUKHCONP1AZ9SLEX5110, DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9ELFF4055, DUKHMOBI1APS00002065, DUKHMOBP1APS00002030, DUKHCONP1AZ9ELGF4030, DUKHCONP1AZ9ELRF4075, DUKHCONP1AZ9ARRF3620, DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ9MSEX5005, DUKHCONP1AZ9ELFF4050, DUKHCONP1AZ9ARRF3660, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9HDEX5100, DUKHCONP1AZ9ELGF4025, DUKHCONP1AZ9ELGF4015, DUKHCONP1AZ9AREL3680, DUKHCONP1AZ9ELFF4065 | DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1AZ9PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-11-16 | 2014-12-14 | 2014-11-16 | 2014-12-14 | 0 | Yes | DUKHCONP1AZ9ARRF3655, DUKHCONP1AZ9ARRF3620, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ9PLRF4350, DUKHCONP1AZ9ARRF3660, DUKHCONP1AZ9ARFF3395, DUKHCONP1AZ9MSEX5005, DUKHCONP1AZ9HDEX5100, DUKHCONP1AZ9SLEX5110, DUKHCONP1AZ9PLGF4320, DUKHMOBI1APS00002065, DUKHCONP1AZ9ARGF3095, DUKHCONP1AZ9PLRF4355, DUKHCONP1AZ9AREL3680, DUKHCONP1AZ9WEEX5065, DUKHMOBP1APS00002030, DUKHCONP1AZ9SLEX5105 | DUKHHANP1AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L20 PACKAGE-1A INFRASTRUCTURE WORKS |  | 407 | 407 | 0% | 2013-08-24 | 2014-12-22 | 2013-08-24 | 2014-12-22 | 14 |  |  |  | 0 | 0
DHBL.K30.L20.10 ZONE - 1 |  | 229 | 229 | 0% | 2013-08-24 | 2014-05-21 | 2013-08-24 | 2014-05-21 | 92 |  |  |  | 0 | 0
DHBL.K30.L20.10 .10 INFRASTRUCTURE WORKS |  | 229 | 229 | 0% | 2013-08-24 | 2014-05-21 | 2013-08-24 | 2014-05-21 | 92 |  |  |  | 0 | 0
DHBL.K30.L20.10 .10 .10 DRAINAGE LINES |  | 50 | 50 | 0% | 2013-08-24 | 2013-10-22 | 2013-08-24 | 2013-10-22 | 20 |  |  |  | 0 | 0
DUKHCONI1AZ1DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-10-03 | 2013-10-22 | 2013-10-03 | 2013-10-22 | 20 | No | DUKHCONI1AZ1DRGL5125, DUKHCONI1AZ1DRGL5125 | DUKHCONI1AZ1SAGL5135, DUKHCONI1AZ1WSGL5155, DUKHCONI1AZ2DRGL5115, DUKHCONI1AZ1SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ1DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-08-24 | 2013-09-21 | 2013-08-24 | 2013-09-21 | 20 | No | DUKHENGI1ADWDRAP4250, DUKHCONP1AZ2STGF2010 | DUKHCONI1AZ1DRGL5120, DUKHMOBI1APS00002065, DUKHCONI1AZ1DRGL5120, DUKHCONI1AZ1SAGL5140, DUKHCONI1AZ1SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ1DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-09-04 | 2013-10-02 | 2013-09-04 | 2013-10-02 | 20 | No | DUKHCONI1AZ1DRGL5115, DUKHCONI1AZ1DRGL5115 | DUKHCONI1AZ1DRGL5125, DUKHCONI1AZ1DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ1DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-09-16 | 2013-10-14 | 2013-09-16 | 2013-10-14 | 20 | No | DUKHCONI1AZ1DRGL5120, DUKHCONI1AZ1DRGL5120 | DUKHCONI1AZ1DRGL5130, DUKHCONI1AZ1DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L20.10 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-10-03 | 2013-12-26 | 2013-10-03 | 2013-12-26 | 67 |  |  |  | 0 | 0
DUKHCONI1AZ1SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2013-12-03 | 2013-12-26 | 2013-12-03 | 2013-12-26 | 67 | No | DUKHCONI1AZ1SAGL5145, DUKHCONI1AZ1SAGL5135 | DUKHCONI1AZ1RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ1SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-10-03 | 2013-11-03 | 2013-10-03 | 2013-11-03 | 92 | No | DUKHCONI1AZ1DRGL5130, DUKHENGI1ADWDRAP4250, DUKHCONI1AZ1DRGL5115, DUKHENGI03DWDRAP5810 | DUKHCONI1AZ2SAGL5135, DUKHCONI1AZ1SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ1SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 20 | No | DUKHCONI1AZ1SAGL5140 | DUKHCONI1AZ1WSGL5170, DUKHCONI1AZ1SAGL5150, DUKHCONI1AZ2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ1SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-10-03 | 2013-11-03 | 2013-10-03 | 2013-11-03 | 20 | No | DUKHCONI1AZ1DRGL5115, DUKHCONI1AZ1DRGL5130 | DUKHCONI1AZ1SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L20.10 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2013-10-15 | 2014-01-01 | 2013-10-15 | 2014-01-01 | 62 |  |  |  | 0 | 0
DUKHCONI1AZ1WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 20 | No | DUKHCONI1AZ1SAGL5145, DUKHCONI1AZ1WSGL5165 | DUKHCONI1AZ1FFGL5185, DUKHCONI1AZ1WSGL5175, DUKHCONI1AZ2WSGL5155 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 62 | No | DUKHCONI1AZ1WSGL5170, DUKHCONI1AZ1WSGL5155 | DUKHCONI1AZ2WSGL5175, DUKHCONI1AZ1WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ1WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-10-15 | 2013-11-14 | 2013-10-15 | 2013-11-14 | 20 | No | DUKHCONI1AZ1DRGL5130, DUKHENGI1ADWWSAP4270 | DUKHCONI1AZ1WSGL5175, DUKHCONI1AZ1WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ1WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2013-12-09 | 2014-01-01 | 2013-12-09 | 2014-01-01 | 62 | No | DUKHCONI1AZ1WSGL5175 | DUKHCONI1AZ1FFGL5210, DUKHCONI1AZ2WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ1WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-10-23 | 2013-11-20 | 2013-10-23 | 2013-11-20 | 20 | No | DUKHCONI1AZ1WSGL5155 | DUKHCONI1AZ1WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ1WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2013-10-29 | 2013-11-26 | 2013-10-29 | 2013-11-26 | 20 | No | DUKHCONI1AZ1WSGL5160 | DUKHCONI1AZ1WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L20.10 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2013-11-16 | 2014-01-15 | 2013-11-16 | 2014-01-15 | 50 |  |  |  | 0 | 0
DUKHCONI1AZ1FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 20 | No | DUKHCONI1AZ1FFGL5195 | DUKHCONI1AZ1FFGL5205, DUKHCONI1AZ1ELGL5215, DUKHCONI1AZ2FFGL5185, DUKHCONI1AZ1RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ1FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 50 | No | DUKHCONI1AZ1FFGL5205, DUKHCONI1AZ1WSGL5180 | DUKHCONI1AZ2FFGL5210, DUKHCONI1ASBIWGL7440, DUKHCONI1AZ1RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-12-11 | 2014-01-09 | 2013-12-11 | 2014-01-09 | 50 | No | DUKHCONI1AZ1FFGL5185, DUKHCONI1AZ1FFGL5200, DUKHPROGEN00PRDV3690 | DUKHCONI1AZ1FFGL5210, DUKHCONI1AZ2FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ1FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 20 | No | DUKHCONI1AZ1WSGL5170, DUKHENGI1ADWFFAP4260 | DUKHCONI1AZ1FFGL5205, DUKHCONI1AZ1FFGL5190 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ1FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2013-11-24 | 2013-12-23 | 2013-11-24 | 2013-12-23 | 20 | No | DUKHCONI1AZ1FFGL5185, DUKHPROGEN00PRDV3540, DUKHPROGEN00PRDV3650 | DUKHCONI1AZ1FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ1FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 20 | No | DUKHCONI1AZ1FFGL5190 | DUKHCONI1AZ1FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L20.10 .10 .30 ELECTRICAL LINES |  | 51 | 51 | 0% | 2013-12-14 | 2014-02-12 | 2013-12-14 | 2014-02-12 | 95 |  |  |  | 0 | 0
DUKHCONI1AZ1ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 31 | No | DUKHCONI1AZ1ELGL5220, DUKHCONI1AZ1ELGL5215 | DUKHCONI1AZ2ELGL5215, DUKHCONI1AZ1RWGL6000, DUKHCONI1AZ1IRGL5265, DUKHCONI1AZ1ELGL5230, DUKHCONI1AZ1IRGL5285, DUKHCONI1AZ1ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 95 | No | DUKHCONI1AZ1ELGL5225, DUKHCONI1AZ1ELGL5225 | DUKHCONI1AZ2ELGL5230, DUKHCONI1AZ1STGL5260, DUKHCONI1AZ1STGL5255 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 28 | No | DUKHENGI1ADWELAP4280, DUKHCONI1AZ1FFGL5200 | DUKHCONI1AZ1ELGL5220, DUKHCONI1AZ1ELGL5225, DUKHCONI1AZ1STGL5235 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ1ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 31 | No | DUKHCONI1AZ1ELGL5215 | DUKHCONI1AZ1ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L20.10 .10 .35 STREET LIGHTING |  | 97 | 97 | 0% | 2013-12-14 | 2014-04-07 | 2013-12-14 | 2014-04-07 | 95 |  |  |  | 0 | 0
DUKHCONI1AZ1STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2013-12-26 | 2014-01-23 | 2013-12-26 | 2014-01-23 | 28 | No | DUKHCONI1AZ1STGL5235, DUKHCONI1AZ1STGL5245 | DUKHCONI1AZ2STGL5235, DUKHCONI1AZ1RWGL6000, DUKHCONI1AZ1BWGL5315, DUKHCONI1AZ1TCGL5295, DUKHCONI1AZ1STGL5255 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ1STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 28 | No | DUKHCONI1AZ1STGL5235 | DUKHCONI1AZ1STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ1STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 28 | No | DUKHCONI1AZ1STGL5240 | DUKHCONI1AZ1STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ1STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 95 | No | DUKHCONI1AZ1ELGL5230, DUKHCONI1AZ1STGL5255 | DUKHCONI1AZ2STGL5260, DUKHCONI1AZ1PSGL7015 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ1STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 28 | No | DUKHENGI1ADWSTAP4290, DUKHCONI1AZ1ELGL5215 | DUKHCONI1AZ1STGL5250, DUKHCONI1AZ1STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ1STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 95 | No | DUKHPROGEN00PRDV3250, DUKHCONI1AZ1STGL5250, DUKHPROGEN00PRDV3350, DUKHCONI1AZ1ELGL5230 | DUKHCONI1AZ2STGL5255, DUKHCONI1AZ1STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L20.10 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-01-27 | 2014-04-03 | 2014-01-27 | 2014-04-03 | 73 |  |  |  | 0 | 0
DUKHCONI1AZ1IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 53 | No | DUKHCONI1AZ1IRGL5275 | DUKHCONI1AZ1IRGL5285, DUKHCONI1AZ1IRGL5290, DUKHCONI1AZ2IRGL5265 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 73 | No | DUKHCONI1AZ1IRGL5280, DUKHCONI1AZ1ELGL5225 | DUKHCONI1AZ1IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ1IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 53 | No | DUKHCONI1AZ1ELGL5225, DUKHENGI1ADWIRAP4310 | DUKHCONI1AZ1IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 73 | No | DUKHPROGEN00PRDV3860, DUKHCONI1AZ1IRGL5285, DUKHPROGEN00PRDV3830, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3840, DUKHPROGEN00PRDV3870, DUKHPROGEN00PRDV3760, DUKHCONI1AZ1IRGL5280 | DUKHCONI1AZ1SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ1IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 53 | No | DUKHPROGEN00PRDV3670, DUKHCONI1AZ1IRGL5265 | DUKHCONI1AZ1IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ1IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 53 | No | DUKHCONI1AZ1IRGL5270 | DUKHCONI1AZ1IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L20.10 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-01-07 | 2014-02-23 | 2014-01-07 | 2014-02-23 | 33 |  |  |  | 0 | 0
DUKHCONI1AZ1TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 28 | No | DUKHCONI1AZ1TCGL5300 | DUKHCONI1AZ2TCGL5295, DUKHCONI1AZ1TCGL5310, DUKHCONI1AZ1TCGL5310, DUKHCONI1AZ1RWGL6000 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ1TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 33 | No | DUKHCONI1AZ1TCGL5305, DUKHCONI1AZ1TCGL5305 | DUKHCONI1AZ1RWGL6000, DUKHCONI1AZ2TCGL5310, DUKHCONI1ASBTRGL7630 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ1TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 28 | No | DUKHENGI1ADWTCAP4300, DUKHCONI1AZ1STGL5250 | DUKHCONI1AZ1TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ1TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-01-13 | 2014-02-04 | 2014-01-13 | 2014-02-04 | 28 | No | DUKHCONI1AZ1TCGL5295 | DUKHCONI1AZ1TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L20.10 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-01-07 | 2014-04-03 | 2014-01-07 | 2014-04-03 | 99 |  |  |  | 0 | 0
DUKHCONI1AZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 99 | No | DUKHCONI1AZ1BWGL5320, DUKHCONI1AZ1BWGL5325, DUKHCONI1AZ1BWGL5325 | DUKHCONI1AZ2BWGL5330, DUKHCONI1AZ1PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-02-23 | 2014-03-23 | 2014-02-23 | 2014-03-23 | 99 | No | DUKHCONI1AZ1BWGL5315, DUKHCONI1AZ1BWGL5320 | DUKHCONP1AZ1MSEX5335, DUKHCONI1AZ1BWGL5330, DUKHCONI1AZ1BWGL5330, DUKHCONP1AZ2MSEX5335, DUKHCONI1AZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-01-07 | 2014-02-04 | 2014-01-07 | 2014-02-04 | 99 | No | DUKHPROGEN00PRDV3820, DUKHCONI1AZ1STGL5250, DUKHENGI1ADWBWAP4330 | DUKHCONI1AZ2BWGL5315, DUKHCONI1AZ1BWGL5320, DUKHCONI1AZ1BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-01-23 | 2014-02-22 | 2014-01-23 | 2014-02-22 | 99 | No | DUKHCONI1AZ1BWGL5315, DUKHPROGEN00PRDV3800 | DUKHCONI1AZ1BWGL5330, DUKHCONI1AZ1BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L20.10 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-02-12 | 2014-04-28 | 2014-02-12 | 2014-04-28 | 103 |  |  |  | 0 | 0
DUKHCONI1AZ1RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-02-12 | 2014-02-23 | 2014-02-12 | 2014-02-23 | 28 | No | DUKHCONI1AZ1TCGL5310, DUKHENGI1ADWBWAP4330, DUKHCONI1AZ1STGL5250, DUKHCONI1AZ1ELGL5225, DUKHCONI1AZ1SAGL5150, DUKHCONI1AZ1FFGL5200, DUKHPROGEN00PRDV3750, DUKHCONI1AZ1FFGL5210, DUKHCONI1AZ1TCGL5305 | DUKHCONI1AZ1RWGL6005, DUKHCONI1AZ1HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-04-17 | 2014-04-22 | 2014-04-17 | 2014-04-22 | 97 | No | DUKHCONI1AZ1RWGL6020 | DUKHCONI1AZ1RWGL6030, DUKHCONI1AZ2RWGL6025, DUKHCONI1AZ1HDGL7040 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ1RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 28 | No | DUKHCONI1AZ1RWGL6010 | DUKHCONI1AZ2RWGL6000, DUKHCONI1AZ1RWGL6020, DUKHCONI1AZ1PSGL7000, DUKHCONI1AZ1PSGL7005 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ1RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-03-08 | 2014-04-05 | 2014-03-08 | 2014-04-05 | 28 | No | DUKHCONI1AZ1RWGL6005 | DUKHCONI1AZ1RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-04-12 | 2014-04-16 | 2014-04-12 | 2014-04-16 | 88 | No | DUKHCONI1AZ1RWGL6015 | DUKHCONI1AZ1PSGL7010, DUKHCONI1AZ1RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ1RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 28 | No | DUKHCONI1AZ1RWGL6000 | DUKHCONI1AZ1RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ1RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-04-23 | 2014-04-28 | 2014-04-23 | 2014-04-28 | 103 | No | DUKHPROGEN00PRDV3710, DUKHCONI1AZ1RWGL6025, DUKHPROGEN00PRDV3720, DUKHPROGEN00PRDV3700 | DUKHCONI1AZ2RWGL6030, DUKHCONI1AZ1PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L20.10 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-03-25 | 2014-05-21 | 2014-03-25 | 2014-05-21 | 88 |  |  |  | 0 | 0
DUKHCONI1AZ1PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 88 | No | DUKHPROGEN00PRDV3730, DUKHCONI1AZ1BWGL5330, DUKHCONI1AZ1PSGL7005, DUKHCONI1AZ1RWGL6020, DUKHCONI1AZ1RWGL6030 | DUKHCONI1AZ1PSGL7015, DUKHCONI1AZ2PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI1AZ1PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 88 | No | DUKHCONI1AZ1PSGL7010, DUKHCONI1AZ1STGL5260 | DUKHCONI1AZ2PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1AZ1PSGL7000 | Excavation | 15 | 15 | 0% | 2014-03-25 | 2014-04-10 | 2014-03-25 | 2014-04-10 | 93 | No | DUKHENGI1ADWPSAP4340, DUKHCONI1AZ1RWGL6015 | DUKHCONI1AZ1PSGL7005, DUKHCONI1AZ1PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1AZ1PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-04-06 | 2014-04-22 | 2014-04-06 | 2014-04-22 | 88 | No | DUKHCONI1AZ1PSGL7000, DUKHCONI1AZ1PSGL7000, DUKHCONI1AZ1RWGL6015 | DUKHCONI1AZ2PSGL7000, DUKHCONI1AZ1PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L20.10 .10 .65 HARD LANDSCAPING |  | 80 | 80 | 0% | 2014-02-12 | 2014-05-15 | 2014-02-12 | 2014-05-15 | 97 |  |  |  | 0 | 0
DUKHCONI1AZ1HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-03-08 | 2014-04-05 | 2014-03-08 | 2014-04-05 | 62 | No | DUKHCONI1AZ1HDGL7025 | DUKHCONI1AZ1HDGL7035, DUKHCONI1AZ2HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ1HDGL7040 | Construction of Speed Humps | 20 | 20 | 0% | 2014-04-23 | 2014-05-15 | 2014-04-23 | 2014-05-15 | 97 | No | DUKHPROGEN00PRDV3750, DUKHCONI1AZ1RWGL6025, DUKHCONI1AZ1HDGL7035 | DUKHCONI1AZ1SLGL7210, DUKHCONI1AZ2HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ1HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-03-08 | 2014-04-05 | 2014-03-08 | 2014-04-05 | 62 | No | DUKHCONI1AZ1HDGL7030, DUKHPROGEN00PRDV3740 | DUKHCONI1AZ1SLGL7200, DUKHCONI1AZ1HDGL7040, DUKHCONI1AZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ1HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 62 | No | DUKHCONI1AZ1HDGL7020 | DUKHCONI1AZ1HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ1HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-02-12 | 2014-03-06 | 2014-02-12 | 2014-03-06 | 62 | No | DUKHENGI1ADWSLAP4320, DUKHCONI1AZ1RWGL6000 | DUKHCONI1AZ1HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L20.10 .10 .70 SOFT LANDSCAPING |  | 50 | 50 | 0% | 2014-03-19 | 2014-05-15 | 2014-03-19 | 2014-05-15 | 97 |  |  |  | 0 | 0
DUKHCONI1AZ1SLGL7200 | Excavation | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 62 | No | DUKHCONI1AZ1HDGL7035, DUKHCONI1AZ1IRGL5290, DUKHENGI1ADWSLAP4320 | DUKHCONI1AZ1SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ1SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 97 | No | DUKHCONI1AZ1HDGL7040, DUKHCONI1AZ1SLGL7205 | DUKHCONI1AZ2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ1SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 62 | No | DUKHCONI1AZ1SLGL7200, DUKHPROGEN00PRDV3790 | DUKHCONI1AZ2SLGL7200, DUKHCONI1AZ1SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L20.15 ZONE- 2 |  | 217 | 217 | 0% | 2013-11-06 | 2014-07-19 | 2013-11-06 | 2014-07-19 | 92 |  |  |  | 0 | 0
DHBL.K30.L20.15 .10 INFRASTRUCTURE WORKS |  | 217 | 217 | 0% | 2013-11-06 | 2014-07-19 | 2013-11-06 | 2014-07-19 | 92 |  |  |  | 0 | 0
DHBL.K30.L20.15 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-11-06 | 2013-12-26 | 2013-11-06 | 2013-12-26 | 9 |  |  |  | 0 | 0
DUKHCONI1AZ2DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-12-09 | 2013-12-26 | 2013-12-09 | 2013-12-26 | 9 | No | DUKHCONI1AZ2DRGL5125, DUKHCONI1AZ2DRGL5125 | DUKHCONI1AZ3DRGL5115, DUKHCONI1AZ2WSGL5155, DUKHCONI1AZ2SAGL5135, DUKHCONI1AZ2SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ2DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-11-06 | 2013-12-04 | 2013-11-06 | 2013-12-04 | 9 | No | DUKHCONI1AZ1DRGL5130, DUKHCONP1AZ3STFF2030 | DUKHCONI1AZ2SAGL5140, DUKHCONI1AZ2SAGL5135, DUKHCONI1AZ2DRGL5120, DUKHCONI1AZ2DRGL5120 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ2DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-11-13 | 2013-12-11 | 2013-11-13 | 2013-12-11 | 9 | No | DUKHCONI1AZ2DRGL5115, DUKHCONI1AZ2DRGL5115 | DUKHCONI1AZ2DRGL5125, DUKHCONI1AZ2DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ2DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 9 | No | DUKHCONI1AZ2DRGL5120, DUKHCONI1AZ2DRGL5120 | DUKHCONI1AZ2DRGL5130, DUKHCONI1AZ2DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L20.15 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-12-07 | 2014-02-27 | 2013-12-07 | 2014-02-27 | 54 |  |  |  | 0 | 0
DUKHCONI1AZ2SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-02-04 | 2014-02-27 | 2014-02-04 | 2014-02-27 | 54 | No | DUKHCONI1AZ2SAGL5135, DUKHCONI1AZ2SAGL5145 | DUKHCONI1AZ2RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ2SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-12-09 | 2014-01-07 | 2013-12-09 | 2014-01-07 | 77 | No | DUKHCONI1AZ1SAGL5135, DUKHCONI1AZ2DRGL5130, DUKHCONI1AZ2DRGL5115 | DUKHCONI1AZ2SAGL5150, DUKHCONI1AZ3SAGL5135 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ2SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 14 | No | DUKHCONI1AZ1SAGL5145, DUKHCONI1AZ2SAGL5140 | DUKHCONI1AZ2WSGL5170, DUKHCONI1AZ2SAGL5150, DUKHCONI1AZ3SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ2SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-12-07 | 2014-01-05 | 2013-12-07 | 2014-01-05 | 14 | No | DUKHCONI1AZ2DRGL5115, DUKHCONI1AZ2DRGL5130 | DUKHCONI1AZ2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L20.15 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2013-12-22 | 2014-03-08 | 2013-12-22 | 2014-03-08 | 47 |  |  |  | 0 | 0
DUKHCONI1AZ2WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 12 | No | DUKHCONI1AZ2SAGL5145, DUKHCONI1AZ2WSGL5165 | DUKHCONI1AZ2WSGL5175, DUKHCONI1AZ3WSGL5155, DUKHCONI1AZ2FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 47 | No | DUKHCONI1AZ2WSGL5170, DUKHCONI1AZ1WSGL5175, DUKHCONI1AZ2WSGL5155 | DUKHCONI1AZ2WSGL5180, DUKHCONI1AZ3WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ2WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 12 | No | DUKHCONI1AZ1WSGL5170, DUKHCONI1AZ2DRGL5130 | DUKHCONI1AZ2WSGL5175, DUKHCONI1AZ2WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ2WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-02-13 | 2014-03-08 | 2014-02-13 | 2014-03-08 | 47 | No | DUKHCONI1AZ2WSGL5175, DUKHCONI1AZ1WSGL5180 | DUKHCONI1AZ3WSGL5180, DUKHCONI1AZ2FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ2WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 12 | No | DUKHCONI1AZ2WSGL5155 | DUKHCONI1AZ2WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ2WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 12 | No | DUKHCONI1AZ2WSGL5160 | DUKHCONI1AZ2WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L20.15 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-01-14 | 2014-03-16 | 2014-01-14 | 2014-03-16 | 40 |  |  |  | 0 | 0
DUKHCONI1AZ2FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 12 | No | DUKHCONI1AZ2FFGL5195 | DUKHCONI1AZ2RWGL6000, DUKHCONI1AZ3FFGL5185, DUKHCONI1AZ2FFGL5205, DUKHCONI1AZ2ELGL5215 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ2FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 40 | No | DUKHCONI1AZ1FFGL5210, DUKHCONI1AZ2FFGL5205, DUKHCONI1AZ2WSGL5180 | DUKHCONI1AZ4RWGL6000, DUKHCONI1AZ3FFGL5210, DUKHCONI1ASBIWGL7440, DUKHCONI1AZ2RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 40 | No | DUKHCONI1AZ2FFGL5200, DUKHCONI1AZ1FFGL5205, DUKHCONI1AZ2FFGL5185 | DUKHCONI1AZ3FFGL5205, DUKHCONI1AZ2FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ2FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 12 | No | DUKHCONI1AZ2WSGL5170, DUKHCONI1AZ1FFGL5200 | DUKHCONI1AZ2FFGL5190, DUKHCONI1AZ2FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ2FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 12 | No | DUKHCONI1AZ2FFGL5185 | DUKHCONI1AZ2FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ2FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 12 | No | DUKHCONI1AZ2FFGL5190 | DUKHCONI1AZ2FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L20.15 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-02-12 | 2014-04-07 | 2014-02-12 | 2014-04-07 | 95 |  |  |  | 0 | 0
DUKHCONI1AZ2ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 21 | No | DUKHCONI1AZ2ELGL5215, DUKHCONI1AZ2ELGL5220 | DUKHCONI1AZ2IRGL5285, DUKHCONI1AZ2RWGL6000, DUKHCONI1AZ2IRGL5265, DUKHCONI1AZ3ELGL5215, DUKHCONI1AZ2ELGL5230, DUKHCONI1AZ2ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 95 | No | DUKHCONI1AZ1ELGL5230, DUKHCONI1AZ2ELGL5225, DUKHCONI1AZ2ELGL5225 | DUKHCONI1AZ3ELGL5230, DUKHCONI1AZ2STGL5260 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 18 | No | DUKHCONI1AZ1ELGL5225, DUKHCONI1AZ2FFGL5200 | DUKHCONI1AZ2ELGL5220, DUKHCONI1AZ2ELGL5225, DUKHCONI1AZ2STGL5235 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ2ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 21 | No | DUKHCONI1AZ2ELGL5215 | DUKHCONI1AZ2ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L20.15 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-02-12 | 2014-05-06 | 2014-02-12 | 2014-05-06 | 95 |  |  |  | 0 | 0
DUKHCONI1AZ2STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 18 | No | DUKHCONI1AZ2STGL5245, DUKHCONI1AZ2STGL5235 | DUKHCONI1AZ2BWGL5315, DUKHCONI1AZ2TCGL5295, DUKHCONI1AZ2RWGL6000, DUKHCONI1AZ3STGL5235, DUKHCONI1AZ2STGL5255, DUKHCONI1AZ2STGL5255 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ2STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 18 | No | DUKHCONI1AZ2STGL5235 | DUKHCONI1AZ2STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ2STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 18 | No | DUKHCONI1AZ2STGL5240 | DUKHCONI1AZ2STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ2STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 95 | No | DUKHCONI1AZ1STGL5260, DUKHCONI1AZ2ELGL5230, DUKHCONI1AZ2STGL5255, DUKHCONI1AZ2STGL5255 | DUKHCONI1AZ3STGL5260, DUKHCONI1AZ2PSGL7015 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ2STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 18 | No | DUKHCONI1AZ1STGL5250, DUKHCONI1AZ2ELGL5215 | DUKHCONI1AZ2STGL5240, DUKHCONI1AZ2STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ2STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-03-12 | 2014-04-09 | 2014-03-12 | 2014-04-09 | 93 | No | DUKHCONI1AZ1STGL5255, DUKHCONI1AZ2STGL5250, DUKHCONI1AZ2STGL5250 | DUKHCONI1AZ3STGL5255, DUKHCONI1AZ2STGL5260, DUKHCONI1AZ2STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L20.15 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-03-27 | 2014-06-01 | 2014-03-27 | 2014-06-01 | 58 |  |  |  | 0 | 0
DUKHCONI1AZ2IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-04-14 | 2014-05-12 | 2014-04-14 | 2014-05-12 | 43 | No | DUKHCONI1AZ2IRGL5275 | DUKHCONI1AZ2IRGL5285, DUKHCONI1AZ2IRGL5290, DUKHCONI1AZ3IRGL5265 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 58 | No | DUKHCONI1AZ2ELGL5225, DUKHCONI1AZ2IRGL5280 | DUKHCONI1AZ2IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ2IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 43 | No | DUKHCONI1AZ2ELGL5225, DUKHCONI1AZ1IRGL5280 | DUKHCONI1AZ2IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 58 | No | DUKHCONI1AZ2IRGL5285, DUKHCONI1AZ2IRGL5280 | DUKHCONI1AZ2SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ2IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 43 | No | DUKHCONI1AZ2IRGL5265 | DUKHCONI1AZ2IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ2IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 43 | No | DUKHCONI1AZ2IRGL5270 | DUKHCONI1AZ2IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L20.15 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-03-08 | 2014-04-22 | 2014-03-08 | 2014-04-22 | 97 |  |  |  | 0 | 0
DUKHCONI1AZ2TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 18 | No | DUKHCONI1AZ2TCGL5300 | DUKHCONI1AZ3TCGL5295, DUKHCONI1AZ2RWGL6000, DUKHCONI1AZ2TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ2TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-03-31 | 2014-04-22 | 2014-03-31 | 2014-04-22 | 97 | No | DUKHCONI1AZ1TCGL5310, DUKHCONI1AZ2TCGL5305 | DUKHCONI1ASBTRGL7630, DUKHCONI1AZ3TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ2TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 18 | No | DUKHCONI1AZ1TCGL5305, DUKHCONI1AZ2STGL5250 | DUKHCONI1AZ2TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ2TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-03-13 | 2014-04-05 | 2014-03-13 | 2014-04-05 | 18 | No | DUKHCONI1AZ2TCGL5295 | DUKHCONI1AZ2TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L20.15 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-03-08 | 2014-06-01 | 2014-03-08 | 2014-06-01 | 74 |  |  |  | 0 | 0
DUKHCONI1AZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 74 | No | DUKHCONI1AZ1BWGL5330, DUKHCONI1AZ2BWGL5325 | DUKHCONI1AZ2PSGL7010, DUKHCONI1AZ3BWGL5330 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-04-22 | 2014-05-20 | 2014-04-22 | 2014-05-20 | 74 | No | DUKHCONI1AZ2BWGL5320, DUKHCONI1AZ2BWGL5315, DUKHCONI1AZ1BWGL5325 | DUKHCONP1AZ3MSEX5335, DUKHCONI1AZ2BWGL5330, DUKHCONI1AZ3BWGL5325, DUKHCONP1AZ4MSEX5335 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-03-08 | 2014-04-05 | 2014-03-08 | 2014-04-05 | 74 | No | DUKHCONI1AZ2STGL5250, DUKHCONI1AZ1BWGL5315 | DUKHCONI1AZ2BWGL5325, DUKHCONI1AZ2BWGL5320, DUKHCONI1AZ3BWGL5315 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-03-24 | 2014-04-21 | 2014-03-24 | 2014-04-21 | 74 | No | DUKHCONI1AZ2BWGL5315 | DUKHCONI1AZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L20.15 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-04-12 | 2014-06-25 | 2014-04-12 | 2014-06-25 | 78 |  |  |  | 0 | 0
DUKHCONI1AZ2RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-04-12 | 2014-04-22 | 2014-04-12 | 2014-04-22 | 18 | No | DUKHCONI1AZ1RWGL6015, DUKHCONI1AZ2ELGL5225, DUKHCONI1AZ2STGL5250, DUKHCONI1AZ2FFGL5200, DUKHCONI1AZ2TCGL5305, DUKHCONI1AZ2SAGL5150, DUKHCONI1AZ2FFGL5210 | DUKHCONI1AZ2HDGL7020, DUKHCONI1AZ2RWGL6005 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-06-15 | 2014-06-19 | 2014-06-15 | 2014-06-19 | 78 | No | DUKHCONI1AZ1RWGL6025, DUKHCONI1AZ2RWGL6020 | DUKHCONI1AZ2RWGL6030, DUKHCONI1AZ2HDGL7040, DUKHCONI1AZ3RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ2RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-05-17 | 2014-06-08 | 2014-05-17 | 2014-06-08 | 18 | No | DUKHCONI1AZ2RWGL6010 | DUKHCONI1AZ3RWGL6000, DUKHCONI1AZ2RWGL6020, DUKHCONI1AZ2PSGL7005, DUKHCONI1AZ2PSGL7000 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ2RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-05-05 | 2014-06-02 | 2014-05-05 | 2014-06-02 | 18 | No | DUKHCONI1AZ2RWGL6005 | DUKHCONI1AZ2RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-06-09 | 2014-06-14 | 2014-06-09 | 2014-06-14 | 63 | No | DUKHCONI1AZ2RWGL6015 | DUKHCONI1AZ2PSGL7010, DUKHCONI1AZ2RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ2RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 18 | No | DUKHCONI1AZ2RWGL6000 | DUKHCONI1AZ2RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ2RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-06-21 | 2014-06-25 | 2014-06-21 | 2014-06-25 | 78 | No | DUKHCONI1AZ2RWGL6025, DUKHCONI1AZ1RWGL6030 | DUKHCONI1AZ3RWGL6030, DUKHCONI1AZ2PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L20.15 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-05-22 | 2014-07-19 | 2014-05-22 | 2014-07-19 | 63 |  |  |  | 0 | 0
DUKHCONI1AZ2PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 63 | No | DUKHCONI1AZ2BWGL5330, DUKHCONI1AZ2PSGL7005, DUKHCONI1AZ2RWGL6020, DUKHCONI1AZ2RWGL6030, DUKHCONI1AZ1PSGL7010 | DUKHCONI1AZ2PSGL7015, DUKHCONI1AZ3PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI1AZ2PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-06-21 | 2014-07-19 | 2014-06-21 | 2014-07-19 | 63 | No | DUKHCONI1AZ2PSGL7010, DUKHCONI1AZ2STGL5260, DUKHCONI1AZ1PSGL7015 | DUKHCONI1AZ3PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1AZ2PSGL7000 | Excavation | 15 | 15 | 0% | 2014-05-22 | 2014-06-08 | 2014-05-22 | 2014-06-08 | 68 | No | DUKHCONI1AZ1PSGL7005, DUKHCONI1AZ2RWGL6015 | DUKHCONI1AZ2PSGL7005, DUKHCONI1AZ2PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1AZ2PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-06-03 | 2014-06-19 | 2014-06-03 | 2014-06-19 | 63 | No | DUKHCONI1AZ2PSGL7000, DUKHCONI1AZ2PSGL7000, DUKHCONI1AZ2RWGL6015 | DUKHCONI1AZ3PSGL7000, DUKHCONI1AZ2PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L20.15 .10 .65 HARD LANDSCAPING |  | 80 | 80 | 0% | 2014-04-12 | 2014-07-13 | 2014-04-12 | 2014-07-13 | 97 |  |  |  | 0 | 0
DUKHCONI1AZ2HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-05-05 | 2014-06-02 | 2014-05-05 | 2014-06-02 | 47 | No | DUKHCONI1AZ1HDGL7030, DUKHCONI1AZ2HDGL7025 | DUKHCONI1AZ3HDGL7030, DUKHCONI1AZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ2HDGL7040 | Construction of Speed Humps | 20 | 20 | 0% | 2014-06-21 | 2014-07-13 | 2014-06-21 | 2014-07-13 | 97 | No | DUKHCONI1AZ1HDGL7040, DUKHCONI1AZ2RWGL6025, DUKHCONI1AZ2HDGL7035 | DUKHCONI1AZ3HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ2HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-05-05 | 2014-06-02 | 2014-05-05 | 2014-06-02 | 47 | No | DUKHCONI1AZ2HDGL7030, DUKHCONI1AZ1HDGL7035 | DUKHCONI1AZ3HDGL7035, DUKHCONI1AZ2SLGL7200, DUKHCONI1AZ2HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ2HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 47 | No | DUKHCONI1AZ2HDGL7020 | DUKHCONI1AZ2HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ2HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-04-12 | 2014-05-04 | 2014-04-12 | 2014-05-04 | 47 | No | DUKHCONI1AZ2RWGL6000 | DUKHCONI1AZ2HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L20.15 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-05-17 | 2014-07-07 | 2014-05-17 | 2014-07-07 | 77 |  |  |  | 0 | 0
DUKHCONI1AZ2SLGL7200 | Excavation | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 47 | No | DUKHCONI1AZ1SLGL7205, DUKHCONI1AZ2IRGL5290, DUKHCONI1AZ2HDGL7035 | DUKHCONI1AZ2SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ2SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 77 | No | DUKHCONI1AZ1SLGL7210, DUKHCONI1AZ2SLGL7205 | DUKHCONI1AZ3SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ2SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 47 | No | DUKHCONI1AZ2SLGL7200 | DUKHCONI1AZ3SLGL7200, DUKHCONI1AZ2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L20.20 ZONE - 3 |  | 217 | 217 | 0% | 2013-12-28 | 2014-09-10 | 2013-12-28 | 2014-09-10 | 59 |  |  |  | 0 | 0
DHBL.K30.L20.20 .10 INFRASTRUCTURE WORKS |  | 217 | 217 | 0% | 2013-12-28 | 2014-09-10 | 2013-12-28 | 2014-09-10 | 59 |  |  |  | 0 | 0
DHBL.K30.L20.20 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-12-28 | 2014-02-16 | 2013-12-28 | 2014-02-16 | 9 |  |  |  | 0 | 0
DUKHCONI1AZ3DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2014-01-29 | 2014-02-16 | 2014-01-29 | 2014-02-16 | 9 | No | DUKHCONI1AZ3DRGL5125, DUKHCONI1AZ3DRGL5125 | DUKHCONI1AZ3WSGL5155, DUKHCONI1AZ4DRGL5115, DUKHCONI1AZ3SAGL5140, DUKHCONI1AZ3SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ3DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 9 | No | DUKHCONI1AZ2DRGL5130, DUKHCONP1AZ5STFF2025 | DUKHCONI1AZ3DRGL5120, DUKHCONI1AZ3SAGL5140, DUKHCONI1AZ3DRGL5120, DUKHCONI1AZ3SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ3DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2014-01-04 | 2014-02-01 | 2014-01-04 | 2014-02-01 | 9 | No | DUKHCONI1AZ3DRGL5115, DUKHCONI1AZ3DRGL5115 | DUKHCONI1AZ3DRGL5125, DUKHCONI1AZ3DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ3DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2014-01-12 | 2014-02-09 | 2014-01-12 | 2014-02-09 | 9 | No | DUKHCONI1AZ3DRGL5120, DUKHCONI1AZ3DRGL5120 | DUKHCONI1AZ3DRGL5130, DUKHCONI1AZ3DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L20.20 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2014-01-27 | 2014-04-19 | 2014-01-27 | 2014-04-19 | 51 |  |  |  | 0 | 0
DUKHCONI1AZ3SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-03-27 | 2014-04-19 | 2014-03-27 | 2014-04-19 | 51 | No | DUKHCONI1AZ3SAGL5135, DUKHCONI1AZ3SAGL5145 | DUKHCONI1AZ3RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ3SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 74 | No | DUKHCONI1AZ3DRGL5115, DUKHCONI1AZ2SAGL5135, DUKHCONI1AZ3DRGL5130 | DUKHCONI1AZ4SAGL5135, DUKHCONI1AZ3SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ3SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 13 | No | DUKHCONI1AZ3SAGL5140, DUKHCONI1AZ2SAGL5145 | DUKHCONI1AZ3WSGL5170, DUKHCONI1AZ3SAGL5150, DUKHCONI1AZ4SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ3SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 13 | No | DUKHCONI1AZ3DRGL5115, DUKHCONI1AZ3DRGL5130 | DUKHCONI1AZ3SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L20.20 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-02-10 | 2014-04-27 | 2014-02-10 | 2014-04-27 | 44 |  |  |  | 0 | 0
DUKHCONI1AZ3WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-03-01 | 2014-03-29 | 2014-03-01 | 2014-03-29 | 11 | No | DUKHCONI1AZ3SAGL5145, DUKHCONI1AZ3WSGL5165 | DUKHCONI1AZ3FFGL5185, DUKHCONI1AZ4WSGL5155, DUKHCONI1AZ3WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ3WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 44 | No | DUKHCONI1AZ3WSGL5155, DUKHCONI1AZ3WSGL5170, DUKHCONI1AZ2WSGL5175 | DUKHCONI1AZ3WSGL5180, DUKHCONI1AZ4WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ3WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-02-10 | 2014-03-11 | 2014-02-10 | 2014-03-11 | 11 | No | DUKHCONI1AZ3DRGL5130, DUKHCONI1AZ2WSGL5170 | DUKHCONI1AZ3WSGL5175, DUKHCONI1AZ3WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ3WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-04-05 | 2014-04-27 | 2014-04-05 | 2014-04-27 | 44 | No | DUKHCONI1AZ2WSGL5180, DUKHCONI1AZ3WSGL5175 | DUKHCONI1AZ3FFGL5210, DUKHCONI1AZ4WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ3WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 11 | No | DUKHCONI1AZ3WSGL5155 | DUKHCONI1AZ3WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ3WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-02-23 | 2014-03-23 | 2014-02-23 | 2014-03-23 | 11 | No | DUKHCONI1AZ3WSGL5160 | DUKHCONI1AZ3WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L20.20 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-03-06 | 2014-05-05 | 2014-03-06 | 2014-05-05 | 37 |  |  |  | 0 | 0
DUKHCONI1AZ3FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 11 | No | DUKHCONI1AZ3FFGL5195 | DUKHCONI1AZ3ELGL5215, DUKHCONI1AZ4FFGL5185, DUKHCONI1AZ3RWGL6000, DUKHCONI1AZ3FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ3FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 37 | No | DUKHCONI1AZ2FFGL5210, DUKHCONI1AZ3FFGL5205, DUKHCONI1AZ3WSGL5180 | DUKHCONI1ASBIWGL7440, DUKHCONI1AZ4FFGL5210, DUKHCONI1AZ3RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ3FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 37 | No | DUKHCONI1AZ3FFGL5185, DUKHCONI1AZ2FFGL5205, DUKHCONI1AZ3FFGL5200 | DUKHCONI1AZ3FFGL5210, DUKHCONI1AZ4FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ3FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 11 | No | DUKHCONI1AZ3WSGL5170, DUKHCONI1AZ2FFGL5200 | DUKHCONI1AZ3FFGL5205, DUKHCONI1AZ3FFGL5190 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ3FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 11 | No | DUKHCONI1AZ3FFGL5185 | DUKHCONI1AZ3FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ3FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-03-20 | 2014-04-17 | 2014-03-20 | 2014-04-17 | 11 | No | DUKHCONI1AZ3FFGL5190 | DUKHCONI1AZ3FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L20.20 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-04-03 | 2014-05-27 | 2014-04-03 | 2014-05-27 | 77 |  |  |  | 0 | 0
DUKHCONI1AZ3ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 18 | No | DUKHCONI1AZ3ELGL5215, DUKHCONI1AZ3ELGL5220 | DUKHCONI1AZ3RWGL6000, DUKHCONI1AZ3IRGL5265, DUKHCONI1AZ4ELGL5215, DUKHCONI1AZ3IRGL5285, DUKHCONI1AZ3ELGL5230, DUKHCONI1AZ3ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ3ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-04-29 | 2014-05-27 | 2014-04-29 | 2014-05-27 | 77 | No | DUKHCONI1AZ2ELGL5230, DUKHCONI1AZ3ELGL5225, DUKHCONI1AZ3ELGL5225 | DUKHCONI1AZ3STGL5260, DUKHCONI1AZ4ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ3ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 15 | No | DUKHCONI1AZ3FFGL5200, DUKHCONI1AZ2ELGL5225 | DUKHCONI1AZ3STGL5235, DUKHCONI1AZ3ELGL5220, DUKHCONI1AZ3ELGL5225 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ3ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-04-09 | 2014-05-07 | 2014-04-09 | 2014-05-07 | 18 | No | DUKHCONI1AZ3ELGL5215 | DUKHCONI1AZ3ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L20.20 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-04-03 | 2014-06-25 | 2014-04-03 | 2014-06-25 | 77 |  |  |  | 0 | 0
DUKHCONI1AZ3STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 15 | No | DUKHCONI1AZ3STGL5235, DUKHCONI1AZ3STGL5245 | DUKHCONI1AZ4STGL5235, DUKHCONI1AZ3BWGL5315, DUKHCONI1AZ3STGL5255, DUKHCONI1AZ3RWGL6000, DUKHCONI1AZ3TCGL5295 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ3STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-04-09 | 2014-05-07 | 2014-04-09 | 2014-05-07 | 15 | No | DUKHCONI1AZ3STGL5235 | DUKHCONI1AZ3STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ3STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-04-09 | 2014-05-07 | 2014-04-09 | 2014-05-07 | 15 | No | DUKHCONI1AZ3STGL5240 | DUKHCONI1AZ3STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ3STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 77 | No | DUKHCONI1AZ3ELGL5230, DUKHCONI1AZ2STGL5260, DUKHCONI1AZ3STGL5255 | DUKHCONI1AZ4STGL5260, DUKHCONI1AZ3PSGL7015 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ3STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 15 | No | DUKHCONI1AZ3ELGL5215, DUKHCONI1AZ2STGL5250 | DUKHCONI1AZ3STGL5250, DUKHCONI1AZ3STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ3STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 79 | No | DUKHCONI1AZ2STGL5255, DUKHCONI1AZ3STGL5250 | DUKHCONI1AZ4STGL5255, DUKHCONI1AZ3STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L20.20 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-05-17 | 2014-07-21 | 2014-05-17 | 2014-07-21 | 50 |  |  |  | 0 | 0
DUKHCONI1AZ3IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-06-03 | 2014-07-01 | 2014-06-03 | 2014-07-01 | 40 | No | DUKHCONI1AZ3IRGL5275 | DUKHCONI1AZ3IRGL5290, DUKHCONI1AZ3IRGL5285, DUKHCONI1AZ4IRGL5265 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ3IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 50 | No | DUKHCONI1AZ3ELGL5225, DUKHCONI1AZ3IRGL5280 | DUKHCONI1AZ3IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ3IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 40 | No | DUKHCONI1AZ3ELGL5225, DUKHCONI1AZ2IRGL5280 | DUKHCONI1AZ3IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ3IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 50 | No | DUKHCONI1AZ3IRGL5280, DUKHCONI1AZ3IRGL5285 | DUKHCONI1AZ3SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ3IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 40 | No | DUKHCONI1AZ3IRGL5265 | DUKHCONI1AZ3IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ3IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 40 | No | DUKHCONI1AZ3IRGL5270 | DUKHCONI1AZ3IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L20.20 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-04-27 | 2014-06-11 | 2014-04-27 | 2014-06-11 | 74 |  |  |  | 0 | 0
DUKHCONI1AZ3TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-05-08 | 2014-05-31 | 2014-05-08 | 2014-05-31 | 15 | No | DUKHCONI1AZ3TCGL5300 | DUKHCONI1AZ3TCGL5310, DUKHCONI1AZ3RWGL6000, DUKHCONI1AZ4TCGL5295 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ3TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-05-20 | 2014-06-11 | 2014-05-20 | 2014-06-11 | 74 | No | DUKHCONI1AZ3TCGL5305, DUKHCONI1AZ2TCGL5310 | DUKHCONI1ASBTRGL7630, DUKHCONI1AZ4TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ3TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-04-27 | 2014-05-19 | 2014-04-27 | 2014-05-19 | 15 | No | DUKHCONI1AZ2TCGL5305, DUKHCONI1AZ3STGL5250 | DUKHCONI1AZ3TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ3TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-05-03 | 2014-05-25 | 2014-05-03 | 2014-05-25 | 15 | No | DUKHCONI1AZ3TCGL5295 | DUKHCONI1AZ3TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L20.20 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-04-27 | 2014-07-21 | 2014-04-27 | 2014-07-21 | 81 |  |  |  | 0 | 0
DUKHCONI1AZ3BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 81 | No | DUKHCONI1AZ2BWGL5330, DUKHCONI1AZ3BWGL5325 | DUKHCONI1AZ4BWGL5330, DUKHCONI1AZ3PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ3BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-06-11 | 2014-07-09 | 2014-06-11 | 2014-07-09 | 70 | No | DUKHCONI1AZ3BWGL5315, DUKHCONI1AZ2BWGL5325, DUKHCONI1AZ3BWGL5320 | DUKHCONP1AZ6MSEX5335, DUKHCONP1AZ5MSEX5335, DUKHCONI1AZ3BWGL5330, DUKHCONI1AZ4BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ3BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 70 | No | DUKHCONI1AZ3STGL5250, DUKHCONI1AZ2BWGL5315 | DUKHCONI1AZ3BWGL5320, DUKHCONI1AZ3BWGL5325, DUKHCONI1AZ4BWGL5315 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ3BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-05-13 | 2014-06-10 | 2014-05-13 | 2014-06-10 | 70 | No | DUKHCONI1AZ3BWGL5315 | DUKHCONI1AZ3BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L20.20 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-06-01 | 2014-08-18 | 2014-06-01 | 2014-08-18 | 60 |  |  |  | 0 | 0
DUKHCONI1AZ3RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-06-01 | 2014-06-11 | 2014-06-01 | 2014-06-11 | 15 | No | DUKHCONI1AZ2RWGL6015, DUKHCONI1AZ3ELGL5225, DUKHCONI1AZ3FFGL5200, DUKHCONI1AZ3TCGL5305, DUKHCONI1AZ3SAGL5150, DUKHCONI1AZ3STGL5250, DUKHCONI1AZ3FFGL5210 | DUKHCONI1AZ3RWGL6005, DUKHCONI1AZ3HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ3RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-08-07 | 2014-08-12 | 2014-08-07 | 2014-08-12 | 60 | No | DUKHCONI1AZ2RWGL6025, DUKHCONI1AZ3RWGL6020 | DUKHCONI1AZ3HDGL7040, DUKHCONI1AZ4RWGL6025, DUKHCONI1AZ3RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ3RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-07-06 | 2014-07-28 | 2014-07-06 | 2014-07-28 | 15 | No | DUKHCONI1AZ3RWGL6010 | DUKHCONI1AZ3RWGL6020, DUKHCONI1AZ3PSGL7005, DUKHCONI1AZ4RWGL6000, DUKHCONI1AZ3PSGL7000 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ3RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-06-24 | 2014-07-22 | 2014-06-24 | 2014-07-22 | 15 | No | DUKHCONI1AZ3RWGL6005 | DUKHCONI1AZ3RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ3RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-07-29 | 2014-08-06 | 2014-07-29 | 2014-08-06 | 45 | No | DUKHCONI1AZ3RWGL6015 | DUKHCONI1AZ3PSGL7010, DUKHCONI1AZ3RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ3RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 15 | No | DUKHCONI1AZ3RWGL6000 | DUKHCONI1AZ3RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ3RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-08-13 | 2014-08-18 | 2014-08-13 | 2014-08-18 | 60 | No | DUKHCONI1AZ2RWGL6030, DUKHCONI1AZ3RWGL6025 | DUKHCONI1AZ4RWGL6030, DUKHCONI1AZ3PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L20.20 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-07-12 | 2014-09-10 | 2014-07-12 | 2014-09-10 | 45 |  |  |  | 0 | 0
DUKHCONI1AZ3PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-08-07 | 2014-09-04 | 2014-08-07 | 2014-09-04 | 45 | No | DUKHCONI1AZ3RWGL6020, DUKHCONI1AZ3PSGL7005, DUKHCONI1AZ3BWGL5330, DUKHCONI1AZ3RWGL6030, DUKHCONI1AZ2PSGL7010 | DUKHCONI1AZ3PSGL7015, DUKHCONI1AZ4PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI1AZ3PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-08-13 | 2014-09-10 | 2014-08-13 | 2014-09-10 | 45 | No | DUKHCONI1AZ3PSGL7010, DUKHCONI1AZ2PSGL7015, DUKHCONI1AZ3STGL5260 | DUKHCONI1AZ4PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1AZ3PSGL7000 | Excavation | 15 | 15 | 0% | 2014-07-12 | 2014-07-28 | 2014-07-12 | 2014-07-28 | 50 | No | DUKHCONI1AZ2PSGL7005, DUKHCONI1AZ3RWGL6015 | DUKHCONI1AZ3PSGL7005, DUKHCONI1AZ3PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1AZ3PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-07-23 | 2014-08-12 | 2014-07-23 | 2014-08-12 | 45 | No | DUKHCONI1AZ3PSGL7000, DUKHCONI1AZ3RWGL6015, DUKHCONI1AZ3PSGL7000 | DUKHCONI1AZ3PSGL7010, DUKHCONI1AZ4PSGL7000 | 0 | 0 | PARKING SHED
DHBL.K30.L20.20 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-06-01 | 2014-08-24 | 2014-06-01 | 2014-08-24 | 74 |  |  |  | 0 | 0
DUKHCONI1AZ3HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-06-24 | 2014-07-22 | 2014-06-24 | 2014-07-22 | 39 | No | DUKHCONI1AZ2HDGL7030, DUKHCONI1AZ3HDGL7025 | DUKHCONI1AZ3HDGL7035, DUKHCONI1AZ4HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ3HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-08-13 | 2014-08-24 | 2014-08-13 | 2014-08-24 | 74 | No | DUKHCONI1AZ3HDGL7035, DUKHCONI1AZ2HDGL7040, DUKHCONI1AZ3RWGL6025 | DUKHCONI1AZ4HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ3HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-06-24 | 2014-07-22 | 2014-06-24 | 2014-07-22 | 39 | No | DUKHCONI1AZ3HDGL7030, DUKHCONI1AZ2HDGL7035 | DUKHCONI1AZ3HDGL7040, DUKHCONI1AZ3SLGL7200, DUKHCONI1AZ4HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ3HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 39 | No | DUKHCONI1AZ3HDGL7020 | DUKHCONI1AZ3HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ3HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-06-01 | 2014-06-23 | 2014-06-01 | 2014-06-23 | 39 | No | DUKHCONI1AZ3RWGL6000 | DUKHCONI1AZ3HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L20.20 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-07-06 | 2014-08-30 | 2014-07-06 | 2014-08-30 | 59 |  |  |  | 0 | 0
DUKHCONI1AZ3SLGL7200 | Excavation | 25 | 25 | 0% | 2014-07-06 | 2014-08-06 | 2014-07-06 | 2014-08-06 | 39 | No | DUKHCONI1AZ3HDGL7035, DUKHCONI1AZ3IRGL5290, DUKHCONI1AZ2SLGL7205 | DUKHCONI1AZ3SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ3SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-07-29 | 2014-08-30 | 2014-07-29 | 2014-08-30 | 59 | No | DUKHCONI1AZ2SLGL7210, DUKHCONI1AZ3SLGL7205 | DUKHCONI1AZ4SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ3SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-07-17 | 2014-08-18 | 2014-07-17 | 2014-08-18 | 39 | No | DUKHCONI1AZ3SLGL7200 | DUKHCONI1AZ3SLGL7210, DUKHCONI1AZ4SLGL7200 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L20.25 ZONE - 4 |  | 217 | 217 | 0% | 2014-02-17 | 2014-11-02 | 2014-02-17 | 2014-11-02 | 31 |  |  |  | 0 | 0
DHBL.K30.L20.25 .10 INFRASTRUCTURE WORKS |  | 217 | 217 | 0% | 2014-02-17 | 2014-11-02 | 2014-02-17 | 2014-11-02 | 31 |  |  |  | 0 | 0
DHBL.K30.L20.25 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2014-02-17 | 2014-04-07 | 2014-02-17 | 2014-04-07 | 9 |  |  |  | 0 | 0
DUKHCONI1AZ4DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2014-03-22 | 2014-04-07 | 2014-03-22 | 2014-04-07 | 9 | No | DUKHCONI1AZ4DRGL5125, DUKHCONI1AZ4DRGL5125 | DUKHCONI1AZ4WSGL5155, DUKHCONI1AZ4SAGL5135, DUKHCONI1AZ5DRGL5115, DUKHCONI1AZ4SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ4DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 9 | No | DUKHCONP1AZ1STGF2005, DUKHCONI1AZ3DRGL5130 | DUKHCONI1AZ4DRGL5120, DUKHCONI1AZ4DRGL5120, DUKHCONI1AZ4SAGL5135, DUKHCONI1AZ4SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ4DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 9 | No | DUKHCONI1AZ4DRGL5115, DUKHCONI1AZ4DRGL5115 | DUKHCONI1AZ4DRGL5125, DUKHCONI1AZ4DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ4DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 9 | No | DUKHCONI1AZ4DRGL5120, DUKHCONI1AZ4DRGL5120 | DUKHCONI1AZ4DRGL5130, DUKHCONI1AZ4DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L20.25 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2014-03-19 | 2014-06-08 | 2014-03-19 | 2014-06-08 | 48 |  |  |  | 0 | 0
DUKHCONI1AZ4SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-05-17 | 2014-06-08 | 2014-05-17 | 2014-06-08 | 48 | No | DUKHCONI1AZ4SAGL5145, DUKHCONI1AZ4SAGL5135 | DUKHCONI1AZ4RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ4SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 71 | No | DUKHCONI1AZ4DRGL5130, DUKHCONI1AZ3SAGL5135, DUKHCONI1AZ4DRGL5115 | DUKHCONI1AZ5SAGL5135, DUKHCONI1AZ4SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ4SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 12 | No | DUKHCONI1AZ4SAGL5140, DUKHCONI1AZ3SAGL5145 | DUKHCONI1AZ4SAGL5150, DUKHCONI1AZ5SAGL5145, DUKHCONI1AZ4WSGL5170 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ4SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 12 | No | DUKHCONI1AZ4DRGL5115, DUKHCONI1AZ4DRGL5130 | DUKHCONI1AZ4SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L20.25 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-04-02 | 2014-06-16 | 2014-04-02 | 2014-06-16 | 41 |  |  |  | 0 | 0
DUKHCONI1AZ4WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 10 | No | DUKHCONI1AZ4WSGL5165, DUKHCONI1AZ4SAGL5145 | DUKHCONI1AZ5WSGL5155, DUKHCONI1AZ4FFGL5185, DUKHCONI1AZ4WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ4WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 41 | No | DUKHCONI1AZ4WSGL5170, DUKHCONI1AZ3WSGL5175, DUKHCONI1AZ4WSGL5155 | DUKHCONI1AZ5WSGL5175, DUKHCONI1AZ4WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ4WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 10 | No | DUKHCONI1AZ4DRGL5130, DUKHCONI1AZ3WSGL5170 | DUKHCONI1AZ4WSGL5175, DUKHCONI1AZ4WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ4WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-05-25 | 2014-06-16 | 2014-05-25 | 2014-06-16 | 41 | No | DUKHCONI1AZ4WSGL5175, DUKHCONI1AZ3WSGL5180 | DUKHCONI1AZ5WSGL5180, DUKHCONI1AZ4FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ4WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 10 | No | DUKHCONI1AZ4WSGL5155 | DUKHCONI1AZ4WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ4WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-04-14 | 2014-05-12 | 2014-04-14 | 2014-05-12 | 10 | No | DUKHCONI1AZ4WSGL5160 | DUKHCONI1AZ4WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L20.25 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-04-26 | 2014-06-24 | 2014-04-26 | 2014-06-24 | 34 |  |  |  | 0 | 0
DUKHCONI1AZ4FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 10 | No | DUKHCONI1AZ4FFGL5195 | DUKHCONI1AZ4FFGL5205, DUKHCONI1AZ4RWGL6000, DUKHCONI1AZ4ELGL5215, DUKHCONI1AZ5FFGL5185 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ4FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-05-27 | 2014-06-24 | 2014-05-27 | 2014-06-24 | 34 | No | DUKHCONI1AZ3FFGL5210, DUKHCONI1AZ4FFGL5205, DUKHCONI1AZ4WSGL5180 | DUKHCONI1ASBIWGL7440, DUKHCONI1AZ5FFGL5210, DUKHCONI1AZ4RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ4FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-05-21 | 2014-06-18 | 2014-05-21 | 2014-06-18 | 34 | No | DUKHCONI1AZ4FFGL5200, DUKHCONI1AZ4FFGL5185, DUKHCONI1AZ3FFGL5205 | DUKHCONI1AZ5FFGL5205, DUKHCONI1AZ4FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ4FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 10 | No | DUKHCONI1AZ4WSGL5170, DUKHCONI1AZ3FFGL5200 | DUKHCONI1AZ4FFGL5190, DUKHCONI1AZ4FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ4FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 10 | No | DUKHCONI1AZ4FFGL5185 | DUKHCONI1AZ4FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ4FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-05-10 | 2014-06-07 | 2014-05-10 | 2014-06-07 | 10 | No | DUKHCONI1AZ4FFGL5190 | DUKHCONI1AZ4FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L20.25 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-05-24 | 2014-07-16 | 2014-05-24 | 2014-07-16 | 59 |  |  |  | 0 | 0
DUKHCONI1AZ4ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-06-07 | 2014-07-05 | 2014-06-07 | 2014-07-05 | 15 | No | DUKHCONI1AZ4ELGL5215, DUKHCONI1AZ4ELGL5220 | DUKHCONI1AZ5ELGL5215, DUKHCONI1AZ4IRGL5285, DUKHCONI1AZ4ELGL5230, DUKHCONI1AZ4RWGL6000, DUKHCONI1AZ4IRGL5265, DUKHCONI1AZ4ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ4ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-06-18 | 2014-07-16 | 2014-06-18 | 2014-07-16 | 59 | No | DUKHCONI1AZ4ELGL5225, DUKHCONI1AZ3ELGL5230, DUKHCONI1AZ4ELGL5225 | DUKHCONI1AZ4STGL5260, DUKHCONI1AZ5ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ4ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 12 | No | DUKHCONI1AZ4FFGL5200, DUKHCONI1AZ3ELGL5225 | DUKHCONI1AZ4STGL5235, DUKHCONI1AZ4ELGL5225, DUKHCONI1AZ4ELGL5220 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ4ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 15 | No | DUKHCONI1AZ4ELGL5215 | DUKHCONI1AZ4ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L20.25 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-05-24 | 2014-08-18 | 2014-05-24 | 2014-08-18 | 59 |  |  |  | 0 | 0
DUKHCONI1AZ4STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-06-04 | 2014-07-02 | 2014-06-04 | 2014-07-02 | 12 | No | DUKHCONI1AZ4STGL5235, DUKHCONI1AZ4STGL5245 | DUKHCONI1AZ4STGL5255, DUKHCONI1AZ5STGL5235, DUKHCONI1AZ4TCGL5295, DUKHCONI1AZ4BWGL5315, DUKHCONI1AZ4RWGL6000 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ4STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 12 | No | DUKHCONI1AZ4STGL5235 | DUKHCONI1AZ4STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ4STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 12 | No | DUKHCONI1AZ4STGL5240 | DUKHCONI1AZ4STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ4STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-07-17 | 2014-08-18 | 2014-07-17 | 2014-08-18 | 59 | No | DUKHCONI1AZ4STGL5255, DUKHCONI1AZ4ELGL5230, DUKHCONI1AZ3STGL5260 | DUKHCONI1AZ5STGL5260, DUKHCONI1AZ4PSGL7015 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ4STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 12 | No | DUKHCONI1AZ3STGL5250, DUKHCONI1AZ4ELGL5215 | DUKHCONI1AZ4STGL5240, DUKHCONI1AZ4STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ4STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 76 | No | DUKHCONI1AZ4STGL5250, DUKHCONI1AZ3STGL5255 | DUKHCONI1AZ4STGL5260, DUKHCONI1AZ5STGL5255 | 0 | 0 | STREET LIGHTING
DHBL.K30.L20.25 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-07-06 | 2014-09-13 | 2014-07-06 | 2014-09-13 | 42 |  |  |  | 0 | 0
DUKHCONI1AZ4IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-07-23 | 2014-08-24 | 2014-07-23 | 2014-08-24 | 37 | No | DUKHCONI1AZ4IRGL5275 | DUKHCONI1AZ4IRGL5285, DUKHCONI1AZ4IRGL5290, DUKHCONI1AZ5IRGL5265 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ4IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-08-07 | 2014-09-04 | 2014-08-07 | 2014-09-04 | 42 | No | DUKHCONI1AZ4IRGL5280, DUKHCONI1AZ4ELGL5225 | DUKHCONI1AZ4IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ4IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-07-06 | 2014-08-06 | 2014-07-06 | 2014-08-06 | 37 | No | DUKHCONI1AZ4ELGL5225, DUKHCONI1AZ3IRGL5280 | DUKHCONI1AZ4IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ4IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-08-16 | 2014-09-13 | 2014-08-16 | 2014-09-13 | 42 | No | DUKHCONI1AZ4IRGL5285, DUKHCONI1AZ4IRGL5280 | DUKHCONI1AZ4SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ4IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-07-12 | 2014-08-12 | 2014-07-12 | 2014-08-12 | 37 | No | DUKHCONI1AZ4IRGL5265 | DUKHCONI1AZ4IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ4IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-07-17 | 2014-08-18 | 2014-07-17 | 2014-08-18 | 37 | No | DUKHCONI1AZ4IRGL5270 | DUKHCONI1AZ4IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L20.25 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-06-16 | 2014-07-31 | 2014-06-16 | 2014-07-31 | 51 |  |  |  | 0 | 0
DUKHCONI1AZ4TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-06-28 | 2014-07-20 | 2014-06-28 | 2014-07-20 | 12 | No | DUKHCONI1AZ4TCGL5300 | DUKHCONI1AZ4RWGL6000, DUKHCONI1AZ4TCGL5310, DUKHCONI1AZ5TCGL5295 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ4TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-07-09 | 2014-07-31 | 2014-07-09 | 2014-07-31 | 51 | No | DUKHCONI1AZ3TCGL5310, DUKHCONI1AZ4TCGL5305 | DUKHCONI1AZ5TCGL5310, DUKHCONI1ASBTRGL7630 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ4TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-06-16 | 2014-07-08 | 2014-06-16 | 2014-07-08 | 12 | No | DUKHCONI1AZ4STGL5250, DUKHCONI1AZ3TCGL5305 | DUKHCONI1AZ4TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ4TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-06-22 | 2014-07-14 | 2014-06-22 | 2014-07-14 | 12 | No | DUKHCONI1AZ4TCGL5295 | DUKHCONI1AZ4TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L20.25 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-06-16 | 2014-09-13 | 2014-06-16 | 2014-09-13 | 63 |  |  |  | 0 | 0
DUKHCONI1AZ4BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-08-16 | 2014-09-13 | 2014-08-16 | 2014-09-13 | 63 | No | DUKHCONI1AZ3BWGL5330, DUKHCONI1AZ4BWGL5325 | DUKHCONI1AZ4PSGL7010, DUKHCONI1AZ5BWGL5330 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ4BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-07-31 | 2014-09-01 | 2014-07-31 | 2014-09-01 | 52 | No | DUKHCONI1AZ4BWGL5320, DUKHCONI1AZ4BWGL5315, DUKHCONI1AZ3BWGL5325 | DUKHCONP1AZ7MSEX5335, DUKHCONP1AZ8MSEX5335, DUKHCONI1AZ4BWGL5330, DUKHCONI1AZ5BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ4BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 52 | No | DUKHCONI1AZ3BWGL5315, DUKHCONI1AZ4STGL5250 | DUKHCONI1AZ5BWGL5315, DUKHCONI1AZ4BWGL5325, DUKHCONI1AZ4BWGL5320 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ4BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-07-02 | 2014-07-30 | 2014-07-02 | 2014-07-30 | 52 | No | DUKHCONI1AZ4BWGL5315 | DUKHCONI1AZ4BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L20.25 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-07-21 | 2014-10-07 | 2014-07-21 | 2014-10-07 | 42 |  |  |  | 0 | 0
DUKHCONI1AZ4RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-07-21 | 2014-07-31 | 2014-07-21 | 2014-07-31 | 12 | No | DUKHCONI1AZ4SAGL5150, DUKHCONI1AZ2FFGL5210, DUKHCONI1AZ4FFGL5200, DUKHCONI1AZ3RWGL6015, DUKHCONI1AZ4ELGL5225, DUKHCONI1AZ4TCGL5305, DUKHCONI1AZ4FFGL5210, DUKHCONI1AZ4STGL5250 | DUKHCONI1AZ4RWGL6005, DUKHCONI1AZ4HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ4RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-09-27 | 2014-10-01 | 2014-09-27 | 2014-10-01 | 41 | No | DUKHCONI1AZ4RWGL6020, DUKHCONI1AZ3RWGL6025 | DUKHCONI1AZ4HDGL7040, DUKHCONI1AZ5RWGL6025, DUKHCONI1AZ4RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ4RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-08-28 | 2014-09-20 | 2014-08-28 | 2014-09-20 | 12 | No | DUKHCONI1AZ4RWGL6010 | DUKHCONI1AZ4PSGL7000, DUKHCONI1AZ5RWGL6000, DUKHCONI1AZ4RWGL6020, DUKHCONI1AZ4PSGL7005 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ4RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 12 | No | DUKHCONI1AZ4RWGL6005 | DUKHCONI1AZ4RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ4RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-09-21 | 2014-09-25 | 2014-09-21 | 2014-09-25 | 27 | No | DUKHCONI1AZ4RWGL6015 | DUKHCONI1AZ4RWGL6025, DUKHCONI1AZ4PSGL7010 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ4RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-08-05 | 2014-09-02 | 2014-08-05 | 2014-09-02 | 12 | No | DUKHCONI1AZ4RWGL6000 | DUKHCONI1AZ4RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ4RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-10-02 | 2014-10-07 | 2014-10-02 | 2014-10-07 | 42 | No | DUKHCONI1AZ3RWGL6030, DUKHCONI1AZ4RWGL6025 | DUKHCONI1AZ5RWGL6030, DUKHCONI1AZ4PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L20.25 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-09-03 | 2014-11-02 | 2014-09-03 | 2014-11-02 | 27 |  |  |  | 0 | 0
DUKHCONI1AZ4PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 27 | No | DUKHCONI1AZ4PSGL7005, DUKHCONI1AZ4BWGL5330, DUKHCONI1AZ4RWGL6020, DUKHCONI1AZ4RWGL6030, DUKHCONI1AZ3PSGL7010 | DUKHCONI1AZ4PSGL7015, DUKHCONI1AZ5PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI1AZ4PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-10-02 | 2014-11-02 | 2014-10-02 | 2014-11-02 | 27 | No | DUKHCONI1AZ4PSGL7010, DUKHCONI1AZ3PSGL7015, DUKHCONI1AZ4STGL5260 | DUKHCONI1AZ5PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1AZ4PSGL7000 | Excavation | 15 | 15 | 0% | 2014-09-03 | 2014-09-20 | 2014-09-03 | 2014-09-20 | 32 | No | DUKHCONI1AZ4RWGL6015, DUKHCONI1AZ3PSGL7005 | DUKHCONI1AZ4PSGL7005, DUKHCONI1AZ4PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1AZ4PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-09-15 | 2014-10-01 | 2014-09-15 | 2014-10-01 | 27 | No | DUKHCONI1AZ4PSGL7000, DUKHCONI1AZ4PSGL7000, DUKHCONI1AZ4RWGL6015 | DUKHCONI1AZ5PSGL7000, DUKHCONI1AZ4PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L20.25 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-07-21 | 2014-10-15 | 2014-07-21 | 2014-10-15 | 41 |  |  |  | 0 | 0
DUKHCONI1AZ4HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 31 | No | DUKHCONI1AZ4HDGL7025, DUKHCONI1AZ3HDGL7030 | DUKHCONI1AZ5HDGL7030, DUKHCONI1AZ4HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ4HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-10-02 | 2014-10-15 | 2014-10-02 | 2014-10-15 | 41 | No | DUKHCONI1AZ4HDGL7035, DUKHCONI1AZ4RWGL6025, DUKHCONI1AZ3HDGL7040 | DUKHCONI1AZ5HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ4HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 31 | No | DUKHCONI1AZ3HDGL7035, DUKHCONI1AZ4HDGL7030 | DUKHCONI1AZ4HDGL7040, DUKHCONI1AZ5HDGL7035, DUKHCONI1AZ4SLGL7200 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ4HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-08-05 | 2014-09-02 | 2014-08-05 | 2014-09-02 | 31 | No | DUKHCONI1AZ4HDGL7020 | DUKHCONI1AZ4HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ4HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-07-21 | 2014-08-16 | 2014-07-21 | 2014-08-16 | 31 | No | DUKHCONI1AZ4RWGL6000 | DUKHCONI1ASBGZGL7900, DUKHCONI1AZ4HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L20.25 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-08-28 | 2014-10-21 | 2014-08-28 | 2014-10-21 | 41 |  |  |  | 0 | 0
DUKHCONI1AZ4SLGL7200 | Excavation | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 31 | No | DUKHCONI1AZ4IRGL5290, DUKHCONI1AZ4HDGL7035, DUKHCONI1AZ3SLGL7205 | DUKHCONI1AZ4SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ4SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-09-21 | 2014-10-21 | 2014-09-21 | 2014-10-21 | 41 | No | DUKHCONI1AZ3SLGL7210, DUKHCONI1AZ4SLGL7205 | DUKHCONI1AZ5SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ4SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-09-09 | 2014-10-07 | 2014-09-09 | 2014-10-07 | 31 | No | DUKHCONI1AZ4SLGL7200 | DUKHCONI1AZ5SLGL7200, DUKHCONI1AZ4SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L20.30 ZONE - 5 |  | 216 | 216 | 0% | 2014-04-08 | 2014-12-22 | 2014-04-08 | 2014-12-22 | 14 |  |  |  | 0 | 0
DHBL.K30.L20.30 .10 INFRASTRUCTURE WORKS |  | 216 | 216 | 0% | 2014-04-08 | 2014-12-22 | 2014-04-08 | 2014-12-22 | 14 |  |  |  | 0 | 0
DHBL.K30.L20.30 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2014-04-08 | 2014-05-27 | 2014-04-08 | 2014-05-27 | 9 |  |  |  | 0 | 0
DUKHCONI1AZ5DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2014-05-11 | 2014-05-27 | 2014-05-11 | 2014-05-27 | 9 | No | DUKHCONI1AZ5DRGL5125, DUKHCONI1AZ5DRGL5125 | DUKHCONI1AZ5SAGL5140, DUKHCONI1AZ5SAGL5135, DUKHCONI1AZ5WSGL5155 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ5DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 9 | No | DUKHCONP1AZ8STFF2030, DUKHCONI1AZ4DRGL5130 | DUKHCONI1AZ5DRGL5120, DUKHCONI1AZ5DRGL5120, DUKHCONI1AZ5SAGL5140, DUKHCONI1AZ5SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ5DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 9 | No | DUKHCONI1AZ5DRGL5115, DUKHCONI1AZ5DRGL5115 | DUKHCONI1AZ5DRGL5125, DUKHCONI1AZ5DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1AZ5DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 9 | No | DUKHCONI1AZ5DRGL5120, DUKHCONI1AZ5DRGL5120 | DUKHCONI1AZ5DRGL5130, DUKHCONI1AZ5DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L20.30 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2014-05-08 | 2014-07-28 | 2014-05-08 | 2014-07-28 | 45 |  |  |  | 0 | 0
DUKHCONI1AZ5SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-07-06 | 2014-07-28 | 2014-07-06 | 2014-07-28 | 45 | No | DUKHCONI1AZ5SAGL5135, DUKHCONI1AZ5SAGL5145 | DUKHCONI1AZ5RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ5SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 68 | No | DUKHCONI1AZ5DRGL5130, DUKHCONI1AZ4SAGL5135, DUKHCONI1AZ5DRGL5115 | DUKHCONI1AZ5SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ5SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-06-07 | 2014-07-05 | 2014-06-07 | 2014-07-05 | 11 | No | DUKHCONI1AZ4SAGL5145, DUKHCONI1AZ5SAGL5140 | DUKHCONI1AZ5WSGL5170, DUKHCONI1AZ5SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1AZ5SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2014-05-08 | 2014-06-05 | 2014-05-08 | 2014-06-05 | 11 | No | DUKHCONI1AZ5DRGL5130, DUKHCONI1AZ5DRGL5115 | DUKHCONI1AZ5SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L20.30 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-05-22 | 2014-08-09 | 2014-05-22 | 2014-08-09 | 38 |  |  |  | 0 | 0
DUKHCONI1AZ5WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 9 | No | DUKHCONI1AZ5WSGL5165, DUKHCONI1AZ5SAGL5145 | DUKHCONI1AZ5WSGL5175, DUKHCONI1AZ5FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ5WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 38 | No | DUKHCONI1AZ5WSGL5155, DUKHCONI1AZ5WSGL5170, DUKHCONI1AZ4WSGL5175 | DUKHCONI1AZ5WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ5WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 9 | No | DUKHCONI1AZ4WSGL5170, DUKHCONI1AZ5DRGL5130 | DUKHCONI1AZ5WSGL5175, DUKHCONI1AZ5WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ5WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-07-14 | 2014-08-09 | 2014-07-14 | 2014-08-09 | 38 | No | DUKHCONI1AZ5WSGL5175, DUKHCONI1AZ4WSGL5180 | DUKHCONI1AZ5FFGL5210, DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ5WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 9 | No | DUKHCONI1AZ5WSGL5155 | DUKHCONI1AZ5WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1AZ5WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-06-03 | 2014-07-01 | 2014-06-03 | 2014-07-01 | 9 | No | DUKHCONI1AZ5WSGL5160 | DUKHCONI1AZ5WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L20.30 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-06-15 | 2014-08-17 | 2014-06-15 | 2014-08-17 | 31 |  |  |  | 0 | 0
DUKHCONI1AZ5FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-07-05 | 2014-08-05 | 2014-07-05 | 2014-08-05 | 9 | No | DUKHCONI1AZ5FFGL5195 | DUKHCONI1AZ5FFGL5205, DUKHCONI1AZ5RWGL6000, DUKHCONI1AZ5ELGL5215 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ5FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 31 | No | DUKHCONI1AZ5FFGL5205, DUKHCONI1AZ5WSGL5180, DUKHCONI1AZ4FFGL5210 | DUKHHANP1AGNELTC9010, DUKHCONI1ASBIWGL7440, DUKHCONI1AZ5RWGL6000, DUKHHANP1AGNPLTC9005 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ5FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-07-10 | 2014-08-11 | 2014-07-10 | 2014-08-11 | 31 | No | DUKHCONI1AZ4FFGL5205, DUKHCONI1AZ5FFGL5200, DUKHCONI1AZ5FFGL5185 | DUKHCONI1AZ5FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ5FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 9 | No | DUKHCONI1AZ4FFGL5200, DUKHCONI1AZ5WSGL5170 | DUKHCONI1AZ5FFGL5190, DUKHCONI1AZ5FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ5FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 9 | No | DUKHCONI1AZ5FFGL5185 | DUKHCONI1AZ5FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1AZ5FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-06-29 | 2014-07-27 | 2014-06-29 | 2014-07-27 | 9 | No | DUKHCONI1AZ5FFGL5190 | DUKHCONI1AZ5FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L20.30 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-07-13 | 2014-09-08 | 2014-07-13 | 2014-09-08 | 41 |  |  |  | 0 | 0
DUKHCONI1AZ5ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-07-27 | 2014-08-27 | 2014-07-27 | 2014-08-27 | 22 | No | DUKHCONI1AZ5ELGL5220, DUKHCONI1AZ5ELGL5215 | DUKHCONI1AZ5IRGL5285, DUKHCONI1AZ5ELGL5230, DUKHCONI1AZ5IRGL5265, DUKHCONI1AZ5RWGL6000, DUKHCONI1AZ5ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ5ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-08-11 | 2014-09-08 | 2014-08-11 | 2014-09-08 | 41 | No | DUKHCONI1AZ5ELGL5225, DUKHCONI1AZ4ELGL5230, DUKHCONI1AZ5ELGL5225 | DUKHCONI1AZ5STGL5260, DUKHCONI1ASBIWGL7450 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ5ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 9 | No | DUKHCONI1AZ4ELGL5225, DUKHCONI1AZ5FFGL5200 | DUKHCONI1AZ5STGL5235, DUKHCONI1AZ5ELGL5225, DUKHCONI1AZ5ELGL5220 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1AZ5ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-07-19 | 2014-08-19 | 2014-07-19 | 2014-08-19 | 22 | No | DUKHCONI1AZ5ELGL5215 | DUKHCONI1AZ5ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L20.30 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-07-13 | 2014-10-07 | 2014-07-13 | 2014-10-07 | 41 |  |  |  | 0 | 0
DUKHCONI1AZ5STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-07-24 | 2014-08-25 | 2014-07-24 | 2014-08-25 | 9 | No | DUKHCONI1AZ5STGL5235, DUKHCONI1AZ5STGL5245 | DUKHCONI1AZ5STGL5255, DUKHCONI1AZ5TCGL5295, DUKHCONI1AZ5RWGL6000, DUKHCONI1AZ5BWGL5315 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ5STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-07-19 | 2014-08-19 | 2014-07-19 | 2014-08-19 | 9 | No | DUKHCONI1AZ5STGL5235 | DUKHCONI1AZ5STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ5STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-07-19 | 2014-08-19 | 2014-07-19 | 2014-08-19 | 9 | No | DUKHCONI1AZ5STGL5240 | DUKHCONI1AZ5STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ5STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-09-09 | 2014-10-07 | 2014-09-09 | 2014-10-07 | 41 | No | DUKHCONI1AZ5STGL5255, DUKHCONI1AZ5STGL5255, DUKHCONI1AZ5ELGL5230, DUKHCONI1AZ4STGL5260 | DUKHCONI1AZ5PSGL7015, DUKHHANP1AGNPLTC9005, DUKHCONI1ASBIWGL7450, DUKHHANP1AGNELTC9010 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ5STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 9 | No | DUKHCONI1AZ5ELGL5215, DUKHCONI1AZ4STGL5250 | DUKHCONI1AZ5STGL5250, DUKHCONI1AZ5STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI1AZ5STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-08-09 | 2014-09-06 | 2014-08-09 | 2014-09-06 | 58 | No | DUKHCONI1AZ5STGL5250, DUKHCONI1AZ4STGL5255 | DUKHCONI1AZ5STGL5260, DUKHCONI1AZ5STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L20.30 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-08-28 | 2014-11-04 | 2014-08-28 | 2014-11-04 | 34 |  |  |  | 0 | 0
DUKHCONI1AZ5IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-09-15 | 2014-10-15 | 2014-09-15 | 2014-10-15 | 34 | No | DUKHCONI1AZ5IRGL5275 | DUKHCONI1AZ5IRGL5285, DUKHCONI1AZ5IRGL5290, DUKHCONI1ASBTRGL7620 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ5IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 34 | No | DUKHCONI1AZ5ELGL5225, DUKHCONI1AZ5IRGL5280 | DUKHCONI1AZ5IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ5IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 34 | No | DUKHCONI1AZ5ELGL5225, DUKHCONI1AZ4IRGL5280 | DUKHCONI1AZ5IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ5IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-10-05 | 2014-11-04 | 2014-10-05 | 2014-11-04 | 34 | No | DUKHCONI1AZ5IRGL5280, DUKHCONI1AZ5IRGL5285 | DUKHCONI1AZ5SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ5IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-09-03 | 2014-10-01 | 2014-09-03 | 2014-10-01 | 34 | No | DUKHCONI1AZ5IRGL5265 | DUKHCONI1AZ5IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1AZ5IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-09-09 | 2014-10-07 | 2014-09-09 | 2014-10-07 | 34 | No | DUKHCONI1AZ5IRGL5270 | DUKHCONI1AZ5IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L20.30 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-08-09 | 2014-09-23 | 2014-08-09 | 2014-09-23 | 28 |  |  |  | 0 | 0
DUKHCONI1AZ5TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-08-20 | 2014-09-11 | 2014-08-20 | 2014-09-11 | 9 | No | DUKHCONI1AZ5TCGL5300 | DUKHCONI1AZ5TCGL5310, DUKHCONI1AZ5RWGL6000 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ5TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-09-01 | 2014-09-23 | 2014-09-01 | 2014-09-23 | 28 | No | DUKHCONI1AZ4TCGL5310, DUKHCONI1AZ5TCGL5305 | DUKHHANP1AGNPLTC9005, DUKHCONI1ASBIWGL7450, DUKHCONI1ASBTRGL7630, DUKHHANP1AGNELTC9010 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ5TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-08-09 | 2014-08-31 | 2014-08-09 | 2014-08-31 | 9 | No | DUKHCONI1AZ4TCGL5305, DUKHCONI1AZ5STGL5250 | DUKHCONI1AZ5TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1AZ5TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-08-14 | 2014-09-06 | 2014-08-14 | 2014-09-06 | 9 | No | DUKHCONI1AZ5TCGL5295 | DUKHCONI1AZ5TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L20.30 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-08-09 | 2014-11-04 | 2014-08-09 | 2014-11-04 | 45 |  |  |  | 0 | 0
DUKHCONI1AZ5BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-10-05 | 2014-11-04 | 2014-10-05 | 2014-11-04 | 45 | No | DUKHCONI1AZ5BWGL5325, DUKHCONI1AZ4BWGL5330 | DUKHCONI1AZ5PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ5BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-09-23 | 2014-10-23 | 2014-09-23 | 2014-10-23 | 34 | No | DUKHCONI1AZ5BWGL5315, DUKHCONI1AZ5BWGL5320, DUKHCONI1AZ4BWGL5325 | DUKHCONI1AZ5BWGL5330, DUKHCONP1AZ9MSEX5335 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ5BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-08-09 | 2014-09-06 | 2014-08-09 | 2014-09-06 | 34 | No | DUKHCONI1AZ4BWGL5315, DUKHCONI1AZ5STGL5250 | DUKHCONI1AZ5BWGL5325, DUKHCONI1AZ5BWGL5320 | 0 | 0 | BOUNDARY WALL
DUKHCONI1AZ5BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-08-25 | 2014-09-22 | 2014-08-25 | 2014-09-22 | 34 | No | DUKHCONI1AZ5BWGL5315 | DUKHCONI1AZ5BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L20.30 .10 .55 ROAD WORKS |  | 64 | 64 | 0% | 2014-09-13 | 2014-11-27 | 2014-09-13 | 2014-11-27 | 25 |  |  |  | 0 | 0
DUKHCONI1AZ5RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-09-13 | 2014-09-23 | 2014-09-13 | 2014-09-23 | 9 | No | DUKHCONI1AZ5SAGL5150, DUKHCONI1AZ4RWGL6015, DUKHCONI1AZ5FFGL5200, DUKHCONI1AZ5ELGL5225, DUKHCONI1AZ5TCGL5305, DUKHCONI1AZ5STGL5250, DUKHCONI1AZ5FFGL5210 | DUKHCONI1AZ5RWGL6005, DUKHCONI1AZ5HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ5RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-11-17 | 2014-11-22 | 2014-11-17 | 2014-11-22 | 9 | No | DUKHCONI1AZ5RWGL6020, DUKHCONI1AZ4RWGL6025 | DUKHCONI1AZ5HDGL7040, DUKHCONI1AZ5RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ5RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-10-19 | 2014-11-10 | 2014-10-19 | 2014-11-10 | 9 | No | DUKHCONI1AZ5RWGL6010 | DUKHCONI1AZ5PSGL7000, DUKHCONI1AZ5PSGL7005, DUKHCONI1AZ5RWGL6020 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ5RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-10-06 | 2014-11-05 | 2014-10-06 | 2014-11-05 | 9 | No | DUKHCONI1AZ5RWGL6005 | DUKHCONI1AZ5RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ5RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-11-11 | 2014-11-16 | 2014-11-11 | 2014-11-16 | 9 | No | DUKHCONI1AZ5RWGL6015 | DUKHCONI1AZ5PSGL7010, DUKHCONI1AZ5RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ5RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-09-24 | 2014-10-25 | 2014-09-24 | 2014-10-25 | 9 | No | DUKHCONI1AZ5RWGL6000 | DUKHCONI1AZ5RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1AZ5RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-11-23 | 2014-11-27 | 2014-11-23 | 2014-11-27 | 25 | No | DUKHCONI1AZ4RWGL6030, DUKHCONI1AZ5RWGL6025 | DUKHCONI1AZ5PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L20.30 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-10-25 | 2014-12-22 | 2014-10-25 | 2014-12-22 | 10 |  |  |  | 0 | 0
DUKHCONI1AZ5PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-11-17 | 2014-12-15 | 2014-11-17 | 2014-12-15 | 10 | No | DUKHCONI1AZ5RWGL6020, DUKHCONI1AZ5PSGL7005, DUKHCONI1AZ5BWGL5330, DUKHCONI1AZ4PSGL7010, DUKHCONI1AZ5RWGL6030 | DUKHCONI1AZ5PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1AZ5PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-11-23 | 2014-12-22 | 2014-11-23 | 2014-12-22 | 10 | No | DUKHCONI1AZ5PSGL7010, DUKHCONI1AZ5STGL5260, DUKHCONI1AZ4PSGL7015 | DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | PARKING SHED
DUKHCONI1AZ5PSGL7000 | Excavation | 15 | 15 | 0% | 2014-10-25 | 2014-11-10 | 2014-10-25 | 2014-11-10 | 15 | No | DUKHCONI1AZ4PSGL7005, DUKHCONI1AZ5RWGL6015 | DUKHCONI1AZ5PSGL7005, DUKHCONI1AZ5PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1AZ5PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-11-05 | 2014-11-22 | 2014-11-05 | 2014-11-22 | 10 | No | DUKHCONI1AZ5PSGL7000, DUKHCONI1AZ5PSGL7000, DUKHCONI1AZ5RWGL6015 | DUKHCONI1AZ5PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L20.30 .10 .65 HARD LANDSCAPING |  | 69 | 69 | 0% | 2014-09-13 | 2014-12-03 | 2014-09-13 | 2014-12-03 | 9 |  |  |  | 0 | 0
DUKHCONI1AZ5HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-10-06 | 2014-11-05 | 2014-10-06 | 2014-11-05 | 23 | No | DUKHCONI1AZ4HDGL7030, DUKHCONI1AZ5HDGL7025 | DUKHCONI1AZ5HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ5HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-11-23 | 2014-12-03 | 2014-11-23 | 2014-12-03 | 9 | No | DUKHCONI1AZ5RWGL6025, DUKHCONI1AZ5HDGL7035, DUKHCONI1AZ4HDGL7040 | DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ5HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-10-06 | 2014-11-05 | 2014-10-06 | 2014-11-05 | 23 | No | DUKHCONI1AZ4HDGL7035, DUKHCONI1AZ5HDGL7030 | DUKHCONI1AZ5SLGL7200, DUKHCONI1AZ5HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ5HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-09-24 | 2014-10-25 | 2014-09-24 | 2014-10-25 | 23 | No | DUKHCONI1AZ5HDGL7020, DUKHCONI1ASBGZGL7910 | DUKHCONI1AZ5HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1AZ5HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-09-13 | 2014-10-05 | 2014-09-13 | 2014-10-05 | 23 | No | DUKHCONI1AZ5RWGL6000 | DUKHCONI1AZ5HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L20.30 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-10-20 | 2014-12-10 | 2014-10-20 | 2014-12-10 | 23 |  |  |  | 0 | 0
DUKHCONI1AZ5SLGL7200 | Excavation for Landscaping | 25 | 25 | 0% | 2014-10-20 | 2014-11-17 | 2014-10-20 | 2014-11-17 | 23 | No | DUKHCONI1AZ5IRGL5290, DUKHCONI1AZ4SLGL7205, DUKHCONI1AZ5HDGL7035 | DUKHCONI1AZ5SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ5SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-11-12 | 2014-12-10 | 2014-11-12 | 2014-12-10 | 23 | No | DUKHCONI1AZ5SLGL7205, DUKHCONI1ASBSSGL7935, DUKHCONI1AZ4SLGL7210 | DUKHHANP1AGNPLTC9005, DUKHHANP1AGNELTC9010 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1AZ5SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-11-01 | 2014-11-29 | 2014-11-01 | 2014-11-29 | 23 | No | DUKHCONI1AZ5SLGL7200 | DUKHCONI1AZ5SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L20.35 SECONDARY BUILDINGS |  | 154 | 154 | 0% | 2014-05-26 | 2014-11-26 | 2014-05-26 | 2014-11-26 | 35 |  |  |  | 0 | 0
DHBL.K30.L20.35 .10 INFRASTRUCTURE WORKS |  | 154 | 154 | 0% | 2014-05-26 | 2014-11-26 | 2014-05-26 | 2014-11-26 | 35 |  |  |  | 0 | 0
DHBL.K30.L20.35 .10 .10 IRRIGATION WATER TANK & PUMP ROOM |  | 151 | 151 | 0% | 2014-05-26 | 2014-11-23 | 2014-05-26 | 2014-11-23 | 18 |  |  |  | 0 | 0
DUKHCONI1ASBIWGL7445 | AC Works | 25 | 25 | 0% | 2014-10-06 | 2014-11-05 | 2014-10-06 | 2014-11-05 | 18 | No | DUKHCONI1ASBIWGL7440 | DUKHCONI1ASBIWGL7450 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7405 | Blinding & base waterproofing | 10 | 10 | 0% | 2014-06-16 | 2014-06-26 | 2014-06-16 | 2014-06-26 | 18 | No | DUKHCONI1ASBIWGL7400 | DUKHCONI1ASBIWGL7410 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7420 | Construction of Roof Slab | 20 | 20 | 0% | 2014-08-13 | 2014-09-04 | 2014-08-13 | 2014-09-04 | 18 | No | DUKHCONI1ASBIWGL7415 | DUKHCONI1ASBIWGL7430, DUKHCONI1ASBIWGL7425 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7410 | Construction of Raft slab | 12 | 12 | 0% | 2014-06-28 | 2014-07-10 | 2014-06-28 | 2014-07-10 | 18 | No | DUKHCONI1ASBIWGL7405 | DUKHCONI1ASBIWGL7415 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7415 | Construction of RCC Wall | 25 | 25 | 0% | 2014-07-12 | 2014-08-12 | 2014-07-12 | 2014-08-12 | 18 | No | DUKHCONI1ASBIWGL7410 | DUKHCONI1ASBIWGL7420 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7450 | Electrical Works | 25 | 25 | 0% | 2014-10-06 | 2014-11-05 | 2014-10-06 | 2014-11-05 | 18 | No | DUKHCONI1ASBIWGL7445, DUKHCONI1AZ5TCGL5310, DUKHCONI1AZ5STGL5260, DUKHCONI1AZ5ELGL5230 | DUKHCONI1ASBIWGL7455 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7400 | Excavation | 18 | 18 | 0% | 2014-05-26 | 2014-06-15 | 2014-05-26 | 2014-06-15 | 18 | No | DUKHENGI1ADWIWAP4360, DUKHCONP1AZ9STRF2040 | DUKHCONI1ASBTRGL7600, DUKHCONI1ASBIWGL7405 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7430 | Floor screed | 5 | 5 | 0% | 2014-09-30 | 2014-10-05 | 2014-09-30 | 2014-10-05 | 18 | No | DUKHCONI1ASBIWGL7425, DUKHCONI1ASBIWGL7420 | DUKHCONI1ASBIWGL7440 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7435 | Installation of Boundary Fences | 15 | 15 | 0% | 2014-10-05 | 2014-10-23 | 2014-10-05 | 2014-10-23 | 39 | No | DUKHCONI1ASBIWGL7950, DUKHPROGEN00PRDV3850 | DUKHCONI1ASBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7465 | Installation of G.I Handrails | 5 | 5 | 0% | 2014-11-18 | 2014-11-23 | 2014-11-18 | 2014-11-23 | 18 | No | DUKHCONI1ASBIWGL7460, DUKHCONI1ASBIWGL7435 | DUKHHANP1AGNACTC9000, DUKHHANP1AGNPLTC9005, DUKHHANP1AGNELTC9010 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7460 | Installation of Steel Ladder | 5 | 5 | 0% | 2014-11-12 | 2014-11-17 | 2014-11-12 | 2014-11-17 | 18 | No | DUKHPROGEN00PRDV3630, DUKHCONI1ASBIWGL7455 | DUKHCONI1ASBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7455 | Internal epoxy coating & Painting | 5 | 5 | 0% | 2014-11-06 | 2014-11-11 | 2014-11-06 | 2014-11-11 | 18 | No | DUKHCONI1ASBIWGL7450 | DUKHCONI1ASBIWGL7460 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7950 | Laying of Interlock | 10 | 10 | 0% | 2014-09-23 | 2014-10-04 | 2014-09-23 | 2014-10-04 | 39 | No | DUKHCONI1ASBIWGL7425 | DUKHCONI1ASBIWGL7435 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7440 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-10-06 | 2014-11-05 | 2014-10-06 | 2014-11-05 | 18 | No | DUKHCONI1ASBIWGL7430, DUKHCONI1AZ3FFGL5210, DUKHCONI1AZ4FFGL5210, DUKHCONI1AZ2FFGL5210, DUKHCONI1AZ5FFGL5210, DUKHCONI1AZ1FFGL5210 | DUKHCONI1ASBIWGL7445 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1ASBIWGL7425 | Waterproofing & Backfilling | 15 | 15 | 0% | 2014-09-06 | 2014-09-22 | 2014-09-06 | 2014-09-22 | 24 | No | DUKHCONI1ASBIWGL7420 | DUKHCONI1ASBIWGL7950, DUKHCONI1ASBIWGL7430 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DHBL.K30.L20.35 .10 .15 TELECOMMUNICATION ROOM |  | 115 | 115 | 0% | 2014-06-16 | 2014-11-02 | 2014-06-16 | 2014-11-02 | 36 |  |  |  | 0 | 0
DUKHCONI1ASBTRGL7625 | AC Works | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 36 | No | DUKHCONI1ASBTRGL7620 | DUKHCONI1ASBTRGL7630, DUKHCONI1ASBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1ASBTRGL7610 | Construction Column,Beams & Roof Slab | 20 | 20 | 0% | 2014-07-21 | 2014-08-16 | 2014-07-21 | 2014-08-16 | 40 | No | DUKHCONI1ASBTRGL7605 | DUKHCONI1ASBTRGL7615 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1ASBTRGL7605 | Construction of foundation & Grade slab | 20 | 20 | 0% | 2014-06-28 | 2014-07-20 | 2014-06-28 | 2014-07-20 | 40 | No | DUKHCONI1ASBTRGL7600 | DUKHCONI1ASBTRGL7610 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1ASBTRGL7630 | Electrical Works-Telecom Room | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 36 | No | DUKHCONI1AZ2TCGL5310, DUKHCONI1AZ1TCGL5310, DUKHCONI1ASBTRGL7625, DUKHCONI1AZ3TCGL5310, DUKHCONI1AZ4TCGL5310, DUKHCONI1AZ5TCGL5310 | DUKHCONI1ASBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1ASBTRGL7600 | Excavation | 10 | 10 | 0% | 2014-06-16 | 2014-06-26 | 2014-06-16 | 2014-06-26 | 30 | No | DUKHCONI1ASBIWGL7400, DUKHENGI1ADWTRAP4370 | DUKHCONI1ASBGHGL7800, DUKHCONI1ASBTRGL7605 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1ASBTRGL7635 | Final Paintings | 5 | 5 | 0% | 2014-10-28 | 2014-11-02 | 2014-10-28 | 2014-11-02 | 36 | No | DUKHCONI1ASBTRGL7615, DUKHCONI1ASBTRGL7620, DUKHCONI1ASBTRGL7625, DUKHCONI1ASBTRGL7630 | DUKHHANP1AGNACTC9000, DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1ASBTRGL7615 | Finishing Works | 25 | 25 | 0% | 2014-09-10 | 2014-10-08 | 2014-09-10 | 2014-10-08 | 40 | No | DUKHCONI1ASBTRGL7610 | DUKHCONI1ASBTRGL7635, DUKHCONI1ASBTRGL7620 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1ASBTRGL7620 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-09-27 | 2014-10-27 | 2014-09-27 | 2014-10-27 | 36 | No | DUKHCONI1ASBTRGL7615, DUKHCONI1AZ5IRGL5280 | DUKHCONI1ASBTRGL7625, DUKHCONI1ASBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DHBL.K30.L20.35 .10 .20 GUARD HOUSE |  | 111 | 111 | 0% | 2014-06-28 | 2014-11-09 | 2014-06-28 | 2014-11-09 | 30 |  |  |  | 0 | 0
DUKHCONI1ASBGHGL7825 | AC Works | 25 | 25 | 0% | 2014-10-04 | 2014-11-03 | 2014-10-04 | 2014-11-03 | 30 | No | DUKHCONI1ASBGHGL7820 | DUKHCONI1ASBGHGL7830, DUKHCONI1ASBGHGL7835 | 0 | 0 | GUARD HOUSE
DUKHCONI1ASBGHGL7810 | Construction Column,Beams & Roof Slab | 20 | 20 | 0% | 2014-08-05 | 2014-08-27 | 2014-08-05 | 2014-08-27 | 30 | No | DUKHCONI1ASBGHGL7805 | DUKHCONI1ASBGHGL7815 | 0 | 0 | GUARD HOUSE
DUKHCONI1ASBGHGL7805 | Construction of foundation & Grade slab | 20 | 20 | 0% | 2014-07-09 | 2014-07-31 | 2014-07-09 | 2014-07-31 | 30 | No | DUKHCONI1ASBGHGL7800 | DUKHCONI1ASBGHGL7810 | 0 | 0 | GUARD HOUSE
DUKHCONI1ASBGHGL7830 | Electrical Works-Telecom Room | 25 | 25 | 0% | 2014-10-04 | 2014-11-03 | 2014-10-04 | 2014-11-03 | 30 | No | DUKHCONI1ASBGHGL7825 | DUKHCONI1ASBGHGL7835 | 0 | 0 | GUARD HOUSE
DUKHCONI1ASBGHGL7800 | Excavation | 10 | 10 | 0% | 2014-06-28 | 2014-07-08 | 2014-06-28 | 2014-07-08 | 30 | No | DUKHCONI1ASBTRGL7600, DUKHENGI1ADWGHAP4390 | DUKHCONI1ASBGHGL7805 | 0 | 0 | GUARD HOUSE
DUKHCONI1ASBGHGL7835 | Final Paintings | 5 | 5 | 0% | 2014-11-04 | 2014-11-09 | 2014-11-04 | 2014-11-09 | 30 | No | DUKHCONI1ASBGHGL7830, DUKHCONI1ASBGHGL7820, DUKHCONI1ASBGHGL7825, DUKHCONI1ASBGHGL7815 | DUKHHANP1AGNACTC9000, DUKHHANP1AGNELTC9010, DUKHHANP1AGNPLTC9005 | 0 | 0 | GUARD HOUSE
DUKHCONI1ASBGHGL7815 | Finishing Works | 25 | 25 | 0% | 2014-09-22 | 2014-10-22 | 2014-09-22 | 2014-10-22 | 30 | No | DUKHCONI1ASBGHGL7810 | DUKHCONI1ASBGHGL7820, DUKHCONI1ASBGHGL7835 | 0 | 0 | GUARD HOUSE
DUKHCONI1ASBGHGL7820 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-10-04 | 2014-11-03 | 2014-10-04 | 2014-11-03 | 30 | No | DUKHCONI1ASBGHGL7815 | DUKHCONI1ASBGHGL7825, DUKHCONI1ASBGHGL7835 | 0 | 0 | GUARD HOUSE
DHBL.K30.L20.35 .10 .25 GAZEBO |  | 50 | 50 | 0% | 2014-08-17 | 2014-10-15 | 2014-08-17 | 2014-10-15 | 31 |  |  |  | 0 | 0
DUKHCONI1ASBGZGL7900 | Construction of Concrete structure | 20 | 20 | 0% | 2014-08-17 | 2014-09-08 | 2014-08-17 | 2014-09-08 | 31 | No | DUKHPROGEN00PRDV3780, DUKHCONI1AZ4HDGL7020, DUKHENGI1ADWGZAP4380 | DUKHCONI1ASBGZGL7905, DUKHCONI1ASBSSGL7930 | 0 | 0 | GAZEBO
DUKHCONI1ASBGZGL7910 | Electrical Works-Gazebo | 15 | 15 | 0% | 2014-09-27 | 2014-10-15 | 2014-09-27 | 2014-10-15 | 31 | No | DUKHCONI1ASBGZGL7915, DUKHCONI1ASBGZGL7905 | DUKHCONI1AZ5HDGL7025 | 0 | 0 | GAZEBO
DUKHCONI1ASBGZGL7905 | Installation of Wooden Works | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 31 | No | DUKHCONI1ASBGZGL7900 | DUKHCONI1ASBGZGL7915, DUKHCONI1ASBGZGL7910 | 0 | 0 | GAZEBO
DUKHCONI1ASBGZGL7915 | Park Benches Installation | 15 | 15 | 0% | 2014-08-28 | 2014-09-14 | 2014-08-28 | 2014-09-14 | 41 | No | DUKHCONI1ASBGZGL7905 | DUKHCONI1ASBGZGL7910 | 0 | 0 | GAZEBO
DHBL.K30.L20.35 .10 .30 SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS) |  | 66 | 66 | 0% | 2014-09-09 | 2014-11-26 | 2014-09-09 | 2014-11-26 | 35 |  |  |  | 0 | 0
DUKHCONI1ASBSSGL7930 | Construction of Drainage Channel | 30 | 30 | 0% | 2014-09-09 | 2014-10-15 | 2014-09-09 | 2014-10-15 | 35 | No | DUKHCONI1ASBGZGL7900 | DUKHCONI1ASBSSGL7920, DUKHCONI1ASBSSGL7920 | 0 | 0 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS)
DUKHCONI1ASBSSGL7935 | Fencing Works | 30 | 30 | 0% | 2014-10-23 | 2014-11-26 | 2014-10-23 | 2014-11-26 | 35 | No | DUKHCONI1ASBSSGL7925, DUKHCONI1ASBSSGL7925 | DUKHCONI1AZ5SLGL7210 | 0 | 0 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS)
DUKHCONI1ASBSSGL7920 | Hard landscaping around substation | 30 | 30 | 0% | 2014-09-23 | 2014-10-29 | 2014-09-23 | 2014-10-29 | 35 | No | DUKHCONI1ASBSSGL7930, DUKHCONI1ASBSSGL7930 | DUKHCONI1ASBSSGL7925, DUKHCONI1ASBSSGL7925 | 0 | 0 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS)
DUKHCONI1ASBSSGL7925 | Soft landscaping around substation | 30 | 30 | 0% | 2014-10-07 | 2014-11-12 | 2014-10-07 | 2014-11-12 | 35 | No | DUKHCONI1ASBSSGL7920, DUKHCONI1ASBSSGL7920 | DUKHCONI1ASBSSGL7935, DUKHCONI1ASBSSGL7935 | 0 | 0 | SUBSTATION-(LANDSCAPING,FENCES & CHANNEL WORKS)
DHBL.K30.L25 PACKAGE-1B |  | 621 | 621 | 0% | 2012-12-01 | 2014-12-10 | 2012-12-01 | 2014-12-10 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.03 SITE PREPARATORY WORKS |  | 76 | 76 | 0% | 2012-12-01 | 2013-02-28 | 2012-12-01 | 2013-02-28 | 52 |  |  |  | 0 | 0
DUKHCONP1BGNSP002400 | Approval for new Layout for rerouting | 10 | 10 | 0% | 2013-01-19 | 2013-01-29 | 2013-01-19 | 2013-01-29 | 37 | No | DUKHCONP1BGNSP002300 | DUKHCONP1BGNSP002500 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP004000 | Demolition of Existing building & landscaping | 20 | 20 | 0% | 2012-12-20 | 2013-01-12 | 2012-12-20 | 2013-01-12 | 87 | No | DUKHCONP1BGNSP003000 | DUKHCONP1BGNSP005000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP005000 | Demolition of existing services works | 20 | 20 | 0% | 2012-12-26 | 2013-01-17 | 2012-12-26 | 2013-01-17 | 87 | No | DUKHCONP1BGNSP004000 | DUKHCONP1BZ1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP002200 | Information Required for Rerouting | 14 | 14 | 0% | 2012-12-25 | 2013-01-09 | 2012-12-25 | 2013-01-09 | 37 | No | DUKHCONP1BGNSP002100 | DUKHCONP1BGNSP002300 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP002300 | Preparation & Submission for new Layout for rerouting | 7 | 7 | 0% | 2013-01-10 | 2013-01-17 | 2013-01-10 | 2013-01-17 | 37 | No | DUKHCONP1BGNSP002200 | DUKHCONP1BGNSP002400 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP002500 | Rerouting Works | 25 | 25 | 0% | 2013-01-30 | 2013-02-28 | 2013-01-30 | 2013-02-28 | 37 | No | DUKHCONP1BGNSP002400 | DUKHCONP1BZ1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP002000 | Scanning for Existing Services for rerouting | 10 | 10 | 0% | 2012-12-06 | 2012-12-17 | 2012-12-06 | 2012-12-17 | 37 | No | DUKHCONP1BGNSP001000 | DUKHCONP1BGNSP002100, DUKHCONP1BGNSP003000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP003000 | Site stripping | 20 | 20 | 0% | 2012-12-13 | 2013-01-06 | 2012-12-13 | 2013-01-06 | 87 | No | DUKHCONP1BGNSP002000 | DUKHCONP1BGNSP004000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP002100 | Submission of Scanning Reports | 5 | 5 | 0% | 2012-12-19 | 2012-12-24 | 2012-12-19 | 2012-12-24 | 37 | No | DUKHCONP1BGNSP002000 | DUKHCONP1BGNSP002200 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP1BGNSP001000 | Survey works, | 20 | 20 | 0% | 2012-12-01 | 2012-12-24 | 2012-12-01 | 2012-12-24 | 37 | No | DUKHMOBP010000004000 | DUKHMOBI1BPS00001000, DUKHCONP1BGNSP002000 | 0 | 0 | SITE PREPARATORY WORKS
DHBL.K30.L25.10 ZONE - 1 (4 Twin Villas) |  | 383 | 383 | 0% | 2013-04-14 | 2014-07-12 | 2013-04-14 | 2014-07-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.10 .10 STRUCTURAL WORKS |  | 237 | 237 | 0% | 2013-04-14 | 2014-01-21 | 2013-04-14 | 2014-01-21 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.10 .10 .10 SUB STRUCTURE |  | 119 | 119 | 0% | 2013-04-14 | 2013-09-02 | 2013-04-14 | 2013-09-02 | 0 |  |  |  | 0 | 0
DHBL.K30.L25.10 .10 .10 .10 UPTO GRADE SLAB |  | 119 | 119 | 0% | 2013-04-14 | 2013-09-02 | 2013-04-14 | 2013-09-02 | 0 |  |  |  | 0 | 0
DUKHCONP1BZ1STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-06-19 | 2013-07-17 | 2013-06-19 | 2013-07-17 | 0 | Yes | DUKHCONP1BZ1STUG1030, DUKHCONP1BZ1STUG1030 | DUKHCONP1BZ1STUG1040, DUKHCONP1BZ1STUG1040, DUKHCONP1BZ2STUG1035 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-05-20 | 2013-06-11 | 2013-05-20 | 2013-06-11 | 0 | Yes | DUKHCONP1BZ1STUG1015, DUKHCONP1BZ1STUG1015 | DUKHCONP1BZ1STUG1025, DUKHCONP1BZ1STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-07-06 | 2013-08-03 | 2013-07-06 | 2013-08-03 | 0 | Yes | DUKHCONP1BZ1STUG1035, DUKHENGP1BDWSTAP4410, DUKHCONP1BZ1STUG1035 | DUKHCONP1BZ1STUG1045, DUKHCONP1BZ1PLUG4300, DUKHCONP1BZ1STUG1045, DUKHCONP1BZ1PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-05-29 | 2013-06-26 | 2013-05-29 | 2013-06-26 | 0 | Yes | DUKHCONP1BZ1STUG1020, DUKHCONP1BZ1STUG1020 | DUKHCONP1BZ2STUG1025, DUKHCONP1BZ1STUG1030, DUKHCONP1BZ1STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-08-01 | 2013-09-02 | 2013-08-01 | 2013-09-02 | 0 | Yes | DUKHCONP1BZ1STUG1040, DUKHCONP1BZ1PLUG4300, DUKHENGP1BDWSTAP4410, DUKHCONP1BZ1PLUG4300, DUKHCONP1BZ1STUG1040 | DUKHCONP1BZ1STGF2000, DUKHCONP1BZ2STUG1045, DUKHCONP1BZ1STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-04-25 | 2013-05-21 | 2013-04-25 | 2013-05-21 | 0 | Yes | DUKHCONP1BZ1STUG1000, DUKHCONP1BZ1STUG1000 | DUKHCONP1BZ1STUG1010, DUKHCONP1BZ1STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-04-29 | 2013-05-25 | 2013-04-29 | 2013-05-25 | 0 | Yes | DUKHCONP1BZ1STUG1005, DUKHCONP1BZ1STUG1005 | DUKHCONP1BZ1STUG1015, DUKHCONP1BZ1STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-04-14 | 2013-05-12 | 2013-04-14 | 2013-05-12 | 0 | Yes | DUKHCONP1AZ2STUG1000, DUKHCONP1BGNSP005000, DUKHMOBI1BPS00001250, DUKHCONP1BGNSP002500, DUKHMOBI1BPS00002113, DUKHENGP1BDWSTAP4400 | DUKHCONP1BZ1STUG1005, DUKHCONP1BZ1STUG1005, DUKHCONP1BZ2STUG1000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-05-05 | 2013-06-02 | 2013-05-05 | 2013-06-02 | 0 | Yes | DUKHCONP1BZ1STUG1010, DUKHCONP1BZ1STUG1010 | DUKHCONP1BZ1STUG1020, DUKHCONP1BZ1STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ1STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-06-08 | 2013-07-06 | 2013-06-08 | 2013-07-06 | 0 | Yes | DUKHCONP1BZ1STUG1025, DUKHCONP1BZ1STUG1025 | DUKHCONP1BZ1STUG1035, DUKHCONP1BZ1STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L25.10 .10 .15 SUPERSTRUCTURE |  | 129 | 129 | 0% | 2013-08-21 | 2014-01-21 | 2013-08-21 | 2014-01-21 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.10 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-08-21 | 2013-10-15 | 2013-08-21 | 2013-10-15 | 0 |  |  |  | 0 | 0
DUKHCONP1BZ1STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-09-30 | 2013-10-15 | 2013-09-30 | 2013-10-15 | 0 | Yes | DUKHCONP1BZ1STGF2010, DUKHCONP1BZ1STGF2010 | DUKHCONP1BZ1STFF2020, DUKHCONP1BZ1ARGF3000, DUKHCONP1BZ1STFF2020, DUKHCONP1BZ2STGF2015, DUKHCONP1BZ1ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-09-14 | 2013-10-12 | 2013-09-14 | 2013-10-12 | 0 | Yes | DUKHCONP1BZ1STGF2005, DUKHENGP1BDWSTAP4430, DUKHCONP1BZ1STGF2005 | DUKHCONP1BZ1STGF2015, DUKHCONP1BZ1STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1STGF2005 | Column-Concrete | 23 | 23 | 0% | 2013-08-31 | 2013-09-25 | 2013-08-31 | 2013-09-25 | 0 | Yes | DUKHCONP1BZ1STGF2000, DUKHCONP1BZ1STGF2000 | DUKHCONP1BZ1STGF2010, DUKHCONP1BZ1STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-08-21 | 2013-09-18 | 2013-08-21 | 2013-09-18 | 0 | Yes | DUKHCONP1BZ1STUG1045, DUKHENGP1BDWSTAP4420, DUKHCONP1BZ1STUG1045 | DUKHCONP1BZ1STGF2005, DUKHCONP1BZ2STGF2000, DUKHCONP1BZ1STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.10 .10 .15 .15 FIRST FLOORS |  | 48 | 48 | 0% | 2013-10-02 | 2013-11-28 | 2013-10-02 | 2013-11-28 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ1STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-11-13 | 2013-11-28 | 2013-11-13 | 2013-11-28 | 3 | No | DUKHCONP1BZ1STFF2030, DUKHCONP1BZ1STFF2030 | DUKHCONP1BZ1STRF2040, DUKHCONP1BZ1ARFF3300, DUKHCONP1BZ1STRF2040, DUKHCONP1BZ2STFF2035, DUKHCONP1BZ1ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-10-28 | 2013-11-25 | 2013-10-28 | 2013-11-25 | 3 | No | DUKHCONP1BZ1STFF2025, DUKHCONP1BZ1STFF2025 | DUKHCONP1BZ1STFF2035, DUKHCONP1BZ1STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1STFF2025 | Column-Concrete | 23 | 23 | 0% | 2013-10-12 | 2013-11-09 | 2013-10-12 | 2013-11-09 | 3 | No | DUKHCONP1BZ1STFF2020, DUKHCONP1BZ1STFF2020 | DUKHCONP1BZ1STFF2030, DUKHCONP1BZ1STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-10-02 | 2013-11-02 | 2013-10-02 | 2013-11-02 | 0 | Yes | DUKHENGP1BDWSTAP4440, DUKHCONP1BZ1STGF2015, DUKHCONP1BZ1STGF2015 | DUKHCONP1BZ2STFF2020, DUKHCONP1BZ1STFF2025, DUKHCONP1BZ1ARFF3300, DUKHCONP1BZ1STFF2025, DUKHCONP1BZ1ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.10 .10 .15 .20 ROOF |  | 54 | 54 | 0% | 2013-11-19 | 2014-01-21 | 2013-11-19 | 2014-01-21 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ1STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-11-23 | 2013-12-11 | 2013-11-23 | 2013-12-11 | 21 | No | DUKHCONP1BZ1STRF2040, DUKHCONP1BZ1STRF2040 | DUKHCONP1BZ1STRF2050, DUKHCONP1BZ1STRF2050 | 0 | 0 | ROOF
DUKHCONP1BZ1STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-11-19 | 2013-12-09 | 2013-11-19 | 2013-12-09 | 21 | No | DUKHCONP1BZ1STFF2035, DUKHCONP1BZ1STFF2035 | DUKHCONP1BZ1STRF2045, DUKHCONP1BZ1STRF2045, DUKHCONP1BZ2STRF2040 | 0 | 0 | ROOF
DUKHCONP1BZ1STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-12-11 | 2014-01-09 | 2013-12-11 | 2014-01-09 | 51 | No | DUKHCONP1BZ1STRF2055, DUKHCONP1BZ1STRF2055 | DUKHCONP1BZ1WEEX5030, DUKHCONP1BZ1ARRF3630, DUKHCONP1BZ1STRF2065, DUKHCONP1BZ1STRF2065, DUKHCONP1BZ1WEEX5030, DUKHCONP1BZ1ARRF3630 | 0 | 0 | ROOF
DUKHCONP1BZ1STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 78 | No | DUKHCONP1BZ1STRF2060, DUKHCONP1BZ1STRF2060 | DUKHCONP1BZ1ARRF3630, DUKHCONP1BZ1ARRF3630, DUKHCONP1BZ2STRF2065, DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1AREL3665 | 0 | 0 | ROOF
DUKHCONP1BZ1STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2013-12-09 | 2013-12-24 | 2013-12-09 | 2013-12-24 | 21 | No | DUKHCONP1BZ1STRF2050, DUKHCONP1BZ1STRF2050 | DUKHCONP1BZ1STRF2060, DUKHCONP1BZ1MSEX5020, DUKHCONP1BZ1ARRF3600, DUKHCONP1BZ1MSEX5020, DUKHCONP1BZ2STRF2055, DUKHCONP1BZ1MSEX5000, DUKHCONP1BZ1ARRF3600, DUKHCONP1BZ1STRF2060, DUKHCONP1BZ1MSEX5000 | 0 | 0 | ROOF
DUKHCONP1BZ1STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2013-11-25 | 2013-12-17 | 2013-11-25 | 2013-12-17 | 21 | No | DUKHCONP1BZ1STRF2045, DUKHCONP1BZ1STRF2045 | DUKHCONP1BZ1STRF2055, DUKHCONP1BZ1STRF2055 | 0 | 0 | ROOF
DHBL.K30.L25.10 .15 FINISHING WORKS |  | 195 | 195 | 0% | 2013-10-27 | 2014-06-12 | 2013-10-27 | 2014-06-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.10 .15 .10 INTERNAL FINISHES |  | 195 | 195 | 0% | 2013-10-27 | 2014-06-12 | 2013-10-27 | 2014-06-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.10 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-10-27 | 2014-04-09 | 2013-10-27 | 2014-04-09 | 58 |  |  |  | 0 | 0
DUKHCONP1BZ1ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-02-12 | 2014-03-01 | 2014-02-12 | 2014-03-01 | 58 | No | DUKHCONP1BZ1ARGF3065, DUKHCONP1BZ1ARGF3065 | DUKHCONP1BZ1ARGF3080, DUKHCONP1BZ1ARGF3075, DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ1ARGF3075, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 53 | No | DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ARGF3045 | DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ1ELGF4020, DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ1ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-02-19 | 2014-03-13 | 2014-02-19 | 2014-03-13 | 68 | No | DUKHCONP1BZ1ARGF3070, DUKHCONP1BZ1ARGF3070 | DUKHCONP1BZ2ARGF3080, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3000 | Block work | 25 | 25 | 0% | 2013-10-27 | 2013-11-24 | 2013-10-27 | 2013-11-24 | 44 | No | DUKHCONP1BZ1STGF2015, DUKHCONP1BZ1STGF2015 | DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1ELGF4000, DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ1PLGF4305, DUKHCONP1BZ1ELGF4000, DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1PLGF4305 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 58 | No | DUKHCONP1BZ1ARGF3070, DUKHCONP1BZ1ARGF3070 | DUKHCONP1BZ1ARGF3085, DUKHCONP1BZ2ARGF3075, DUKHCONP1BZ1ARGF3085, DUKHCONP1BZ1ARGF3090, DUKHCONP1BZ1ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-12-11 | 2014-01-09 | 2013-12-11 | 2014-01-09 | 50 | No | DUKHCONP1BZ1PLGF4305, DUKHCONP1BZ1ARGF3015, DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1ARGF3015, DUKHCONP1BZ1PLGF4305, DUKHCONP1BZ1PLGF4310 | DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ2ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-01-14 | 2014-01-30 | 2014-01-14 | 2014-01-30 | 58 | No | DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3010, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3010, DUKHCONP1BZ1ARGF3025 | DUKHCONP1BZ1ARGF3050, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-03-12 | 2014-04-09 | 2014-03-12 | 2014-04-09 | 58 | No | DUKHCONP1BZ1ARGF3030, DUKHCONP1BZ1ARGF3090, DUKHCONP1BZ1ACGF4610, DUKHCONP1BZ1ARGF3085, DUKHCONP1BZ1ARGF3040, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3080, DUKHCONP1BZ1ARGF3090, DUKHCONP1BZ1ACGF4610, DUKHCONP1BZ1ARGF3040, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3030, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3070, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3070, DUKHCONP1BZ1ARGF3080, DUKHCONP1BZ1ARGF3085 | DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-01-05 | 2014-01-27 | 2014-01-05 | 2014-01-27 | 50 | No | DUKHCONP1BZ1ELGF4010, DUKHCONP1BZ1ARGF3030, DUKHCONP1BZ1ARGF3030, DUKHCONP1BZ1ELGF4010, DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3025 | DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ1ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-11-26 | 2013-12-21 | 2013-11-26 | 2013-12-21 | 58 | No | DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1ARGF3005 | DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3040, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-01-22 | 2014-02-15 | 2014-01-22 | 2014-02-15 | 58 | No | DUKHCONP1BZ1ARGF3040, DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3040 | DUKHCONP1BZ1ARGF3065, DUKHCONP1BZ1ARGF3065, DUKHCONP1BZ1ARGF3085, DUKHCONP1BZ1ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 50 | No | DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ACGF4600 | DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ1ELGF4030, DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ1ELGF4030, DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1ELGF4020, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1PLGF4320, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ1PLGF4320, DUKHCONP1BZ1ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-03-03 | 2014-03-19 | 2014-03-03 | 2014-03-19 | 58 | No | DUKHCONP1BZ1ARGF3075, DUKHCONP1BZ1ARGF3075 | DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-12-04 | 2014-01-02 | 2013-12-04 | 2014-01-02 | 64 | No | DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1ARGF3005 | DUKHCONP1BZ2ARGF3030, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-11-18 | 2013-12-16 | 2013-11-18 | 2013-12-16 | 50 | No | DUKHCONP1BZ1ELGF4000, DUKHCONP1BZ1ARGF3000, DUKHCONP1BZ1ELGF4000, DUKHCONP1BZ1PLGF4305, DUKHCONP1BZ1PLGF4305, DUKHCONP1BZ1ARGF3000 | DUKHCONP1BZ1ARGF3015, DUKHCONP1BZ1ARGF3030, DUKHCONP1BZ1ARGF3010, DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ARGF3030, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ1ARGF3015, DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 50 | No | DUKHCONP1BZ1ARGF3010, DUKHCONP1BZ1ARGF3020, DUKHCONP1BZ1ARGF3020, DUKHCONP1BZ1ARGF3010 | DUKHCONP1BZ1ARGF3050, DUKHCONP1BZ1ARGF3050, DUKHCONP1BZ1ARGF3040, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 63 | No | DUKHCONP1BZ1ARGF3075, DUKHCONP1BZ1ARGF3075, DUKHCONP1BZ1ARGF3050, DUKHCONP1BZ1ARGF3050 | DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-01-07 | 2014-01-23 | 2014-01-07 | 2014-01-23 | 60 | No | DUKHCONP1BZ1ARGF3010, DUKHCONP1BZ1ARGF3010, DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ1ARGF3025 | DUKHCONP1BZ1ARGF3065, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3040, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARGF3040, DUKHCONP1BZ1ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-12-05 | 2013-12-23 | 2013-12-05 | 2013-12-23 | 50 | No | DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1ARGF3005 | DUKHCONP1BZ1ARGF3020, DUKHCONP1BZ1ARGF3020, DUKHCONP1BZ2ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-02-05 | 2014-02-23 | 2014-02-05 | 2014-02-23 | 58 | No | DUKHCONP1BZ1ARGF3035, DUKHCONP1BZ1ARGF3050, DUKHCONP1BZ1ARGF3050, DUKHCONP1BZ1ARGF3035 | DUKHCONP1BZ1ARGF3070, DUKHCONP1BZ1PLGF4315, DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ1ARGF3070, DUKHCONP1BZ1PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.10 .15 .10 .15 FIRST FLOORS |  | 159 | 159 | 0% | 2013-12-08 | 2014-06-12 | 2013-12-08 | 2014-06-12 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ1ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-04-12 | 2014-05-04 | 2014-04-12 | 2014-05-04 | 3 | No | DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ARFF3365 | DUKHCONP1BZ2ARFF3370, DUKHCONP1BZ1ARFF3375, DUKHCONP1BZ1ARFF3375, DUKHCONP1BZ1ARFF3380, DUKHCONP1BZ1ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-04-19 | 2014-05-11 | 2014-04-19 | 2014-05-11 | 16 | No | DUKHCONP1BZ1ARFF3370, DUKHCONP1BZ1ARFF3370 | DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3300 | Block work | 25 | 25 | 0% | 2013-12-08 | 2014-01-06 | 2013-12-08 | 2014-01-06 | 3 | No | DUKHCONP1BZ1STFF2035, DUKHCONP1BZ1STFF2020, DUKHCONP1BZ1STFF2020, DUKHCONP1BZ1STFF2035 | DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1ELFF4035, DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ELFF4035, DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ2ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 3 | No | DUKHCONP1BZ1ARFF3370, DUKHCONP1BZ1ARFF3370 | DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3385, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3390, DUKHCONP1BZ1ARFF3390, DUKHCONP1BZ1ARFF3385, DUKHCONP1BZ2ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-02-04 | 2014-03-05 | 2014-02-04 | 2014-03-05 | 3 | No | DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1ARFF3315, DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1ARFF3315, DUKHCONP1BZ1PLFF4330 | DUKHCONP1BZ1ARFF3325, DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ1ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 3 | No | DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3350, DUKHCONP1BZ1ARFF3375, DUKHCONP1BZ1ARFF3390, DUKHCONP1BZ1ARFF3330, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ARFF3380, DUKHCONP1BZ1ARFF3385, DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ1ARFF3330, DUKHCONP1BZ1ARFF3375, DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3380, DUKHCONP1BZ1ARFF3390, DUKHCONP1BZ1ARFF3385, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ1ARFF3350, DUKHCONP1BZ1ARFF3360 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ1ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 3 | No | DUKHCONP1BZ1ARFF3330, DUKHCONP1BZ1ARFF3325, DUKHCONP1BZ1ELFF4045, DUKHCONP1BZ1ELFF4045, DUKHCONP1BZ1ARFF3325, DUKHCONP1BZ1ARFF3330 | DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-01-13 | 2014-02-05 | 2014-01-13 | 2014-02-05 | 20 | No | DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ARFF3305 | DUKHCONP1BZ1ARFF3325, DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 14 | No | DUKHCONP1BZ1ARFF3325, DUKHCONP1BZ1ARFF3325 | DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ARFF3385, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3385, DUKHCONP1BZ1ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 3 | No | DUKHCONP1BZ1ARFF3345, DUKHCONP1BZ1ACFF4615, DUKHCONP1BZ1ACFF4615, DUKHCONP1BZ1ARFF3345 | DUKHCONP1BZ1ELFF4050, DUKHCONP1BZ1ELFF4060, DUKHCONP1BZ1ELFF4060, DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ1PLFF4340, DUKHCONP1BZ1ACFF4620, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ELFF4050, DUKHCONP1BZ1ELFF4055, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1PLFF4340, DUKHCONP1BZ1ACFF4620, DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ELFF4055, DUKHCONP1BZ2ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-05-04 | 2014-05-26 | 2014-05-04 | 2014-05-26 | 3 | No | DUKHCONP1BZ1ARFF3375, DUKHCONP1BZ1ARFF3350, DUKHCONP1BZ1ARFF3350, DUKHCONP1BZ1ARFF3375 | DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-05-04 | 2014-05-26 | 2014-05-04 | 2014-05-26 | 5 | No | DUKHCONP1BZ1ARFF3375, DUKHCONP1BZ1ARFF3375 | DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 29 | No | DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ARFF3305 | DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3345, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 3 | No | DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1ELFF4035, DUKHCONP1BZ1ELFF4035, DUKHCONP1BZ1ARFF3300, DUKHCONP1BZ1ARFF3300 | DUKHCONP1BZ1ACFF4615, DUKHCONP1BZ1ACFF4615, DUKHCONP1BZ1ARFF3330, DUKHCONP1BZ1ARFF3315, DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1ARFF3310, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1ARFF3315, DUKHCONP1BZ1ARFF3330, DUKHCONP1BZ1ARFF3310 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 3 | No | DUKHCONP1BZ1ARFF3310, DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ1ARFF3310, DUKHCONP1BZ1ARFF3320 | DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3345, DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3350, DUKHCONP1BZ1ARFF3350, DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ1ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-03-04 | 2014-03-20 | 2014-03-04 | 2014-03-20 | 22 | No | DUKHCONP1BZ1ARFF3325, DUKHCONP1BZ1ARFF3310, DUKHCONP1BZ1ARFF3325, DUKHCONP1BZ1ARFF3310 | DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-01-26 | 2014-02-12 | 2014-01-26 | 2014-02-12 | 3 | No | DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ARFF3305 | DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ2ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-04-03 | 2014-04-20 | 2014-04-03 | 2014-04-20 | 3 | No | DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3350, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ARFF3335, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ARFF3350 | DUKHCONP1BZ1ARFF3370, DUKHCONP1BZ1PLFF4335, DUKHCONP1BZ1ARFF3370, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.10 .15 .10 .20 ROOF |  | 59 | 59 | 0% | 2014-01-04 | 2014-03-13 | 2014-01-04 | 2014-03-13 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ1ARRF3600 | Block work | 20 | 20 | 0% | 2014-01-04 | 2014-01-26 | 2014-01-04 | 2014-01-26 | 75 | No | DUKHCONP1BZ1STRF2055, DUKHCONP1BZ1STRF2055 | DUKHCONP1BZ1ARRF3605, DUKHCONP1BZ1ARRF3605, DUKHCONP1BZ2ARRF3600 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-02-25 | 2014-03-13 | 2014-02-25 | 2014-03-13 | 81 | No | DUKHCONP1BZ1ARRF3695, DUKHCONP1BZ1ARRF3695 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1ACTC8000, DUKHCONP1BZ1PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-01-26 | 2014-02-12 | 2014-01-26 | 2014-02-12 | 81 | No | DUKHCONP1BZ1ARRF3605, DUKHCONP1BZ1ARRF3605 | DUKHCONP1BZ1ARRF3695, DUKHCONP1BZ1ARRF3695 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-02-06 | 2014-03-02 | 2014-02-06 | 2014-03-02 | 81 | No | DUKHCONP1BZ1ARRF3610, DUKHCONP1BZ1ARRF3610 | DUKHCONP1BZ1ARRF3620, DUKHCONP1BZ1AREL3680, DUKHCONP1BZ1AREL3680, DUKHCONP1BZ1ARRF3620 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-01-12 | 2014-02-03 | 2014-01-12 | 2014-02-03 | 75 | No | DUKHCONP1BZ1ARRF3600, DUKHCONP1BZ1ARRF3600 | DUKHCONP1BZ1ARRF3610, DUKHCONP1BZ1ARRF3610, DUKHCONP1BZ1PLRF4345, DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L25.10 .15 .15 EXTERNAL FINISHES |  | 63 | 63 | 0% | 2014-01-05 | 2014-03-19 | 2014-01-05 | 2014-03-19 | 76 |  |  |  | 0 | 0
DHBL.K30.L25.10 .15 .15 .10 ROOF |  | 58 | 58 | 0% | 2014-01-05 | 2014-03-13 | 2014-01-05 | 2014-03-13 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ1ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 78 | No | DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ARRF3645 | DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ1ARRF3655 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-02-25 | 2014-03-13 | 2014-02-25 | 2014-03-13 | 81 | No | DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ1ARRF3655 | DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 78 | No | DUKHCONP1BZ1ARRF3635, DUKHCONP1BZ1ARRF3635 | DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ARRF3645 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-02-10 | 2014-03-05 | 2014-02-10 | 2014-03-05 | 78 | No | DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ARRF3650, DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ARRF3650 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1PLRF4355, DUKHCONP1BZ1ARRF3660, DUKHCONP1BZ1ARRF3660, DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ1PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 78 | No | DUKHCONP1BZ1ARRF3630, DUKHCONP1BZ1ARRF3630 | DUKHCONP1BZ1ARRF3640, DUKHCONP1BZ1ARRF3640 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 78 | No | DUKHCONP1BZ1STRF2060, DUKHCONP1BZ1STRF2065, DUKHCONP1BZ1STRF2065, DUKHCONP1BZ1STRF2060 | DUKHCONP1BZ2ARRF3630, DUKHCONP1BZ1ARRF3635, DUKHCONP1BZ1ARRF3635 | 0 | 0 | ROOF
DUKHCONP1BZ1ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-01-18 | 2014-02-16 | 2014-01-18 | 2014-02-16 | 78 | No | DUKHCONP1BZ1ARRF3640, DUKHCONP1BZ1ARRF3640 | DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1ARRF3650, DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ1ARRF3650, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ1ELRF4070, DUKHCONP1BZ1ELRF4070 | 0 | 0 | ROOF
DHBL.K30.L25.10 .15 .15 .15 ELEVATION |  | 50 | 50 | 0% | 2014-01-20 | 2014-03-19 | 2014-01-20 | 2014-03-19 | 76 |  |  |  | 0 | 0
DUKHCONP1BZ1AREL3680 | External Painting | 20 | 20 | 0% | 2014-02-25 | 2014-03-19 | 2014-02-25 | 2014-03-19 | 76 | No | DUKHCONP1BZ1AREL3675, DUKHCONP1BZ1ARRF3695, DUKHCONP1BZ1AREL3670, DUKHCONP1BZ1AREL3670, DUKHCONP1BZ1AREL3675, DUKHCONP1BZ1ARRF3695 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ1ACTC8000, DUKHCONP1BZ2AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1BZ1AREL3665 | External Plastering | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 75 | No | DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1STRF2065, DUKHCONP1BZ1ARRF3605, DUKHCONP1BZ1STRF2065 | DUKHCONP1BZ1AREL3675, DUKHCONP1BZ1AREL3670, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ2AREL3665, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1AREL3675, DUKHCONP1BZ1AREL3670 | 0 | 0 | ELEVATION
DUKHCONP1BZ1AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-02-06 | 2014-03-02 | 2014-02-06 | 2014-03-02 | 76 | No | DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1AREL3665 | DUKHCONP1BZ2AREL3670, DUKHCONP1BZ1AREL3680, DUKHCONP1BZ1AREL3680, DUKHCONP1BZ1AREL3675 | 0 | 0 | ELEVATION
DUKHCONP1BZ1AREL3675 | GRC works | 20 | 20 | 0% | 2014-02-13 | 2014-03-08 | 2014-02-13 | 2014-03-08 | 76 | No | DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1AREL3670, DUKHCONP1BZ1AREL3665 | DUKHCONP1BZ1AREL3680, DUKHCONP1BZ2AREL3675, DUKHCONP1BZ1AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L25.10 .20 MEP WORKS |  | 272 | 272 | 0% | 2013-07-23 | 2014-06-12 | 2013-07-23 | 2014-06-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.10 .20 .10 ELECTRICAL WORKS |  | 190 | 190 | 0% | 2013-11-02 | 2014-06-12 | 2013-11-02 | 2014-06-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.10 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-11-02 | 2014-03-12 | 2013-11-02 | 2014-03-12 | 57 |  |  |  | 0 | 0
DUKHCONP1BZ1ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-11-13 | 2013-12-05 | 2013-11-13 | 2013-12-05 | 77 | No | DUKHCONP1BZ1ELGF4000, DUKHCONP1BZ1ELGF4000 | DUKHCONP1BZ1ELGF4010, DUKHCONP1BZ1ELGF4010, DUKHCONP1BZ2ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-11-02 | 2013-11-30 | 2013-11-02 | 2013-11-30 | 59 | No | DUKHCONP1BZ1ARGF3000, DUKHCONP1BZ1ARGF3000 | DUKHCONP1BZ1ELGF4005, DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 72 | No | DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ARGF3060 | DUKHCONP1BZ1ELFF4055, DUKHCONP1BZ1ELFF4055, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ2ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 50 | No | DUKHCONP1BZ1ELGF4010, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ELGF4010, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ARGF3060 | DUKHCONP1BZ1ELGF4030, DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 52 | No | DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ELGF4020, DUKHCONP1BZ1ELGF4020, DUKHCONP1BZ1ARGF3055 | DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ1ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-02-12 | 2014-03-06 | 2014-02-12 | 2014-03-06 | 50 | No | DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ELGF4020, DUKHCONP1BZ1ELGF4020 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1ELFF4050, DUKHCONP1BZ1ELFF4050, DUKHCONP1BZ2ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 77 | No | DUKHCONP1BZ1ELGF4005, DUKHCONP1BZ1ELGF4005 | DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ELGF4020, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ1ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.10 .20 .10 .15 FIRST FLOORS |  | 129 | 129 | 0% | 2013-12-14 | 2014-05-14 | 2013-12-14 | 2014-05-14 | 28 |  |  |  | 0 | 0
DUKHCONP1BZ1ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-26 | 2014-01-18 | 2013-12-26 | 2014-01-18 | 46 | No | DUKHCONP1BZ1ELFF4035, DUKHCONP1BZ1ELFF4035 | DUKHCONP1BZ1ELFF4045, DUKHCONP1BZ1ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 16 | No | DUKHCONP1BZ1ARFF3300, DUKHCONP1BZ1ARFF3300 | DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ELFF4040, DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 45 | No | DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ARFF3360 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ2ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-04-03 | 2014-04-26 | 2014-04-03 | 2014-04-26 | 3 | No | DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ELFF4045, DUKHCONP1BZ1ELFF4045 | DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ1ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 3 | No | DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ELFF4060, DUKHCONP1BZ1ELFF4060, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1ELGF4025 | DUKHCONP1BZ1ELRF4070, DUKHCONP1BZ1ELRF4070, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ2ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-03-25 | 2014-04-22 | 2014-03-25 | 2014-04-22 | 25 | No | DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1MSEX5010, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ELGF4030, DUKHCONP1BZ1ELGF4030 | DUKHCONP1BZ1ELRF4070, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-01-04 | 2014-02-01 | 2014-01-04 | 2014-02-01 | 46 | No | DUKHCONP1BZ1ELFF4040, DUKHCONP1BZ1ELFF4040 | DUKHCONP1BZ1ARFF3345, DUKHCONP1BZ1ELFF4060, DUKHCONP1BZ2ELFF4045, DUKHCONP1BZ1ARFF3345, DUKHCONP1BZ1ELFF4060, DUKHCONP1BZ1ELRF4070, DUKHCONP1BZ1ELRF4070 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.10 .20 .10 .20 ROOF |  | 33 | 33 | 0% | 2014-05-06 | 2014-06-12 | 2014-05-06 | 2014-06-12 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ1ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-05-06 | 2014-05-26 | 2014-05-06 | 2014-05-26 | 3 | No | DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ1ELFF4050, DUKHCONP1BZ1ELFF4045, DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ELFF4045, DUKHCONP1BZ1ELFF4050 | DUKHCONP1BZ1ELRF4075, DUKHCONP1BZ1ELRF4075 | 0 | 0 | ROOF
DUKHCONP1BZ1ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-05-18 | 2014-06-12 | 2014-05-18 | 2014-06-12 | 3 | No | DUKHCONP1BZ1ELRF4070, DUKHCONP1BZ1ELRF4070 | DUKHCONP1BZ1ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L25.10 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 256 | 256 | 0% | 2013-07-23 | 2014-05-25 | 2013-07-23 | 2014-05-25 | 19 |  |  |  | 0 | 0
DHBL.K30.L25.10 .20 .15 .10 GROUND FLOOR |  | 193 | 193 | 0% | 2013-07-23 | 2014-03-12 | 2013-07-23 | 2014-03-12 | 82 |  |  |  | 0 | 0
DUKHCONP1BZ1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-07-23 | 2013-08-18 | 2013-07-23 | 2013-08-18 | 0 | Yes | DUKHCONP1BZ1STUG1040, DUKHCONP1BZ1STUG1040 | DUKHCONP1BZ1STUG1045, DUKHCONP1BZ1STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-11-12 | 2013-12-02 | 2013-11-12 | 2013-12-02 | 44 | No | DUKHCONP1BZ1ARGF3000, DUKHCONP1BZ1ARGF3000, DUKHCONP1BZ1PLGF4305, DUKHCONP1BZ1PLGF4305 | DUKHCONP1BZ1MSEX5000, DUKHCONP1BZ1ARGF3020, DUKHCONP1BZ1PLGF4315, DUKHCONP1BZ1MSEX5000, DUKHCONP1BZ1PLGF4315, DUKHCONP1BZ1ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-11-12 | 2013-12-02 | 2013-11-12 | 2013-12-02 | 44 | No | DUKHCONP1BZ1ARGF3000, DUKHCONP1BZ1ARGF3000 | DUKHCONP1BZ1ARGF3020, DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ1ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-02-24 | 2014-03-12 | 2014-02-24 | 2014-03-12 | 82 | No | DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1PLGF4315, DUKHCONP1BZ1PLGF4315, DUKHCONP1BZ1ARGF3060 | DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ2PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-02-12 | 2014-03-06 | 2014-02-12 | 2014-03-06 | 82 | No | DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1ARGF3065, DUKHCONP1BZ1ARGF3065 | DUKHCONP1BZ2PLGF4315, DUKHCONP1BZ1PLGF4320, DUKHCONP1BZ1PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.10 .20 .15 .15 FIRST FLOORS |  | 113 | 113 | 0% | 2013-12-26 | 2014-05-07 | 2013-12-26 | 2014-05-07 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ1PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2013-12-26 | 2014-01-15 | 2013-12-26 | 2014-01-15 | 30 | No | DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1ARFF3300, DUKHCONP1BZ1PLFF4325, DUKHCONP1BZ1ARFF3300 | DUKHCONP1BZ1PLFF4335, DUKHCONP1BZ1PLFF4335, DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ2PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-12-26 | 2014-01-15 | 2013-12-26 | 2014-01-15 | 3 | No | DUKHCONP1BZ1ARFF3300, DUKHCONP1BZ1ARFF3300 | DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ1PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-04-21 | 2014-05-07 | 2014-04-21 | 2014-05-07 | 19 | No | DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1PLFF4335, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1PLFF4335 | DUKHCONP1BZ1PLRF4355, DUKHCONP1BZ2PLFF4340, DUKHCONP1BZ1PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-04-09 | 2014-05-01 | 2014-04-09 | 2014-05-01 | 19 | No | DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ1ARFF3365 | DUKHCONP1BZ1PLFF4340, DUKHCONP1BZ1PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.10 .20 .15 .20 ROOF |  | 100 | 100 | 0% | 2014-01-28 | 2014-05-25 | 2014-01-28 | 2014-05-25 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ1PLRF4345 | Installation of Plumbing pipes & fittings | 14 | 14 | 0% | 2014-01-28 | 2014-02-13 | 2014-01-28 | 2014-02-13 | 81 | No | DUKHCONP1BZ1ARRF3605, DUKHCONP1BZ1ARRF3605 | DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1PLRF4355, DUKHCONP1BZ1PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ1PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-02-09 | 2014-02-26 | 2014-02-09 | 2014-02-26 | 79 | No | DUKHCONP1BZ1PLRF4345, DUKHCONP1BZ1PLRF4345, DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1PLFF4330, DUKHCONP1BZ1AREL3665, DUKHCONP1BZ1ARRF3645 | DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ1PLRF4355, DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ1PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ1PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 19 | No | DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ1PLFF4340, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ1PLRF4345, DUKHCONP1BZ1PLFF4340, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1PLRF4345, DUKHCONP1BZ1ARRF3655 | DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ1PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L25.10 .20 .20 AC WORKS |  | 145 | 145 | 0% | 2013-12-02 | 2014-05-21 | 2013-12-02 | 2014-05-21 | 22 |  |  |  | 0 | 0
DHBL.K30.L25.10 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-12-02 | 2014-03-10 | 2013-12-02 | 2014-03-10 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ1ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 69 | No | DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ1ACGF4605 | DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ACRF4635, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ACRF4635, DUKHCONP1BZ2ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 69 | No | DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ARGF3055 | DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ1ACGF4610, DUKHCONP1BZ1ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ1ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-12-02 | 2013-12-25 | 2013-12-02 | 2013-12-25 | 81 | No | DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ1ARGF3005 | DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ1ARGF3055, DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ2ACGF4600 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.10 .20 .20 .15 FIRST FLOORS |  | 95 | 95 | 0% | 2014-01-19 | 2014-05-10 | 2014-01-19 | 2014-05-10 | 17 |  |  |  | 0 | 0
DUKHCONP1BZ1ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-04-17 | 2014-05-10 | 2014-04-17 | 2014-05-10 | 17 | No | DUKHCONP1BZ1ACFF4620, DUKHCONP1BZ1ACFF4620 | DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ1ACRF4635, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ACRF4635, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 17 | No | DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ACFF4615, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ACFF4615 | DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ2ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ1ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 46 | No | DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ1ARFF3305 | DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ1ACFF4620, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ARFF3360, DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ1ACFF4620 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.10 .20 .20 .20 ROOF |  | 95 | 95 | 0% | 2014-01-30 | 2014-05-21 | 2014-01-30 | 2014-05-21 | 22 |  |  |  | 0 | 0
DUKHCONP1BZ1ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 22 | No | DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ1ACGF4610, DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ1ACGF4610, DUKHCONP1BZ1ACRF4630 | DUKHCONP1BZ1ACTC8000, DUKHCONP1BZ2ACRF4635 | 0 | 0 | ROOF
DUKHCONP1BZ1ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 87 | No | DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ACGF4600, DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ACFF4615, DUKHCONP1BZ1ARRF3645, DUKHCONP1BZ1ACFF4615 | DUKHCONP1BZ1ACRF4635, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ1ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L25.10 .25 EXTERNAL WORKS |  | 161 | 161 | 0% | 2013-12-09 | 2014-06-16 | 2013-12-09 | 2014-06-16 | 25 |  |  |  | 0 | 0
DHBL.K30.L25.10 .25 .10 MISCELLANEOUS |  | 161 | 161 | 0% | 2013-12-09 | 2014-06-16 | 2013-12-09 | 2014-06-16 | 25 |  |  |  | 0 | 0
DUKHCONP1BZ1MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 25 | No | DUKHCONI1BZ1BWGL5325 | DUKHCONP1BZ2MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ1MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 30 | No | DUKHCONP1BZ1MSEX5000, DUKHCONP1BZ1MSEX5000 | DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ1MSEX5015, DUKHCONP1BZ1ACTC8000, DUKHCONP1BZ1MSEX5015, DUKHCONP1BZ1ELTC8010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ1MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2013-12-09 | 2014-01-07 | 2013-12-09 | 2014-01-07 | 69 | No | DUKHCONP1BZ1STRF2055, DUKHCONP1BZ1STRF2055 | DUKHCONP1BZ1MSEX5025, DUKHCONP1BZ1MSEX5025, DUKHCONP1BZ1HDEX5090, DUKHCONP1BZ1HDEX5090, DUKHCONP1BZ2MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ1MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-01-25 | 2014-02-17 | 2014-01-25 | 2014-02-17 | 30 | No | DUKHCONP1BZ1MSEX5005, DUKHCONP1BZ1MSEX5005 | DUKHCONP1BZ1MSEX5010, DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ1WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ1MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 21 | No | DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1PLGF4310, DUKHCONP1BZ1STRF2055, DUKHCONP1BZ1STRF2055 | DUKHCONP1BZ1MSEX5005, DUKHMOBP1BPS00002100, DUKHCONP1BZ1MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ1MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2013-12-30 | 2014-01-21 | 2013-12-30 | 2014-01-21 | 69 | No | DUKHCONP1BZ1MSEX5020, DUKHCONP1BZ1MSEX5020 | DUKHCONP1BZ1WEEX5050, DUKHCONP1BZ1HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ1MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 30 | No | DUKHCONP1BZ1MSEX5015 | DUKHCONP1BZ1ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L25.10 .25 .15 WATER TANK ENCLOSURE |  | 78 | 78 | 0% | 2013-12-24 | 2014-03-25 | 2013-12-24 | 2014-03-25 | 71 |  |  |  | 0 | 0
DUKHCONP1BZ1WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 71 | No | DUKHCONP1BZ1WEEX5035, DUKHCONP1BZ1WEEX5035 | DUKHCONP1BZ1WEEX5045, DUKHCONP1BZ1WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ1WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 71 | No | DUKHCONP1BZ1WEEX5030, DUKHCONP1BZ1WEEX5030 | DUKHCONP1BZ1WEEX5040, DUKHCONP1BZ1WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ1WEEX5030 | Excavation | 20 | 20 | 0% | 2013-12-24 | 2014-01-15 | 2013-12-24 | 2014-01-15 | 51 | No | DUKHCONP1BZ1STRF2060, DUKHCONP1BZ1STRF2060 | DUKHCONP1BZ1WEEX5035, DUKHCONP1BZ1WEEX5035, DUKHCONP1BZ2WEEX5030 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ1WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 71 | No | DUKHCONP1BZ1WEEX5040, DUKHCONP1BZ1WEEX5040 | DUKHCONP1BZ1WEEX5050, DUKHCONP1BZ1WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ1WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 71 | No | DUKHCONP1BZ1WEEX5060, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1MSEX5015, DUKHCONP1BZ1WEEX5060, DUKHCONP1BZ1MSEX5015 | DUKHCONP1BZ1PLRF4355, DUKHCONP1BZ2WEEX5065, DUKHCONP1BZ1PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ1WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-02-06 | 2014-03-02 | 2014-02-06 | 2014-03-02 | 71 | No | DUKHCONP1BZ1WEEX5045, DUKHCONP1BZ1WEEX5045, DUKHCONP1BZ1MSEX5025 | DUKHCONP1BZ1WEEX5060, DUKHCONP1BZ1WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ1WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 71 | No | DUKHCONP1BZ1WEEX5050, DUKHCONP1BZ1WEEX5050 | DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ2WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L25.10 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2014-01-07 | 2014-02-26 | 2014-01-07 | 2014-02-26 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ1HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 69 | No | DUKHCONP1BZ1HDEX5090, DUKHCONP1BZ1HDEX5090 | DUKHCONP1BZ1HDEX5100, DUKHCONP1BZ1HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ1HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-02-03 | 2014-02-26 | 2014-02-03 | 2014-02-26 | 69 | No | DUKHCONP1BZ1HDEX5095, DUKHCONP1BZ1HDEX5095 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1SLEX5105, DUKHCONP1BZ1SLEX5105, DUKHCONP1BZ1ACTC8000, DUKHCONP1BZ1PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ1HDEX5090 | kerb works | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 69 | No | DUKHCONP1BZ1MSEX5020, DUKHCONP1BZ1MSEX5020, DUKHCONP1BZ1MSEX5025 | DUKHCONP1BZ1HDEX5095, DUKHCONP1BZ1HDEX5095, DUKHCONP1BZ2HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L25.10 .25 .25 SOFT LANDSCAPING |  | 35 | 35 | 0% | 2014-02-16 | 2014-03-27 | 2014-02-16 | 2014-03-27 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ1SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 69 | No | DUKHCONP1BZ1HDEX5100, DUKHCONP1BZ1HDEX5100 | DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1SLEX5110, DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ1ACTC8000, DUKHCONP1BZ1SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1BZ1SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 69 | No | DUKHCONP1BZ1SLEX5105, DUKHCONP1BZ1SLEX5105 | DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L25.10 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ1ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 3 | No | DUKHCONP1BZ1ARRF3620, DUKHCONP1BZ1ACRF4635, DUKHCONP1BZ1SLEX5105, DUKHCONP1BZ1MSEX5005, DUKHCONP1BZ1HDEX5100, DUKHCONP1BZ1AREL3680, DUKHCONP1BZ1ARRF3660, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ1SLEX5110 | DUKHCONP1BZ2ACTC8000, DUKHHANP1BGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 3 | No | DUKHCONP1BZ1HDEX5100, DUKHCONP1BZ1SLEX5105, DUKHCONP1BZ1AREL3680, DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ELFF4055, DUKHCONP1BZ1ARRF3620, DUKHCONP1BZ1ELFF4065, DUKHCONP1BZ1ELGF4030, DUKHCONP1BZ1ELRF4075, DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1ARRF3660, DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ1SLEX5110, DUKHCONP1BZ1ELFF4050, DUKHCONP1BZ1MSEX5005 | DUKHCONP1BZ2ELTC8010, DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 3 | No | DUKHCONP1BZ1SLEX5105, DUKHCONP1BZ1AREL3680, DUKHCONP1BZ1ARRF3660, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ1MSEX5005, DUKHCONP1BZ1SLEX5110, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ1ARRF3620, DUKHCONP1BZ1PLGF4320, DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ1PLRF4355, DUKHCONP1BZ1HDEX5100 | DUKHHANP1BGNPLTC9005, DUKHCONP1BZ2PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L25.15 ZONE - 2 (4 Twin Villas) |  | 383 | 383 | 0% | 2013-05-13 | 2014-08-13 | 2013-05-13 | 2014-08-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.15 .10 STRUCTURAL WORKS |  | 237 | 237 | 0% | 2013-05-13 | 2014-02-20 | 2013-05-13 | 2014-02-20 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.15 .10 .10 SUB STRUCTURE |  | 119 | 119 | 0% | 2013-05-13 | 2013-10-01 | 2013-05-13 | 2013-10-01 | 0 |  |  |  | 0 | 0
DHBL.K30.L25.15 .10 .10 .10 UPTO GRADE SLAB |  | 119 | 119 | 0% | 2013-05-13 | 2013-10-01 | 2013-05-13 | 2013-10-01 | 0 |  |  |  | 0 | 0
DUKHCONP1BZ2STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-07-18 | 2013-08-19 | 2013-07-18 | 2013-08-19 | 0 | Yes | DUKHCONP1BZ2STUG1030, DUKHCONP1BZ2STUG1030, DUKHCONP1BZ1STUG1035 | DUKHCONP1BZ3STUG1035, DUKHCONP1BZ2STUG1040, DUKHCONP1BZ2STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-06-18 | 2013-07-10 | 2013-06-18 | 2013-07-10 | 0 | Yes | DUKHCONP1BZ2STUG1015, DUKHCONP1BZ2STUG1015 | DUKHCONP1BZ2STUG1025, DUKHCONP1BZ2STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-08-04 | 2013-09-04 | 2013-08-04 | 2013-09-04 | 0 | Yes | DUKHCONP1BZ2STUG1035, DUKHCONP1BZ2STUG1035 | DUKHCONP1BZ2STUG1045, DUKHCONP1BZ2STUG1045, DUKHCONP1BZ2PLUG4300, DUKHCONP1BZ2PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-06-27 | 2013-07-25 | 2013-06-27 | 2013-07-25 | 0 | Yes | DUKHCONP1BZ2STUG1020, DUKHCONP1BZ1STUG1025, DUKHCONP1BZ2STUG1020 | DUKHCONP1BZ3STUG1025, DUKHCONP1BZ2STUG1030, DUKHCONP1BZ2STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-09-03 | 2013-10-01 | 2013-09-03 | 2013-10-01 | 0 | Yes | DUKHCONP1BZ2STUG1040, DUKHCONP1BZ2STUG1040, DUKHCONP1BZ2PLUG4300, DUKHCONP1BZ1STUG1045, DUKHCONP1BZ2PLUG4300 | DUKHCONP1BZ2STGF2000, DUKHCONP1BZ2STGF2000, DUKHCONP1BZ3STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-05-25 | 2013-06-19 | 2013-05-25 | 2013-06-19 | 0 | Yes | DUKHCONP1BZ2STUG1000, DUKHCONP1BZ2STUG1000 | DUKHCONP1BZ2STUG1010, DUKHCONP1BZ2STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-05-28 | 2013-06-23 | 2013-05-28 | 2013-06-23 | 0 | Yes | DUKHCONP1BZ2STUG1005, DUKHCONP1BZ2STUG1005 | DUKHCONP1BZ2STUG1015, DUKHCONP1BZ2STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-05-13 | 2013-06-10 | 2013-05-13 | 2013-06-10 | 0 | Yes | DUKHCONP1BZ1STUG1000 | DUKHCONP1BZ3STUG1000, DUKHCONP1BZ2STUG1005, DUKHCONP1BZ2STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-06-03 | 2013-07-01 | 2013-06-03 | 2013-07-01 | 0 | Yes | DUKHCONP1BZ2STUG1010, DUKHCONP1BZ2STUG1010 | DUKHCONP1BZ2STUG1020, DUKHCONP1BZ2STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ2STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-07-07 | 2013-08-04 | 2013-07-07 | 2013-08-04 | 0 | Yes | DUKHCONP1BZ2STUG1025, DUKHCONP1BZ2STUG1025 | DUKHCONP1BZ2STUG1035, DUKHCONP1BZ2STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L25.15 .10 .15 SUPERSTRUCTURE |  | 129 | 129 | 0% | 2013-09-19 | 2014-02-20 | 2013-09-19 | 2014-02-20 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.15 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-09-19 | 2013-11-16 | 2013-09-19 | 2013-11-16 | 0 |  |  |  | 0 | 0
DUKHCONP1BZ2STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-10-31 | 2013-11-16 | 2013-10-31 | 2013-11-16 | 0 | Yes | DUKHCONP1BZ2STGF2010, DUKHCONP1BZ2STGF2010, DUKHCONP1BZ1STGF2015 | DUKHCONP1BZ2STFF2020, DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ3STGF2015, DUKHCONP1BZ2STFF2020, DUKHCONP1BZ2ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-10-13 | 2013-11-12 | 2013-10-13 | 2013-11-12 | 0 | Yes | DUKHCONP1BZ2STGF2005, DUKHCONP1BZ2STGF2005 | DUKHCONP1BZ2STGF2015, DUKHCONP1BZ2STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2STGF2005 | Column-Concrete | 23 | 23 | 0% | 2013-09-29 | 2013-10-27 | 2013-09-29 | 2013-10-27 | 0 | Yes | DUKHCONP1BZ2STGF2000, DUKHCONP1BZ2STGF2000 | DUKHCONP1BZ2STGF2010, DUKHCONP1BZ2STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-09-19 | 2013-10-20 | 2013-09-19 | 2013-10-20 | 0 | Yes | DUKHCONP1BZ2STUG1045, DUKHCONP1BZ1STGF2000, DUKHCONP1BZ2STUG1045 | DUKHCONP1BZ3STGF2000, DUKHCONP1BZ2STGF2005, DUKHCONP1BZ2STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.15 .10 .15 .15 FIRST FLOORS |  | 39 | 39 | 0% | 2013-11-03 | 2013-12-17 | 2013-11-03 | 2013-12-17 | 12 |  |  |  | 0 | 0
DUKHCONP1BZ2STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-12-02 | 2013-12-17 | 2013-12-02 | 2013-12-17 | 12 | No | DUKHCONP1BZ2STFF2030, DUKHCONP1BZ2STFF2030, DUKHCONP1BZ1STFF2035 | DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ2STRF2040, DUKHCONP1BZ3STFF2035, DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ2STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 12 | No | DUKHCONP1BZ2STFF2025, DUKHCONP1BZ2STFF2025 | DUKHCONP1BZ2STFF2035, DUKHCONP1BZ2STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2STFF2025 | Column-Concrete | 23 | 23 | 0% | 2013-11-12 | 2013-12-08 | 2013-11-12 | 2013-12-08 | 0 | Yes | DUKHCONP1BZ2STFF2020, DUKHCONP1BZ2STFF2020 | DUKHCONI1BZ1DRGL5115, DUKHCONP1BZ2STFF2030, DUKHCONP1BZ2STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-11-03 | 2013-12-01 | 2013-11-03 | 2013-12-01 | 0 | Yes | DUKHCONP1BZ1STFF2020, DUKHCONP1BZ2STGF2015, DUKHCONP1BZ2STGF2015 | DUKHCONP1BZ3STFF2020, DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ2STFF2025, DUKHCONP1BZ2STFF2025, DUKHCONP1BZ2ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.15 .10 .15 .20 ROOF |  | 61 | 61 | 0% | 2013-12-10 | 2014-02-20 | 2013-12-10 | 2014-02-20 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ2STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-12-14 | 2014-01-02 | 2013-12-14 | 2014-01-02 | 37 | No | DUKHCONP1BZ2STRF2040, DUKHCONP1BZ2STRF2040 | DUKHCONP1BZ2STRF2050, DUKHCONP1BZ2STRF2050 | 0 | 0 | ROOF
DUKHCONP1BZ2STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-12-10 | 2013-12-31 | 2013-12-10 | 2013-12-31 | 37 | No | DUKHCONP1BZ2STFF2035, DUKHCONP1BZ1STRF2040, DUKHCONP1BZ2STFF2035 | DUKHCONP1BZ3STRF2040, DUKHCONP1BZ2STRF2045, DUKHCONP1BZ2STRF2045 | 0 | 0 | ROOF
DUKHCONP1BZ2STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 61 | No | DUKHCONP1BZ2STRF2055, DUKHCONP1BZ2STRF2055 | DUKHCONP1BZ2ARRF3630, DUKHCONP1BZ2STRF2065, DUKHCONP1BZ3STRF2060, DUKHCONP1BZ2STRF2065, DUKHCONP1BZ2ARRF3630 | 0 | 0 | ROOF
DUKHCONP1BZ2STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 78 | No | DUKHCONP1BZ1STRF2065, DUKHCONP1BZ2STRF2060, DUKHCONP1BZ2STRF2060 | DUKHCONP1BZ2AREL3665, DUKHCONP1BZ2ARRF3630, DUKHCONP1BZ2AREL3665, DUKHCONP1BZ3STRF2065, DUKHCONP1BZ2ARRF3630 | 0 | 0 | ROOF
DUKHCONP1BZ2STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2013-12-31 | 2014-01-14 | 2013-12-31 | 2014-01-14 | 37 | No | DUKHCONP1BZ1STRF2055, DUKHCONP1BZ2STRF2050, DUKHCONP1BZ2STRF2050 | DUKHCONP1BZ2ARRF3600, DUKHCONP1BZ3STRF2055, DUKHCONP1BZ2WEEX5030, DUKHCONP1BZ2MSEX5000, DUKHCONP1BZ2WEEX5030, DUKHCONP1BZ2MSEX5000, DUKHCONP1BZ2MSEX5020, DUKHCONP1BZ2ARRF3600, DUKHCONP1BZ2STRF2060, DUKHCONP1BZ2STRF2060, DUKHCONP1BZ2MSEX5020 | 0 | 0 | ROOF
DUKHCONP1BZ2STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2013-12-16 | 2014-01-08 | 2013-12-16 | 2014-01-08 | 37 | No | DUKHCONP1BZ2STRF2045, DUKHCONP1BZ2STRF2045 | DUKHCONP1BZ2STRF2055, DUKHCONP1BZ2STRF2055 | 0 | 0 | ROOF
DHBL.K30.L25.15 .15 FINISHING WORKS |  | 195 | 195 | 0% | 2013-11-25 | 2014-07-12 | 2013-11-25 | 2014-07-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.15 .15 .10 INTERNAL FINISHES |  | 195 | 195 | 0% | 2013-11-25 | 2014-07-12 | 2013-11-25 | 2014-07-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.15 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-11-25 | 2014-05-08 | 2013-11-25 | 2014-05-08 | 58 |  |  |  | 0 | 0
DUKHCONP1BZ2ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-03-13 | 2014-03-30 | 2014-03-13 | 2014-03-30 | 58 | No | DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ1ARGF3070, DUKHCONP1BZ2ARGF3065 | DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3075, DUKHCONP1BZ3ARGF3070, DUKHCONP1BZ2ARGF3075, DUKHCONP1BZ2ARGF3080, DUKHCONP1BZ2ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 53 | No | DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ2ACGF4600 | DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ELGF4015, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-03-20 | 2014-04-12 | 2014-03-20 | 2014-04-12 | 68 | No | DUKHCONP1BZ1ARGF3080, DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ2ARGF3070 | DUKHCONP1BZ3ARGF3080, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3000 | Block work | 25 | 25 | 0% | 2013-11-25 | 2013-12-24 | 2013-11-25 | 2013-12-24 | 50 | No | DUKHCONP1BZ2STGF2015, DUKHCONP1BZ1ARGF3000, DUKHCONP1BZ2STGF2015 | DUKHCONP1BZ2PLGF4310, DUKHCONP1BZ2ELGF4000, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ2ELGF4000, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 58 | No | DUKHCONP1BZ1ARGF3075, DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ2ARGF3070 | DUKHCONP1BZ2ARGF3090, DUKHCONP1BZ2ARGF3085, DUKHCONP1BZ2ARGF3085, DUKHCONP1BZ2ARGF3090, DUKHCONP1BZ3ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 50 | No | DUKHCONP1BZ2PLGF4310, DUKHCONP1BZ2ARGF3015, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ1ARGF3020, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ2PLGF4310, DUKHCONP1BZ2ARGF3015 | DUKHCONP1BZ3ARGF3020, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-02-13 | 2014-03-02 | 2014-02-13 | 2014-03-02 | 58 | No | DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ2ARGF3035 | DUKHCONP1BZ2ARGF3050, DUKHCONP1BZ2ARGF3050, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-04-10 | 2014-05-08 | 2014-04-10 | 2014-05-08 | 58 | No | DUKHCONP1BZ2ARGF3030, DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3085, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3080, DUKHCONP1BZ2ARGF3080, DUKHCONP1BZ2ACGF4610, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ1ARGF3095, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ2ARGF3085, DUKHCONP1BZ2ARGF3030, DUKHCONP1BZ2ACGF4610, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ2ARGF3090, DUKHCONP1BZ2ARGF3090 | DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-02-03 | 2014-02-26 | 2014-02-03 | 2014-02-26 | 50 | No | DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ELGF4010, DUKHCONP1BZ2ARGF3030, DUKHCONP1BZ2ELGF4010, DUKHCONP1BZ1ARGF3045, DUKHCONP1BZ2ARGF3030, DUKHCONP1BZ2ARGF3025 | DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ3ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-12-26 | 2014-01-19 | 2013-12-26 | 2014-01-19 | 58 | No | DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2ARGF3005 | DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-02-22 | 2014-03-16 | 2014-02-22 | 2014-03-16 | 58 | No | DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3025 | DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ2ARGF3085, DUKHCONP1BZ2ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 50 | No | DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ1ARGF3060, DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ2ARGF3045 | DUKHCONP1BZ2ELGF4015, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ2ELGF4015, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ2ELGF4030, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ELGF4030, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ2PLGF4320, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2PLGF4320, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-04-01 | 2014-04-17 | 2014-04-01 | 2014-04-17 | 58 | No | DUKHCONP1BZ2ARGF3075, DUKHCONP1BZ2ARGF3075 | DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-01-04 | 2014-02-01 | 2014-01-04 | 2014-02-01 | 64 | No | DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ1ARGF3030, DUKHCONP1BZ2ARGF3005 | DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ2ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 50 | No | DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ2ELGF4000, DUKHCONP1BZ2ELGF4000, DUKHCONP1BZ1ARGF3005, DUKHCONP1BZ2ARGF3000 | DUKHCONP1BZ2ARGF3015, DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ARGF3030, DUKHCONP1BZ2ARGF3015, DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ2ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 50 | No | DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ2ARGF3020, DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ1ARGF3025, DUKHCONP1BZ2ARGF3020 | DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ2ARGF3050, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ2ARGF3050, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ2ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-03-27 | 2014-04-19 | 2014-03-27 | 2014-04-19 | 63 | No | DUKHCONP1BZ2ARGF3050, DUKHCONP1BZ2ARGF3075, DUKHCONP1BZ2ARGF3075, DUKHCONP1BZ2ARGF3050 | DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-02-05 | 2014-02-23 | 2014-02-05 | 2014-02-23 | 60 | No | DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ2ARGF3010, DUKHCONP1BZ2ARGF3025 | DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARGF3040, DUKHCONP1BZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-01-05 | 2014-01-21 | 2014-01-05 | 2014-01-21 | 50 | No | DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ1ARGF3015 | DUKHCONP1BZ2ARGF3020, DUKHCONP1BZ3ARGF3015, DUKHCONP1BZ2ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-03-08 | 2014-03-24 | 2014-03-08 | 2014-03-24 | 58 | No | DUKHCONP1BZ2ARGF3050, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ2ARGF3050, DUKHCONP1BZ2ARGF3035, DUKHCONP1BZ1ARGF3065 | DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ2PLGF4315, DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ2PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.15 .15 .10 .15 FIRST FLOORS |  | 159 | 159 | 0% | 2014-01-07 | 2014-07-12 | 2014-01-07 | 2014-07-12 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ2ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-05-11 | 2014-06-02 | 2014-05-11 | 2014-06-02 | 3 | No | DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ1ARFF3370, DUKHCONP1BZ2ARFF3365 | DUKHCONP1BZ2ARFF3375, DUKHCONP1BZ2ARFF3380, DUKHCONP1BZ2ARFF3375, DUKHCONP1BZ2ARFF3380, DUKHCONP1BZ3ARFF3370 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-05-18 | 2014-06-09 | 2014-05-18 | 2014-06-09 | 16 | No | DUKHCONP1BZ2ARFF3370, DUKHCONP1BZ2ARFF3370 | DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3300 | Block work | 25 | 25 | 0% | 2014-01-07 | 2014-02-04 | 2014-01-07 | 2014-02-04 | 3 | No | DUKHCONP1BZ2STFF2035, DUKHCONP1BZ2STFF2020, DUKHCONP1BZ2STFF2035, DUKHCONP1BZ2STFF2020, DUKHCONP1BZ1ARFF3300 | DUKHCONP1BZ2PLFF4325, DUKHCONP1BZ2PLFF4325, DUKHCONP1BZ2ELFF4035, DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ELFF4035 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 3 | No | DUKHCONP1BZ2ARFF3370, DUKHCONP1BZ2ARFF3370, DUKHCONP1BZ1ARFF3375 | DUKHCONP1BZ2ARFF3390, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3385, DUKHCONP1BZ2ARFF3385, DUKHCONP1BZ2ARFF3390, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 3 | No | DUKHCONP1BZ2ARFF3315, DUKHCONP1BZ2PLFF4325, DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ1ARFF3320, DUKHCONP1BZ2ARFF3315, DUKHCONP1BZ2PLFF4325 | DUKHCONP1BZ3ARFF3320, DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ2ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 3 | No | DUKHCONP1BZ2ARFF3335, DUKHCONP1BZ2ARFF3350, DUKHCONP1BZ2ARFF3385, DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ2ARFF3350, DUKHCONP1BZ2ARFF3375, DUKHCONP1BZ2ARFF3385, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ2ARFF3380, DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ2ARFF3335, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ1ARFF3395, DUKHCONP1BZ2ARFF3330, DUKHCONP1BZ2ARFF3330, DUKHCONP1BZ2ARFF3390, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3380, DUKHCONP1BZ2ARFF3375, DUKHCONP1BZ2ARFF3390 | DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ2ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-04-06 | 2014-04-28 | 2014-04-06 | 2014-04-28 | 3 | No | DUKHCONP1BZ2ARFF3330, DUKHCONP1BZ2ELFF4045, DUKHCONP1BZ2ELFF4045, DUKHCONP1BZ1ARFF3345, DUKHCONP1BZ2ARFF3330, DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ2ARFF3325 | DUKHCONP1BZ3ARFF3345, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-02-12 | 2014-03-08 | 2014-02-12 | 2014-03-08 | 20 | No | DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3305 | DUKHCONP1BZ2ARFF3335, DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ2ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-04-06 | 2014-04-28 | 2014-04-06 | 2014-04-28 | 14 | No | DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ2ARFF3325 | DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ2ARFF3385, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ2ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 3 | No | DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ1ARFF3360 | DUKHCONP1BZ2ELFF4055, DUKHCONP1BZ2PLFF4340, DUKHCONP1BZ2ACFF4620, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ2ELFF4055, DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ2ELFF4050, DUKHCONP1BZ2ACFF4620, DUKHCONP1BZ2ELFF4050, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ2PLFF4340, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ3ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-06-02 | 2014-06-24 | 2014-06-02 | 2014-06-24 | 3 | No | DUKHCONP1BZ2ARFF3375, DUKHCONP1BZ2ARFF3375, DUKHCONP1BZ2ARFF3350, DUKHCONP1BZ2ARFF3350 | DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-06-02 | 2014-06-24 | 2014-06-02 | 2014-06-24 | 5 | No | DUKHCONP1BZ2ARFF3375, DUKHCONP1BZ2ARFF3375 | DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 29 | No | DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3305 | DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 3 | No | DUKHCONP1BZ2ELFF4035, DUKHCONP1BZ2PLFF4325, DUKHCONP1BZ2PLFF4325, DUKHCONP1BZ2ELFF4035, DUKHCONP1BZ1ARFF3305, DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ2ARFF3300 | DUKHCONP1BZ2ARFF3310, DUKHCONP1BZ2ARFF3310, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ2ARFF3330, DUKHCONP1BZ2ARFF3315, DUKHCONP1BZ2ARFF3315, DUKHCONP1BZ2AREL3665, DUKHCONP1BZ2ARFF3330, DUKHCONP1BZ2AREL3665, DUKHCONP1BZ3ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 3 | No | DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ2ARFF3310, DUKHCONP1BZ2ARFF3310, DUKHCONP1BZ1ARFF3325 | DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ2ARFF3350, DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ2ARFF3350, DUKHCONP1BZ2ARFF3335, DUKHCONP1BZ2ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-04-02 | 2014-04-19 | 2014-04-02 | 2014-04-19 | 22 | No | DUKHCONP1BZ2ARFF3310, DUKHCONP1BZ2ARFF3310, DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ2ARFF3325 | DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ2ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-02-25 | 2014-03-13 | 2014-02-25 | 2014-03-13 | 3 | No | DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ1ARFF3315 | DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ3ARFF3315, DUKHCONP1BZ2ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-05-03 | 2014-05-19 | 2014-05-03 | 2014-05-19 | 3 | No | DUKHCONP1BZ2ARFF3350, DUKHCONP1BZ1ARFF3365, DUKHCONP1BZ2ARFF3335, DUKHCONP1BZ2ARFF3350, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3335 | DUKHCONP1BZ2ARFF3370, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2PLFF4335, DUKHCONP1BZ2ARFF3370, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ2PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.15 .15 .10 .20 ROOF |  | 64 | 64 | 0% | 2014-01-27 | 2014-04-12 | 2014-01-27 | 2014-04-12 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ2ARRF3600 | Block work | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 80 | No | DUKHCONP1BZ2STRF2055, DUKHCONP1BZ1ARRF3600, DUKHCONP1BZ2STRF2055 | DUKHCONP1BZ2ARRF3605, DUKHCONP1BZ3ARRF3600, DUKHCONP1BZ2ARRF3605 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-03-26 | 2014-04-12 | 2014-03-26 | 2014-04-12 | 81 | No | DUKHCONP1BZ2ARRF3695, DUKHCONP1BZ2ARRF3695 | DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-02-24 | 2014-03-12 | 2014-02-24 | 2014-03-12 | 81 | No | DUKHCONP1BZ2ARRF3605, DUKHCONP1BZ2ARRF3605 | DUKHCONP1BZ2ARRF3695, DUKHCONP1BZ2ARRF3695 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-03-09 | 2014-03-31 | 2014-03-09 | 2014-03-31 | 81 | No | DUKHCONP1BZ2ARRF3610, DUKHCONP1BZ2ARRF3610 | DUKHCONP1BZ2ARRF3620, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ2ARRF3620 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-02-04 | 2014-02-27 | 2014-02-04 | 2014-02-27 | 80 | No | DUKHCONP1BZ2ARRF3600, DUKHCONP1BZ2ARRF3600 | DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ2ARRF3610, DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ2ARRF3610, DUKHCONP1BZ2AREL3665 | 0 | 0 | ROOF
DHBL.K30.L25.15 .15 .15 EXTERNAL FINISHES |  | 63 | 63 | 0% | 2014-02-03 | 2014-04-17 | 2014-02-03 | 2014-04-17 | 76 |  |  |  | 0 | 0
DHBL.K30.L25.15 .15 .15 .10 ROOF |  | 58 | 58 | 0% | 2014-02-03 | 2014-04-12 | 2014-02-03 | 2014-04-12 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ2ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 78 | No | DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2ARRF3645 | DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2ARRF3655 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-03-26 | 2014-04-12 | 2014-03-26 | 2014-04-12 | 81 | No | DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2ARRF3655 | DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 78 | No | DUKHCONP1BZ2ARRF3635, DUKHCONP1BZ2ARRF3635 | DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2ARRF3645 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-03-12 | 2014-04-03 | 2014-03-12 | 2014-04-03 | 78 | No | DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2ARRF3650, DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ1ARRF3655, DUKHCONP1BZ2ARRF3650 | DUKHCONP1BZ2ARRF3660, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ2ARRF3660, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ2ELTC8010 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-02-06 | 2014-03-08 | 2014-02-06 | 2014-03-08 | 78 | No | DUKHCONP1BZ2ARRF3630, DUKHCONP1BZ2ARRF3630 | DUKHCONP1BZ2ARRF3640, DUKHCONP1BZ2ARRF3640 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 78 | No | DUKHCONP1BZ2STRF2065, DUKHCONP1BZ2STRF2060, DUKHCONP1BZ1ARRF3630, DUKHCONP1BZ2STRF2060, DUKHCONP1BZ2STRF2065 | DUKHCONP1BZ3ARRF3630, DUKHCONP1BZ2ARRF3635, DUKHCONP1BZ2ARRF3635 | 0 | 0 | ROOF
DUKHCONP1BZ2ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 78 | No | DUKHCONP1BZ2ARRF3640, DUKHCONP1BZ2ARRF3640 | DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2ELRF4070, DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2ARRF3650, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ2ARRF3650, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2ELRF4070, DUKHCONP1BZ2ACRF4630 | 0 | 0 | ROOF
DHBL.K30.L25.15 .15 .15 .15 ELEVATION |  | 50 | 50 | 0% | 2014-02-19 | 2014-04-17 | 2014-02-19 | 2014-04-17 | 76 |  |  |  | 0 | 0
DUKHCONP1BZ2AREL3680 | External Painting | 20 | 20 | 0% | 2014-03-26 | 2014-04-17 | 2014-03-26 | 2014-04-17 | 76 | No | DUKHCONP1BZ2AREL3670, DUKHCONP1BZ2ARRF3695, DUKHCONP1BZ2ARRF3695, DUKHCONP1BZ2AREL3675, DUKHCONP1BZ2AREL3670, DUKHCONP1BZ2AREL3675, DUKHCONP1BZ1AREL3680 | DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ3AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1BZ2AREL3665 | External Plastering | 25 | 25 | 0% | 2014-02-19 | 2014-03-19 | 2014-02-19 | 2014-03-19 | 75 | No | DUKHCONP1BZ2STRF2065, DUKHCONP1BZ2STRF2065, DUKHCONP1BZ2ARRF3605, DUKHCONP1BZ1AREL3665, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3305 | DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2AREL3675, DUKHCONP1BZ2AREL3670, DUKHCONP1BZ2AREL3670, DUKHCONP1BZ3AREL3665, DUKHCONP1BZ2AREL3675, DUKHCONP1BZ2PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP1BZ2AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-03-09 | 2014-03-31 | 2014-03-09 | 2014-03-31 | 76 | No | DUKHCONP1BZ2AREL3665, DUKHCONP1BZ2AREL3665, DUKHCONP1BZ1AREL3670 | DUKHCONP1BZ2AREL3675, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ3AREL3670 | 0 | 0 | ELEVATION
DUKHCONP1BZ2AREL3675 | GRC works | 20 | 20 | 0% | 2014-03-15 | 2014-04-06 | 2014-03-15 | 2014-04-06 | 76 | No | DUKHCONP1BZ2AREL3665, DUKHCONP1BZ2AREL3670, DUKHCONP1BZ1AREL3675, DUKHCONP1BZ2AREL3665 | DUKHCONP1BZ2AREL3680, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ3AREL3675 | 0 | 0 | ELEVATION
DHBL.K30.L25.15 .20 MEP WORKS |  | 272 | 272 | 0% | 2013-08-25 | 2014-07-12 | 2013-08-25 | 2014-07-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.15 .20 .10 ELECTRICAL WORKS |  | 190 | 190 | 0% | 2013-12-01 | 2014-07-12 | 2013-12-01 | 2014-07-12 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.15 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-12-01 | 2014-04-10 | 2013-12-01 | 2014-04-10 | 57 |  |  |  | 0 | 0
DUKHCONP1BZ2ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-12 | 2014-01-05 | 2013-12-12 | 2014-01-05 | 77 | No | DUKHCONP1BZ1ELGF4005, DUKHCONP1BZ2ELGF4000, DUKHCONP1BZ2ELGF4000 | DUKHCONP1BZ2ELGF4010, DUKHCONP1BZ2ELGF4010, DUKHCONP1BZ3ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-12-01 | 2013-12-30 | 2013-12-01 | 2013-12-30 | 59 | No | DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ2ARGF3000 | DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2ELGF4005, DUKHCONP1BZ2ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 72 | No | DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ1ELGF4015, DUKHCONP1BZ2ARGF3055 | DUKHCONP1BZ2ELFF4055, DUKHCONP1BZ3ELGF4015, DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-03-02 | 2014-03-24 | 2014-03-02 | 2014-03-24 | 50 | No | DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ELGF4010, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ2ELGF4010 | DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ELGF4030, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 52 | No | DUKHCONP1BZ1ELGF4025, DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3060 | DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-03-13 | 2014-04-05 | 2014-03-13 | 2014-04-05 | 50 | No | DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ1ELGF4030, DUKHCONP1BZ2ELGF4020 | DUKHCONP1BZ2ELFF4050, DUKHCONP1BZ2ELFF4050, DUKHCONP1BZ3ELGF4030, DUKHCONP1BZ2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 77 | No | DUKHCONP1BZ2ELGF4005, DUKHCONP1BZ2ELGF4005 | DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ2ELGF4020, DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ2ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.15 .20 .10 .15 FIRST FLOORS |  | 129 | 129 | 0% | 2014-01-13 | 2014-06-12 | 2014-01-13 | 2014-06-12 | 28 |  |  |  | 0 | 0
DUKHCONP1BZ2ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-01-25 | 2014-02-17 | 2014-01-25 | 2014-02-17 | 46 | No | DUKHCONP1BZ2ELFF4035, DUKHCONP1BZ2ELFF4035 | DUKHCONP1BZ2ELFF4045, DUKHCONP1BZ2ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 16 | No | DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ2ARFF3300 | DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ELFF4040, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 45 | No | DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ELGF4015, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ1ELFF4055, DUKHCONP1BZ2ELGF4015 | DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ3ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-05-03 | 2014-05-25 | 2014-05-03 | 2014-05-25 | 3 | No | DUKHCONP1BZ2ELFF4045, DUKHCONP1BZ1ELFF4060, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ELFF4045 | DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ2ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 3 | No | DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ1ELFF4065 | DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2ELRF4070, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ2ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 25 | No | DUKHCONP1BZ2ELGF4030, DUKHCONP1BZ2ELGF4030, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2MSEX5010 | DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2ELRF4070, DUKHCONP1BZ2ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 46 | No | DUKHCONP1BZ2ELFF4040, DUKHCONP1BZ1ELFF4045, DUKHCONP1BZ2ELFF4040 | DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ2ELRF4070, DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ2ELRF4070 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.15 .20 .10 .20 ROOF |  | 33 | 33 | 0% | 2014-06-04 | 2014-07-12 | 2014-06-04 | 2014-07-12 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ2ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-06-04 | 2014-06-24 | 2014-06-04 | 2014-06-24 | 3 | No | DUKHCONP1BZ2ELFF4050, DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ2ELFF4050, DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2ELFF4045, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ2ELFF4045 | DUKHCONP1BZ2ELRF4075, DUKHCONP1BZ2ELRF4075 | 0 | 0 | ROOF
DUKHCONP1BZ2ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-06-16 | 2014-07-12 | 2014-06-16 | 2014-07-12 | 3 | No | DUKHCONP1BZ2ELRF4070, DUKHCONP1BZ2ELRF4070 | DUKHCONP1BZ2ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L25.15 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 256 | 256 | 0% | 2013-08-25 | 2014-06-23 | 2013-08-25 | 2014-06-23 | 19 |  |  |  | 0 | 0
DHBL.K30.L25.15 .20 .15 .10 GROUND FLOOR |  | 193 | 193 | 0% | 2013-08-25 | 2014-04-10 | 2013-08-25 | 2014-04-10 | 82 |  |  |  | 0 | 0
DUKHCONP1BZ2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-08-25 | 2013-09-16 | 2013-08-25 | 2013-09-16 | 0 | Yes | DUKHCONP1BZ2STUG1040, DUKHCONP1BZ2STUG1040 | DUKHCONP1BZ2STUG1045, DUKHCONP1BZ2STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-12-11 | 2014-01-01 | 2013-12-11 | 2014-01-01 | 53 | No | DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ2ARGF3000 | DUKHCONP1BZ2MSEX5000, DUKHCONP1BZ2ARGF3020, DUKHCONP1BZ2PLGF4315, DUKHCONP1BZ2MSEX5000, DUKHCONP1BZ2ARGF3020, DUKHCONP1BZ2PLGF4315 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-12-11 | 2014-01-01 | 2013-12-11 | 2014-01-01 | 50 | No | DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ1PLGF4305 | DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2PLGF4310, DUKHCONP1BZ2PLGF4310, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2ARGF3020, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ2ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-03-25 | 2014-04-10 | 2014-03-25 | 2014-04-10 | 82 | No | DUKHCONP1BZ2PLGF4315, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ1PLGF4320, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2PLGF4315 | DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ3PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-03-13 | 2014-04-05 | 2014-03-13 | 2014-04-05 | 82 | No | DUKHCONP1BZ1PLGF4315, DUKHCONP1BZ2PLGF4310, DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ2PLGF4310 | DUKHCONP1BZ2PLGF4320, DUKHCONP1BZ3PLGF4315, DUKHCONP1BZ2PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.15 .20 .15 .15 FIRST FLOORS |  | 113 | 113 | 0% | 2014-01-25 | 2014-06-05 | 2014-01-25 | 2014-06-05 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ2PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-01-25 | 2014-02-15 | 2014-01-25 | 2014-02-15 | 30 | No | DUKHCONP1BZ2PLFF4325, DUKHCONP1BZ2PLFF4325, DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ1PLFF4330 | DUKHCONP1BZ2PLFF4335, DUKHCONP1BZ2PLFF4335, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ3PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-01-25 | 2014-02-15 | 2014-01-25 | 2014-02-15 | 3 | No | DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ2ARFF3300 | DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ2ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-05-20 | 2014-06-05 | 2014-05-20 | 2014-06-05 | 19 | No | DUKHCONP1BZ2PLFF4335, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2PLFF4335, DUKHCONP1BZ1PLFF4340, DUKHCONP1BZ2ARFF3360 | DUKHCONP1BZ3PLFF4340, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ2PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-05-08 | 2014-05-31 | 2014-05-08 | 2014-05-31 | 19 | No | DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ2ARFF3365, DUKHCONP1BZ2ARFF3365 | DUKHCONP1BZ2PLFF4340, DUKHCONP1BZ2PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.15 .20 .15 .20 ROOF |  | 105 | 105 | 0% | 2014-02-22 | 2014-06-23 | 2014-02-22 | 2014-06-23 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ2PLRF4345 | Installation of Plumbing pipes & fittings | 14 | 14 | 0% | 2014-02-22 | 2014-03-09 | 2014-02-22 | 2014-03-09 | 84 | No | DUKHCONP1BZ2ARRF3605, DUKHCONP1BZ1PLRF4345, DUKHCONP1BZ2ARRF3605 | DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ3PLRF4345, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ2PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ2PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-03-16 | 2014-04-01 | 2014-03-16 | 2014-04-01 | 75 | No | DUKHCONP1BZ2AREL3665, DUKHCONP1BZ2PLFF4330, DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ1PLRF4350, DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2AREL3665, DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2PLFF4330 | DUKHCONP1BZ2WEEX5065, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ2WEEX5065, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ2PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ2PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-05-26 | 2014-06-23 | 2014-05-26 | 2014-06-23 | 19 | No | DUKHCONP1BZ2PLFF4340, DUKHCONP1BZ1PLRF4355, DUKHCONP1BZ2PLFF4340, DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2WEEX5065 | DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ2PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L25.15 .20 .20 AC WORKS |  | 145 | 145 | 0% | 2014-01-01 | 2014-06-19 | 2014-01-01 | 2014-06-19 | 22 |  |  |  | 0 | 0
DHBL.K30.L25.15 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-01-01 | 2014-04-08 | 2014-01-01 | 2014-04-08 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ2ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 69 | No | DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ1ACGF4610 | DUKHCONP1BZ3ACGF4610, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ACRF4635, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 69 | No | DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ1ACGF4605, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ARGF3060 | DUKHCONP1BZ2ACGF4610, DUKHCONP1BZ2ACGF4610, DUKHCONP1BZ3ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ2ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-01 | 2014-01-23 | 2014-01-01 | 2014-01-23 | 81 | No | DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ1ACGF4600 | DUKHCONP1BZ2ARGF3055, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ2ARGF3055 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.15 .20 .20 .15 FIRST FLOORS |  | 95 | 95 | 0% | 2014-02-18 | 2014-06-08 | 2014-02-18 | 2014-06-08 | 17 |  |  |  | 0 | 0
DUKHCONP1BZ2ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-05-17 | 2014-06-08 | 2014-05-17 | 2014-06-08 | 17 | No | DUKHCONP1BZ1ACFF4625, DUKHCONP1BZ2ACFF4620, DUKHCONP1BZ2ACFF4620 | DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2ACRF4635, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ2ACRF4635, DUKHCONP1BZ2ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 17 | No | DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ1ACFF4620 | DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ3ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ2ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 46 | No | DUKHCONP1BZ1ACFF4615, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ2ARFF3305 | DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ2ACFF4620, DUKHCONP1BZ2ACFF4620, DUKHCONP1BZ2ACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.15 .20 .20 .20 ROOF |  | 95 | 95 | 0% | 2014-03-02 | 2014-06-19 | 2014-03-02 | 2014-06-19 | 22 |  |  |  | 0 | 0
DUKHCONP1BZ2ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 22 | No | DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ2ACGF4610, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ1ACRF4635, DUKHCONP1BZ2ACGF4610 | DUKHCONP1BZ3ACRF4635, DUKHCONP1BZ2ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ2ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 87 | No | DUKHCONP1BZ1ACRF4630, DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ2ARRF3645, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ2ARRF3645 | DUKHCONP1BZ2ACRF4635, DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ2ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L25.15 .25 EXTERNAL WORKS |  | 161 | 161 | 0% | 2014-01-08 | 2014-07-15 | 2014-01-08 | 2014-07-15 | 25 |  |  |  | 0 | 0
DHBL.K30.L25.15 .25 .10 MISCELLANEOUS |  | 161 | 161 | 0% | 2014-01-08 | 2014-07-15 | 2014-01-08 | 2014-07-15 | 25 |  |  |  | 0 | 0
DUKHCONP1BZ2MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 25 | No | DUKHCONP1BZ1MSEX5335, DUKHCONI1BZ1BWGL5325 | DUKHCONP1BZ3MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ2MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 37 | No | DUKHCONP1BZ2MSEX5000, DUKHCONP1BZ2MSEX5000 | DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ2MSEX5015, DUKHCONP1BZ2MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ2MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 69 | No | DUKHCONP1BZ2STRF2055, DUKHCONP1BZ2STRF2055, DUKHCONP1BZ1MSEX5020 | DUKHCONP1BZ2MSEX5025, DUKHCONP1BZ2HDEX5090, DUKHCONP1BZ2HDEX5090, DUKHCONP1BZ2MSEX5025, DUKHCONP1BZ3MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ2MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 37 | No | DUKHCONP1BZ2MSEX5005, DUKHCONP1BZ2MSEX5005 | DUKHCONP1BZ2WEEX5050, DUKHCONP1BZ2WEEX5065, DUKHCONP1BZ2MSEX5010, DUKHCONP1BZ2WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ2MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-01-12 | 2014-02-09 | 2014-01-12 | 2014-02-09 | 37 | No | DUKHCONP1BZ2PLGF4310, DUKHCONP1BZ2STRF2055, DUKHCONP1BZ2STRF2055, DUKHCONP1BZ2PLGF4310 | DUKHCONP1BZ2MSEX5005, DUKHCONP1BZ2MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ2MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-01-28 | 2014-02-20 | 2014-01-28 | 2014-02-20 | 69 | No | DUKHCONP1BZ2MSEX5020, DUKHCONP1BZ2MSEX5020 | DUKHCONP1BZ2HDEX5090, DUKHCONP1BZ2WEEX5050, DUKHCONP1BZ2WEEX5060, DUKHCONP1BZ2WEEX5045 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ2MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-03-11 | 2014-04-08 | 2014-03-11 | 2014-04-08 | 37 | No | DUKHCONP1BZ2MSEX5015 | DUKHCONP1BZ2ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L25.15 .25 .15 WATER TANK ENCLOSURE |  | 83 | 83 | 0% | 2014-01-16 | 2014-04-23 | 2014-01-16 | 2014-04-23 | 71 |  |  |  | 0 | 0
DUKHCONP1BZ2WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 74 | No | DUKHCONP1BZ2WEEX5035, DUKHCONP1BZ2WEEX5035 | DUKHCONP1BZ2WEEX5045, DUKHCONP1BZ2WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ2WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 51 | No | DUKHCONP1BZ2WEEX5030, DUKHCONP1BZ2WEEX5030 | DUKHCONP1BZ2WEEX5040, DUKHCONP1BZ2WEEX5040, DUKHCONP1BZ3WEEX5030 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ2WEEX5030 | Excavation | 20 | 20 | 0% | 2014-01-16 | 2014-02-08 | 2014-01-16 | 2014-02-08 | 51 | No | DUKHCONP1BZ2STRF2055, DUKHCONP1BZ1WEEX5030, DUKHCONP1BZ2STRF2055 | DUKHCONP1BZ2WEEX5035, DUKHCONP1BZ2WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ2WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 74 | No | DUKHCONP1BZ2WEEX5040, DUKHCONP1BZ2WEEX5040, DUKHCONP1BZ2MSEX5025 | DUKHCONP1BZ2WEEX5050, DUKHCONP1BZ2WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ2WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 71 | No | DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2WEEX5060, DUKHCONP1BZ2MSEX5015, DUKHCONP1BZ1WEEX5065, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2MSEX5015, DUKHCONP1BZ2WEEX5060 | DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ2PLRF4355 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ2WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-03-05 | 2014-03-27 | 2014-03-05 | 2014-03-27 | 74 | No | DUKHCONP1BZ2WEEX5045, DUKHCONP1BZ2MSEX5025, DUKHCONP1BZ2MSEX5015, DUKHCONP1BZ2WEEX5045 | DUKHCONP1BZ2WEEX5060, DUKHCONP1BZ2WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ2WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 71 | No | DUKHCONP1BZ2MSEX5025, DUKHCONP1BZ2WEEX5050, DUKHCONP1BZ1WEEX5060, DUKHCONP1BZ2WEEX5050 | DUKHCONP1BZ3WEEX5060, DUKHCONP1BZ2WEEX5065, DUKHCONP1BZ2WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L25.15 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2014-02-05 | 2014-03-27 | 2014-02-05 | 2014-03-27 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ2HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 69 | No | DUKHCONP1BZ2HDEX5090, DUKHCONP1BZ2HDEX5090 | DUKHCONP1BZ2HDEX5100, DUKHCONP1BZ2HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ2HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-03-05 | 2014-03-27 | 2014-03-05 | 2014-03-27 | 69 | No | DUKHCONP1BZ2HDEX5095, DUKHCONP1BZ2HDEX5095 | DUKHCONP1BZ2SLEX5105, DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ2SLEX5105, DUKHCONP1BZ2ELTC8010 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ2HDEX5090 | kerb works | 20 | 20 | 0% | 2014-02-05 | 2014-03-01 | 2014-02-05 | 2014-03-01 | 69 | No | DUKHCONP1BZ2MSEX5020, DUKHCONP1BZ2MSEX5020, DUKHCONP1BZ2MSEX5025, DUKHCONP1BZ1HDEX5090 | DUKHCONP1BZ2HDEX5095, DUKHCONP1BZ2HDEX5095, DUKHCONP1BZ3HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L25.15 .25 .25 SOFT LANDSCAPING |  | 35 | 35 | 0% | 2014-03-17 | 2014-04-26 | 2014-03-17 | 2014-04-26 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ2SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-03-17 | 2014-04-14 | 2014-03-17 | 2014-04-14 | 69 | No | DUKHCONP1BZ2HDEX5100, DUKHCONP1BZ2HDEX5100 | DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ2SLEX5110, DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ2SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1BZ2SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-03-29 | 2014-04-26 | 2014-03-29 | 2014-04-26 | 69 | No | DUKHCONP1BZ2SLEX5105, DUKHCONP1BZ2SLEX5105 | DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ2PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L25.15 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ2ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 3 | No | DUKHCONP1BZ2AREL3680, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2HDEX5100, DUKHCONP1BZ2SLEX5110, DUKHCONP1BZ2MSEX5005, DUKHCONP1BZ1ACTC8000, DUKHCONP1BZ2ACRF4635, DUKHCONP1BZ2ARRF3620, DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ2SLEX5105, DUKHCONP1BZ2ARGF3095 | DUKHCONP1BZ3ACTC8000, DUKHHANP1BGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 3 | No | DUKHCONP1BZ2ELFF4050, DUKHCONP1BZ2MSEX5005, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ2ELFF4055, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ2ARRF3620, DUKHCONP1BZ2ELRF4075, DUKHCONP1BZ2SLEX5105, DUKHCONP1BZ2ELGF4015, DUKHCONP1BZ2SLEX5110, DUKHCONP1BZ2ARRF3660, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2HDEX5100, DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ2ELGF4030 | DUKHHANP1BGNELTC9010, DUKHCONP1BZ3ELTC8010, DUKHHANP1BGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 3 | No | DUKHCONP1BZ2SLEX5105, DUKHCONP1BZ2MSEX5005, DUKHCONP1BZ2ARRF3620, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ2WEEX5065, DUKHCONP1BZ2HDEX5100, DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ2PLGF4320, DUKHCONP1BZ2ARRF3660, DUKHCONP1BZ2PLRF4350, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ2SLEX5110 | DUKHCONP1BZ3PLTC8005, DUKHHANP1BGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L25.20 ZONE - 3 (4 Twin Villas) |  | 383 | 383 | 0% | 2013-06-11 | 2014-09-11 | 2013-06-11 | 2014-09-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.20 .10 STRUCTURAL WORKS |  | 237 | 237 | 0% | 2013-06-11 | 2014-03-22 | 2013-06-11 | 2014-03-22 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.20 .10 .10 SUB STRUCTURE |  | 120 | 120 | 0% | 2013-06-11 | 2013-11-03 | 2013-06-11 | 2013-11-03 | 11 |  |  |  | 0 | 0
DHBL.K30.L25.20 .10 .10 .10 UPTO GRADE SLAB |  | 120 | 120 | 0% | 2013-06-11 | 2013-11-03 | 2013-06-11 | 2013-11-03 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ3STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-08-21 | 2013-09-18 | 2013-08-21 | 2013-09-18 | 11 | No | DUKHCONP1BZ2STUG1035, DUKHCONP1BZ3STUG1030, DUKHCONP1BZ3STUG1030 | DUKHCONP1BZ3STUG1040, DUKHCONP1BZ3STUG1040, DUKHCONP1BZ4STUG1035 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-07-18 | 2013-08-13 | 2013-07-18 | 2013-08-13 | 11 | No | DUKHCONP1BZ3STUG1015, DUKHCONP1BZ3STUG1015 | DUKHCONP1BZ3STUG1025, DUKHCONP1BZ3STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-09-07 | 2013-10-05 | 2013-09-07 | 2013-10-05 | 11 | No | DUKHCONP1BZ3STUG1035, DUKHCONP1BZ3STUG1035 | DUKHCONP1BZ3STUG1045, DUKHCONP1BZ3PLUG4300, DUKHCONP1BZ3STUG1045, DUKHCONP1BZ3PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-07-28 | 2013-08-28 | 2013-07-28 | 2013-08-28 | 11 | No | DUKHCONP1BZ2STUG1025, DUKHCONP1BZ3STUG1020, DUKHCONP1BZ3STUG1020 | DUKHCONP1BZ3STUG1030, DUKHCONP1BZ3STUG1030, DUKHCONP1BZ4STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-10-03 | 2013-11-03 | 2013-10-03 | 2013-11-03 | 11 | No | DUKHCONP1BZ3PLUG4300, DUKHCONP1BZ3STUG1040, DUKHCONP1BZ2STUG1045, DUKHCONP1BZ3PLUG4300, DUKHCONP1BZ3STUG1040 | DUKHCONP1BZ3STGF2000, DUKHCONP1BZ4STUG1045, DUKHCONP1BZ3STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-06-23 | 2013-07-18 | 2013-06-23 | 2013-07-18 | 11 | No | DUKHCONP1BZ3STUG1000, DUKHCONP1BZ3STUG1000 | DUKHCONP1BZ3STUG1010, DUKHCONP1BZ3STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-06-27 | 2013-07-23 | 2013-06-27 | 2013-07-23 | 11 | No | DUKHCONP1BZ3STUG1005, DUKHCONP1BZ3STUG1005 | DUKHCONP1BZ3STUG1015, DUKHCONP1BZ3STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-06-11 | 2013-07-09 | 2013-06-11 | 2013-07-09 | 11 | No | DUKHCONP1BZ2STUG1000 | DUKHCONP1BZ4STUG1000, DUKHCONP1BZ3STUG1005, DUKHCONP1BZ3STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-07-03 | 2013-07-31 | 2013-07-03 | 2013-07-31 | 11 | No | DUKHCONP1BZ3STUG1010, DUKHCONP1BZ3STUG1010 | DUKHCONP1BZ3STUG1020, DUKHCONP1BZ3STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ3STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-08-06 | 2013-09-07 | 2013-08-06 | 2013-09-07 | 11 | No | DUKHCONP1BZ3STUG1025, DUKHCONP1BZ3STUG1025 | DUKHCONP1BZ3STUG1035, DUKHCONP1BZ3STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L25.20 .10 .15 SUPERSTRUCTURE |  | 128 | 128 | 0% | 2013-10-22 | 2014-03-22 | 2013-10-22 | 2014-03-22 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.20 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-10-22 | 2013-12-16 | 2013-10-22 | 2013-12-16 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ3STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-12-01 | 2013-12-16 | 2013-12-01 | 2013-12-16 | 11 | No | DUKHCONP1BZ3STGF2010, DUKHCONP1BZ2STGF2015, DUKHCONP1BZ3STGF2010 | DUKHCONP1BZ3STFF2020, DUKHCONP1BZ4STGF2015, DUKHCONP1BZ3STFF2020, DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ3ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-11-14 | 2013-12-12 | 2013-11-14 | 2013-12-12 | 11 | No | DUKHCONP1BZ3STGF2005, DUKHCONP1BZ3STGF2005 | DUKHCONP1BZ3STGF2015, DUKHCONP1BZ3STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3STGF2005 | Column-Concrete | 23 | 23 | 0% | 2013-10-31 | 2013-11-26 | 2013-10-31 | 2013-11-26 | 11 | No | DUKHCONP1BZ3STGF2000, DUKHCONP1BZ3STGF2000 | DUKHCONP1BZ3STGF2010, DUKHCONP1BZ3STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-10-22 | 2013-11-19 | 2013-10-22 | 2013-11-19 | 11 | No | DUKHCONP1BZ3STUG1045, DUKHCONP1BZ2STGF2000, DUKHCONP1BZ3STUG1045 | DUKHCONP1BZ3STGF2005, DUKHCONP1BZ4STGF2000, DUKHCONP1BZ3STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.20 .10 .15 .15 FIRST FLOORS |  | 39 | 39 | 0% | 2013-12-03 | 2014-01-18 | 2013-12-03 | 2014-01-18 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ3STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-01-02 | 2014-01-18 | 2014-01-02 | 2014-01-18 | 11 | No | DUKHCONP1BZ3STFF2030, DUKHCONP1BZ3STFF2030, DUKHCONP1BZ2STFF2035 | DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ4STFF2035, DUKHCONP1BZ3STRF2040, DUKHCONP1BZ3STRF2040, DUKHCONP1BZ3ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-12-16 | 2014-01-14 | 2013-12-16 | 2014-01-14 | 11 | No | DUKHCONP1BZ3STFF2025, DUKHCONP1BZ3STFF2025 | DUKHCONP1BZ3STFF2035, DUKHCONP1BZ3STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3STFF2025 | Column-Concrete | 23 | 23 | 0% | 2013-12-12 | 2014-01-08 | 2013-12-12 | 2014-01-08 | 11 | No | DUKHCONP1BZ3STFF2020, DUKHCONP1BZ3STFF2020 | DUKHCONP1BZ3STFF2030, DUKHCONP1BZ3STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 11 | No | DUKHCONP1BZ3STGF2015, DUKHCONP1BZ2STFF2020, DUKHCONP1BZ3STGF2015 | DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ4STFF2020, DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ3STFF2025, DUKHCONP1BZ3STFF2025 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.20 .10 .15 .20 ROOF |  | 62 | 62 | 0% | 2014-01-08 | 2014-03-22 | 2014-01-08 | 2014-03-22 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ3STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-01-12 | 2014-01-30 | 2014-01-12 | 2014-01-30 | 38 | No | DUKHCONP1BZ3STRF2040, DUKHCONP1BZ3STRF2040 | DUKHCONP1BZ3STRF2050, DUKHCONP1BZ3STRF2050 | 0 | 0 | ROOF
DUKHCONP1BZ3STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-01-08 | 2014-01-28 | 2014-01-08 | 2014-01-28 | 34 | No | DUKHCONP1BZ3STFF2035, DUKHCONP1BZ3STFF2035, DUKHCONP1BZ2STRF2040 | DUKHCONP1BZ4STRF2040, DUKHCONP1BZ3STRF2045, DUKHCONP1BZ3STRF2045 | 0 | 0 | ROOF
DUKHCONP1BZ3STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 61 | No | DUKHCONP1BZ3STRF2055, DUKHCONP1BZ2STRF2060, DUKHCONP1BZ3STRF2055 | DUKHCONP1BZ3ARRF3630, DUKHCONP1BZ3ARRF3630, DUKHCONP1BZ3WEEX5030, DUKHCONP1BZ3STRF2065, DUKHCONP1BZ3STRF2065 | 0 | 0 | ROOF
DUKHCONP1BZ3STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-02-22 | 2014-03-22 | 2014-02-22 | 2014-03-22 | 78 | No | DUKHCONP1BZ2STRF2065, DUKHCONP1BZ3STRF2060, DUKHCONP1BZ3STRF2060 | DUKHCONP1BZ3AREL3665, DUKHCONP1BZ4STRF2065, DUKHCONP1BZ3AREL3665, DUKHCONP1BZ3ARRF3630, DUKHCONP1BZ3ARRF3630 | 0 | 0 | ROOF
DUKHCONP1BZ3STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-01-28 | 2014-02-12 | 2014-01-28 | 2014-02-12 | 38 | No | DUKHCONP1BZ2STRF2055, DUKHCONP1BZ3STRF2050, DUKHCONP1BZ3STRF2050 | DUKHCONP1BZ3ARRF3600, DUKHCONP1BZ4STRF2055, DUKHCONP1BZ3ARRF3600, DUKHCONP1BZ3WEEX5030, DUKHCONP1BZ3STRF2060, DUKHCONP1BZ3MSEX5020, DUKHCONP1BZ3WEEX5030, DUKHCONP1BZ3MSEX5020, DUKHCONP1BZ3MSEX5000, DUKHCONP1BZ3STRF2060, DUKHCONP1BZ3MSEX5000 | 0 | 0 | ROOF
DUKHCONP1BZ3STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-01-14 | 2014-02-05 | 2014-01-14 | 2014-02-05 | 38 | No | DUKHCONP1BZ3STRF2045, DUKHCONP1BZ3STRF2045 | DUKHCONP1BZ3STRF2055, DUKHCONP1BZ3STRF2055 | 0 | 0 | ROOF
DHBL.K30.L25.20 .15 FINISHING WORKS |  | 194 | 194 | 0% | 2013-12-26 | 2014-08-13 | 2013-12-26 | 2014-08-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.20 .15 .10 INTERNAL FINISHES |  | 194 | 194 | 0% | 2013-12-26 | 2014-08-13 | 2013-12-26 | 2014-08-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.20 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-12-26 | 2014-06-08 | 2013-12-26 | 2014-06-08 | 57 |  |  |  | 0 | 0
DUKHCONP1BZ3ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-04-13 | 2014-04-29 | 2014-04-13 | 2014-04-29 | 57 | No | DUKHCONP1BZ2ARGF3070, DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ3ARGF3065 | DUKHCONP1BZ3ARGF3075, DUKHCONP1BZ3ARGF3080, DUKHCONP1BZ3ARGF3080, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ3ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 52 | No | DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ3ACGF4600 | DUKHCONP1BZ3ELGF4015, DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ3ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-04-20 | 2014-05-12 | 2014-04-20 | 2014-05-12 | 67 | No | DUKHCONP1BZ2ARGF3080, DUKHCONP1BZ3ARGF3070, DUKHCONP1BZ3ARGF3070 | DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ4ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3000 | Block work | 25 | 25 | 0% | 2013-12-26 | 2014-01-23 | 2013-12-26 | 2014-01-23 | 49 | No | DUKHCONP1BZ2ARGF3000, DUKHCONP1BZ3STGF2015, DUKHCONP1BZ3STGF2015 | DUKHCONP1BZ3ELGF4000, DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ3ELGF4000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-04-19 | 2014-05-11 | 2014-04-19 | 2014-05-11 | 57 | No | DUKHCONP1BZ3ARGF3070, DUKHCONP1BZ2ARGF3075, DUKHCONP1BZ3ARGF3070 | DUKHCONP1BZ3ARGF3090, DUKHCONP1BZ3ARGF3085, DUKHCONP1BZ4ARGF3075, DUKHCONP1BZ3ARGF3090, DUKHCONP1BZ3ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-02-10 | 2014-03-11 | 2014-02-10 | 2014-03-11 | 49 | No | DUKHCONP1BZ3ARGF3015, DUKHCONP1BZ2ARGF3020, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ3ARGF3015, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ3PLGF4310 | DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ3ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-03-16 | 2014-04-01 | 2014-03-16 | 2014-04-01 | 57 | No | DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3010, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3010 | DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3050, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 57 | No | DUKHCONP1BZ2ARGF3095, DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ACGF4610, DUKHCONP1BZ3ARGF3080, DUKHCONP1BZ3ARGF3090, DUKHCONP1BZ3ARGF3085, DUKHCONP1BZ3ARGF3090, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3070, DUKHCONP1BZ3ARGF3070, DUKHCONP1BZ3ARGF3080, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3085, DUKHCONP1BZ3ACGF4610 | DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 49 | No | DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ELGF4010, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ3ELGF4010, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ2ARGF3045, DUKHCONP1BZ3ARGF3025 | DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-01-26 | 2014-02-19 | 2014-01-26 | 2014-02-19 | 57 | No | DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3ARGF3005 | DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-03-24 | 2014-04-15 | 2014-03-24 | 2014-04-15 | 57 | No | DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3040 | DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ3ARGF3085, DUKHCONP1BZ3ARGF3085, DUKHCONP1BZ3ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 49 | No | DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ2ARGF3060, DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ3ARGF3045 | DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ELGF4015, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3PLGF4320, DUKHCONP1BZ3ELGF4030, DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ3ELGF4015, DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ3PLGF4320, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ3ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-05-01 | 2014-05-18 | 2014-05-01 | 2014-05-18 | 57 | No | DUKHCONP1BZ3ARGF3075, DUKHCONP1BZ3ARGF3075 | DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 63 | No | DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ2ARGF3030 | DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ4ARGF3030, DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-01-18 | 2014-02-16 | 2014-01-18 | 2014-02-16 | 49 | No | DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ3ELGF4000, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ2ARGF3005, DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ3ELGF4000 | DUKHCONP1BZ3ARGF3015, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ3ARGF3010, DUKHCONP1BZ3ARGF3015, DUKHCONP1BZ3ARGF3010, DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ3ACGF4600 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 49 | No | DUKHCONP1BZ3ARGF3010, DUKHCONP1BZ3ARGF3010, DUKHCONP1BZ2ARGF3025, DUKHCONP1BZ3ARGF3020, DUKHCONP1BZ3ARGF3020 | DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ3ARGF3050, DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3050, DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-04-27 | 2014-05-19 | 2014-04-27 | 2014-05-19 | 62 | No | DUKHCONP1BZ3ARGF3050, DUKHCONP1BZ3ARGF3050, DUKHCONP1BZ3ARGF3075, DUKHCONP1BZ3ARGF3075 | DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-03-09 | 2014-03-25 | 2014-03-09 | 2014-03-25 | 59 | No | DUKHCONP1BZ3ARGF3010, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ3ARGF3010 | DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3ARGF3040, DUKHCONP1BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-02-04 | 2014-02-22 | 2014-02-04 | 2014-02-22 | 49 | No | DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ2ARGF3015 | DUKHCONP1BZ3ARGF3020, DUKHCONP1BZ3ARGF3020, DUKHCONP1BZ4ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-04-07 | 2014-04-23 | 2014-04-07 | 2014-04-23 | 57 | No | DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ3ARGF3050, DUKHCONP1BZ3ARGF3035, DUKHCONP1BZ2ARGF3065, DUKHCONP1BZ3ARGF3050 | DUKHCONP1BZ3PLGF4315, DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ3PLGF4315, DUKHCONP1BZ3ARGF3070, DUKHCONP1BZ3ARGF3070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.20 .15 .10 .15 FIRST FLOORS |  | 159 | 159 | 0% | 2014-02-05 | 2014-08-13 | 2014-02-05 | 2014-08-13 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ3ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-06-09 | 2014-07-01 | 2014-06-09 | 2014-07-01 | 3 | No | DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ2ARFF3370 | DUKHCONP1BZ4ARFF3370, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ3ARFF3380, DUKHCONP1BZ3ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-06-16 | 2014-07-08 | 2014-06-16 | 2014-07-08 | 16 | No | DUKHCONP1BZ3ARFF3370, DUKHCONP1BZ3ARFF3370 | DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3300 | Block work | 25 | 25 | 0% | 2014-02-05 | 2014-03-06 | 2014-02-05 | 2014-03-06 | 3 | No | DUKHCONP1BZ3STFF2035, DUKHCONP1BZ3STFF2020, DUKHCONP1BZ2ARFF3300, DUKHCONP1BZ3STFF2035, DUKHCONP1BZ3STFF2020 | DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3PLFF4325, DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3PLFF4325, DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ3ELFF4035, DUKHCONP1BZ3ELFF4035, DUKHCONP1BZ3PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 3 | No | DUKHCONP1BZ3ARFF3370, DUKHCONP1BZ3ARFF3370, DUKHCONP1BZ2ARFF3375 | DUKHCONP1BZ3ARFF3385, DUKHCONP1BZ3ARFF3390, DUKHCONP1BZ3ARFF3385, DUKHCONP1BZ3ARFF3390, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ4ARFF3375, DUKHCONP1BZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-04-05 | 2014-05-03 | 2014-04-05 | 2014-05-03 | 3 | No | DUKHCONP1BZ2ARFF3320, DUKHCONP1BZ3ARFF3315, DUKHCONP1BZ3PLFF4325, DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3ARFF3315, DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3PLFF4325 | DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ3ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 3 | No | DUKHCONP1BZ2ARFF3395, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ARFF3380, DUKHCONP1BZ3ARFF3350, DUKHCONP1BZ3ARFF3390, DUKHCONP1BZ3ARFF3335, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3385, DUKHCONP1BZ3ARFF3385, DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ3ARFF3330, DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ3ARFF3330, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ3ARFF3335, DUKHCONP1BZ3ARFF3350, DUKHCONP1BZ3ARFF3380, DUKHCONP1BZ3ARFF3390 | DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-05-05 | 2014-05-27 | 2014-05-05 | 2014-05-27 | 3 | No | DUKHCONP1BZ2ARFF3345, DUKHCONP1BZ3ARFF3330, DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ3ARFF3330, DUKHCONP1BZ3ELFF4045 | DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ4ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-03-13 | 2014-04-06 | 2014-03-13 | 2014-04-06 | 20 | No | DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3ARFF3305 | DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ3ARFF3335, DUKHCONP1BZ3ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-05-05 | 2014-05-27 | 2014-05-05 | 2014-05-27 | 14 | No | DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ3ARFF3325 | DUKHCONP1BZ3ARFF3385, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 3 | No | DUKHCONP1BZ3ARFF3345, DUKHCONP1BZ3ARFF3345, DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ2ARFF3360, DUKHCONP1BZ3ACFF4615 | DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ELFF4055, DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ3ELFF4055, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3PLFF4340, DUKHCONP1BZ3ELFF4050, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ3PLFF4340, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ3ELFF4050, DUKHCONP1BZ3ACFF4620, DUKHCONP1BZ3ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-07-01 | 2014-07-23 | 2014-07-01 | 2014-07-23 | 3 | No | DUKHCONP1BZ3ARFF3350, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ3ARFF3350 | DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-07-01 | 2014-07-23 | 2014-07-01 | 2014-07-23 | 5 | No | DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ3ARFF3375 | DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 29 | No | DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3ARFF3305 | DUKHCONP1BZ3ARFF3345, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 3 | No | DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ3ELFF4035, DUKHCONP1BZ3ELFF4035, DUKHCONP1BZ3PLFF4325, DUKHCONP1BZ2ARFF3305, DUKHCONP1BZ3PLFF4325 | DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ3ARFF3330, DUKHCONP1BZ3ARFF3315, DUKHCONP1BZ3ARFF3310, DUKHCONP1BZ3AREL3665, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ3ARFF3330, DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ3ARFF3315, DUKHCONP1BZ3ARFF3310, DUKHCONP1BZ3AREL3665 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-04-14 | 2014-05-12 | 2014-04-14 | 2014-05-12 | 3 | No | DUKHCONP1BZ3ARFF3310, DUKHCONP1BZ3ARFF3320, DUKHCONP1BZ2ARFF3325, DUKHCONP1BZ3ARFF3310, DUKHCONP1BZ3ARFF3320 | DUKHCONP1BZ3ARFF3335, DUKHCONP1BZ3ARFF3345, DUKHCONP1BZ3ARFF3350, DUKHCONP1BZ3ARFF3335, DUKHCONP1BZ3ARFF3350, DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ3ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-05-01 | 2014-05-18 | 2014-05-01 | 2014-05-18 | 22 | No | DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ3ARFF3310, DUKHCONP1BZ3ARFF3325, DUKHCONP1BZ3ARFF3310 | DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-03-26 | 2014-04-12 | 2014-03-26 | 2014-04-12 | 3 | No | DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ2ARFF3315, DUKHCONP1BZ3ARFF3305 | DUKHCONP1BZ3ARFF3320, DUKHCONP1BZ4ARFF3315, DUKHCONP1BZ3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-06-01 | 2014-06-17 | 2014-06-01 | 2014-06-17 | 3 | No | DUKHCONP1BZ3ARFF3335, DUKHCONP1BZ3ARFF3350, DUKHCONP1BZ3ARFF3350, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ARFF3335, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ2ARFF3365 | DUKHCONP1BZ3ARFF3370, DUKHCONP1BZ3PLFF4335, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARFF3370, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3PLFF4335, DUKHCONP1BZ4ARFF3365 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.20 .15 .10 .20 ROOF |  | 65 | 65 | 0% | 2014-02-23 | 2014-05-08 | 2014-02-23 | 2014-05-08 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ3ARRF3600 | Block work | 20 | 20 | 0% | 2014-02-23 | 2014-03-17 | 2014-02-23 | 2014-03-17 | 78 | No | DUKHCONP1BZ3STRF2055, DUKHCONP1BZ2ARRF3600, DUKHCONP1BZ3STRF2055 | DUKHCONP1BZ3ARRF3605, DUKHCONP1BZ3ARRF3605, DUKHCONP1BZ4ARRF3600 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-04-22 | 2014-05-08 | 2014-04-22 | 2014-05-08 | 78 | No | DUKHCONP1BZ3ARRF3695, DUKHCONP1BZ3ARRF3695 | DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3ARRF3660, DUKHCONP1BZ3PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-03-24 | 2014-04-09 | 2014-03-24 | 2014-04-09 | 78 | No | DUKHCONP1BZ3ARRF3605, DUKHCONP1BZ3ARRF3605 | DUKHCONP1BZ3ARRF3695, DUKHCONP1BZ3ARRF3695 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-04-05 | 2014-04-27 | 2014-04-05 | 2014-04-27 | 78 | No | DUKHCONP1BZ3ARRF3610, DUKHCONP1BZ3ARRF3610 | DUKHCONP1BZ3AREL3680, DUKHCONP1BZ3ARRF3620, DUKHCONP1BZ3ARRF3620, DUKHCONP1BZ3AREL3680 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 78 | No | DUKHCONP1BZ3ARRF3600, DUKHCONP1BZ3ARRF3600 | DUKHCONP1BZ3AREL3665, DUKHCONP1BZ3ARRF3610, DUKHCONP1BZ3PLRF4345, DUKHCONP1BZ3ARRF3610, DUKHCONP1BZ3PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L25.20 .15 .15 EXTERNAL FINISHES |  | 63 | 63 | 0% | 2014-03-05 | 2014-05-17 | 2014-03-05 | 2014-05-17 | 76 |  |  |  | 0 | 0
DHBL.K30.L25.20 .15 .15 .10 ROOF |  | 61 | 61 | 0% | 2014-03-05 | 2014-05-14 | 2014-03-05 | 2014-05-14 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ3ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 78 | No | DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ARRF3645 | DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3ARRF3655 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-04-28 | 2014-05-14 | 2014-04-28 | 2014-05-14 | 78 | No | DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3ARRF3620 | DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ3ELTC8010 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 78 | No | DUKHCONP1BZ3ARRF3635, DUKHCONP1BZ3ARRF3635 | DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ARRF3645 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-04-10 | 2014-05-03 | 2014-04-10 | 2014-05-03 | 78 | No | DUKHCONP1BZ3ARRF3650, DUKHCONP1BZ2ARRF3655, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ARRF3650 | DUKHCONP1BZ3ARRF3660, DUKHCONP1BZ3ARRF3660, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ3ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 78 | No | DUKHCONP1BZ3ARRF3630, DUKHCONP1BZ3ARRF3630 | DUKHCONP1BZ3ARRF3640, DUKHCONP1BZ3ARRF3640 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 78 | No | DUKHCONP1BZ2ARRF3630, DUKHCONP1BZ3STRF2060, DUKHCONP1BZ3STRF2060, DUKHCONP1BZ3STRF2065, DUKHCONP1BZ3STRF2065 | DUKHCONP1BZ4ARRF3630, DUKHCONP1BZ3ARRF3635, DUKHCONP1BZ3ARRF3635 | 0 | 0 | ROOF
DUKHCONP1BZ3ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 78 | No | DUKHCONP1BZ3ARRF3640, DUKHCONP1BZ3ARRF3640 | DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ3ARRF3650, DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ3ARRF3650, DUKHCONP1BZ3ACRF4630 | 0 | 0 | ROOF
DHBL.K30.L25.20 .15 .15 .15 ELEVATION |  | 50 | 50 | 0% | 2014-03-20 | 2014-05-17 | 2014-03-20 | 2014-05-17 | 76 |  |  |  | 0 | 0
DUKHCONP1BZ3AREL3680 | External Painting | 20 | 20 | 0% | 2014-04-24 | 2014-05-17 | 2014-04-24 | 2014-05-17 | 76 | No | DUKHCONP1BZ3AREL3675, DUKHCONP1BZ3AREL3670, DUKHCONP1BZ3ARRF3695, DUKHCONP1BZ2AREL3680, DUKHCONP1BZ3AREL3675, DUKHCONP1BZ3AREL3670, DUKHCONP1BZ3ARRF3695 | DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ4AREL3680, DUKHCONP1BZ3ELTC8010 | 0 | 0 | ELEVATION
DUKHCONP1BZ3AREL3665 | External Plastering | 25 | 25 | 0% | 2014-03-20 | 2014-04-17 | 2014-03-20 | 2014-04-17 | 76 | No | DUKHCONP1BZ3STRF2065, DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3ARRF3605, DUKHCONP1BZ3STRF2065, DUKHCONP1BZ2AREL3665, DUKHCONP1BZ3ARFF3305 | DUKHCONP1BZ3AREL3670, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3AREL3675, DUKHCONP1BZ3AREL3675, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3AREL3670 | 0 | 0 | ELEVATION
DUKHCONP1BZ3AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-04-07 | 2014-04-29 | 2014-04-07 | 2014-04-29 | 76 | No | DUKHCONP1BZ3AREL3665, DUKHCONP1BZ2AREL3670, DUKHCONP1BZ3AREL3665 | DUKHCONP1BZ3AREL3680, DUKHCONP1BZ4AREL3670, DUKHCONP1BZ3AREL3680, DUKHCONP1BZ3AREL3675 | 0 | 0 | ELEVATION
DUKHCONP1BZ3AREL3675 | GRC works | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 76 | No | DUKHCONP1BZ3AREL3665, DUKHCONP1BZ3AREL3665, DUKHCONP1BZ2AREL3675, DUKHCONP1BZ3AREL3670 | DUKHCONP1BZ3AREL3680, DUKHCONP1BZ4AREL3675, DUKHCONP1BZ3AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L25.20 .20 MEP WORKS |  | 271 | 271 | 0% | 2013-09-24 | 2014-08-13 | 2013-09-24 | 2014-08-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.20 .20 .10 ELECTRICAL WORKS |  | 189 | 189 | 0% | 2014-01-01 | 2014-08-13 | 2014-01-01 | 2014-08-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.20 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-01-01 | 2014-05-11 | 2014-01-01 | 2014-05-11 | 56 |  |  |  | 0 | 0
DUKHCONP1BZ3ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-01-13 | 2014-02-04 | 2014-01-13 | 2014-02-04 | 76 | No | DUKHCONP1BZ3ELGF4000, DUKHCONP1BZ2ELGF4005, DUKHCONP1BZ3ELGF4000 | DUKHCONP1BZ3ELGF4010, DUKHCONP1BZ3ELGF4010, DUKHCONP1BZ4ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-01-01 | 2014-01-29 | 2014-01-01 | 2014-01-29 | 58 | No | DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ3ARGF3000 | DUKHCONP1BZ3ELGF4005, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3ELGF4005, DUKHCONP1BZ3ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 71 | No | DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ2ELGF4015, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ARGF3055 | DUKHCONP1BZ3ELFF4055, DUKHCONP1BZ3ELFF4055, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ4ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-04-01 | 2014-04-23 | 2014-04-01 | 2014-04-23 | 49 | No | DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ3ELGF4010, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ELGF4010, DUKHCONP1BZ3ARGF3060 | DUKHCONP1BZ3ELGF4030, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-04-13 | 2014-05-11 | 2014-04-13 | 2014-05-11 | 51 | No | DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ2ELGF4025, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ3ELGF4020 | DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ4ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 49 | No | DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ2ELGF4030, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ELGF4020 | DUKHCONP1BZ3ELFF4050, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ3ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 76 | No | DUKHCONP1BZ3ELGF4005, DUKHCONP1BZ3ELGF4005 | DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ3ELGF4020, DUKHCONP1BZ3ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.20 .20 .10 .15 FIRST FLOORS |  | 129 | 129 | 0% | 2014-02-12 | 2014-07-12 | 2014-02-12 | 2014-07-12 | 28 |  |  |  | 0 | 0
DUKHCONP1BZ3ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-02-24 | 2014-03-18 | 2014-02-24 | 2014-03-18 | 46 | No | DUKHCONP1BZ3ELFF4035, DUKHCONP1BZ3ELFF4035 | DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ3ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 16 | No | DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ3ARFF3300 | DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3ELFF4040, DUKHCONP1BZ3ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-05-25 | 2014-06-22 | 2014-05-25 | 2014-06-22 | 45 | No | DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ELGF4015, DUKHCONP1BZ3ELGF4015, DUKHCONP1BZ2ELFF4055, DUKHCONP1BZ3ARFF3360 | DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ4ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-06-01 | 2014-06-23 | 2014-06-01 | 2014-06-23 | 3 | No | DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ2ELFF4060, DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ3ARFF3360 | DUKHCONP1BZ4ELFF4060, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ3ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 3 | No | DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ2ELFF4065, DUKHCONP1BZ3ARFF3360 | DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ3ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 25 | No | DUKHCONP1BZ3ELGF4030, DUKHCONP1BZ3MSEX5010, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ELGF4030 | DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ3ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 46 | No | DUKHCONP1BZ3ELFF4040, DUKHCONP1BZ2ELFF4045, DUKHCONP1BZ3ELFF4040 | DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ4ELFF4045, DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ3ARFF3345, DUKHCONP1BZ3ARFF3345 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.20 .20 .10 .20 ROOF |  | 33 | 33 | 0% | 2014-07-03 | 2014-08-13 | 2014-07-03 | 2014-08-13 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ3ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-07-03 | 2014-07-23 | 2014-07-03 | 2014-07-23 | 3 | No | DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ3ELFF4050, DUKHCONP1BZ3ELFF4050, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ELFF4065 | DUKHCONP1BZ3ELRF4075, DUKHCONP1BZ3ELRF4075 | 0 | 0 | ROOF
DUKHCONP1BZ3ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-07-15 | 2014-08-13 | 2014-07-15 | 2014-08-13 | 3 | No | DUKHCONP1BZ3ELRF4070, DUKHCONP1BZ3ELRF4070 | DUKHCONP1BZ3ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L25.20 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 255 | 255 | 0% | 2013-09-24 | 2014-07-22 | 2013-09-24 | 2014-07-22 | 19 |  |  |  | 0 | 0
DHBL.K30.L25.20 .20 .15 .10 GROUND FLOOR |  | 193 | 193 | 0% | 2013-09-24 | 2014-05-11 | 2013-09-24 | 2014-05-11 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-09-24 | 2013-10-16 | 2013-09-24 | 2013-10-16 | 11 | No | DUKHCONP1BZ3STUG1040, DUKHCONP1BZ3STUG1040 | DUKHCONP1BZ3STUG1045, DUKHCONP1BZ3STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-01-12 | 2014-02-01 | 2014-01-12 | 2014-02-01 | 52 | No | DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ3ARGF3000 | DUKHCONP1BZ3MSEX5000, DUKHCONP1BZ3PLGF4315, DUKHCONP1BZ3MSEX5000, DUKHCONP1BZ3ARGF3020, DUKHCONP1BZ3PLGF4315, DUKHCONP1BZ3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-01-12 | 2014-02-01 | 2014-01-12 | 2014-02-01 | 49 | No | DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ2PLGF4305, DUKHCONP1BZ3ARGF3000 | DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ3ARGF3020, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-04-24 | 2014-05-11 | 2014-04-24 | 2014-05-11 | 81 | No | DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ2PLGF4320, DUKHCONP1BZ3PLGF4315, DUKHCONP1BZ3PLGF4315 | DUKHCONP1BZ4PLGF4320, DUKHCONP1BZ3PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 81 | No | DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ2PLGF4315 | DUKHCONP1BZ3PLGF4320, DUKHCONP1BZ3PLGF4320, DUKHCONP1BZ4PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.20 .20 .15 .15 FIRST FLOORS |  | 113 | 113 | 0% | 2014-02-24 | 2014-07-05 | 2014-02-24 | 2014-07-05 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ3PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-02-24 | 2014-03-16 | 2014-02-24 | 2014-03-16 | 30 | No | DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ3PLFF4325, DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ3PLFF4325, DUKHCONP1BZ2PLFF4330 | DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3PLFF4335, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ3ARFF3320, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3PLFF4335, DUKHCONP1BZ3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-02-24 | 2014-03-16 | 2014-02-24 | 2014-03-16 | 3 | No | DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ3ARFF3300 | DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3ARFF3320, DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-06-18 | 2014-07-05 | 2014-06-18 | 2014-07-05 | 19 | No | DUKHCONP1BZ2PLFF4340, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3PLFF4335, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3PLFF4335 | DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ4PLFF4340, DUKHCONP1BZ3PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-06-07 | 2014-06-29 | 2014-06-07 | 2014-06-29 | 19 | No | DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ3PLFF4330 | DUKHCONP1BZ3PLFF4340, DUKHCONP1BZ3PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.20 .20 .15 .20 ROOF |  | 105 | 105 | 0% | 2014-03-23 | 2014-07-22 | 2014-03-23 | 2014-07-22 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ3PLRF4345 | Installation of Plumbing pipes & fittings | 14 | 14 | 0% | 2014-03-23 | 2014-04-07 | 2014-03-23 | 2014-04-07 | 84 | No | DUKHCONP1BZ2PLRF4345, DUKHCONP1BZ3ARRF3605, DUKHCONP1BZ3ARRF3605 | DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ4PLRF4345 | 0 | 0 | ROOF
DUKHCONP1BZ3PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-04-09 | 2014-04-26 | 2014-04-09 | 2014-04-26 | 79 | No | DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3PLRF4345, DUKHCONP1BZ3PLRF4345, DUKHCONP1BZ3AREL3665, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ3AREL3665, DUKHCONP1BZ2PLRF4350 | DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ3PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ3PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-06-24 | 2014-07-22 | 2014-06-24 | 2014-07-22 | 19 | No | DUKHCONP1BZ3PLFF4340, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ2PLRF4355, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3PLRF4345, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3PLRF4345, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3PLFF4340 | DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ4PLRF4355 | 0 | 0 | ROOF
DHBL.K30.L25.20 .20 .20 AC WORKS |  | 144 | 144 | 0% | 2014-02-01 | 2014-07-19 | 2014-02-01 | 2014-07-19 | 22 |  |  |  | 0 | 0
DHBL.K30.L25.20 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-02-01 | 2014-05-08 | 2014-02-01 | 2014-05-08 | 68 |  |  |  | 0 | 0
DUKHCONP1BZ3ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-04-16 | 2014-05-08 | 2014-04-16 | 2014-05-08 | 68 | No | DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ2ACGF4610, DUKHCONP1BZ3ACGF4605 | DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ4ACGF4610, DUKHCONP1BZ3ACRF4635, DUKHCONP1BZ3ACRF4635, DUKHCONP1BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 68 | No | DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ2ACGF4605, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ3ACGF4600 | DUKHCONP1BZ3ACGF4610, DUKHCONP1BZ3ACGF4610, DUKHCONP1BZ4ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ3ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-02-01 | 2014-02-24 | 2014-02-01 | 2014-02-24 | 80 | No | DUKHCONP1BZ2ACGF4600, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ3ARGF3005 | DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ3ARGF3055, DUKHCONP1BZ3ACRF4630 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.20 .20 .20 .15 FIRST FLOORS |  | 95 | 95 | 0% | 2014-03-19 | 2014-07-07 | 2014-03-19 | 2014-07-07 | 17 |  |  |  | 0 | 0
DUKHCONP1BZ3ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-06-15 | 2014-07-07 | 2014-06-15 | 2014-07-07 | 17 | No | DUKHCONP1BZ3ACFF4620, DUKHCONP1BZ2ACFF4625, DUKHCONP1BZ3ACFF4620 | DUKHCONP1BZ3ACRF4635, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ACRF4635, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ4ACFF4625, DUKHCONP1BZ3ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-05-25 | 2014-06-22 | 2014-05-25 | 2014-06-22 | 17 | No | DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ2ACFF4620, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ3ARFF3360 | DUKHCONP1BZ4ACFF4620, DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ3ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ3ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 46 | No | DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ2ACFF4615, DUKHCONP1BZ3ARFF3305 | DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ3ACFF4620, DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ3ACFF4620, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ3ARFF3360 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.20 .20 .20 .20 ROOF |  | 95 | 95 | 0% | 2014-03-31 | 2014-07-19 | 2014-03-31 | 2014-07-19 | 22 |  |  |  | 0 | 0
DUKHCONP1BZ3ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-06-21 | 2014-07-19 | 2014-06-21 | 2014-07-19 | 22 | No | DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ2ACRF4635, DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ3ACGF4610, DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ3ACGF4610 | DUKHCONP1BZ4ACRF4635, DUKHCONP1BZ3ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ3ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 87 | No | DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ2ACRF4630, DUKHCONP1BZ3ACFF4615, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ARRF3645, DUKHCONP1BZ3ACGF4600 | DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ3ACRF4635, DUKHCONP1BZ3ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L25.20 .25 EXTERNAL WORKS |  | 161 | 161 | 0% | 2014-02-06 | 2014-08-17 | 2014-02-06 | 2014-08-17 | 25 |  |  |  | 0 | 0
DHBL.K30.L25.20 .25 .10 MISCELLANEOUS |  | 161 | 161 | 0% | 2014-02-06 | 2014-08-17 | 2014-02-06 | 2014-08-17 | 25 |  |  |  | 0 | 0
DUKHCONP1BZ3MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 25 | No | DUKHCONP1BZ2MSEX5335, DUKHCONI1BZ2BWGL5325 | DUKHCONP1BZ4MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ3MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 38 | No | DUKHCONP1BZ3MSEX5000, DUKHCONP1BZ3MSEX5000 | DUKHCONP1BZ3MSEX5015, DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3MSEX5015, DUKHCONP1BZ3ELTC8010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ3MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-02-06 | 2014-03-08 | 2014-02-06 | 2014-03-08 | 69 | No | DUKHCONP1BZ2MSEX5020, DUKHCONP1BZ3STRF2055, DUKHCONP1BZ3STRF2055 | DUKHCONP1BZ3HDEX5090, DUKHCONP1BZ3MSEX5025, DUKHCONP1BZ3MSEX5025, DUKHCONP1BZ3HDEX5090, DUKHCONP1BZ4MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ3MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-03-16 | 2014-04-07 | 2014-03-16 | 2014-04-07 | 38 | No | DUKHCONP1BZ3MSEX5005, DUKHCONP1BZ3MSEX5005 | DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ3MSEX5010, DUKHCONP1BZ3WEEX5050, DUKHCONP1BZ3WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ3MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 38 | No | DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ3PLGF4310, DUKHCONP1BZ3STRF2055, DUKHCONP1BZ3STRF2055 | DUKHCONP1BZ3MSEX5005, DUKHCONP1BZ3MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ3MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-02-25 | 2014-03-19 | 2014-02-25 | 2014-03-19 | 71 | No | DUKHCONP1BZ3MSEX5020, DUKHCONP1BZ3MSEX5020 | DUKHCONP1BZ3WEEX5050, DUKHCONP1BZ3WEEX5045, DUKHCONP1BZ3WEEX5060, DUKHCONP1BZ3HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ3MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 38 | No | DUKHCONP1BZ3MSEX5015 | DUKHCONP1BZ3ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L25.20 .25 .15 WATER TANK ENCLOSURE |  | 83 | 83 | 0% | 2014-02-22 | 2014-05-28 | 2014-02-22 | 2014-05-28 | 66 |  |  |  | 0 | 0
DUKHCONP1BZ3WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 66 | No | DUKHCONP1BZ3WEEX5035, DUKHCONP1BZ3WEEX5035 | DUKHCONP1BZ3WEEX5045, DUKHCONP1BZ3WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ3WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 51 | No | DUKHCONP1BZ3WEEX5030, DUKHCONP1BZ3WEEX5030 | DUKHCONP1BZ3WEEX5040, DUKHCONP1BZ3WEEX5040, DUKHCONP1BZ4WEEX5030 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ3WEEX5030 | Excavation | 20 | 20 | 0% | 2014-02-22 | 2014-03-16 | 2014-02-22 | 2014-03-16 | 51 | No | DUKHCONP1BZ2WEEX5035, DUKHCONP1BZ3STRF2055, DUKHCONP1BZ3STRF2060, DUKHCONP1BZ3STRF2055 | DUKHCONP1BZ3WEEX5035, DUKHCONP1BZ3WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ3WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 66 | No | DUKHCONP1BZ3MSEX5025, DUKHCONP1BZ3WEEX5040, DUKHCONP1BZ3WEEX5040 | DUKHCONP1BZ3WEEX5050, DUKHCONP1BZ3WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ3WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 66 | No | DUKHCONP1BZ3MSEX5015, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3MSEX5015, DUKHCONP1BZ2WEEX5065, DUKHCONP1BZ3WEEX5060, DUKHCONP1BZ3WEEX5060 | DUKHCONP1BZ4WEEX5065, DUKHCONP1BZ3PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ3WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 66 | No | DUKHCONP1BZ3MSEX5025, DUKHCONP1BZ3MSEX5015, DUKHCONP1BZ3WEEX5045, DUKHCONP1BZ3WEEX5045 | DUKHCONP1BZ3WEEX5060, DUKHCONP1BZ3WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ3WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 66 | No | DUKHCONP1BZ2WEEX5060, DUKHCONP1BZ3MSEX5025, DUKHCONP1BZ3WEEX5050, DUKHCONP1BZ3WEEX5050 | DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ4WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L25.20 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2014-03-05 | 2014-04-23 | 2014-03-05 | 2014-04-23 | 71 |  |  |  | 0 | 0
DUKHCONP1BZ3HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 71 | No | DUKHCONP1BZ3HDEX5090, DUKHCONP1BZ3HDEX5090 | DUKHCONP1BZ3HDEX5100, DUKHCONP1BZ3HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ3HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-04-01 | 2014-04-23 | 2014-04-01 | 2014-04-23 | 71 | No | DUKHCONP1BZ3HDEX5095, DUKHCONP1BZ3HDEX5095 | DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ3PLTC8005, DUKHCONP1BZ3SLEX5105, DUKHCONP1BZ3SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ3HDEX5090 | kerb works | 20 | 20 | 0% | 2014-03-05 | 2014-03-27 | 2014-03-05 | 2014-03-27 | 71 | No | DUKHCONP1BZ3MSEX5020, DUKHCONP1BZ3MSEX5025, DUKHCONP1BZ2HDEX5090, DUKHCONP1BZ3MSEX5020 | DUKHCONP1BZ3HDEX5095, DUKHCONP1BZ4HDEX5090, DUKHCONP1BZ3HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L25.20 .25 .25 SOFT LANDSCAPING |  | 35 | 35 | 0% | 2014-04-13 | 2014-05-22 | 2014-04-13 | 2014-05-22 | 71 |  |  |  | 0 | 0
DUKHCONP1BZ3SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-04-13 | 2014-05-11 | 2014-04-13 | 2014-05-11 | 71 | No | DUKHCONP1BZ3HDEX5100, DUKHCONP1BZ3HDEX5100 | DUKHCONP1BZ3SLEX5110, DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3SLEX5110, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ3PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1BZ3SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 71 | No | DUKHCONP1BZ3SLEX5105, DUKHCONP1BZ3SLEX5105 | DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ3PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L25.20 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-08-14 | 2014-09-11 | 2014-08-14 | 2014-09-11 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ3ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-08-14 | 2014-09-11 | 2014-08-14 | 2014-09-11 | 3 | No | DUKHCONP1BZ3ARRF3660, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3HDEX5100, DUKHCONP1BZ3SLEX5110, DUKHCONP1BZ3AREL3680, DUKHCONP1BZ3MSEX5005, DUKHCONP1BZ3SLEX5105, DUKHCONP1BZ2ACTC8000, DUKHCONP1BZ3ARRF3620, DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3ACRF4635 | DUKHHANP1BGNACTC9000, DUKHCONP1BZ4ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-08-14 | 2014-09-11 | 2014-08-14 | 2014-09-11 | 3 | No | DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ3HDEX5100, DUKHCONP1BZ3ARRF3620, DUKHCONP1BZ3ELFF4055, DUKHCONP1BZ3ELGF4015, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3SLEX5110, DUKHCONP1BZ3ELGF4030, DUKHCONP1BZ3SLEX5105, DUKHCONP1BZ3AREL3680, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ3MSEX5005, DUKHCONP1BZ3ELFF4050, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3ARRF3660, DUKHCONP1BZ3ELRF4075 | DUKHHANP1BGNELTC9010, DUKHCONP1BZ4ELTC8010, DUKHHANP1BGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-08-14 | 2014-09-11 | 2014-08-14 | 2014-09-11 | 3 | No | DUKHCONP1BZ3MSEX5005, DUKHCONP1BZ3AREL3680, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ3HDEX5100, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ3ARRF3660, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ3SLEX5105, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ3SLEX5110, DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ3ARRF3620, DUKHCONP1BZ3PLGF4320 | DUKHHANP1BGNPLTC9005, DUKHCONP1BZ4PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L25.25 ZONE - 4 (4 Twin Villas) |  | 383 | 383 | 0% | 2013-07-10 | 2014-10-13 | 2013-07-10 | 2014-10-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.25 .10 STRUCTURAL WORKS |  | 237 | 237 | 0% | 2013-07-10 | 2014-04-20 | 2013-07-10 | 2014-04-20 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.25 .10 .10 SUB STRUCTURE |  | 120 | 120 | 0% | 2013-07-10 | 2013-12-02 | 2013-07-10 | 2013-12-02 | 11 |  |  |  | 0 | 0
DHBL.K30.L25.25 .10 .10 .10 UPTO GRADE SLAB |  | 120 | 120 | 0% | 2013-07-10 | 2013-12-02 | 2013-07-10 | 2013-12-02 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ4STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-09-19 | 2013-10-20 | 2013-09-19 | 2013-10-20 | 11 | No | DUKHCONP1BZ4STUG1030, DUKHCONP1BZ4STUG1030, DUKHCONP1BZ3STUG1035 | DUKHCONP1BZ5STUG1035, DUKHCONP1BZ4STUG1040, DUKHCONP1BZ4STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-08-20 | 2013-09-11 | 2013-08-20 | 2013-09-11 | 11 | No | DUKHCONP1BZ4STUG1015, DUKHCONP1BZ4STUG1015 | DUKHCONP1BZ4STUG1025, DUKHCONP1BZ4STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-10-06 | 2013-11-05 | 2013-10-06 | 2013-11-05 | 11 | No | DUKHCONP1BZ4STUG1035, DUKHCONP1BZ4STUG1035 | DUKHCONP1BZ4STUG1045, DUKHCONP1BZ4STUG1045, DUKHCONP1BZ4PLUG4300, DUKHCONP1BZ4PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-08-29 | 2013-09-26 | 2013-08-29 | 2013-09-26 | 11 | No | DUKHCONP1BZ3STUG1025, DUKHCONP1BZ4STUG1020, DUKHCONP1BZ4STUG1020 | DUKHCONP1BZ5STUG1025, DUKHCONP1BZ4STUG1030, DUKHCONP1BZ4STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 11 | No | DUKHCONP1BZ4STUG1040, DUKHCONP1BZ4PLUG4300, DUKHCONP1BZ3STUG1045, DUKHCONP1BZ4PLUG4300, DUKHCONP1BZ4STUG1040 | DUKHCONP1BZ4STGF2000, DUKHCONP1BZ5STUG1045, DUKHCONP1BZ4STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-07-22 | 2013-08-20 | 2013-07-22 | 2013-08-20 | 11 | No | DUKHCONP1BZ4STUG1000, DUKHCONP1BZ4STUG1000 | DUKHCONP1BZ4STUG1010, DUKHCONP1BZ4STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-07-27 | 2013-08-25 | 2013-07-27 | 2013-08-25 | 11 | No | DUKHCONP1BZ4STUG1005, DUKHCONP1BZ4STUG1005 | DUKHCONP1BZ4STUG1015, DUKHCONP1BZ4STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-07-10 | 2013-08-07 | 2013-07-10 | 2013-08-07 | 11 | No | DUKHCONP1BZ3STUG1000 | DUKHCONP1BZ4STUG1005, DUKHCONP1BZ5STUG1000, DUKHCONP1BZ4STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-08-01 | 2013-09-02 | 2013-08-01 | 2013-09-02 | 11 | No | DUKHCONP1BZ4STUG1010, DUKHCONP1BZ4STUG1010 | DUKHCONP1BZ4STUG1020, DUKHCONP1BZ4STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ4STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-09-08 | 2013-10-06 | 2013-09-08 | 2013-10-06 | 11 | No | DUKHCONP1BZ4STUG1025, DUKHCONP1BZ4STUG1025 | DUKHCONP1BZ4STUG1035, DUKHCONP1BZ4STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L25.25 .10 .15 SUPERSTRUCTURE |  | 128 | 128 | 0% | 2013-11-20 | 2014-04-20 | 2013-11-20 | 2014-04-20 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.25 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-11-20 | 2014-01-15 | 2013-11-20 | 2014-01-15 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ4STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2013-12-31 | 2014-01-15 | 2013-12-31 | 2014-01-15 | 11 | No | DUKHCONP1BZ4STGF2010, DUKHCONP1BZ4STGF2010, DUKHCONP1BZ3STGF2015 | DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ5STGF2015, DUKHCONP1BZ4STFF2020, DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ4STFF2020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 11 | No | DUKHCONP1BZ4STGF2005, DUKHCONP1BZ4STGF2005 | DUKHCONP1BZ4STGF2015, DUKHCONP1BZ4STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4STGF2005 | Column-Concrete | 23 | 23 | 0% | 2013-11-30 | 2013-12-26 | 2013-11-30 | 2013-12-26 | 11 | No | DUKHCONP1BZ4STGF2000, DUKHCONP1BZ4STGF2000 | DUKHCONP1BZ4STGF2010, DUKHCONP1BZ4STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-11-20 | 2013-12-19 | 2013-11-20 | 2013-12-19 | 11 | No | DUKHCONP1BZ4STUG1045, DUKHCONP1BZ3STGF2000, DUKHCONP1BZ4STUG1045 | DUKHCONP1BZ5STGF2000, DUKHCONP1BZ4STGF2005, DUKHCONP1BZ4STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.25 .10 .15 .15 FIRST FLOORS |  | 39 | 39 | 0% | 2014-01-02 | 2014-02-17 | 2014-01-02 | 2014-02-17 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ4STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-02-01 | 2014-02-17 | 2014-02-01 | 2014-02-17 | 11 | No | DUKHCONP1BZ4STFF2030, DUKHCONP1BZ3STFF2035, DUKHCONP1BZ4STFF2030 | DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ5STFF2035, DUKHCONP1BZ4STRF2040, DUKHCONP1BZ4STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-01-15 | 2014-02-13 | 2014-01-15 | 2014-02-13 | 11 | No | DUKHCONP1BZ4STFF2025, DUKHCONP1BZ4STFF2025 | DUKHCONP1BZ4STFF2035, DUKHCONP1BZ4STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4STFF2025 | Column-Concrete | 23 | 23 | 0% | 2014-01-12 | 2014-02-06 | 2014-01-12 | 2014-02-06 | 11 | No | DUKHCONP1BZ4STFF2020, DUKHCONP1BZ4STFF2020 | DUKHCONP1BZ4STFF2030, DUKHCONP1BZ4STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 11 | No | DUKHCONP1BZ4STGF2015, DUKHCONP1BZ3STFF2020, DUKHCONP1BZ4STGF2015 | DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ5STFF2020, DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ4STFF2025, DUKHCONP1BZ4STFF2025 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.25 .10 .15 .20 ROOF |  | 62 | 62 | 0% | 2014-02-06 | 2014-04-20 | 2014-02-06 | 2014-04-20 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ4STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-02-10 | 2014-03-02 | 2014-02-10 | 2014-03-02 | 37 | No | DUKHCONP1BZ4STRF2040, DUKHCONP1BZ4STRF2040 | DUKHCONP1BZ4STRF2050, DUKHCONP1BZ4STRF2050 | 0 | 0 | ROOF
DUKHCONP1BZ4STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-02-06 | 2014-02-27 | 2014-02-06 | 2014-02-27 | 27 | No | DUKHCONP1BZ3STRF2040, DUKHCONP1BZ4STFF2035, DUKHCONP1BZ4STFF2035 | DUKHCONP1BZ5STRF2040, DUKHCONP1BZ4STRF2045, DUKHCONP1BZ4STRF2045 | 0 | 0 | ROOF
DUKHCONP1BZ4STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 73 | No | DUKHCONP1BZ4STRF2055, DUKHCONP1BZ4STRF2055 | DUKHCONP1BZ4ARRF3630, DUKHCONP1BZ5STRF2060, DUKHCONP1BZ4ARRF3630, DUKHCONP1BZ4STRF2065, DUKHCONP1BZ4STRF2065 | 0 | 0 | ROOF
DUKHCONP1BZ4STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-03-23 | 2014-04-20 | 2014-03-23 | 2014-04-20 | 78 | No | DUKHCONP1BZ3STRF2065, DUKHCONP1BZ4STRF2060, DUKHCONP1BZ4STRF2060 | DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4ARRF3630, DUKHCONP1BZ5STRF2065, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4ARRF3630 | 0 | 0 | ROOF
DUKHCONP1BZ4STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-02-27 | 2014-03-13 | 2014-02-27 | 2014-03-13 | 37 | No | DUKHCONP1BZ3STRF2055, DUKHCONP1BZ4STRF2050, DUKHCONP1BZ4STRF2050 | DUKHCONP1BZ4WEEX5030, DUKHCONP1BZ4STRF2060, DUKHCONP1BZ4ARRF3600, DUKHCONP1BZ4STRF2060, DUKHCONP1BZ4MSEX5000, DUKHCONP1BZ5STRF2055, DUKHCONP1BZ4MSEX5020, DUKHCONP1BZ4WEEX5030, DUKHCONP1BZ4ARRF3600, DUKHCONP1BZ4MSEX5000, DUKHCONP1BZ4MSEX5020 | 0 | 0 | ROOF
DUKHCONP1BZ4STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-02-13 | 2014-03-08 | 2014-02-13 | 2014-03-08 | 37 | No | DUKHCONP1BZ4STRF2045, DUKHCONP1BZ4STRF2045 | DUKHCONP1BZ4STRF2055, DUKHCONP1BZ4STRF2055 | 0 | 0 | ROOF
DHBL.K30.L25.25 .15 FINISHING WORKS |  | 194 | 194 | 0% | 2014-01-25 | 2014-09-11 | 2014-01-25 | 2014-09-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.25 .15 .10 INTERNAL FINISHES |  | 194 | 194 | 0% | 2014-01-25 | 2014-09-11 | 2014-01-25 | 2014-09-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.25 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-01-25 | 2014-07-07 | 2014-01-25 | 2014-07-07 | 57 |  |  |  | 0 | 0
DUKHCONP1BZ4ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-05-12 | 2014-05-28 | 2014-05-12 | 2014-05-28 | 57 | No | DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ3ARGF3070 | DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ4ARGF3075, DUKHCONP1BZ4ARGF3080, DUKHCONP1BZ4ARGF3075, DUKHCONP1BZ4ARGF3080, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-04-13 | 2014-05-11 | 2014-04-13 | 2014-05-11 | 52 | No | DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ4ARGF3045 | DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ4ACGF4605, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ4ELGF4025, DUKHCONP1BZ4ACGF4605, DUKHCONP1BZ4ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-05-19 | 2014-06-10 | 2014-05-19 | 2014-06-10 | 67 | No | DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ3ARGF3080 | DUKHCONP1BZ5ARGF3080, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3000 | Block work | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 49 | No | DUKHCONP1BZ4STGF2015, DUKHCONP1BZ3ARGF3000, DUKHCONP1BZ4STGF2015 | DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4ELGF4000, DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ4PLGF4310, DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4ELGF4000, DUKHCONP1BZ4PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-05-18 | 2014-06-09 | 2014-05-18 | 2014-06-09 | 57 | No | DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ3ARGF3075 | DUKHCONP1BZ4ARGF3090, DUKHCONP1BZ4ARGF3085, DUKHCONP1BZ4ARGF3090, DUKHCONP1BZ4ARGF3085, DUKHCONP1BZ5ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-03-12 | 2014-04-09 | 2014-03-12 | 2014-04-09 | 49 | No | DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ4PLGF4310, DUKHCONP1BZ4ARGF3015, DUKHCONP1BZ3ARGF3020, DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ4ARGF3015, DUKHCONP1BZ4PLGF4310 | DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-04-14 | 2014-04-30 | 2014-04-14 | 2014-04-30 | 57 | No | DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3010, DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3010, DUKHCONP1BZ4ARGF3035 | DUKHCONP1BZ4ARGF3050, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3050, DUKHCONP1BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 57 | No | DUKHCONP1BZ4ARGF3090, DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3030, DUKHCONP1BZ4ARGF3080, DUKHCONP1BZ4ARGF3085, DUKHCONP1BZ4ACGF4610, DUKHCONP1BZ3ARGF3095, DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ4ARGF3080, DUKHCONP1BZ4ACGF4610, DUKHCONP1BZ4ARGF3030, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ4ARGF3090, DUKHCONP1BZ4ARGF3085 | DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-04-05 | 2014-04-27 | 2014-04-05 | 2014-04-27 | 49 | No | DUKHCONP1BZ4ARGF3030, DUKHCONP1BZ4ELGF4010, DUKHCONP1BZ3ARGF3045, DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3030, DUKHCONP1BZ4ELGF4010, DUKHCONP1BZ4ARGF3025 | DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-02-25 | 2014-03-20 | 2014-02-25 | 2014-03-20 | 57 | No | DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4ARGF3005 | DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-04-22 | 2014-05-14 | 2014-04-22 | 2014-05-14 | 57 | No | DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3040 | DUKHCONP1BZ4ARGF3085, DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ4ARGF3085, DUKHCONP1BZ4ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 49 | No | DUKHCONP1BZ3ARGF3060, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ACGF4600 | DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ4ELGF4025, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4PLGF4320, DUKHCONP1BZ4ACGF4605, DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ4PLGF4320, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ4ELGF4025, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ4ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-05-31 | 2014-06-16 | 2014-05-31 | 2014-06-16 | 57 | No | DUKHCONP1BZ4ARGF3075, DUKHCONP1BZ4ARGF3075 | DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 63 | No | DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ3ARGF3030, DUKHCONP1BZ4ARGF3005 | DUKHCONP1BZ5ARGF3030, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 49 | No | DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ4ELGF4000, DUKHCONP1BZ4ELGF4000, DUKHCONP1BZ3ARGF3005, DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ4ARGF3000 | DUKHCONP1BZ4ARGF3010, DUKHCONP1BZ4ARGF3015, DUKHCONP1BZ4ARGF3010, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ARGF3030, DUKHCONP1BZ4ARGF3015, DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 49 | No | DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ4ARGF3010, DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ3ARGF3025, DUKHCONP1BZ4ARGF3010 | DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3050, DUKHCONP1BZ4ARGF3050, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-05-26 | 2014-06-17 | 2014-05-26 | 2014-06-17 | 62 | No | DUKHCONP1BZ4ARGF3050, DUKHCONP1BZ4ARGF3075, DUKHCONP1BZ4ARGF3050, DUKHCONP1BZ4ARGF3075 | DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-04-07 | 2014-04-23 | 2014-04-07 | 2014-04-23 | 59 | No | DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ4ARGF3010, DUKHCONP1BZ4ARGF3010 | DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3040, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-03-06 | 2014-03-23 | 2014-03-06 | 2014-03-23 | 49 | No | DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ3ARGF3015 | DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ5ARGF3015, DUKHCONP1BZ4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-05-06 | 2014-05-22 | 2014-05-06 | 2014-05-22 | 57 | No | DUKHCONP1BZ3ARGF3065, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3035, DUKHCONP1BZ4ARGF3050, DUKHCONP1BZ4ARGF3050 | DUKHCONP1BZ5ARGF3065, DUKHCONP1BZ4PLGF4315, DUKHCONP1BZ4PLGF4315, DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ4ARGF3070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.25 .15 .10 .15 FIRST FLOORS |  | 159 | 159 | 0% | 2014-03-08 | 2014-09-11 | 2014-03-08 | 2014-09-11 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ4ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-07-08 | 2014-07-30 | 2014-07-08 | 2014-07-30 | 3 | No | DUKHCONP1BZ3ARFF3370, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4ARFF3365 | DUKHCONP1BZ5ARFF3370, DUKHCONP1BZ4ARFF3380, DUKHCONP1BZ4ARFF3380, DUKHCONP1BZ4ARFF3375, DUKHCONP1BZ4ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-07-15 | 2014-08-10 | 2014-07-15 | 2014-08-10 | 16 | No | DUKHCONP1BZ4ARFF3370, DUKHCONP1BZ4ARFF3370 | DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3300 | Block work | 25 | 25 | 0% | 2014-03-08 | 2014-04-05 | 2014-03-08 | 2014-04-05 | 3 | No | DUKHCONP1BZ4STFF2020, DUKHCONP1BZ4STFF2035, DUKHCONP1BZ4STFF2035, DUKHCONP1BZ3ARFF3300, DUKHCONP1BZ4STFF2020 | DUKHCONP1BZ4PLFF4325, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4PLFF4325, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4ELFF4035, DUKHCONP1BZ4ELFF4035, DUKHCONP1BZ5ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-07-16 | 2014-08-17 | 2014-07-16 | 2014-08-17 | 3 | No | DUKHCONP1BZ4ARFF3370, DUKHCONP1BZ3ARFF3375, DUKHCONP1BZ4ARFF3370 | DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3390, DUKHCONP1BZ4ARFF3385, DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ4ARFF3385, DUKHCONP1BZ4ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 3 | No | DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4PLFF4325, DUKHCONP1BZ4PLFF4325, DUKHCONP1BZ3ARFF3320, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4ARFF3315, DUKHCONP1BZ4ARFF3315 | DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ5ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-08-14 | 2014-09-11 | 2014-08-14 | 2014-09-11 | 3 | No | DUKHCONP1BZ4ARFF3385, DUKHCONP1BZ4ARFF3330, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ARFF3375, DUKHCONP1BZ4ARFF3375, DUKHCONP1BZ4ARFF3335, DUKHCONP1BZ4ARFF3385, DUKHCONP1BZ4ARFF3335, DUKHCONP1BZ4ARFF3380, DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4ARFF3390, DUKHCONP1BZ4ARFF3330, DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3390, DUKHCONP1BZ4ACFF4625, DUKHCONP1BZ4ACFF4625, DUKHCONP1BZ3ARFF3395, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ARFF3380 | DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4PLTC8005 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-06-03 | 2014-06-25 | 2014-06-03 | 2014-06-25 | 3 | No | DUKHCONP1BZ4ARFF3330, DUKHCONP1BZ4ELFF4045, DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ4ELFF4045, DUKHCONP1BZ4ARFF3330, DUKHCONP1BZ3ARFF3345 | DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ5ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-04-12 | 2014-05-05 | 2014-04-12 | 2014-05-05 | 20 | No | DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4ARFF3305 | DUKHCONP1BZ4ARFF3335, DUKHCONP1BZ4ARFF3335, DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ4ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-06-03 | 2014-06-25 | 2014-06-03 | 2014-06-25 | 14 | No | DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ4ARFF3325 | DUKHCONP1BZ4ARFF3385, DUKHCONP1BZ4ARFF3385, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 3 | No | DUKHCONP1BZ4ARFF3345, DUKHCONP1BZ3ARFF3360, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ4ARFF3345, DUKHCONP1BZ4ACFF4615 | DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ELFF4055, DUKHCONP1BZ4ELFF4060, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ4ELFF4060, DUKHCONP1BZ4ACFF4620, DUKHCONP1BZ4ACFF4620, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4ELFF4050, DUKHCONP1BZ4PLFF4340, DUKHCONP1BZ4ELFF4055, DUKHCONP1BZ4PLFF4340, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ELFF4050, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ4ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-07-30 | 2014-08-25 | 2014-07-30 | 2014-08-25 | 3 | No | DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3375, DUKHCONP1BZ4ARFF3375 | DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-07-30 | 2014-08-25 | 2014-07-30 | 2014-08-25 | 5 | No | DUKHCONP1BZ4ARFF3375, DUKHCONP1BZ4ARFF3375 | DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 29 | No | DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4ARFF3305 | DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3345, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 3 | No | DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ3ARFF3305, DUKHCONP1BZ4PLFF4325, DUKHCONP1BZ4PLFF4325, DUKHCONP1BZ4ELFF4035, DUKHCONP1BZ4ELFF4035 | DUKHCONP1BZ4ARFF3315, DUKHCONP1BZ4ARFF3310, DUKHCONP1BZ4ARFF3330, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4ARFF3310, DUKHCONP1BZ4ARFF3330, DUKHCONP1BZ4ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-05-13 | 2014-06-10 | 2014-05-13 | 2014-06-10 | 3 | No | DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ4ARFF3310, DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ4ARFF3310, DUKHCONP1BZ3ARFF3325 | DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3345, DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ4ARFF3345, DUKHCONP1BZ4ARFF3335, DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-05-31 | 2014-06-16 | 2014-05-31 | 2014-06-16 | 22 | No | DUKHCONP1BZ4ARFF3310, DUKHCONP1BZ4ARFF3310, DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ4ARFF3325 | DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-04-24 | 2014-05-11 | 2014-04-24 | 2014-05-11 | 3 | No | DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ3ARFF3315, DUKHCONP1BZ4ARFF3305 | DUKHCONP1BZ5ARFF3315, DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ4ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-06-30 | 2014-07-16 | 2014-06-30 | 2014-07-16 | 3 | No | DUKHCONP1BZ4ARFF3335, DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3350, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ3ARFF3365, DUKHCONP1BZ4ARFF3335, DUKHCONP1BZ4ARFF3360 | DUKHCONP1BZ4ARFF3370, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4PLFF4335, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ4PLFF4335, DUKHCONP1BZ4ARFF3370 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.25 .15 .10 .20 ROOF |  | 65 | 65 | 0% | 2014-03-24 | 2014-06-07 | 2014-03-24 | 2014-06-07 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ4ARRF3600 | Block work | 20 | 20 | 0% | 2014-03-24 | 2014-04-15 | 2014-03-24 | 2014-04-15 | 78 | No | DUKHCONP1BZ4STRF2055, DUKHCONP1BZ3ARRF3600, DUKHCONP1BZ4STRF2055 | DUKHCONP1BZ5ARRF3600, DUKHCONP1BZ4ARRF3605, DUKHCONP1BZ4ARRF3605 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-05-21 | 2014-06-07 | 2014-05-21 | 2014-06-07 | 78 | No | DUKHCONP1BZ4ARRF3695, DUKHCONP1BZ4ARRF3695 | DUKHCONP1BZ4ARRF3660, DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ4ELTC8010 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-04-22 | 2014-05-08 | 2014-04-22 | 2014-05-08 | 78 | No | DUKHCONP1BZ4ARRF3605, DUKHCONP1BZ4ARRF3605 | DUKHCONP1BZ4ARRF3695, DUKHCONP1BZ4ARRF3695 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-05-04 | 2014-05-26 | 2014-05-04 | 2014-05-26 | 78 | No | DUKHCONP1BZ4ARRF3610, DUKHCONP1BZ4ARRF3610 | DUKHCONP1BZ4AREL3680, DUKHCONP1BZ4AREL3680, DUKHCONP1BZ4ARRF3620, DUKHCONP1BZ4ARRF3620 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-04-05 | 2014-04-27 | 2014-04-05 | 2014-04-27 | 78 | No | DUKHCONP1BZ4ARRF3600, DUKHCONP1BZ4ARRF3600 | DUKHCONP1BZ4ARRF3610, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4PLRF4345, DUKHCONP1BZ4ARRF3610, DUKHCONP1BZ4PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L25.25 .15 .15 EXTERNAL FINISHES |  | 63 | 63 | 0% | 2014-04-03 | 2014-06-15 | 2014-04-03 | 2014-06-15 | 76 |  |  |  | 0 | 0
DHBL.K30.L25.25 .15 .15 .10 ROOF |  | 61 | 61 | 0% | 2014-04-03 | 2014-06-12 | 2014-04-03 | 2014-06-12 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ4ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 78 | No | DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4ARRF3645 | DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4ARRF3655 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-05-27 | 2014-06-12 | 2014-05-27 | 2014-06-12 | 78 | No | DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4ARRF3620, DUKHCONP1BZ4ARRF3655 | DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 78 | No | DUKHCONP1BZ4ARRF3635, DUKHCONP1BZ4ARRF3635 | DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4ARRF3645 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-05-10 | 2014-06-01 | 2014-05-10 | 2014-06-01 | 78 | No | DUKHCONP1BZ4ARRF3650, DUKHCONP1BZ4ARRF3650, DUKHCONP1BZ3ARRF3655, DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4ARRF3645 | DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4ARRF3660, DUKHCONP1BZ4ARRF3660, DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ5ARRF3655 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 78 | No | DUKHCONP1BZ4ARRF3630, DUKHCONP1BZ4ARRF3630 | DUKHCONP1BZ4ARRF3640, DUKHCONP1BZ4ARRF3640 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 78 | No | DUKHCONP1BZ3ARRF3630, DUKHCONP1BZ4STRF2065, DUKHCONP1BZ4STRF2060, DUKHCONP1BZ4STRF2060, DUKHCONP1BZ4STRF2065 | DUKHCONP1BZ5ARRF3630, DUKHCONP1BZ4ARRF3635, DUKHCONP1BZ4ARRF3635 | 0 | 0 | ROOF
DUKHCONP1BZ4ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 78 | No | DUKHCONP1BZ4ARRF3640, DUKHCONP1BZ4ARRF3640 | DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4ARRF3650, DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4ARRF3650 | 0 | 0 | ROOF
DHBL.K30.L25.25 .15 .15 .15 ELEVATION |  | 50 | 50 | 0% | 2014-04-19 | 2014-06-15 | 2014-04-19 | 2014-06-15 | 76 |  |  |  | 0 | 0
DUKHCONP1BZ4AREL3680 | External Painting | 20 | 20 | 0% | 2014-05-24 | 2014-06-15 | 2014-05-24 | 2014-06-15 | 76 | No | DUKHCONP1BZ4AREL3670, DUKHCONP1BZ4AREL3675, DUKHCONP1BZ4ARRF3695, DUKHCONP1BZ4ARRF3695, DUKHCONP1BZ3AREL3680, DUKHCONP1BZ4AREL3670, DUKHCONP1BZ4AREL3675 | DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ5AREL3680, DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4ELTC8010 | 0 | 0 | ELEVATION
DUKHCONP1BZ4AREL3665 | External Plastering | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 76 | No | DUKHCONP1BZ4STRF2065, DUKHCONP1BZ4ARRF3605, DUKHCONP1BZ4STRF2065, DUKHCONP1BZ3AREL3665, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4ARFF3305 | DUKHCONP1BZ5AREL3665, DUKHCONP1BZ4AREL3670, DUKHCONP1BZ4AREL3670, DUKHCONP1BZ4AREL3675, DUKHCONP1BZ4AREL3675, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP1BZ4AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-05-06 | 2014-05-28 | 2014-05-06 | 2014-05-28 | 76 | No | DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ3AREL3670 | DUKHCONP1BZ4AREL3680, DUKHCONP1BZ5AREL3670, DUKHCONP1BZ4AREL3675, DUKHCONP1BZ4AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1BZ4AREL3675 | GRC works | 20 | 20 | 0% | 2014-05-12 | 2014-06-03 | 2014-05-12 | 2014-06-03 | 76 | No | DUKHCONP1BZ4AREL3670, DUKHCONP1BZ3AREL3675, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4AREL3665 | DUKHCONP1BZ4AREL3680, DUKHCONP1BZ5AREL3675, DUKHCONP1BZ4AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L25.25 .20 MEP WORKS |  | 271 | 271 | 0% | 2013-10-26 | 2014-09-11 | 2013-10-26 | 2014-09-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.25 .20 .10 ELECTRICAL WORKS |  | 189 | 189 | 0% | 2014-01-30 | 2014-09-11 | 2014-01-30 | 2014-09-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.25 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-01-30 | 2014-06-09 | 2014-01-30 | 2014-06-09 | 56 |  |  |  | 0 | 0
DUKHCONP1BZ4ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-02-12 | 2014-03-06 | 2014-02-12 | 2014-03-06 | 76 | No | DUKHCONP1BZ4ELGF4000, DUKHCONP1BZ4ELGF4000, DUKHCONP1BZ3ELGF4005 | DUKHCONP1BZ4ELGF4010, DUKHCONP1BZ4ELGF4010, DUKHCONP1BZ5ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 58 | No | DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ4ARGF3000 | DUKHCONP1BZ4ELGF4005, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 71 | No | DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ3ELGF4015 | DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ4ELFF4055, DUKHCONP1BZ4ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-04-30 | 2014-05-22 | 2014-04-30 | 2014-05-22 | 49 | No | DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ELGF4010, DUKHCONP1BZ4ELGF4010, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3060 | DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ4ELGF4025, DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ4ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 51 | No | DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ3ELGF4025, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ELGF4020 | DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ4ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-05-12 | 2014-06-03 | 2014-05-12 | 2014-06-03 | 49 | No | DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ3ELGF4030 | DUKHCONP1BZ4ELFF4050, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ4ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 76 | No | DUKHCONP1BZ4ELGF4005, DUKHCONP1BZ4ELGF4005 | DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ4ELGF4020, DUKHCONP1BZ4ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.25 .20 .10 .15 FIRST FLOORS |  | 129 | 129 | 0% | 2014-03-13 | 2014-08-13 | 2014-03-13 | 2014-08-13 | 28 |  |  |  | 0 | 0
DUKHCONP1BZ4ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-03-25 | 2014-04-16 | 2014-03-25 | 2014-04-16 | 46 | No | DUKHCONP1BZ4ELFF4035, DUKHCONP1BZ4ELFF4035 | DUKHCONP1BZ4ELFF4045, DUKHCONP1BZ4ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 16 | No | DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ4ARFF3300 | DUKHCONP1BZ4ELFF4040, DUKHCONP1BZ4ELFF4040, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 45 | No | DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ3ELFF4055, DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ4ARFF3360 | DUKHCONP1BZ5ELFF4055, DUKHCONP1BZ4ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-06-30 | 2014-07-22 | 2014-06-30 | 2014-07-22 | 3 | No | DUKHCONP1BZ3ELFF4060, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ELFF4045, DUKHCONP1BZ4ELFF4045 | DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ5ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 3 | No | DUKHCONP1BZ4ELGF4025, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ELFF4060, DUKHCONP1BZ3ELFF4065, DUKHCONP1BZ4ELFF4060, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ELGF4025 | DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ5ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-06-21 | 2014-07-19 | 2014-06-21 | 2014-07-19 | 25 | No | DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ4MSEX5010, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ARFF3360 | DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 46 | No | DUKHCONP1BZ3ELFF4045, DUKHCONP1BZ4ELFF4040, DUKHCONP1BZ4ELFF4040 | DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ4ARFF3345, DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4ARFF3345, DUKHCONP1BZ4ELFF4060, DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4ELFF4060 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.25 .20 .10 .20 ROOF |  | 33 | 33 | 0% | 2014-08-05 | 2014-09-11 | 2014-08-05 | 2014-09-11 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ4ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-08-05 | 2014-08-25 | 2014-08-05 | 2014-08-25 | 3 | No | DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ4ELFF4050, DUKHCONP1BZ4ELFF4045, DUKHCONP1BZ4ELFF4050, DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4ELFF4045 | DUKHCONP1BZ4ELRF4075, DUKHCONP1BZ4ELRF4075 | 0 | 0 | ROOF
DUKHCONP1BZ4ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-08-17 | 2014-09-11 | 2014-08-17 | 2014-09-11 | 3 | No | DUKHCONP1BZ4ELRF4070, DUKHCONP1BZ4ELRF4070 | DUKHCONP1BZ4ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L25.25 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 255 | 255 | 0% | 2013-10-26 | 2014-08-24 | 2013-10-26 | 2014-08-24 | 19 |  |  |  | 0 | 0
DHBL.K30.L25.25 .20 .15 .10 GROUND FLOOR |  | 193 | 193 | 0% | 2013-10-26 | 2014-06-09 | 2013-10-26 | 2014-06-09 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-10-26 | 2013-11-17 | 2013-10-26 | 2013-11-17 | 11 | No | DUKHCONP1BZ4STUG1040, DUKHCONP1BZ4STUG1040 | DUKHCONP1BZ4STUG1045, DUKHCONP1BZ4STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-02-10 | 2014-03-03 | 2014-02-10 | 2014-03-03 | 52 | No | DUKHCONP1BZ4PLGF4305, DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ4PLGF4305 | DUKHCONP1BZ4PLGF4315, DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ4MSEX5000, DUKHCONP1BZ4MSEX5000, DUKHCONP1BZ4PLGF4315, DUKHCONP1BZ4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-02-10 | 2014-03-03 | 2014-02-10 | 2014-03-03 | 49 | No | DUKHCONP1BZ4ARGF3000, DUKHCONP1BZ3PLGF4305, DUKHCONP1BZ4ARGF3000 | DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4PLGF4310, DUKHCONP1BZ5PLGF4305, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ4PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-05-24 | 2014-06-09 | 2014-05-24 | 2014-06-09 | 81 | No | DUKHCONP1BZ4PLGF4315, DUKHCONP1BZ3PLGF4320, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4PLGF4315 | DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ5PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-05-12 | 2014-06-03 | 2014-05-12 | 2014-06-03 | 81 | No | DUKHCONP1BZ4PLGF4310, DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ4PLGF4310, DUKHCONP1BZ3PLGF4315 | DUKHCONP1BZ4PLGF4320, DUKHCONP1BZ5PLGF4315, DUKHCONP1BZ4PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.25 .20 .15 .15 FIRST FLOORS |  | 113 | 113 | 0% | 2014-03-25 | 2014-08-06 | 2014-03-25 | 2014-08-06 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ4PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-03-25 | 2014-04-14 | 2014-03-25 | 2014-04-14 | 30 | No | DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ3PLFF4330, DUKHCONP1BZ4PLFF4325, DUKHCONP1BZ4PLFF4325 | DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4PLFF4335, DUKHCONP1BZ4PLFF4335, DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ5PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-03-25 | 2014-04-14 | 2014-03-25 | 2014-04-14 | 3 | No | DUKHCONP1BZ4ARFF3300, DUKHCONP1BZ4ARFF3300 | DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-07-17 | 2014-08-06 | 2014-07-17 | 2014-08-06 | 19 | No | DUKHCONP1BZ4PLFF4335, DUKHCONP1BZ4PLFF4335, DUKHCONP1BZ3PLFF4340, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ARFF3360 | DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ5PLFF4340, DUKHCONP1BZ4PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-07-06 | 2014-07-28 | 2014-07-06 | 2014-07-28 | 19 | No | DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4ARFF3365 | DUKHCONP1BZ4PLFF4340, DUKHCONP1BZ4PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.25 .20 .15 .20 ROOF |  | 105 | 105 | 0% | 2014-04-21 | 2014-08-24 | 2014-04-21 | 2014-08-24 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ4PLRF4345 | Installation of Plumbing pipes & fittings | 14 | 14 | 0% | 2014-04-21 | 2014-05-06 | 2014-04-21 | 2014-05-06 | 86 | No | DUKHCONP1BZ4ARRF3605, DUKHCONP1BZ4ARRF3605, DUKHCONP1BZ3PLRF4345 | DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ4PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-05-08 | 2014-05-25 | 2014-05-08 | 2014-05-25 | 79 | No | DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ3PLRF4350, DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4PLRF4345, DUKHCONP1BZ4AREL3665, DUKHCONP1BZ4PLRF4345 | DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ4WEEX5065, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ4WEEX5065 | 0 | 0 | ROOF
DUKHCONP1BZ4PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-07-23 | 2014-08-24 | 2014-07-23 | 2014-08-24 | 19 | No | DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4PLFF4340, DUKHCONP1BZ4WEEX5065, DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ3PLRF4355, DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4PLFF4340, DUKHCONP1BZ4PLRF4345, DUKHCONP1BZ4PLRF4345 | DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ4PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L25.25 .20 .20 AC WORKS |  | 144 | 144 | 0% | 2014-03-03 | 2014-08-20 | 2014-03-03 | 2014-08-20 | 22 |  |  |  | 0 | 0
DHBL.K30.L25.25 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-03-03 | 2014-06-07 | 2014-03-03 | 2014-06-07 | 68 |  |  |  | 0 | 0
DUKHCONP1BZ4ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-05-15 | 2014-06-07 | 2014-05-15 | 2014-06-07 | 68 | No | DUKHCONP1BZ3ACGF4610, DUKHCONP1BZ4ACGF4605, DUKHCONP1BZ4ACGF4605 | DUKHCONP1BZ4ACRF4635, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ACRF4635, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ5ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 68 | No | DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ3ACGF4605, DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3060 | DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ4ACGF4610, DUKHCONP1BZ4ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ4ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-03-03 | 2014-03-25 | 2014-03-03 | 2014-03-25 | 80 | No | DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ3ACGF4600, DUKHCONP1BZ4ARGF3005 | DUKHCONP1BZ4ACGF4605, DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3055, DUKHCONP1BZ4ARGF3060, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ4ACGF4605, DUKHCONP1BZ4ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.25 .20 .20 .15 FIRST FLOORS |  | 95 | 95 | 0% | 2014-04-17 | 2014-08-09 | 2014-04-17 | 2014-08-09 | 17 |  |  |  | 0 | 0
DUKHCONP1BZ4ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-07-14 | 2014-08-09 | 2014-07-14 | 2014-08-09 | 17 | No | DUKHCONP1BZ4ACFF4620, DUKHCONP1BZ3ACFF4625, DUKHCONP1BZ4ACFF4620 | DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4ACRF4635, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ACRF4635 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 17 | No | DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ3ACFF4620, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ4ARFF3360 | DUKHCONP1BZ4ACFF4625, DUKHCONP1BZ5ACFF4620, DUKHCONP1BZ4ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ4ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-04-17 | 2014-05-10 | 2014-04-17 | 2014-05-10 | 46 | No | DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ3ACFF4615 | DUKHCONP1BZ4ACFF4620, DUKHCONP1BZ4ARFF3360, DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ4ACFF4620, DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ4ARFF3360 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.25 .20 .20 .20 ROOF |  | 95 | 95 | 0% | 2014-04-29 | 2014-08-20 | 2014-04-29 | 2014-08-20 | 22 |  |  |  | 0 | 0
DUKHCONP1BZ4ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-07-20 | 2014-08-20 | 2014-07-20 | 2014-08-20 | 22 | No | DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ4ACFF4625, DUKHCONP1BZ4ACGF4610, DUKHCONP1BZ3ACRF4635, DUKHCONP1BZ4ACRF4630, DUKHCONP1BZ4ACGF4610, DUKHCONP1BZ4ACFF4625 | DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ5ACRF4635 | 0 | 0 | ROOF
DUKHCONP1BZ4ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-04-29 | 2014-05-27 | 2014-04-29 | 2014-05-27 | 87 | No | DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4ARRF3645, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ3ACRF4630, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ4ACGF4600 | DUKHCONP1BZ4ACRF4635, DUKHCONP1BZ4ACRF4635, DUKHCONP1BZ5ACRF4630 | 0 | 0 | ROOF
DHBL.K30.L25.25 .25 EXTERNAL WORKS |  | 164 | 164 | 0% | 2014-03-05 | 2014-09-15 | 2014-03-05 | 2014-09-15 | 25 |  |  |  | 0 | 0
DHBL.K30.L25.25 .25 .10 MISCELLANEOUS |  | 164 | 164 | 0% | 2014-03-05 | 2014-09-15 | 2014-03-05 | 2014-09-15 | 25 |  |  |  | 0 | 0
DUKHCONP1BZ4MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 25 | No | DUKHCONP1BZ3MSEX5335, DUKHCONI1BZ2BWGL5325 | DUKHHANP1BGNELTC9010, DUKHHANP1BGNPLTC9005, DUKHCONP1BZ5MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ4MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 43 | No | DUKHCONP1BZ4MSEX5000, DUKHCONP1BZ4MSEX5000 | DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4MSEX5015, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ4MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ4MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 69 | No | DUKHCONP1BZ4STRF2055, DUKHCONP1BZ4STRF2055, DUKHCONP1BZ3MSEX5020 | DUKHCONP1BZ4MSEX5025, DUKHCONP1BZ4HDEX5090, DUKHCONP1BZ4MSEX5025, DUKHCONP1BZ4HDEX5090, DUKHCONP1BZ5MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ4MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-04-08 | 2014-04-30 | 2014-04-08 | 2014-04-30 | 43 | No | DUKHCONP1BZ4MSEX5005, DUKHCONP1BZ4MSEX5005 | DUKHCONP1BZ4MSEX5010, DUKHCONP1BZ4WEEX5065, DUKHCONP1BZ4WEEX5050, DUKHCONP1BZ4WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ4MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 43 | No | DUKHCONP1BZ4PLGF4310, DUKHCONP1BZ4PLGF4310, DUKHCONP1BZ4STRF2055, DUKHCONP1BZ4STRF2055 | DUKHCONP1BZ4MSEX5005, DUKHCONP1BZ4MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ4MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-03-26 | 2014-04-17 | 2014-03-26 | 2014-04-17 | 72 | No | DUKHCONP1BZ4MSEX5020, DUKHCONP1BZ4MSEX5020 | DUKHCONP1BZ4WEEX5060, DUKHCONP1BZ4WEEX5050, DUKHCONP1BZ4HDEX5090, DUKHCONP1BZ4WEEX5045 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ4MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-05-01 | 2014-05-29 | 2014-05-01 | 2014-05-29 | 43 | No | DUKHCONP1BZ4MSEX5015 | DUKHCONP1BZ4ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L25.25 .25 .15 WATER TANK ENCLOSURE |  | 85 | 85 | 0% | 2014-04-03 | 2014-07-10 | 2014-04-03 | 2014-07-10 | 54 |  |  |  | 0 | 0
DUKHCONP1BZ4WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-04-21 | 2014-05-19 | 2014-04-21 | 2014-05-19 | 54 | No | DUKHCONP1BZ4WEEX5035, DUKHCONP1BZ4WEEX5035 | DUKHCONP1BZ4WEEX5045, DUKHCONP1BZ4WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ4WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-04-09 | 2014-05-07 | 2014-04-09 | 2014-05-07 | 54 | No | DUKHCONP1BZ4WEEX5030, DUKHCONP1BZ4WEEX5030 | DUKHCONP1BZ4WEEX5040, DUKHCONP1BZ4WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ4WEEX5030 | Excavation | 20 | 20 | 0% | 2014-04-03 | 2014-04-26 | 2014-04-03 | 2014-04-26 | 51 | No | DUKHCONP1BZ4STRF2055, DUKHCONP1BZ4STRF2055, DUKHCONP1BZ3WEEX5035 | DUKHCONP1BZ4WEEX5035, DUKHCONP1BZ5WEEX5030, DUKHCONP1BZ4WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ4WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 54 | No | DUKHCONP1BZ4MSEX5025, DUKHCONP1BZ4WEEX5040, DUKHCONP1BZ4WEEX5040 | DUKHCONP1BZ4WEEX5050, DUKHCONP1BZ4WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ4WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 54 | No | DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4WEEX5060, DUKHCONP1BZ3WEEX5065, DUKHCONP1BZ4MSEX5015, DUKHCONP1BZ4WEEX5060, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4MSEX5015 | DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ4PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ4WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-05-20 | 2014-06-11 | 2014-05-20 | 2014-06-11 | 54 | No | DUKHCONP1BZ4WEEX5045, DUKHCONP1BZ4MSEX5025, DUKHCONP1BZ4WEEX5045, DUKHCONP1BZ4MSEX5015 | DUKHCONP1BZ4WEEX5060, DUKHCONP1BZ4WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ4WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 54 | No | DUKHCONP1BZ4MSEX5025, DUKHCONP1BZ4WEEX5050, DUKHCONP1BZ4WEEX5050, DUKHCONP1BZ3WEEX5060 | DUKHCONP1BZ4WEEX5065, DUKHCONP1BZ5WEEX5060, DUKHCONP1BZ4WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L25.25 .25 .20 HARD LANDSCAPING |  | 42 | 42 | 0% | 2014-04-03 | 2014-05-21 | 2014-04-03 | 2014-05-21 | 72 |  |  |  | 0 | 0
DUKHCONP1BZ4HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-04-15 | 2014-05-07 | 2014-04-15 | 2014-05-07 | 72 | No | DUKHCONP1BZ4HDEX5090, DUKHCONP1BZ4HDEX5090 | DUKHCONP1BZ4HDEX5100, DUKHCONP1BZ4HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ4HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-04-29 | 2014-05-21 | 2014-04-29 | 2014-05-21 | 72 | No | DUKHCONP1BZ4HDEX5095, DUKHCONP1BZ4HDEX5095 | DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ4SLEX5105, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ4HDEX5090 | kerb works | 20 | 20 | 0% | 2014-04-03 | 2014-04-26 | 2014-04-03 | 2014-04-26 | 72 | No | DUKHCONP1BZ4MSEX5020, DUKHCONP1BZ4MSEX5025, DUKHCONP1BZ4MSEX5020, DUKHCONP1BZ3HDEX5090 | DUKHCONP1BZ4HDEX5095, DUKHCONP1BZ5HDEX5090, DUKHCONP1BZ4HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L25.25 .25 .25 SOFT LANDSCAPING |  | 35 | 35 | 0% | 2014-05-11 | 2014-06-19 | 2014-05-11 | 2014-06-19 | 72 |  |  |  | 0 | 0
DUKHCONP1BZ4SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 72 | No | DUKHCONP1BZ4HDEX5100, DUKHCONP1BZ4HDEX5100 | DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4SLEX5110, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ4SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1BZ4SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 72 | No | DUKHCONP1BZ4SLEX5105, DUKHCONP1BZ4SLEX5105 | DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ4ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L25.25 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-09-13 | 2014-10-13 | 2014-09-13 | 2014-10-13 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ4ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-09-13 | 2014-10-13 | 2014-09-13 | 2014-10-13 | 3 | No | DUKHCONP1BZ4ACFF4625, DUKHCONP1BZ4HDEX5100, DUKHCONP1BZ4MSEX5005, DUKHCONP1BZ3ACTC8000, DUKHCONP1BZ4ARRF3660, DUKHCONP1BZ4AREL3680, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4SLEX5105, DUKHCONP1BZ4ARRF3620, DUKHCONP1BZ4ACRF4635, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4SLEX5110 | DUKHCONP1BZ5ACTC8000, DUKHHANP1BGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-09-13 | 2014-10-13 | 2014-09-13 | 2014-10-13 | 3 | No | DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ4ELRF4075, DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ4SLEX5105, DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4ARRF3660, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ4MSEX5005, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ELFF4050, DUKHCONP1BZ4ELGF4025, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ4ELFF4055, DUKHCONP1BZ4SLEX5110, DUKHCONP1BZ4HDEX5100, DUKHCONP1BZ4AREL3680, DUKHCONP1BZ4ARRF3620 | DUKHCONP1BZ5ELTC8010, DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-09-13 | 2014-10-13 | 2014-09-13 | 2014-10-13 | 3 | No | DUKHCONP1BZ4ARRF3655, DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ4AREL3680, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ4SLEX5105, DUKHCONP1BZ4HDEX5100, DUKHCONP1BZ4SLEX5110, DUKHCONP1BZ4MSEX5005, DUKHCONP1BZ4ARRF3620, DUKHCONP1BZ4PLGF4320, DUKHCONP1BZ4WEEX5065, DUKHCONP1BZ4ARRF3660, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ3PLTC8005 | DUKHHANP1BGNPLTC9005, DUKHCONP1BZ5PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L25.30 ZONE - 5 (5 Twin Villas) |  | 383 | 383 | 0% | 2013-08-08 | 2014-11-11 | 2013-08-08 | 2014-11-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.30 .10 STRUCTURAL WORKS |  | 237 | 237 | 0% | 2013-08-08 | 2014-05-19 | 2013-08-08 | 2014-05-19 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.30 .10 .10 SUB STRUCTURE |  | 120 | 120 | 0% | 2013-08-08 | 2014-01-01 | 2013-08-08 | 2014-01-01 | 11 |  |  |  | 0 | 0
DHBL.K30.L25.30 .10 .10 .10 UPTO GRADE SLAB |  | 120 | 120 | 0% | 2013-08-08 | 2014-01-01 | 2013-08-08 | 2014-01-01 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ5STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-10-21 | 2013-11-18 | 2013-10-21 | 2013-11-18 | 11 | No | DUKHCONP1BZ4STUG1035, DUKHCONP1BZ5STUG1030, DUKHCONP1BZ5STUG1030 | DUKHCONP1BZ5STUG1040, DUKHCONP1BZ6STUG1035, DUKHCONP1BZ5STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-09-18 | 2013-10-10 | 2013-09-18 | 2013-10-10 | 11 | No | DUKHCONP1BZ5STUG1015, DUKHCONP1BZ5STUG1015 | DUKHCONP1BZ5STUG1025, DUKHCONP1BZ5STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-11-06 | 2013-12-04 | 2013-11-06 | 2013-12-04 | 11 | No | DUKHCONP1BZ5STUG1035, DUKHCONP1BZ5STUG1035 | DUKHCONP1BZ5STUG1045, DUKHCONP1BZ5STUG1045, DUKHCONP1BZ5PLUG4300, DUKHCONP1BZ5PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-09-28 | 2013-10-28 | 2013-09-28 | 2013-10-28 | 11 | No | DUKHCONP1BZ5STUG1020, DUKHCONP1BZ4STUG1025, DUKHCONP1BZ5STUG1020 | DUKHCONP1BZ6STUG1025, DUKHCONP1BZ5STUG1030, DUKHCONP1BZ5STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 11 | No | DUKHCONP1BZ5STUG1040, DUKHCONP1BZ5PLUG4300, DUKHCONP1BZ5STUG1040, DUKHCONP1BZ5PLUG4300, DUKHCONP1BZ4STUG1045 | DUKHCONP1BZ5STGF2000, DUKHCONP1BZ5STGF2000, DUKHCONP1BZ6STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-08-24 | 2013-09-18 | 2013-08-24 | 2013-09-18 | 11 | No | DUKHCONP1BZ5STUG1000, DUKHCONP1BZ5STUG1000 | DUKHCONP1BZ5STUG1010, DUKHCONP1BZ5STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-08-28 | 2013-09-23 | 2013-08-28 | 2013-09-23 | 11 | No | DUKHCONP1BZ5STUG1005, DUKHCONP1BZ5STUG1005 | DUKHCONP1BZ5STUG1015, DUKHCONP1BZ5STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-08-08 | 2013-09-09 | 2013-08-08 | 2013-09-09 | 11 | No | DUKHCONP1BZ4STUG1000 | DUKHCONP1BZ5STUG1005, DUKHCONP1BZ6STUG1000, DUKHCONP1BZ5STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-09-03 | 2013-10-01 | 2013-09-03 | 2013-10-01 | 11 | No | DUKHCONP1BZ5STUG1010, DUKHCONP1BZ5STUG1010 | DUKHCONP1BZ5STUG1020, DUKHCONP1BZ5STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ5STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-10-07 | 2013-11-06 | 2013-10-07 | 2013-11-06 | 11 | No | DUKHCONP1BZ5STUG1025, DUKHCONP1BZ5STUG1025 | DUKHCONP1BZ5STUG1035, DUKHCONP1BZ5STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L25.30 .10 .15 SUPERSTRUCTURE |  | 128 | 128 | 0% | 2013-12-21 | 2014-05-19 | 2013-12-21 | 2014-05-19 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.30 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2013-12-21 | 2014-02-15 | 2013-12-21 | 2014-02-15 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ5STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-01-29 | 2014-02-15 | 2014-01-29 | 2014-02-15 | 11 | No | DUKHCONP1BZ4STGF2015, DUKHCONP1BZ5STGF2010, DUKHCONP1BZ5STGF2010 | DUKHCONP1BZ5STFF2020, DUKHCONP1BZ6STGF2015, DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ5STFF2020, DUKHCONP1BZ5ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 11 | No | DUKHCONP1BZ5STGF2005, DUKHCONP1BZ5STGF2005 | DUKHCONP1BZ5STGF2015, DUKHCONP1BZ5STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5STGF2005 | Column-Concrete | 23 | 23 | 0% | 2013-12-30 | 2014-01-25 | 2013-12-30 | 2014-01-25 | 11 | No | DUKHCONP1BZ5STGF2000, DUKHCONP1BZ5STGF2000 | DUKHCONP1BZ5STGF2010, DUKHCONP1BZ5STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 11 | No | DUKHCONP1BZ4STGF2000, DUKHCONP1BZ5STUG1045, DUKHCONP1BZ5STUG1045 | DUKHCONP1BZ6STGF2000, DUKHCONP1BZ5STGF2005, DUKHCONP1BZ5STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.30 .10 .15 .15 FIRST FLOORS |  | 39 | 39 | 0% | 2014-02-01 | 2014-03-18 | 2014-02-01 | 2014-03-18 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ5STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-03-03 | 2014-03-18 | 2014-03-03 | 2014-03-18 | 11 | No | DUKHCONP1BZ5STFF2030, DUKHCONP1BZ4STFF2035, DUKHCONP1BZ5STFF2030 | DUKHCONP1BZ6STFF2035, DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ5STRF2040, DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ5STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 11 | No | DUKHCONP1BZ5STFF2025, DUKHCONP1BZ5STFF2025 | DUKHCONP1BZ5STFF2035, DUKHCONP1BZ5STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5STFF2025 | Column-Concrete | 23 | 23 | 0% | 2014-02-10 | 2014-03-09 | 2014-02-10 | 2014-03-09 | 11 | No | DUKHCONP1BZ5STFF2020, DUKHCONP1BZ5STFF2020 | DUKHCONP1BZ5STFF2030, DUKHCONP1BZ5STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 11 | No | DUKHCONP1BZ5STGF2015, DUKHCONP1BZ4STFF2020, DUKHCONP1BZ5STGF2015 | DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ5STFF2025, DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ6STFF2020, DUKHCONP1BZ5STFF2025 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.30 .10 .15 .20 ROOF |  | 62 | 62 | 0% | 2014-03-09 | 2014-05-19 | 2014-03-09 | 2014-05-19 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ5STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-03-12 | 2014-03-31 | 2014-03-12 | 2014-03-31 | 25 | No | DUKHCONP1BZ5STRF2040, DUKHCONP1BZ5STRF2040 | DUKHCONP1BZ5STRF2050, DUKHCONP1BZ5STRF2050 | 0 | 0 | ROOF
DUKHCONP1BZ5STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-03-09 | 2014-03-29 | 2014-03-09 | 2014-03-29 | 20 | No | DUKHCONP1BZ5STFF2035, DUKHCONP1BZ4STRF2040, DUKHCONP1BZ5STFF2035 | DUKHCONP1BZ5STRF2045, DUKHCONP1BZ6STRF2040, DUKHCONP1BZ5STRF2045 | 0 | 0 | ROOF
DUKHCONP1BZ5STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-04-05 | 2014-05-03 | 2014-04-05 | 2014-05-03 | 73 | No | DUKHCONP1BZ4STRF2060, DUKHCONP1BZ5STRF2055, DUKHCONP1BZ5STRF2055 | DUKHCONP1BZ5ARRF3630, DUKHCONP1BZ6STRF2060, DUKHCONP1BZ5ARRF3630, DUKHCONP1BZ5STRF2065, DUKHCONP1BZ5STRF2065 | 0 | 0 | ROOF
DUKHCONP1BZ5STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-04-21 | 2014-05-19 | 2014-04-21 | 2014-05-19 | 78 | No | DUKHCONP1BZ4STRF2065, DUKHCONP1BZ5STRF2060, DUKHCONP1BZ5STRF2060 | DUKHCONP1BZ5ARRF3630, DUKHCONP1BZ5AREL3665, DUKHCONP1BZ6STRF2065, DUKHCONP1BZ5ARRF3630, DUKHCONP1BZ5AREL3665 | 0 | 0 | ROOF
DUKHCONP1BZ5STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-03-29 | 2014-04-12 | 2014-03-29 | 2014-04-12 | 25 | No | DUKHCONP1BZ5STRF2050, DUKHCONP1BZ4STRF2055, DUKHCONP1BZ5STRF2050 | DUKHCONP1BZ5MSEX5000, DUKHCONP1BZ5MSEX5000, DUKHCONP1BZ5WEEX5030, DUKHCONP1BZ5STRF2060, DUKHCONP1BZ5MSEX5020, DUKHCONP1BZ5ARRF3600, DUKHCONP1BZ5MSEX5020, DUKHCONP1BZ5STRF2060, DUKHCONP1BZ6STRF2055, DUKHCONP1BZ5ARRF3600, DUKHCONP1BZ5WEEX5030 | 0 | 0 | ROOF
DUKHCONP1BZ5STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-03-15 | 2014-04-06 | 2014-03-15 | 2014-04-06 | 25 | No | DUKHCONP1BZ5STRF2045, DUKHCONP1BZ5STRF2045 | DUKHCONP1BZ5STRF2055, DUKHCONP1BZ5STRF2055 | 0 | 0 | ROOF
DHBL.K30.L25.30 .15 FINISHING WORKS |  | 194 | 194 | 0% | 2014-02-24 | 2014-10-13 | 2014-02-24 | 2014-10-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.30 .15 .10 INTERNAL FINISHES |  | 194 | 194 | 0% | 2014-02-24 | 2014-10-13 | 2014-02-24 | 2014-10-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.30 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-02-24 | 2014-08-09 | 2014-02-24 | 2014-08-09 | 57 |  |  |  | 0 | 0
DUKHCONP1BZ5ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-06-10 | 2014-06-26 | 2014-06-10 | 2014-06-26 | 57 | No | DUKHCONP1BZ5ARGF3065, DUKHCONP1BZ4ARGF3070, DUKHCONP1BZ5ARGF3065 | DUKHCONP1BZ5ARGF3075, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ5ARGF3080, DUKHCONP1BZ5ARGF3080, DUKHCONP1BZ5ARGF3075, DUKHCONP1BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 52 | No | DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ5ACGF4600 | DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ5ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-06-17 | 2014-07-09 | 2014-06-17 | 2014-07-09 | 67 | No | DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ4ARGF3080, DUKHCONP1BZ5ARGF3070 | DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ6ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3000 | Block work | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 49 | No | DUKHCONP1BZ5STGF2015, DUKHCONP1BZ5STGF2015, DUKHCONP1BZ4ARGF3000 | DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5ELGF4000, DUKHCONP1BZ5ELGF4000, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5PLGF4305, DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5PLGF4305 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-06-16 | 2014-07-08 | 2014-06-16 | 2014-07-08 | 57 | No | DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ4ARGF3075 | DUKHCONP1BZ5ARGF3085, DUKHCONP1BZ6ARGF3075, DUKHCONP1BZ5ARGF3085, DUKHCONP1BZ5ARGF3090, DUKHCONP1BZ5ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-04-10 | 2014-05-08 | 2014-04-10 | 2014-05-08 | 49 | No | DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ4ARGF3020, DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5PLGF4305, DUKHCONP1BZ5ARGF3015, DUKHCONP1BZ5ARGF3015, DUKHCONP1BZ5PLGF4305 | DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ6ARGF3020, DUKHCONP1BZ5ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-05-13 | 2014-05-29 | 2014-05-13 | 2014-05-29 | 57 | No | DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ5ARGF3010, DUKHCONP1BZ5ARGF3010, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ5ARGF3035, DUKHCONP1BZ5ARGF3035 | DUKHCONP1BZ5ARGF3050, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3050, DUKHCONP1BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-07-08 | 2014-08-09 | 2014-07-08 | 2014-08-09 | 57 | No | DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ5ARGF3030, DUKHCONP1BZ5ARGF3080, DUKHCONP1BZ5ARGF3030, DUKHCONP1BZ5ARGF3085, DUKHCONP1BZ4ARGF3095, DUKHCONP1BZ5ACGF4610, DUKHCONP1BZ5ARGF3090, DUKHCONP1BZ5ACGF4610, DUKHCONP1BZ5ARGF3080, DUKHCONP1BZ5ARGF3090, DUKHCONP1BZ5ARGF3085, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3035, DUKHCONP1BZ5ARGF3035, DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3060 | DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ5ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-05-04 | 2014-05-26 | 2014-05-04 | 2014-05-26 | 49 | No | DUKHCONP1BZ5ELGF4010, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ5ELGF4010, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ4ARGF3045, DUKHCONP1BZ5ARGF3030, DUKHCONP1BZ5ARGF3030 | DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ6ARGF3045, DUKHCONP1BZ5ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-03-26 | 2014-04-19 | 2014-03-26 | 2014-04-19 | 57 | No | DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5ARGF3005 | DUKHCONP1BZ5ARGF3035, DUKHCONP1BZ5ARGF3035, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ5ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-05-21 | 2014-06-12 | 2014-05-21 | 2014-06-12 | 57 | No | DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ5ARGF3040 | DUKHCONP1BZ5ARGF3085, DUKHCONP1BZ5ARGF3085, DUKHCONP1BZ5ARGF3065, DUKHCONP1BZ5ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 49 | No | DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ4ARGF3060 | DUKHCONP1BZ5PLGF4320, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ5PLGF4320, DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-06-29 | 2014-07-15 | 2014-06-29 | 2014-07-15 | 57 | No | DUKHCONP1BZ5ARGF3075, DUKHCONP1BZ5ARGF3075 | DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 63 | No | DUKHCONP1BZ4ARGF3030, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5ARGF3005 | DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ6ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 49 | No | DUKHCONP1BZ5ELGF4000, DUKHCONP1BZ5PLGF4305, DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ5ELGF4000, DUKHCONP1BZ4ARGF3005, DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ5PLGF4305 | DUKHCONP1BZ5ARGF3015, DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ARGF3030, DUKHCONP1BZ5ARGF3015, DUKHCONP1BZ5ARGF3030, DUKHCONP1BZ5ARGF3010, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 49 | No | DUKHCONP1BZ4ARGF3025, DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ5ARGF3010, DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ5ARGF3010 | DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3035, DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ5ARGF3050, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3050, DUKHCONP1BZ5ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-06-24 | 2014-07-16 | 2014-06-24 | 2014-07-16 | 62 | No | DUKHCONP1BZ5ARGF3075, DUKHCONP1BZ5ARGF3050, DUKHCONP1BZ5ARGF3075, DUKHCONP1BZ5ARGF3050 | DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-05-06 | 2014-05-22 | 2014-05-06 | 2014-05-22 | 59 | No | DUKHCONP1BZ5ARGF3010, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ5ARGF3010, DUKHCONP1BZ5ARGF3025 | DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3065, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3040, DUKHCONP1BZ5ARGF3065, DUKHCONP1BZ5ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-04-05 | 2014-04-21 | 2014-04-05 | 2014-04-21 | 49 | No | DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ4ARGF3015 | DUKHCONP1BZ6ARGF3015, DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-06-04 | 2014-06-21 | 2014-06-04 | 2014-06-21 | 57 | No | DUKHCONP1BZ4ARGF3065, DUKHCONP1BZ5ARGF3035, DUKHCONP1BZ5ARGF3050, DUKHCONP1BZ5ARGF3050, DUKHCONP1BZ5ARGF3035 | DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ6ARGF3065, DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ5PLGF4315, DUKHCONP1BZ5PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.30 .15 .10 .15 FIRST FLOORS |  | 159 | 159 | 0% | 2014-04-06 | 2014-10-13 | 2014-04-06 | 2014-10-13 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ5ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-08-10 | 2014-09-01 | 2014-08-10 | 2014-09-01 | 3 | No | DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ4ARFF3370, DUKHCONP1BZ5ARFF3365 | DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ5ARFF3380, DUKHCONP1BZ6ARFF3370, DUKHCONP1BZ5ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-08-17 | 2014-09-08 | 2014-08-17 | 2014-09-08 | 16 | No | DUKHCONP1BZ5ARFF3370, DUKHCONP1BZ5ARFF3370 | DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3300 | Block work | 25 | 25 | 0% | 2014-04-06 | 2014-05-04 | 2014-04-06 | 2014-05-04 | 3 | No | DUKHCONP1BZ5STFF2020, DUKHCONP1BZ5STFF2035, DUKHCONP1BZ5STFF2020, DUKHCONP1BZ5STFF2035, DUKHCONP1BZ4ARFF3300 | DUKHCONP1BZ5PLFF4325, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5ELFF4035, DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5ELFF4035, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5PLFF4325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-08-18 | 2014-09-15 | 2014-08-18 | 2014-09-15 | 3 | No | DUKHCONP1BZ5ARFF3370, DUKHCONP1BZ5ARFF3370, DUKHCONP1BZ4ARFF3375 | DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3390, DUKHCONP1BZ6ARFF3375, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3390, DUKHCONP1BZ5ARFF3385, DUKHCONP1BZ5ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-06-02 | 2014-06-30 | 2014-06-02 | 2014-06-30 | 3 | No | DUKHCONP1BZ5ARFF3315, DUKHCONP1BZ5ARFF3315, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ4ARFF3320, DUKHCONP1BZ5PLFF4325, DUKHCONP1BZ5PLFF4325 | DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ5ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-09-13 | 2014-10-13 | 2014-09-13 | 2014-10-13 | 3 | No | DUKHCONP1BZ5ARFF3390, DUKHCONP1BZ5ARFF3330, DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5ARFF3380, DUKHCONP1BZ5ARFF3350, DUKHCONP1BZ5ARFF3390, DUKHCONP1BZ4ARFF3395, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ5ARFF3330, DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3350, DUKHCONP1BZ5ARFF3380, DUKHCONP1BZ5ARFF3385, DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ARFF3385 | DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ5PLTC8005 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-07-02 | 2014-07-24 | 2014-07-02 | 2014-07-24 | 3 | No | DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ5ARFF3330, DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ5ARFF3330, DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ4ARFF3345 | DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ5ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-05-11 | 2014-06-03 | 2014-05-11 | 2014-06-03 | 20 | No | DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5ARFF3305 | DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-07-02 | 2014-07-24 | 2014-07-02 | 2014-07-24 | 14 | No | DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ5ARFF3325 | DUKHCONP1BZ5ARFF3385, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5ARFF3385, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-07-14 | 2014-08-14 | 2014-07-14 | 2014-08-14 | 3 | No | DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ4ARFF3360 | DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ5ELFF4050, DUKHCONP1BZ5ELFF4050, DUKHCONP1BZ5ELFF4060, DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5PLFF4340, DUKHCONP1BZ5ELFF4055, DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ5ACFF4620, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ELFF4055, DUKHCONP1BZ5ELFF4060, DUKHCONP1BZ5ACFF4620, DUKHCONP1BZ5PLFF4340, DUKHCONP1BZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-09-01 | 2014-09-23 | 2014-09-01 | 2014-09-23 | 3 | No | DUKHCONP1BZ5ARFF3350, DUKHCONP1BZ5ARFF3350, DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ5ARFF3375 | DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-09-01 | 2014-09-23 | 2014-09-01 | 2014-09-23 | 5 | No | DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ5ARFF3375 | DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 29 | No | DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5ARFF3305 | DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 3 | No | DUKHCONP1BZ5PLFF4325, DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ5ELFF4035, DUKHCONP1BZ4ARFF3305, DUKHCONP1BZ5ELFF4035, DUKHCONP1BZ5PLFF4325, DUKHCONP1BZ5ARFF3300 | DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5ARFF3330, DUKHCONP1BZ5ARFF3315, DUKHCONP1BZ5ARFF3315, DUKHCONP1BZ5ARFF3310, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5AREL3665, DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ5ARFF3310, DUKHCONP1BZ5AREL3665, DUKHCONP1BZ5ARFF3330 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-06-11 | 2014-07-09 | 2014-06-11 | 2014-07-09 | 3 | No | DUKHCONP1BZ5ARFF3310, DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ4ARFF3325, DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ5ARFF3310 | DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ5ARFF3350, DUKHCONP1BZ6ARFF3325, DUKHCONP1BZ5ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-06-29 | 2014-07-15 | 2014-06-29 | 2014-07-15 | 22 | No | DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ5ARFF3325, DUKHCONP1BZ5ARFF3310, DUKHCONP1BZ5ARFF3310 | DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-05-24 | 2014-06-09 | 2014-05-24 | 2014-06-09 | 3 | No | DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ4ARFF3315 | DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ6ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-07-29 | 2014-08-18 | 2014-07-29 | 2014-08-18 | 3 | No | DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ4ARFF3365, DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3350, DUKHCONP1BZ5ARFF3335, DUKHCONP1BZ5ARFF3350 | DUKHCONP1BZ5ARFF3370, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ5ARFF3370, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5PLFF4335, DUKHCONP1BZ5PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.30 .15 .10 .20 ROOF |  | 65 | 65 | 0% | 2014-04-22 | 2014-07-06 | 2014-04-22 | 2014-07-06 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ5ARRF3600 | Block work | 20 | 20 | 0% | 2014-04-22 | 2014-05-14 | 2014-04-22 | 2014-05-14 | 78 | No | DUKHCONP1BZ5STRF2055, DUKHCONP1BZ4ARRF3600, DUKHCONP1BZ5STRF2055 | DUKHCONP1BZ5ARRF3605, DUKHCONP1BZ5ARRF3605, DUKHCONP1BZ6ARRF3600 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-06-19 | 2014-07-06 | 2014-06-19 | 2014-07-06 | 78 | No | DUKHCONP1BZ5ARRF3695, DUKHCONP1BZ5ARRF3695 | DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ5ARRF3660, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5ELTC8010 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-05-21 | 2014-06-07 | 2014-05-21 | 2014-06-07 | 78 | No | DUKHCONP1BZ5ARRF3605, DUKHCONP1BZ5ARRF3605 | DUKHCONP1BZ5ARRF3695, DUKHCONP1BZ5ARRF3695 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-06-02 | 2014-06-24 | 2014-06-02 | 2014-06-24 | 78 | No | DUKHCONP1BZ5ARRF3610, DUKHCONP1BZ5ARRF3610 | DUKHCONP1BZ5AREL3680, DUKHCONP1BZ5ARRF3620, DUKHCONP1BZ5AREL3680, DUKHCONP1BZ5ARRF3620 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-05-04 | 2014-05-26 | 2014-05-04 | 2014-05-26 | 78 | No | DUKHCONP1BZ5ARRF3600, DUKHCONP1BZ5ARRF3600 | DUKHCONP1BZ5AREL3665, DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ5ARRF3610, DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ5ARRF3610 | 0 | 0 | ROOF
DHBL.K30.L25.30 .15 .15 EXTERNAL FINISHES |  | 63 | 63 | 0% | 2014-05-03 | 2014-07-14 | 2014-05-03 | 2014-07-14 | 76 |  |  |  | 0 | 0
DHBL.K30.L25.30 .15 .15 .10 ROOF |  | 61 | 61 | 0% | 2014-05-03 | 2014-07-12 | 2014-05-03 | 2014-07-12 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ5ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 78 | No | DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5ARRF3645 | DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ5ARRF3655 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-06-25 | 2014-07-12 | 2014-06-25 | 2014-07-12 | 78 | No | DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ5ARRF3620 | DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ5ELTC8010 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 78 | No | DUKHCONP1BZ5ARRF3635, DUKHCONP1BZ5ARRF3635 | DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5ARRF3645 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-06-08 | 2014-06-30 | 2014-06-08 | 2014-06-30 | 78 | No | DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5ARRF3650, DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5ARRF3650, DUKHCONP1BZ4ARRF3655 | DUKHCONP1BZ5ARRF3660, DUKHCONP1BZ5ARRF3660, DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ5PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-05-06 | 2014-06-03 | 2014-05-06 | 2014-06-03 | 78 | No | DUKHCONP1BZ5ARRF3630, DUKHCONP1BZ5ARRF3630 | DUKHCONP1BZ5ARRF3640, DUKHCONP1BZ5ARRF3640 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 78 | No | DUKHCONP1BZ5STRF2060, DUKHCONP1BZ5STRF2065, DUKHCONP1BZ5STRF2060, DUKHCONP1BZ5STRF2065, DUKHCONP1BZ4ARRF3630 | DUKHCONP1BZ6ARRF3630, DUKHCONP1BZ5ARRF3635, DUKHCONP1BZ5ARRF3635 | 0 | 0 | ROOF
DUKHCONP1BZ5ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 78 | No | DUKHCONP1BZ5ARRF3640, DUKHCONP1BZ5ARRF3640 | DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5ARRF3650, DUKHCONP1BZ5ARRF3650, DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5ARRF3655 | 0 | 0 | ROOF
DHBL.K30.L25.30 .15 .15 .15 ELEVATION |  | 50 | 50 | 0% | 2014-05-18 | 2014-07-14 | 2014-05-18 | 2014-07-14 | 76 |  |  |  | 0 | 0
DUKHCONP1BZ5AREL3680 | External Painting | 20 | 20 | 0% | 2014-06-22 | 2014-07-14 | 2014-06-22 | 2014-07-14 | 76 | No | DUKHCONP1BZ5ARRF3695, DUKHCONP1BZ5AREL3670, DUKHCONP1BZ4AREL3680, DUKHCONP1BZ5AREL3670, DUKHCONP1BZ5ARRF3695, DUKHCONP1BZ5AREL3675, DUKHCONP1BZ5AREL3675 | DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ6AREL3680, DUKHCONP1BZ5PLTC8005 | 0 | 0 | ELEVATION
DUKHCONP1BZ5AREL3665 | External Plastering | 25 | 25 | 0% | 2014-05-18 | 2014-06-15 | 2014-05-18 | 2014-06-15 | 76 | No | DUKHCONP1BZ4AREL3665, DUKHCONP1BZ5STRF2065, DUKHCONP1BZ5ARRF3605, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5STRF2065, DUKHCONP1BZ5ARFF3305 | DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5AREL3670, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5AREL3675, DUKHCONP1BZ5AREL3670, DUKHCONP1BZ5AREL3675, DUKHCONP1BZ6AREL3665 | 0 | 0 | ELEVATION
DUKHCONP1BZ5AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-06-04 | 2014-06-26 | 2014-06-04 | 2014-06-26 | 76 | No | DUKHCONP1BZ4AREL3670, DUKHCONP1BZ5AREL3665, DUKHCONP1BZ5AREL3665 | DUKHCONP1BZ5AREL3675, DUKHCONP1BZ5AREL3680, DUKHCONP1BZ6AREL3670, DUKHCONP1BZ5AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1BZ5AREL3675 | GRC works | 20 | 20 | 0% | 2014-06-10 | 2014-07-02 | 2014-06-10 | 2014-07-02 | 76 | No | DUKHCONP1BZ5AREL3670, DUKHCONP1BZ5AREL3665, DUKHCONP1BZ4AREL3675, DUKHCONP1BZ5AREL3665 | DUKHCONP1BZ6AREL3675, DUKHCONP1BZ5AREL3680, DUKHCONP1BZ5AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L25.30 .20 MEP WORKS |  | 271 | 271 | 0% | 2013-11-24 | 2014-10-13 | 2013-11-24 | 2014-10-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.30 .20 .10 ELECTRICAL WORKS |  | 189 | 189 | 0% | 2014-03-02 | 2014-10-13 | 2014-03-02 | 2014-10-13 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.30 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-03-02 | 2014-07-08 | 2014-03-02 | 2014-07-08 | 56 |  |  |  | 0 | 0
DUKHCONP1BZ5ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-03-13 | 2014-04-05 | 2014-03-13 | 2014-04-05 | 76 | No | DUKHCONP1BZ5ELGF4000, DUKHCONP1BZ5ELGF4000, DUKHCONP1BZ4ELGF4005 | DUKHCONP1BZ5ELGF4010, DUKHCONP1BZ5ELGF4010, DUKHCONP1BZ6ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 58 | No | DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ5ARGF3000 | DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5ELGF4005, DUKHCONP1BZ5ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 71 | No | DUKHCONP1BZ4ELGF4015, DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ARGF3060 | DUKHCONP1BZ5ELFF4055, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5ELFF4055, DUKHCONP1BZ6ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-05-29 | 2014-06-21 | 2014-05-29 | 2014-06-21 | 49 | No | DUKHCONP1BZ5ELGF4010, DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ELGF4010, DUKHCONP1BZ5ARGF3060 | DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ5ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-06-10 | 2014-07-08 | 2014-06-10 | 2014-07-08 | 51 | No | DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ4ELGF4025, DUKHCONP1BZ5ELGF4020 | DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ6ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-06-10 | 2014-07-02 | 2014-06-10 | 2014-07-02 | 49 | No | DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ4ELGF4030, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ELGF4020 | DUKHCONP1BZ5ELFF4050, DUKHCONP1BZ6ELGF4030, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 76 | No | DUKHCONP1BZ5ELGF4005, DUKHCONP1BZ5ELGF4005 | DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ5ELGF4020, DUKHCONP1BZ5ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.30 .20 .10 .15 FIRST FLOORS |  | 129 | 129 | 0% | 2014-04-12 | 2014-09-11 | 2014-04-12 | 2014-09-11 | 28 |  |  |  | 0 | 0
DUKHCONP1BZ5ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-04-23 | 2014-05-15 | 2014-04-23 | 2014-05-15 | 46 | No | DUKHCONP1BZ5ELFF4035, DUKHCONP1BZ5ELFF4035 | DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ5ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 16 | No | DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ5ARFF3300 | DUKHCONP1BZ5ELFF4040, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5ELFF4040, DUKHCONP1BZ5ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-07-22 | 2014-08-23 | 2014-07-22 | 2014-08-23 | 45 | No | DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ4ELFF4055, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ARFF3360 | DUKHCONP1BZ6ELFF4055, DUKHCONP1BZ5ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-07-29 | 2014-08-24 | 2014-07-29 | 2014-08-24 | 3 | No | DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ4ELFF4060 | DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ6ELFF4060, DUKHCONP1BZ5ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-08-14 | 2014-09-11 | 2014-08-14 | 2014-09-11 | 3 | No | DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ELFF4060, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ4ELFF4065, DUKHCONP1BZ5ELFF4060 | DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ5ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-07-20 | 2014-08-20 | 2014-07-20 | 2014-08-20 | 25 | No | DUKHCONP1BZ5MSEX5010, DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ELGF4030 | DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-05-01 | 2014-05-29 | 2014-05-01 | 2014-05-29 | 46 | No | DUKHCONP1BZ4ELFF4045, DUKHCONP1BZ5ELFF4040, DUKHCONP1BZ5ELFF4040 | DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5ELFF4060, DUKHCONP1BZ6ELFF4045, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5ELFF4060 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.30 .20 .10 .20 ROOF |  | 33 | 33 | 0% | 2014-09-03 | 2014-10-13 | 2014-09-03 | 2014-10-13 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ5ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-09-03 | 2014-09-23 | 2014-09-03 | 2014-09-23 | 3 | No | DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ5ELFF4050, DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5ELFF4050 | DUKHCONP1BZ5ELRF4075, DUKHCONP1BZ5ELRF4075 | 0 | 0 | ROOF
DUKHCONP1BZ5ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-09-15 | 2014-10-13 | 2014-09-15 | 2014-10-13 | 3 | No | DUKHCONP1BZ5ELRF4070, DUKHCONP1BZ5ELRF4070 | DUKHCONP1BZ5ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L25.30 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 255 | 255 | 0% | 2013-11-24 | 2014-09-22 | 2013-11-24 | 2014-09-22 | 19 |  |  |  | 0 | 0
DHBL.K30.L25.30 .20 .15 .10 GROUND FLOOR |  | 193 | 193 | 0% | 2013-11-24 | 2014-07-08 | 2013-11-24 | 2014-07-08 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-11-24 | 2013-12-16 | 2013-11-24 | 2013-12-16 | 11 | No | DUKHCONP1BZ5STUG1040, DUKHCONP1BZ5STUG1040 | DUKHCONP1BZ5STUG1045, DUKHCONP1BZ5STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-03-12 | 2014-04-01 | 2014-03-12 | 2014-04-01 | 52 | No | DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ5PLGF4305, DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ5PLGF4305 | DUKHCONP1BZ5MSEX5000, DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ5MSEX5000, DUKHCONP1BZ5PLGF4315, DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ5PLGF4315 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-03-12 | 2014-04-01 | 2014-03-12 | 2014-04-01 | 49 | No | DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ5ARGF3000, DUKHCONP1BZ4PLGF4305 | DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-06-22 | 2014-07-08 | 2014-06-22 | 2014-07-08 | 81 | No | DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ4PLGF4320, DUKHCONP1BZ5PLGF4315, DUKHCONP1BZ5PLGF4315 | DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ6PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-06-10 | 2014-07-02 | 2014-06-10 | 2014-07-02 | 81 | No | DUKHCONP1BZ4PLGF4315, DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5ARGF3065, DUKHCONP1BZ5ARGF3065 | DUKHCONP1BZ6PLGF4315, DUKHCONP1BZ5PLGF4320, DUKHCONP1BZ5PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.30 .20 .15 .15 FIRST FLOORS |  | 113 | 113 | 0% | 2014-04-23 | 2014-09-04 | 2014-04-23 | 2014-09-04 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ5PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-04-23 | 2014-05-13 | 2014-04-23 | 2014-05-13 | 30 | No | DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ5PLFF4325, DUKHCONP1BZ4PLFF4330, DUKHCONP1BZ5PLFF4325, DUKHCONP1BZ5ARFF3300 | DUKHCONP1BZ5PLFF4335, DUKHCONP1BZ5PLFF4335, DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5PLRF4350 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-04-23 | 2014-05-13 | 2014-04-23 | 2014-05-13 | 3 | No | DUKHCONP1BZ5ARFF3300, DUKHCONP1BZ5ARFF3300 | DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ5ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-08-19 | 2014-09-04 | 2014-08-19 | 2014-09-04 | 19 | No | DUKHCONP1BZ4PLFF4340, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5PLFF4335, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5PLFF4335 | DUKHCONP1BZ6PLFF4340, DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ5PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-08-07 | 2014-08-30 | 2014-08-07 | 2014-08-30 | 19 | No | DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ5ARFF3365 | DUKHCONP1BZ5PLFF4340, DUKHCONP1BZ5PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.30 .20 .15 .20 ROOF |  | 105 | 105 | 0% | 2014-05-20 | 2014-09-22 | 2014-05-20 | 2014-09-22 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ5PLRF4345 | Installation of Plumbing pipes & fittings | 14 | 14 | 0% | 2014-05-20 | 2014-06-04 | 2014-05-20 | 2014-06-04 | 86 | No | DUKHCONP1BZ5ARRF3605, DUKHCONP1BZ4PLRF4345, DUKHCONP1BZ5ARRF3605 | DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ6PLRF4345, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ5PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-06-07 | 2014-06-23 | 2014-06-07 | 2014-06-23 | 79 | No | DUKHCONP1BZ5AREL3665, DUKHCONP1BZ4PLRF4350, DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5AREL3665, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ5PLFF4330 | DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ5PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-08-25 | 2014-09-22 | 2014-08-25 | 2014-09-22 | 19 | No | DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ4PLRF4355, DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ5PLFF4340, DUKHCONP1BZ5PLFF4340, DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ5PLRF4350 | DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ5PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L25.30 .20 .20 AC WORKS |  | 144 | 144 | 0% | 2014-04-01 | 2014-09-18 | 2014-04-01 | 2014-09-18 | 22 |  |  |  | 0 | 0
DHBL.K30.L25.30 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-04-01 | 2014-07-06 | 2014-04-01 | 2014-07-06 | 68 |  |  |  | 0 | 0
DUKHCONP1BZ5ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-06-14 | 2014-07-06 | 2014-06-14 | 2014-07-06 | 68 | No | DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ4ACGF4610 | DUKHCONP1BZ6ACGF4610, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ACRF4635, DUKHCONP1BZ5ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 68 | No | DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ4ACGF4605, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ5ARGF3055 | DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ5ACGF4610, DUKHCONP1BZ5ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ5ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-04-01 | 2014-04-23 | 2014-04-01 | 2014-04-23 | 80 | No | DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ4ACGF4600, DUKHCONP1BZ5ARGF3005 | DUKHCONP1BZ5ARGF3055, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5ARGF3055 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.30 .20 .20 .15 FIRST FLOORS |  | 95 | 95 | 0% | 2014-05-17 | 2014-09-07 | 2014-05-17 | 2014-09-07 | 17 |  |  |  | 0 | 0
DUKHCONP1BZ5ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-08-16 | 2014-09-07 | 2014-08-16 | 2014-09-07 | 17 | No | DUKHCONP1BZ4ACFF4625, DUKHCONP1BZ5ACFF4620, DUKHCONP1BZ5ACFF4620 | DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ6ACFF4625, DUKHCONP1BZ5ACRF4635, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ACRF4635 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-07-22 | 2014-08-23 | 2014-07-22 | 2014-08-23 | 17 | No | DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ4ACFF4620 | DUKHCONP1BZ6ACFF4620, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ5ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ5ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-05-17 | 2014-06-08 | 2014-05-17 | 2014-06-08 | 46 | No | DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ4ACFF4615, DUKHCONP1BZ5ARFF3305 | DUKHCONP1BZ5ACFF4620, DUKHCONP1BZ5ACFF4620, DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5ARFF3360, DUKHCONP1BZ6ACFF4615, DUKHCONP1BZ5ARFF3360 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.30 .20 .20 .20 ROOF |  | 95 | 95 | 0% | 2014-05-28 | 2014-09-18 | 2014-05-28 | 2014-09-18 | 22 |  |  |  | 0 | 0
DUKHCONP1BZ5ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-08-21 | 2014-09-18 | 2014-08-21 | 2014-09-18 | 22 | No | DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ5ACGF4610, DUKHCONP1BZ5ACGF4610, DUKHCONP1BZ4ACRF4635 | DUKHCONP1BZ6ACRF4635, DUKHCONP1BZ5ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ5ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 87 | No | DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ5ARRF3645, DUKHCONP1BZ4ACRF4630 | DUKHCONP1BZ5ACRF4635, DUKHCONP1BZ6ACRF4630, DUKHCONP1BZ5ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L25.30 .25 EXTERNAL WORKS |  | 164 | 164 | 0% | 2014-04-03 | 2014-10-16 | 2014-04-03 | 2014-10-16 | 25 |  |  |  | 0 | 0
DHBL.K30.L25.30 .25 .10 MISCELLANEOUS |  | 164 | 164 | 0% | 2014-04-03 | 2014-10-16 | 2014-04-03 | 2014-10-16 | 25 |  |  |  | 0 | 0
DUKHCONP1BZ5MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-09-16 | 2014-10-16 | 2014-09-16 | 2014-10-16 | 25 | No | DUKHCONP1BZ4MSEX5335, DUKHCONI1BZ3BWGL5325 | DUKHHANP1BGNPLTC9005, DUKHCONP1BZ6MSEX5335, DUKHHANP1BGNELTC9010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ5MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 43 | No | DUKHCONP1BZ5MSEX5000, DUKHCONP1BZ5MSEX5000 | DUKHCONP1BZ5MSEX5015, DUKHCONP1BZ5MSEX5015, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ5MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 69 | No | DUKHCONP1BZ4MSEX5020, DUKHCONP1BZ5STRF2055, DUKHCONP1BZ5STRF2055 | DUKHCONP1BZ5MSEX5025, DUKHCONP1BZ5MSEX5025, DUKHCONP1BZ5HDEX5090, DUKHCONP1BZ5HDEX5090, DUKHCONP1BZ6MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ5MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-05-07 | 2014-05-29 | 2014-05-07 | 2014-05-29 | 43 | No | DUKHCONP1BZ5MSEX5005, DUKHCONP1BZ5MSEX5005 | DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ5WEEX5050, DUKHCONP1BZ5MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ5MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 43 | No | DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5PLGF4310, DUKHCONP1BZ5STRF2055, DUKHCONP1BZ5STRF2055 | DUKHCONP1BZ5MSEX5005, DUKHCONP1BZ5MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ5MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-04-24 | 2014-05-17 | 2014-04-24 | 2014-05-17 | 71 | No | DUKHCONP1BZ5MSEX5020, DUKHCONP1BZ5MSEX5020 | DUKHCONP1BZ5WEEX5045, DUKHCONP1BZ5HDEX5090, DUKHCONP1BZ5WEEX5050, DUKHCONP1BZ5WEEX5060 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ5MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-05-31 | 2014-06-28 | 2014-05-31 | 2014-06-28 | 43 | No | DUKHCONP1BZ5MSEX5015 | DUKHCONP1BZ5ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L25.30 .25 .15 WATER TANK ENCLOSURE |  | 90 | 90 | 0% | 2014-04-27 | 2014-08-12 | 2014-04-27 | 2014-08-12 | 54 |  |  |  | 0 | 0
DUKHCONP1BZ5WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-05-20 | 2014-06-17 | 2014-05-20 | 2014-06-17 | 59 | No | DUKHCONP1BZ5WEEX5035, DUKHCONP1BZ5WEEX5035 | DUKHCONP1BZ5WEEX5045, DUKHCONP1BZ5WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ5WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-05-08 | 2014-06-05 | 2014-05-08 | 2014-06-05 | 51 | No | DUKHCONP1BZ5WEEX5030, DUKHCONP1BZ5WEEX5030 | DUKHCONP1BZ6WEEX5030, DUKHCONP1BZ5WEEX5040, DUKHCONP1BZ5WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ5WEEX5030 | Excavation | 20 | 20 | 0% | 2014-04-27 | 2014-05-19 | 2014-04-27 | 2014-05-19 | 51 | No | DUKHCONP1BZ4WEEX5030, DUKHCONP1BZ5STRF2055, DUKHCONP1BZ5STRF2055 | DUKHCONP1BZ5WEEX5035, DUKHCONP1BZ5WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ5WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 59 | No | DUKHCONP1BZ5MSEX5025, DUKHCONP1BZ5WEEX5040, DUKHCONP1BZ5WEEX5040 | DUKHCONP1BZ5WEEX5050, DUKHCONP1BZ5WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ5WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-07-12 | 2014-08-12 | 2014-07-12 | 2014-08-12 | 54 | No | DUKHCONP1BZ5MSEX5015, DUKHCONP1BZ5MSEX5015, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5WEEX5060, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5WEEX5060, DUKHCONP1BZ4WEEX5065 | DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ6WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ5WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-06-18 | 2014-07-10 | 2014-06-18 | 2014-07-10 | 59 | No | DUKHCONP1BZ5WEEX5045, DUKHCONP1BZ5MSEX5015, DUKHCONP1BZ5MSEX5025, DUKHCONP1BZ5WEEX5045 | DUKHCONP1BZ5WEEX5060, DUKHCONP1BZ5WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ5WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-06-30 | 2014-07-28 | 2014-06-30 | 2014-07-28 | 54 | No | DUKHCONP1BZ5WEEX5050, DUKHCONP1BZ5WEEX5050, DUKHCONP1BZ4WEEX5060, DUKHCONP1BZ5MSEX5025 | DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ6WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L25.30 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2014-05-03 | 2014-06-21 | 2014-05-03 | 2014-06-21 | 71 |  |  |  | 0 | 0
DUKHCONP1BZ5HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-05-14 | 2014-06-05 | 2014-05-14 | 2014-06-05 | 71 | No | DUKHCONP1BZ5HDEX5090, DUKHCONP1BZ5HDEX5090 | DUKHCONP1BZ5HDEX5100, DUKHCONP1BZ5HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ5HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-05-29 | 2014-06-21 | 2014-05-29 | 2014-06-21 | 71 | No | DUKHCONP1BZ5HDEX5095, DUKHCONP1BZ5HDEX5095 | DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5SLEX5105, DUKHCONP1BZ5SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ5HDEX5090 | kerb works | 20 | 20 | 0% | 2014-05-03 | 2014-05-25 | 2014-05-03 | 2014-05-25 | 71 | No | DUKHCONP1BZ4HDEX5090, DUKHCONP1BZ5MSEX5020, DUKHCONP1BZ5MSEX5025, DUKHCONP1BZ5MSEX5020 | DUKHCONP1BZ5HDEX5095, DUKHCONP1BZ6HDEX5090, DUKHCONP1BZ5HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L25.30 .25 .25 SOFT LANDSCAPING |  | 35 | 35 | 0% | 2014-06-10 | 2014-07-20 | 2014-06-10 | 2014-07-20 | 71 |  |  |  | 0 | 0
DUKHCONP1BZ5SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-06-10 | 2014-07-08 | 2014-06-10 | 2014-07-08 | 71 | No | DUKHCONP1BZ5HDEX5100, DUKHCONP1BZ5HDEX5100 | DUKHCONP1BZ5SLEX5110, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5SLEX5110, DUKHCONP1BZ5ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1BZ5SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-06-22 | 2014-07-20 | 2014-06-22 | 2014-07-20 | 71 | No | DUKHCONP1BZ5SLEX5105, DUKHCONP1BZ5SLEX5105 | DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ5ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L25.30 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-10-14 | 2014-11-11 | 2014-10-14 | 2014-11-11 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ5ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-10-14 | 2014-11-11 | 2014-10-14 | 2014-11-11 | 3 | No | DUKHCONP1BZ5HDEX5100, DUKHCONP1BZ5ARRF3620, DUKHCONP1BZ4ACTC8000, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARRF3660, DUKHCONP1BZ5AREL3680, DUKHCONP1BZ5MSEX5005, DUKHCONP1BZ5SLEX5110, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ACRF4635, DUKHCONP1BZ5SLEX5105 | DUKHHANP1BGNACTC9000, DUKHCONP1BZ6ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-10-14 | 2014-11-11 | 2014-10-14 | 2014-11-11 | 3 | No | DUKHCONP1BZ5ELRF4075, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ5SLEX5105, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ5AREL3680, DUKHCONP1BZ5HDEX5100, DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ5ARRF3660, DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ5ELFF4050, DUKHCONP1BZ5MSEX5005, DUKHCONP1BZ5ARRF3620, DUKHCONP1BZ5ELFF4065, DUKHCONP1BZ5ELFF4055, DUKHCONP1BZ5SLEX5110 | DUKHHANP1BGNPLTC9005, DUKHCONP1BZ6ELTC8010, DUKHHANP1BGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-10-14 | 2014-11-11 | 2014-10-14 | 2014-11-11 | 3 | No | DUKHCONP1BZ5SLEX5110, DUKHCONP1BZ5HDEX5100, DUKHCONP1BZ5PLGF4320, DUKHCONP1BZ5SLEX5105, DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ5ARRF3660, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ5ARRF3620, DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ5MSEX5005, DUKHCONP1BZ5AREL3680 | DUKHHANP1BGNPLTC9005, DUKHCONP1BZ6PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L25.35 ZONE - 6 (5 Twin Villas) |  | 383 | 383 | 0% | 2013-09-10 | 2014-12-10 | 2013-09-10 | 2014-12-10 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.35 .10 STRUCTURAL WORKS |  | 237 | 237 | 0% | 2013-09-10 | 2014-06-17 | 2013-09-10 | 2014-06-17 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.35 .10 .10 SUB STRUCTURE |  | 120 | 120 | 0% | 2013-09-10 | 2014-01-30 | 2013-09-10 | 2014-01-30 | 11 |  |  |  | 0 | 0
DHBL.K30.L25.35 .10 .10 .10 UPTO GRADE SLAB |  | 120 | 120 | 0% | 2013-09-10 | 2014-01-30 | 2013-09-10 | 2014-01-30 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ6STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-11-19 | 2013-12-17 | 2013-11-19 | 2013-12-17 | 11 | No | DUKHCONP1BZ6STUG1030, DUKHCONP1BZ5STUG1035, DUKHCONP1BZ6STUG1030 | DUKHCONP1BZ6STUG1040, DUKHCONP1BZ6STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-10-20 | 2013-11-11 | 2013-10-20 | 2013-11-11 | 11 | No | DUKHCONP1BZ6STUG1015, DUKHCONP1BZ6STUG1015 | DUKHCONP1BZ6STUG1025, DUKHCONP1BZ6STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 11 | No | DUKHCONP1BZ6STUG1035, DUKHCONP1BZ6STUG1035 | DUKHCONP1BZ6STUG1045, DUKHCONP1BZ6PLUG4300, DUKHCONP1BZ6PLUG4300, DUKHCONP1BZ6STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-10-29 | 2013-11-26 | 2013-10-29 | 2013-11-26 | 11 | No | DUKHCONP1BZ5STUG1025, DUKHCONP1BZ6STUG1020, DUKHCONP1BZ6STUG1020 | DUKHCONP1BZ6STUG1030, DUKHCONP1BZ6STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 11 | No | DUKHCONP1BZ6STUG1040, DUKHCONP1BZ6PLUG4300, DUKHCONP1BZ6PLUG4300, DUKHCONP1BZ6STUG1040, DUKHCONP1BZ5STUG1045 | DUKHCONP1BZ6STGF2000, DUKHCONP1BZ6STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-09-22 | 2013-10-20 | 2013-09-22 | 2013-10-20 | 11 | No | DUKHCONP1BZ6STUG1000, DUKHCONP1BZ6STUG1000 | DUKHCONP1BZ6STUG1010, DUKHCONP1BZ6STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-09-26 | 2013-10-24 | 2013-09-26 | 2013-10-24 | 11 | No | DUKHCONP1BZ6STUG1005, DUKHCONP1BZ6STUG1005 | DUKHCONP1BZ6STUG1015, DUKHCONP1BZ6STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-09-10 | 2013-10-08 | 2013-09-10 | 2013-10-08 | 11 | No | DUKHCONP1BZ5STUG1000 | DUKHCONP1BZ6STUG1005, DUKHCONP1BZ6STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-10-02 | 2013-11-02 | 2013-10-02 | 2013-11-02 | 11 | No | DUKHCONP1BZ6STUG1010, DUKHCONP1BZ6STUG1010 | DUKHCONP1BZ6STUG1020, DUKHCONP1BZ6STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP1BZ6STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-11-07 | 2013-12-05 | 2013-11-07 | 2013-12-05 | 11 | No | DUKHCONP1BZ6STUG1025, DUKHCONP1BZ6STUG1025 | DUKHCONP1BZ6STUG1035, DUKHCONP1BZ6STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L25.35 .10 .15 SUPERSTRUCTURE |  | 128 | 128 | 0% | 2014-01-19 | 2014-06-17 | 2014-01-19 | 2014-06-17 | 78 |  |  |  | 0 | 0
DHBL.K30.L25.35 .10 .15 .10 GROUND FLOOR |  | 48 | 48 | 0% | 2014-01-19 | 2014-03-16 | 2014-01-19 | 2014-03-16 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ6STGF2015 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-03-01 | 2014-03-16 | 2014-03-01 | 2014-03-16 | 11 | No | DUKHCONP1BZ6STGF2010, DUKHCONP1BZ5STGF2015, DUKHCONP1BZ6STGF2010 | DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ6STFF2020, DUKHCONP1BZ6STFF2020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 11 | No | DUKHCONP1BZ6STGF2005, DUKHCONP1BZ6STGF2005 | DUKHCONP1BZ6STGF2015, DUKHCONP1BZ6STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6STGF2005 | Column-Concrete | 23 | 23 | 0% | 2014-01-28 | 2014-02-24 | 2014-01-28 | 2014-02-24 | 11 | No | DUKHCONP1BZ6STGF2000, DUKHCONP1BZ6STGF2000 | DUKHCONP1BZ6STGF2010, DUKHCONP1BZ6STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 11 | No | DUKHCONP1BZ5STGF2000, DUKHCONP1BZ6STUG1045, DUKHCONP1BZ6STUG1045 | DUKHCONP1BZ6STGF2005, DUKHCONP1BZ6STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.35 .10 .15 .15 FIRST FLOORS |  | 39 | 39 | 0% | 2014-03-03 | 2014-04-16 | 2014-03-03 | 2014-04-16 | 11 |  |  |  | 0 | 0
DUKHCONP1BZ6STFF2035 | Beam, Stairs ,Slab-Concrete | 14 | 14 | 0% | 2014-04-01 | 2014-04-16 | 2014-04-01 | 2014-04-16 | 11 | No | DUKHCONP1BZ5STFF2035, DUKHCONP1BZ6STFF2030, DUKHCONP1BZ6STFF2030 | DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6STRF2040, DUKHCONP1BZ6STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 11 | No | DUKHCONP1BZ6STFF2025, DUKHCONP1BZ6STFF2025 | DUKHCONP1BZ6STFF2035, DUKHCONP1BZ6STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6STFF2025 | Column-Concrete | 23 | 23 | 0% | 2014-03-12 | 2014-04-07 | 2014-03-12 | 2014-04-07 | 11 | No | DUKHCONP1BZ6STFF2020, DUKHCONP1BZ6STFF2020 | DUKHCONP1BZ6STFF2030, DUKHCONP1BZ6STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 11 | No | DUKHCONP1BZ6STGF2015, DUKHCONP1BZ5STFF2020, DUKHCONP1BZ6STGF2015 | DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6STFF2025, DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6STFF2025 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.35 .10 .15 .20 ROOF |  | 62 | 62 | 0% | 2014-04-07 | 2014-06-17 | 2014-04-07 | 2014-06-17 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ6STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-04-10 | 2014-04-29 | 2014-04-10 | 2014-04-29 | 13 | No | DUKHCONP1BZ6STRF2040, DUKHCONP1BZ6STRF2040 | DUKHCONP1BZ6STRF2050, DUKHCONP1BZ6STRF2050 | 0 | 0 | ROOF
DUKHCONP1BZ6STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-04-07 | 2014-04-27 | 2014-04-07 | 2014-04-27 | 13 | No | DUKHCONP1BZ5STRF2040, DUKHCONP1BZ6STFF2035, DUKHCONP1BZ6STFF2035 | DUKHCONP1BZ6STRF2045, DUKHCONP1BZ6STRF2045 | 0 | 0 | ROOF
DUKHCONP1BZ6STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 73 | No | DUKHCONP1BZ5STRF2060, DUKHCONP1BZ6STRF2055, DUKHCONP1BZ6STRF2055 | DUKHCONP1BZ6WEEX5030, DUKHCONP1BZ6ARRF3630, DUKHCONP1BZ6ARRF3630, DUKHCONP1BZ6STRF2065, DUKHCONP1BZ6STRF2065 | 0 | 0 | ROOF
DUKHCONP1BZ6STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-05-20 | 2014-06-17 | 2014-05-20 | 2014-06-17 | 78 | No | DUKHCONP1BZ5STRF2065, DUKHCONP1BZ6STRF2060, DUKHCONP1BZ6STRF2060 | DUKHCONP1BZ6ARRF3630, DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6ARRF3630 | 0 | 0 | ROOF
DUKHCONP1BZ6STRF2055 | Slab-Concrete-Head room | 13 | 13 | 0% | 2014-04-27 | 2014-05-11 | 2014-04-27 | 2014-05-11 | 13 | No | DUKHCONP1BZ6STRF2050, DUKHCONP1BZ5STRF2055, DUKHCONP1BZ6STRF2050 | DUKHCONP1BZ6MSEX5020, DUKHCONP1BZ6ARRF3600, DUKHCONP1BZ6WEEX5030, DUKHCONP1BZ6STRF2060, DUKHCONP1BZ6WEEX5030, DUKHCONP1BZ6ARRF3600, DUKHCONI1BSBIWGL7400, DUKHCONP1BZ6MSEX5020, DUKHCONP1BZ6MSEX5000, DUKHCONP1BZ6MSEX5000, DUKHCONP1BZ6STRF2060 | 0 | 0 | ROOF
DUKHCONP1BZ6STRF2050 | Slab-Rebar & Formwork - Head Room | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 13 | No | DUKHCONP1BZ6STRF2045, DUKHCONP1BZ6STRF2045 | DUKHCONP1BZ6STRF2055, DUKHCONP1BZ6STRF2055 | 0 | 0 | ROOF
DHBL.K30.L25.35 .15 FINISHING WORKS |  | 194 | 194 | 0% | 2014-03-25 | 2014-11-11 | 2014-03-25 | 2014-11-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.35 .15 .10 INTERNAL FINISHES |  | 194 | 194 | 0% | 2014-03-25 | 2014-11-11 | 2014-03-25 | 2014-11-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.35 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2014-03-25 | 2014-09-07 | 2014-03-25 | 2014-09-07 | 57 |  |  |  | 0 | 0
DUKHCONP1BZ6ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-07-09 | 2014-07-26 | 2014-07-09 | 2014-07-26 | 57 | No | DUKHCONP1BZ5ARGF3070, DUKHCONP1BZ6ARGF3065, DUKHCONP1BZ6ARGF3065 | DUKHCONP1BZ6ARGF3080, DUKHCONP1BZ6ARGF3080, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3075, DUKHCONP1BZ6ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-06-10 | 2014-07-08 | 2014-06-10 | 2014-07-08 | 52 | No | DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ARGF3045, DUKHCONP1BZ6ARGF3045 | DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ6ELGF4015, DUKHCONP1BZ6ELGF4025, DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ6ELGF4025, DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ6ELGF4015, DUKHCONP1BZ6ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-07-16 | 2014-08-11 | 2014-07-16 | 2014-08-11 | 67 | No | DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ5ARGF3080 | DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3000 | Block work | 25 | 25 | 0% | 2014-03-25 | 2014-04-22 | 2014-03-25 | 2014-04-22 | 49 | No | DUKHCONP1BZ6STGF2015, DUKHCONP1BZ6STGF2015, DUKHCONP1BZ5ARGF3000 | DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ6ELGF4000, DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ6ELGF4000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-07-15 | 2014-08-10 | 2014-07-15 | 2014-08-10 | 57 | No | DUKHCONP1BZ5ARGF3075, DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ6ARGF3070 | DUKHCONP1BZ6ARGF3090, DUKHCONP1BZ6ARGF3085, DUKHCONP1BZ6ARGF3085, DUKHCONP1BZ6ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-05-10 | 2014-06-07 | 2014-05-10 | 2014-06-07 | 49 | No | DUKHCONP1BZ6ARGF3015, DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ5ARGF3020, DUKHCONP1BZ6ARGF3015, DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ6PLGF4310 | DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-06-11 | 2014-06-28 | 2014-06-11 | 2014-06-28 | 57 | No | DUKHCONP1BZ6ARGF3010, DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ARGF3010, DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ARGF3035 | DUKHCONP1BZ6ARGF3050, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-08-10 | 2014-09-07 | 2014-08-10 | 2014-09-07 | 57 | No | DUKHCONP1BZ6ARGF3080, DUKHCONP1BZ6ARGF3090, DUKHCONP1BZ6ARGF3085, DUKHCONP1BZ6ACGF4610, DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ARGF3090, DUKHCONP1BZ5ARGF3095, DUKHCONP1BZ6ARGF3030, DUKHCONP1BZ6ARGF3030, DUKHCONP1BZ6ARGF3080, DUKHCONP1BZ6ARGF3085, DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ6ACGF4610, DUKHCONP1BZ6ARGF3060 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-06-02 | 2014-06-24 | 2014-06-02 | 2014-06-24 | 49 | No | DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ELGF4010, DUKHCONP1BZ6ARGF3030, DUKHCONP1BZ5ARGF3045, DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ARGF3030, DUKHCONP1BZ6ELGF4010 | DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-04-24 | 2014-05-18 | 2014-04-24 | 2014-05-18 | 57 | No | DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6ARGF3005 | DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-06-19 | 2014-07-12 | 2014-06-19 | 2014-07-12 | 57 | No | DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3025 | DUKHCONP1BZ6ARGF3085, DUKHCONP1BZ6ARGF3065, DUKHCONP1BZ6ARGF3085, DUKHCONP1BZ6ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 49 | No | DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ5ARGF3060, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ARGF3045, DUKHCONP1BZ6ARGF3045 | DUKHCONP1BZ6ELGF4015, DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ6PLGF4320, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ELGF4025, DUKHCONP1BZ6ELGF4030, DUKHCONP1BZ6ELGF4015, DUKHCONP1BZ6ELGF4030, DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ6PLGF4320, DUKHCONP1BZ6ELGF4025, DUKHCONP1BZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-07-28 | 2014-08-17 | 2014-07-28 | 2014-08-17 | 57 | No | DUKHCONP1BZ6ARGF3075, DUKHCONP1BZ6ARGF3075 | DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 63 | No | DUKHCONP1BZ5ARGF3030, DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6ARGF3005 | DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3045, DUKHCONP1BZ6ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 49 | No | DUKHCONP1BZ6ELGF4000, DUKHCONP1BZ5ARGF3005, DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ6ELGF4000, DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ6PLGF4305 | DUKHCONP1BZ6ARGF3015, DUKHCONP1BZ6ARGF3015, DUKHCONP1BZ6ARGF3010, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ARGF3030, DUKHCONP1BZ6ARGF3030, DUKHCONP1BZ6ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 49 | No | DUKHCONP1BZ6ARGF3020, DUKHCONP1BZ5ARGF3025, DUKHCONP1BZ6ARGF3010, DUKHCONP1BZ6ARGF3020, DUKHCONP1BZ6ARGF3010 | DUKHCONP1BZ6ARGF3045, DUKHCONP1BZ6ARGF3050, DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3045, DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ6ARGF3050, DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-07-23 | 2014-08-18 | 2014-07-23 | 2014-08-18 | 62 | No | DUKHCONP1BZ6ARGF3050, DUKHCONP1BZ6ARGF3075, DUKHCONP1BZ6ARGF3075, DUKHCONP1BZ6ARGF3050 | DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-06-04 | 2014-06-21 | 2014-06-04 | 2014-06-21 | 59 | No | DUKHCONP1BZ6ARGF3010, DUKHCONP1BZ6ARGF3010, DUKHCONP1BZ6ARGF3025, DUKHCONP1BZ6ARGF3025 | DUKHCONP1BZ6ARGF3065, DUKHCONP1BZ6ARGF3040, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3065, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-05-04 | 2014-05-20 | 2014-05-04 | 2014-05-20 | 49 | No | DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ5ARGF3015, DUKHCONP1BZ6ARGF3005 | DUKHCONP1BZ6ARGF3020, DUKHCONP1BZ6ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ARGF3065 | Wooden door & PVC Door | 15 | 15 | 0% | 2014-07-03 | 2014-07-20 | 2014-07-03 | 2014-07-20 | 57 | No | DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ5ARGF3065, DUKHCONP1BZ6ARGF3035, DUKHCONP1BZ6ARGF3050, DUKHCONP1BZ6ARGF3050 | DUKHCONP1BZ6PLGF4315, DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ6ARGF3070, DUKHCONP1BZ6PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.35 .15 .10 .15 FIRST FLOORS |  | 159 | 159 | 0% | 2014-05-05 | 2014-11-11 | 2014-05-05 | 2014-11-11 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ6ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-09-08 | 2014-09-30 | 2014-09-08 | 2014-09-30 | 3 | No | DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ5ARFF3370 | DUKHCONP1BZ6ARFF3375, DUKHCONP1BZ6ARFF3375, DUKHCONP1BZ6ARFF3380, DUKHCONP1BZ6ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-09-15 | 2014-10-07 | 2014-09-15 | 2014-10-07 | 16 | No | DUKHCONP1BZ6ARFF3370, DUKHCONP1BZ6ARFF3370 | DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3300 | Block work | 25 | 25 | 0% | 2014-05-05 | 2014-06-02 | 2014-05-05 | 2014-06-02 | 3 | No | DUKHCONP1BZ6STFF2020, DUKHCONP1BZ6STFF2035, DUKHCONP1BZ6STFF2020, DUKHCONP1BZ6STFF2035, DUKHCONP1BZ5ARFF3300 | DUKHCONP1BZ6PLFF4325, DUKHCONP1BZ6ELFF4035, DUKHCONP1BZ6ELFF4035, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6PLFF4325, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-09-16 | 2014-10-16 | 2014-09-16 | 2014-10-16 | 3 | No | DUKHCONP1BZ6ARFF3370, DUKHCONP1BZ5ARFF3375, DUKHCONP1BZ6ARFF3370 | DUKHCONP1BZ6ARFF3390, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3385, DUKHCONP1BZ6ARFF3390, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-07-01 | 2014-07-29 | 2014-07-01 | 2014-07-29 | 3 | No | DUKHCONP1BZ6ARFF3315, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6PLFF4325, DUKHCONP1BZ6ARFF3315, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ5ARFF3320, DUKHCONP1BZ6PLFF4325 | DUKHCONP1BZ6ARFF3325, DUKHCONP1BZ6ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-10-14 | 2014-11-11 | 2014-10-14 | 2014-11-11 | 3 | No | DUKHCONP1BZ5ARFF3395, DUKHCONP1BZ6ACFF4625, DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ARFF3390, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ARFF3380, DUKHCONP1BZ6ARFF3330, DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3375, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3390, DUKHCONP1BZ6ACFF4625, DUKHCONP1BZ6ARFF3380, DUKHCONP1BZ6ARFF3385, DUKHCONP1BZ6ARFF3335, DUKHCONP1BZ6ARFF3375, DUKHCONP1BZ6ARFF3385, DUKHCONP1BZ6ARFF3330, DUKHCONP1BZ6ARFF3335 | DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6PLTC8005, DUKHCONP1BZ6ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-07-31 | 2014-08-26 | 2014-07-31 | 2014-08-26 | 3 | No | DUKHCONP1BZ6ARFF3330, DUKHCONP1BZ6ELFF4045, DUKHCONP1BZ6ELFF4045, DUKHCONP1BZ6ARFF3330, DUKHCONP1BZ5ARFF3345, DUKHCONP1BZ6ARFF3325, DUKHCONP1BZ6ARFF3325 | DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-06-09 | 2014-07-02 | 2014-06-09 | 2014-07-02 | 20 | No | DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6ARFF3305 | DUKHCONP1BZ6ARFF3335, DUKHCONP1BZ6ARFF3335, DUKHCONP1BZ6ARFF3325, DUKHCONP1BZ6ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-07-31 | 2014-08-26 | 2014-07-31 | 2014-08-26 | 14 | No | DUKHCONP1BZ6ARFF3325, DUKHCONP1BZ6ARFF3325 | DUKHCONP1BZ6ARFF3385, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-08-16 | 2014-09-13 | 2014-08-16 | 2014-09-13 | 3 | No | DUKHCONP1BZ6ACFF4615, DUKHCONP1BZ6ACFF4615, DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ5ARFF3360 | DUKHCONP1BZ6PLFF4340, DUKHCONP1BZ6ELFF4050, DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6PLFF4340, DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ELFF4055, DUKHCONP1BZ6ELFF4050, DUKHCONP1BZ6ACFF4620, DUKHCONP1BZ6ELFF4055, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ACFF4620, DUKHCONP1BZ6ELFF4060, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-09-30 | 2014-10-25 | 2014-09-30 | 2014-10-25 | 3 | No | DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3375, DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3375 | DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-09-30 | 2014-10-25 | 2014-09-30 | 2014-10-25 | 5 | No | DUKHCONP1BZ6ARFF3375, DUKHCONP1BZ6ARFF3375 | DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 29 | No | DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6ARFF3305 | DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 3 | No | DUKHCONP1BZ6PLFF4325, DUKHCONP1BZ6ELFF4035, DUKHCONP1BZ6ELFF4035, DUKHCONP1BZ6PLFF4325, DUKHCONP1BZ5ARFF3305, DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6ARFF3300 | DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6ACFF4615, DUKHCONP1BZ6ARFF3330, DUKHCONP1BZ6ARFF3310, DUKHCONP1BZ6ARFF3330, DUKHCONP1BZ6ARFF3315, DUKHCONP1BZ6ARFF3315, DUKHCONP1BZ6ARFF3310, DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6ACFF4615 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-07-10 | 2014-08-11 | 2014-07-10 | 2014-08-11 | 3 | No | DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ6ARFF3310, DUKHCONP1BZ6ARFF3310, DUKHCONP1BZ5ARFF3325 | DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3335, DUKHCONP1BZ6ARFF3335, DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ6ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-07-28 | 2014-08-17 | 2014-07-28 | 2014-08-17 | 22 | No | DUKHCONP1BZ6ARFF3310, DUKHCONP1BZ6ARFF3325, DUKHCONP1BZ6ARFF3310, DUKHCONP1BZ6ARFF3325 | DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-06-22 | 2014-07-08 | 2014-06-22 | 2014-07-08 | 3 | No | DUKHCONP1BZ5ARFF3315, DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6ARFF3305 | DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ6ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-08-31 | 2014-09-16 | 2014-08-31 | 2014-09-16 | 3 | No | DUKHCONP1BZ5ARFF3365, DUKHCONP1BZ6ARFF3335, DUKHCONP1BZ6ARFF3335, DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3350, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ARFF3360 | DUKHCONP1BZ6ARFF3370, DUKHCONP1BZ6ARFF3370, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6PLFF4335, DUKHCONP1BZ6PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.35 .15 .10 .20 ROOF |  | 65 | 65 | 0% | 2014-05-21 | 2014-08-07 | 2014-05-21 | 2014-08-07 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ6ARRF3600 | Block work | 20 | 20 | 0% | 2014-05-21 | 2014-06-12 | 2014-05-21 | 2014-06-12 | 78 | No | DUKHCONP1BZ6STRF2055, DUKHCONP1BZ5ARRF3600, DUKHCONP1BZ6STRF2055 | DUKHCONP1BZ6ARRF3605, DUKHCONP1BZ6ARRF3605 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3620 | Epoxy Painting -Storage area | 15 | 15 | 0% | 2014-07-19 | 2014-08-07 | 2014-07-19 | 2014-08-07 | 78 | No | DUKHCONP1BZ6ARRF3695, DUKHCONP1BZ6ARRF3695 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6PLTC8005, DUKHCONP1BZ6ARRF3660, DUKHCONP1BZ6ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-06-19 | 2014-07-06 | 2014-06-19 | 2014-07-06 | 78 | No | DUKHCONP1BZ6ARRF3605, DUKHCONP1BZ6ARRF3605 | DUKHCONP1BZ6ARRF3695, DUKHCONP1BZ6ARRF3695 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3695 | Painting -Storage area | 20 | 20 | 0% | 2014-07-01 | 2014-07-23 | 2014-07-01 | 2014-07-23 | 78 | No | DUKHCONP1BZ6ARRF3610, DUKHCONP1BZ6ARRF3610 | DUKHCONP1BZ6ARRF3620, DUKHCONP1BZ6AREL3680, DUKHCONP1BZ6ARRF3620, DUKHCONP1BZ6AREL3680 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-06-02 | 2014-06-24 | 2014-06-02 | 2014-06-24 | 78 | No | DUKHCONP1BZ6ARRF3600, DUKHCONP1BZ6ARRF3600 | DUKHCONP1BZ6ARRF3610, DUKHCONP1BZ6PLRF4345, DUKHCONP1BZ6ARRF3610, DUKHCONP1BZ6PLRF4345, DUKHCONP1BZ6AREL3665 | 0 | 0 | ROOF
DHBL.K30.L25.35 .15 .15 EXTERNAL FINISHES |  | 63 | 63 | 0% | 2014-06-01 | 2014-08-16 | 2014-06-01 | 2014-08-16 | 76 |  |  |  | 0 | 0
DHBL.K30.L25.35 .15 .15 .10 ROOF |  | 61 | 61 | 0% | 2014-06-01 | 2014-08-13 | 2014-06-01 | 2014-08-13 | 78 |  |  |  | 0 | 0
DUKHCONP1BZ6ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-06-22 | 2014-07-20 | 2014-06-22 | 2014-07-20 | 78 | No | DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ6ARRF3645 | DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ6ARRF3655 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-07-24 | 2014-08-13 | 2014-07-24 | 2014-08-13 | 78 | No | DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ6ARRF3620, DUKHCONP1BZ6ARRF3655 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 78 | No | DUKHCONP1BZ6ARRF3635, DUKHCONP1BZ6ARRF3635 | DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ6ARRF3645 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-07-07 | 2014-07-29 | 2014-07-07 | 2014-07-29 | 78 | No | DUKHCONP1BZ6ARRF3650, DUKHCONP1BZ5ARRF3655, DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ6ARRF3650, DUKHCONP1BZ6ARRF3645 | DUKHCONP1BZ6ARRF3660, DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ARRF3660, DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6PLTC8005 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-06-04 | 2014-07-02 | 2014-06-04 | 2014-07-02 | 78 | No | DUKHCONP1BZ6ARRF3630, DUKHCONP1BZ6ARRF3630 | DUKHCONP1BZ6ARRF3640, DUKHCONP1BZ6ARRF3640 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 78 | No | DUKHCONP1BZ5ARRF3630, DUKHCONP1BZ6STRF2065, DUKHCONP1BZ6STRF2060, DUKHCONP1BZ6STRF2060, DUKHCONP1BZ6STRF2065 | DUKHCONP1BZ6ARRF3635, DUKHCONP1BZ6ARRF3635 | 0 | 0 | ROOF
DUKHCONP1BZ6ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-06-14 | 2014-07-12 | 2014-06-14 | 2014-07-12 | 78 | No | DUKHCONP1BZ6ARRF3640, DUKHCONP1BZ6ARRF3640 | DUKHCONP1BZ6ARRF3650, DUKHCONP1BZ6ARRF3650, DUKHCONP1BZ6ACRF4630, DUKHCONP1BZ6ACRF4630, DUKHCONP1BZ6ELRF4070, DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6ELRF4070, DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ6PLRF4350 | 0 | 0 | ROOF
DHBL.K30.L25.35 .15 .15 .15 ELEVATION |  | 50 | 50 | 0% | 2014-06-16 | 2014-08-16 | 2014-06-16 | 2014-08-16 | 76 |  |  |  | 0 | 0
DUKHCONP1BZ6AREL3680 | External Painting | 20 | 20 | 0% | 2014-07-21 | 2014-08-16 | 2014-07-21 | 2014-08-16 | 76 | No | DUKHCONP1BZ6AREL3670, DUKHCONP1BZ6AREL3675, DUKHCONP1BZ6AREL3670, DUKHCONP1BZ6ARRF3695, DUKHCONP1BZ6AREL3675, DUKHCONP1BZ5AREL3680, DUKHCONP1BZ6ARRF3695 | DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6PLTC8005 | 0 | 0 | ELEVATION
DUKHCONP1BZ6AREL3665 | External Plastering | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 76 | No | DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6STRF2065, DUKHCONP1BZ6STRF2065, DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ5AREL3665, DUKHCONP1BZ6ARRF3605 | DUKHCONP1BZ6AREL3675, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6AREL3670, DUKHCONP1BZ6AREL3675, DUKHCONP1BZ6AREL3670 | 0 | 0 | ELEVATION
DUKHCONP1BZ6AREL3670 | External stone cladding works | 20 | 20 | 0% | 2014-07-03 | 2014-07-26 | 2014-07-03 | 2014-07-26 | 76 | No | DUKHCONP1BZ5AREL3670, DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6AREL3665 | DUKHCONP1BZ6AREL3680, DUKHCONP1BZ6AREL3675, DUKHCONP1BZ6AREL3680 | 0 | 0 | ELEVATION
DUKHCONP1BZ6AREL3675 | GRC works | 20 | 20 | 0% | 2014-07-09 | 2014-07-31 | 2014-07-09 | 2014-07-31 | 76 | No | DUKHCONP1BZ5AREL3675, DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6AREL3670, DUKHCONP1BZ6AREL3665 | DUKHCONP1BZ6AREL3680, DUKHCONP1BZ6AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L25.35 .20 MEP WORKS |  | 271 | 271 | 0% | 2013-12-24 | 2014-11-11 | 2013-12-24 | 2014-11-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.35 .20 .10 ELECTRICAL WORKS |  | 189 | 189 | 0% | 2014-03-31 | 2014-11-11 | 2014-03-31 | 2014-11-11 | 3 |  |  |  | 0 | 0
DHBL.K30.L25.35 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2014-03-31 | 2014-08-10 | 2014-03-31 | 2014-08-10 | 56 |  |  |  | 0 | 0
DUKHCONP1BZ6ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-04-12 | 2014-05-04 | 2014-04-12 | 2014-05-04 | 76 | No | DUKHCONP1BZ6ELGF4000, DUKHCONP1BZ6ELGF4000, DUKHCONP1BZ5ELGF4005 | DUKHCONP1BZ6ELGF4010, DUKHCONP1BZ6ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 58 | No | DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ6ARGF3000 | DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6ELGF4005, DUKHCONP1BZ6ELGF4005, DUKHCONP1BZ6ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-06-22 | 2014-07-20 | 2014-06-22 | 2014-07-20 | 71 | No | DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ5ELGF4015, DUKHCONP1BZ6ARGF3055 | DUKHCONP1BZ6ELFF4055, DUKHCONP1BZ6ELFF4055, DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-06-28 | 2014-07-20 | 2014-06-28 | 2014-07-20 | 49 | No | DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ELGF4010, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ELGF4010, DUKHCONP1BZ6ARGF3055 | DUKHCONP1BZ6ELGF4030, DUKHCONP1BZ6ELGF4030, DUKHCONP1BZ6ELGF4025, DUKHCONP1BZ6ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-07-09 | 2014-08-10 | 2014-07-09 | 2014-08-10 | 51 | No | DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ5ELGF4025, DUKHCONP1BZ6ARGF3060 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ6ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-07-09 | 2014-07-31 | 2014-07-09 | 2014-07-31 | 49 | No | DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ5ELGF4030, DUKHCONP1BZ6ARGF3060 | DUKHCONP1BZ6ELFF4050, DUKHCONP1BZ6ELFF4050, DUKHCONP1BZ6ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 76 | No | DUKHCONP1BZ6ELGF4005, DUKHCONP1BZ6ELGF4005 | DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ6ARGF3045, DUKHCONP1BZ6ELGF4020, DUKHCONP1BZ6ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.35 .20 .10 .15 FIRST FLOORS |  | 129 | 129 | 0% | 2014-05-11 | 2014-10-13 | 2014-05-11 | 2014-10-13 | 28 |  |  |  | 0 | 0
DUKHCONP1BZ6ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-05-22 | 2014-06-14 | 2014-05-22 | 2014-06-14 | 46 | No | DUKHCONP1BZ6ELFF4035, DUKHCONP1BZ6ELFF4035 | DUKHCONP1BZ6ELFF4045, DUKHCONP1BZ6ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 16 | No | DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6ARFF3300 | DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6ELFF4040, DUKHCONP1BZ6ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-08-24 | 2014-09-21 | 2014-08-24 | 2014-09-21 | 45 | No | DUKHCONP1BZ6ELGF4015, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ELGF4015, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ5ELFF4055, DUKHCONP1BZ6ELGF4015 | DUKHCONP1BZ6ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-08-31 | 2014-09-22 | 2014-08-31 | 2014-09-22 | 3 | No | DUKHCONP1BZ6ELFF4045, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ5ELFF4060, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ELFF4045 | DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ6ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-09-13 | 2014-10-13 | 2014-09-13 | 2014-10-13 | 3 | No | DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ELFF4060, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ELFF4060, DUKHCONP1BZ6ELGF4025, DUKHCONP1BZ6ELGF4025, DUKHCONP1BZ5ELFF4065 | DUKHCONP1BZ6ELRF4070, DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-08-21 | 2014-09-18 | 2014-08-21 | 2014-09-18 | 25 | No | DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ELGF4030, DUKHCONP1BZ6MSEX5010, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ELGF4030 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ELRF4070, DUKHCONP1BZ6ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-05-31 | 2014-06-28 | 2014-05-31 | 2014-06-28 | 46 | No | DUKHCONP1BZ5ELFF4045, DUKHCONP1BZ6ELFF4040, DUKHCONP1BZ6ELFF4040 | DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ6ELRF4070, DUKHCONP1BZ6ARFF3345, DUKHCONP1BZ6ELFF4060, DUKHCONP1BZ6ELRF4070, DUKHCONP1BZ6ELFF4060 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.35 .20 .10 .20 ROOF |  | 33 | 33 | 0% | 2014-10-02 | 2014-11-11 | 2014-10-02 | 2014-11-11 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ6ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-10-02 | 2014-10-25 | 2014-10-02 | 2014-10-25 | 3 | No | DUKHCONP1BZ6ELFF4045, DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ6ELFF4050, DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ6ELFF4045, DUKHCONP1BZ6ELFF4050 | DUKHCONP1BZ6ELRF4075, DUKHCONP1BZ6ELRF4075 | 0 | 0 | ROOF
DUKHCONP1BZ6ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-10-16 | 2014-11-11 | 2014-10-16 | 2014-11-11 | 3 | No | DUKHCONP1BZ6ELRF4070, DUKHCONP1BZ6ELRF4070 | DUKHCONP1BZ6ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L25.35 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 255 | 255 | 0% | 2013-12-24 | 2014-10-23 | 2013-12-24 | 2014-10-23 | 19 |  |  |  | 0 | 0
DHBL.K30.L25.35 .20 .15 .10 GROUND FLOOR |  | 193 | 193 | 0% | 2013-12-24 | 2014-08-10 | 2013-12-24 | 2014-08-10 | 81 |  |  |  | 0 | 0
DUKHCONP1BZ6PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-12-24 | 2014-01-15 | 2013-12-24 | 2014-01-15 | 11 | No | DUKHCONP1BZ6STUG1040, DUKHCONP1BZ6STUG1040 | DUKHCONP1BZ6STUG1045, DUKHCONP1BZ6STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2014-04-10 | 2014-04-30 | 2014-04-10 | 2014-04-30 | 52 | No | DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ6PLGF4305, DUKHCONP1BZ6ARGF3000 | DUKHCONP1BZ6PLGF4315, DUKHCONP1BZ6MSEX5000, DUKHCONP1BZ6PLGF4315, DUKHCONP1BZ6ARGF3020, DUKHCONP1BZ6ARGF3020, DUKHCONP1BZ6MSEX5000 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-04-10 | 2014-04-30 | 2014-04-10 | 2014-04-30 | 49 | No | DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ6ARGF3000, DUKHCONP1BZ5PLGF4305 | DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ6ARGF3020, DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-07-21 | 2014-08-10 | 2014-07-21 | 2014-08-10 | 81 | No | DUKHCONP1BZ6PLGF4315, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ5PLGF4320, DUKHCONP1BZ6PLGF4315, DUKHCONP1BZ6ARGF3060 | DUKHCONP1BZ6PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-07-09 | 2014-07-31 | 2014-07-09 | 2014-07-31 | 81 | No | DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ6ARGF3065, DUKHCONP1BZ5PLGF4315, DUKHCONP1BZ6ARGF3065 | DUKHCONP1BZ6PLGF4320, DUKHCONP1BZ6PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.35 .20 .15 .15 FIRST FLOORS |  | 113 | 113 | 0% | 2014-05-22 | 2014-10-04 | 2014-05-22 | 2014-10-04 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ6PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-05-22 | 2014-06-11 | 2014-05-22 | 2014-06-11 | 30 | No | DUKHCONP1BZ6PLFF4325, DUKHCONP1BZ6PLFF4325, DUKHCONP1BZ5PLFF4330, DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6ARFF3300 | DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6PLFF4335, DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ6PLFF4335, DUKHCONP1BZ6PLRF4350 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-05-22 | 2014-06-11 | 2014-05-22 | 2014-06-11 | 3 | No | DUKHCONP1BZ6ARFF3300, DUKHCONP1BZ6ARFF3300 | DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6ARFF3320, DUKHCONP1BZ6ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-09-17 | 2014-10-04 | 2014-09-17 | 2014-10-04 | 19 | No | DUKHCONP1BZ5PLFF4340, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6PLFF4335, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6PLFF4335 | DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-09-06 | 2014-09-28 | 2014-09-06 | 2014-09-28 | 19 | No | DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6ARFF3365, DUKHCONP1BZ6ARFF3365 | DUKHCONP1BZ6PLFF4340, DUKHCONP1BZ6PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.35 .20 .15 .20 ROOF |  | 105 | 105 | 0% | 2014-06-18 | 2014-10-23 | 2014-06-18 | 2014-10-23 | 19 |  |  |  | 0 | 0
DUKHCONP1BZ6PLRF4345 | Installation of Plumbing pipes & fittings | 14 | 14 | 0% | 2014-06-18 | 2014-07-03 | 2014-06-18 | 2014-07-03 | 86 | No | DUKHCONP1BZ6ARRF3605, DUKHCONP1BZ5PLRF4345, DUKHCONP1BZ6ARRF3605 | DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6PLRF4355 | 0 | 0 | ROOF
DUKHCONP1BZ6PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-07-06 | 2014-07-22 | 2014-07-06 | 2014-07-22 | 79 | No | DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ5PLRF4350, DUKHCONP1BZ6AREL3665, DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ6PLRF4345, DUKHCONP1BZ6PLFF4330, DUKHCONP1BZ6PLRF4345, DUKHCONP1BZ6ARRF3645 | DUKHCONP1BZ6WEEX5065, DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6PLTC8005, DUKHCONP1BZ6WEEX5065 | 0 | 0 | ROOF
DUKHCONP1BZ6PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-09-23 | 2014-10-23 | 2014-09-23 | 2014-10-23 | 19 | No | DUKHCONP1BZ5PLRF4355, DUKHCONP1BZ6PLFF4340, DUKHCONP1BZ6WEEX5065, DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ6PLFF4340, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ6PLRF4345, DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ6PLRF4345 | DUKHCONP1BZ6PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L25.35 .20 .20 AC WORKS |  | 144 | 144 | 0% | 2014-04-30 | 2014-10-20 | 2014-04-30 | 2014-10-20 | 22 |  |  |  | 0 | 0
DHBL.K30.L25.35 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-04-30 | 2014-08-07 | 2014-04-30 | 2014-08-07 | 68 |  |  |  | 0 | 0
DUKHCONP1BZ6ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-07-13 | 2014-08-07 | 2014-07-13 | 2014-08-07 | 68 | No | DUKHCONP1BZ5ACGF4610, DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ6ACGF4605 | DUKHCONP1BZ6ACRF4635, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ACRF4635, DUKHCONP1BZ6ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-06-22 | 2014-07-20 | 2014-06-22 | 2014-07-20 | 68 | No | DUKHCONP1BZ5ACGF4605, DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ARGF3055 | DUKHCONP1BZ6ACGF4610, DUKHCONP1BZ6ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP1BZ6ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-04-30 | 2014-05-22 | 2014-04-30 | 2014-05-22 | 80 | No | DUKHCONP1BZ5ACGF4600, DUKHCONP1BZ6ARGF3005, DUKHCONP1BZ6ARGF3005 | DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ARGF3060, DUKHCONP1BZ6ARGF3055, DUKHCONP1BZ6ACRF4630, DUKHCONP1BZ6ACRF4630, DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ6ACGF4605, DUKHCONP1BZ6ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L25.35 .20 .20 .15 FIRST FLOORS |  | 95 | 95 | 0% | 2014-06-15 | 2014-10-06 | 2014-06-15 | 2014-10-06 | 17 |  |  |  | 0 | 0
DUKHCONP1BZ6ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-09-14 | 2014-10-06 | 2014-09-14 | 2014-10-06 | 17 | No | DUKHCONP1BZ6ACFF4620, DUKHCONP1BZ5ACFF4625, DUKHCONP1BZ6ACFF4620 | DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ACRF4635, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ACRF4635, DUKHCONP1BZ6ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-08-24 | 2014-09-21 | 2014-08-24 | 2014-09-21 | 17 | No | DUKHCONP1BZ5ACFF4620, DUKHCONP1BZ6ACFF4615, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ACFF4615 | DUKHCONP1BZ6ACFF4625, DUKHCONP1BZ6ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP1BZ6ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-06-15 | 2014-07-07 | 2014-06-15 | 2014-07-07 | 46 | No | DUKHCONP1BZ6ARFF3305, DUKHCONP1BZ5ACFF4615, DUKHCONP1BZ6ARFF3305 | DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ARFF3360, DUKHCONP1BZ6ACFF4620, DUKHCONP1BZ6ACRF4630, DUKHCONP1BZ6ACFF4620, DUKHCONP1BZ6ACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L25.35 .20 .20 .20 ROOF |  | 95 | 95 | 0% | 2014-06-26 | 2014-10-20 | 2014-06-26 | 2014-10-20 | 22 |  |  |  | 0 | 0
DUKHCONP1BZ6ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-09-20 | 2014-10-20 | 2014-09-20 | 2014-10-20 | 22 | No | DUKHCONP1BZ6ACGF4610, DUKHCONP1BZ5ACRF4635, DUKHCONP1BZ6ACFF4625, DUKHCONP1BZ6ACGF4610, DUKHCONP1BZ6ACRF4630, DUKHCONP1BZ6ACFF4625, DUKHCONP1BZ6ACRF4630 | DUKHCONP1BZ6ACTC8000 | 0 | 0 | ROOF
DUKHCONP1BZ6ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-06-26 | 2014-07-24 | 2014-06-26 | 2014-07-24 | 87 | No | DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ6ARRF3645, DUKHCONP1BZ5ACRF4630, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ACGF4600, DUKHCONP1BZ6ACFF4615, DUKHCONP1BZ6ACFF4615 | DUKHCONP1BZ6ACRF4635, DUKHCONP1BZ6ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L25.35 .25 EXTERNAL WORKS |  | 161 | 161 | 0% | 2014-05-06 | 2014-11-15 | 2014-05-06 | 2014-11-15 | 25 |  |  |  | 0 | 0
DHBL.K30.L25.35 .25 .10 MISCELLANEOUS |  | 161 | 161 | 0% | 2014-05-06 | 2014-11-15 | 2014-05-06 | 2014-11-15 | 25 |  |  |  | 0 | 0
DUKHCONP1BZ6MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-10-18 | 2014-11-15 | 2014-10-18 | 2014-11-15 | 25 | No | DUKHCONI1BZ4BWGL5325, DUKHCONP1BZ5MSEX5335 | DUKHHANP1BGNELTC9010, DUKHHANP1BGNPLTC9005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ6MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 38 | No | DUKHCONP1BZ6MSEX5000, DUKHCONP1BZ6MSEX5000 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6PLTC8005, DUKHCONP1BZ6MSEX5015, DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ6MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-05-06 | 2014-06-03 | 2014-05-06 | 2014-06-03 | 69 | No | DUKHCONP1BZ6STRF2055, DUKHCONP1BZ6STRF2055, DUKHCONP1BZ5MSEX5020 | DUKHCONP1BZ6MSEX5025, DUKHCONP1BZ6HDEX5090, DUKHCONP1BZ6MSEX5025, DUKHCONP1BZ6HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ6MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-06-11 | 2014-07-03 | 2014-06-11 | 2014-07-03 | 38 | No | DUKHCONP1BZ6MSEX5005, DUKHCONP1BZ6MSEX5005 | DUKHCONP1BZ6WEEX5065, DUKHCONP1BZ6WEEX5050, DUKHCONP1BZ6MSEX5010, DUKHCONP1BZ6WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ6MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-05-08 | 2014-06-05 | 2014-05-08 | 2014-06-05 | 38 | No | DUKHCONP1BZ6PLGF4310, DUKHCONP1BZ6STRF2055, DUKHCONP1BZ6STRF2055, DUKHCONP1BZ6PLGF4310 | DUKHCONP1BZ6MSEX5005, DUKHCONP1BZ6MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ6MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-05-26 | 2014-06-17 | 2014-05-26 | 2014-06-17 | 69 | No | DUKHCONP1BZ6MSEX5020, DUKHCONP1BZ6MSEX5020 | DUKHCONP1BZ6WEEX5045, DUKHCONP1BZ6WEEX5050, DUKHCONP1BZ6HDEX5090, DUKHCONP1BZ6WEEX5060 | 0 | 0 | MISCELLANEOUS
DUKHCONP1BZ6MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-07-05 | 2014-08-05 | 2014-07-05 | 2014-08-05 | 38 | No | DUKHCONP1BZ6MSEX5015 | DUKHCONP1BZ6ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L25.35 .25 .15 WATER TANK ENCLOSURE |  | 83 | 83 | 0% | 2014-06-07 | 2014-09-14 | 2014-06-07 | 2014-09-14 | 51 |  |  |  | 0 | 0
DUKHCONP1BZ6WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 51 | No | DUKHCONP1BZ6WEEX5035, DUKHCONP1BZ6WEEX5035 | DUKHCONP1BZ6WEEX5045, DUKHCONP1BZ6WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ6WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-06-18 | 2014-07-16 | 2014-06-18 | 2014-07-16 | 51 | No | DUKHCONP1BZ6WEEX5030, DUKHCONP1BZ6WEEX5030 | DUKHCONP1BZ6WEEX5040, DUKHCONP1BZ6WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ6WEEX5030 | Excavation | 20 | 20 | 0% | 2014-06-07 | 2014-06-29 | 2014-06-07 | 2014-06-29 | 51 | No | DUKHCONP1BZ5WEEX5035, DUKHCONP1BZ6STRF2060, DUKHCONP1BZ6STRF2055, DUKHCONP1BZ6STRF2055 | DUKHCONP1BZ6WEEX5035, DUKHCONP1BZ6WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ6WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-07-09 | 2014-08-10 | 2014-07-09 | 2014-08-10 | 51 | No | DUKHCONP1BZ6WEEX5040, DUKHCONP1BZ6MSEX5025, DUKHCONP1BZ6WEEX5040 | DUKHCONP1BZ6WEEX5050, DUKHCONP1BZ6WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ6WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 51 | No | DUKHCONP1BZ6MSEX5015, DUKHCONP1BZ6PLRF4350, DUKHCONP1BZ5WEEX5065, DUKHCONP1BZ6WEEX5060, DUKHCONP1BZ6MSEX5015, DUKHCONP1BZ6WEEX5060, DUKHCONP1BZ6PLRF4350 | DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ6WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-07-27 | 2014-08-21 | 2014-07-27 | 2014-08-21 | 51 | No | DUKHCONP1BZ6MSEX5025, DUKHCONP1BZ6MSEX5015, DUKHCONP1BZ6WEEX5045, DUKHCONP1BZ6WEEX5045 | DUKHCONP1BZ6WEEX5060, DUKHCONP1BZ6WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP1BZ6WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-08-05 | 2014-09-02 | 2014-08-05 | 2014-09-02 | 51 | No | DUKHCONP1BZ6WEEX5050, DUKHCONP1BZ6WEEX5050, DUKHCONP1BZ6MSEX5025, DUKHCONP1BZ5WEEX5060 | DUKHCONP1BZ6WEEX5065, DUKHCONP1BZ6WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L25.35 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2014-06-03 | 2014-07-22 | 2014-06-03 | 2014-07-22 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ6HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-06-15 | 2014-07-07 | 2014-06-15 | 2014-07-07 | 69 | No | DUKHCONP1BZ6HDEX5090, DUKHCONP1BZ6HDEX5090 | DUKHCONP1BZ6HDEX5100, DUKHCONP1BZ6HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ6HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-06-30 | 2014-07-22 | 2014-06-30 | 2014-07-22 | 69 | No | DUKHCONP1BZ6HDEX5095, DUKHCONP1BZ6HDEX5095 | DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6PLTC8005, DUKHCONP1BZ6SLEX5105, DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6SLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP1BZ6HDEX5090 | kerb works | 20 | 20 | 0% | 2014-06-03 | 2014-06-25 | 2014-06-03 | 2014-06-25 | 69 | No | DUKHCONP1BZ6MSEX5025, DUKHCONP1BZ5HDEX5090, DUKHCONP1BZ6MSEX5020, DUKHCONP1BZ6MSEX5020 | DUKHCONP1BZ6HDEX5095, DUKHCONP1BZ6HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L25.35 .25 .25 SOFT LANDSCAPING |  | 35 | 35 | 0% | 2014-07-12 | 2014-08-24 | 2014-07-12 | 2014-08-24 | 69 |  |  |  | 0 | 0
DUKHCONP1BZ6SLEX5105 | Laying of Grass/ green area | 25 | 25 | 0% | 2014-07-12 | 2014-08-12 | 2014-07-12 | 2014-08-12 | 69 | No | DUKHCONP1BZ6HDEX5100, DUKHCONP1BZ6HDEX5100 | DUKHCONP1BZ6ACTC8000, DUKHCONP1BZ6SLEX5110, DUKHCONP1BZ6PLTC8005, DUKHCONP1BZ6SLEX5110, DUKHCONP1BZ6ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP1BZ6SLEX5110 | Laying of Palm tree | 25 | 25 | 0% | 2014-07-23 | 2014-08-24 | 2014-07-23 | 2014-08-24 | 69 | No | DUKHCONP1BZ6SLEX5105, DUKHCONP1BZ6SLEX5105 | DUKHCONP1BZ6PLTC8005, DUKHCONP1BZ6ELTC8010, DUKHCONP1BZ6ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L25.35 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-11-12 | 2014-12-10 | 2014-11-12 | 2014-12-10 | 3 |  |  |  | 0 | 0
DUKHCONP1BZ6ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-11-12 | 2014-12-10 | 2014-11-12 | 2014-12-10 | 3 | No | DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ6SLEX5105, DUKHMOBI1BPS00002135, DUKHCONP1BZ6AREL3680, DUKHCONP1BZ6MSEX5005, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ACRF4635, DUKHMOBP1BPS00002100, DUKHCONP1BZ6SLEX5110, DUKHCONP1BZ6HDEX5100, DUKHCONP1BZ6ACFF4625, DUKHCONP1BZ6ARRF3620 | DUKHHANP1BGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ6ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-11-12 | 2014-12-10 | 2014-11-12 | 2014-12-10 | 3 | No | DUKHCONP1BZ6HDEX5100, DUKHCONP1BZ6MSEX5005, DUKHCONP1BZ6ARRF3660, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6ARRF3620, DUKHCONP1BZ6ELGF4025, DUKHMOBI1BPS00002135, DUKHCONP1BZ6ELFF4050, DUKHMOBP1BPS00002100, DUKHCONP1BZ6ARRF3655, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ6SLEX5110, DUKHCONP1BZ6AREL3680, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ELFF4065, DUKHCONP1BZ6ELRF4075, DUKHCONP1BZ6ELGF4015, DUKHCONP1BZ6ELGF4030, DUKHCONP1BZ6SLEX5105, DUKHCONP1BZ6ELFF4055 | DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP1BZ6PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-11-12 | 2014-12-10 | 2014-11-12 | 2014-12-10 | 3 | No | DUKHCONP1BZ6SLEX5110, DUKHCONP1BZ6MSEX5005, DUKHCONP1BZ6PLGF4320, DUKHCONP1BZ6ARRF3620, DUKHCONP1BZ6SLEX5105, DUKHCONP1BZ6WEEX5065, DUKHCONP1BZ6ARRF3660, DUKHCONP1BZ6ARFF3395, DUKHCONP1BZ6ARGF3095, DUKHCONP1BZ6HDEX5100, DUKHCONP1BZ6PLRF4355, DUKHCONP1BZ6PLRF4350, DUKHMOBP1BPS00002100, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ6AREL3680, DUKHCONP1BZ6ARRF3655, DUKHMOBI1BPS00002135 | DUKHHANP1BGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L30 PACKAGE-1B INFRASTRUCTURE WORKS |  | 338 | 338 | 0% | 2013-11-25 | 2015-01-01 | 2013-11-25 | 2015-01-01 | 6 |  |  |  | 0 | 0
DHBL.K30.L30.10 ZONE - 1 |  | 217 | 217 | 0% | 2013-11-25 | 2014-08-10 | 2013-11-25 | 2014-08-10 | 76 |  |  |  | 0 | 0
DHBL.K30.L30.10 .10 INFRASTRUCTURE WORKS |  | 217 | 217 | 0% | 2013-11-25 | 2014-08-10 | 2013-11-25 | 2014-08-10 | 76 |  |  |  | 0 | 0
DHBL.K30.L30.10 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-11-25 | 2014-01-14 | 2013-11-25 | 2014-01-14 | 0 |  |  |  | 0 | 0
DUKHCONI1BZ1DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-12-29 | 2014-01-14 | 2013-12-29 | 2014-01-14 | 0 | Yes | DUKHCONI1BZ1DRGL5125, DUKHCONI1BZ1DRGL5125 | DUKHCONI1BZ1SAGL5135, DUKHCONI1BZ1WSGL5155, DUKHCONI1BZ2DRGL5115, DUKHCONI1BZ1SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ1DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-11-25 | 2013-12-24 | 2013-11-25 | 2013-12-24 | 0 | Yes | DUKHCONP1BZ2STFF2025, DUKHENGI1BDWDRAP4650 | DUKHCONI1BZ1SAGL5135, DUKHCONI1BZ1DRGL5120, DUKHCONI1BZ1SAGL5140, DUKHMOBI1BPS00002135, DUKHCONI1BZ1DRGL5120 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ1DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-12-02 | 2013-12-31 | 2013-12-02 | 2013-12-31 | 0 | Yes | DUKHCONI1BZ1DRGL5115, DUKHCONI1BZ1DRGL5115 | DUKHCONI1BZ1DRGL5125, DUKHCONI1BZ1DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ1DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 0 | Yes | DUKHCONI1BZ1DRGL5120, DUKHCONI1BZ1DRGL5120 | DUKHCONI1BZ1DRGL5130, DUKHCONI1BZ1DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L30.10 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-12-29 | 2014-03-20 | 2013-12-29 | 2014-03-20 | 34 |  |  |  | 0 | 0
DUKHCONI1BZ1SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 34 | No | DUKHCONI1BZ1SAGL5135, DUKHCONI1BZ1SAGL5145 | DUKHCONI1BZ1RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ1SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 59 | No | DUKHCONI1BZ1DRGL5115, DUKHCONI1BZ1DRGL5130, DUKHENGI1BDWDRAP4650 | DUKHCONI1BZ1SAGL5150, DUKHCONI1BZ2SAGL5135 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ1SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 0 | Yes | DUKHCONI1BZ1SAGL5140 | DUKHCONI1BZ1SAGL5150, DUKHCONI1BZ1WSGL5170, DUKHCONI1BZ2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ1SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 0 | Yes | DUKHCONI1BZ1DRGL5115, DUKHCONI1BZ1DRGL5130 | DUKHCONI1BZ1SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L30.10 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-01-09 | 2014-03-26 | 2014-01-09 | 2014-03-26 | 29 |  |  |  | 0 | 0
DUKHCONI1BZ1WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 0 | Yes | DUKHCONI1BZ1WSGL5165, DUKHCONI1BZ1SAGL5145 | DUKHCONI1BZ1WSGL5175, DUKHCONI1BZ2WSGL5155, DUKHCONI1BZ1FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 29 | No | DUKHCONI1BZ1WSGL5170, DUKHCONI1BZ1WSGL5155 | DUKHCONI1BZ2WSGL5175, DUKHCONI1BZ1WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ1WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-01-09 | 2014-02-06 | 2014-01-09 | 2014-02-06 | 0 | Yes | DUKHENGI1BDWWSAP4670, DUKHCONI1BZ1DRGL5130 | DUKHCONI1BZ1WSGL5175, DUKHCONI1BZ1WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ1WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-03-04 | 2014-03-26 | 2014-03-04 | 2014-03-26 | 29 | No | DUKHCONI1BZ1WSGL5175 | DUKHCONI1BZ2WSGL5180, DUKHCONI1BZ1FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ1WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-01-15 | 2014-02-13 | 2014-01-15 | 2014-02-13 | 0 | Yes | DUKHCONI1BZ1WSGL5155 | DUKHCONI1BZ1WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ1WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 0 | Yes | DUKHCONI1BZ1WSGL5160 | DUKHCONI1BZ1WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L30.10 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-02-02 | 2014-04-03 | 2014-02-02 | 2014-04-03 | 22 |  |  |  | 0 | 0
DUKHCONI1BZ1FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-02-23 | 2014-03-23 | 2014-02-23 | 2014-03-23 | 0 | Yes | DUKHCONI1BZ1FFGL5195 | DUKHCONI1BZ2FFGL5185, DUKHCONI1BZ1FFGL5205, DUKHCONI1BZ1ELGL5215, DUKHCONI1BZ1RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ1FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 22 | No | DUKHCONI1BZ1WSGL5180, DUKHCONI1BZ1FFGL5205 | DUKHCONI1BZ3RWGL6000, DUKHCONI1BZ2FFGL5210, DUKHCONI1BSBIWGL7440, DUKHCONI1BZ1RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-03-01 | 2014-03-29 | 2014-03-01 | 2014-03-29 | 22 | No | DUKHCONI1BZ1FFGL5200, DUKHCONI1BZ1FFGL5185 | DUKHCONI1BZ2FFGL5205, DUKHCONI1BZ1FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ1FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 0 | Yes | DUKHENGI1BDWFFAP4660, DUKHCONI1BZ1WSGL5170 | DUKHCONI1BZ1FFGL5190, DUKHCONI1BZ1FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ1FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-02-10 | 2014-03-11 | 2014-02-10 | 2014-03-11 | 0 | Yes | DUKHCONI1BZ1FFGL5185 | DUKHCONI1BZ1FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ1FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 0 | Yes | DUKHCONI1BZ1FFGL5190 | DUKHCONI1BZ1FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L30.10 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-03-03 | 2014-04-26 | 2014-03-03 | 2014-04-26 | 79 |  |  |  | 0 | 0
DUKHCONI1BZ1ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-03-17 | 2014-04-14 | 2014-03-17 | 2014-04-14 | 3 | No | DUKHCONI1BZ1ELGL5215, DUKHCONI1BZ1ELGL5220 | DUKHCONI1BZ1IRGL5285, DUKHCONI1BZ1IRGL5265, DUKHCONI1BZ1ELGL5230, DUKHCONI1BZ1RWGL6000, DUKHCONI1BZ1ELGL5230, DUKHCONI1BZ2ELGL5215 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-03-29 | 2014-04-26 | 2014-03-29 | 2014-04-26 | 79 | No | DUKHCONI1BZ1ELGL5225, DUKHCONI1BZ1ELGL5225 | DUKHCONI1BZ2ELGL5230, DUKHCONI1BZ1STGL5260 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 0 | Yes | DUKHENGI1BDWELAP4680, DUKHCONI1BZ1FFGL5200 | DUKHCONI1BZ1ELGL5225, DUKHCONI1BZ1ELGL5220, DUKHCONI1BZ1STGL5235 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ1ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 3 | No | DUKHCONI1BZ1ELGL5215 | DUKHCONI1BZ1ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L30.10 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-03-03 | 2014-05-25 | 2014-03-03 | 2014-05-25 | 79 |  |  |  | 0 | 0
DUKHCONI1BZ1STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 0 | Yes | DUKHCONI1BZ1STGL5245, DUKHCONI1BZ1STGL5235 | DUKHCONI1BZ1RWGL6000, DUKHCONI1BZ2STGL5235, DUKHCONI1BZ1TCGL5295, DUKHCONI1BZ1BWGL5315, DUKHCONI1BZ1STGL5255 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ1STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 0 | Yes | DUKHCONI1BZ1STGL5235 | DUKHCONI1BZ1STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ1STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 0 | Yes | DUKHCONI1BZ1STGL5240 | DUKHCONI1BZ1STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ1STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 79 | No | DUKHCONI1BZ1STGL5255, DUKHCONI1BZ1ELGL5230 | DUKHCONI1BZ1PSGL7015, DUKHCONI1BZ2STGL5260 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ1STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 0 | Yes | DUKHENGI1BDWSTAP4690, DUKHCONI1BZ1ELGL5215 | DUKHCONI1BZ1STGL5250, DUKHCONI1BZ1STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ1STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 99 | No | DUKHCONI1BZ1STGL5250 | DUKHCONI1BZ1STGL5260, DUKHCONI1BZ2STGL5255 | 0 | 0 | STREET LIGHTING
DHBL.K30.L30.10 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-04-15 | 2014-06-19 | 2014-04-15 | 2014-06-19 | 22 |  |  |  | 0 | 0
DUKHCONI1BZ1IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 7 | No | DUKHCONI1BZ1IRGL5275 | DUKHCONI1BZ1IRGL5290, DUKHCONI1BZ1IRGL5285, DUKHCONI1BZ2IRGL5265 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-05-14 | 2014-06-11 | 2014-05-14 | 2014-06-11 | 22 | No | DUKHCONI1BZ1ELGL5225, DUKHCONI1BZ1IRGL5280 | DUKHCONI1BZ1IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ1IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 7 | No | DUKHCONI1BZ1ELGL5225, DUKHENGI1BDWIRAP4710 | DUKHCONI1BZ1IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 22 | No | DUKHCONI1BZ1IRGL5280, DUKHCONI1BZ1IRGL5285 | DUKHCONI1BZ1SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ1IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-04-21 | 2014-05-19 | 2014-04-21 | 2014-05-19 | 7 | No | DUKHCONI1BZ1IRGL5265 | DUKHCONI1BZ1IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ1IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 7 | No | DUKHCONI1BZ1IRGL5270 | DUKHCONI1BZ1IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L30.10 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-03-26 | 2014-05-11 | 2014-03-26 | 2014-05-11 | 91 |  |  |  | 0 | 0
DUKHCONI1BZ1TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-04-07 | 2014-04-29 | 2014-04-07 | 2014-04-29 | 0 | Yes | DUKHCONI1BZ1TCGL5300 | DUKHCONI1BZ1TCGL5310, DUKHCONI1BZ1RWGL6000, DUKHCONI1BZ2TCGL5295 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ1TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-04-19 | 2014-05-11 | 2014-04-19 | 2014-05-11 | 91 | No | DUKHCONI1BZ1TCGL5305 | DUKHCONI1BSBTRGL7630, DUKHCONI1BZ2TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ1TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-03-26 | 2014-04-17 | 2014-03-26 | 2014-04-17 | 0 | Yes | DUKHENGI1BDWTCAP4700, DUKHCONI1BZ1STGL5250 | DUKHCONI1BZ1TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ1TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-04-01 | 2014-04-23 | 2014-04-01 | 2014-04-23 | 0 | Yes | DUKHCONI1BZ1TCGL5295 | DUKHCONI1BZ1TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L30.10 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-03-26 | 2014-06-19 | 2014-03-26 | 2014-06-19 | 88 |  |  |  | 0 | 0
DUKHCONI1BZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 88 | No | DUKHCONI1BZ1BWGL5325 | DUKHCONI1BZ1PSGL7010, DUKHCONI1BZ2BWGL5330 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 25 | No | DUKHCONI1BZ1BWGL5315, DUKHCONI1BZ1BWGL5320 | DUKHCONI1BZ1BWGL5330, DUKHCONI1BZ2BWGL5325, DUKHCONP1BZ2MSEX5335, DUKHCONP1BZ1MSEX5335 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 25 | No | DUKHCONI1BZ1STGL5250, DUKHENGI1BDWBWAP4730 | DUKHCONI1BZ2BWGL5315, DUKHCONI1BZ1BWGL5325, DUKHCONI1BZ1BWGL5320 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 25 | No | DUKHCONI1BZ1BWGL5315 | DUKHCONI1BZ1BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L30.10 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-04-30 | 2014-07-14 | 2014-04-30 | 2014-07-14 | 67 |  |  |  | 0 | 0
DUKHCONI1BZ1RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-04-30 | 2014-05-11 | 2014-04-30 | 2014-05-11 | 0 | Yes | DUKHCONI1BZ1STGL5250, DUKHCONI1BZ1TCGL5305, DUKHCONI1BZ1FFGL5200, DUKHCONI1BZ1ELGL5225, DUKHENGI1BDWBWAP4730, DUKHCONI1BZ1FFGL5210, DUKHCONI1BZ1SAGL5150 | DUKHCONI1BZ1HDGL7020, DUKHCONI1BZ1RWGL6005 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-07-03 | 2014-07-08 | 2014-07-03 | 2014-07-08 | 67 | No | DUKHCONI1BZ1RWGL6020 | DUKHCONI1BZ1HDGL7040, DUKHCONI1BZ1RWGL6030, DUKHCONI1BZ2RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ1RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-06-04 | 2014-06-26 | 2014-06-04 | 2014-06-26 | 0 | Yes | DUKHCONI1BZ1RWGL6010 | DUKHCONI1BZ1PSGL7000, DUKHCONI1BZ1RWGL6020, DUKHCONI1BZ1PSGL7005, DUKHCONI1BZ2RWGL6000 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ1RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 0 | Yes | DUKHCONI1BZ1RWGL6005 | DUKHCONI1BZ1RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-06-28 | 2014-07-02 | 2014-06-28 | 2014-07-02 | 52 | No | DUKHCONI1BZ1RWGL6015 | DUKHCONI1BZ1PSGL7010, DUKHCONI1BZ1RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ1RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 0 | Yes | DUKHCONI1BZ1RWGL6000 | DUKHCONI1BZ1RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ1RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-07-09 | 2014-07-14 | 2014-07-09 | 2014-07-14 | 67 | No | DUKHCONI1BZ1RWGL6025 | DUKHCONI1BZ2RWGL6030, DUKHCONI1BZ1PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L30.10 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-06-10 | 2014-08-10 | 2014-06-10 | 2014-08-10 | 52 |  |  |  | 0 | 0
DUKHCONI1BZ1PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-07-03 | 2014-07-31 | 2014-07-03 | 2014-07-31 | 52 | No | DUKHCONI1BZ1BWGL5330, DUKHCONI1BZ1RWGL6020, DUKHCONI1BZ1RWGL6030, DUKHCONI1BZ1PSGL7005 | DUKHCONI1BZ1PSGL7015, DUKHCONI1BZ2PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI1BZ1PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-07-09 | 2014-08-10 | 2014-07-09 | 2014-08-10 | 52 | No | DUKHCONI1BZ1STGL5260, DUKHCONI1BZ1PSGL7010 | DUKHCONI1BZ2PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1BZ1PSGL7000 | Excavation | 15 | 15 | 0% | 2014-06-10 | 2014-06-26 | 2014-06-10 | 2014-06-26 | 57 | No | DUKHCONI1BZ1RWGL6015, DUKHENGI1BDWPSAP4740 | DUKHCONI1BZ1PSGL7005, DUKHCONI1BZ1PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1BZ1PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-06-22 | 2014-07-08 | 2014-06-22 | 2014-07-08 | 52 | No | DUKHCONI1BZ1PSGL7000, DUKHCONI1BZ1RWGL6015, DUKHCONI1BZ1PSGL7000 | DUKHCONI1BZ1PSGL7010, DUKHCONI1BZ2PSGL7000 | 0 | 0 | PARKING SHED
DHBL.K30.L30.10 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-04-30 | 2014-07-20 | 2014-04-30 | 2014-07-20 | 91 |  |  |  | 0 | 0
DUKHCONI1BZ1HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 11 | No | DUKHCONI1BZ1HDGL7025 | DUKHCONI1BZ2HDGL7030, DUKHCONI1BZ1HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ1HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-07-09 | 2014-07-20 | 2014-07-09 | 2014-07-20 | 91 | No | DUKHCONI1BZ1RWGL6025, DUKHCONI1BZ1HDGL7035 | DUKHCONI1BZ2HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ1HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 11 | No | DUKHCONI1BZ1HDGL7030 | DUKHCONI1BZ1SLGL7200, DUKHCONI1BZ1HDGL7040, DUKHCONI1BZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ1HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 11 | No | DUKHCONI1BZ1HDGL7020 | DUKHCONI1BZ1HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ1HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-04-30 | 2014-05-22 | 2014-04-30 | 2014-05-22 | 11 | No | DUKHENGI1BDWSLAP4720, DUKHCONI1BZ1RWGL6000 | DUKHCONI1BZ1HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L30.10 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-06-04 | 2014-07-26 | 2014-06-04 | 2014-07-26 | 41 |  |  |  | 0 | 0
DUKHCONI1BZ1SLGL7200 | Excavation | 25 | 25 | 0% | 2014-06-04 | 2014-07-02 | 2014-06-04 | 2014-07-02 | 11 | No | DUKHCONI1BZ1IRGL5290, DUKHCONI1BZ1HDGL7035, DUKHENGI1BDWSLAP4720 | DUKHCONI1BZ1SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ1SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 41 | No | DUKHCONI1BZ1SLGL7205 | DUKHCONI1BZ2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ1SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 11 | No | DUKHCONI1BZ1SLGL7200 | DUKHCONI1BZ2SLGL7200, DUKHCONI1BZ1SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L30.15 ZONE - 2 |  | 222 | 222 | 0% | 2014-01-06 | 2014-09-25 | 2014-01-06 | 2014-09-25 | 46 |  |  |  | 0 | 0
DHBL.K30.L30.15 .10 INFRASTRUCTURE WORKS |  | 222 | 222 | 0% | 2014-01-06 | 2014-09-25 | 2014-01-06 | 2014-09-25 | 46 |  |  |  | 0 | 0
DHBL.K30.L30.15 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2014-01-06 | 2014-02-25 | 2014-01-06 | 2014-02-25 | 5 |  |  |  | 0 | 0
DUKHCONI1BZ2DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2014-02-08 | 2014-02-25 | 2014-02-08 | 2014-02-25 | 5 | No | DUKHCONI1BZ2DRGL5125, DUKHCONI1BZ2DRGL5125 | DUKHCONI1BZ2WSGL5155, DUKHCONI1BZ3DRGL5115, DUKHCONI1BZ2SAGL5140, DUKHCONI1BZ2SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ2DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 5 | No | DUKHCONI1BZ1DRGL5130 | DUKHCONI1BZ2SAGL5135, DUKHCONI1BZ2SAGL5140, DUKHCONI1BZ2DRGL5120, DUKHCONI1BZ2DRGL5120 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ2DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 5 | No | DUKHCONI1BZ2DRGL5115, DUKHCONI1BZ2DRGL5115 | DUKHCONI1BZ2DRGL5125, DUKHCONI1BZ2DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ2DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 5 | No | DUKHCONI1BZ2DRGL5120, DUKHCONI1BZ2DRGL5120 | DUKHCONI1BZ2DRGL5130, DUKHCONI1BZ2DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L30.15 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2014-02-08 | 2014-04-30 | 2014-02-08 | 2014-04-30 | 39 |  |  |  | 0 | 0
DUKHCONI1BZ2SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-04-08 | 2014-04-30 | 2014-04-08 | 2014-04-30 | 39 | No | DUKHCONI1BZ2SAGL5135, DUKHCONI1BZ2SAGL5145 | DUKHCONI1BZ2RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ2SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 64 | No | DUKHCONI1BZ1SAGL5135, DUKHCONI1BZ2DRGL5115, DUKHCONI1BZ2DRGL5130 | DUKHCONI1BZ2SAGL5150, DUKHCONI1BZ3SAGL5135 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ2SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 5 | No | DUKHCONI1BZ2SAGL5140, DUKHCONI1BZ1SAGL5145 | DUKHCONI1BZ3SAGL5145, DUKHCONI1BZ2SAGL5150, DUKHCONI1BZ2WSGL5170 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ2SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 5 | No | DUKHCONI1BZ2DRGL5130, DUKHCONI1BZ2DRGL5115 | DUKHCONI1BZ2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L30.15 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-02-26 | 2014-05-12 | 2014-02-26 | 2014-05-12 | 29 |  |  |  | 0 | 0
DUKHCONI1BZ2WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 0 | Yes | DUKHCONI1BZ2WSGL5165, DUKHCONI1BZ2SAGL5145 | DUKHCONI1BZ2FFGL5185, DUKHCONI1BZ3WSGL5155, DUKHCONI1BZ2WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 29 | No | DUKHCONI1BZ2WSGL5155, DUKHCONI1BZ1WSGL5175, DUKHCONI1BZ2WSGL5170 | DUKHCONI1BZ3WSGL5175, DUKHCONI1BZ2WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ2WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 0 | Yes | DUKHCONI1BZ2DRGL5130, DUKHCONI1BZ1WSGL5170 | DUKHCONI1BZ2WSGL5175, DUKHCONI1BZ2WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ2WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-04-20 | 2014-05-12 | 2014-04-20 | 2014-05-12 | 29 | No | DUKHCONI1BZ1WSGL5180, DUKHCONI1BZ2WSGL5175 | DUKHCONI1BZ2FFGL5210, DUKHCONI1BZ3WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ2WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 0 | Yes | DUKHCONI1BZ2WSGL5155 | DUKHCONI1BZ2WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ2WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 0 | Yes | DUKHCONI1BZ2WSGL5160 | DUKHCONI1BZ2WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L30.15 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-03-22 | 2014-05-20 | 2014-03-22 | 2014-05-20 | 22 |  |  |  | 0 | 0
DUKHCONI1BZ2FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-04-10 | 2014-05-08 | 2014-04-10 | 2014-05-08 | 0 | Yes | DUKHCONI1BZ2FFGL5195 | DUKHCONI1BZ2ELGL5215, DUKHCONI1BZ2FFGL5205, DUKHCONI1BZ3FFGL5185, DUKHCONI1BZ2RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ2FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-04-22 | 2014-05-20 | 2014-04-22 | 2014-05-20 | 22 | No | DUKHCONI1BZ2WSGL5180, DUKHCONI1BZ2FFGL5205, DUKHCONI1BZ1FFGL5210 | DUKHCONI1BZ3FFGL5210, DUKHCONI1BZ2RWGL6000, DUKHCONI1BSBIWGL7440 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 22 | No | DUKHCONI1BZ2FFGL5200, DUKHCONI1BZ1FFGL5205, DUKHCONI1BZ2FFGL5185 | DUKHCONI1BZ2FFGL5210, DUKHCONI1BZ3FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ2FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 0 | Yes | DUKHCONI1BZ1FFGL5200, DUKHCONI1BZ2WSGL5170 | DUKHCONI1BZ2FFGL5190, DUKHCONI1BZ2FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ2FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-03-30 | 2014-04-27 | 2014-03-30 | 2014-04-27 | 0 | Yes | DUKHCONI1BZ2FFGL5185 | DUKHCONI1BZ2FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ2FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-04-05 | 2014-05-03 | 2014-04-05 | 2014-05-03 | 0 | Yes | DUKHCONI1BZ2FFGL5190 | DUKHCONI1BZ2FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L30.15 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-04-19 | 2014-06-11 | 2014-04-19 | 2014-06-11 | 64 |  |  |  | 0 | 0
DUKHCONI1BZ2ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 3 | No | DUKHCONI1BZ2ELGL5220, DUKHCONI1BZ2ELGL5215 | DUKHCONI1BZ2IRGL5285, DUKHCONI1BZ2IRGL5265, DUKHCONI1BZ3ELGL5215, DUKHCONI1BZ2ELGL5230, DUKHCONI1BZ2ELGL5230, DUKHCONI1BZ2RWGL6000 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-05-14 | 2014-06-11 | 2014-05-14 | 2014-06-11 | 64 | No | DUKHCONI1BZ1ELGL5230, DUKHCONI1BZ2ELGL5225, DUKHCONI1BZ2ELGL5225 | DUKHCONI1BZ3ELGL5230, DUKHCONI1BZ2STGL5260 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 0 | Yes | DUKHCONI1BZ2FFGL5200, DUKHCONI1BZ1ELGL5225 | DUKHCONI1BZ2STGL5235, DUKHCONI1BZ2ELGL5225, DUKHCONI1BZ2ELGL5220 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ2ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 3 | No | DUKHCONI1BZ2ELGL5215 | DUKHCONI1BZ2ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L30.15 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-04-19 | 2014-07-10 | 2014-04-19 | 2014-07-10 | 64 |  |  |  | 0 | 0
DUKHCONI1BZ2STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 0 | Yes | DUKHCONI1BZ2STGL5245, DUKHCONI1BZ2STGL5235 | DUKHCONI1BZ2BWGL5315, DUKHCONI1BZ2STGL5255, DUKHCONI1BZ3STGL5235, DUKHCONI1BZ2TCGL5295, DUKHCONI1BZ2RWGL6000 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ2STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 0 | Yes | DUKHCONI1BZ2STGL5235 | DUKHCONI1BZ2STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ2STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 0 | Yes | DUKHCONI1BZ2STGL5240 | DUKHCONI1BZ2STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ2STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 64 | No | DUKHCONI1BZ2STGL5255, DUKHCONI1BZ2ELGL5230, DUKHCONI1BZ1STGL5260 | DUKHCONI1BZ2PSGL7015, DUKHCONI1BZ3STGL5260 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ2STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 0 | Yes | DUKHCONI1BZ2ELGL5215, DUKHCONI1BZ1STGL5250 | DUKHCONI1BZ2STGL5240, DUKHCONI1BZ2STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ2STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 84 | No | DUKHCONI1BZ2STGL5250, DUKHCONI1BZ1STGL5255 | DUKHCONI1BZ2STGL5260, DUKHCONI1BZ3STGL5255 | 0 | 0 | STREET LIGHTING
DHBL.K30.L30.15 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-06-01 | 2014-08-09 | 2014-06-01 | 2014-08-09 | 17 |  |  |  | 0 | 0
DUKHCONI1BZ2IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-06-18 | 2014-07-16 | 2014-06-18 | 2014-07-16 | 7 | No | DUKHCONI1BZ2IRGL5275 | DUKHCONI1BZ2IRGL5290, DUKHCONI1BZ3IRGL5265, DUKHCONI1BZ2IRGL5285 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-06-30 | 2014-07-28 | 2014-06-30 | 2014-07-28 | 17 | No | DUKHCONI1BZ2ELGL5225, DUKHCONI1BZ2IRGL5280 | DUKHCONI1BZ2IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ2IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 7 | No | DUKHCONI1BZ2ELGL5225, DUKHCONI1BZ1IRGL5280 | DUKHCONI1BZ2IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-07-08 | 2014-08-09 | 2014-07-08 | 2014-08-09 | 17 | No | DUKHCONI1BZ2IRGL5285, DUKHCONI1BZ2IRGL5280 | DUKHCONI1BZ2SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ2IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-06-07 | 2014-07-05 | 2014-06-07 | 2014-07-05 | 7 | No | DUKHCONI1BZ2IRGL5265 | DUKHCONI1BZ2IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ2IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 7 | No | DUKHCONI1BZ2IRGL5270 | DUKHCONI1BZ2IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L30.15 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-05-12 | 2014-06-26 | 2014-05-12 | 2014-06-26 | 71 |  |  |  | 0 | 0
DUKHCONI1BZ2TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-05-24 | 2014-06-15 | 2014-05-24 | 2014-06-15 | 0 | Yes | DUKHCONI1BZ2TCGL5300 | DUKHCONI1BZ3TCGL5295, DUKHCONI1BZ2RWGL6000, DUKHCONI1BZ2TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ2TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-06-04 | 2014-06-26 | 2014-06-04 | 2014-06-26 | 71 | No | DUKHCONI1BZ1TCGL5310, DUKHCONI1BZ2TCGL5305 | DUKHCONI1BZ3TCGL5310, DUKHCONI1BSBTRGL7630 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ2TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-05-12 | 2014-06-03 | 2014-05-12 | 2014-06-03 | 0 | Yes | DUKHCONI1BZ2STGL5250, DUKHCONI1BZ1TCGL5305 | DUKHCONI1BZ2TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ2TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-05-18 | 2014-06-09 | 2014-05-18 | 2014-06-09 | 0 | Yes | DUKHCONI1BZ2TCGL5295 | DUKHCONI1BZ2TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L30.15 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-05-12 | 2014-08-09 | 2014-05-12 | 2014-08-09 | 73 |  |  |  | 0 | 0
DUKHCONI1BZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-07-08 | 2014-08-09 | 2014-07-08 | 2014-08-09 | 73 | No | DUKHCONI1BZ2BWGL5325, DUKHCONI1BZ1BWGL5330 | DUKHCONI1BZ3BWGL5330, DUKHCONI1BZ2PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-06-26 | 2014-07-24 | 2014-06-26 | 2014-07-24 | 35 | No | DUKHCONI1BZ2BWGL5320, DUKHCONI1BZ2BWGL5315, DUKHCONI1BZ1BWGL5325 | DUKHCONI1BZ2BWGL5330, DUKHCONP1BZ4MSEX5335, DUKHCONP1BZ3MSEX5335, DUKHCONI1BZ3BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 35 | No | DUKHCONI1BZ2STGL5250, DUKHCONI1BZ1BWGL5315 | DUKHCONI1BZ3BWGL5315, DUKHCONI1BZ2BWGL5325, DUKHCONI1BZ2BWGL5320 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 35 | No | DUKHCONI1BZ2BWGL5315 | DUKHCONI1BZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L30.15 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-06-16 | 2014-09-02 | 2014-06-16 | 2014-09-02 | 52 |  |  |  | 0 | 0
DUKHCONI1BZ2RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-06-16 | 2014-06-26 | 2014-06-16 | 2014-06-26 | 0 | Yes | DUKHCONI1BZ2SAGL5150, DUKHCONI1BZ2FFGL5210, DUKHCONI1BZ2TCGL5305, DUKHCONI1BZ2FFGL5200, DUKHCONI1BZ1RWGL6015, DUKHCONI1BZ2STGL5250, DUKHCONI1BZ2ELGL5225 | DUKHCONI1BZ2HDGL7020, DUKHCONI1BZ2RWGL6005 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-08-23 | 2014-08-27 | 2014-08-23 | 2014-08-27 | 52 | No | DUKHCONI1BZ1RWGL6025, DUKHCONI1BZ2RWGL6020 | DUKHCONI1BZ2HDGL7040, DUKHCONI1BZ3RWGL6025, DUKHCONI1BZ2RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ2RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-07-21 | 2014-08-16 | 2014-07-21 | 2014-08-16 | 0 | Yes | DUKHCONI1BZ2RWGL6010 | DUKHCONI1BZ2PSGL7005, DUKHCONI1BZ3RWGL6000, DUKHCONI1BZ2PSGL7000, DUKHCONI1BZ2RWGL6020 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ2RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-07-09 | 2014-08-10 | 2014-07-09 | 2014-08-10 | 0 | Yes | DUKHCONI1BZ2RWGL6005 | DUKHCONI1BZ2RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-08-17 | 2014-08-21 | 2014-08-17 | 2014-08-21 | 37 | No | DUKHCONI1BZ2RWGL6015 | DUKHCONI1BZ2PSGL7010, DUKHCONI1BZ2RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ2RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 0 | Yes | DUKHCONI1BZ2RWGL6000 | DUKHCONI1BZ2RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ2RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-08-28 | 2014-09-02 | 2014-08-28 | 2014-09-02 | 52 | No | DUKHCONI1BZ1RWGL6030, DUKHCONI1BZ2RWGL6025 | DUKHCONI1BZ2PSGL7010, DUKHCONI1BZ3RWGL6030 | 0 | 0 | ROAD WORKS
DHBL.K30.L30.15 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-07-27 | 2014-09-25 | 2014-07-27 | 2014-09-25 | 37 |  |  |  | 0 | 0
DUKHCONI1BZ2PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-08-23 | 2014-09-20 | 2014-08-23 | 2014-09-20 | 37 | No | DUKHCONI1BZ2RWGL6030, DUKHCONI1BZ2BWGL5330, DUKHCONI1BZ2RWGL6020, DUKHCONI1BZ1PSGL7010, DUKHCONI1BZ2PSGL7005 | DUKHCONI1BZ2PSGL7015, DUKHCONI1BZ3PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI1BZ2PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 37 | No | DUKHCONI1BZ2STGL5260, DUKHCONI1BZ1PSGL7015, DUKHCONI1BZ2PSGL7010 | DUKHCONI1BZ3PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1BZ2PSGL7000 | Excavation | 15 | 15 | 0% | 2014-07-27 | 2014-08-16 | 2014-07-27 | 2014-08-16 | 42 | No | DUKHCONI1BZ2RWGL6015, DUKHCONI1BZ1PSGL7005 | DUKHCONI1BZ2PSGL7005, DUKHCONI1BZ2PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1BZ2PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-08-11 | 2014-08-27 | 2014-08-11 | 2014-08-27 | 37 | No | DUKHCONI1BZ2RWGL6015, DUKHCONI1BZ2PSGL7000, DUKHCONI1BZ2PSGL7000 | DUKHCONI1BZ3PSGL7000, DUKHCONI1BZ2PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L30.15 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-06-16 | 2014-09-08 | 2014-06-16 | 2014-09-08 | 61 |  |  |  | 0 | 0
DUKHCONI1BZ2HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-07-09 | 2014-08-10 | 2014-07-09 | 2014-08-10 | 6 | No | DUKHCONI1BZ1HDGL7030, DUKHCONI1BZ2HDGL7025 | DUKHCONI1BZ3HDGL7030, DUKHCONI1BZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ2HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-08-28 | 2014-09-08 | 2014-08-28 | 2014-09-08 | 61 | No | DUKHCONI1BZ2RWGL6025, DUKHCONI1BZ2HDGL7035, DUKHCONI1BZ1HDGL7040 | DUKHCONI1BZ3HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ2HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-07-09 | 2014-08-10 | 2014-07-09 | 2014-08-10 | 6 | No | DUKHCONI1BZ1HDGL7035, DUKHCONI1BZ2HDGL7030 | DUKHCONI1BZ3HDGL7035, DUKHCONI1BZ2HDGL7040, DUKHCONI1BZ2SLGL7200 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ2HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 6 | No | DUKHCONI1BZ2HDGL7020 | DUKHCONI1BZ2HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ2HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-06-16 | 2014-07-08 | 2014-06-16 | 2014-07-08 | 6 | No | DUKHCONI1BZ2RWGL6000 | DUKHCONI1BZ2HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L30.15 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-07-21 | 2014-09-14 | 2014-07-21 | 2014-09-14 | 26 |  |  |  | 0 | 0
DUKHCONI1BZ2SLGL7200 | Excavation | 25 | 25 | 0% | 2014-07-21 | 2014-08-21 | 2014-07-21 | 2014-08-21 | 6 | No | DUKHCONI1BZ2IRGL5290, DUKHCONI1BZ1SLGL7205, DUKHCONI1BZ2HDGL7035 | DUKHCONI1BZ2SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ2SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 26 | No | DUKHCONI1BZ2SLGL7205, DUKHCONI1BZ1SLGL7210 | DUKHCONI1BZ3SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ2SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-08-05 | 2014-09-02 | 2014-08-05 | 2014-09-02 | 6 | No | DUKHCONI1BZ2SLGL7200 | DUKHCONI1BZ2SLGL7210, DUKHCONI1BZ3SLGL7200 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L30.20 ZONE - 3 |  | 227 | 227 | 0% | 2014-02-17 | 2014-11-13 | 2014-02-17 | 2014-11-13 | 22 |  |  |  | 0 | 0
DHBL.K30.L30.20 .10 INFRASTRUCTURE WORKS |  | 227 | 227 | 0% | 2014-02-17 | 2014-11-13 | 2014-02-17 | 2014-11-13 | 22 |  |  |  | 0 | 0
DHBL.K30.L30.20 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2014-02-17 | 2014-04-07 | 2014-02-17 | 2014-04-07 | 10 |  |  |  | 0 | 0
DUKHCONI1BZ3DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2014-03-22 | 2014-04-07 | 2014-03-22 | 2014-04-07 | 10 | No | DUKHCONI1BZ3DRGL5125, DUKHCONI1BZ3DRGL5125 | DUKHCONI1BZ4DRGL5115, DUKHCONI1BZ3SAGL5135, DUKHCONI1BZ3SAGL5140, DUKHCONI1BZ3WSGL5155 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ3DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 10 | No | DUKHCONI1BZ2DRGL5130 | DUKHCONI1BZ3SAGL5140, DUKHCONI1BZ3DRGL5120, DUKHCONI1BZ3SAGL5135, DUKHCONI1BZ3DRGL5120 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ3DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 10 | No | DUKHCONI1BZ3DRGL5115, DUKHCONI1BZ3DRGL5115 | DUKHCONI1BZ3DRGL5125, DUKHCONI1BZ3DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ3DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 10 | No | DUKHCONI1BZ3DRGL5120, DUKHCONI1BZ3DRGL5120 | DUKHCONI1BZ3DRGL5130, DUKHCONI1BZ3DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L30.20 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2014-03-22 | 2014-06-10 | 2014-03-22 | 2014-06-10 | 44 |  |  |  | 0 | 0
DUKHCONI1BZ3SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-05-19 | 2014-06-10 | 2014-05-19 | 2014-06-10 | 44 | No | DUKHCONI1BZ3SAGL5145, DUKHCONI1BZ3SAGL5135 | DUKHCONI1BZ3RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ3SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 69 | No | DUKHCONI1BZ3DRGL5130, DUKHCONI1BZ3DRGL5115, DUKHCONI1BZ2SAGL5135 | DUKHCONI1BZ4SAGL5135, DUKHCONI1BZ3SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ3SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 10 | No | DUKHCONI1BZ2SAGL5145, DUKHCONI1BZ3SAGL5140 | DUKHCONI1BZ4SAGL5145, DUKHCONI1BZ3SAGL5150, DUKHCONI1BZ3WSGL5170 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ3SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 10 | No | DUKHCONI1BZ3DRGL5115, DUKHCONI1BZ3DRGL5130 | DUKHCONI1BZ3SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L30.20 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-04-14 | 2014-06-28 | 2014-04-14 | 2014-06-28 | 29 |  |  |  | 0 | 0
DUKHCONI1BZ3WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-05-01 | 2014-05-29 | 2014-05-01 | 2014-05-29 | 0 | Yes | DUKHCONI1BZ3WSGL5165, DUKHCONI1BZ3SAGL5145 | DUKHCONI1BZ3WSGL5175, DUKHCONI1BZ4WSGL5155, DUKHCONI1BZ3FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ3WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-05-07 | 2014-06-04 | 2014-05-07 | 2014-06-04 | 29 | No | DUKHCONI1BZ2WSGL5175, DUKHCONI1BZ3WSGL5155, DUKHCONI1BZ3WSGL5170 | DUKHCONI1BZ3WSGL5180, DUKHCONI1BZ4WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ3WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-04-14 | 2014-05-12 | 2014-04-14 | 2014-05-12 | 0 | Yes | DUKHCONI1BZ2WSGL5170, DUKHCONI1BZ3DRGL5130 | DUKHCONI1BZ3WSGL5160, DUKHCONI1BZ3WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ3WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-06-05 | 2014-06-28 | 2014-06-05 | 2014-06-28 | 29 | No | DUKHCONI1BZ3WSGL5175, DUKHCONI1BZ2WSGL5180 | DUKHCONI1BZ4WSGL5180, DUKHCONI1BZ3FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ3WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 0 | Yes | DUKHCONI1BZ3WSGL5155 | DUKHCONI1BZ3WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ3WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-04-26 | 2014-05-24 | 2014-04-26 | 2014-05-24 | 0 | Yes | DUKHCONI1BZ3WSGL5160 | DUKHCONI1BZ3WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L30.20 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-05-07 | 2014-07-06 | 2014-05-07 | 2014-07-06 | 22 |  |  |  | 0 | 0
DUKHCONI1BZ3FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-05-27 | 2014-06-24 | 2014-05-27 | 2014-06-24 | 0 | Yes | DUKHCONI1BZ3FFGL5195 | DUKHCONI1BZ3FFGL5205, DUKHCONI1BZ4FFGL5185, DUKHCONI1BZ3RWGL6000, DUKHCONI1BZ3ELGL5215 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ3FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-06-08 | 2014-07-06 | 2014-06-08 | 2014-07-06 | 22 | No | DUKHCONI1BZ2FFGL5210, DUKHCONI1BZ3FFGL5205, DUKHCONI1BZ3WSGL5180 | DUKHCONI1BZ3RWGL6000, DUKHCONI1BSBIWGL7440, DUKHCONI1BZ4FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ3FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-06-02 | 2014-06-30 | 2014-06-02 | 2014-06-30 | 22 | No | DUKHCONI1BZ3FFGL5200, DUKHCONI1BZ3FFGL5185, DUKHCONI1BZ2FFGL5205 | DUKHCONI1BZ4FFGL5205, DUKHCONI1BZ3FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ3FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-05-07 | 2014-06-04 | 2014-05-07 | 2014-06-04 | 0 | Yes | DUKHCONI1BZ2FFGL5200, DUKHCONI1BZ3WSGL5170 | DUKHCONI1BZ3FFGL5205, DUKHCONI1BZ3FFGL5190 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ3FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-05-15 | 2014-06-12 | 2014-05-15 | 2014-06-12 | 0 | Yes | DUKHCONI1BZ3FFGL5185 | DUKHCONI1BZ3FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ3FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-05-21 | 2014-06-18 | 2014-05-21 | 2014-06-18 | 0 | Yes | DUKHCONI1BZ3FFGL5190 | DUKHCONI1BZ3FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L30.20 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-06-04 | 2014-07-28 | 2014-06-04 | 2014-07-28 | 49 |  |  |  | 0 | 0
DUKHCONI1BZ3ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-06-18 | 2014-07-16 | 2014-06-18 | 2014-07-16 | 3 | No | DUKHCONI1BZ3ELGL5220, DUKHCONI1BZ3ELGL5215 | DUKHCONI1BZ3RWGL6000, DUKHCONI1BZ3ELGL5230, DUKHCONI1BZ3ELGL5230, DUKHCONI1BZ3IRGL5265, DUKHCONI1BZ3IRGL5285, DUKHCONI1BZ4ELGL5215 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ3ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-06-30 | 2014-07-28 | 2014-06-30 | 2014-07-28 | 49 | No | DUKHCONI1BZ2ELGL5230, DUKHCONI1BZ3ELGL5225, DUKHCONI1BZ3ELGL5225 | DUKHCONI1BZ3STGL5260, DUKHCONI1BZ4ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ3ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-06-04 | 2014-07-02 | 2014-06-04 | 2014-07-02 | 0 | Yes | DUKHCONI1BZ2ELGL5225, DUKHCONI1BZ3FFGL5200 | DUKHCONI1BZ3ELGL5220, DUKHCONI1BZ3STGL5235, DUKHCONI1BZ3ELGL5225 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ3ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-06-10 | 2014-07-08 | 2014-06-10 | 2014-07-08 | 3 | No | DUKHCONI1BZ3ELGL5215 | DUKHCONI1BZ3ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L30.20 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-06-04 | 2014-08-30 | 2014-06-04 | 2014-08-30 | 49 |  |  |  | 0 | 0
DUKHCONI1BZ3STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-06-16 | 2014-07-14 | 2014-06-16 | 2014-07-14 | 0 | Yes | DUKHCONI1BZ3STGL5235, DUKHCONI1BZ3STGL5245 | DUKHCONI1BZ3STGL5255, DUKHCONI1BZ3TCGL5295, DUKHCONI1BZ4STGL5235, DUKHCONI1BZ3BWGL5315, DUKHCONI1BZ3RWGL6000 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ3STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-06-10 | 2014-07-08 | 2014-06-10 | 2014-07-08 | 0 | Yes | DUKHCONI1BZ3STGL5235 | DUKHCONI1BZ3STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ3STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-06-10 | 2014-07-08 | 2014-06-10 | 2014-07-08 | 0 | Yes | DUKHCONI1BZ3STGL5240 | DUKHCONI1BZ3STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ3STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-07-29 | 2014-08-30 | 2014-07-29 | 2014-08-30 | 49 | No | DUKHCONI1BZ3ELGL5230, DUKHCONI1BZ3STGL5255, DUKHCONI1BZ2STGL5260 | DUKHCONI1BZ3PSGL7015, DUKHCONI1BZ4STGL5260 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ3STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-06-04 | 2014-07-02 | 2014-06-04 | 2014-07-02 | 0 | Yes | DUKHCONI1BZ2STGL5250, DUKHCONI1BZ3ELGL5215 | DUKHCONI1BZ3STGL5250, DUKHCONI1BZ3STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ3STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 69 | No | DUKHCONI1BZ3STGL5250, DUKHCONI1BZ2STGL5255 | DUKHCONI1BZ3STGL5260, DUKHCONI1BZ4STGL5255 | 0 | 0 | STREET LIGHTING
DHBL.K30.L30.20 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-07-17 | 2014-09-24 | 2014-07-17 | 2014-09-24 | 12 |  |  |  | 0 | 0
DUKHCONI1BZ3IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-08-07 | 2014-09-04 | 2014-08-07 | 2014-09-04 | 7 | No | DUKHCONI1BZ3IRGL5275 | DUKHCONI1BZ4IRGL5265, DUKHCONI1BZ3IRGL5290, DUKHCONI1BZ3IRGL5285 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ3IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-08-19 | 2014-09-16 | 2014-08-19 | 2014-09-16 | 12 | No | DUKHCONI1BZ3ELGL5225, DUKHCONI1BZ3IRGL5280 | DUKHCONI1BZ3IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ3IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-07-17 | 2014-08-18 | 2014-07-17 | 2014-08-18 | 7 | No | DUKHCONI1BZ2IRGL5280, DUKHCONI1BZ3ELGL5225 | DUKHCONI1BZ3IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ3IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-08-27 | 2014-09-24 | 2014-08-27 | 2014-09-24 | 12 | No | DUKHCONI1BZ3IRGL5280, DUKHCONI1BZ3IRGL5285 | DUKHCONI1BZ3SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ3IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-07-23 | 2014-08-24 | 2014-07-23 | 2014-08-24 | 7 | No | DUKHCONI1BZ3IRGL5265 | DUKHCONI1BZ3IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ3IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-07-29 | 2014-08-30 | 2014-07-29 | 2014-08-30 | 7 | No | DUKHCONI1BZ3IRGL5270 | DUKHCONI1BZ3IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L30.20 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-06-28 | 2014-08-16 | 2014-06-28 | 2014-08-16 | 51 |  |  |  | 0 | 0
DUKHCONI1BZ3TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-07-09 | 2014-07-31 | 2014-07-09 | 2014-07-31 | 0 | Yes | DUKHCONI1BZ3TCGL5300 | DUKHCONI1BZ4TCGL5295, DUKHCONI1BZ3RWGL6000, DUKHCONI1BZ3TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ3TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-07-21 | 2014-08-16 | 2014-07-21 | 2014-08-16 | 51 | No | DUKHCONI1BZ2TCGL5310, DUKHCONI1BZ3TCGL5305 | DUKHCONI1BSBTRGL7630, DUKHCONI1BZ4TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ3TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-06-28 | 2014-07-20 | 2014-06-28 | 2014-07-20 | 0 | Yes | DUKHCONI1BZ3STGL5250, DUKHCONI1BZ2TCGL5305 | DUKHCONI1BZ3TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ3TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-07-03 | 2014-07-26 | 2014-07-03 | 2014-07-26 | 0 | Yes | DUKHCONI1BZ3TCGL5295 | DUKHCONI1BZ3TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L30.20 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-06-28 | 2014-09-24 | 2014-06-28 | 2014-09-24 | 58 |  |  |  | 0 | 0
DUKHCONI1BZ3BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-08-27 | 2014-09-24 | 2014-08-27 | 2014-09-24 | 58 | No | DUKHCONI1BZ2BWGL5330, DUKHCONI1BZ3BWGL5325 | DUKHCONI1BZ3PSGL7010, DUKHCONI1BZ4BWGL5330 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ3BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-08-16 | 2014-09-13 | 2014-08-16 | 2014-09-13 | 45 | No | DUKHCONI1BZ3BWGL5315, DUKHCONI1BZ3BWGL5320, DUKHCONI1BZ2BWGL5325 | DUKHCONI1BZ3BWGL5330, DUKHCONP1BZ5MSEX5335, DUKHCONI1BZ4BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ3BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-06-28 | 2014-07-26 | 2014-06-28 | 2014-07-26 | 45 | No | DUKHCONI1BZ2BWGL5315, DUKHCONI1BZ3STGL5250 | DUKHCONI1BZ3BWGL5320, DUKHCONI1BZ3BWGL5325, DUKHCONI1BZ4BWGL5315 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ3BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-07-14 | 2014-08-14 | 2014-07-14 | 2014-08-14 | 45 | No | DUKHCONI1BZ3BWGL5315 | DUKHCONI1BZ3BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L30.20 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-08-05 | 2014-10-21 | 2014-08-05 | 2014-10-21 | 37 |  |  |  | 0 | 0
DUKHCONI1BZ3RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-08-05 | 2014-08-16 | 2014-08-05 | 2014-08-16 | 0 | Yes | DUKHCONI1BZ3FFGL5210, DUKHCONI1BZ3ELGL5225, DUKHCONI1BZ2RWGL6015, DUKHCONI1BZ3FFGL5200, DUKHCONI1BZ3SAGL5150, DUKHCONI1BZ1FFGL5210, DUKHCONI1BZ3TCGL5305, DUKHCONI1BZ3STGL5250 | DUKHCONI1BZ3RWGL6005, DUKHCONI1BZ3HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ3RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-10-08 | 2014-10-15 | 2014-10-08 | 2014-10-15 | 31 | No | DUKHCONI1BZ3RWGL6020, DUKHCONI1BZ2RWGL6025 | DUKHCONI1BZ3HDGL7040, DUKHCONI1BZ4RWGL6025, DUKHCONI1BZ3RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ3RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-09-09 | 2014-10-01 | 2014-09-09 | 2014-10-01 | 0 | Yes | DUKHCONI1BZ3RWGL6010 | DUKHCONI1BZ3RWGL6020, DUKHCONI1BZ4RWGL6000, DUKHCONI1BZ3PSGL7000, DUKHCONI1BZ3PSGL7005 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ3RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 0 | Yes | DUKHCONI1BZ3RWGL6005 | DUKHCONI1BZ3RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ3RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-10-02 | 2014-10-07 | 2014-10-02 | 2014-10-07 | 22 | No | DUKHCONI1BZ3RWGL6015 | DUKHCONI1BZ3PSGL7010, DUKHCONI1BZ3RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ3RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 0 | Yes | DUKHCONI1BZ3RWGL6000 | DUKHCONI1BZ3RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ3RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-10-16 | 2014-10-21 | 2014-10-16 | 2014-10-21 | 37 | No | DUKHCONI1BZ2RWGL6030, DUKHCONI1BZ3RWGL6025 | DUKHCONI1BZ4RWGL6030, DUKHCONI1BZ3PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L30.20 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-09-15 | 2014-11-13 | 2014-09-15 | 2014-11-13 | 22 |  |  |  | 0 | 0
DUKHCONI1BZ3PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-10-08 | 2014-11-08 | 2014-10-08 | 2014-11-08 | 22 | No | DUKHCONI1BZ3RWGL6020, DUKHCONI1BZ3BWGL5330, DUKHCONI1BZ3PSGL7005, DUKHCONI1BZ3RWGL6030, DUKHCONI1BZ2PSGL7010 | DUKHCONI1BZ4PSGL7010, DUKHCONI1BZ3PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1BZ3PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-10-16 | 2014-11-13 | 2014-10-16 | 2014-11-13 | 22 | No | DUKHCONI1BZ2PSGL7015, DUKHCONI1BZ3STGL5260, DUKHCONI1BZ3PSGL7010 | DUKHCONI1BZ4PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1BZ3PSGL7000 | Excavation | 15 | 15 | 0% | 2014-09-15 | 2014-10-01 | 2014-09-15 | 2014-10-01 | 27 | No | DUKHCONI1BZ2PSGL7005, DUKHCONI1BZ3RWGL6015 | DUKHCONI1BZ3PSGL7005, DUKHCONI1BZ3PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1BZ3PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-09-27 | 2014-10-15 | 2014-09-27 | 2014-10-15 | 22 | No | DUKHCONI1BZ3PSGL7000, DUKHCONI1BZ3PSGL7000, DUKHCONI1BZ3RWGL6015 | DUKHCONI1BZ4PSGL7000, DUKHCONI1BZ3PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L30.20 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-08-05 | 2014-10-27 | 2014-08-05 | 2014-10-27 | 31 |  |  |  | 0 | 0
DUKHCONI1BZ3HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 1 | No | DUKHCONI1BZ2HDGL7030, DUKHCONI1BZ3HDGL7025 | DUKHCONI1BZ4HDGL7030, DUKHCONI1BZ3HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ3HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-10-16 | 2014-10-27 | 2014-10-16 | 2014-10-27 | 31 | No | DUKHCONI1BZ3HDGL7035, DUKHCONI1BZ3RWGL6025, DUKHCONI1BZ2HDGL7040 | DUKHCONI1BZ4HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ3HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-08-28 | 2014-09-25 | 2014-08-28 | 2014-09-25 | 1 | No | DUKHCONI1BZ2HDGL7035, DUKHCONI1BZ3HDGL7030 | DUKHCONI1BZ3HDGL7040, DUKHCONI1BZ4HDGL7035, DUKHCONI1BZ3SLGL7200 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ3HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 1 | No | DUKHCONI1BZ3HDGL7020 | DUKHCONI1BZ3HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ3HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-08-05 | 2014-08-27 | 2014-08-05 | 2014-08-27 | 1 | No | DUKHCONI1BZ3RWGL6000 | DUKHCONI1BZ3HDGL7025, DUKHCONI1BSBGZGL7900 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L30.20 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-09-09 | 2014-11-02 | 2014-09-09 | 2014-11-02 | 11 |  |  |  | 0 | 0
DUKHCONI1BZ3SLGL7200 | Excavation | 25 | 25 | 0% | 2014-09-09 | 2014-10-07 | 2014-09-09 | 2014-10-07 | 1 | No | DUKHCONI1BZ3IRGL5290, DUKHCONI1BZ2SLGL7205, DUKHCONI1BZ3HDGL7035 | DUKHCONI1BZ3SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ3SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-10-02 | 2014-11-02 | 2014-10-02 | 2014-11-02 | 11 | No | DUKHCONI1BZ2SLGL7210, DUKHCONI1BZ3SLGL7205 | DUKHCONI1BZ4SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ3SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-09-21 | 2014-10-21 | 2014-09-21 | 2014-10-21 | 1 | No | DUKHCONI1BZ3SLGL7200 | DUKHCONI1BZ3SLGL7210, DUKHCONI1BZ4SLGL7200 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L30.25 ZONE - 4 |  | 233 | 233 | 0% | 2014-03-30 | 2015-01-01 | 2014-03-30 | 2015-01-01 | 6 |  |  |  | 0 | 0
DHBL.K30.L30.25 .10 INFRASTRUCTURE WORKS |  | 233 | 233 | 0% | 2014-03-30 | 2015-01-01 | 2014-03-30 | 2015-01-01 | 6 |  |  |  | 0 | 0
DHBL.K30.L30.25 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2014-03-30 | 2014-05-18 | 2014-03-30 | 2014-05-18 | 15 |  |  |  | 0 | 0
DUKHCONI1BZ4DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2014-05-01 | 2014-05-18 | 2014-05-01 | 2014-05-18 | 15 | No | DUKHCONI1BZ4DRGL5125, DUKHCONI1BZ4DRGL5125 | DUKHCONI1BZ4SAGL5135, DUKHCONI1BZ4SAGL5140, DUKHCONI1BZ4WSGL5155 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ4DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2014-03-30 | 2014-04-27 | 2014-03-30 | 2014-04-27 | 15 | No | DUKHCONI1BZ3DRGL5130 | DUKHCONI1BZ4SAGL5140, DUKHCONI1BZ4DRGL5120, DUKHCONI1BZ4SAGL5135, DUKHCONI1BZ4DRGL5120 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ4DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2014-04-06 | 2014-05-04 | 2014-04-06 | 2014-05-04 | 15 | No | DUKHCONI1BZ4DRGL5115, DUKHCONI1BZ4DRGL5115 | DUKHCONI1BZ4DRGL5125, DUKHCONI1BZ4DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI1BZ4DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2014-04-14 | 2014-05-12 | 2014-04-14 | 2014-05-12 | 15 | No | DUKHCONI1BZ4DRGL5120, DUKHCONI1BZ4DRGL5120 | DUKHCONI1BZ4DRGL5130, DUKHCONI1BZ4DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L30.25 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2014-05-01 | 2014-07-21 | 2014-05-01 | 2014-07-21 | 49 |  |  |  | 0 | 0
DUKHCONI1BZ4SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-06-29 | 2014-07-21 | 2014-06-29 | 2014-07-21 | 49 | No | DUKHCONI1BZ4SAGL5145, DUKHCONI1BZ4SAGL5135 | DUKHCONI1BZ4RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ4SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2014-05-01 | 2014-05-29 | 2014-05-01 | 2014-05-29 | 74 | No | DUKHCONI1BZ3SAGL5135, DUKHCONI1BZ4DRGL5130, DUKHCONI1BZ4DRGL5115 | DUKHCONI1BZ4SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ4SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-05-31 | 2014-06-28 | 2014-05-31 | 2014-06-28 | 15 | No | DUKHCONI1BZ3SAGL5145, DUKHCONI1BZ4SAGL5140 | DUKHCONI1BZ4SAGL5150, DUKHCONI1BZ4WSGL5170 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI1BZ4SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2014-05-01 | 2014-05-29 | 2014-05-01 | 2014-05-29 | 15 | No | DUKHCONI1BZ4DRGL5115, DUKHCONI1BZ4DRGL5130 | DUKHCONI1BZ4SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L30.25 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-05-31 | 2014-08-17 | 2014-05-31 | 2014-08-17 | 29 |  |  |  | 0 | 0
DUKHCONI1BZ4WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-06-17 | 2014-07-15 | 2014-06-17 | 2014-07-15 | 0 | Yes | DUKHCONI1BZ4SAGL5145, DUKHCONI1BZ4WSGL5165 | DUKHCONI1BZ4FFGL5185, DUKHCONI1BZ4WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ4WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 29 | No | DUKHCONI1BZ4WSGL5155, DUKHCONI1BZ4WSGL5170, DUKHCONI1BZ3WSGL5175 | DUKHCONI1BZ4WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ4WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-05-31 | 2014-06-28 | 2014-05-31 | 2014-06-28 | 0 | Yes | DUKHCONI1BZ3WSGL5170, DUKHCONI1BZ4DRGL5130 | DUKHCONI1BZ4WSGL5175, DUKHCONI1BZ4WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ4WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-07-22 | 2014-08-17 | 2014-07-22 | 2014-08-17 | 29 | No | DUKHCONI1BZ4WSGL5175, DUKHCONI1BZ3WSGL5180 | DUKHHANP1BGNELTC9010, DUKHCONI1BZ4FFGL5210, DUKHHANP1BGNPLTC9005 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ4WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-06-05 | 2014-07-03 | 2014-06-05 | 2014-07-03 | 0 | Yes | DUKHCONI1BZ4WSGL5155 | DUKHCONI1BZ4WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI1BZ4WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-06-11 | 2014-07-09 | 2014-06-11 | 2014-07-09 | 0 | Yes | DUKHCONI1BZ4WSGL5160 | DUKHCONI1BZ4WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L30.25 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-06-23 | 2014-08-25 | 2014-06-23 | 2014-08-25 | 22 |  |  |  | 0 | 0
DUKHCONI1BZ4FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-07-13 | 2014-08-13 | 2014-07-13 | 2014-08-13 | 0 | Yes | DUKHCONI1BZ4FFGL5195 | DUKHCONI1BZ4RWGL6000, DUKHCONI1BZ4ELGL5215, DUKHCONI1BZ4FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ4FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-07-24 | 2014-08-25 | 2014-07-24 | 2014-08-25 | 22 | No | DUKHCONI1BZ4FFGL5205, DUKHCONI1BZ4WSGL5180, DUKHCONI1BZ3FFGL5210 | DUKHHANP1BGNELTC9010, DUKHCONI1BZ4RWGL6000, DUKHCONI1BSBIWGL7440, DUKHHANP1BGNPLTC9005 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ4FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-07-19 | 2014-08-19 | 2014-07-19 | 2014-08-19 | 22 | No | DUKHCONI1BZ3FFGL5205, DUKHCONI1BZ4FFGL5200, DUKHCONI1BZ4FFGL5185 | DUKHCONI1BZ4FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ4FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 0 | Yes | DUKHCONI1BZ4WSGL5170, DUKHCONI1BZ3FFGL5200 | DUKHCONI1BZ4FFGL5190, DUKHCONI1BZ4FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ4FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-07-01 | 2014-07-29 | 2014-07-01 | 2014-07-29 | 0 | Yes | DUKHCONI1BZ4FFGL5185 | DUKHCONI1BZ4FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI1BZ4FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-07-07 | 2014-08-07 | 2014-07-07 | 2014-08-07 | 0 | Yes | DUKHCONI1BZ4FFGL5190 | DUKHCONI1BZ4FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L30.25 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-07-21 | 2014-09-16 | 2014-07-21 | 2014-09-16 | 34 |  |  |  | 0 | 0
DUKHCONI1BZ4ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-08-07 | 2014-09-04 | 2014-08-07 | 2014-09-04 | 7 | No | DUKHCONI1BZ4ELGL5220, DUKHCONI1BZ4ELGL5215 | DUKHCONI1BZ4ELGL5230, DUKHCONI1BZ4ELGL5230, DUKHCONI1BZ4IRGL5265, DUKHCONI1BZ4RWGL6000, DUKHCONI1BZ4IRGL5285 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ4ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-08-19 | 2014-09-16 | 2014-08-19 | 2014-09-16 | 34 | No | DUKHCONI1BZ4ELGL5225, DUKHCONI1BZ4ELGL5225, DUKHCONI1BZ3ELGL5230 | DUKHCONI1BZ4STGL5260, DUKHCONI1BSBIWGL7450 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ4ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-07-21 | 2014-08-21 | 2014-07-21 | 2014-08-21 | 0 | Yes | DUKHCONI1BZ4FFGL5200, DUKHCONI1BZ3ELGL5225 | DUKHCONI1BZ4STGL5235, DUKHCONI1BZ4ELGL5225, DUKHCONI1BZ4ELGL5220 | 0 | 0 | ELECTRICAL LINES
DUKHCONI1BZ4ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-07-27 | 2014-08-27 | 2014-07-27 | 2014-08-27 | 7 | No | DUKHCONI1BZ4ELGL5215 | DUKHCONI1BZ4ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L30.25 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-07-21 | 2014-10-18 | 2014-07-21 | 2014-10-18 | 34 |  |  |  | 0 | 0
DUKHCONI1BZ4STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-08-05 | 2014-09-02 | 2014-08-05 | 2014-09-02 | 0 | Yes | DUKHCONI1BZ4STGL5235, DUKHCONI1BZ4STGL5245 | DUKHCONI1BZ4STGL5255, DUKHCONI1BZ4BWGL5315, DUKHCONI1BZ4TCGL5295, DUKHCONI1BZ4RWGL6000 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ4STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-07-27 | 2014-08-27 | 2014-07-27 | 2014-08-27 | 0 | Yes | DUKHCONI1BZ4STGL5235 | DUKHCONI1BZ4STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ4STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-07-27 | 2014-08-27 | 2014-07-27 | 2014-08-27 | 0 | Yes | DUKHCONI1BZ4STGL5240 | DUKHCONI1BZ4STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ4STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-09-17 | 2014-10-18 | 2014-09-17 | 2014-10-18 | 34 | No | DUKHCONI1BZ4ELGL5230, DUKHCONI1BZ3STGL5260, DUKHCONI1BZ4STGL5255 | DUKHCONI1BSBIWGL7450, DUKHHANP1BGNPLTC9005, DUKHCONI1BZ4PSGL7015, DUKHHANP1BGNELTC9010 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ4STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-07-21 | 2014-08-21 | 2014-07-21 | 2014-08-21 | 0 | Yes | DUKHCONI1BZ4ELGL5215, DUKHCONI1BZ3STGL5250 | DUKHCONI1BZ4STGL5240, DUKHCONI1BZ4STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI1BZ4STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 54 | No | DUKHCONI1BZ4STGL5250, DUKHCONI1BZ3STGL5255 | DUKHCONI1BZ4STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L30.25 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-09-06 | 2014-11-12 | 2014-09-06 | 2014-11-12 | 7 |  |  |  | 0 | 0
DUKHCONI1BZ4IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-09-23 | 2014-10-23 | 2014-09-23 | 2014-10-23 | 7 | No | DUKHCONI1BZ4IRGL5275 | DUKHCONI1BSBTRGL7620, DUKHCONI1BZ4IRGL5290, DUKHCONI1BZ4IRGL5285 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ4IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-10-05 | 2014-11-04 | 2014-10-05 | 2014-11-04 | 7 | No | DUKHCONI1BZ4IRGL5280, DUKHCONI1BZ4ELGL5225 | DUKHCONI1BZ4IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ4IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-09-06 | 2014-10-04 | 2014-09-06 | 2014-10-04 | 7 | No | DUKHCONI1BZ3IRGL5280, DUKHCONI1BZ4ELGL5225 | DUKHCONI1BZ4IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ4IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-10-15 | 2014-11-12 | 2014-10-15 | 2014-11-12 | 7 | No | DUKHCONI1BZ4IRGL5285, DUKHCONI1BZ4IRGL5280 | DUKHCONI1BZ4SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ4IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-09-11 | 2014-10-12 | 2014-09-11 | 2014-10-12 | 7 | No | DUKHCONI1BZ4IRGL5265 | DUKHCONI1BZ4IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI1BZ4IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-09-17 | 2014-10-18 | 2014-09-17 | 2014-10-18 | 7 | No | DUKHCONI1BZ4IRGL5270 | DUKHCONI1BZ4IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L30.25 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-08-17 | 2014-10-01 | 2014-08-17 | 2014-10-01 | 31 |  |  |  | 0 | 0
DUKHCONI1BZ4TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-08-28 | 2014-09-20 | 2014-08-28 | 2014-09-20 | 0 | Yes | DUKHCONI1BZ4TCGL5300 | DUKHCONI1BZ4TCGL5310, DUKHCONI1BZ4RWGL6000 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ4TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-09-09 | 2014-10-01 | 2014-09-09 | 2014-10-01 | 31 | No | DUKHCONI1BZ4TCGL5305, DUKHCONI1BZ3TCGL5310 | DUKHCONI1BSBTRGL7630, DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ4TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-08-17 | 2014-09-08 | 2014-08-17 | 2014-09-08 | 0 | Yes | DUKHCONI1BZ3TCGL5305, DUKHCONI1BZ4STGL5250 | DUKHCONI1BZ4TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI1BZ4TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-08-23 | 2014-09-14 | 2014-08-23 | 2014-09-14 | 0 | Yes | DUKHCONI1BZ4TCGL5295 | DUKHCONI1BZ4TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L30.25 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-08-17 | 2014-11-12 | 2014-08-17 | 2014-11-12 | 43 |  |  |  | 0 | 0
DUKHCONI1BZ4BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-10-15 | 2014-11-12 | 2014-10-15 | 2014-11-12 | 43 | No | DUKHCONI1BZ3BWGL5330, DUKHCONI1BZ4BWGL5325 | DUKHCONI1BZ4PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ4BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-10-01 | 2014-11-01 | 2014-10-01 | 2014-11-01 | 30 | No | DUKHCONI1BZ4BWGL5315, DUKHCONI1BZ3BWGL5325, DUKHCONI1BZ4BWGL5320 | DUKHCONI1BZ4BWGL5330, DUKHCONP1BZ6MSEX5335 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ4BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-08-17 | 2014-09-14 | 2014-08-17 | 2014-09-14 | 30 | No | DUKHCONI1BZ4STGL5250, DUKHCONI1BZ3BWGL5315 | DUKHCONI1BZ4BWGL5325, DUKHCONI1BZ4BWGL5320 | 0 | 0 | BOUNDARY WALL
DUKHCONI1BZ4BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-09-02 | 2014-09-30 | 2014-09-02 | 2014-09-30 | 30 | No | DUKHCONI1BZ4BWGL5315 | DUKHCONI1BZ4BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L30.25 .10 .55 ROAD WORKS |  | 66 | 66 | 0% | 2014-09-21 | 2014-12-08 | 2014-09-21 | 2014-12-08 | 21 |  |  |  | 0 | 0
DUKHCONI1BZ4RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-09-21 | 2014-10-01 | 2014-09-21 | 2014-10-01 | 0 | Yes | DUKHCONI1BZ4SAGL5150, DUKHCONI1BZ4FFGL5200, DUKHCONI1BZ3RWGL6015, DUKHCONI1BZ4FFGL5210, DUKHCONI1BZ4TCGL5305, DUKHCONI1BZ4ELGL5225, DUKHCONI1BZ4STGL5250 | DUKHCONI1BZ4RWGL6005, DUKHCONI1BZ4HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ4RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-11-27 | 2014-12-02 | 2014-11-27 | 2014-12-02 | 0 | Yes | DUKHCONI1BZ3RWGL6025, DUKHCONI1BZ4RWGL6020 | DUKHCONI1BZ4HDGL7040, DUKHCONI1BZ4RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ4RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-10-28 | 2014-11-19 | 2014-10-28 | 2014-11-19 | 0 | Yes | DUKHCONI1BZ4RWGL6010 | DUKHCONI1BZ4PSGL7000, DUKHCONI1BZ4RWGL6020, DUKHCONI1BZ4PSGL7005 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ4RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-10-16 | 2014-11-13 | 2014-10-16 | 2014-11-13 | 0 | Yes | DUKHCONI1BZ4RWGL6005 | DUKHCONI1BZ4RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ4RWGL6020 | Laying of Road Base Asphalt Concrete | 6 | 6 | 0% | 2014-11-20 | 2014-11-26 | 2014-11-20 | 2014-11-26 | 0 | Yes | DUKHCONI1BZ4RWGL6015 | DUKHCONI1BZ4PSGL7010, DUKHCONI1BZ4RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ4RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-10-02 | 2014-11-02 | 2014-10-02 | 2014-11-02 | 0 | Yes | DUKHCONI1BZ4RWGL6000 | DUKHCONI1BZ4RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI1BZ4RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-12-03 | 2014-12-08 | 2014-12-03 | 2014-12-08 | 21 | No | DUKHCONI1BZ3RWGL6030, DUKHCONI1BZ4RWGL6025 | DUKHCONI1BZ4PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L30.25 .10 .60 PARKING SHED |  | 51 | 51 | 0% | 2014-11-03 | 2015-01-01 | 2014-11-03 | 2015-01-01 | 6 |  |  |  | 0 | 0
DUKHCONI1BZ4PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-11-27 | 2014-12-27 | 2014-11-27 | 2014-12-27 | 6 | No | DUKHCONI1BZ3PSGL7010, DUKHCONI1BZ4RWGL6030, DUKHCONI1BZ4RWGL6020, DUKHCONI1BZ4PSGL7005, DUKHCONI1BZ4BWGL5330 | DUKHCONI1BZ4PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI1BZ4PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-12-03 | 2015-01-01 | 2014-12-03 | 2015-01-01 | 6 | No | DUKHCONI1BZ3PSGL7015, DUKHCONI1BZ4PSGL7010, DUKHCONI1BZ4STGL5260 | DUKHHANP1BGNELTC9010, DUKHHANP1BGNACTC9000, DUKHHANP1BGNPLTC9005 | 0 | 0 | PARKING SHED
DUKHCONI1BZ4PSGL7000 | Excavation | 15 | 15 | 0% | 2014-11-03 | 2014-11-19 | 2014-11-03 | 2014-11-19 | 12 | No | DUKHCONI1BZ3PSGL7005, DUKHCONI1BZ4RWGL6015 | DUKHCONI1BZ4PSGL7005, DUKHCONI1BZ4PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI1BZ4PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-11-15 | 2014-12-01 | 2014-11-15 | 2014-12-01 | 7 | No | DUKHCONI1BZ4PSGL7000, DUKHCONI1BZ4RWGL6015, DUKHCONI1BZ4PSGL7000 | DUKHCONI1BZ4PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L30.25 .10 .65 HARD LANDSCAPING |  | 71 | 71 | 0% | 2014-09-21 | 2014-12-14 | 2014-09-21 | 2014-12-14 | 0 |  |  |  | 0 | 0
DUKHCONI1BZ4HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-10-16 | 2014-11-13 | 2014-10-16 | 2014-11-13 | 0 | Yes | DUKHCONI1BZ3HDGL7030, DUKHCONI1BZ4HDGL7025 | DUKHCONI1BZ4HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ4HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-12-03 | 2014-12-14 | 2014-12-03 | 2014-12-14 | 0 | Yes | DUKHCONI1BZ4RWGL6025, DUKHCONI1BZ4HDGL7035, DUKHCONI1BZ3HDGL7040 | DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010, DUKHHANP1BGNACTC9000 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ4HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-10-16 | 2014-11-13 | 2014-10-16 | 2014-11-13 | 0 | Yes | DUKHCONI1BZ3HDGL7035, DUKHCONI1BZ4HDGL7030 | DUKHCONI1BZ4HDGL7040, DUKHCONI1BZ4SLGL7200 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ4HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-10-02 | 2014-11-02 | 2014-10-02 | 2014-11-02 | 0 | Yes | DUKHCONI1BSBGZGL7910, DUKHCONI1BZ4HDGL7020 | DUKHCONI1BZ4HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI1BZ4HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-09-21 | 2014-10-15 | 2014-09-21 | 2014-10-15 | 0 | Yes | DUKHCONI1BZ4RWGL6000 | DUKHCONI1BZ4HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L30.25 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-10-23 | 2014-12-14 | 2014-10-23 | 2014-12-14 | 0 |  |  |  | 0 | 0
DUKHCONI1BZ4SLGL7200 | Excavation for Landscaping | 25 | 25 | 0% | 2014-10-23 | 2014-11-20 | 2014-10-23 | 2014-11-20 | 0 | Yes | DUKHCONI1BZ4HDGL7035, DUKHCONI1BZ3SLGL7205, DUKHCONI1BZ4IRGL5290 | DUKHCONI1BZ4SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ4SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-11-16 | 2014-12-14 | 2014-11-16 | 2014-12-14 | 0 | Yes | DUKHCONI1BZ3SLGL7210, DUKHCONI1BZ4SLGL7205 | DUKHHANP1BGNPLTC9005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI1BZ4SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-11-04 | 2014-12-02 | 2014-11-04 | 2014-12-02 | 0 | Yes | DUKHCONI1BZ4SLGL7200 | DUKHCONI1BZ4SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L30.30 SECONDARY BUILDINGS |  | 181 | 181 | 0% | 2014-04-27 | 2014-11-29 | 2014-04-27 | 2014-11-29 | 13 |  |  |  | 0 | 0
DHBL.K30.L30.30 .10 INFRASTRUCTURE WORKS |  | 181 | 181 | 0% | 2014-04-27 | 2014-11-29 | 2014-04-27 | 2014-11-29 | 13 |  |  |  | 0 | 0
DHBL.K30.L30.30 .10 .10 IRRIGATION WATER TANK & PUMP ROOM |  | 160 | 160 | 0% | 2014-04-27 | 2014-11-04 | 2014-04-27 | 2014-11-04 | 34 |  |  |  | 0 | 0
DUKHCONI1BSBIWGL7445 | AC Works | 25 | 25 | 0% | 2014-08-26 | 2014-09-23 | 2014-08-26 | 2014-09-23 | 53 | No | DUKHCONI1BSBIWGL7440 | DUKHCONI1BSBIWGL7450 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7405 | Blinding & base waterproofing | 10 | 10 | 0% | 2014-05-14 | 2014-05-25 | 2014-05-14 | 2014-05-25 | 13 | No | DUKHCONI1BSBIWGL7400 | DUKHCONI1BSBIWGL7410 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7420 | Construction of Roof Slab | 20 | 20 | 0% | 2014-07-06 | 2014-07-28 | 2014-07-06 | 2014-07-28 | 54 | No | DUKHCONI1BSBIWGL7415 | DUKHCONI1BSBIWGL7425 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7410 | Construction of Raft slab | 10 | 10 | 0% | 2014-05-26 | 2014-06-05 | 2014-05-26 | 2014-06-05 | 13 | No | DUKHCONI1BSBIWGL7405 | DUKHCONI1BSBIWGL7415 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7415 | Construction of RCC Wall | 25 | 25 | 0% | 2014-06-07 | 2014-07-05 | 2014-06-07 | 2014-07-05 | 13 | No | DUKHCONI1BSBIWGL7410 | DUKHCONI1BSBIWGL7420, DUKHCONI1BSBTRGL7600 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7450 | Electrical Works | 25 | 25 | 0% | 2014-09-17 | 2014-10-18 | 2014-09-17 | 2014-10-18 | 34 | No | DUKHCONI1BSBIWGL7445, DUKHCONI1BZ4STGL5260, DUKHCONI1BZ4ELGL5230 | DUKHCONI1BSBIWGL7455 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7400 | Excavation | 15 | 15 | 0% | 2014-04-27 | 2014-05-13 | 2014-04-27 | 2014-05-13 | 13 | No | DUKHENGI1BDWIWAP4760, DUKHCONP1BZ6STRF2055 | DUKHCONI1BSBIWGL7405 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7430 | Floor screed | 5 | 5 | 0% | 2014-08-19 | 2014-08-24 | 2014-08-19 | 2014-08-24 | 54 | No | DUKHCONI1BSBIWGL7425 | DUKHCONI1BSBIWGL7440 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7435 | Installation of Boundary Fences | 15 | 15 | 0% | 2014-08-31 | 2014-09-16 | 2014-08-31 | 2014-09-16 | 69 | No | DUKHCONI1BSBIWGL7950 | DUKHCONI1BSBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7465 | Installation of G.I Handrails | 5 | 5 | 0% | 2014-10-30 | 2014-11-04 | 2014-10-30 | 2014-11-04 | 34 | No | DUKHCONI1BSBIWGL7460, DUKHCONI1BSBIWGL7435 | DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010, DUKHHANP1BGNACTC9000 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7460 | Installation of Steel Ladder | 5 | 5 | 0% | 2014-10-25 | 2014-10-29 | 2014-10-25 | 2014-10-29 | 34 | No | DUKHCONI1BSBIWGL7455 | DUKHCONI1BSBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7455 | Internal epoxy coating & Painting | 5 | 5 | 0% | 2014-10-19 | 2014-10-23 | 2014-10-19 | 2014-10-23 | 34 | No | DUKHCONI1BSBIWGL7450 | DUKHCONI1BSBIWGL7460 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7950 | Laying of Interlock | 10 | 10 | 0% | 2014-08-19 | 2014-08-30 | 2014-08-19 | 2014-08-30 | 69 | No | DUKHCONI1BSBIWGL7425 | DUKHCONI1BSBIWGL7435 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7440 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-08-26 | 2014-09-23 | 2014-08-26 | 2014-09-23 | 53 | No | DUKHCONI1BZ1FFGL5210, DUKHCONI1BZ3FFGL5210, DUKHCONI1BSBIWGL7430, DUKHCONI1BZ2FFGL5210, DUKHCONI1BZ4FFGL5210 | DUKHCONI1BSBIWGL7445 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI1BSBIWGL7425 | Waterproofing & Backfilling | 15 | 15 | 0% | 2014-07-29 | 2014-08-18 | 2014-07-29 | 2014-08-18 | 54 | No | DUKHCONI1BSBIWGL7420 | DUKHCONI1BSBIWGL7950, DUKHCONI1BSBIWGL7430 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DHBL.K30.L30.30 .10 .15 TELECOMMUNICATION ROOM |  | 120 | 120 | 0% | 2014-07-06 | 2014-11-27 | 2014-07-06 | 2014-11-27 | 14 |  |  |  | 0 | 0
DUKHCONI1BSBTRGL7625 | AC Works | 25 | 25 | 0% | 2014-10-25 | 2014-11-22 | 2014-10-25 | 2014-11-22 | 14 | No | DUKHCONI1BSBTRGL7620 | DUKHCONI1BSBTRGL7630, DUKHCONI1BSBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1BSBTRGL7610 | Construction Column,Beams & Roof Slab | 20 | 20 | 0% | 2014-08-13 | 2014-09-04 | 2014-08-13 | 2014-09-04 | 23 | No | DUKHCONI1BSBTRGL7605 | DUKHCONI1BSBTRGL7615 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1BSBTRGL7605 | Construction of foundation & Grade slab | 20 | 20 | 0% | 2014-07-17 | 2014-08-12 | 2014-07-17 | 2014-08-12 | 23 | No | DUKHCONI1BSBTRGL7600 | DUKHCONI1BSBTRGL7610 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1BSBTRGL7630 | Electrical Works-Telecom Room | 25 | 25 | 0% | 2014-10-25 | 2014-11-22 | 2014-10-25 | 2014-11-22 | 14 | No | DUKHCONI1BZ4TCGL5310, DUKHCONI1BSBTRGL7625, DUKHCONI1BZ1TCGL5310, DUKHCONI1BZ3TCGL5310, DUKHCONI1BZ2TCGL5310 | DUKHCONI1BSBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1BSBTRGL7600 | Excavation | 10 | 10 | 0% | 2014-07-06 | 2014-07-16 | 2014-07-06 | 2014-07-16 | 13 | No | DUKHCONI1BSBIWGL7415, DUKHENGI1BDWTRAP4770 | DUKHCONI1BSBTRGL7605, DUKHCONI1BSBGHGL7800 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1BSBTRGL7635 | Final Paintings | 5 | 5 | 0% | 2014-11-23 | 2014-11-27 | 2014-11-23 | 2014-11-27 | 14 | No | DUKHCONI1BSBTRGL7615, DUKHCONI1BSBTRGL7630, DUKHCONI1BSBTRGL7620, DUKHCONI1BSBTRGL7625 | DUKHHANP1BGNACTC9000, DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1BSBTRGL7615 | Finishing Works | 25 | 25 | 0% | 2014-09-30 | 2014-10-30 | 2014-09-30 | 2014-10-30 | 23 | No | DUKHCONI1BSBTRGL7610 | DUKHCONI1BSBTRGL7620, DUKHCONI1BSBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI1BSBTRGL7620 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-10-25 | 2014-11-22 | 2014-10-25 | 2014-11-22 | 14 | No | DUKHCONI1BSBTRGL7615, DUKHCONI1BZ4IRGL5280 | DUKHCONI1BSBTRGL7625, DUKHCONI1BSBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DHBL.K30.L30.30 .10 .20 GUARD HOUSE |  | 111 | 111 | 0% | 2014-07-17 | 2014-11-29 | 2014-07-17 | 2014-11-29 | 13 |  |  |  | 0 | 0
DUKHCONI1BSBGHGL7825 | AC Works | 25 | 25 | 0% | 2014-10-26 | 2014-11-23 | 2014-10-26 | 2014-11-23 | 13 | No | DUKHCONI1BSBGHGL7820 | DUKHCONI1BSBGHGL7835, DUKHCONI1BSBGHGL7830 | 0 | 0 | GUARD HOUSE
DUKHCONI1BSBGHGL7810 | Construction Column,Beams & Roof Slab | 20 | 20 | 0% | 2014-08-25 | 2014-09-16 | 2014-08-25 | 2014-09-16 | 13 | No | DUKHCONI1BSBGHGL7805 | DUKHCONI1BSBGHGL7815 | 0 | 0 | GUARD HOUSE
DUKHCONI1BSBGHGL7805 | Construction of foundation & Grade slab | 20 | 20 | 0% | 2014-07-29 | 2014-08-24 | 2014-07-29 | 2014-08-24 | 13 | No | DUKHCONI1BSBGHGL7800 | DUKHCONI1BSBGHGL7810 | 0 | 0 | GUARD HOUSE
DUKHCONI1BSBGHGL7830 | Electrical Works-Telecom Room | 25 | 25 | 0% | 2014-10-26 | 2014-11-23 | 2014-10-26 | 2014-11-23 | 13 | No | DUKHCONI1BSBGHGL7825 | DUKHCONI1BSBGHGL7835 | 0 | 0 | GUARD HOUSE
DUKHCONI1BSBGHGL7800 | Excavation | 10 | 10 | 0% | 2014-07-17 | 2014-07-28 | 2014-07-17 | 2014-07-28 | 13 | No | DUKHCONI1BSBTRGL7600, DUKHENGI1BDWGHAP4790 | DUKHCONI1BSBGHGL7805 | 0 | 0 | GUARD HOUSE
DUKHCONI1BSBGHGL7835 | Final Paintings | 5 | 5 | 0% | 2014-11-24 | 2014-11-29 | 2014-11-24 | 2014-11-29 | 13 | No | DUKHCONI1BSBGHGL7820, DUKHCONI1BSBGHGL7825, DUKHCONI1BSBGHGL7830, DUKHCONI1BSBGHGL7815 | DUKHHANP1BGNPLTC9005, DUKHHANP1BGNELTC9010, DUKHHANP1BGNACTC9000 | 0 | 0 | GUARD HOUSE
DUKHCONI1BSBGHGL7815 | Finishing Works | 25 | 25 | 0% | 2014-10-14 | 2014-11-11 | 2014-10-14 | 2014-11-11 | 13 | No | DUKHCONI1BSBGHGL7810 | DUKHCONI1BSBGHGL7820, DUKHCONI1BSBGHGL7835 | 0 | 0 | GUARD HOUSE
DUKHCONI1BSBGHGL7820 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-10-26 | 2014-11-23 | 2014-10-26 | 2014-11-23 | 13 | No | DUKHCONI1BSBGHGL7815 | DUKHCONI1BSBGHGL7835, DUKHCONI1BSBGHGL7825 | 0 | 0 | GUARD HOUSE
DHBL.K30.L30.30 .10 .25 GAZEBO |  | 50 | 50 | 0% | 2014-08-28 | 2014-10-27 | 2014-08-28 | 2014-10-27 | 5 |  |  |  | 0 | 0
DUKHCONI1BSBGZGL7900 | Construction of Concrete structure | 20 | 20 | 0% | 2014-08-28 | 2014-09-20 | 2014-08-28 | 2014-09-20 | 5 | No | DUKHENGI1BDWGZAP4780, DUKHCONI1BZ3HDGL7020 | DUKHCONI1BSBGZGL7905 | 0 | 0 | GAZEBO
DUKHCONI1BSBGZGL7910 | Electrical Works-Gazebo | 15 | 15 | 0% | 2014-10-08 | 2014-10-27 | 2014-10-08 | 2014-10-27 | 5 | No | DUKHCONI1BSBGZGL7905, DUKHCONI1BSBGZGL7915 | DUKHCONI1BZ4HDGL7025 | 0 | 0 | GAZEBO
DUKHCONI1BSBGZGL7905 | Installation of Wooden Works | 25 | 25 | 0% | 2014-09-09 | 2014-10-07 | 2014-09-09 | 2014-10-07 | 5 | No | DUKHCONI1BSBGZGL7900 | DUKHCONI1BSBGZGL7910, DUKHCONI1BSBGZGL7915 | 0 | 0 | GAZEBO
DUKHCONI1BSBGZGL7915 | Park Benches Installation | 15 | 15 | 0% | 2014-09-09 | 2014-09-25 | 2014-09-09 | 2014-09-25 | 15 | No | DUKHCONI1BSBGZGL7905 | DUKHCONI1BSBGZGL7910 | 0 | 0 | GAZEBO
DHBL.K30.L35 PACKAGE-2A |  | 456 | 456 | 0% | 2012-11-18 | 2014-05-13 | 2012-11-18 | 2014-05-13 | 27 |  |  |  | 0 | 0
DHBL.K30.L35.03 SITE PREPARATORY WORKS |  | 92 | 92 | 0% | 2012-11-18 | 2013-03-06 | 2012-11-18 | 2013-03-06 | 3 |  |  |  | 0 | 0
DUKHCONP2AGNSP002400 | Approval for new Layout for rerouting | 14 | 14 | 0% | 2013-01-20 | 2013-02-04 | 2013-01-20 | 2013-02-04 | 0 | Yes | DUKHCONP2AGNSP002300 | DUKHCONP2AGNSP002500 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP004000 | Demolition of Existing building & landscaping | 20 | 20 | 0% | 2012-12-12 | 2013-01-05 | 2012-12-12 | 2013-01-05 | 48 | No | DUKHCONP2AGNSP003000 | DUKHCONP2AGNSP005000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP005000 | Demolition of existing services works | 20 | 20 | 0% | 2012-12-20 | 2013-01-12 | 2012-12-20 | 2013-01-12 | 48 | No | DUKHCONP2AGNSP004000 | DUKHCONP2AZ1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP002200 | Information Required for Rerouting | 14 | 14 | 0% | 2012-12-26 | 2013-01-10 | 2012-12-26 | 2013-01-10 | 0 | Yes | DUKHCONP2AGNSP002100 | DUKHCONP2AGNSP002300 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP002300 | Preparation & Submission for New Layout | 7 | 7 | 0% | 2013-01-12 | 2013-01-19 | 2013-01-12 | 2013-01-19 | 0 | Yes | DUKHCONP2AGNSP002200 | DUKHCONP2AGNSP002400 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP002500 | Rerouting Works | 25 | 25 | 0% | 2013-02-05 | 2013-03-06 | 2013-02-05 | 2013-03-06 | 0 | Yes | DUKHCONP2AGNSP002400 | DUKHCONP2AZ1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP002000 | Scanning for Existing Services for rerouting | 10 | 10 | 0% | 2012-12-05 | 2012-12-16 | 2012-12-05 | 2012-12-16 | 0 | Yes | DUKHMOBP020000004000, DUKHCONP2AGNSP001000 | DUKHCONP2AGNSP002100, DUKHCONP2AGNSP003000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP003000 | Site stripping | 20 | 20 | 0% | 2012-12-05 | 2012-12-29 | 2012-12-05 | 2012-12-29 | 48 | No | DUKHCONP2AGNSP002000 | DUKHCONP2AGNSP004000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP002100 | Submission of Scanning Reports | 7 | 7 | 0% | 2012-12-17 | 2012-12-25 | 2012-12-17 | 2012-12-25 | 0 | Yes | DUKHCONP2AGNSP002000 | DUKHCONP2AGNSP002200 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2AGNSP001000 | Survey works, | 20 | 20 | 0% | 2012-11-18 | 2012-12-10 | 2012-11-18 | 2012-12-10 | 0 | Yes | DUKHMOBP020000004000 | DUKHCONP2AGNSP002000 | 0 | 0 | SITE PREPARATORY WORKS
DHBL.K30.L35.05 MOCK UP VILLA |  | 105 | 105 | 0% | 2013-08-18 | 2013-12-21 | 2013-08-18 | 2013-12-21 | 74 |  |  |  | 0 | 0
DHBL.K30.L35.05 .15 FINISHING WORKS |  | 96 | 96 | 0% | 2013-08-18 | 2013-12-09 | 2013-08-18 | 2013-12-09 | 83 |  |  |  | 0 | 0
DHBL.K30.L35.05 .15 .10 INTERNAL FINISHES |  | 93 | 93 | 0% | 2013-08-21 | 2013-12-09 | 2013-08-21 | 2013-12-09 | 83 |  |  |  | 0 | 0
DHBL.K30.L35.05 .15 .10 .10 GROUND FLOOR |  | 93 | 93 | 0% | 2013-08-21 | 2013-12-09 | 2013-08-21 | 2013-12-09 | 83 |  |  |  | 0 | 0
DUKHCONP2AMKARGF3080 | Aluminum windows | 7 | 7 | 0% | 2013-10-29 | 2013-11-05 | 2013-10-29 | 2013-11-05 | 65 | No | DUKHCONP2AMKARGF3065, DUKHPROGEN00PRDV3470 | DUKHCONP2AMKARGF3090, DUKHCONP2AMKARGF3095, DUKHCONP2AZ1ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3000 | Block work | 6 | 6 | 0% | 2013-08-21 | 2013-08-27 | 2013-08-21 | 2013-08-27 | 6 | No | DUKHCONP2AZ1STGF2015, DUKHPROGEN00PRDV3010 | DUKHCONP2AZ1ARGF3000, DUKHCONP2AMKARGF3005, DUKHCONP2AMKPLGF4305, DUKHCONP2AMKPLGF4310, DUKHCONP2AMKELGF4000 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3075 | Carpentry & Joinery Works | 10 | 10 | 0% | 2013-11-12 | 2013-11-23 | 2013-11-12 | 2013-11-23 | 45 | No | DUKHPROGEN00PRDV3570, DUKHPROGEN00PRDV3550, DUKHPROGEN00PRDV3560 | DUKHCONP2AZ1ARGF3075, DUKHCONP2AMKARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3020 | Ceramic Wall Tiling | 6 | 6 | 0% | 2013-09-16 | 2013-09-22 | 2013-09-16 | 2013-09-22 | 26 | No | DUKHCONP2AMKPLGF4310, DUKHCONP2AMKARGF3015, DUKHPROGEN00PRDV3120 | DUKHCONP2AZ1ARGF3020, DUKHCONP2AMKARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3040 | Cobble Tile flooring | 5 | 5 | 0% | 2013-09-30 | 2013-10-05 | 2013-09-30 | 2013-10-05 | 52 | No | DUKHCONP2AMKARGF3010, DUKHPROGEN00PRDV3090, DUKHCONP2AMKARGF3025 | DUKHCONP2AMKARGF3035, DUKHCONP2AMKARGF3095, DUKHCONP2AZ1ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3095 | Final Painting | 7 | 7 | 0% | 2013-12-02 | 2013-12-09 | 2013-12-02 | 2013-12-09 | 83 | No | DUKHCONP2AMKARGF3090, DUKHCONP2AMKELRF4070, DUKHCONP2AMKARGF3080, DUKHCONP2AMKELRF4075, DUKHCONP2AMKARGF3040, DUKHCONP2AMKACRF4635, DUKHCONP2AMKARGF3030, DUKHCONP2AMKARGF3060, DUKHPROGEN00PRDV3420, DUKHCONP2AMKARGF3035 | DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3045 | Fixing of Suspension systems | 7 | 7 | 0% | 2013-10-01 | 2013-10-08 | 2013-10-01 | 2013-10-08 | 25 | No | DUKHCONP2AMKARGF3030, DUKHCONP2AMKARGF3025, DUKHCONP2AMKELGF4010 | DUKHCONP2AMKARGF3060, DUKHCONP2AZ1ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3010 | Flooring screed | 7 | 7 | 0% | 2013-09-07 | 2013-09-14 | 2013-09-07 | 2013-09-14 | 21 | No | DUKHCONP2AMKARGF3005 | DUKHCONP2AMKARGF3025, DUKHCONP2AMKARGF3035, DUKHCONP2AZ1ARGF3010, DUKHCONP2AMKARGF3040, DUKHCONP2AMKARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3060 | Gypsum board false ceiling | 8 | 8 | 0% | 2013-10-09 | 2013-10-20 | 2013-10-09 | 2013-10-20 | 25 | No | DUKHCONP2AMKARGF3045, DUKHCONP2AMKACGF4600, DUKHPROGEN00PRDV3300 | DUKHCONP2AMKELGF4030, DUKHCONP2AMKELGF4015, DUKHCONP2AMKPLGF4320, DUKHCONP2AZ1ARGF3060, DUKHCONP2AMKELGF4025, DUKHCONP2AMKARGF3095, DUKHCONP2AMKACGF4605, DUKHCONP2AMKARGF3065, DUKHCONP2AMKELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3090 | Installation of Granite Counter Top | 7 | 7 | 0% | 2013-11-24 | 2013-12-01 | 2013-11-24 | 2013-12-01 | 50 | No | DUKHCONP2AMKARGF3080, DUKHCONP2AMKARGF3075 | DUKHCONP2AZ1ARGF3090, DUKHCONP2AMKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3030 | Paint First coat | 5 | 5 | 0% | 2013-09-25 | 2013-09-30 | 2013-09-25 | 2013-09-30 | 10 | No | DUKHPROGEN00PRDV3320, DUKHCONP2AMKARGF3005 | DUKHCONP2AMKARGF3045, DUKHCONP2AMKARGF3095, DUKHCONP2AZ1ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3005 | Plastering work | 7 | 7 | 0% | 2013-09-03 | 2013-09-10 | 2013-09-03 | 2013-09-10 | 12 | No | DUKHCONP2AMKARGF3000, DUKHPROGEN00PRDV3040, DUKHCONP2AMKELGF4000 | DUKHCONP2AZ1ARGF3005, DUKHCONP2AMKARGF3030, DUKHCONP2AMKARGF3010, DUKHCONP2AMKARGF3015, DUKHCONP2AMKACGF4600, DUKHCONP2AMKELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3025 | Porcelain Tile flooring | 6 | 6 | 0% | 2013-09-23 | 2013-09-29 | 2013-09-23 | 2013-09-29 | 26 | No | DUKHCONP2AMKARGF3010, DUKHPROGEN00PRDV3130, DUKHCONP2AMKARGF3020 | DUKHCONP2AZ1ARGF3025, DUKHCONP2AMKARGF3045, DUKHCONP2AMKARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3035 | Slate Tile Flooring & Skirting | 5 | 5 | 0% | 2013-10-06 | 2013-10-10 | 2013-10-06 | 2013-10-10 | 52 | No | DUKHCONP2AMKARGF3010, DUKHCONP2AMKARGF3040, DUKHPROGEN00PRDV3100 | DUKHCONP2AMKARGF3095, DUKHCONP2AZ1ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3015 | Wet area waterproofing & Protection Screed | 5 | 5 | 0% | 2013-09-10 | 2013-09-15 | 2013-09-10 | 2013-09-15 | 21 | No | DUKHCONP2AMKARGF3005, DUKHCONP2AMKARGF3010 | DUKHCONP2AMKARGF3020, DUKHCONP2AZ1ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKARGF3065 | Wooden door | 7 | 7 | 0% | 2013-10-21 | 2013-10-28 | 2013-10-21 | 2013-10-28 | 25 | No | DUKHCONP2AMKARGF3060, DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3450 | DUKHCONP2AMKARGF3080, DUKHCONP2AZ1ARGF3065, DUKHCONP2AMKPLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.05 .15 .15 EXTERNAL FINISHES |  | 36 | 36 | 0% | 2013-08-18 | 2013-09-28 | 2013-08-18 | 2013-09-28 | 83 |  |  |  | 0 | 0
DHBL.K30.L35.05 .15 .15 .10 ROOF |  | 28 | 28 | 0% | 2013-08-18 | 2013-09-18 | 2013-08-18 | 2013-09-18 | 91 |  |  |  | 0 | 0
DUKHCONP2AMKARRF3660 | Installation of Access Ladder | 5 | 5 | 0% | 2013-09-14 | 2013-09-18 | 2013-09-14 | 2013-09-18 | 91 | No | DUKHPROGEN00PRDV3400, DUKHCONP2AMKARRF3645 | DUKHCONP2AZ1ARRF3660 | 0 | 0 | ROOF
DUKHCONP2AMKARRF3640 | Installation of Insulation & Protection | 4 | 4 | 0% | 2013-09-02 | 2013-09-05 | 2013-09-02 | 2013-09-05 | 30 | No | DUKHCONP2AMKARRF3635 | DUKHCONP2AMKARRF3645, DUKHCONP2AZ1ARRF3640 | 0 | 0 | ROOF
DUKHCONP2AMKARRF3625 | Laying of Pitched Roof | 7 | 7 | 0% | 2013-08-18 | 2013-08-25 | 2013-08-18 | 2013-08-25 | 30 | No | DUKHPROGEN00PRDV3140, DUKHCONP2AZ1STRF2065, DUKHCONP2AZ1STRF2060 | DUKHCONP2AZ1ARRF3625, DUKHCONP2AMKARRF3630 | 0 | 0 | ROOF
DUKHCONP2AMKARRF3635 | Laying of Waterproofing Membrane | 4 | 4 | 0% | 2013-08-28 | 2013-09-01 | 2013-08-28 | 2013-09-01 | 30 | No | DUKHCONP2AMKARRF3630 | DUKHCONP2AZ1ARRF3635, DUKHCONP2AMKARRF3640 | 0 | 0 | ROOF
DUKHCONP2AMKARRF3630 | Leveling Screed for Waterproofing | 2 | 2 | 0% | 2013-08-26 | 2013-08-27 | 2013-08-26 | 2013-08-27 | 30 | No | DUKHCONP2AMKARRF3625 | DUKHCONP2AZ1ARRF3630, DUKHCONP2AMKARRF3635 | 0 | 0 | ROOF
DUKHCONP2AMKARRF3645 | Lime Stone Chips & Paving slab Installation | 2 | 2 | 0% | 2013-09-07 | 2013-09-08 | 2013-09-07 | 2013-09-08 | 30 | No | DUKHCONP2AMKARRF3640 | DUKHCONP2AMKPLRF4350, DUKHCONP2AMKACRF4630, DUKHCONP2AMKELRF4070, DUKHCONP2AMKARRF3660, DUKHCONP2AMKACRF4635, DUKHCONP2AMKAREL3665, DUKHCONP2AZ1ARRF3645 | 0 | 0 | ROOF
DHBL.K30.L35.05 .15 .15 .15 ELEVATION |  | 17 | 17 | 0% | 2013-09-09 | 2013-09-28 | 2013-09-09 | 2013-09-28 | 38 |  |  |  | 0 | 0
DUKHCONP2AMKAREL3680 | External Painting | 7 | 7 | 0% | 2013-09-21 | 2013-09-28 | 2013-09-21 | 2013-09-28 | 38 | No | DUKHCONP2AMKAREL3665 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1AREL3680, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1PLTC8005, DUKHCONP2AMKMSEX5025 | 0 | 0 | ELEVATION
DUKHCONP2AMKAREL3665 | External Plastering | 10 | 10 | 0% | 2013-09-09 | 2013-09-19 | 2013-09-09 | 2013-09-19 | 30 | No | DUKHCONP2AMKARRF3645, DUKHCONP2AZ1STRF2060 | DUKHCONP2AMKMSEX5020, DUKHCONP2AMKAREL3680, DUKHCONP2AZ1AREL3665 | 0 | 0 | ELEVATION
DHBL.K30.L35.05 .20 MEP WORKS |  | 83 | 83 | 0% | 2013-08-28 | 2013-12-04 | 2013-08-28 | 2013-12-04 | 80 |  |  |  | 0 | 0
DHBL.K30.L35.05 .20 .10 ELECTRICAL WORKS |  | 66 | 66 | 0% | 2013-08-28 | 2013-11-14 | 2013-08-28 | 2013-11-14 | 97 |  |  |  | 0 | 0
DHBL.K30.L35.05 .20 .10 .10 GROUND FLOOR |  | 61 | 61 | 0% | 2013-08-28 | 2013-11-09 | 2013-08-28 | 2013-11-09 | 90 |  |  |  | 0 | 0
DUKHCONP2AMKELGF4005 | Cable tray & trunking installation | 5 | 5 | 0% | 2013-09-11 | 2013-09-16 | 2013-09-11 | 2013-09-16 | 15 | No | DUKHCONP2AMKELGF4000, DUKHCONP2AMKARGF3005 | DUKHCONP2AMKELGF4010, DUKHCONP2AZ1ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKELGF4000 | Fixing of wall conduits & switch socket boxes | 5 | 5 | 0% | 2013-08-28 | 2013-09-02 | 2013-08-28 | 2013-09-02 | 12 | No | DUKHCONP2AMKARGF3000 | DUKHCONP2AMKELGF4005, DUKHCONP2AZ1ELGF4000, DUKHCONP2AMKARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKELGF4015 | Install. of CAMS & Fire Fighting Accessories | 7 | 7 | 0% | 2013-11-02 | 2013-11-09 | 2013-11-02 | 2013-11-09 | 59 | No | DUKHPROGEN00PRDV3360, DUKHCONP2AMKARGF3060, DUKHCONP2AMKELGF4025, DUKHPROGEN00PRDV3380, DUKHPROGEN00PRDV3370, DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3260 | DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ELGF4015, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKELGF4020 | Installation of DBS,MCCB Accessories. | 5 | 5 | 0% | 2013-10-21 | 2013-10-26 | 2013-10-21 | 2013-10-26 | 66 | No | DUKHCONP2AMKELGF4010, DUKHPROGEN00PRDV3170, DUKHCONP2AMKARGF3060 | DUKHCONP2AMKELGF4025, DUKHCONP2AMKELGF4030, DUKHCONP2AZ1ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKELGF4025 | Installation of Lighting fixtures & Accessories | 5 | 5 | 0% | 2013-10-27 | 2013-10-31 | 2013-10-27 | 2013-10-31 | 66 | No | DUKHPROGEN00PRDV3190, DUKHCONP2AMKELGF4020, DUKHCONP2AMKARGF3060 | DUKHCONP2AMKELRF4070, DUKHCONP2AZ1ELGF4025, DUKHCONP2AMKELGF4015, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKELGF4030 | Installation of Telephone System | 5 | 5 | 0% | 2013-10-27 | 2013-10-31 | 2013-10-27 | 2013-10-31 | 97 | No | DUKHCONP2AMKARGF3060, DUKHPROGEN00PRDV3270, DUKHPROGEN00PRDV3280, DUKHCONP2AMKELGF4020 | DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ELTC8010, DUKHCONP2AMKELRF4070, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKELGF4010 | Installation of wiring & Main Cabling | 5 | 5 | 0% | 2013-09-17 | 2013-09-22 | 2013-09-17 | 2013-09-22 | 32 | No | DUKHCONP2AMKELGF4005, DUKHPROGEN00PRDV3180 | DUKHCONP2AMKELGF4020, DUKHCONP2AMKELRF4070, DUKHCONP2AZ1ELGF4010, DUKHCONP2AMKARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.05 .20 .10 .20 ROOF |  | 12 | 12 | 0% | 2013-11-02 | 2013-11-14 | 2013-11-02 | 2013-11-14 | 97 |  |  |  | 0 | 0
DUKHCONP2AMKELRF4070 | Installation of Isolator | 5 | 5 | 0% | 2013-11-02 | 2013-11-06 | 2013-11-02 | 2013-11-06 | 97 | No | DUKHCONP2AMKELGF4025, DUKHPROGEN00PRDV3200, DUKHCONP2AMKARRF3645, DUKHCONP2AMKELGF4010, DUKHCONP2AMKELGF4030 | DUKHCONP2AMKARGF3095, DUKHCONP2AMKELRF4075, DUKHCONP2AZ1ELRF4070 | 0 | 0 | ROOF
DUKHCONP2AMKELRF4075 | Installation of TV Dish Antenna | 7 | 7 | 0% | 2013-11-07 | 2013-11-14 | 2013-11-07 | 2013-11-14 | 97 | No | DUKHCONP2AMKELRF4070, DUKHPROGEN00PRDV3290 | DUKHCONP2AMKARGF3095, DUKHCONP2AZ1ELRF4075, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ACTC8000 | 0 | 0 | ROOF
DHBL.K30.L35.05 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 83 | 83 | 0% | 2013-08-28 | 2013-12-04 | 2013-08-28 | 2013-12-04 | 10 |  |  |  | 0 | 0
DHBL.K30.L35.05 .20 .15 .10 GROUND FLOOR |  | 78 | 78 | 0% | 2013-08-28 | 2013-11-28 | 2013-08-28 | 2013-11-28 | 10 |  |  |  | 0 | 0
DUKHCONP2AMKPLGF4310 | Installation of Drainage pipes &testing | 5 | 5 | 0% | 2013-08-28 | 2013-09-02 | 2013-08-28 | 2013-09-02 | 15 | No | DUKHCONP2AMKARGF3000, DUKHCONP2AMKPLGF4305 | DUKHCONP2AMKARGF3020, DUKHCONP2AMKPLRF4350, DUKHCONP2AZ1PLGF4310, DUKHCONP2AMKPLGF4315, DUKHCONP2AMKMSEX5000 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKPLGF4305 | Installation of Plumbing pipes & testing | 5 | 5 | 0% | 2013-08-28 | 2013-09-02 | 2013-08-28 | 2013-09-02 | 14 | No | DUKHCONP2AMKARGF3000, DUKHPROGEN00PRDV3080 | DUKHCONP2AMKPLRF4350, DUKHCONP2AZ1PLGF4305, DUKHCONP2AMKPLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKPLGF4320 | Installation of Water Heater | 5 | 5 | 0% | 2013-11-24 | 2013-11-28 | 2013-11-24 | 2013-11-28 | 10 | No | DUKHCONP2AMKARGF3060, DUKHCONP2AMKPLGF4315 | DUKHCONP2AZ1ACTC8000, DUKHCONP2AMKPLRF4350, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLGF4320, DUKHCONP2AZ1PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKPLGF4315 | Sanitary Fittings & Accessories | 7 | 7 | 0% | 2013-11-16 | 2013-11-23 | 2013-11-16 | 2013-11-23 | 10 | No | DUKHPROGEN00PRDV3770, DUKHPROGEN00PRDV3150, DUKHCONP2AMKARGF3065, DUKHCONP2AMKPLGF4310, DUKHPROGEN00PRDV3230 | DUKHCONP2AMKPLRF4350, DUKHCONP2AZ1PLGF4315, DUKHCONP2AMKPLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.05 .20 .15 .20 ROOF |  | 5 | 5 | 0% | 2013-11-30 | 2013-12-04 | 2013-11-30 | 2013-12-04 | 10 |  |  |  | 0 | 0
DUKHCONP2AMKPLRF4350 | Installation of Rain water Pipes | 5 | 5 | 0% | 2013-11-30 | 2013-12-04 | 2013-11-30 | 2013-12-04 | 10 | No | DUKHCONP2AMKARRF3645, DUKHCONP2AMKPLGF4315, DUKHCONP2AMKPLGF4320, DUKHCONP2AMKPLGF4305, DUKHCONP2AMKPLGF4310 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1PLTC8005, DUKHCONP2AMKWEEX5065 | 0 | 0 | ROOF
DHBL.K30.L35.05 .20 .20 AC WORKS |  | 53 | 53 | 0% | 2013-09-11 | 2013-11-13 | 2013-09-11 | 2013-11-13 | 98 |  |  |  | 0 | 0
DHBL.K30.L35.05 .20 .20 .10 GROUND FLOOR |  | 45 | 45 | 0% | 2013-09-11 | 2013-11-04 | 2013-09-11 | 2013-11-04 | 98 |  |  |  | 0 | 0
DUKHCONP2AMKACGF4610 | Fixing of Split AC | 8 | 8 | 0% | 2013-10-27 | 2013-11-04 | 2013-10-27 | 2013-11-04 | 98 | No | DUKHCONP2AMKACGF4605, DUKHPROGEN00PRDV3240 | DUKHCONP2AZ1ACGF4610, DUKHCONP2AMKACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKACGF4605 | Fixing of Ventilation Equipments | 5 | 5 | 0% | 2013-10-21 | 2013-10-26 | 2013-10-21 | 2013-10-26 | 92 | No | DUKHCONP2AMKACGF4600, DUKHPROGEN00PRDV3530, DUKHCONP2AMKARGF3060, DUKHPROGEN00PRDV3340 | DUKHCONP2AMKACGF4610, DUKHCONP2AZ1ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP2AMKACGF4600 | Installation AC Pipes | 5 | 5 | 0% | 2013-09-11 | 2013-09-16 | 2013-09-11 | 2013-09-16 | 41 | No | DUKHCONP2AMKARGF3005, DUKHPROGEN00PRDV3160 | DUKHCONP2AMKARGF3060, DUKHCONP2AMKACGF4605, DUKHCONP2AZ1ACGF4600, DUKHCONP2AMKACRF4630 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.05 .20 .20 .20 ROOF |  | 48 | 48 | 0% | 2013-09-17 | 2013-11-13 | 2013-09-17 | 2013-11-13 | 98 |  |  |  | 0 | 0
DUKHCONP2AMKACRF4635 | Installation of Condensing Unit | 8 | 8 | 0% | 2013-11-05 | 2013-11-13 | 2013-11-05 | 2013-11-13 | 98 | No | DUKHCONP2AMKACGF4610, DUKHCONP2AMKARRF3645, DUKHCONP2AMKACRF4630 | DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ELTC8010, DUKHCONP2AMKARGF3095, DUKHCONP2AZ1ACRF4635, DUKHCONP2AZ1ACTC8000 | 0 | 0 | ROOF
DUKHCONP2AMKACRF4630 | Installation of Refrigerant Pipes | 5 | 5 | 0% | 2013-09-17 | 2013-09-22 | 2013-09-17 | 2013-09-22 | 88 | No | DUKHCONP2AMKARRF3645, DUKHCONP2AMKACGF4600 | DUKHCONP2AZ1ACRF4630, DUKHCONP2AMKACRF4635 | 0 | 0 | ROOF
DHBL.K30.L35.05 .25 EXTERNAL WORKS |  | 91 | 91 | 0% | 2013-09-03 | 2013-12-21 | 2013-09-03 | 2013-12-21 | 64 |  |  |  | 0 | 0
DHBL.K30.L35.05 .25 .10 MISCELLANEOUS |  | 27 | 27 | 0% | 2013-09-03 | 2013-10-03 | 2013-09-03 | 2013-10-03 | 38 |  |  |  | 0 | 0
DUKHCONP2AMKMSEX5005 | Construction of Soak pit, Chambers | 7 | 7 | 0% | 2013-09-11 | 2013-09-18 | 2013-09-11 | 2013-09-18 | 15 | No | DUKHCONP2AMKMSEX5000 | DUKHCONP2AMKMSEX5015, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1MSEX5005, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLTC8005, DUKHCONP2AMKWEEX5030 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AMKMSEX5020 | Construction Entrance Ramp | 7 | 7 | 0% | 2013-09-21 | 2013-09-28 | 2013-09-21 | 2013-09-28 | 30 | No | DUKHCONP2AMKAREL3665 | DUKHCONP2AZ1MSEX5020, DUKHCONP2AMKHDEX5090, DUKHCONP2AMKMSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AMKMSEX5015 | Construction of grease Trap | 7 | 7 | 0% | 2013-09-19 | 2013-09-26 | 2013-09-19 | 2013-09-26 | 15 | No | DUKHCONP2AMKMSEX5005 | DUKHCONP2AZ1MSEX5015, DUKHCONP2AMKWEEX5065, DUKHCONP2AMKWEEX5030 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AMKMSEX5000 | Construction of Manholes | 7 | 7 | 0% | 2013-09-03 | 2013-09-10 | 2013-09-03 | 2013-09-10 | 15 | No | DUKHCONP2AMKPLGF4310 | DUKHCONP2AMKMSEX5005, DUKHCONP2AZ1MSEX5000, DUKHCONP2AMKWEEX5030 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AMKMSEX5025 | SS.Handrails and Balustrades | 5 | 5 | 0% | 2013-09-29 | 2013-10-03 | 2013-09-29 | 2013-10-03 | 38 | No | DUKHCONP2AMKMSEX5020, DUKHCONP2AMKAREL3680 | DUKHCONP2AZ1MSEX5025, DUKHCONP2AMKWEEX5060, DUKHCONP2AMKHDEX5090 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L35.05 .25 .15 WATER TANK ENCLOSURE |  | 74 | 74 | 0% | 2013-09-19 | 2013-12-16 | 2013-09-19 | 2013-12-16 | 10 |  |  |  | 0 | 0
DUKHCONP2AMKWEEX5040 | Block works & Plastering | 7 | 7 | 0% | 2013-10-02 | 2013-10-09 | 2013-10-02 | 2013-10-09 | 26 | No | DUKHCONP2AMKWEEX5035 | DUKHCONP2AMKWEEX5045, DUKHCONP2AZ1WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AMKWEEX5035 | Construction of Raft | 7 | 7 | 0% | 2013-09-24 | 2013-10-01 | 2013-09-24 | 2013-10-01 | 25 | No | DUKHCONP2AMKWEEX5030 | DUKHCONP2AZ1WEEX5035, DUKHCONP2AMKWEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AMKWEEX5030 | Excavation | 4 | 4 | 0% | 2013-09-19 | 2013-09-23 | 2013-09-19 | 2013-09-23 | 15 | No | DUKHCONP2AMKMSEX5005, DUKHCONP2AMKMSEX5015, DUKHCONP2AMKMSEX5000 | DUKHCONP2AZ1WEEX5030, DUKHCONP2AMKWEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AMKWEEX5045 | Flooring & Painting | 7 | 7 | 0% | 2013-10-10 | 2013-10-20 | 2013-10-10 | 2013-10-20 | 29 | No | DUKHCONP2AMKWEEX5040 | DUKHCONP2AZ1WEEX5045, DUKHCONP2AMKWEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AMKWEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 10 | 10 | 0% | 2013-12-05 | 2013-12-16 | 2013-12-05 | 2013-12-16 | 10 | No | DUKHPROGEN00PRDV3220, DUKHPROGEN00PRDV3330, DUKHPROGEN00PRDV3520, DUKHPROGEN00PRDV3640, DUKHCONP2AMKWEEX5060, DUKHCONP2AMKMSEX5015, DUKHPROGEN00PRDV3680, DUKHCONP2AMKPLRF4350 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AMKWEEX5050 | Installation of Steel Gate | 5 | 5 | 0% | 2013-10-28 | 2013-11-02 | 2013-10-28 | 2013-11-02 | 28 | No | DUKHPROGEN00PRDV3500, DUKHPROGEN00PRDV3510, DUKHPROGEN00PRDV3610, DUKHCONP2AMKWEEX5045 | DUKHCONP2AMKWEEX5060, DUKHCONP2AZ1WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AMKWEEX5060 | Structural steel & SS Shed cover installation | 10 | 10 | 0% | 2013-11-03 | 2013-11-13 | 2013-11-03 | 2013-11-13 | 28 | No | DUKHPROGEN00PRDV3620, DUKHCONP2AMKWEEX5050, DUKHCONP2AMKMSEX5025, DUKHPROGEN00PRDV3630 | DUKHCONP2AMKWEEX5065, DUKHCONP2AZ1WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L35.05 .25 .20 HARD LANDSCAPING |  | 15 | 15 | 0% | 2013-10-05 | 2013-10-23 | 2013-10-05 | 2013-10-23 | 53 |  |  |  | 0 | 0
DUKHCONP2AMKHDEX5095 | Cobble Stone Works | 5 | 5 | 0% | 2013-10-10 | 2013-10-15 | 2013-10-10 | 2013-10-15 | 45 | No | DUKHCONP2AMKHDEX5090 | DUKHCONP2AZ1HDEX5095, DUKHCONP2AMKHDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2AMKHDEX5100 | Interlock works | 5 | 5 | 0% | 2013-10-16 | 2013-10-23 | 2013-10-16 | 2013-10-23 | 53 | No | DUKHPROGEN00PRDV3660, DUKHCONP2AMKHDEX5095 | DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1HDEX5100, DUKHCONP2AZ1PLTC8005, DUKHCONP2AMKSLEX5105 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2AMKHDEX5090 | kerb works | 5 | 5 | 0% | 2013-10-05 | 2013-10-09 | 2013-10-05 | 2013-10-09 | 40 | No | DUKHCONP2AMKMSEX5020, DUKHPROGEN00PRDV3600, DUKHCONP2AMKMSEX5025 | DUKHCONP2AMKHDEX5095, DUKHCONP2AZ1HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L35.05 .25 .25 SOFT LANDSCAPING |  | 14 | 14 | 0% | 2013-12-04 | 2013-12-21 | 2013-12-04 | 2013-12-21 | 64 |  |  |  | 0 | 0
DUKHCONP2AMKSLEX5105 | Laying of Grass/ green area | 7 | 7 | 0% | 2013-12-04 | 2013-12-11 | 2013-12-04 | 2013-12-11 | 21 | No | DUKHPROGEN00PRDV3670, DUKHPROGEN00PRDV3790, DUKHCONP2AMKHDEX5100 | DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1SLEX5105, DUKHCONP2AMKSLEX5110, DUKHCONP2AZ1ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP2AMKSLEX5110 | Laying of Palm tree | 7 | 7 | 0% | 2013-12-12 | 2013-12-21 | 2013-12-12 | 2013-12-21 | 64 | No | DUKHCONP2AMKSLEX5105 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L35.10 ZONE - 1 (3 Twin Villas) |  | 348 | 348 | 0% | 2013-02-23 | 2014-04-12 | 2013-02-23 | 2014-04-12 | 54 |  |  |  | 0 | 0
DHBL.K30.L35.10 .10 STRUCTURAL WORKS |  | 163 | 163 | 0% | 2013-02-23 | 2013-09-03 | 2013-02-23 | 2013-09-03 | 30 |  |  |  | 0 | 0
DHBL.K30.L35.10 .10 .10 SUB STRUCTURE |  | 110 | 110 | 0% | 2013-02-23 | 2013-06-30 | 2013-02-23 | 2013-06-30 | 0 |  |  |  | 0 | 0
DHBL.K30.L35.10 .10 .10 .10 UPTO GRADE SLAB |  | 110 | 110 | 0% | 2013-02-23 | 2013-06-30 | 2013-02-23 | 2013-06-30 | 0 |  |  |  | 0 | 0
DUKHCONP2AZ1STUG1035 | Backfilling Upto Grade Beam Bottom | 20 | 20 | 0% | 2013-04-23 | 2013-05-15 | 2013-04-23 | 2013-05-15 | 0 | Yes | DUKHCONP2AZ1STUG1030, DUKHCONP2AZ1STUG1030 | DUKHCONP2AZ1STUG1040, DUKHCONP2AZ1STUG1040, DUKHCONP2AZ2STUG1035 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-03-24 | 2013-04-15 | 2013-03-24 | 2013-04-15 | 0 | Yes | DUKHMOBP020000004080, DUKHCONP2AZ1STUG1015, DUKHMOBP020000004060, DUKHMOBP020000004090, DUKHCONP2AZ1STUG1015, DUKHMOBP020000004070 | DUKHCONP2AZ1STUG1025, DUKHCONP2AZ2STUG1020, DUKHCONP2AZ1STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-05-05 | 2013-06-02 | 2013-05-05 | 2013-06-02 | 0 | Yes | DUKHENGP2ADWSTAP4810, DUKHCONP2AZ1STUG1035, DUKHCONP2AZ1STUG1035 | DUKHCONP2AZ1PLUG4300, DUKHCONP2AZ1PLUG4300, DUKHCONP2AZ2STUG1040, DUKHCONP2AZ1STUG1045, DUKHCONP2AZ1STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1025 | Construction of neck of columns | 20 | 20 | 0% | 2013-04-02 | 2013-04-24 | 2013-04-02 | 2013-04-24 | 0 | Yes | DUKHCONP2AZ1STUG1020, DUKHCONP2AZ1STUG1020 | DUKHCONP2AZ1STUG1030, DUKHCONP2AZ1STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-06-02 | 2013-06-30 | 2013-06-02 | 2013-06-30 | 0 | Yes | DUKHCONP2AZ1PLUG4300, DUKHCONP2AZ1PLUG4300, DUKHCONP2AZ1STUG1040, DUKHENGP2ADWSTAP4810, DUKHCONP2AZ1STUG1040 | DUKHCONP2AZ1STGF2000, DUKHCONP2AZ1STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1005 | Footing Antitermite | 20 | 20 | 0% | 2013-03-06 | 2013-03-28 | 2013-03-06 | 2013-03-28 | 0 | Yes | DUKHCONP2AZ1STUG1000, DUKHCONP2AZ1STUG1000 | DUKHCONP2AZ1STUG1010, DUKHCONP2AZ1STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1010 | Footing Blinding | 20 | 20 | 0% | 2013-03-09 | 2013-03-31 | 2013-03-09 | 2013-03-31 | 0 | Yes | DUKHCONP2AZ1STUG1005, DUKHCONP2AZ1STUG1005 | DUKHCONP2AZ1STUG1015, DUKHCONP2AZ1STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-02-23 | 2013-03-23 | 2013-02-23 | 2013-03-23 | 0 | Yes | DUKHMOBP020000004050, DUKHCONP2AGNSP005000, DUKHCONP2AGNSP002500 | DUKHCONP2AZ2STUG1000, DUKHCONP2AZ1STUG1005, DUKHCONP2AZ1STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1015 | Footing Waterproofing & Screed | 20 | 20 | 0% | 2013-03-12 | 2013-04-03 | 2013-03-12 | 2013-04-03 | 0 | Yes | DUKHENGP2ADWSTAP4800, DUKHCONP2AZ1STUG1010, DUKHPROGEN00PRDV3020, DUKHCONP2AZ1STUG1010 | DUKHCONP2AZ1STUG1020, DUKHCONP2AZ1STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ1STUG1030 | Waterproofing Footing & Neck Column | 20 | 20 | 0% | 2013-04-11 | 2013-05-04 | 2013-04-11 | 2013-05-04 | 0 | Yes | DUKHCONP2AZ1STUG1025, DUKHCONP2AZ1STUG1025 | DUKHCONP2AZ1STUG1035, DUKHCONP2AZ1STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L35.10 .10 .15 SUPERSTRUCTURE |  | 63 | 63 | 0% | 2013-06-19 | 2013-09-03 | 2013-06-19 | 2013-09-03 | 30 |  |  |  | 0 | 0
DHBL.K30.L35.10 .10 .15 .10 GROUND FLOOR |  | 45 | 45 | 0% | 2013-06-19 | 2013-08-13 | 2013-06-19 | 2013-08-13 | 0 |  |  |  | 0 | 0
DUKHCONP2AZ1STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-07-24 | 2013-08-13 | 2013-07-24 | 2013-08-13 | 0 | Yes | DUKHCONP2AZ1STGF2010, DUKHCONP2AZ1STGF2010 | DUKHCONP2AZ2STGF2015, DUKHCONP2AZ1STRF2060, DUKHCONP2AMKARGF3000, DUKHCONP2AZ1ARGF3000, DUKHCONP2AZ1ARGF3000, DUKHCONP2AZ1STRF2060 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-07-08 | 2013-08-05 | 2013-07-08 | 2013-08-05 | 0 | Yes | DUKHCONP2AZ1STGF2005, DUKHCONP2AZ1STGF2005, DUKHENGP2ADWSTAP4830 | DUKHCONP2AZ1WEEX5030, DUKHCONP2AZ1STGF2015, DUKHCONP2AZ1STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1STGF2005 | Column-Concrete | 15 | 15 | 0% | 2013-06-30 | 2013-07-16 | 2013-06-30 | 2013-07-16 | 0 | Yes | DUKHCONP2AZ1STGF2000, DUKHCONP2AZ1STGF2000 | DUKHCONP2AZ1STGF2010, DUKHCONP2AZ1STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1STGF2000 | Column-Rebar & Formwork | 20 | 20 | 0% | 2013-06-19 | 2013-07-11 | 2013-06-19 | 2013-07-11 | 0 | Yes | DUKHCONP2AZ1STUG1045, DUKHENGP2ADWSTAP4820, DUKHCONP2AZ1STUG1045 | DUKHCONP2AZ1STGF2005, DUKHCONP2AZ2STGF2000, DUKHCONP2AZ1STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.10 .10 .15 .20 ROOF |  | 26 | 26 | 0% | 2013-08-01 | 2013-09-03 | 2013-08-01 | 2013-09-03 | 30 |  |  |  | 0 | 0
DUKHCONP2AZ1STRF2060 | Construction of Parapets | 20 | 20 | 0% | 2013-08-01 | 2013-08-27 | 2013-08-01 | 2013-08-27 | 0 | Yes | DUKHCONP2AZ1STGF2015, DUKHCONP2AZ1STGF2015 | DUKHCONP2AZ1ARRF3625, DUKHCONP2AZ1STRF2065, DUKHCONP2AZ1ARRF3625, DUKHCONI2AZ1DRGL5115, DUKHCONP2AZ2STRF2060, DUKHCONP2AMKARRF3625, DUKHCONP2AMKAREL3665, DUKHCONP2AZ1STRF2065 | 0 | 0 | ROOF
DUKHCONP2AZ1STRF2065 | Construction of up stands/Plinth | 20 | 20 | 0% | 2013-08-08 | 2013-09-03 | 2013-08-08 | 2013-09-03 | 30 | No | DUKHCONP2AZ1STRF2060, DUKHCONP2AZ1STRF2060 | DUKHCONP2AZ1MSEX5020, DUKHCONP2AZ1MSEX5000, DUKHCONP2AZ1ARRF3625, DUKHCONP2AZ1MSEX5020, DUKHCONP2AZ1AREL3665, DUKHCONP2AZ1ARRF3625, DUKHCONP2AZ1MSEX5000, DUKHCONP2AMKARRF3625, DUKHCONP2AZ1AREL3665 | 0 | 0 | ROOF
DHBL.K30.L35.10 .15 FINISHING WORKS |  | 163 | 163 | 0% | 2013-08-26 | 2014-03-08 | 2013-08-26 | 2014-03-08 | 34 |  |  |  | 0 | 0
DHBL.K30.L35.10 .15 .10 INTERNAL FINISHES |  | 161 | 161 | 0% | 2013-08-28 | 2014-03-08 | 2013-08-28 | 2014-03-08 | 34 |  |  |  | 0 | 0
DHBL.K30.L35.10 .15 .10 .10 GROUND FLOOR |  | 161 | 161 | 0% | 2013-08-28 | 2014-03-08 | 2013-08-28 | 2014-03-08 | 34 |  |  |  | 0 | 0
DUKHCONP2AZ1ARGF3080 | Aluminum windows | 18 | 18 | 0% | 2014-01-16 | 2014-02-05 | 2014-01-16 | 2014-02-05 | 44 | No | DUKHCONP2AMKARGF3080, DUKHCONP2AZ1ARGF3065 | DUKHCONP2AZ2ARGF3080, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3000 | Block work | 25 | 25 | 0% | 2013-08-28 | 2013-09-25 | 2013-08-28 | 2013-09-25 | 6 | No | DUKHCONP2AMKARGF3000, DUKHCONP2AZ1STGF2015, DUKHCONP2AZ1STGF2015 | DUKHCONP2AZ1ARGF3005, DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1ELGF4000, DUKHCONP2AZ2ARGF3000, DUKHCONP2AZ1ARGF3005, DUKHCONP2AZ1ELGF4000, DUKHCONP2AZ1PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3075 | Carpentry & Joinery Works | 18 | 18 | 0% | 2014-01-05 | 2014-01-25 | 2014-01-05 | 2014-01-25 | 10 | No | DUKHCONP2AZ1ARGF3065, DUKHCONP2AMKARGF3075, DUKHCONP2AZ1ARGF3065 | DUKHCONP2AZ1ARGF3090, DUKHCONP2AZ2ARGF3075, DUKHCONP2AZ1ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3020 | Ceramic Wall Tiling | 15 | 15 | 0% | 2013-10-23 | 2013-11-09 | 2013-10-23 | 2013-11-09 | 7 | No | DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1ARGF3015, DUKHCONP2AZ1PLGF4310, DUKHCONP2AMKARGF3020, DUKHCONP2AZ1ARGF3015, DUKHCONP2AZ1PLGF4305 | DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2013-12-15 | 2014-01-01 | 2013-12-15 | 2014-01-01 | 31 | No | DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ARGF3010, DUKHCONP2AZ1ARGF3010, DUKHCONP2AZ1ARGF3035, DUKHCONP2AMKARGF3040 | DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ2ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-02-06 | 2014-03-08 | 2014-02-06 | 2014-03-08 | 34 | No | DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ1ARGF3065, DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ1ARGF3080, DUKHCONP2AZ1ARGF3090, DUKHCONP2AZ1ARGF3030, DUKHCONP2AZ1ARGF3080, DUKHCONP2AZ1ACGF4610, DUKHCONP2AZ1ARGF3090, DUKHCONP2AZ1ARGF3030, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ1ARGF3060, DUKHCONP2AMKARGF3095, DUKHCONP2AZ1ACGF4610 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3045 | Fixing of Suspension systems | 15 | 15 | 0% | 2013-12-01 | 2013-12-17 | 2013-12-01 | 2013-12-17 | 7 | No | DUKHCONP2AZ1ARGF3030, DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ELGF4010, DUKHCONP2AZ1ELGF4010, DUKHCONP2AZ1ARGF3030, DUKHCONP2AZ1ARGF3025, DUKHCONP2AMKARGF3045 | DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3010 | Flooring screed | 20 | 20 | 0% | 2013-09-30 | 2013-10-24 | 2013-09-30 | 2013-10-24 | 25 | No | DUKHCONP2AZ1ARGF3005, DUKHCONP2AMKARGF3010, DUKHCONP2AZ1ARGF3005 | DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ1ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3060 | Gypsum board false ceiling | 20 | 20 | 0% | 2013-12-17 | 2014-01-09 | 2013-12-17 | 2014-01-09 | 7 | No | DUKHCONP2AMKARGF3060, DUKHCONP2AZ1ARGF3045, DUKHCONP2AZ1ARGF3045, DUKHCONP2AZ1ACGF4600, DUKHCONP2AZ1ACGF4600 | DUKHCONP2AZ1PLGF4320, DUKHCONP2AZ1ELGF4025, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ1ELGF4015, DUKHCONP2AZ1ELGF4025, DUKHCONP2AZ1PLGF4320, DUKHCONP2AZ1ACGF4605, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ1ARGF3065, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ELGF4015, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ1ACGF4605, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-01-15 | 2014-02-01 | 2014-01-15 | 2014-02-01 | 13 | No | DUKHCONP2AZ1ARGF3075, DUKHCONP2AMKARGF3090, DUKHCONP2AZ1ARGF3075 | DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ2ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3030 | Paint First coat | 20 | 20 | 0% | 2013-10-06 | 2013-10-30 | 2013-10-06 | 2013-10-30 | 6 | No | DUKHCONP2AZ1ARGF3005, DUKHCONP2AZ1ARGF3005, DUKHCONP2AMKARGF3030 | DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3045, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ2ARGF3030, DUKHCONP2AZ1ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-09-18 | 2013-10-16 | 2013-09-18 | 2013-10-16 | 6 | No | DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1ARGF3000, DUKHCONP2AMKARGF3005, DUKHCONP2AZ1ELGF4000, DUKHCONP2AZ1ELGF4000, DUKHCONP2AZ1ARGF3000, DUKHCONP2AZ1PLGF4305 | DUKHCONP2AZ1ACGF4600, DUKHCONP2AZ1ARGF3030, DUKHCONP2AZ1ARGF3010, DUKHCONP2AZ1ARGF3015, DUKHCONP2AZ1ARGF3030, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ1ARGF3010, DUKHCONP2AZ1ARGF3015, DUKHCONP2AZ1ACGF4600 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3025 | Porcelain Tile flooring | 20 | 20 | 0% | 2013-11-09 | 2013-12-01 | 2013-11-09 | 2013-12-01 | 7 | No | DUKHCONP2AZ1ARGF3010, DUKHCONP2AZ1ARGF3020, DUKHCONP2AZ1ARGF3020, DUKHCONP2AMKARGF3025, DUKHCONP2AZ1ARGF3010 | DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ1ARGF3045, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ1ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3035 | Slate Tile Flooring & Skirting | 18 | 18 | 0% | 2013-11-26 | 2013-12-16 | 2013-11-26 | 2013-12-16 | 15 | No | DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ1ARGF3010, DUKHCONP2AZ1ARGF3010, DUKHCONP2AMKARGF3035 | DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3065, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ1ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3015 | Wet area waterproofing & Protection Screed | 20 | 20 | 0% | 2013-10-02 | 2013-10-27 | 2013-10-02 | 2013-10-27 | 7 | No | DUKHCONP2AZ1ARGF3005, DUKHCONP2AMKARGF3015, DUKHCONP2AZ1ARGF3005 | DUKHCONP2AZ1ARGF3020, DUKHCONP2AZ1ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ARGF3065 | Wooden door | 15 | 15 | 0% | 2013-12-30 | 2014-01-15 | 2013-12-30 | 2014-01-15 | 7 | No | DUKHCONP2AMKARGF3065, DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ARGF3035 | DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3075, DUKHCONP2AZ1PLGF4315, DUKHCONP2AZ1ARGF3080, DUKHCONP2AZ1PLGF4315, DUKHCONP2AZ1ARGF3075 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.10 .15 .15 EXTERNAL FINISHES |  | 77 | 77 | 0% | 2013-08-26 | 2013-11-25 | 2013-08-26 | 2013-11-25 | 65 |  |  |  | 0 | 0
DHBL.K30.L35.10 .15 .15 .10 ROOF |  | 53 | 53 | 0% | 2013-08-26 | 2013-10-28 | 2013-08-26 | 2013-10-28 | 79 |  |  |  | 0 | 0
DUKHCONP2AZ1ARRF3660 | Installation of Access Ladder | 20 | 20 | 0% | 2013-10-03 | 2013-10-28 | 2013-10-03 | 2013-10-28 | 79 | No | DUKHCONP2AMKARRF3660, DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1ARRF3645 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1AREL3680, DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ2ARRF3660, DUKHCONP2AZ1ACTC8000 | 0 | 0 | ROOF
DUKHCONP2AZ1ARRF3640 | Installation of Insulation & Protection | 18 | 18 | 0% | 2013-09-19 | 2013-10-09 | 2013-09-19 | 2013-10-09 | 35 | No | DUKHCONP2AZ1ARRF3635, DUKHCONP2AZ1ARRF3635, DUKHCONP2AMKARRF3640 | DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1ARRF3645 | 0 | 0 | ROOF
DUKHCONP2AZ1ARRF3625 | Laying of Pitched Roof | 25 | 25 | 0% | 2013-08-26 | 2013-09-23 | 2013-08-26 | 2013-09-23 | 30 | No | DUKHCONP2AZ1STRF2060, DUKHCONP2AZ1STRF2060, DUKHCONP2AZ1STRF2065, DUKHCONP2AMKARRF3625, DUKHCONP2AZ1STRF2065, DUKHPROGEN00PRDV3140 | DUKHCONP2AZ1ARRF3630, DUKHCONP2AZ1ARRF3630 | 0 | 0 | ROOF
DUKHCONP2AZ1ARRF3635 | Laying of Waterproofing Membrane | 18 | 18 | 0% | 2013-09-15 | 2013-10-05 | 2013-09-15 | 2013-10-05 | 35 | No | DUKHCONP2AMKARRF3635, DUKHCONP2AZ1ARRF3630, DUKHPROGEN00PRDV3050, DUKHCONP2AZ1ARRF3630 | DUKHCONP2AZ1ARRF3640, DUKHCONP2AZ1ARRF3640 | 0 | 0 | ROOF
DUKHCONP2AZ1ARRF3630 | Leveling Screed for Waterproofing | 18 | 18 | 0% | 2013-09-09 | 2013-09-29 | 2013-09-09 | 2013-09-29 | 30 | No | DUKHCONP2AZ1ARRF3625, DUKHCONP2AMKARRF3630, DUKHCONP2AZ1ARRF3625 | DUKHCONP2AZ1ARRF3635, DUKHCONP2AZ1ARRF3635, DUKHCONP2AZ2ARRF3625 | 0 | 0 | ROOF
DUKHCONP2AZ1ARRF3645 | Lime Stone Chips & Paving slab Installation | 18 | 18 | 0% | 2013-09-28 | 2013-10-20 | 2013-09-28 | 2013-10-20 | 35 | No | DUKHCONP2AZ1ARRF3640, DUKHCONP2AZ1ARRF3640, DUKHCONP2AMKARRF3645 | DUKHCONP2AZ1ACRF4630, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ2ARRF3640, DUKHCONP2AZ1ELRF4070, DUKHCONP2AZ1AREL3665, DUKHCONP2AZ1ARRF3660, DUKHCONP2AZ1ACRF4630, DUKHCONP2AZ1ELRF4070, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1ARRF3660, DUKHCONP2AZ1AREL3665 | 0 | 0 | ROOF
DHBL.K30.L35.10 .15 .15 .15 ELEVATION |  | 39 | 39 | 0% | 2013-10-09 | 2013-11-25 | 2013-10-09 | 2013-11-25 | 65 |  |  |  | 0 | 0
DUKHCONP2AZ1AREL3680 | External Painting | 20 | 20 | 0% | 2013-11-03 | 2013-11-25 | 2013-11-03 | 2013-11-25 | 65 | No | DUKHCONP2AZ1AREL3665, DUKHCONP2AZ1ARRF3660, DUKHCONP2AMKAREL3680, DUKHCONP2AZ1AREL3665 | DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ2AREL3680 | 0 | 0 | ELEVATION
DUKHCONP2AZ1AREL3665 | External Plastering | 25 | 25 | 0% | 2013-10-09 | 2013-11-09 | 2013-10-09 | 2013-11-09 | 35 | No | DUKHCONP2AZ1STRF2065, DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1STRF2065, DUKHCONP2AMKAREL3665 | DUKHCONP2AZ1AREL3680, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ2AREL3665, DUKHCONP2AZ1AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L35.10 .20 MEP WORKS |  | 236 | 236 | 0% | 2013-05-23 | 2014-03-02 | 2013-05-23 | 2014-03-02 | 49 |  |  |  | 0 | 0
DHBL.K30.L35.10 .20 .10 ELECTRICAL WORKS |  | 140 | 140 | 0% | 2013-09-11 | 2014-02-25 | 2013-09-11 | 2014-02-25 | 48 |  |  |  | 0 | 0
DHBL.K30.L35.10 .20 .10 .10 GROUND FLOOR |  | 118 | 118 | 0% | 2013-09-11 | 2014-01-29 | 2013-09-11 | 2014-01-29 | 51 |  |  |  | 0 | 0
DUKHCONP2AZ1ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-09-19 | 2013-10-12 | 2013-09-19 | 2013-10-12 | 13 | No | DUKHCONP2AZ1ELGF4000, DUKHCONP2AMKELGF4005, DUKHCONP2AZ1ELGF4000 | DUKHCONP2AZ1ELGF4010, DUKHCONP2AZ2ELGF4005, DUKHCONP2AZ1ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ELGF4000 | Fixing of wall conduits & switch socket boxes | 20 | 20 | 0% | 2013-09-11 | 2013-10-03 | 2013-09-11 | 2013-10-03 | 7 | No | DUKHCONP2AZ1ARGF3000, DUKHCONP2AMKELGF4000, DUKHCONP2AZ1ARGF3000 | DUKHCONP2AZ1ELGF4005, DUKHCONP2AZ1ARGF3005, DUKHCONP2AZ1ARGF3005, DUKHCONP2AZ1ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 20 | 20 | 0% | 2014-01-04 | 2014-01-26 | 2014-01-04 | 2014-01-26 | 13 | No | DUKHCONP2AZ1ARGF3060, DUKHCONP2AMKELGF4015, DUKHCONP2AZ1ARGF3060 | DUKHCONP2AZ2ELGF4015, DUKHCONP2AZ1ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2013-12-26 | 2014-01-18 | 2013-12-26 | 2014-01-18 | 48 | No | DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ELGF4010, DUKHCONP2AZ1ELGF4010, DUKHCONP2AZ1ARGF3060, DUKHCONP2AMKELGF4020 | DUKHCONP2AZ1ELGF4025, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ1ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ELGF4025 | Installation of Lighting fixtures & Accessories | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 48 | No | DUKHCONP2AZ1ARGF3060, DUKHCONP2AMKELGF4025, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ELGF4020 | DUKHCONP2AZ1ELRF4070, DUKHCONP2AZ1ELRF4070, DUKHCONP2AZ1ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 51 | No | DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1MSEX5010, DUKHCONP2AMKELGF4030 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ2ELGF4030, DUKHCONP2AZ1ELRF4070, DUKHCONP2AZ1ELRF4070 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ELGF4010 | Installation of wiring & Main Cabling | 20 | 20 | 0% | 2013-09-28 | 2013-10-22 | 2013-09-28 | 2013-10-22 | 41 | No | DUKHCONP2AZ1ELGF4005, DUKHCONP2AZ1ELGF4005, DUKHCONP2AMKELGF4010 | DUKHCONP2AZ1ELRF4070, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ1ARGF3045, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ1ARGF3045, DUKHCONP2AZ1ELRF4070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.10 .20 .10 .20 ROOF |  | 30 | 30 | 0% | 2014-01-21 | 2014-02-25 | 2014-01-21 | 2014-02-25 | 48 |  |  |  | 0 | 0
DUKHCONP2AZ1ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-01-21 | 2014-02-10 | 2014-01-21 | 2014-02-10 | 48 | No | DUKHCONP2AZ1ELGF4010, DUKHCONP2AZ1ELGF4025, DUKHCONP2AZ1ELGF4025, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ1ARRF3645, DUKHCONP2AMKELRF4070, DUKHCONP2AZ1ELGF4010 | DUKHCONP2AZ1ELRF4075, DUKHCONP2AZ1ELRF4075 | 0 | 0 | ROOF
DUKHCONP2AZ1ELRF4075 | Installation of TV Dish Antenna | 20 | 20 | 0% | 2014-02-02 | 2014-02-25 | 2014-02-02 | 2014-02-25 | 48 | No | DUKHCONP2AMKELRF4075, DUKHCONP2AZ1ELRF4070, DUKHCONP2AZ1ELRF4070 | DUKHCONP2AZ2ELRF4075, DUKHCONP2AZ1ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L35.10 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 223 | 223 | 0% | 2013-05-23 | 2014-02-15 | 2013-05-23 | 2014-02-15 | 62 |  |  |  | 0 | 0
DHBL.K30.L35.10 .20 .15 .10 GROUND FLOOR |  | 223 | 223 | 0% | 2013-05-23 | 2014-02-15 | 2013-05-23 | 2014-02-15 | 62 |  |  |  | 0 | 0
DUKHCONP2AZ1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-05-23 | 2013-06-15 | 2013-05-23 | 2013-06-15 | 0 | Yes | DUKHCONP2AZ1STUG1040, DUKHCONP2AZ1STUG1040, DUKHPROGEN00PRDV3060, DUKHPROGEN00PRDV3070 | DUKHCONP2AZ1STUG1045, DUKHCONP2AZ1STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-09-15 | 2013-10-05 | 2013-09-15 | 2013-10-05 | 30 | No | DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1ARGF3000, DUKHCONP2AMKPLGF4310, DUKHCONP2AZ1ARGF3000 | DUKHCONP2AZ1MSEX5000, DUKHCONP2AZ1ARGF3020, DUKHCONP2AZ1ARGF3020, DUKHCONP2AZ1MSEX5000, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1PLGF4315, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1PLGF4315, DUKHCONP2AZ2PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1PLGF4305 | Installation of Plumbing pipes & testing | 20 | 20 | 0% | 2013-09-12 | 2013-10-05 | 2013-09-12 | 2013-10-05 | 6 | No | DUKHCONP2AZ1ARGF3000, DUKHCONP2AZ1ARGF3000, DUKHCONP2AMKPLGF4305 | DUKHCONP2AZ1ARGF3020, DUKHCONP2AZ1ARGF3005, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1ARGF3020, DUKHCONP2AZ1ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-01-28 | 2014-02-15 | 2014-01-28 | 2014-02-15 | 62 | No | DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1PLGF4315, DUKHCONP2AMKPLGF4320 | DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ2PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-01-05 | 2014-01-27 | 2014-01-05 | 2014-01-27 | 7 | No | DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1ARGF3065, DUKHCONP2AMKPLGF4315, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1ARGF3065 | DUKHCONP2AZ1PLGF4320, DUKHCONP2AZ2PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.10 .20 .15 .20 ROOF |  | 15 | 15 | 0% | 2013-12-05 | 2013-12-23 | 2013-12-05 | 2013-12-23 | 15 |  |  |  | 0 | 0
DUKHCONP2AZ1PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2013-12-05 | 2013-12-23 | 2013-12-05 | 2013-12-23 | 15 | No | DUKHCONP2AZ1AREL3665, DUKHCONP2AZ1AREL3665, DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1PLGF4305, DUKHCONP2AZ1PLGF4310, DUKHCONP2AMKPLRF4350, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1ARRF3645 | DUKHCONP2AZ1WEEX5065, DUKHCONP2AZ1WEEX5065, DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ2PLRF4350 | 0 | 0 | ROOF
DHBL.K30.L35.10 .20 .20 AC WORKS |  | 126 | 126 | 0% | 2013-10-02 | 2014-03-02 | 2013-10-02 | 2014-03-02 | 39 |  |  |  | 0 | 0
DHBL.K30.L35.10 .20 .20 .10 GROUND FLOOR |  | 116 | 116 | 0% | 2013-10-02 | 2014-02-18 | 2013-10-02 | 2014-02-18 | 34 |  |  |  | 0 | 0
DUKHCONP2AZ1ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-01-26 | 2014-02-18 | 2014-01-26 | 2014-02-18 | 34 | No | DUKHCONP2AZ1ACGF4605, DUKHCONP2AMKACGF4610, DUKHCONP2AZ1ACGF4605 | DUKHCONP2AZ1ACRF4635, DUKHCONP2AZ1ACRF4635, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-04 | 2014-02-01 | 2014-01-04 | 2014-02-01 | 34 | No | DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ACGF4600, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ACGF4600, DUKHCONP2AMKACGF4605 | DUKHCONP2AZ1ACGF4610, DUKHCONP2AZ1ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ1ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-10-02 | 2013-10-27 | 2013-10-02 | 2013-10-27 | 28 | No | DUKHCONP2AZ1ARGF3005, DUKHCONP2AMKACGF4600, DUKHCONP2AZ1ARGF3005 | DUKHCONP2AZ1ACRF4630, DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ1ACGF4605, DUKHCONP2AZ1ARGF3060, DUKHCONP2AZ1ACRF4630, DUKHCONP2AZ1ACGF4605, DUKHCONP2AZ1ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.10 .20 .20 .20 ROOF |  | 112 | 112 | 0% | 2013-10-21 | 2014-03-02 | 2013-10-21 | 2014-03-02 | 39 |  |  |  | 0 | 0
DUKHCONP2AZ1ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 39 | No | DUKHCONP2AZ1ACGF4610, DUKHCONP2AZ1ACGF4610, DUKHCONP2AZ1ACRF4630, DUKHCONP2AMKACRF4635, DUKHCONP2AZ1ACRF4630 | DUKHCONP2AZ2ACRF4635, DUKHCONP2AZ1ACTC8000 | 0 | 0 | ROOF
DUKHCONP2AZ1ACRF4630 | Installation of Refrigerant Pipes | 20 | 20 | 0% | 2013-10-21 | 2013-11-12 | 2013-10-21 | 2013-11-12 | 66 | No | DUKHCONP2AZ1ACGF4600, DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1ARRF3645, DUKHCONP2AZ1ACGF4600, DUKHCONP2AMKACRF4630 | DUKHCONP2AZ1ACRF4635, DUKHCONP2AZ2ACRF4630, DUKHCONP2AZ1ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L35.10 .25 EXTERNAL WORKS |  | 171 | 171 | 0% | 2013-09-21 | 2014-04-12 | 2013-09-21 | 2014-04-12 | 29 |  |  |  | 0 | 0
DHBL.K30.L35.10 .25 .10 MISCELLANEOUS |  | 171 | 171 | 0% | 2013-09-21 | 2014-04-12 | 2013-09-21 | 2014-04-12 | 29 |  |  |  | 0 | 0
DUKHCONP2AZ1MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 29 | No | DUKHCONI2AZ1BWGL5325 | DUKHCONP2AZ2MSEX5335 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ1MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-10-13 | 2013-11-12 | 2013-10-13 | 2013-11-12 | 42 | No | DUKHCONP2AMKMSEX5005, DUKHCONP2AZ1MSEX5000, DUKHCONP2AZ1MSEX5000 | DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1MSEX5015, DUKHCONP2AZ1MSEX5015, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLTC8005 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ1MSEX5020 | Construction Entrance Ramp | 20 | 20 | 0% | 2013-09-21 | 2013-10-13 | 2013-09-21 | 2013-10-13 | 30 | No | DUKHCONP2AZ1STRF2065, DUKHCONP2AZ1STRF2065, DUKHCONP2AMKMSEX5020 | DUKHCONP2AZ1MSEX5025, DUKHCONP2AZ1MSEX5055, DUKHMOBP2APS00002170, DUKHCONP2AZ1MSEX5025, DUKHCONP2AZ2MSEX5020, DUKHCONP2AZ1HDEX5090, DUKHCONP2AZ1HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ1MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2013-11-04 | 2013-11-26 | 2013-11-04 | 2013-11-26 | 42 | No | DUKHCONP2AZ1MSEX5005, DUKHCONP2AMKMSEX5015, DUKHCONP2AZ1MSEX5005 | DUKHCONP2AZ1WEEX5065, DUKHCONP2AZ1WEEX5065, DUKHCONP2AZ1MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ1MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-09-29 | 2013-10-29 | 2013-09-29 | 2013-10-29 | 42 | No | DUKHCONP2AZ1STRF2065, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ1STRF2065, DUKHCONP2AMKMSEX5000 | DUKHCONP2AZ1MSEX5005, DUKHCONP2AZ2MSEX5000, DUKHCONP2AZ1MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ1MSEX5055 | Installation Steel Door | 20 | 20 | 0% | 2013-09-26 | 2013-10-21 | 2013-09-26 | 2013-10-21 | 35 | No | DUKHCONP2AZ1MSEX5020 | DUKHCONP2AZ1MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ1MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2013-10-08 | 2013-11-02 | 2013-10-08 | 2013-11-02 | 35 | No | DUKHCONP2AZ1MSEX5020, DUKHCONP2AMKMSEX5025, DUKHCONP2AZ1MSEX5020, DUKHCONP2AZ1MSEX5055 | DUKHCONP2AZ1WEEX5050, DUKHCONP2AZ1WEEX5050, DUKHCONP2AZ1HDEX5090, DUKHCONP2AZ2MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ1MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2013-11-27 | 2013-12-26 | 2013-11-27 | 2013-12-26 | 60 | No | DUKHCONP2AZ1MSEX5015 | DUKHCONP2AZ1ELGF4030 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L35.10 .25 .15 WATER TANK ENCLOSURE |  | 97 | 97 | 0% | 2013-09-24 | 2014-01-18 | 2013-09-24 | 2014-01-18 | 20 |  |  |  | 0 | 0
DUKHCONP2AZ1WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2013-10-12 | 2013-11-11 | 2013-10-12 | 2013-11-11 | 25 | No | DUKHCONP2AZ1WEEX5035, DUKHCONP2AZ1WEEX5035, DUKHCONP2AMKWEEX5040 | DUKHCONP2AZ1WEEX5045, DUKHCONP2AZ1WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ1WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2013-10-02 | 2013-11-02 | 2013-10-02 | 2013-11-02 | 25 | No | DUKHCONP2AZ1WEEX5030, DUKHCONP2AZ1WEEX5030, DUKHCONP2AMKWEEX5035 | DUKHCONP2AZ1WEEX5040, DUKHCONP2AZ1WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ1WEEX5030 | Excavation | 20 | 20 | 0% | 2013-09-24 | 2013-10-16 | 2013-09-24 | 2013-10-16 | 15 | No | DUKHCONP2AMKWEEX5030, DUKHCONP2AZ1STGF2010 | DUKHCONP2AZ1WEEX5035, DUKHCONP2AZ1WEEX5035, DUKHCONP2AZ2WEEX5030 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ1WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 25 | No | DUKHCONP2AZ1WEEX5040, DUKHCONP2AZ1WEEX5040, DUKHCONP2AMKWEEX5045 | DUKHCONP2AZ1WEEX5050, DUKHCONP2AZ1WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ1WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 10 | No | DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1MSEX5015, DUKHCONP2AZ1WEEX5060, DUKHCONP2AZ1MSEX5015, DUKHCONP2AZ1WEEX5060, DUKHCONP2AMKWEEX5065 | DUKHCONP2AZ2WEEX5065, DUKHCONP2AZ1WEEX5070, DUKHCONP2AZ1PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ1WEEX5070 | Installation ladder for water Tank | 20 | 20 | 0% | 2013-12-26 | 2014-01-18 | 2013-12-26 | 2014-01-18 | 20 | No | DUKHCONP2AZ1WEEX5065 | DUKHCONP2AZ2WEEX5070 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ1WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2013-11-12 | 2013-12-04 | 2013-11-12 | 2013-12-04 | 25 | No | DUKHCONP2AZ1MSEX5025, DUKHCONP2AZ1MSEX5025, DUKHCONP2AMKWEEX5050, DUKHCONP2AZ1WEEX5045, DUKHCONP2AZ1WEEX5045 | DUKHCONP2AZ1WEEX5060, DUKHCONP2AZ1WEEX5060, DUKHCONP2AZ2WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ1WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2013-11-18 | 2013-12-16 | 2013-11-18 | 2013-12-16 | 25 | No | DUKHCONP2AZ1WEEX5050, DUKHCONP2AZ1WEEX5050, DUKHCONP2AMKWEEX5060 | DUKHCONP2AZ1WEEX5065, DUKHCONP2AZ1WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L35.10 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2013-10-16 | 2013-12-07 | 2013-10-16 | 2013-12-07 | 35 |  |  |  | 0 | 0
DUKHCONP2AZ1HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2013-10-30 | 2013-11-21 | 2013-10-30 | 2013-11-21 | 35 | No | DUKHCONP2AZ1HDEX5090, DUKHCONP2AZ1HDEX5090, DUKHCONP2AMKHDEX5095 | DUKHCONP2AZ1HDEX5100, DUKHCONP2AZ1HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2AZ1HDEX5100 | Interlock works | 20 | 20 | 0% | 2013-11-14 | 2013-12-07 | 2013-11-14 | 2013-12-07 | 35 | No | DUKHCONP2AZ1HDEX5095, DUKHCONP2AZ1HDEX5095, DUKHCONP2AMKHDEX5100 | DUKHCONP2AZ1SLEX5105, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1SLEX5105, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2AZ1HDEX5090 | kerb works | 20 | 20 | 0% | 2013-10-16 | 2013-11-10 | 2013-10-16 | 2013-11-10 | 35 | No | DUKHCONP2AMKHDEX5090, DUKHCONP2AZ1MSEX5025, DUKHCONP2AZ1MSEX5020, DUKHCONP2AZ1MSEX5020 | DUKHCONP2AZ1HDEX5095, DUKHCONP2AZ1HDEX5095, DUKHCONP2AZ2HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L35.10 .25 .25 SOFT LANDSCAPING |  | 30 | 30 | 0% | 2013-12-12 | 2014-01-16 | 2013-12-12 | 2014-01-16 | 61 |  |  |  | 0 | 0
DUKHCONP2AZ1SLEX5105 | Laying of Grass/ green area | 20 | 20 | 0% | 2013-12-12 | 2014-01-05 | 2013-12-12 | 2014-01-05 | 21 | No | DUKHCONP2AZ1HDEX5100, DUKHCONP2AZ1HDEX5100, DUKHCONP2AMKSLEX5105 | DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ1PLTC8005, DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1SLEX5110, DUKHCONP2AZ2SLEX5105, DUKHCONP2AZ1SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP2AZ1SLEX5110 | Laying of Palm tree | 20 | 20 | 0% | 2013-12-25 | 2014-01-16 | 2013-12-25 | 2014-01-16 | 61 | No | DUKHCONP2AZ1SLEX5105, DUKHCONP2AZ1SLEX5105, DUKHCONP2AMKSLEX5110 | DUKHCONP2AZ1ACTC8000, DUKHCONP2AZ1ELTC8010, DUKHCONP2AZ2SLEX5110, DUKHCONP2AZ1PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L35.10 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 59 |  |  |  | 0 | 0
DUKHCONP2AZ1ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 59 | No | DUKHCONP2AZ1MSEX5005, DUKHCONP2AZ1SLEX5110, DUKHCONP2AMKPLGF4320, DUKHCONP2AMKMSEX5005, DUKHCONP2AZ1HDEX5100, DUKHCONP2AMKWEEX5065, DUKHCONP2AMKAREL3680, DUKHCONP2AZ1AREL3680, DUKHCONP2AMKARGF3095, DUKHCONP2AMKELGF4025, DUKHCONP2AMKELGF4015, DUKHCONP2AMKHDEX5100, DUKHCONP2AZ1SLEX5105, DUKHCONP2AZ1ACRF4635, DUKHCONP2AZ1ARGF3095, DUKHCONP2AMKACRF4635, DUKHCONP2AMKPLRF4350, DUKHCONP2AMKSLEX5105, DUKHCONP2AMKSLEX5110, DUKHCONP2AZ1ARRF3660, DUKHCONP2AMKELRF4075, DUKHCONP2AMKELGF4030 | DUKHHANP2AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2AZ1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 59 | No | DUKHCONP2AZ1SLEX5110, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ1ARRF3660, DUKHCONP2AMKAREL3680, DUKHCONP2AMKACRF4635, DUKHCONP2AMKMSEX5005, DUKHCONP2AMKWEEX5065, DUKHCONP2AZ1SLEX5105, DUKHCONP2AZ1ELGF4015, DUKHCONP2AMKELGF4025, DUKHCONP2AMKPLRF4350, DUKHCONP2AMKSLEX5105, DUKHCONP2AZ1HDEX5100, DUKHCONP2AZ1ELRF4075, DUKHCONP2AMKELGF4030, DUKHCONP2AMKSLEX5110, DUKHCONP2AZ1ELGF4025, DUKHCONP2AMKARGF3095, DUKHCONP2AMKHDEX5100, DUKHCONP2AMKELRF4075, DUKHCONP2AMKPLGF4320, DUKHCONP2AZ1MSEX5005, DUKHCONP2AZ1AREL3680, DUKHCONP2AMKELGF4015 | DUKHHANP2AGNELTC9010, DUKHHANP2AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2AZ1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 59 | No | DUKHCONP2AMKACRF4635, DUKHCONP2AZ1AREL3680, DUKHCONP2AMKELGF4015, DUKHCONP2AMKELGF4030, DUKHCONP2AMKSLEX5105, DUKHCONP2AZ1PLGF4320, DUKHCONP2AZ1HDEX5100, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ1ARRF3660, DUKHCONP2AMKARGF3095, DUKHCONP2AMKAREL3680, DUKHCONP2AMKMSEX5005, DUKHCONP2AZ1SLEX5105, DUKHCONP2AMKELGF4025, DUKHCONP2AMKELRF4075, DUKHCONP2AMKWEEX5065, DUKHCONP2AZ1SLEX5110, DUKHCONP2AMKSLEX5110, DUKHCONP2AZ1MSEX5005, DUKHCONP2AZ1WEEX5065, DUKHCONP2AZ1ARGF3095, DUKHCONP2AMKPLRF4350, DUKHCONP2AMKPLGF4320, DUKHCONP2AMKHDEX5100 | DUKHHANP2AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L35.15 ZONE - 2 (3 Twin Villas) |  | 350 | 350 | 0% | 2013-03-24 | 2014-05-13 | 2013-03-24 | 2014-05-13 | 27 |  |  |  | 0 | 0
DHBL.K30.L35.15 .10 STRUCTURAL WORKS |  | 158 | 158 | 0% | 2013-03-24 | 2013-09-26 | 2013-03-24 | 2013-09-26 | 42 |  |  |  | 0 | 0
DHBL.K30.L35.15 .10 .10 SUB STRUCTURE |  | 105 | 105 | 0% | 2013-03-24 | 2013-07-23 | 2013-03-24 | 2013-07-23 | 13 |  |  |  | 0 | 0
DHBL.K30.L35.15 .10 .10 .10 UPTO GRADE SLAB |  | 105 | 105 | 0% | 2013-03-24 | 2013-07-23 | 2013-03-24 | 2013-07-23 | 13 |  |  |  | 0 | 0
DUKHCONP2AZ2STUG1035 | Backfilling Upto Grade Beam Bottom | 20 | 20 | 0% | 2013-05-22 | 2013-06-13 | 2013-05-22 | 2013-06-13 | 13 | No | DUKHCONP2AZ2STUG1030, DUKHCONP2AZ1STUG1035, DUKHCONP2AZ2STUG1030 | DUKHCONP2AZ2STUG1040, DUKHCONP2AZ2STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-04-22 | 2013-05-14 | 2013-04-22 | 2013-05-14 | 13 | No | DUKHCONP2AZ2STUG1015, DUKHCONP2AZ2STUG1015, DUKHCONP2AZ1STUG1020 | DUKHCONP2AZ2STUG1025, DUKHCONP2AZ2STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-06-03 | 2013-07-01 | 2013-06-03 | 2013-07-01 | 13 | No | DUKHCONP2AZ2STUG1035, DUKHCONP2AZ1STUG1040, DUKHCONP2AZ2STUG1035 | DUKHCONP2AZ2STUG1045, DUKHCONP2AZ2STUG1045, DUKHCONP2AZ2PLUG4300, DUKHCONP2AZ2PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1025 | Construction of neck of columns | 20 | 20 | 0% | 2013-05-01 | 2013-05-23 | 2013-05-01 | 2013-05-23 | 13 | No | DUKHCONP2AZ2STUG1020, DUKHCONP2AZ2STUG1020 | DUKHCONP2AZ2STUG1030, DUKHCONP2AZ2STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-06-25 | 2013-07-23 | 2013-06-25 | 2013-07-23 | 13 | No | DUKHCONP2AZ2PLUG4300, DUKHCONP2AZ2PLUG4300, DUKHCONP2AZ2STUG1040, DUKHCONP2AZ2STUG1040 | DUKHCONP2AZ2STGF2000, DUKHCONP2AZ2STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1005 | Footing Antitermite | 20 | 20 | 0% | 2013-04-04 | 2013-04-27 | 2013-04-04 | 2013-04-27 | 13 | No | DUKHCONP2AZ2STUG1000, DUKHCONP2AZ2STUG1000 | DUKHCONP2AZ2STUG1010, DUKHCONP2AZ2STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1010 | Footing Blinding | 20 | 20 | 0% | 2013-04-07 | 2013-04-29 | 2013-04-07 | 2013-04-29 | 13 | No | DUKHCONP2AZ2STUG1005, DUKHCONP2AZ2STUG1005 | DUKHCONP2AZ2STUG1015, DUKHCONP2AZ2STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-03-24 | 2013-04-21 | 2013-03-24 | 2013-04-21 | 13 | No | DUKHCONP2AZ1STUG1000 | DUKHCONP2AZ2STUG1005, DUKHCONP2AZ2STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1015 | Footing Waterproofing & Screed | 20 | 20 | 0% | 2013-04-13 | 2013-05-05 | 2013-04-13 | 2013-05-05 | 13 | No | DUKHCONP2AZ2STUG1010, DUKHCONP2AZ2STUG1010 | DUKHCONP2AZ2STUG1020, DUKHCONP2AZ2STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2AZ2STUG1030 | Waterproofing Footing & Neck Column | 20 | 20 | 0% | 2013-05-11 | 2013-06-02 | 2013-05-11 | 2013-06-02 | 13 | No | DUKHCONP2AZ2STUG1025, DUKHCONP2AZ2STUG1025 | DUKHCONP2AZ2STUG1035, DUKHCONP2AZ2STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L35.15 .10 .15 SUPERSTRUCTURE |  | 63 | 63 | 0% | 2013-07-13 | 2013-09-26 | 2013-07-13 | 2013-09-26 | 42 |  |  |  | 0 | 0
DHBL.K30.L35.15 .10 .15 .10 GROUND FLOOR |  | 45 | 45 | 0% | 2013-07-13 | 2013-09-05 | 2013-07-13 | 2013-09-05 | 13 |  |  |  | 0 | 0
DUKHCONP2AZ2STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-08-20 | 2013-09-05 | 2013-08-20 | 2013-09-05 | 13 | No | DUKHCONP2AZ1STGF2015, DUKHCONP2AZ2STGF2010, DUKHCONP2AZ2STGF2010 | DUKHCONP2AZ2STRF2060, DUKHCONP2AZ2STRF2060, DUKHCONP2AZ2ARGF3000, DUKHCONP2AZ2ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-07-31 | 2013-09-01 | 2013-07-31 | 2013-09-01 | 13 | No | DUKHCONP2AZ2STGF2005, DUKHCONP2AZ2STGF2005 | DUKHCONP2AZ2STGF2015, DUKHCONP2AZ2STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2STGF2005 | Column-Concrete | 15 | 15 | 0% | 2013-07-23 | 2013-08-08 | 2013-07-23 | 2013-08-08 | 13 | No | DUKHCONP2AZ2STGF2000, DUKHCONP2AZ2STGF2000 | DUKHCONP2AZ2STGF2010, DUKHCONP2AZ2STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2STGF2000 | Column-Rebar & Formwork | 20 | 20 | 0% | 2013-07-13 | 2013-08-04 | 2013-07-13 | 2013-08-04 | 13 | No | DUKHCONP2AZ1STGF2000, DUKHCONP2AZ2STUG1045, DUKHCONP2AZ2STUG1045 | DUKHCONP2AZ2STGF2005, DUKHCONP2AZ2STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.15 .10 .15 .20 ROOF |  | 26 | 26 | 0% | 2013-08-28 | 2013-09-26 | 2013-08-28 | 2013-09-26 | 42 |  |  |  | 0 | 0
DUKHCONP2AZ2STRF2060 | Construction of Parapets | 20 | 20 | 0% | 2013-08-28 | 2013-09-19 | 2013-08-28 | 2013-09-19 | 19 | No | DUKHCONP2AZ2STGF2015, DUKHCONP2AZ2STGF2015, DUKHCONP2AZ1STRF2060 | DUKHCONP2BZ3STRF2060, DUKHCONP2AZ2ARRF3625, DUKHCONP2AZ2STRF2065, DUKHCONP2AZ2ARRF3625, DUKHCONP2AZ2STRF2065, DUKHCONP2AZ2WEEX5030, DUKHCONP2AZ2WEEX5030 | 0 | 0 | ROOF
DUKHCONP2AZ2STRF2065 | Construction of up stands/Plinth | 20 | 20 | 0% | 2013-09-04 | 2013-09-26 | 2013-09-04 | 2013-09-26 | 42 | No | DUKHCONP2AZ2STRF2060, DUKHCONP2AZ2STRF2060 | DUKHCONP2AZ2AREL3665, DUKHCONP2AZ2MSEX5020, DUKHCONP2AZ2MSEX5000, DUKHCONP2AZ2MSEX5000, DUKHCONP2AZ2ARRF3625, DUKHCONP2AZ2AREL3665, DUKHCONP2AZ2MSEX5020, DUKHCONP2AZ2ARRF3625 | 0 | 0 | ROOF
DHBL.K30.L35.15 .15 FINISHING WORKS |  | 172 | 172 | 0% | 2013-09-14 | 2014-04-06 | 2013-09-14 | 2014-04-06 | 34 |  |  |  | 0 | 0
DHBL.K30.L35.15 .15 .10 INTERNAL FINISHES |  | 172 | 172 | 0% | 2013-09-14 | 2014-04-06 | 2013-09-14 | 2014-04-06 | 34 |  |  |  | 0 | 0
DHBL.K30.L35.15 .15 .10 .10 GROUND FLOOR |  | 172 | 172 | 0% | 2013-09-14 | 2014-04-06 | 2013-09-14 | 2014-04-06 | 34 |  |  |  | 0 | 0
DUKHCONP2AZ2ARGF3080 | Aluminum windows | 18 | 18 | 0% | 2014-02-09 | 2014-03-02 | 2014-02-09 | 2014-03-02 | 49 | No | DUKHCONP2AZ2ARGF3065, DUKHCONP2AZ1ARGF3080 | DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3000 | Block work | 25 | 25 | 0% | 2013-09-14 | 2013-10-12 | 2013-09-14 | 2013-10-12 | 13 | No | DUKHCONP2AZ1ARGF3000, DUKHCONP2AZ2STGF2015, DUKHCONP2AZ2STGF2015 | DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ2ELGF4000, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2ELGF4000, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2PLGF4305 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3075 | Carpentry & Joinery Works | 18 | 18 | 0% | 2014-01-28 | 2014-02-18 | 2014-01-28 | 2014-02-18 | 8 | No | DUKHCONP2AZ2ARGF3065, DUKHCONP2AZ1ARGF3075, DUKHCONP2AZ2ARGF3065 | DUKHCONP2AZ2ARGF3090, DUKHCONP2AZ2ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3020 | Ceramic Wall Tiling | 15 | 15 | 0% | 2013-11-07 | 2013-11-24 | 2013-11-07 | 2013-11-24 | 14 | No | DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ2ARGF3015, DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ2ARGF3015 | DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ2ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-01-08 | 2014-01-25 | 2014-01-08 | 2014-01-25 | 26 | No | DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ1ARGF3040, DUKHCONP2AZ2ARGF3010 | DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3095, DUKHCONP2BZ3ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 34 | No | DUKHCONP2AZ2ACGF4610, DUKHCONP2AZ2ARGF3040, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3065, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3090, DUKHCONP2AZ2ACGF4610, DUKHCONP2AZ2ARGF3030, DUKHCONP2AZ2ARGF3080, DUKHCONP2AZ2ARGF3080, DUKHCONP2AZ1ARGF3095, DUKHCONP2AZ2ARGF3040, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3090, DUKHCONP2AZ2ARGF3030, DUKHCONP2AZ2ARGF3060 | DUKHCONP2AZ2ELTC8010, DUKHCONP2AZ2ACTC8000, DUKHCONP2AZ2PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3045 | Fixing of Suspension systems | 15 | 15 | 0% | 2013-12-25 | 2014-01-11 | 2013-12-25 | 2014-01-11 | 7 | No | DUKHCONP2AZ2ELGF4010, DUKHCONP2AZ2ARGF3030, DUKHCONP2AZ2ELGF4010, DUKHCONP2AZ2ARGF3030, DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ2ARGF3025 | DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3010 | Flooring screed | 20 | 20 | 0% | 2013-10-26 | 2013-11-17 | 2013-10-26 | 2013-11-17 | 25 | No | DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ1ARGF3010 | DUKHCONP2AZ2ARGF3040, DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ2ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3060 | Gypsum board false ceiling | 20 | 20 | 0% | 2014-01-11 | 2014-02-02 | 2014-01-11 | 2014-02-02 | 7 | No | DUKHCONP2AZ2ARGF3045, DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ2ARGF3045, DUKHCONP2AZ1ARGF3060 | DUKHCONP2AZ2ACGF4605, DUKHCONP2AZ2ARGF3065, DUKHCONP2AZ2ELGF4015, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2ELGF4015, DUKHCONP2AZ2ELGF4030, DUKHCONP2AZ2PLGF4320, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ACGF4605, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2PLGF4320, DUKHCONP2AZ2ELGF4030, DUKHCONP2AZ2ELGF4025, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ELGF4025, DUKHCONP2AZ2ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-02-08 | 2014-02-25 | 2014-02-08 | 2014-02-25 | 8 | No | DUKHCONP2AZ2ARGF3075, DUKHCONP2AZ2ARGF3075, DUKHCONP2AZ1ARGF3090 | DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3095, DUKHCONP2BZ3ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3030 | Paint First coat | 20 | 20 | 0% | 2013-10-31 | 2013-11-23 | 2013-10-31 | 2013-11-23 | 6 | No | DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ1ARGF3030 | DUKHCONP2AZ2ARGF3045, DUKHCONP2AZ2ARGF3045, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3095, DUKHCONP2BZ3ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-10-03 | 2013-11-03 | 2013-10-03 | 2013-11-03 | 13 | No | DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ2ELGF4000, DUKHCONP2AZ1ARGF3005, DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ2ARGF3000, DUKHCONP2AZ2ARGF3000, DUKHCONP2AZ2ELGF4000 | DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ2ARGF3030, DUKHCONP2AZ2ARGF3030, DUKHCONP2AZ2ARGF3015, DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ2ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3025 | Porcelain Tile flooring | 20 | 20 | 0% | 2013-12-02 | 2013-12-25 | 2013-12-02 | 2013-12-25 | 7 | No | DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ1ARGF3025, DUKHCONP2AZ2ARGF3020, DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ2ARGF3020 | DUKHCONP2AZ2ARGF3045, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3040, DUKHCONP2AZ2ARGF3045, DUKHCONP2AZ2ARGF3040, DUKHCONP2AZ2ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3035 | Slate Tile Flooring & Skirting | 18 | 18 | 0% | 2013-12-21 | 2014-01-09 | 2013-12-21 | 2014-01-09 | 13 | No | DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ2ARGF3010, DUKHCONP2AZ2ARGF3025, DUKHCONP2AZ1ARGF3035, DUKHCONP2AZ2ARGF3025 | DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3040, DUKHCONP2AZ2ARGF3040, DUKHCONP2BZ3ARGF3035, DUKHCONP2AZ2ARGF3065, DUKHCONP2AZ2ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3015 | Wet area waterproofing & Protection Screed | 20 | 20 | 0% | 2013-10-20 | 2013-11-11 | 2013-10-20 | 2013-11-11 | 14 | No | DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3005 | DUKHCONP2AZ2ARGF3020, DUKHCONP2AZ2ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ARGF3065 | Wooden door | 15 | 15 | 0% | 2014-01-22 | 2014-02-08 | 2014-01-22 | 2014-02-08 | 7 | No | DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3035, DUKHCONP2AZ2ARGF3060 | DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3080, DUKHCONP2AZ2ARGF3075, DUKHCONP2AZ2PLGF4315, DUKHCONP2AZ2ARGF3075, DUKHCONP2AZ2PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.15 .15 .15 EXTERNAL FINISHES |  | 77 | 77 | 0% | 2013-09-30 | 2013-12-31 | 2013-09-30 | 2013-12-31 | 55 |  |  |  | 0 | 0
DHBL.K30.L35.15 .15 .15 .10 ROOF |  | 53 | 53 | 0% | 2013-09-30 | 2013-12-02 | 2013-09-30 | 2013-12-02 | 69 |  |  |  | 0 | 0
DUKHCONP2AZ2ARRF3660 | Installation of Access Ladder | 20 | 20 | 0% | 2013-11-10 | 2013-12-02 | 2013-11-10 | 2013-12-02 | 69 | No | DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ1ARRF3660, DUKHCONP2AZ2ARRF3645 | DUKHCONP2AZ2ELTC8010, DUKHCONP2BZ3ARRF3660, DUKHCONP2AZ2ACTC8000, DUKHCONP2AZ2AREL3680, DUKHCONP2AZ2PLTC8005 | 0 | 0 | ROOF
DUKHCONP2AZ2ARRF3640 | Installation of Insulation & Protection | 18 | 18 | 0% | 2013-10-27 | 2013-11-16 | 2013-10-27 | 2013-11-16 | 30 | No | DUKHCONP2AZ2ARRF3635, DUKHCONP2AZ2ARRF3635, DUKHCONP2AZ1ARRF3645 | DUKHCONP2BZ3ARRF3640, DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2ARRF3645 | 0 | 0 | ROOF
DUKHCONP2AZ2ARRF3625 | Laying of Pitched Roof | 25 | 25 | 0% | 2013-09-30 | 2013-10-30 | 2013-09-30 | 2013-10-30 | 30 | No | DUKHCONP2AZ2STRF2060, DUKHCONP2AZ2STRF2060, DUKHCONP2AZ2STRF2065, DUKHCONP2AZ2STRF2065, DUKHCONP2AZ1ARRF3630 | DUKHCONP2AZ2ARRF3630, DUKHCONP2AZ2ARRF3630, DUKHCONP2BZ3ARRF3625 | 0 | 0 | ROOF
DUKHCONP2AZ2ARRF3635 | Laying of Waterproofing Membrane | 18 | 18 | 0% | 2013-10-22 | 2013-11-11 | 2013-10-22 | 2013-11-11 | 30 | No | DUKHCONP2AZ2ARRF3630, DUKHCONP2AZ2ARRF3630 | DUKHCONP2AZ2ARRF3640, DUKHCONP2AZ2ARRF3640 | 0 | 0 | ROOF
DUKHCONP2AZ2ARRF3630 | Leveling Screed for Waterproofing | 18 | 18 | 0% | 2013-10-14 | 2013-11-05 | 2013-10-14 | 2013-11-05 | 30 | No | DUKHCONP2AZ2ARRF3625, DUKHCONP2AZ2ARRF3625 | DUKHCONP2AZ2ARRF3635, DUKHCONP2AZ2ARRF3635 | 0 | 0 | ROOF
DUKHCONP2AZ2ARRF3645 | Lime Stone Chips & Paving slab Installation | 18 | 18 | 0% | 2013-11-04 | 2013-11-24 | 2013-11-04 | 2013-11-24 | 30 | No | DUKHCONP2AZ2ARRF3640, DUKHCONP2AZ2ARRF3640 | DUKHCONP2AZ2ACRF4630, DUKHCONP2AZ2ARRF3660, DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2AREL3665, DUKHCONP2AZ2ACRF4630, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2ARRF3660, DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2AREL3665 | 0 | 0 | ROOF
DHBL.K30.L35.15 .15 .15 .15 ELEVATION |  | 39 | 39 | 0% | 2013-11-16 | 2013-12-31 | 2013-11-16 | 2013-12-31 | 55 |  |  |  | 0 | 0
DUKHCONP2AZ2AREL3680 | External Painting | 20 | 20 | 0% | 2013-12-08 | 2013-12-31 | 2013-12-08 | 2013-12-31 | 55 | No | DUKHCONP2AZ2AREL3665, DUKHCONP2AZ2ARRF3660, DUKHCONP2AZ1AREL3680, DUKHCONP2AZ2AREL3665 | DUKHCONP2AZ2PLTC8005, DUKHCONP2BZ3AREL3680, DUKHCONP2AZ2ACTC8000, DUKHCONP2AZ2ELTC8010 | 0 | 0 | ELEVATION
DUKHCONP2AZ2AREL3665 | External Plastering | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 30 | No | DUKHCONP2AZ2STRF2065, DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2STRF2065, DUKHCONP2AZ1AREL3665, DUKHCONP2AZ2ARRF3645 | DUKHCONP2BZ3AREL3665, DUKHCONP2AZ2AREL3680, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2AREL3680, DUKHCONP2AZ2PLRF4350 | 0 | 0 | ELEVATION
DHBL.K30.L35.15 .20 MEP WORKS |  | 240 | 240 | 0% | 2013-06-17 | 2014-03-31 | 2013-06-17 | 2014-03-31 | 39 |  |  |  | 0 | 0
DHBL.K30.L35.15 .20 .10 ELECTRICAL WORKS |  | 146 | 146 | 0% | 2013-09-28 | 2014-03-20 | 2013-09-28 | 2014-03-20 | 48 |  |  |  | 0 | 0
DHBL.K30.L35.15 .20 .10 .10 GROUND FLOOR |  | 124 | 124 | 0% | 2013-09-28 | 2014-02-23 | 2013-09-28 | 2014-02-23 | 51 |  |  |  | 0 | 0
DUKHCONP2AZ2ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-10-13 | 2013-11-06 | 2013-10-13 | 2013-11-06 | 13 | No | DUKHCONP2AZ1ELGF4005, DUKHCONP2AZ2ELGF4000, DUKHCONP2AZ2ELGF4000 | DUKHCONP2AZ2ELGF4010, DUKHCONP2BZ3ELGF4005, DUKHCONP2AZ2ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ELGF4000 | Fixing of wall conduits & switch socket boxes | 20 | 20 | 0% | 2013-09-28 | 2013-10-22 | 2013-09-28 | 2013-10-22 | 13 | No | DUKHCONP2AZ2ARGF3000, DUKHCONP2AZ2ARGF3000 | DUKHCONP2AZ2ELGF4005, DUKHCONP2AZ2ELGF4005, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 13 | No | DUKHCONP2AZ1ELGF4015, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3060 | DUKHCONP2AZ2ELTC8010, DUKHCONP2BZ3ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 48 | No | DUKHCONP2AZ2ELGF4010, DUKHCONP2AZ2ELGF4010, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ1ELGF4020, DUKHCONP2AZ2ARGF3060 | DUKHCONP2AZ2ELGF4025, DUKHCONP2AZ2ELGF4025, DUKHCONP2AZ2ELGF4030, DUKHCONP2AZ2ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ELGF4025 | Installation of Lighting fixtures & Accessories | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 48 | No | DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3060 | DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 51 | No | DUKHCONP2AZ2MSEX5010, DUKHCONP2AZ1ELGF4030, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3060 | DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2ELTC8010, DUKHCONP2AZ2ELRF4070 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ELGF4010 | Installation of wiring & Main Cabling | 20 | 20 | 0% | 2013-10-23 | 2013-11-14 | 2013-10-23 | 2013-11-14 | 41 | No | DUKHCONP2AZ2ELGF4005, DUKHCONP2AZ2ELGF4005 | DUKHCONP2AZ2ARGF3045, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2ELGF4020, DUKHCONP2AZ2ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.15 .20 .10 .20 ROOF |  | 30 | 30 | 0% | 2014-02-15 | 2014-03-20 | 2014-02-15 | 2014-03-20 | 48 |  |  |  | 0 | 0
DUKHCONP2AZ2ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-02-15 | 2014-03-06 | 2014-02-15 | 2014-03-06 | 48 | No | DUKHCONP2AZ2ELGF4010, DUKHCONP2AZ2ELGF4010, DUKHCONP2AZ2ELGF4025, DUKHCONP2AZ2ELGF4030, DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2ELGF4025, DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2ELGF4030 | DUKHCONP2AZ2ELRF4075, DUKHCONP2AZ2ELRF4075 | 0 | 0 | ROOF
DUKHCONP2AZ2ELRF4075 | Installation of TV Dish Antenna | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 48 | No | DUKHCONP2AZ1ELRF4075, DUKHCONP2AZ2ELRF4070, DUKHCONP2AZ2ELRF4070 | DUKHCONP2AZ2ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L35.15 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 217 | 217 | 0% | 2013-06-17 | 2014-03-04 | 2013-06-17 | 2014-03-04 | 62 |  |  |  | 0 | 0
DHBL.K30.L35.15 .20 .15 .10 GROUND FLOOR |  | 217 | 217 | 0% | 2013-06-17 | 2014-03-04 | 2013-06-17 | 2014-03-04 | 62 |  |  |  | 0 | 0
DUKHCONP2AZ2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-06-17 | 2013-07-09 | 2013-06-17 | 2013-07-09 | 13 | No | DUKHCONP2AZ2STUG1040, DUKHCONP2AZ2STUG1040 | DUKHCONP2AZ2STUG1045, DUKHCONP2AZ2STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-10-06 | 2013-10-28 | 2013-10-06 | 2013-10-28 | 32 | No | DUKHCONP2AZ2ARGF3000, DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ1PLGF4310, DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ2ARGF3000 | DUKHCONP2AZ2ARGF3020, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2ARGF3020, DUKHCONP2AZ2PLGF4315, DUKHCONP2AZ2MSEX5000, DUKHCONP2AZ2PLGF4315, DUKHCONP2AZ2MSEX5000 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2PLGF4305 | Installation of Plumbing pipes & testing | 20 | 20 | 0% | 2013-09-28 | 2013-10-22 | 2013-09-28 | 2013-10-22 | 13 | No | DUKHCONP2AZ2ARGF3000, DUKHCONP2AZ2ARGF3000 | DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3020, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2ARGF3020, DUKHCONP2AZ2PLRF4350 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-02-16 | 2014-03-04 | 2014-02-16 | 2014-03-04 | 62 | No | DUKHCONP2AZ2PLGF4315, DUKHCONP2AZ1PLGF4320, DUKHCONP2AZ2PLGF4315, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3060 | DUKHCONP2AZ2PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-01-28 | 2014-02-20 | 2014-01-28 | 2014-02-20 | 7 | No | DUKHCONP2AZ2ARGF3065, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ1PLGF4315, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2ARGF3065 | DUKHCONP2AZ2PLGF4320, DUKHCONP2AZ2PLGF4320, DUKHCONP2BZ3PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.15 .20 .15 .20 ROOF |  | 15 | 15 | 0% | 2013-12-24 | 2014-01-09 | 2013-12-24 | 2014-01-09 | 25 |  |  |  | 0 | 0
DUKHCONP2AZ2PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2013-12-24 | 2014-01-09 | 2013-12-24 | 2014-01-09 | 25 | No | DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ1PLRF4350, DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2AREL3665, DUKHCONP2AZ2PLGF4305, DUKHCONP2AZ2AREL3665, DUKHCONP2AZ2PLGF4305 | DUKHCONP2AZ2WEEX5065, DUKHCONP2BZ3PLRF4350, DUKHCONP2AZ2WEEX5065, DUKHCONP2AZ2PLTC8005, DUKHCONP2AZ2ACTC8000 | 0 | 0 | ROOF
DHBL.K30.L35.15 .20 .20 AC WORKS |  | 131 | 131 | 0% | 2013-10-28 | 2014-03-31 | 2013-10-28 | 2014-03-31 | 39 |  |  |  | 0 | 0
DHBL.K30.L35.15 .20 .20 .10 GROUND FLOOR |  | 116 | 116 | 0% | 2013-10-28 | 2014-03-13 | 2013-10-28 | 2014-03-13 | 39 |  |  |  | 0 | 0
DUKHCONP2AZ2ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-02-19 | 2014-03-13 | 2014-02-19 | 2014-03-13 | 39 | No | DUKHCONP2AZ2ACGF4605, DUKHCONP2AZ2ACGF4605 | DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ACRF4635, DUKHCONP2AZ2ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 39 | No | DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ACGF4600 | DUKHCONP2AZ2ACGF4610, DUKHCONP2AZ2ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP2AZ2ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-10-28 | 2013-11-19 | 2013-10-28 | 2013-11-19 | 28 | No | DUKHCONP2AZ1ACGF4600, DUKHCONP2AZ2ARGF3005, DUKHCONP2AZ2ARGF3005 | DUKHCONP2BZ3ACGF4600, DUKHCONP2AZ2ACGF4605, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ARGF3060, DUKHCONP2AZ2ACRF4630, DUKHCONP2AZ2ACRF4630, DUKHCONP2AZ2ACGF4605 | 0 | 0 | GROUND FLOOR
DHBL.K30.L35.15 .20 .20 .20 ROOF |  | 111 | 111 | 0% | 2013-11-20 | 2014-03-31 | 2013-11-20 | 2014-03-31 | 39 |  |  |  | 0 | 0
DUKHCONP2AZ2ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 39 | No | DUKHCONP2AZ1ACRF4635, DUKHCONP2AZ2ACRF4630, DUKHCONP2AZ2ACGF4610, DUKHCONP2AZ2ACRF4630, DUKHCONP2AZ2ACGF4610 | DUKHCONP2AZ2ACTC8000 | 0 | 0 | ROOF
DUKHCONP2AZ2ACRF4630 | Installation of Refrigerant Pipes | 20 | 20 | 0% | 2013-11-20 | 2013-12-12 | 2013-11-20 | 2013-12-12 | 60 | No | DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ2ARRF3645, DUKHCONP2AZ2ACGF4600, DUKHCONP2AZ1ACRF4630 | DUKHCONP2BZ3ACRF4630, DUKHCONP2AZ2ACRF4635, DUKHCONP2AZ2ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L35.15 .25 EXTERNAL WORKS |  | 178 | 178 | 0% | 2013-10-14 | 2014-05-13 | 2013-10-14 | 2014-05-13 | 27 |  |  |  | 0 | 0
DHBL.K30.L35.15 .25 .10 MISCELLANEOUS |  | 178 | 178 | 0% | 2013-10-14 | 2014-05-13 | 2013-10-14 | 2014-05-13 | 27 |  |  |  | 0 | 0
DUKHCONP2AZ2MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 27 | No | DUKHCONI2AZ2BWGL5325, DUKHCONP2AZ1MSEX5335 | DUKHHANP2AGNACTC9000, DUKHHANP2AGNPLTC9005, DUKHHANP2AGNELTC9010 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ2MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-11-13 | 2013-12-11 | 2013-11-13 | 2013-12-11 | 42 | No | DUKHCONP2AZ2MSEX5000, DUKHCONP2AZ2MSEX5000 | DUKHCONP2AZ2ACTC8000, DUKHCONP2AZ2MSEX5015, DUKHCONP2AZ2MSEX5015, DUKHCONP2AZ2PLTC8005, DUKHCONP2AZ2ELTC8010 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ2MSEX5020 | Construction Entrance Ramp | 20 | 20 | 0% | 2013-10-14 | 2013-11-07 | 2013-10-14 | 2013-11-07 | 30 | No | DUKHCONP2AZ2STRF2065, DUKHCONP2AZ2STRF2065, DUKHCONP2AZ1MSEX5020 | DUKHCONP2AZ2HDEX5090, DUKHCONP2AZ2MSEX5055, DUKHCONP2AZ2MSEX5025, DUKHCONP2AZ2HDEX5090, DUKHCONP2AZ2MSEX5025, DUKHCONP2BZ3MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ2MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2013-12-03 | 2013-12-26 | 2013-12-03 | 2013-12-26 | 42 | No | DUKHCONP2AZ2MSEX5005, DUKHCONP2AZ2MSEX5005 | DUKHCONP2AZ2WEEX5065, DUKHCONP2AZ2MSEX5010, DUKHCONP2AZ2WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ2MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-10-30 | 2013-11-27 | 2013-10-30 | 2013-11-27 | 42 | No | DUKHCONP2AZ2STRF2065, DUKHCONP2AZ2STRF2065, DUKHCONP2AZ1MSEX5000, DUKHCONP2AZ2PLGF4310, DUKHCONP2AZ2PLGF4310 | DUKHCONP2AZ2MSEX5005, DUKHCONP2AZ2MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ2MSEX5055 | Installation Steel Door | 20 | 20 | 0% | 2013-10-28 | 2013-11-19 | 2013-10-28 | 2013-11-19 | 30 | No | DUKHCONP2AZ2MSEX5020 | DUKHCONP2AZ2MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ2MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2013-11-09 | 2013-12-01 | 2013-11-09 | 2013-12-01 | 30 | No | DUKHCONP2AZ2MSEX5020, DUKHCONP2AZ1MSEX5025, DUKHCONP2AZ2MSEX5020, DUKHCONP2AZ2MSEX5055 | DUKHCONP2AZ2WEEX5050, DUKHCONP2AZ2HDEX5090, DUKHCONP2AZ2WEEX5050, DUKHCONP2BZ3MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2AZ2MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 55 | No | DUKHCONP2AZ2MSEX5015 | DUKHCONP2AZ2ELGF4030 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L35.15 .25 .15 WATER TANK ENCLOSURE |  | 102 | 102 | 0% | 2013-10-20 | 2014-02-17 | 2013-10-20 | 2014-02-17 | 15 |  |  |  | 0 | 0
DUKHCONP2AZ2WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 32 | No | DUKHCONP2AZ2WEEX5035, DUKHCONP2AZ2WEEX5035 | DUKHCONP2AZ2WEEX5045, DUKHCONP2AZ2WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ2WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 32 | No | DUKHCONP2AZ2WEEX5030, DUKHCONP2AZ2WEEX5030 | DUKHCONP2AZ2WEEX5040, DUKHCONP2AZ2WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ2WEEX5030 | Excavation | 20 | 20 | 0% | 2013-10-20 | 2013-11-11 | 2013-10-20 | 2013-11-11 | 15 | No | DUKHCONP2AZ1WEEX5030, DUKHCONP2AZ2STRF2060, DUKHCONP2AZ2STRF2060 | DUKHCONP2BZ3WEEX5030, DUKHCONP2AZ2WEEX5035, DUKHCONP2AZ2WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ2WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 32 | No | DUKHCONP2AZ2WEEX5040, DUKHCONP2AZ2WEEX5040 | DUKHCONP2AZ2WEEX5050, DUKHCONP2AZ2WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ2WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 10 | No | DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2WEEX5060, DUKHCONP2AZ2WEEX5060, DUKHCONP2AZ2MSEX5015, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ1WEEX5065, DUKHCONP2AZ2MSEX5015 | DUKHCONP2AZ2WEEX5070, DUKHCONP2BZ3WEEX5065, DUKHCONP2AZ2PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ2WEEX5070 | Installation ladder for water Tank | 20 | 20 | 0% | 2014-01-25 | 2014-02-17 | 2014-01-25 | 2014-02-17 | 15 | No | DUKHCONP2AZ2WEEX5065, DUKHCONP2AZ1WEEX5070 | DUKHCONP2BZ3WEEX5070 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ2WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2013-12-05 | 2013-12-29 | 2013-12-05 | 2013-12-29 | 30 | No | DUKHCONP2AZ2WEEX5045, DUKHCONP2AZ2MSEX5025, DUKHCONP2AZ1WEEX5050, DUKHCONP2AZ2MSEX5025, DUKHCONP2AZ2WEEX5045 | DUKHCONP2BZ3WEEX5050, DUKHCONP2AZ2WEEX5060, DUKHCONP2AZ2WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2AZ2WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2013-12-11 | 2014-01-09 | 2013-12-11 | 2014-01-09 | 30 | No | DUKHCONP2AZ2WEEX5050, DUKHCONP2AZ2WEEX5050 | DUKHCONP2AZ2WEEX5065, DUKHCONP2AZ2WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L35.15 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2013-11-17 | 2014-01-06 | 2013-11-17 | 2014-01-06 | 30 |  |  |  | 0 | 0
DUKHCONP2AZ2HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2013-11-28 | 2013-12-22 | 2013-11-28 | 2013-12-22 | 30 | No | DUKHCONP2AZ2HDEX5090, DUKHCONP2AZ2HDEX5090 | DUKHCONP2AZ2HDEX5100, DUKHCONP2AZ2HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2AZ2HDEX5100 | Interlock works | 20 | 20 | 0% | 2013-12-14 | 2014-01-06 | 2013-12-14 | 2014-01-06 | 30 | No | DUKHCONP2AZ2HDEX5095, DUKHCONP2AZ2HDEX5095 | DUKHCONP2AZ2ACTC8000, DUKHCONP2AZ2SLEX5105, DUKHCONP2AZ2ELTC8010, DUKHCONP2AZ2SLEX5105, DUKHCONP2AZ2PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2AZ2HDEX5090 | kerb works | 20 | 20 | 0% | 2013-11-17 | 2013-12-09 | 2013-11-17 | 2013-12-09 | 30 | No | DUKHCONP2AZ2MSEX5020, DUKHCONP2AZ2MSEX5025, DUKHCONP2AZ1HDEX5090, DUKHCONP2AZ2MSEX5020 | DUKHCONP2BZ3HDEX5090, DUKHCONP2AZ2HDEX5095, DUKHCONP2AZ2HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L35.15 .25 .25 SOFT LANDSCAPING |  | 30 | 30 | 0% | 2014-01-06 | 2014-02-09 | 2014-01-06 | 2014-02-09 | 61 |  |  |  | 0 | 0
DUKHCONP2AZ2SLEX5105 | Laying of Grass/ green area | 20 | 20 | 0% | 2014-01-06 | 2014-01-28 | 2014-01-06 | 2014-01-28 | 21 | No | DUKHCONP2AZ2HDEX5100, DUKHCONP2AZ1SLEX5105, DUKHCONP2AZ2HDEX5100 | DUKHCONP2AZ2SLEX5110, DUKHCONP2AZ2PLTC8005, DUKHCONP2AZ2ELTC8010, DUKHCONP2BZ3SLEX5105, DUKHCONP2AZ2SLEX5110, DUKHCONP2AZ2ACTC8000 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP2AZ2SLEX5110 | Laying of Palm tree | 20 | 20 | 0% | 2014-01-18 | 2014-02-09 | 2014-01-18 | 2014-02-09 | 61 | No | DUKHCONP2AZ2SLEX5105, DUKHCONP2AZ2SLEX5105, DUKHCONP2AZ1SLEX5110 | DUKHCONP2AZ2PLTC8005, DUKHCONP2BZ3SLEX5110, DUKHCONP2AZ2ACTC8000, DUKHCONP2AZ2ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L35.15 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 34 |  |  |  | 0 | 0
DUKHCONP2AZ2ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 34 | No | DUKHMOBP2APS00002170, DUKHCONP2AZ2HDEX5100, DUKHCONP2AZ2MSEX5005, DUKHMOBI2APS00002205, DUKHCONP2AZ2ACRF4635, DUKHCONP2AZ2AREL3680, DUKHCONP2AZ2ARRF3660, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2SLEX5110, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2SLEX5105 | DUKHHANP2AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2AZ2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 34 | No | DUKHMOBP2APS00002170, DUKHCONP2AZ2ELGF4015, DUKHCONP2AZ2ARRF3660, DUKHCONP2AZ2SLEX5105, DUKHMOBI2APS00002205, DUKHCONP2AZ2ELGF4030, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2ELRF4075, DUKHCONP2AZ2AREL3680, DUKHCONP2AZ2ELGF4025, DUKHCONP2AZ2HDEX5100, DUKHCONP2AZ2SLEX5110, DUKHCONP2AZ2MSEX5005 | DUKHHANP2AGNELTC9010, DUKHHANP2AGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2AZ2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 34 | No | DUKHMOBI2APS00002205, DUKHCONP2AZ2AREL3680, DUKHCONP2AZ2SLEX5105, DUKHCONP2AZ2SLEX5110, DUKHMOBP2APS00002170, DUKHCONP2AZ2PLGF4320, DUKHCONP2AZ2PLRF4350, DUKHCONP2AZ2ARRF3660, DUKHCONP2AZ2ARGF3095, DUKHCONP2AZ2MSEX5005, DUKHCONP2AZ2WEEX5065, DUKHCONP2AZ2HDEX5100 | DUKHHANP2AGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L40 PACKAGE-2A INFRASTRUCTURE WORKS |  | 260 | 260 | 0% | 2013-08-28 | 2014-07-01 | 2013-08-28 | 2014-07-01 | 5 |  |  |  | 0 | 0
DHBL.K30.L40.10 ZONE - 1 |  | 217 | 217 | 0% | 2013-08-28 | 2014-05-12 | 2013-08-28 | 2014-05-12 | 23 |  |  |  | 0 | 0
DHBL.K30.L40.10 .10 INFRASTRUCTURE WORKS |  | 217 | 217 | 0% | 2013-08-28 | 2014-05-12 | 2013-08-28 | 2014-05-12 | 23 |  |  |  | 0 | 0
DHBL.K30.L40.10 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-08-28 | 2013-10-16 | 2013-08-28 | 2013-10-16 | 0 |  |  |  | 0 | 0
DUKHCONI2AZ1DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-09-30 | 2013-10-16 | 2013-09-30 | 2013-10-16 | 0 | Yes | DUKHCONI2AZ1DRGL5125, DUKHCONI2AZ1DRGL5125 | DUKHCONI2AZ1SAGL5140, DUKHCONI2AZ1WSGL5155, DUKHCONI2AZ1SAGL5135, DUKHCONI2AZ2DRGL5115 | 0 | 0 | DRAINAGE LINES
DUKHCONI2AZ1DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-08-28 | 2013-09-25 | 2013-08-28 | 2013-09-25 | 0 | Yes | DUKHENGI2ADWDRAP5050, DUKHCONP2AZ1STRF2060 | DUKHCONI2AZ1SAGL5135, DUKHCONI2AZ1SAGL5140, DUKHCONI2AZ1DRGL5120, DUKHCONI2AZ1DRGL5120, DUKHMOBI2APS00002205 | 0 | 0 | DRAINAGE LINES
DUKHCONI2AZ1DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-09-04 | 2013-10-02 | 2013-09-04 | 2013-10-02 | 0 | Yes | DUKHCONI2AZ1DRGL5115, DUKHCONI2AZ1DRGL5115 | DUKHCONI2AZ1DRGL5125, DUKHCONI2AZ1DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI2AZ1DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-09-12 | 2013-10-10 | 2013-09-12 | 2013-10-10 | 0 | Yes | DUKHCONI2AZ1DRGL5120, DUKHCONI2AZ1DRGL5120 | DUKHCONI2AZ1DRGL5130, DUKHCONI2AZ1DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L40.10 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-09-30 | 2013-12-23 | 2013-09-30 | 2013-12-23 | 37 |  |  |  | 0 | 0
DUKHCONI2AZ1SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2013-11-30 | 2013-12-23 | 2013-11-30 | 2013-12-23 | 37 | No | DUKHCONI2AZ1SAGL5135, DUKHCONI2AZ1SAGL5145 | DUKHCONI2AZ1RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2AZ1SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-09-30 | 2013-10-30 | 2013-09-30 | 2013-10-30 | 62 | No | DUKHENGI2ADWDRAP5050, DUKHCONI2AZ1DRGL5115, DUKHCONI2AZ1DRGL5130 | DUKHCONI2AZ1SAGL5150, DUKHCONI2AZ2SAGL5135 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2AZ1SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2013-10-31 | 2013-11-28 | 2013-10-31 | 2013-11-28 | 1 | No | DUKHCONI2AZ1SAGL5140 | DUKHCONI2AZ1WSGL5170, DUKHCONI2AZ1SAGL5150, DUKHCONI2AZ2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2AZ1SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-09-30 | 2013-10-30 | 2013-09-30 | 2013-10-30 | 1 | No | DUKHCONI2AZ1DRGL5130, DUKHCONI2AZ1DRGL5115 | DUKHCONI2AZ1SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L40.10 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2013-10-12 | 2013-12-29 | 2013-10-12 | 2013-12-29 | 32 |  |  |  | 0 | 0
DUKHCONI2AZ1WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2013-10-31 | 2013-11-28 | 2013-10-31 | 2013-11-28 | 1 | No | DUKHCONI2AZ1SAGL5145, DUKHCONI2AZ1WSGL5165 | DUKHCONI2AZ2WSGL5155, DUKHCONI2AZ1WSGL5175, DUKHCONI2AZ1FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-11-06 | 2013-12-04 | 2013-11-06 | 2013-12-04 | 32 | No | DUKHCONI2AZ1WSGL5155, DUKHCONI2AZ1WSGL5170 | DUKHCONI2AZ1WSGL5180, DUKHCONI2AZ2WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ1WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-10-12 | 2013-11-11 | 2013-10-12 | 2013-11-11 | 1 | No | DUKHCONI2AZ1DRGL5130, DUKHENGI2ADWWSAP5070 | DUKHCONI2AZ1WSGL5160, DUKHCONI2ASBIWGL7400, DUKHCONI2AZ1WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ1WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2013-12-05 | 2013-12-29 | 2013-12-05 | 2013-12-29 | 32 | No | DUKHCONI2AZ1WSGL5175 | DUKHCONI2AZ2WSGL5180, DUKHCONI2AZ1FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ1WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-10-20 | 2013-11-17 | 2013-10-20 | 2013-11-17 | 1 | No | DUKHCONI2AZ1WSGL5155 | DUKHCONI2AZ1WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ1WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 1 | No | DUKHCONI2AZ1WSGL5160 | DUKHCONI2AZ1WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L40.10 .10 .25 FIREFIGHTING LINES |  | 57 | 57 | 0% | 2013-11-06 | 2014-01-12 | 2013-11-06 | 2014-01-12 | 20 |  |  |  | 0 | 0
DUKHCONI2AZ1FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2013-11-26 | 2013-12-25 | 2013-11-26 | 2013-12-25 | 1 | No | DUKHCONI2AZ1FFGL5195 | DUKHCONI2AZ1ELGL5215, DUKHCONI2AZ1FFGL5205, DUKHCONI2AZ1RWGL6000, DUKHCONI2AZ2FFGL5185 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ1FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 20 | No | DUKHCONI2AZ1WSGL5180, DUKHCONI2AZ1FFGL5205 | DUKHCONI2AZ1RWGL6000, DUKHCONI2ASBIWGL7440, DUKHCONI2AZ2FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-12-08 | 2014-01-06 | 2013-12-08 | 2014-01-06 | 20 | No | DUKHCONI2AZ1FFGL5200, DUKHCONI2AZ1FFGL5185, DUKHPROGEN00PRDV3690 | DUKHCONI2AZ1FFGL5210, DUKHCONI2AZ2FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ1FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2013-11-06 | 2013-12-04 | 2013-11-06 | 2013-12-04 | 1 | No | DUKHENGI2ADWFFAP5060, DUKHCONI2AZ1WSGL5170 | DUKHCONI2AZ1FFGL5190, DUKHCONI2AZ1FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ1FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2013-11-14 | 2013-12-12 | 2013-11-14 | 2013-12-12 | 1 | No | DUKHCONI2AZ1FFGL5185, DUKHPROGEN00PRDV3540, DUKHPROGEN00PRDV3650 | DUKHCONI2AZ1FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ1FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2013-11-20 | 2013-12-19 | 2013-11-20 | 2013-12-19 | 1 | No | DUKHCONI2AZ1FFGL5190 | DUKHCONI2AZ1FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L40.10 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2013-12-04 | 2014-01-28 | 2013-12-04 | 2014-01-28 | 51 |  |  |  | 0 | 0
DUKHCONI2AZ1ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2013-12-19 | 2014-01-16 | 2013-12-19 | 2014-01-16 | 6 | No | DUKHCONI2AZ1ELGL5215, DUKHCONI2AZ1ELGL5220 | DUKHCONI2AZ1ELGL5230, DUKHCONI2AZ1IRGL5285, DUKHCONI2AZ1ELGL5230, DUKHCONI2AZ1RWGL6000, DUKHCONI2AZ1IRGL5265, DUKHCONI2AZ2ELGL5215 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2AZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2013-12-31 | 2014-01-28 | 2013-12-31 | 2014-01-28 | 51 | No | DUKHCONI2AZ1ELGL5225, DUKHCONI2AZ1ELGL5225 | DUKHCONI2AZ1STGL5260, DUKHCONI2AZ2ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2AZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2013-12-04 | 2014-01-02 | 2013-12-04 | 2014-01-02 | 3 | No | DUKHCONI2AZ1FFGL5200, DUKHENGI2ADWELAP5080 | DUKHCONI2AZ1ELGL5220, DUKHCONI2AZ1ELGL5225, DUKHCONI2AZ1STGL5235 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2AZ1ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 6 | No | DUKHCONI2AZ1ELGL5215 | DUKHCONI2AZ1ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L40.10 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2013-12-04 | 2014-02-27 | 2013-12-04 | 2014-02-27 | 51 |  |  |  | 0 | 0
DUKHCONI2AZ1STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2013-12-16 | 2014-01-14 | 2013-12-16 | 2014-01-14 | 3 | No | DUKHCONI2AZ1STGL5245, DUKHCONI2AZ1STGL5235 | DUKHCONI2AZ1RWGL6000, DUKHCONI2AZ1BWGL5315, DUKHCONI2AZ1STGL5255, DUKHCONI2AZ2STGL5235, DUKHCONI2AZ1TCGL5295 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ1STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 3 | No | DUKHCONI2AZ1STGL5235 | DUKHCONI2AZ1STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ1STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 3 | No | DUKHCONI2AZ1STGL5240 | DUKHCONI2AZ1STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ1STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 51 | No | DUKHCONI2AZ1ELGL5230, DUKHCONI2AZ1STGL5255 | DUKHCONI2AZ1PSGL7015, DUKHCONI2AZ2STGL5260 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ1STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2013-12-04 | 2014-01-02 | 2013-12-04 | 2014-01-02 | 3 | No | DUKHENGI2ADWSTAP5090, DUKHCONI2AZ1ELGL5215 | DUKHCONI2AZ1STGL5240, DUKHCONI2AZ1STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ1STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-01-04 | 2014-02-01 | 2014-01-04 | 2014-02-01 | 66 | No | DUKHPROGEN00PRDV3350, DUKHCONI2AZ1STGL5250, DUKHPROGEN00PRDV3250 | DUKHCONI2AZ2STGL5255, DUKHCONI2AZ1STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L40.10 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-01-18 | 2014-03-25 | 2014-01-18 | 2014-03-25 | 34 |  |  |  | 0 | 0
DUKHCONI2AZ1IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-02-04 | 2014-03-05 | 2014-02-04 | 2014-03-05 | 29 | No | DUKHCONI2AZ1IRGL5275 | DUKHCONI2AZ2IRGL5265, DUKHCONI2AZ1IRGL5290, DUKHCONI2AZ1IRGL5285 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-02-17 | 2014-03-17 | 2014-02-17 | 2014-03-17 | 34 | No | DUKHCONI2AZ1IRGL5280, DUKHCONI2AZ1ELGL5225 | DUKHCONI2AZ1IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ1IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-01-18 | 2014-02-16 | 2014-01-18 | 2014-02-16 | 29 | No | DUKHENGI2ADWIRAP5110, DUKHCONI2AZ1ELGL5225 | DUKHCONI2AZ1IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 34 | No | DUKHPROGEN00PRDV3760, DUKHPROGEN00PRDV3830, DUKHCONI2AZ1IRGL5280, DUKHCONI2AZ1IRGL5285, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3860, DUKHPROGEN00PRDV3840, DUKHPROGEN00PRDV3870 | DUKHCONI2AZ1SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ1IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-01-23 | 2014-02-22 | 2014-01-23 | 2014-02-22 | 29 | No | DUKHCONI2AZ1IRGL5265 | DUKHCONI2AZ1IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ1IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 29 | No | DUKHCONI2AZ1IRGL5270 | DUKHCONI2AZ1IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L40.10 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2013-12-29 | 2014-02-13 | 2013-12-29 | 2014-02-13 | 68 |  |  |  | 0 | 0
DUKHCONI2AZ1TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-01-09 | 2014-02-01 | 2014-01-09 | 2014-02-01 | 3 | No | DUKHCONI2AZ1TCGL5300 | DUKHCONI2AZ2TCGL5295, DUKHCONI2AZ1RWGL6000, DUKHCONI2AZ1TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2AZ1TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-01-21 | 2014-02-13 | 2014-01-21 | 2014-02-13 | 68 | No | DUKHCONI2AZ1TCGL5305 | DUKHCONI2AZ2TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2AZ1TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2013-12-29 | 2014-01-20 | 2013-12-29 | 2014-01-20 | 3 | No | DUKHENGI2ADWTCAP5100, DUKHCONI2AZ1STGL5250 | DUKHCONI2AZ1TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2AZ1TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-01-04 | 2014-01-26 | 2014-01-04 | 2014-01-26 | 3 | No | DUKHCONI2AZ1TCGL5295 | DUKHCONI2AZ1TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L40.10 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2013-12-29 | 2014-03-25 | 2013-12-29 | 2014-03-25 | 57 |  |  |  | 0 | 0
DUKHCONI2AZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 57 | No | DUKHCONI2AZ1BWGL5325 | DUKHCONI2AZ1PSGL7010, DUKHCONI2AZ2BWGL5330 | 0 | 0 | BOUNDARY WALL
DUKHCONI2AZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 29 | No | DUKHCONI2AZ1BWGL5320, DUKHCONI2AZ1BWGL5315 | DUKHCONI2AZ1BWGL5330, DUKHCONP2AZ1MSEX5335, DUKHCONI2AZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI2AZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 29 | No | DUKHCONI2AZ1STGL5250, DUKHENGI2ADWBWAP5130, DUKHPROGEN00PRDV3820 | DUKHCONI2AZ1BWGL5320, DUKHCONI2AZ1BWGL5325, DUKHCONI2AZ2BWGL5315 | 0 | 0 | BOUNDARY WALL
DUKHCONI2AZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 29 | No | DUKHPROGEN00PRDV3800, DUKHCONI2AZ1BWGL5315 | DUKHCONI2AZ1BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L40.10 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-02-02 | 2014-04-19 | 2014-02-02 | 2014-04-19 | 36 |  |  |  | 0 | 0
DUKHCONI2AZ1RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-02-02 | 2014-02-13 | 2014-02-02 | 2014-02-13 | 3 | No | DUKHCONI2AZ1STGL5250, DUKHCONI2AZ1FFGL5210, DUKHENGI2ADWBWAP5130, DUKHCONI2AZ1ELGL5225, DUKHCONI2AZ1TCGL5305, DUKHCONI2AZ1FFGL5200, DUKHCONI2AZ1SAGL5150 | DUKHCONI2AZ1RWGL6005, DUKHCONI2AZ1HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-04-08 | 2014-04-13 | 2014-04-08 | 2014-04-13 | 33 | No | DUKHCONI2AZ1RWGL6020 | DUKHCONI2AZ1RWGL6030, DUKHCONI2AZ1HDGL7040, DUKHCONI2AZ2RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ1RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-03-10 | 2014-04-01 | 2014-03-10 | 2014-04-01 | 3 | No | DUKHCONI2AZ1RWGL6010 | DUKHCONI2AZ1RWGL6020, DUKHCONI2AZ1PSGL7000, DUKHCONI2AZ2RWGL6000, DUKHCONI2AZ1PSGL7005 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ1RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 3 | No | DUKHCONI2AZ1RWGL6005 | DUKHCONI2AZ1RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-04-02 | 2014-04-07 | 2014-04-02 | 2014-04-07 | 21 | No | DUKHCONI2AZ1RWGL6015 | DUKHCONI2AZ1PSGL7010, DUKHCONI2AZ1RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ1RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 3 | No | DUKHCONI2AZ1RWGL6000 | DUKHCONI2AZ1RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ1RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-04-14 | 2014-04-19 | 2014-04-14 | 2014-04-19 | 36 | No | DUKHPROGEN00PRDV3720, DUKHPROGEN00PRDV3710, DUKHCONI2AZ1RWGL6025, DUKHPROGEN00PRDV3700 | DUKHCONI2AZ2RWGL6030, DUKHCONI2AZ1PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L40.10 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-03-16 | 2014-05-12 | 2014-03-16 | 2014-05-12 | 21 |  |  |  | 0 | 0
DUKHCONI2AZ1PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 21 | No | DUKHCONI2AZ1PSGL7005, DUKHCONI2AZ1RWGL6020, DUKHPROGEN00PRDV3730, DUKHCONI2AZ1BWGL5330, DUKHCONI2AZ1RWGL6030 | DUKHCONI2AZ1PSGL7015, DUKHCONI2AZ2PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI2AZ1PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-04-14 | 2014-05-12 | 2014-04-14 | 2014-05-12 | 21 | No | DUKHCONI2AZ1PSGL7010, DUKHCONI2AZ1STGL5260 | DUKHCONI2AZ2PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI2AZ1PSGL7000 | Excavation | 15 | 15 | 0% | 2014-03-16 | 2014-04-01 | 2014-03-16 | 2014-04-01 | 26 | No | DUKHCONI2AZ1RWGL6015, DUKHENGI2ADWPSAP5140 | DUKHCONI2AZ1PSGL7005, DUKHCONI2AZ1PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI2AZ1PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-03-27 | 2014-04-13 | 2014-03-27 | 2014-04-13 | 21 | No | DUKHCONI2AZ1PSGL7000, DUKHCONI2AZ1PSGL7000, DUKHCONI2AZ1RWGL6015 | DUKHCONI2AZ1PSGL7010, DUKHCONI2AZ2PSGL7000 | 0 | 0 | PARKING SHED
DHBL.K30.L40.10 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-02-02 | 2014-04-24 | 2014-02-02 | 2014-04-24 | 33 |  |  |  | 0 | 0
DUKHCONI2AZ1HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 23 | No | DUKHCONI2AZ1HDGL7025 | DUKHCONI2AZ2HDGL7030, DUKHCONI2AZ1HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ1HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-04-14 | 2014-04-24 | 2014-04-14 | 2014-04-24 | 33 | No | DUKHPROGEN00PRDV3750, DUKHCONI2AZ1HDGL7035, DUKHCONI2AZ1RWGL6025 | DUKHCONI2AZ2HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ1HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-02-26 | 2014-03-26 | 2014-02-26 | 2014-03-26 | 23 | No | DUKHPROGEN00PRDV3740, DUKHCONI2AZ1HDGL7030 | DUKHCONI2AZ1HDGL7040, DUKHCONI2AZ1SLGL7200, DUKHCONI2AZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ1HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 23 | No | DUKHCONI2AZ1HDGL7020 | DUKHCONI2AZ1HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ1HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-02-02 | 2014-02-25 | 2014-02-02 | 2014-02-25 | 23 | No | DUKHENGI2ADWSLAP5120, DUKHCONI2AZ1RWGL6000 | DUKHCONI2AZ1HDGL7025, DUKHCONI2ASBGZGL7900 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L40.10 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-03-10 | 2014-04-30 | 2014-03-10 | 2014-04-30 | 33 |  |  |  | 0 | 0
DUKHCONI2AZ1SLGL7200 | Excavation | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 23 | No | DUKHENGI2ADWSLAP5120, DUKHCONI2AZ1HDGL7035, DUKHCONI2AZ1IRGL5290 | DUKHCONI2AZ1SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2AZ1SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 33 | No | DUKHCONI2AZ1SLGL7205 | DUKHCONI2AZ2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2AZ1SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 23 | No | DUKHCONI2AZ1SLGL7200 | DUKHCONI2AZ2SLGL7200, DUKHCONI2AZ1SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L40.15 ZONE - 2 |  | 217 | 217 | 0% | 2013-10-20 | 2014-07-01 | 2013-10-20 | 2014-07-01 | 5 |  |  |  | 0 | 0
DHBL.K30.L40.15 .10 INFRASTRUCTURE WORKS |  | 217 | 217 | 0% | 2013-10-20 | 2014-07-01 | 2013-10-20 | 2014-07-01 | 5 |  |  |  | 0 | 0
DHBL.K30.L40.15 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-10-20 | 2013-12-08 | 2013-10-20 | 2013-12-08 | 0 |  |  |  | 0 | 0
DUKHCONI2AZ2DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-11-21 | 2013-12-08 | 2013-11-21 | 2013-12-08 | 0 | Yes | DUKHCONI2AZ2DRGL5125, DUKHCONI2AZ2DRGL5125 | DUKHCONI2AZ2WSGL5155, DUKHCONI2AZ2SAGL5140, DUKHCONI2AZ2SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI2AZ2DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-10-20 | 2013-11-17 | 2013-10-20 | 2013-11-17 | 0 | Yes | DUKHCONI2AZ1DRGL5130 | DUKHCONI2AZ2SAGL5140, DUKHCONI2AZ2SAGL5135, DUKHCONI2AZ2DRGL5120, DUKHCONI2AZ2DRGL5120 | 0 | 0 | DRAINAGE LINES
DUKHCONI2AZ2DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-10-27 | 2013-11-24 | 2013-10-27 | 2013-11-24 | 0 | Yes | DUKHCONI2AZ2DRGL5115, DUKHCONI2AZ2DRGL5115 | DUKHCONI2AZ2DRGL5125, DUKHCONI2AZ2DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI2AZ2DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 0 | Yes | DUKHCONI2AZ2DRGL5120, DUKHCONI2AZ2DRGL5120 | DUKHCONI2AZ2DRGL5130, DUKHCONI2AZ2DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L40.15 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-11-21 | 2014-02-12 | 2013-11-21 | 2014-02-12 | 34 |  |  |  | 0 | 0
DUKHCONI2AZ2SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-01-20 | 2014-02-12 | 2014-01-20 | 2014-02-12 | 34 | No | DUKHCONI2AZ2SAGL5145, DUKHCONI2AZ2SAGL5135 | DUKHCONI2AZ2RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2AZ2SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 59 | No | DUKHCONI2AZ2DRGL5115, DUKHCONI2AZ1SAGL5135, DUKHCONI2AZ2DRGL5130 | DUKHCONI2AZ2SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2AZ2SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 0 | Yes | DUKHCONI2AZ2SAGL5140, DUKHCONI2AZ1SAGL5145 | DUKHCONI2AZ2SAGL5150, DUKHCONI2AZ2WSGL5170 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2AZ2SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 0 | Yes | DUKHCONI2AZ2DRGL5115, DUKHCONI2AZ2DRGL5130 | DUKHCONI2AZ2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L40.15 .10 .20 WATER SUPPLY SYSTEM |  | 66 | 66 | 0% | 2013-12-02 | 2014-02-18 | 2013-12-02 | 2014-02-18 | 29 |  |  |  | 0 | 0
DUKHCONI2AZ2WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 0 | Yes | DUKHCONI2AZ2WSGL5165, DUKHCONI2AZ2SAGL5145 | DUKHCONI2AZ2WSGL5175, DUKHCONI2AZ2FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 29 | No | DUKHCONI2AZ2WSGL5170, DUKHCONI2AZ1WSGL5175, DUKHCONI2AZ2WSGL5155 | DUKHCONI2AZ2WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ2WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-12-02 | 2013-12-31 | 2013-12-02 | 2013-12-31 | 1 | No | DUKHCONI2AZ1WSGL5170, DUKHCONI2AZ2DRGL5130 | DUKHCONI2AZ2WSGL5175, DUKHCONI2AZ2WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ2WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-01-26 | 2014-02-18 | 2014-01-26 | 2014-02-18 | 29 | No | DUKHCONI2AZ1WSGL5180, DUKHCONI2AZ2WSGL5175 | DUKHHANP2AGNELTC9010, DUKHCONI2AZ2FFGL5210, DUKHHANP2AGNACTC9000, DUKHHANP2AGNPLTC9005 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ2WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-12-08 | 2014-01-06 | 2013-12-08 | 2014-01-06 | 1 | No | DUKHCONI2AZ2WSGL5155 | DUKHCONI2AZ2WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2AZ2WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 1 | No | DUKHCONI2AZ2WSGL5160 | DUKHCONI2AZ2WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L40.15 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2013-12-28 | 2014-02-26 | 2013-12-28 | 2014-02-26 | 22 |  |  |  | 0 | 0
DUKHCONI2AZ2FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 0 | Yes | DUKHCONI2AZ2FFGL5195 | DUKHCONI2AZ2RWGL6000, DUKHCONI2AZ2ELGL5215, DUKHCONI2AZ2FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ2FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 22 | No | DUKHCONI2AZ2WSGL5180, DUKHCONI2AZ2FFGL5205, DUKHCONI2AZ1FFGL5210 | DUKHCONI2ASBIWGL7440, DUKHHANP2AGNELTC9010, DUKHCONI2AZ2RWGL6000, DUKHHANP2AGNACTC9000, DUKHHANP2AGNPLTC9005 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 22 | No | DUKHCONI2AZ2FFGL5200, DUKHCONI2AZ1FFGL5205, DUKHCONI2AZ2FFGL5185 | DUKHCONI2AZ2FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ2FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 0 | Yes | DUKHCONI2AZ1FFGL5200, DUKHCONI2AZ2WSGL5170 | DUKHCONI2AZ2FFGL5190, DUKHCONI2AZ2FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ2FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 0 | Yes | DUKHCONI2AZ2FFGL5185 | DUKHCONI2AZ2FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2AZ2FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 0 | Yes | DUKHCONI2AZ2FFGL5190 | DUKHCONI2AZ2FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L40.15 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-01-25 | 2014-03-20 | 2014-01-25 | 2014-03-20 | 33 |  |  |  | 0 | 0
DUKHCONI2AZ2ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 13 | No | DUKHCONI2AZ2ELGL5215, DUKHCONI2AZ2ELGL5220 | DUKHCONI2AZ2IRGL5265, DUKHCONI2AZ2IRGL5285, DUKHCONI2AZ2ELGL5230, DUKHCONI2AZ2ELGL5230, DUKHCONI2AZ2RWGL6000 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2AZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 33 | No | DUKHCONI2AZ2ELGL5225, DUKHCONI2AZ2ELGL5225, DUKHCONI2AZ1ELGL5230 | DUKHCONI2ASBIWGL7450, DUKHCONI2AZ2STGL5260 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2AZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 0 | Yes | DUKHCONI2AZ2FFGL5200, DUKHCONI2AZ1ELGL5225 | DUKHCONI2AZ2ELGL5220, DUKHCONI2AZ2STGL5235, DUKHCONI2AZ2ELGL5225 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2AZ2ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 13 | No | DUKHCONI2AZ2ELGL5215 | DUKHCONI2AZ2ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L40.15 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-01-25 | 2014-04-19 | 2014-01-25 | 2014-04-19 | 33 |  |  |  | 0 | 0
DUKHCONI2AZ2STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-02-05 | 2014-03-06 | 2014-02-05 | 2014-03-06 | 0 | Yes | DUKHCONI2AZ2STGL5235, DUKHCONI2AZ2STGL5245 | DUKHCONI2AZ2RWGL6000, DUKHCONI2AZ2STGL5255, DUKHCONI2AZ2TCGL5295, DUKHCONI2AZ2BWGL5315 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ2STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 0 | Yes | DUKHCONI2AZ2STGL5235 | DUKHCONI2AZ2STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ2STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 0 | Yes | DUKHCONI2AZ2STGL5240 | DUKHCONI2AZ2STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ2STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 33 | No | DUKHCONI2AZ2STGL5255, DUKHCONI2AZ2ELGL5230, DUKHCONI2AZ1STGL5260 | DUKHHANP2AGNACTC9000, DUKHCONI2AZ2PSGL7015, DUKHHANP2AGNPLTC9005, DUKHCONI2ASBIWGL7450, DUKHHANP2AGNELTC9010 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ2STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 0 | Yes | DUKHCONI2AZ2ELGL5215, DUKHCONI2AZ1STGL5250 | DUKHCONI2AZ2STGL5250, DUKHCONI2AZ2STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI2AZ2STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 53 | No | DUKHCONI2AZ2STGL5250, DUKHCONI2AZ1STGL5255 | DUKHCONI2AZ2STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L40.15 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-03-10 | 2014-05-14 | 2014-03-10 | 2014-05-14 | 26 |  |  |  | 0 | 0
DUKHCONI2AZ2IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 26 | No | DUKHCONI2AZ2IRGL5275 | DUKHCONI2AZ2IRGL5290, DUKHCONI2AZ2IRGL5285 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-04-08 | 2014-05-06 | 2014-04-08 | 2014-05-06 | 26 | No | DUKHCONI2AZ2ELGL5225, DUKHCONI2AZ2IRGL5280 | DUKHCONI2AZ2IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ2IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 26 | No | DUKHCONI2AZ1IRGL5280, DUKHCONI2AZ2ELGL5225 | DUKHCONI2AZ2IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 26 | No | DUKHCONI2AZ2IRGL5285, DUKHCONI2AZ2IRGL5280 | DUKHCONI2AZ2SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ2IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 26 | No | DUKHCONI2AZ2IRGL5265 | DUKHCONI2AZ2IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI2AZ2IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 26 | No | DUKHCONI2AZ2IRGL5270 | DUKHCONI2AZ2IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L40.15 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-02-18 | 2014-04-05 | 2014-02-18 | 2014-04-05 | 45 |  |  |  | 0 | 0
DUKHCONI2AZ2TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-03-02 | 2014-03-24 | 2014-03-02 | 2014-03-24 | 0 | Yes | DUKHCONI2AZ2TCGL5300 | DUKHCONI2AZ2RWGL6000, DUKHCONI2AZ2TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2AZ2TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-03-13 | 2014-04-05 | 2014-03-13 | 2014-04-05 | 45 | No | DUKHCONI2AZ1TCGL5310, DUKHCONI2AZ2TCGL5305 | DUKHHANP2AGNACTC9000, DUKHHANP2AGNELTC9010, DUKHCONI2ASBIWGL7450, DUKHHANP2AGNPLTC9005 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2AZ2TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 0 | Yes | DUKHCONI2AZ1TCGL5305, DUKHCONI2AZ2STGL5250 | DUKHCONI2AZ2TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2AZ2TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-02-24 | 2014-03-18 | 2014-02-24 | 2014-03-18 | 0 | Yes | DUKHCONI2AZ2TCGL5295 | DUKHCONI2AZ2TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L40.15 .10 .50 BOUNDARY WALL |  | 73 | 73 | 0% | 2014-02-18 | 2014-05-13 | 2014-02-18 | 2014-05-13 | 40 |  |  |  | 0 | 0
DUKHCONI2AZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 40 | No | DUKHCONI2AZ2BWGL5325, DUKHCONI2AZ1BWGL5330 | DUKHCONI2AZ2PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI2AZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 27 | No | DUKHCONI2AZ2BWGL5315, DUKHCONI2AZ2BWGL5320, DUKHCONI2AZ1BWGL5325 | DUKHCONI2AZ2BWGL5330, DUKHCONP2AZ2MSEX5335 | 0 | 0 | BOUNDARY WALL
DUKHCONI2AZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 27 | No | DUKHCONI2AZ2STGL5250, DUKHCONI2AZ1BWGL5315 | DUKHCONI2AZ2BWGL5320, DUKHCONI2AZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI2AZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 27 | No | DUKHCONI2AZ2BWGL5315 | DUKHCONI2AZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L40.15 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-03-25 | 2014-06-08 | 2014-03-25 | 2014-06-08 | 18 |  |  |  | 0 | 0
DUKHCONI2AZ2RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-03-25 | 2014-04-05 | 2014-03-25 | 2014-04-05 | 0 | Yes | DUKHCONI2AZ2FFGL5200, DUKHCONI2AZ2STGL5250, DUKHCONI2AZ2SAGL5150, DUKHCONI2AZ2FFGL5210, DUKHCONI2AZ1RWGL6015, DUKHCONI2AZ2TCGL5305, DUKHCONI2AZ2ELGL5225 | DUKHCONI2AZ2HDGL7020, DUKHCONI2AZ2RWGL6005 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-05-28 | 2014-06-02 | 2014-05-28 | 2014-06-02 | 0 | Yes | DUKHCONI2AZ2RWGL6020, DUKHCONI2AZ1RWGL6025 | DUKHCONI2AZ2RWGL6030, DUKHCONI2AZ2HDGL7040 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ2RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-04-29 | 2014-05-21 | 2014-04-29 | 2014-05-21 | 0 | Yes | DUKHCONI2AZ2RWGL6010 | DUKHCONI2AZ2PSGL7005, DUKHCONI2AZ2PSGL7000, DUKHCONI2AZ2RWGL6020 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ2RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 0 | Yes | DUKHCONI2AZ2RWGL6005 | DUKHCONI2AZ2RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-05-22 | 2014-05-27 | 2014-05-22 | 2014-05-27 | 0 | Yes | DUKHCONI2AZ2RWGL6015 | DUKHCONI2AZ2PSGL7010, DUKHCONI2AZ2RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ2RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-04-06 | 2014-05-04 | 2014-04-06 | 2014-05-04 | 0 | Yes | DUKHCONI2AZ2RWGL6000 | DUKHCONI2AZ2RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI2AZ2RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-06-03 | 2014-06-08 | 2014-06-03 | 2014-06-08 | 18 | No | DUKHCONI2AZ2RWGL6025, DUKHCONI2AZ1RWGL6030 | DUKHCONI2AZ2PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L40.15 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-05-05 | 2014-07-01 | 2014-05-05 | 2014-07-01 | 3 |  |  |  | 0 | 0
DUKHCONI2AZ2PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 3 | No | DUKHCONI2AZ2BWGL5330, DUKHCONI2AZ2RWGL6030, DUKHCONI2AZ2PSGL7005, DUKHCONI2AZ2RWGL6020, DUKHCONI2AZ1PSGL7010 | DUKHCONI2AZ2PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI2AZ2PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-06-03 | 2014-07-01 | 2014-06-03 | 2014-07-01 | 3 | No | DUKHCONI2AZ2STGL5260, DUKHCONI2AZ1PSGL7015, DUKHCONI2AZ2PSGL7010 | DUKHHANP2AGNELTC9010 | 0 | 0 | PARKING SHED
DUKHCONI2AZ2PSGL7000 | Excavation | 15 | 15 | 0% | 2014-05-05 | 2014-05-21 | 2014-05-05 | 2014-05-21 | 8 | No | DUKHCONI2AZ1PSGL7005, DUKHCONI2AZ2RWGL6015 | DUKHCONI2AZ2PSGL7005, DUKHCONI2AZ2PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI2AZ2PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-05-17 | 2014-06-02 | 2014-05-17 | 2014-06-02 | 3 | No | DUKHCONI2AZ2RWGL6015, DUKHCONI2AZ2PSGL7000, DUKHCONI2AZ2PSGL7000 | DUKHCONI2AZ2PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L40.15 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-03-25 | 2014-06-14 | 2014-03-25 | 2014-06-14 | 0 |  |  |  | 0 | 0
DUKHCONI2AZ2HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 15 | No | DUKHCONI2AZ1HDGL7030, DUKHCONI2AZ2HDGL7025 | DUKHCONI2AZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ2HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-06-03 | 2014-06-14 | 2014-06-03 | 2014-06-14 | 0 | Yes | DUKHCONI2AZ2RWGL6025, DUKHCONI2AZ2HDGL7035, DUKHCONI2AZ1HDGL7040 | DUKHHANP2AGNELTC9010, DUKHHANP2AGNPLTC9005 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ2HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 15 | No | DUKHCONI2AZ2HDGL7030, DUKHCONI2AZ1HDGL7035 | DUKHCONI2AZ2SLGL7200, DUKHCONI2AZ2HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ2HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-04-06 | 2014-05-04 | 2014-04-06 | 2014-05-04 | 15 | No | DUKHCONI2AZ2HDGL7020, DUKHCONI2ASBGZGL7910 | DUKHCONI2AZ2HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2AZ2HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-03-25 | 2014-04-16 | 2014-03-25 | 2014-04-16 | 15 | No | DUKHCONI2AZ2RWGL6000 | DUKHCONI2AZ2HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L40.15 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-04-29 | 2014-06-19 | 2014-04-29 | 2014-06-19 | 15 |  |  |  | 0 | 0
DUKHCONI2AZ2SLGL7200 | Excavation for Landscaping | 25 | 25 | 0% | 2014-04-29 | 2014-05-27 | 2014-04-29 | 2014-05-27 | 15 | No | DUKHCONI2AZ1SLGL7205, DUKHCONI2AZ2IRGL5290, DUKHCONI2AZ2HDGL7035 | DUKHCONI2AZ2SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2AZ2SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 15 | No | DUKHCONI2AZ2SLGL7205, DUKHCONI2AZ1SLGL7210 | DUKHHANP2AGNPLTC9005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2AZ2SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 15 | No | DUKHCONI2AZ2SLGL7200 | DUKHCONI2AZ2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L40.30 SECONDARY BUILDINGS |  | 154 | 154 | 0% | 2013-11-12 | 2014-05-12 | 2013-11-12 | 2014-05-12 | 28 |  |  |  | 0 | 0
DHBL.K30.L40.30 .10 INFRASTRUCTURE WORKS |  | 154 | 154 | 0% | 2013-11-12 | 2014-05-12 | 2013-11-12 | 2014-05-12 | 28 |  |  |  | 0 | 0
DHBL.K30.L40.30 .10 .10 IRRIGATION WATER TANK & PUMP ROOM |  | 154 | 154 | 0% | 2013-11-12 | 2014-05-12 | 2013-11-12 | 2014-05-12 | 28 |  |  |  | 0 | 0
DUKHCONI2ASBIWGL7445 | AC Works | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 28 | No | DUKHCONI2ASBIWGL7440 | DUKHCONI2ASBIWGL7450 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7405 | Blinding & base waterproofing | 10 | 10 | 0% | 2013-11-30 | 2013-12-10 | 2013-11-30 | 2013-12-10 | 28 | No | DUKHCONI2ASBIWGL7400 | DUKHCONI2ASBIWGL7410 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7420 | Construction of Roof Slab | 20 | 20 | 0% | 2014-01-22 | 2014-02-15 | 2014-01-22 | 2014-02-15 | 28 | No | DUKHCONI2ASBIWGL7415 | DUKHCONI2ASBIWGL7430, DUKHCONI2ASBIWGL7425 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7410 | Construction of Raft slab | 10 | 10 | 0% | 2013-12-11 | 2013-12-23 | 2013-12-11 | 2013-12-23 | 28 | No | DUKHCONI2ASBIWGL7405 | DUKHCONI2ASBIWGL7415 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7415 | Construction of RCC Wall | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 28 | No | DUKHCONI2ASBIWGL7410 | DUKHCONI2ASBIWGL7420 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7450 | Electrical Works | 25 | 25 | 0% | 2014-03-27 | 2014-04-24 | 2014-03-27 | 2014-04-24 | 28 | No | DUKHCONI2ASBIWGL7445, DUKHCONI2AZ2TCGL5310, DUKHCONI2AZ2ELGL5230, DUKHCONI2AZ2STGL5260 | DUKHCONI2ASBIWGL7455 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7400 | Excavation | 15 | 15 | 0% | 2013-11-12 | 2013-11-28 | 2013-11-12 | 2013-11-28 | 28 | No | DUKHENGI2ADWIWAP5160, DUKHCONI2AZ1WSGL5155 | DUKHCONI2ASBIWGL7405 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7430 | Floor screed | 5 | 5 | 0% | 2014-03-12 | 2014-03-17 | 2014-03-12 | 2014-03-17 | 28 | No | DUKHCONI2ASBIWGL7420, DUKHCONI2ASBIWGL7425 | DUKHCONI2ASBIWGL7440 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7435 | Installation of Boundary Fences | 15 | 15 | 0% | 2014-03-17 | 2014-04-02 | 2014-03-17 | 2014-04-02 | 57 | No | DUKHCONI2ASBIWGL7950, DUKHPROGEN00PRDV3850 | DUKHCONI2ASBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7465 | Installation of G.I Handrails | 5 | 5 | 0% | 2014-05-07 | 2014-05-12 | 2014-05-07 | 2014-05-12 | 28 | No | DUKHCONI2ASBIWGL7460, DUKHCONI2ASBIWGL7435 | DUKHHANP2AGNELTC9010, DUKHHANP2AGNACTC9000, DUKHHANP2AGNPLTC9005 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7460 | Installation of Steel Ladder | 5 | 5 | 0% | 2014-05-01 | 2014-05-06 | 2014-05-01 | 2014-05-06 | 28 | No | DUKHCONI2ASBIWGL7455 | DUKHCONI2ASBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7455 | Internal epoxy coating & Painting | 5 | 5 | 0% | 2014-04-26 | 2014-04-30 | 2014-04-26 | 2014-04-30 | 28 | No | DUKHCONI2ASBIWGL7450 | DUKHCONI2ASBIWGL7460 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7950 | Laying of Interlock | 10 | 10 | 0% | 2014-03-05 | 2014-03-16 | 2014-03-05 | 2014-03-16 | 57 | No | DUKHCONI2ASBIWGL7425 | DUKHCONI2ASBIWGL7435 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7440 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 28 | No | DUKHCONI2ASBIWGL7430, DUKHCONI2AZ2FFGL5210, DUKHCONI2AZ1FFGL5210 | DUKHCONI2ASBIWGL7445 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2ASBIWGL7425 | Waterproofing & Backfilling | 15 | 15 | 0% | 2014-02-16 | 2014-03-04 | 2014-02-16 | 2014-03-04 | 34 | No | DUKHCONI2ASBIWGL7420 | DUKHCONI2ASBIWGL7430, DUKHCONI2ASBIWGL7950 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DHBL.K30.L40.30 .10 .25 GAZEBO |  | 50 | 50 | 0% | 2014-02-26 | 2014-04-24 | 2014-02-26 | 2014-04-24 | 23 |  |  |  | 0 | 0
DUKHCONI2ASBGZGL7900 | Construction of Concrete structure | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 23 | No | DUKHENGI2ADWGZAP5170, DUKHPROGEN00PRDV3780, DUKHCONI2AZ1HDGL7020 | DUKHCONI2ASBGZGL7905 | 0 | 0 | GAZEBO
DUKHCONI2ASBGZGL7910 | Electrical Works-Gazebo | 15 | 15 | 0% | 2014-04-08 | 2014-04-24 | 2014-04-08 | 2014-04-24 | 23 | No | DUKHCONI2ASBGZGL7905, DUKHCONI2ASBGZGL7915 | DUKHCONI2AZ2HDGL7025 | 0 | 0 | GAZEBO
DUKHCONI2ASBGZGL7905 | Installation of Wooden Works | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 23 | No | DUKHCONI2ASBGZGL7900 | DUKHCONI2ASBGZGL7910, DUKHCONI2ASBGZGL7915 | 0 | 0 | GAZEBO
DUKHCONI2ASBGZGL7915 | Park Benches Installation | 15 | 15 | 0% | 2014-03-10 | 2014-03-26 | 2014-03-10 | 2014-03-26 | 33 | No | DUKHCONI2ASBGZGL7905 | DUKHCONI2ASBGZGL7910 | 0 | 0 | GAZEBO
DHBL.K30.L45 PACKAGE-2B |  | 472 | 472 | 0% | 2012-12-01 | 2014-06-14 | 2012-12-01 | 2014-06-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L45.18 SITE PREPARATORY WORKS |  | 84 | 84 | 0% | 2012-12-01 | 2013-03-10 | 2012-12-01 | 2013-03-10 | 0 |  |  |  | 0 | 0
DUKHCONP2BGNSP002400 | Approval for new Layout for rerouting | 14 | 14 | 0% | 2013-01-23 | 2013-02-07 | 2013-01-23 | 2013-02-07 | 0 | Yes | DUKHCONP2BGNSP002300 | DUKHCONP2BGNSP002500 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP004000 | Demolition of Existing building & landscaping | 20 | 20 | 0% | 2012-12-20 | 2013-01-12 | 2012-12-20 | 2013-01-12 | 43 | No | DUKHCONP2BGNSP003000 | DUKHCONP2BGNSP005000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP005000 | Demolition of existing services works | 20 | 20 | 0% | 2012-12-26 | 2013-01-17 | 2012-12-26 | 2013-01-17 | 43 | No | DUKHCONP2BGNSP004000 | DUKHCONP2BZ3STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP002200 | Information Required for Rerouting | 14 | 14 | 0% | 2012-12-30 | 2013-01-14 | 2012-12-30 | 2013-01-14 | 0 | Yes | DUKHCONP2BGNSP002100 | DUKHCONP2BGNSP002300 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP002300 | Preparation & Submission for New Layout | 7 | 7 | 0% | 2013-01-15 | 2013-01-22 | 2013-01-15 | 2013-01-22 | 0 | Yes | DUKHCONP2BGNSP002200 | DUKHCONP2BGNSP002400 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP002500 | Rerouting Works | 25 | 25 | 0% | 2013-02-09 | 2013-03-10 | 2013-02-09 | 2013-03-10 | 0 | Yes | DUKHCONP2BGNSP002400 | DUKHCONP2BZ3STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP002000 | Scanning for Existing Services for rerouting | 12 | 12 | 0% | 2012-12-06 | 2012-12-20 | 2012-12-06 | 2012-12-20 | 0 | Yes | DUKHCONP2BGNSP001000 | DUKHCONP2BGNSP003000, DUKHCONP2BGNSP002100 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP003000 | Site stripping | 20 | 20 | 0% | 2012-12-13 | 2013-01-06 | 2012-12-13 | 2013-01-06 | 43 | No | DUKHCONP2BGNSP002000 | DUKHCONP2BGNSP004000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP002100 | Submission of Scanning Reports | 7 | 7 | 0% | 2012-12-22 | 2012-12-29 | 2012-12-22 | 2012-12-29 | 0 | Yes | DUKHCONP2BGNSP002000 | DUKHCONP2BGNSP002200 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP2BGNSP001000 | Survey works, | 20 | 20 | 0% | 2012-12-01 | 2012-12-24 | 2012-12-01 | 2012-12-24 | 0 | Yes | DUKHMOBP020000004000 | DUKHCONP2BGNSP002000 | 0 | 0 | SITE PREPARATORY WORKS
DHBL.K30.L45.20 ZONE - 3 (3 Twin Villas) |  | 350 | 350 | 0% | 2013-03-11 | 2014-04-30 | 2013-03-11 | 2014-04-30 | 38 |  |  |  | 0 | 0
DHBL.K30.L45.20 .10 STRUCTURAL WORKS |  | 189 | 189 | 0% | 2013-03-11 | 2013-10-22 | 2013-03-11 | 2013-10-22 | 26 |  |  |  | 0 | 0
DHBL.K30.L45.20 .10 .10 SUB STRUCTURE |  | 105 | 105 | 0% | 2013-03-11 | 2013-07-10 | 2013-03-11 | 2013-07-10 | 2 |  |  |  | 0 | 0
DHBL.K30.L45.20 .10 .10 .10 UPTO GRADE SLAB |  | 105 | 105 | 0% | 2013-03-11 | 2013-07-10 | 2013-03-11 | 2013-07-10 | 2 |  |  |  | 0 | 0
DUKHCONP2BZ3STUG1035 | Backfilling Upto Grade Beam Bottom | 20 | 20 | 0% | 2013-05-09 | 2013-06-01 | 2013-05-09 | 2013-06-01 | 0 | Yes | DUKHCONP2BZ3STUG1030, DUKHCONP2BZ3STUG1030 | DUKHCONP2BZ3STUG1040, DUKHCONP2BZ3STUG1040, DUKHCONP2BZ4STUG1035 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-04-09 | 2013-05-01 | 2013-04-09 | 2013-05-01 | 0 | Yes | DUKHCONP2BZ3STUG1015, DUKHCONP2BZ3STUG1015 | DUKHCONP2BZ3STUG1025, DUKHCONP2BZ3STUG1025, DUKHCONP2BZ4STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-05-21 | 2013-06-18 | 2013-05-21 | 2013-06-18 | 0 | Yes | DUKHENGP2BDWSTAP5190, DUKHCONP2BZ3STUG1035, DUKHCONP2BZ3STUG1035 | DUKHCONP2BZ3STUG1045, DUKHCONP2BZ3PLUG4300, DUKHCONP2BZ3PLUG4300, DUKHCONP2BZ4STUG1040, DUKHCONP2BZ3STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1025 | Construction of neck of columns | 20 | 20 | 0% | 2013-04-18 | 2013-05-11 | 2013-04-18 | 2013-05-11 | 0 | Yes | DUKHCONP2BZ3STUG1020, DUKHCONP2BZ3STUG1020 | DUKHCONP2BZ3STUG1030, DUKHCONP2BZ3STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-06-12 | 2013-07-10 | 2013-06-12 | 2013-07-10 | 2 | No | DUKHCONP2BZ3STUG1040, DUKHENGP2BDWSTAP5190, DUKHCONP2BZ3PLUG4300, DUKHCONP2BZ3PLUG4300, DUKHCONP2BZ3STUG1040 | DUKHCONP2BZ3STGF2000, DUKHCONP2BZ3STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1005 | Footing Antitermite | 20 | 20 | 0% | 2013-03-23 | 2013-04-14 | 2013-03-23 | 2013-04-14 | 0 | Yes | DUKHCONP2BZ3STUG1000, DUKHCONP2BZ3STUG1000 | DUKHCONP2BZ3STUG1010, DUKHCONP2BZ3STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1010 | Footing Blinding | 20 | 20 | 0% | 2013-03-25 | 2013-04-16 | 2013-03-25 | 2013-04-16 | 0 | Yes | DUKHCONP2BZ3STUG1005, DUKHCONP2BZ3STUG1005 | DUKHCONP2BZ3STUG1015, DUKHCONP2BZ3STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-03-11 | 2013-04-08 | 2013-03-11 | 2013-04-08 | 0 | Yes | DUKHCONP2BGNSP005000, DUKHCONP2BGNSP002500 | DUKHCONP2BZ3STUG1005, DUKHCONP2BZ3STUG1005, DUKHCONP2BZ4STUG1000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1015 | Footing Waterproofing & Screed | 20 | 20 | 0% | 2013-03-31 | 2013-04-22 | 2013-03-31 | 2013-04-22 | 0 | Yes | DUKHCONP2BZ3STUG1010, DUKHCONP2BZ3STUG1010, DUKHENGP2BDWSTAP5180 | DUKHCONP2BZ3STUG1020, DUKHCONP2BZ3STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ3STUG1030 | Waterproofing Footing & Neck Column | 20 | 20 | 0% | 2013-04-28 | 2013-05-20 | 2013-04-28 | 2013-05-20 | 0 | Yes | DUKHCONP2BZ3STUG1025, DUKHCONP2BZ3STUG1025 | DUKHCONP2BZ3STUG1035, DUKHCONP2BZ3STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L45.20 .10 .15 SUPERSTRUCTURE |  | 94 | 94 | 0% | 2013-06-30 | 2013-10-22 | 2013-06-30 | 2013-10-22 | 26 |  |  |  | 0 | 0
DHBL.K30.L45.20 .10 .15 .10 GROUND FLOOR |  | 45 | 45 | 0% | 2013-06-30 | 2013-08-24 | 2013-06-30 | 2013-08-24 | 2 |  |  |  | 0 | 0
DUKHCONP2BZ3STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-08-04 | 2013-08-24 | 2013-08-04 | 2013-08-24 | 2 | No | DUKHCONP2BZ3STGF2010, DUKHCONP2BZ3STGF2010 | DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ3STRF2060, DUKHCONP2BZ4STGF2015, DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ3STRF2060 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-07-18 | 2013-08-19 | 2013-07-18 | 2013-08-19 | 2 | No | DUKHCONP2BZ3STGF2005, DUKHENGP2BDWSTAP5210, DUKHCONP2BZ3STGF2005 | DUKHCONP2BZ3STGF2015, DUKHCONP2BZ3STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3STGF2005 | Column-Concrete | 15 | 15 | 0% | 2013-07-10 | 2013-07-27 | 2013-07-10 | 2013-07-27 | 2 | No | DUKHCONP2BZ3STGF2000, DUKHCONP2BZ3STGF2000 | DUKHCONP2BZ3STGF2010, DUKHCONP2BZ3STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3STGF2000 | Column-Rebar & Formwork | 20 | 20 | 0% | 2013-06-30 | 2013-07-22 | 2013-06-30 | 2013-07-22 | 2 | No | DUKHENGP2BDWSTAP5200, DUKHCONP2BZ3STUG1045, DUKHCONP2BZ3STUG1045 | DUKHCONP2BZ4STGF2000, DUKHCONP2BZ3STGF2005, DUKHCONP2BZ3STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.20 .10 .15 .20 ROOF |  | 26 | 26 | 0% | 2013-09-21 | 2013-10-22 | 2013-09-21 | 2013-10-22 | 26 |  |  |  | 0 | 0
DUKHCONP2BZ3STRF2060 | Construction of Parapets | 20 | 20 | 0% | 2013-09-21 | 2013-10-13 | 2013-09-21 | 2013-10-13 | 19 | No | DUKHCONP2AZ2STRF2060, DUKHCONP2BZ3STGF2015, DUKHCONP2BZ3STGF2015 | DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3ARRF3625, DUKHCONP2BZ4STRF2060, DUKHCONP2BZ3ARRF3625 | 0 | 0 | ROOF
DUKHCONP2BZ3STRF2065 | Construction of up stands/Plinth | 20 | 20 | 0% | 2013-09-28 | 2013-10-22 | 2013-09-28 | 2013-10-22 | 26 | No | DUKHCONP2BZ3STRF2060, DUKHCONP2BZ3STRF2060 | DUKHCONP2BZ3MSEX5020, DUKHCONP2BZ3ARRF3625, DUKHCONP2BZ3WEEX5030, DUKHCONP2BZ3ARRF3625, DUKHCONP2BZ3AREL3665, DUKHCONP2BZ3MSEX5000, DUKHCONP2BZ3AREL3665, DUKHCONP2BZ3WEEX5030, DUKHCONP2BZ3MSEX5020, DUKHCONP2BZ3MSEX5000 | 0 | 0 | ROOF
DHBL.K30.L45.20 .15 FINISHING WORKS |  | 179 | 179 | 0% | 2013-09-01 | 2014-04-01 | 2013-09-01 | 2014-04-01 | 38 |  |  |  | 0 | 0
DHBL.K30.L45.20 .15 .10 INTERNAL FINISHES |  | 179 | 179 | 0% | 2013-09-01 | 2014-04-01 | 2013-09-01 | 2014-04-01 | 38 |  |  |  | 0 | 0
DHBL.K30.L45.20 .15 .10 .10 GROUND FLOOR |  | 179 | 179 | 0% | 2013-09-01 | 2014-04-01 | 2013-09-01 | 2014-04-01 | 38 |  |  |  | 0 | 0
DUKHCONP2BZ3ARGF3080 | Aluminum windows | 18 | 18 | 0% | 2014-02-09 | 2014-03-02 | 2014-02-09 | 2014-03-02 | 49 | No | DUKHCONP2BZ3ARGF3065 | DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3000 | Block work | 25 | 25 | 0% | 2013-09-01 | 2013-09-29 | 2013-09-01 | 2013-09-29 | 2 | No | DUKHCONP2BZ3STGF2015, DUKHCONP2BZ3STGF2015 | DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3ELGF4000, DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3ELGF4000, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3075 | Carpentry & Joinery Works | 18 | 18 | 0% | 2014-01-28 | 2014-02-18 | 2014-01-28 | 2014-02-18 | 17 | No | DUKHCONP2BZ3ARGF3065, DUKHCONP2BZ3ARGF3065 | DUKHCONP2BZ3ARGF3090, DUKHCONP2BZ3ARGF3090, DUKHCONP2BZ4ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3020 | Ceramic Wall Tiling | 15 | 15 | 0% | 2013-10-26 | 2013-11-11 | 2013-10-26 | 2013-11-11 | 17 | No | DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3ARGF3015, DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3ARGF3015, DUKHCONP2BZ3PLGF4310 | DUKHCONP2BZ3ARGF3025, DUKHCONP2BZ3ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-01-29 | 2014-02-16 | 2014-01-29 | 2014-02-16 | 23 | No | DUKHCONP2BZ3ARGF3025, DUKHCONP2BZ3ARGF3010, DUKHCONP2BZ3ARGF3010, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ3ARGF3025, DUKHCONP2BZ3ARGF3035, DUKHCONP2AZ2ARGF3040 | DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 38 | No | DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3065, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ3ACGF4610, DUKHCONP2BZ3ARGF3030, DUKHCONP2BZ3ARGF3030, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3080, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ3ACGF4610, DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ3ARGF3090, DUKHCONP2BZ3ARGF3090, DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ3ARGF3080 | DUKHCONP2BZ3ACTC8000, DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ3PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3045 | Fixing of Suspension systems | 15 | 15 | 0% | 2013-12-16 | 2014-01-02 | 2013-12-16 | 2014-01-02 | 6 | No | DUKHCONP2BZ3ELGF4010, DUKHCONP2BZ3ARGF3030, DUKHCONP2BZ3ARGF3025, DUKHCONP2BZ3ELGF4010, DUKHCONP2BZ3ARGF3030, DUKHCONP2BZ3ARGF3025 | DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3010 | Flooring screed | 20 | 20 | 0% | 2013-10-02 | 2013-10-27 | 2013-10-02 | 2013-10-27 | 35 | No | DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3ARGF3005 | DUKHCONP2BZ3ARGF3025, DUKHCONP2BZ3ARGF3025, DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ3ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3060 | Gypsum board false ceiling | 20 | 20 | 0% | 2014-01-02 | 2014-01-25 | 2014-01-02 | 2014-01-25 | 6 | No | DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ARGF3045, DUKHCONP2BZ3ARGF3045 | DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3PLGF4320, DUKHCONP2BZ3ARGF3065, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3PLGF4320, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ELGF4015, DUKHCONP2BZ3ELGF4025, DUKHCONP2BZ3ACGF4605, DUKHCONP2BZ3ARGF3065, DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3ELGF4025, DUKHCONP2BZ3ELGF4030, DUKHCONP2BZ3ELGF4030, DUKHCONP2BZ3ACGF4605, DUKHCONP2BZ3ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-02-26 | 2014-03-15 | 2014-02-26 | 2014-03-15 | 8 | No | DUKHCONP2BZ3ARGF3075, DUKHCONP2BZ3ARGF3075, DUKHCONP2AZ2ARGF3090 | DUKHCONP2BZ4ARGF3090, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3030 | Paint First coat | 20 | 20 | 0% | 2013-11-24 | 2013-12-16 | 2013-11-24 | 2013-12-16 | 6 | No | DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3ARGF3005, DUKHCONP2AZ2ARGF3030 | DUKHCONP2BZ4ARGF3030, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3045, DUKHCONP2BZ3ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-09-21 | 2013-10-21 | 2013-09-21 | 2013-10-21 | 5 | No | DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ3ELGF4000, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3ELGF4000 | DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ARGF3015, DUKHCONP2BZ3ARGF3030, DUKHCONP2BZ3ARGF3030, DUKHCONP2BZ3ARGF3015, DUKHCONP2BZ3ARGF3010, DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3025 | Porcelain Tile flooring | 20 | 20 | 0% | 2013-11-11 | 2013-12-03 | 2013-11-11 | 2013-12-03 | 17 | No | DUKHCONP2BZ3ARGF3010, DUKHCONP2BZ3ARGF3020, DUKHCONP2BZ3ARGF3020, DUKHCONP2BZ3ARGF3010 | DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ4ARGF3025, DUKHCONP2BZ3ARGF3045, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ3ARGF3045, DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ3ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3035 | Slate Tile Flooring & Skirting | 18 | 18 | 0% | 2014-01-11 | 2014-01-30 | 2014-01-11 | 2014-01-30 | 13 | No | DUKHCONP2BZ3ARGF3010, DUKHCONP2BZ3ARGF3025, DUKHCONP2AZ2ARGF3035, DUKHCONP2BZ3ARGF3010, DUKHCONP2BZ3ARGF3025 | DUKHCONP2BZ3ARGF3065, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3065, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ3ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3015 | Wet area waterproofing & Protection Screed | 20 | 20 | 0% | 2013-10-05 | 2013-10-29 | 2013-10-05 | 2013-10-29 | 17 | No | DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3ARGF3005 | DUKHCONP2BZ3ARGF3020, DUKHCONP2BZ3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ARGF3065 | Wooden door | 15 | 15 | 0% | 2014-01-22 | 2014-02-08 | 2014-01-22 | 2014-02-08 | 17 | No | DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ3ARGF3060 | DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3080, DUKHCONP2BZ3PLGF4315, DUKHCONP2BZ3ARGF3075, DUKHCONP2BZ3ARGF3075, DUKHCONP2BZ3PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.20 .15 .15 EXTERNAL FINISHES |  | 77 | 77 | 0% | 2013-10-31 | 2014-01-29 | 2013-10-31 | 2014-01-29 | 50 |  |  |  | 0 | 0
DHBL.K30.L45.20 .15 .15 .10 ROOF |  | 53 | 53 | 0% | 2013-10-31 | 2014-01-01 | 2013-10-31 | 2014-01-01 | 64 |  |  |  | 0 | 0
DUKHCONP2BZ3ARRF3660 | Installation of Access Ladder | 20 | 20 | 0% | 2013-12-09 | 2014-01-01 | 2013-12-09 | 2014-01-01 | 64 | No | DUKHCONP2BZ3ARRF3645, DUKHCONP2BZ3ARRF3645, DUKHCONP2AZ2ARRF3660 | DUKHCONP2BZ3PLTC8005, DUKHCONP2BZ3ACTC8000, DUKHCONP2BZ4ARRF3660, DUKHCONP2BZ3AREL3680, DUKHCONP2BZ3ELTC8010 | 0 | 0 | ROOF
DUKHCONP2BZ3ARRF3640 | Installation of Insulation & Protection | 18 | 18 | 0% | 2013-11-25 | 2013-12-15 | 2013-11-25 | 2013-12-15 | 30 | No | DUKHCONP2AZ2ARRF3640, DUKHCONP2BZ3ARRF3635, DUKHCONP2BZ3ARRF3635 | DUKHCONP2BZ3ARRF3645, DUKHCONP2BZ3ARRF3645, DUKHCONP2BZ4ARRF3640 | 0 | 0 | ROOF
DUKHCONP2BZ3ARRF3625 | Laying of Pitched Roof | 25 | 25 | 0% | 2013-10-31 | 2013-11-28 | 2013-10-31 | 2013-11-28 | 30 | No | DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3STRF2060, DUKHCONP2AZ2ARRF3625, DUKHCONP2BZ3STRF2060 | DUKHCONP2BZ3ARRF3630, DUKHCONP2BZ3ARRF3630, DUKHCONP2BZ4ARRF3625 | 0 | 0 | ROOF
DUKHCONP2BZ3ARRF3635 | Laying of Waterproofing Membrane | 18 | 18 | 0% | 2013-11-20 | 2013-12-10 | 2013-11-20 | 2013-12-10 | 30 | No | DUKHCONP2BZ3ARRF3630, DUKHCONP2BZ3ARRF3630 | DUKHCONP2BZ3ARRF3640, DUKHCONP2BZ3ARRF3640 | 0 | 0 | ROOF
DUKHCONP2BZ3ARRF3630 | Leveling Screed for Waterproofing | 18 | 18 | 0% | 2013-11-14 | 2013-12-04 | 2013-11-14 | 2013-12-04 | 30 | No | DUKHCONP2BZ3ARRF3625, DUKHCONP2BZ3ARRF3625 | DUKHCONP2BZ3ARRF3635, DUKHCONP2BZ3ARRF3635 | 0 | 0 | ROOF
DUKHCONP2BZ3ARRF3645 | Lime Stone Chips & Paving slab Installation | 18 | 18 | 0% | 2013-12-03 | 2013-12-24 | 2013-12-03 | 2013-12-24 | 30 | No | DUKHCONP2BZ3ARRF3640, DUKHCONP2BZ3ARRF3640 | DUKHCONP2BZ3ARRF3660, DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3ARRF3660, DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ3AREL3665, DUKHCONP2BZ3ACRF4630, DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ3ACRF4630, DUKHCONP2BZ3AREL3665, DUKHCONP2BZ3PLRF4350 | 0 | 0 | ROOF
DHBL.K30.L45.20 .15 .15 .15 ELEVATION |  | 39 | 39 | 0% | 2013-12-15 | 2014-01-29 | 2013-12-15 | 2014-01-29 | 50 |  |  |  | 0 | 0
DUKHCONP2BZ3AREL3680 | External Painting | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 50 | No | DUKHCONP2BZ3AREL3665, DUKHCONP2AZ2AREL3680, DUKHCONP2BZ3ARRF3660, DUKHCONP2BZ3AREL3665 | DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ4AREL3680, DUKHCONP2BZ3PLTC8005, DUKHCONP2BZ3ACTC8000 | 0 | 0 | ELEVATION
DUKHCONP2BZ3AREL3665 | External Plastering | 25 | 25 | 0% | 2013-12-15 | 2014-01-13 | 2013-12-15 | 2014-01-13 | 30 | No | DUKHCONP2BZ3ARRF3645, DUKHCONP2AZ2AREL3665, DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3ARRF3645 | DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3AREL3680, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ3AREL3680, DUKHCONP2BZ3PLRF4350 | 0 | 0 | ELEVATION
DHBL.K30.L45.20 .20 MEP WORKS |  | 243 | 243 | 0% | 2013-06-04 | 2014-03-22 | 2013-06-04 | 2014-03-22 | 47 |  |  |  | 0 | 0
DHBL.K30.L45.20 .20 .10 ELECTRICAL WORKS |  | 152 | 152 | 0% | 2013-09-15 | 2014-03-15 | 2013-09-15 | 2014-03-15 | 13 |  |  |  | 0 | 0
DHBL.K30.L45.20 .20 .10 .10 GROUND FLOOR |  | 152 | 152 | 0% | 2013-09-15 | 2014-03-15 | 2013-09-15 | 2014-03-15 | 13 |  |  |  | 0 | 0
DUKHCONP2BZ3ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-11-07 | 2013-11-30 | 2013-11-07 | 2013-11-30 | 13 | No | DUKHCONP2BZ3ELGF4000, DUKHCONP2AZ2ELGF4005, DUKHCONP2BZ3ELGF4000 | DUKHCONP2BZ3ELGF4010, DUKHCONP2BZ4ELGF4005, DUKHCONP2BZ3ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ELGF4000 | Fixing of wall conduits & switch socket boxes | 20 | 20 | 0% | 2013-09-15 | 2013-10-07 | 2013-09-15 | 2013-10-07 | 5 | No | DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ3ARGF3000 | DUKHCONP2BZ3ELGF4005, DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3ELGF4005, DUKHCONP2BZ3ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 20 | 20 | 0% | 2014-02-20 | 2014-03-15 | 2014-02-20 | 2014-03-15 | 13 | No | DUKHCONP2AZ2ELGF4015, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3060 | DUKHCONP2BZ4ELGF4015, DUKHCONP2BZ3ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-01-11 | 2014-02-02 | 2014-01-11 | 2014-02-02 | 15 | No | DUKHCONP2BZ3ELGF4010, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ELGF4010, DUKHCONP2BZ3ARGF3060 | DUKHCONP2BZ3ELGF4025, DUKHCONP2BZ4ELGF4020, DUKHCONP2BZ3ELGF4025, DUKHCONP2BZ3ELGF4030, DUKHCONP2BZ3ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ELGF4025 | Installation of Lighting fixtures & Accessories | 20 | 20 | 0% | 2014-01-22 | 2014-02-15 | 2014-01-22 | 2014-02-15 | 15 | No | DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3060 | DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ3ELRF4070 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-01-22 | 2014-02-15 | 2014-01-22 | 2014-02-15 | 18 | No | DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3MSEX5010 | DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ4ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ELGF4010 | Installation of wiring & Main Cabling | 20 | 20 | 0% | 2013-11-16 | 2013-12-08 | 2013-11-16 | 2013-12-08 | 13 | No | DUKHCONP2BZ3ELGF4005, DUKHCONP2BZ3ELGF4005 | DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ3ARGF3045, DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ3ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.20 .20 .10 .20 ROOF |  | 30 | 30 | 0% | 2014-02-05 | 2014-03-12 | 2014-02-05 | 2014-03-12 | 15 |  |  |  | 0 | 0
DUKHCONP2BZ3ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-02-05 | 2014-02-26 | 2014-02-05 | 2014-02-26 | 15 | No | DUKHCONP2BZ3ELGF4010, DUKHCONP2BZ3ELGF4025, DUKHCONP2BZ3ELGF4030, DUKHCONP2BZ3ARRF3645, DUKHCONP2BZ3ELGF4030, DUKHCONP2BZ3ELGF4010, DUKHCONP2BZ3ELGF4025, DUKHCONP2BZ3ARRF3645 | DUKHCONP2BZ3ELRF4075, DUKHCONP2BZ3ELRF4075 | 0 | 0 | ROOF
DUKHCONP2BZ3ELRF4075 | Installation of TV Dish Antenna | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 15 | No | DUKHCONP2BZ3ELRF4070, DUKHCONP2BZ3ELRF4070 | DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ4ELRF4075 | 0 | 0 | ROOF
DHBL.K30.L45.20 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 243 | 243 | 0% | 2013-06-04 | 2014-03-22 | 2013-06-04 | 2014-03-22 | 47 |  |  |  | 0 | 0
DHBL.K30.L45.20 .20 .15 .10 GROUND FLOOR |  | 243 | 243 | 0% | 2013-06-04 | 2014-03-22 | 2013-06-04 | 2014-03-22 | 47 |  |  |  | 0 | 0
DUKHCONP2BZ3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-06-04 | 2013-06-26 | 2013-06-04 | 2013-06-26 | 2 | No | DUKHCONP2BZ3STUG1040, DUKHCONP2BZ3STUG1040 | DUKHCONP2BZ3STUG1045, DUKHCONP2BZ3STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-09-17 | 2013-10-07 | 2013-09-17 | 2013-10-07 | 30 | No | DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3ARGF3000 | DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3MSEX5000, DUKHCONP2BZ3PLGF4315, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ3MSEX5000, DUKHCONP2BZ3ARGF3020, DUKHCONP2BZ3ARGF3020, DUKHCONP2BZ3PLGF4315 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3PLGF4305 | Installation of Plumbing pipes & testing | 20 | 20 | 0% | 2013-09-15 | 2013-10-07 | 2013-09-15 | 2013-10-07 | 5 | No | DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ3ARGF3000 | DUKHCONP2BZ3ARGF3020, DUKHCONP2BZ3ARGF3020, DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-03-05 | 2014-03-22 | 2014-03-05 | 2014-03-22 | 47 | No | DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3PLGF4315, DUKHCONP2BZ3PLGF4315 | DUKHCONP2BZ3PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-02-22 | 2014-03-16 | 2014-02-22 | 2014-03-16 | 7 | No | DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3ARGF3065, DUKHCONP2AZ2PLGF4315, DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3ARGF3065 | DUKHCONP2BZ4PLGF4315, DUKHCONP2BZ3PLGF4320, DUKHCONP2BZ3PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.20 .20 .15 .20 ROOF |  | 15 | 15 | 0% | 2014-01-11 | 2014-01-27 | 2014-01-11 | 2014-01-27 | 35 |  |  |  | 0 | 0
DUKHCONP2BZ3PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-01-11 | 2014-01-27 | 2014-01-11 | 2014-01-27 | 35 | No | DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3AREL3665, DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3ARRF3645, DUKHCONP2BZ3PLGF4305, DUKHCONP2AZ2PLRF4350, DUKHCONP2BZ3AREL3665, DUKHCONP2BZ3PLGF4305, DUKHCONP2BZ3ARRF3645 | DUKHCONP2BZ3WEEX5065, DUKHCONP2BZ3PLTC8005, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ3WEEX5065 | 0 | 0 | ROOF
DHBL.K30.L45.20 .20 .20 AC WORKS |  | 94 | 94 | 0% | 2013-11-20 | 2014-03-11 | 2013-11-20 | 2014-03-11 | 16 |  |  |  | 0 | 0
DHBL.K30.L45.20 .20 .20 .10 GROUND FLOOR |  | 89 | 89 | 0% | 2013-11-20 | 2014-03-05 | 2013-11-20 | 2014-03-05 | 16 |  |  |  | 0 | 0
DUKHCONP2BZ3ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-02-10 | 2014-03-05 | 2014-02-10 | 2014-03-05 | 16 | No | DUKHCONP2BZ3ACGF4605, DUKHCONP2BZ3ACGF4605 | DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3ACRF4635, DUKHCONP2BZ3ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 16 | No | DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ARGF3060 | DUKHCONP2BZ3ACGF4610, DUKHCONP2BZ3ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ3ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-11-20 | 2013-12-12 | 2013-11-20 | 2013-12-12 | 28 | No | DUKHCONP2AZ2ACGF4600, DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ3ARGF3005 | DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ3ACGF4605, DUKHCONP2BZ3ACRF4630, DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ3ACGF4605, DUKHCONP2BZ3ACRF4630 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.20 .20 .20 .20 ROOF |  | 69 | 69 | 0% | 2013-12-21 | 2014-03-11 | 2013-12-21 | 2014-03-11 | 16 |  |  |  | 0 | 0
DUKHCONP2BZ3ACRF4635 | Installation of Condensing Unit | 20 | 20 | 0% | 2014-02-17 | 2014-03-11 | 2014-02-17 | 2014-03-11 | 16 | No | DUKHCONP2BZ3ACRF4630, DUKHCONP2BZ3ACRF4630, DUKHCONP2BZ3ACGF4610, DUKHCONP2BZ3ACGF4610 | DUKHCONP2BZ3ACTC8000, DUKHCONP2BZ4ACRF4635 | 0 | 0 | ROOF
DUKHCONP2BZ3ACRF4630 | Installation of Refrigerant Pipes | 20 | 20 | 0% | 2013-12-21 | 2014-01-12 | 2013-12-21 | 2014-01-12 | 55 | No | DUKHCONP2AZ2ACRF4630, DUKHCONP2BZ3ARRF3645, DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ3ARRF3645 | DUKHCONP2BZ3ACRF4635, DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ3ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L45.20 .25 EXTERNAL WORKS |  | 139 | 139 | 0% | 2013-10-03 | 2014-03-18 | 2013-10-03 | 2014-03-18 | 50 |  |  |  | 0 | 0
DHBL.K30.L45.20 .25 .10 MISCELLANEOUS |  | 74 | 74 | 0% | 2013-10-03 | 2013-12-31 | 2013-10-03 | 2013-12-31 | 36 |  |  |  | 0 | 0
DUKHCONP2BZ3MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-10-20 | 2013-11-17 | 2013-10-20 | 2013-11-17 | 36 | No | DUKHCONP2BZ3MSEX5000, DUKHCONP2BZ3MSEX5000 | DUKHCONP2BZ3ACTC8000, DUKHCONP2BZ3MSEX5015, DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ3MSEX5015, DUKHCONP2BZ3PLTC8005 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ3MSEX5020 | Construction Entrance Ramp | 20 | 20 | 0% | 2013-11-09 | 2013-12-01 | 2013-11-09 | 2013-12-01 | 30 | No | DUKHCONP2BZ3STRF2065, DUKHCONP2AZ2MSEX5020, DUKHCONP2BZ3STRF2065 | DUKHCONP2BZ3HDEX5090, DUKHCONP2BZ3MSEX5055, DUKHCONP2BZ4MSEX5020, DUKHCONP2BZ3MSEX5025, DUKHCONP2BZ3HDEX5090, DUKHCONP2BZ3MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ3MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2013-11-09 | 2013-12-01 | 2013-11-09 | 2013-12-01 | 36 | No | DUKHCONP2BZ3MSEX5005, DUKHCONP2BZ3MSEX5005 | DUKHCONP2BZ3MSEX5010, DUKHCONP2BZ3WEEX5065, DUKHCONP2BZ3WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ3MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-10-03 | 2013-11-03 | 2013-10-03 | 2013-11-03 | 26 | No | DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3STRF2065 | DUKHMOBP2BPS00002240, DUKHCONP2BZ4MSEX5000, DUKHCONP2BZ3MSEX5005, DUKHCONP2BZ3MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ3MSEX5055 | Installation Steel Door | 20 | 20 | 0% | 2013-11-20 | 2013-12-12 | 2013-11-20 | 2013-12-12 | 30 | No | DUKHCONP2BZ3MSEX5020 | DUKHCONP2BZ3MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ3MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2013-12-02 | 2013-12-25 | 2013-12-02 | 2013-12-25 | 30 | No | DUKHCONP2BZ3MSEX5020, DUKHCONP2BZ3MSEX5055, DUKHCONP2BZ3MSEX5020, DUKHCONP2AZ2MSEX5025 | DUKHCONP2BZ3WEEX5050, DUKHCONP2BZ3WEEX5050, DUKHCONP2BZ3HDEX5090, DUKHCONP2BZ4MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ3MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2013-12-02 | 2013-12-31 | 2013-12-02 | 2013-12-31 | 36 | No | DUKHCONP2BZ3MSEX5015 | DUKHCONP2BZ3ELGF4030 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L45.20 .25 .15 WATER TANK ENCLOSURE |  | 107 | 107 | 0% | 2013-11-12 | 2014-03-18 | 2013-11-12 | 2014-03-18 | 25 |  |  |  | 0 | 0
DUKHCONP2BZ3MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 43 | No | DUKHCONI2BZ1BWGL5325 | DUKHCONP2BZ4MSEX5335 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 35 | No | DUKHCONP2BZ3WEEX5035, DUKHCONP2BZ3WEEX5035 | DUKHCONP2BZ3WEEX5045, DUKHCONP2BZ3WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2013-11-20 | 2013-12-19 | 2013-11-20 | 2013-12-19 | 15 | No | DUKHCONP2BZ3WEEX5030, DUKHCONP2BZ3WEEX5030 | DUKHCONP2BZ4WEEX5030, DUKHCONP2BZ3WEEX5040, DUKHCONP2BZ3WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5030 | Excavation | 20 | 20 | 0% | 2013-11-12 | 2013-12-04 | 2013-11-12 | 2013-12-04 | 15 | No | DUKHCONP2AZ2WEEX5030, DUKHCONP2BZ3STRF2065, DUKHCONP2BZ3STRF2065 | DUKHCONP2BZ3WEEX5035, DUKHCONP2BZ3WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2013-12-11 | 2014-01-09 | 2013-12-11 | 2014-01-09 | 35 | No | DUKHCONP2BZ3WEEX5040, DUKHCONP2BZ3WEEX5040 | DUKHCONP2BZ3WEEX5050, DUKHCONP2BZ3WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 10 | No | DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3WEEX5060, DUKHCONP2BZ3WEEX5060, DUKHCONP2BZ3MSEX5015, DUKHCONP2AZ2WEEX5065, DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3MSEX5015 | DUKHCONP2BZ3PLTC8005, DUKHCONP2BZ3WEEX5070 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5070 | Installation ladder for water Tank | 20 | 20 | 0% | 2014-02-24 | 2014-03-18 | 2014-02-24 | 2014-03-18 | 10 | No | DUKHCONP2AZ2WEEX5070, DUKHCONP2BZ3WEEX5065 | DUKHCONP2BZ4WEEX5070 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2013-12-30 | 2014-01-21 | 2013-12-30 | 2014-01-21 | 35 | No | DUKHCONP2BZ3MSEX5025, DUKHCONP2BZ3MSEX5025, DUKHCONP2BZ3WEEX5045, DUKHCONP2AZ2WEEX5050, DUKHCONP2BZ3WEEX5045 | DUKHCONP2BZ3WEEX5060, DUKHCONP2BZ3WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ3WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 35 | No | DUKHCONP2BZ3WEEX5050, DUKHCONP2BZ3WEEX5050 | DUKHCONP2BZ3WEEX5065, DUKHCONP2BZ3WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L45.20 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2013-12-10 | 2014-01-29 | 2013-12-10 | 2014-01-29 | 30 |  |  |  | 0 | 0
DUKHCONP2BZ3HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2013-12-23 | 2014-01-14 | 2013-12-23 | 2014-01-14 | 30 | No | DUKHCONP2BZ3HDEX5090, DUKHCONP2BZ3HDEX5090 | DUKHCONP2BZ3HDEX5100, DUKHCONP2BZ3HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2BZ3HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 30 | No | DUKHCONP2BZ3HDEX5095, DUKHCONP2BZ3HDEX5095 | DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ3PLTC8005, DUKHCONP2BZ3SLEX5105, DUKHCONP2BZ3SLEX5105, DUKHCONP2BZ3ACTC8000 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2BZ3HDEX5090 | kerb works | 20 | 20 | 0% | 2013-12-10 | 2014-01-02 | 2013-12-10 | 2014-01-02 | 30 | No | DUKHCONP2BZ3MSEX5020, DUKHCONP2AZ2HDEX5090, DUKHCONP2BZ3MSEX5020, DUKHCONP2BZ3MSEX5025 | DUKHCONP2BZ3HDEX5095, DUKHCONP2BZ3HDEX5095, DUKHCONP2BZ4HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L45.20 .25 .25 SOFT LANDSCAPING |  | 30 | 30 | 0% | 2014-01-29 | 2014-03-05 | 2014-01-29 | 2014-03-05 | 61 |  |  |  | 0 | 0
DUKHCONP2BZ3SLEX5105 | Laying of Grass/ green area | 20 | 20 | 0% | 2014-01-29 | 2014-02-22 | 2014-01-29 | 2014-02-22 | 21 | No | DUKHCONP2BZ3HDEX5100, DUKHCONP2AZ2SLEX5105, DUKHCONP2BZ3HDEX5100 | DUKHCONP2BZ3SLEX5110, DUKHCONP2BZ3SLEX5110, DUKHCONP2BZ3ACTC8000, DUKHCONP2BZ3PLTC8005, DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ4SLEX5105 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP2BZ3SLEX5110 | Laying of Palm tree | 20 | 20 | 0% | 2014-02-10 | 2014-03-05 | 2014-02-10 | 2014-03-05 | 61 | No | DUKHCONP2BZ3SLEX5105, DUKHCONP2BZ3SLEX5105, DUKHCONP2AZ2SLEX5110 | DUKHCONP2BZ3ACTC8000, DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ3PLTC8005 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L45.20 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 38 |  |  |  | 0 | 0
DUKHCONP2BZ3ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 38 | No | DUKHCONP2BZ3ARRF3660, DUKHCONP2BZ3MSEX5005, DUKHCONP2BZ3SLEX5110, DUKHCONP2BZ3ACRF4635, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3AREL3680, DUKHCONP2BZ3SLEX5105, DUKHCONP2BZ3HDEX5100 | DUKHHANP2BGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2BZ3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 38 | No | DUKHCONP2BZ3AREL3680, DUKHCONP2BZ3HDEX5100, DUKHCONP2BZ3ELGF4030, DUKHCONP2BZ3MSEX5005, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3SLEX5110, DUKHCONP2BZ3ELGF4025, DUKHCONP2BZ3ARRF3660, DUKHCONP2BZ3ELGF4015, DUKHCONP2BZ3ELRF4075, DUKHCONP2BZ3SLEX5105 | DUKHHANP2BGNACTC9000, DUKHHANP2BGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2BZ3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 38 | No | DUKHCONP2BZ3PLGF4320, DUKHCONP2BZ3ARRF3660, DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ3AREL3680, DUKHCONP2BZ3WEEX5065, DUKHCONP2BZ3HDEX5100, DUKHCONP2BZ3MSEX5005, DUKHCONP2BZ3ARGF3095, DUKHCONP2BZ3SLEX5105, DUKHCONP2BZ3SLEX5110 | DUKHHANP2BGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L45.25 ZONE- 4 (3 Twin Villas) |  | 340 | 340 | 0% | 2013-04-09 | 2014-05-18 | 2013-04-09 | 2014-05-18 | 23 |  |  |  | 0 | 0
DHBL.K30.L45.25 .10 STRUCTURAL WORKS |  | 184 | 184 | 0% | 2013-04-09 | 2013-11-14 | 2013-04-09 | 2013-11-14 | 31 |  |  |  | 0 | 0
DHBL.K30.L45.25 .10 .10 SUB STRUCTURE |  | 107 | 107 | 0% | 2013-04-09 | 2013-08-14 | 2013-04-09 | 2013-08-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L45.25 .10 .10 .10 UPTO GRADE SLAB |  | 107 | 107 | 0% | 2013-04-09 | 2013-08-14 | 2013-04-09 | 2013-08-14 | 0 |  |  |  | 0 | 0
DUKHCONP2BZ4STUG1035 | Backfilling Upto Grade Beam Bottom | 20 | 20 | 0% | 2013-06-08 | 2013-06-30 | 2013-06-08 | 2013-06-30 | 0 | Yes | DUKHCONP2BZ4STUG1030, DUKHCONP2BZ4STUG1030, DUKHCONP2BZ3STUG1035 | DUKHCONP2BZ4STUG1040, DUKHCONP2BZ5STUG1035, DUKHCONP2BZ4STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-05-08 | 2013-05-30 | 2013-05-08 | 2013-05-30 | 0 | Yes | DUKHCONP2BZ4STUG1015, DUKHCONP2BZ3STUG1020, DUKHCONP2BZ4STUG1015 | DUKHCONP2BZ4STUG1025, DUKHCONP2BZ4STUG1025, DUKHCONP2BZ5STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-06-19 | 2013-07-17 | 2013-06-19 | 2013-07-17 | 0 | Yes | DUKHCONP2BZ4STUG1035, DUKHCONP2BZ3STUG1040, DUKHCONP2BZ4STUG1035 | DUKHCONP2BZ4STUG1045, DUKHCONP2BZ4PLUG4300, DUKHCONP2BZ4PLUG4300, DUKHCONP2BZ4STUG1045, DUKHCONP2BZ5STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1025 | Construction of neck of columns | 20 | 20 | 0% | 2013-05-18 | 2013-06-09 | 2013-05-18 | 2013-06-09 | 0 | Yes | DUKHCONP2BZ4STUG1020, DUKHCONP2BZ4STUG1020 | DUKHCONP2BZ4STUG1030, DUKHCONP2BZ4STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-07-14 | 2013-08-14 | 2013-07-14 | 2013-08-14 | 0 | Yes | DUKHCONP2BZ4PLUG4300, DUKHCONP2BZ4STUG1040, DUKHCONP2BZ4STUG1040, DUKHCONP2BZ4PLUG4300 | DUKHCONP2BZ4STGF2000, DUKHCONP2BZ4STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1005 | Footing Antitermite | 20 | 20 | 0% | 2013-04-21 | 2013-05-13 | 2013-04-21 | 2013-05-13 | 0 | Yes | DUKHCONP2BZ4STUG1000, DUKHCONP2BZ4STUG1000 | DUKHCONP2BZ4STUG1010, DUKHCONP2BZ4STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1010 | Footing Blinding | 20 | 20 | 0% | 2013-04-23 | 2013-05-15 | 2013-04-23 | 2013-05-15 | 0 | Yes | DUKHCONP2BZ4STUG1005, DUKHCONP2BZ4STUG1005 | DUKHCONP2BZ4STUG1015, DUKHCONP2BZ4STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-04-09 | 2013-05-07 | 2013-04-09 | 2013-05-07 | 0 | Yes | DUKHCONP2BZ3STUG1000 | DUKHCONP2BZ5STUG1000, DUKHCONP2BZ4STUG1005, DUKHCONP2BZ4STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1015 | Footing Waterproofing & Screed | 20 | 20 | 0% | 2013-04-29 | 2013-05-21 | 2013-04-29 | 2013-05-21 | 0 | Yes | DUKHCONP2BZ4STUG1010, DUKHCONP2BZ4STUG1010 | DUKHCONP2BZ4STUG1020, DUKHCONP2BZ4STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ4STUG1030 | Waterproofing Footing & Neck Column | 20 | 20 | 0% | 2013-05-27 | 2013-06-18 | 2013-05-27 | 2013-06-18 | 0 | Yes | DUKHCONP2BZ4STUG1025, DUKHCONP2BZ4STUG1025 | DUKHCONP2BZ4STUG1035, DUKHCONP2BZ4STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L45.25 .10 .15 SUPERSTRUCTURE |  | 87 | 87 | 0% | 2013-07-31 | 2013-11-14 | 2013-07-31 | 2013-11-14 | 31 |  |  |  | 0 | 0
DHBL.K30.L45.25 .10 .15 .10 GROUND FLOOR |  | 45 | 45 | 0% | 2013-07-31 | 2013-09-24 | 2013-07-31 | 2013-09-24 | 0 |  |  |  | 0 | 0
DUKHCONP2BZ4STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-09-08 | 2013-09-24 | 2013-09-08 | 2013-09-24 | 0 | Yes | DUKHCONP2BZ4STGF2010, DUKHCONP2BZ4STGF2010, DUKHCONP2BZ3STGF2015 | DUKHCONP2BZ4STRF2060, DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ5STGF2015, DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ4STRF2060 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-08-22 | 2013-09-19 | 2013-08-22 | 2013-09-19 | 0 | Yes | DUKHCONP2BZ4STGF2005, DUKHCONP2BZ4STGF2005 | DUKHCONP2BZ4STGF2015, DUKHCONP2BZ4STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4STGF2005 | Column-Concrete | 15 | 15 | 0% | 2013-08-14 | 2013-08-31 | 2013-08-14 | 2013-08-31 | 0 | Yes | DUKHCONP2BZ4STGF2000, DUKHCONP2BZ4STGF2000 | DUKHCONP2BZ4STGF2010, DUKHCONP2BZ4STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4STGF2000 | Column-Rebar & Formwork | 20 | 20 | 0% | 2013-07-31 | 2013-08-26 | 2013-07-31 | 2013-08-26 | 0 | Yes | DUKHCONP2BZ3STGF2000, DUKHCONP2BZ4STUG1045, DUKHCONP2BZ4STUG1045 | DUKHCONP2BZ4STGF2005, DUKHCONP2BZ5STGF2000, DUKHCONI2BZ1DRGL5115, DUKHCONP2BZ4STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.25 .10 .15 .20 ROOF |  | 26 | 26 | 0% | 2013-10-14 | 2013-11-14 | 2013-10-14 | 2013-11-14 | 31 |  |  |  | 0 | 0
DUKHCONP2BZ4STRF2060 | Construction of Parapets | 20 | 20 | 0% | 2013-10-14 | 2013-11-07 | 2013-10-14 | 2013-11-07 | 19 | No | DUKHCONP2BZ4STGF2015, DUKHCONP2BZ3STRF2060, DUKHCONP2BZ4STGF2015 | DUKHCONP2BZ4STRF2065, DUKHCONP2BZ4ARRF3625, DUKHCONP2BZ5STRF2060, DUKHCONP2BZ4ARRF3625, DUKHCONP2BZ4STRF2065 | 0 | 0 | ROOF
DUKHCONP2BZ4STRF2065 | Construction of up stands/Plinth | 20 | 20 | 0% | 2013-10-23 | 2013-11-14 | 2013-10-23 | 2013-11-14 | 31 | No | DUKHCONP2BZ4STRF2060, DUKHCONP2BZ4STRF2060 | DUKHCONP2BZ4MSEX5020, DUKHCONP2BZ4MSEX5020, DUKHCONP2BZ4ARRF3625, DUKHCONP2BZ4MSEX5000, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ4WEEX5030, DUKHCONP2BZ4MSEX5000, DUKHCONP2BZ4WEEX5030, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ4ARRF3625 | 0 | 0 | ROOF
DHBL.K30.L45.25 .15 FINISHING WORKS |  | 167 | 167 | 0% | 2013-10-02 | 2014-04-19 | 2013-10-02 | 2014-04-19 | 23 |  |  |  | 0 | 0
DHBL.K30.L45.25 .15 .10 INTERNAL FINISHES |  | 167 | 167 | 0% | 2013-10-02 | 2014-04-19 | 2013-10-02 | 2014-04-19 | 23 |  |  |  | 0 | 0
DHBL.K30.L45.25 .15 .10 .10 GROUND FLOOR |  | 167 | 167 | 0% | 2013-10-02 | 2014-04-19 | 2013-10-02 | 2014-04-19 | 23 |  |  |  | 0 | 0
DUKHCONP2BZ4ARGF3080 | Aluminum windows | 18 | 18 | 0% | 2014-03-03 | 2014-03-23 | 2014-03-03 | 2014-03-23 | 31 | No | DUKHCONP2BZ4ARGF3065 | DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3000 | Block work | 25 | 25 | 0% | 2013-10-02 | 2013-11-02 | 2013-10-02 | 2013-11-02 | 0 | Yes | DUKHCONP2BZ4STGF2015, DUKHCONP2BZ3ARGF3000, DUKHCONP2BZ4STGF2015 | DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4ELGF4000, DUKHCONP2BZ4ELGF4000, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3075 | Carpentry & Joinery Works | 18 | 18 | 0% | 2014-02-19 | 2014-03-11 | 2014-02-19 | 2014-03-11 | 17 | No | DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ3ARGF3075 | DUKHCONP2BZ5ARGF3075, DUKHCONP2BZ4ARGF3090, DUKHCONP2BZ4ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3020 | Ceramic Wall Tiling | 15 | 15 | 0% | 2013-12-02 | 2013-12-19 | 2013-12-02 | 2013-12-19 | 5 | No | DUKHCONP2BZ4ARGF3015, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4ARGF3015 | DUKHCONP2BZ4ARGF3025, DUKHCONP2BZ4ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-02-20 | 2014-03-09 | 2014-02-20 | 2014-03-09 | 20 | No | DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ3ARGF3040, DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3025, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3025 | DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ5ARGF3040, DUKHCONP2BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 23 | No | DUKHCONP2BZ4ACGF4610, DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ4ARGF3080, DUKHCONP2BZ4ACGF4610, DUKHCONP2BZ4ARGF3030, DUKHCONP2BZ4ARGF3030, DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3090, DUKHCONP2BZ4ARGF3080, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ARGF3090 | DUKHCONP2BZ4PLTC8005, DUKHCONP2BZ4ELTC8010, DUKHCONP2BZ4ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3045 | Fixing of Suspension systems | 15 | 15 | 0% | 2014-01-11 | 2014-01-27 | 2014-01-11 | 2014-01-27 | 5 | No | DUKHCONP2BZ4ARGF3030, DUKHCONP2BZ4ARGF3030, DUKHCONP2BZ4ARGF3025, DUKHCONP2BZ4ELGF4010, DUKHCONP2BZ4ELGF4010, DUKHCONP2BZ4ARGF3025 | DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3010 | Flooring screed | 20 | 20 | 0% | 2013-11-09 | 2013-12-01 | 2013-11-09 | 2013-12-01 | 25 | No | DUKHCONP2BZ3ARGF3010, DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4ARGF3005 | DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3025, DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ5ARGF3010, DUKHCONP2BZ4ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3060 | Gypsum board false ceiling | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 5 | No | DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ3ARGF3060, DUKHCONP2BZ4ARGF3045, DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ4ARGF3045 | DUKHCONP2BZ4ELGF4020, DUKHCONP2BZ4ELGF4030, DUKHCONP2BZ4ELGF4025, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ4ELGF4015, DUKHCONP2BZ4ACGF4605, DUKHCONP2BZ4ELGF4025, DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ4ELGF4030, DUKHCONP2BZ4PLGF4320, DUKHCONP2BZ4ACGF4605, DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ4PLGF4320, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ELGF4015, DUKHCONP2BZ4ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-03-16 | 2014-04-01 | 2014-03-16 | 2014-04-01 | 8 | No | DUKHCONP2BZ3ARGF3090, DUKHCONP2BZ4ARGF3075, DUKHCONP2BZ4ARGF3075 | DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ5ARGF3090, DUKHCONP2BZ4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3030 | Paint First coat | 20 | 20 | 0% | 2013-12-17 | 2014-01-09 | 2013-12-17 | 2014-01-09 | 6 | No | DUKHCONP2BZ3ARGF3030, DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4ARGF3005 | DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3045, DUKHCONP2BZ5ARGF3030, DUKHCONP2BZ4ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-10-28 | 2013-11-25 | 2013-10-28 | 2013-11-25 | 0 | Yes | DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ4ELGF4000, DUKHCONP2BZ3ARGF3005, DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ4ELGF4000 | DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ4ARGF3030, DUKHCONP2BZ4ARGF3030, DUKHCONP2BZ4ARGF3015, DUKHCONP2BZ4ARGF3015, DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ4ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3025 | Porcelain Tile flooring | 20 | 20 | 0% | 2013-12-19 | 2014-01-11 | 2013-12-19 | 2014-01-11 | 5 | No | DUKHCONP2BZ4ARGF3020, DUKHCONP2BZ3ARGF3025, DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ4ARGF3020 | DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ4ARGF3045, DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3045, DUKHCONP2BZ4ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3035 | Slate Tile Flooring & Skirting | 18 | 18 | 0% | 2014-02-01 | 2014-02-22 | 2014-02-01 | 2014-02-22 | 13 | No | DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ4ARGF3025, DUKHCONP2BZ3ARGF3035, DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ4ARGF3025 | DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3015 | Wet area waterproofing & Protection Screed | 20 | 20 | 0% | 2013-11-13 | 2013-12-05 | 2013-11-13 | 2013-12-05 | 5 | No | DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4ARGF3005 | DUKHCONP2BZ4ARGF3020, DUKHCONP2BZ4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ARGF3065 | Wooden door | 15 | 15 | 0% | 2014-02-13 | 2014-03-02 | 2014-02-13 | 2014-03-02 | 17 | No | DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ARGF3060 | DUKHCONP2BZ4ARGF3080, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3075, DUKHCONP2BZ4PLGF4315, DUKHCONP2BZ4PLGF4315, DUKHCONP2BZ4ARGF3075 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.25 .15 .15 EXTERNAL FINISHES |  | 77 | 77 | 0% | 2013-11-30 | 2014-03-01 | 2013-11-30 | 2014-03-01 | 45 |  |  |  | 0 | 0
DHBL.K30.L45.25 .15 .15 .10 ROOF |  | 53 | 53 | 0% | 2013-11-30 | 2014-01-30 | 2013-11-30 | 2014-01-30 | 59 |  |  |  | 0 | 0
DUKHCONP2BZ4ARRF3660 | Installation of Access Ladder | 20 | 20 | 0% | 2014-01-08 | 2014-01-30 | 2014-01-08 | 2014-01-30 | 59 | No | DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ3ARRF3660 | DUKHCONP2BZ5ARRF3660, DUKHCONP2BZ4ACTC8000, DUKHCONP2BZ4AREL3680, DUKHCONP2BZ4ELTC8010, DUKHCONP2BZ4PLTC8005 | 0 | 0 | ROOF
DUKHCONP2BZ4ARRF3640 | Installation of Insulation & Protection | 18 | 18 | 0% | 2013-12-25 | 2014-01-14 | 2013-12-25 | 2014-01-14 | 30 | No | DUKHCONP2BZ3ARRF3640, DUKHCONP2BZ4ARRF3635, DUKHCONP2BZ4ARRF3635 | DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ5ARRF3640, DUKHCONP2BZ4ARRF3645 | 0 | 0 | ROOF
DUKHCONP2BZ4ARRF3625 | Laying of Pitched Roof | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 30 | No | DUKHCONP2BZ4STRF2060, DUKHCONP2BZ4STRF2065, DUKHCONP2BZ3ARRF3625, DUKHCONP2BZ4STRF2060, DUKHCONP2BZ4STRF2065 | DUKHCONP2BZ4ARRF3630, DUKHCONP2BZ4ARRF3630, DUKHCONP2BZ5ARRF3625 | 0 | 0 | ROOF
DUKHCONP2BZ4ARRF3635 | Laying of Waterproofing Membrane | 18 | 18 | 0% | 2013-12-21 | 2014-01-09 | 2013-12-21 | 2014-01-09 | 30 | No | DUKHCONP2BZ4ARRF3630, DUKHCONP2BZ4ARRF3630 | DUKHCONP2BZ4ARRF3640, DUKHCONP2BZ4ARRF3640 | 0 | 0 | ROOF
DUKHCONP2BZ4ARRF3630 | Leveling Screed for Waterproofing | 18 | 18 | 0% | 2013-12-14 | 2014-01-04 | 2013-12-14 | 2014-01-04 | 30 | No | DUKHCONP2BZ4ARRF3625, DUKHCONP2BZ4ARRF3625 | DUKHCONP2BZ4ARRF3635, DUKHCONP2BZ4ARRF3635 | 0 | 0 | ROOF
DUKHCONP2BZ4ARRF3645 | Lime Stone Chips & Paving slab Installation | 18 | 18 | 0% | 2014-01-02 | 2014-01-22 | 2014-01-02 | 2014-01-22 | 30 | No | DUKHCONP2BZ4ARRF3640, DUKHCONP2BZ4ARRF3640 | DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4ARRF3660, DUKHCONP2BZ4ARRF3660, DUKHCONP2BZ4ELRF4070, DUKHCONP2BZ4ELRF4070, DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4AREL3665 | 0 | 0 | ROOF
DHBL.K30.L45.25 .15 .15 .15 ELEVATION |  | 39 | 39 | 0% | 2014-01-14 | 2014-03-01 | 2014-01-14 | 2014-03-01 | 45 |  |  |  | 0 | 0
DUKHCONP2BZ4AREL3680 | External Painting | 20 | 20 | 0% | 2014-02-05 | 2014-03-01 | 2014-02-05 | 2014-03-01 | 45 | No | DUKHCONP2BZ3AREL3680, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ4ARRF3660, DUKHCONP2BZ4AREL3665 | DUKHCONP2BZ4ELTC8010, DUKHCONP2BZ5AREL3680, DUKHCONP2BZ4PLTC8005, DUKHCONP2BZ4ACTC8000 | 0 | 0 | ELEVATION
DUKHCONP2BZ4AREL3665 | External Plastering | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 30 | No | DUKHCONP2BZ4STRF2065, DUKHCONP2BZ3AREL3665, DUKHCONP2BZ4STRF2065, DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ4ARRF3645 | DUKHCONP2BZ4AREL3680, DUKHCONP2BZ5AREL3665, DUKHCONP2BZ4AREL3680, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4PLRF4350 | 0 | 0 | ELEVATION
DHBL.K30.L45.25 .20 MEP WORKS |  | 237 | 237 | 0% | 2013-07-04 | 2014-04-14 | 2013-07-04 | 2014-04-14 | 27 |  |  |  | 0 | 0
DHBL.K30.L45.25 .20 .10 ELECTRICAL WORKS |  | 145 | 145 | 0% | 2013-10-16 | 2014-04-07 | 2013-10-16 | 2014-04-07 | 13 |  |  |  | 0 | 0
DHBL.K30.L45.25 .20 .10 .10 GROUND FLOOR |  | 145 | 145 | 0% | 2013-10-16 | 2014-04-07 | 2013-10-16 | 2014-04-07 | 13 |  |  |  | 0 | 0
DUKHCONP2BZ4ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-01 | 2013-12-24 | 2013-12-01 | 2013-12-24 | 13 | No | DUKHCONP2BZ4ELGF4000, DUKHCONP2BZ4ELGF4000, DUKHCONP2BZ3ELGF4005 | DUKHCONP2BZ5ELGF4005, DUKHCONP2BZ4ELGF4010, DUKHCONP2BZ4ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ELGF4000 | Fixing of wall conduits & switch socket boxes | 20 | 20 | 0% | 2013-10-16 | 2013-11-10 | 2013-10-16 | 2013-11-10 | 3 | No | DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ4ARGF3000 | DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4ELGF4005, DUKHCONP2BZ4ELGF4005, DUKHCONP2BZ4ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 20 | 20 | 0% | 2014-03-16 | 2014-04-07 | 2014-03-16 | 2014-04-07 | 13 | No | DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ3ELGF4015, DUKHCONP2BZ4ARGF3060 | DUKHCONP2BZ5ELGF4015, DUKHCONP2BZ4ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-02-04 | 2014-02-27 | 2014-02-04 | 2014-02-27 | 14 | No | DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ELGF4010, DUKHCONP2BZ3ELGF4020, DUKHCONP2BZ4ELGF4010, DUKHCONP2BZ4ARGF3060 | DUKHCONP2BZ5ELGF4020, DUKHCONP2BZ4ELGF4030, DUKHCONP2BZ4ELGF4025, DUKHCONP2BZ4ELGF4025, DUKHCONP2BZ4ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ELGF4025 | Installation of Lighting fixtures & Accessories | 20 | 20 | 0% | 2014-02-17 | 2014-03-11 | 2014-02-17 | 2014-03-11 | 14 | No | DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ELGF4020, DUKHCONP2BZ4ELGF4020 | DUKHCONP2BZ4ELTC8010, DUKHCONP2BZ4ELRF4070, DUKHCONP2BZ4ELRF4070 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-02-17 | 2014-03-11 | 2014-02-17 | 2014-03-11 | 17 | No | DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ELGF4020, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ3ELGF4030, DUKHCONP2BZ4MSEX5010, DUKHCONP2BZ4ELGF4020 | DUKHCONP2BZ4ELRF4070, DUKHCONP2BZ5ELGF4030, DUKHCONP2BZ4ELTC8010, DUKHCONP2BZ4ELRF4070 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ELGF4010 | Installation of wiring & Main Cabling | 20 | 20 | 0% | 2013-12-09 | 2014-01-01 | 2013-12-09 | 2014-01-01 | 13 | No | DUKHCONP2BZ4ELGF4005, DUKHCONP2BZ4ELGF4005 | DUKHCONP2BZ4ELRF4070, DUKHCONP2BZ4ELGF4020, DUKHCONP2BZ4ELGF4020, DUKHCONP2BZ4ELRF4070, DUKHCONP2BZ4ARGF3045, DUKHCONP2BZ4ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.25 .20 .10 .20 ROOF |  | 30 | 30 | 0% | 2014-03-03 | 2014-04-06 | 2014-03-03 | 2014-04-06 | 14 |  |  |  | 0 | 0
DUKHCONP2BZ4ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-03-03 | 2014-03-23 | 2014-03-03 | 2014-03-23 | 14 | No | DUKHCONP2BZ4ELGF4010, DUKHCONP2BZ4ELGF4030, DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ4ELGF4030, DUKHCONP2BZ4ELGF4010, DUKHCONP2BZ4ELGF4025, DUKHCONP2BZ4ELGF4025 | DUKHCONP2BZ4ELRF4075, DUKHCONP2BZ4ELRF4075 | 0 | 0 | ROOF
DUKHCONP2BZ4ELRF4075 | Installation of TV Dish Antenna | 20 | 20 | 0% | 2014-03-15 | 2014-04-06 | 2014-03-15 | 2014-04-06 | 14 | No | DUKHCONP2BZ4ELRF4070, DUKHCONP2BZ3ELRF4075, DUKHCONP2BZ4ELRF4070 | DUKHCONP2BZ5ELRF4075, DUKHCONP2BZ4ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L45.25 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 237 | 237 | 0% | 2013-07-04 | 2014-04-14 | 2013-07-04 | 2014-04-14 | 27 |  |  |  | 0 | 0
DHBL.K30.L45.25 .20 .15 .10 GROUND FLOOR |  | 237 | 237 | 0% | 2013-07-04 | 2014-04-14 | 2013-07-04 | 2014-04-14 | 27 |  |  |  | 0 | 0
DUKHCONP2BZ4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-07-04 | 2013-07-27 | 2013-07-04 | 2013-07-27 | 0 | Yes | DUKHCONP2BZ4STUG1040, DUKHCONP2BZ4STUG1040 | DUKHCONP2BZ4STUG1045, DUKHCONP2BZ4STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-10-21 | 2013-11-10 | 2013-10-21 | 2013-11-10 | 28 | No | DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ3PLGF4310, DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ4PLGF4305 | DUKHCONP2BZ4ARGF3020, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4PLGF4315, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4MSEX5000, DUKHCONP2BZ4MSEX5000, DUKHCONP2BZ4PLGF4315, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4PLGF4305 | Installation of Plumbing pipes & testing | 20 | 20 | 0% | 2013-10-16 | 2013-11-10 | 2013-10-16 | 2013-11-10 | 0 | Yes | DUKHCONP2BZ4ARGF3000, DUKHCONP2BZ4ARGF3000 | DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4ARGF3020, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-03-29 | 2014-04-14 | 2014-03-29 | 2014-04-14 | 27 | No | DUKHCONP2BZ4PLGF4315, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4PLGF4315 | DUKHCONP2BZ4PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 7 | No | DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ3PLGF4315, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4ARGF3065, DUKHCONP2BZ4ARGF3065 | DUKHCONP2BZ4PLGF4320, DUKHCONP2BZ5PLGF4315, DUKHCONP2BZ4PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.25 .20 .15 .20 ROOF |  | 15 | 15 | 0% | 2014-02-03 | 2014-02-20 | 2014-02-03 | 2014-02-20 | 30 |  |  |  | 0 | 0
DUKHCONP2BZ4PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-02-03 | 2014-02-20 | 2014-02-03 | 2014-02-20 | 30 | No | DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ3PLRF4350, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ4PLGF4305, DUKHCONP2BZ4ARRF3645 | DUKHCONP2BZ4WEEX5065, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ4WEEX5065, DUKHCONP2BZ4PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L45.25 .20 .20 AC WORKS |  | 95 | 95 | 0% | 2013-12-14 | 2014-04-05 | 2013-12-14 | 2014-04-05 | 15 |  |  |  | 0 | 0
DHBL.K30.L45.25 .20 .20 .10 GROUND FLOOR |  | 90 | 90 | 0% | 2013-12-14 | 2014-03-30 | 2013-12-14 | 2014-03-30 | 15 |  |  |  | 0 | 0
DUKHCONP2BZ4ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 15 | No | DUKHCONP2BZ4ACGF4605, DUKHCONP2BZ4ACGF4605 | DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ACRF4635, DUKHCONP2BZ4ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 15 | No | DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ4ARGF3060 | DUKHCONP2BZ4ACGF4610, DUKHCONP2BZ4ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ4ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-12-14 | 2014-01-06 | 2013-12-14 | 2014-01-06 | 28 | No | DUKHCONP2BZ3ACGF4600, DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ4ARGF3005 | DUKHCONP2BZ4ACGF4605, DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ4ACGF4605, DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ4ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.25 .20 .20 .20 ROOF |  | 65 | 65 | 0% | 2014-01-19 | 2014-04-05 | 2014-01-19 | 2014-04-05 | 15 |  |  |  | 0 | 0
DUKHCONP2BZ4ACRF4635 | Installation of Condensing Unit | 20 | 20 | 0% | 2014-03-13 | 2014-04-05 | 2014-03-13 | 2014-04-05 | 15 | No | DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ4ACGF4610, DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ3ACRF4635, DUKHCONP2BZ4ACGF4610 | DUKHCONP2BZ5ACRF4635, DUKHCONP2BZ4ACTC8000 | 0 | 0 | ROOF
DUKHCONP2BZ4ACRF4630 | Installation of Refrigerant Pipes | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 50 | No | DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ3ACRF4630, DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ4ARRF3645, DUKHCONP2BZ4ARRF3645 | DUKHCONP2BZ4ACRF4635, DUKHCONP2BZ4ACRF4635, DUKHCONP2BZ5ACRF4630 | 0 | 0 | ROOF
DHBL.K30.L45.25 .25 EXTERNAL WORKS |  | 138 | 138 | 0% | 2013-11-04 | 2014-04-15 | 2013-11-04 | 2014-04-15 | 26 |  |  |  | 0 | 0
DHBL.K30.L45.25 .25 .10 MISCELLANEOUS |  | 74 | 74 | 0% | 2013-11-04 | 2014-01-29 | 2013-11-04 | 2014-01-29 | 31 |  |  |  | 0 | 0
DUKHCONP2BZ4MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-11-18 | 2013-12-16 | 2013-11-18 | 2013-12-16 | 31 | No | DUKHCONP2BZ4MSEX5000, DUKHCONP2BZ4MSEX5000 | DUKHCONP2BZ4ELTC8010, DUKHCONP2BZ4PLTC8005, DUKHCONP2BZ4ACTC8000, DUKHCONP2BZ4MSEX5015, DUKHCONP2BZ4MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ4MSEX5020 | Construction Entrance Ramp | 20 | 20 | 0% | 2013-12-02 | 2013-12-25 | 2013-12-02 | 2013-12-25 | 30 | No | DUKHCONP2BZ4STRF2065, DUKHCONP2BZ4STRF2065, DUKHCONP2BZ3MSEX5020 | DUKHCONP2BZ4MSEX5025, DUKHCONP2BZ4HDEX5090, DUKHCONP2BZ4HDEX5090, DUKHCONP2BZ4MSEX5025, DUKHCONP2BZ4MSEX5055, DUKHCONP2BZ5MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ4MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2013-12-08 | 2013-12-31 | 2013-12-08 | 2013-12-31 | 31 | No | DUKHCONP2BZ4MSEX5005, DUKHCONP2BZ4MSEX5005 | DUKHCONP2BZ4WEEX5065, DUKHCONP2BZ4WEEX5065, DUKHCONP2BZ4MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ4MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 26 | No | DUKHCONP2BZ3MSEX5000, DUKHCONP2BZ4STRF2065, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4PLGF4310, DUKHCONP2BZ4STRF2065 | DUKHCONP2BZ5MSEX5000, DUKHCONP2BZ4MSEX5005, DUKHCONP2BZ4MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ4MSEX5055 | Installation Steel Door | 20 | 20 | 0% | 2013-12-14 | 2014-01-06 | 2013-12-14 | 2014-01-06 | 30 | No | DUKHCONP2BZ4MSEX5020 | DUKHCONP2BZ4MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ4MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2013-12-26 | 2014-01-18 | 2013-12-26 | 2014-01-18 | 30 | No | DUKHCONP2BZ4MSEX5055, DUKHCONP2BZ4MSEX5020, DUKHCONP2BZ4MSEX5020, DUKHCONP2BZ3MSEX5025 | DUKHCONP2BZ4WEEX5050, DUKHCONP2BZ5MSEX5025, DUKHCONP2BZ4WEEX5050, DUKHCONP2BZ4HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ4MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-01-01 | 2014-01-29 | 2014-01-01 | 2014-01-29 | 31 | No | DUKHCONP2BZ4MSEX5015 | DUKHCONP2BZ4ELGF4030 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L45.25 .25 .15 WATER TANK ENCLOSURE |  | 99 | 99 | 0% | 2013-12-21 | 2014-04-15 | 2013-12-21 | 2014-04-15 | 26 |  |  |  | 0 | 0
DUKHCONP2BZ4MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 26 | No | DUKHCONI2BZ2BWGL5325, DUKHCONP2BZ3MSEX5335 | DUKHHANP2BGNELTC9010, DUKHCONP2BZ5MSEX5335 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 20 | No | DUKHCONP2BZ4WEEX5035, DUKHCONP2BZ4WEEX5035 | DUKHCONP2BZ4WEEX5045, DUKHCONP2BZ4WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2013-12-26 | 2014-01-23 | 2013-12-26 | 2014-01-23 | 15 | No | DUKHCONP2BZ4WEEX5030, DUKHCONP2BZ4WEEX5030 | DUKHCONP2BZ5WEEX5030, DUKHCONP2BZ4WEEX5040, DUKHCONP2BZ4WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5030 | Excavation | 20 | 20 | 0% | 2013-12-21 | 2014-01-12 | 2013-12-21 | 2014-01-12 | 15 | No | DUKHCONP2BZ3WEEX5035, DUKHCONP2BZ4STRF2065, DUKHCONP2BZ4STRF2065 | DUKHCONP2BZ4WEEX5035, DUKHCONP2BZ4WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 20 | No | DUKHCONP2BZ4WEEX5040, DUKHCONP2BZ4WEEX5040 | DUKHCONP2BZ4WEEX5050, DUKHCONP2BZ4WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-02-22 | 2014-03-22 | 2014-02-22 | 2014-03-22 | 20 | No | DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4MSEX5015, DUKHCONP2BZ4MSEX5015, DUKHCONP2BZ4WEEX5060, DUKHCONP2BZ4WEEX5060, DUKHCONP2BZ4PLRF4350 | DUKHCONP2BZ4PLTC8005, DUKHCONP2BZ5WEEX5065, DUKHCONP2BZ4WEEX5070 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5070 | Installation ladder for water Tank | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 10 | No | DUKHCONP2BZ3WEEX5070, DUKHCONP2BZ4WEEX5065 | DUKHCONP2BZ5WEEX5070 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-02-03 | 2014-02-26 | 2014-02-03 | 2014-02-26 | 20 | No | DUKHCONP2BZ4WEEX5045, DUKHCONP2BZ4WEEX5045, DUKHCONP2BZ4MSEX5025, DUKHCONP2BZ4MSEX5025 | DUKHCONP2BZ5WEEX5050, DUKHCONP2BZ4WEEX5060, DUKHCONP2BZ4WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ4WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 20 | No | DUKHCONP2BZ4WEEX5050, DUKHCONP2BZ4WEEX5050 | DUKHCONP2BZ4WEEX5065, DUKHCONP2BZ4WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L45.25 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2014-01-04 | 2014-02-23 | 2014-01-04 | 2014-02-23 | 30 |  |  |  | 0 | 0
DUKHCONP2BZ4HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-01-15 | 2014-02-06 | 2014-01-15 | 2014-02-06 | 30 | No | DUKHCONP2BZ4HDEX5090, DUKHCONP2BZ4HDEX5090 | DUKHCONP2BZ4HDEX5100, DUKHCONP2BZ4HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2BZ4HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-01-30 | 2014-02-23 | 2014-01-30 | 2014-02-23 | 30 | No | DUKHCONP2BZ4HDEX5095, DUKHCONP2BZ4HDEX5095 | DUKHCONP2BZ4SLEX5105, DUKHCONP2BZ4ACTC8000, DUKHCONP2BZ4PLTC8005, DUKHCONP2BZ4SLEX5105, DUKHCONP2BZ4ELTC8010 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2BZ4HDEX5090 | kerb works | 20 | 20 | 0% | 2014-01-04 | 2014-01-26 | 2014-01-04 | 2014-01-26 | 30 | No | DUKHCONP2BZ3HDEX5090, DUKHCONP2BZ4MSEX5020, DUKHCONP2BZ4MSEX5020, DUKHCONP2BZ4MSEX5025 | DUKHCONP2BZ4HDEX5095, DUKHCONP2BZ4HDEX5095, DUKHCONP2BZ5HDEX5090 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L45.25 .25 .25 SOFT LANDSCAPING |  | 30 | 30 | 0% | 2014-02-23 | 2014-03-29 | 2014-02-23 | 2014-03-29 | 21 |  |  |  | 0 | 0
DUKHCONP2BZ4SLEX5105 | Laying of Grass/ green area | 20 | 20 | 0% | 2014-02-23 | 2014-03-17 | 2014-02-23 | 2014-03-17 | 21 | No | DUKHCONP2BZ4HDEX5100, DUKHCONP2BZ4HDEX5100, DUKHCONP2BZ3SLEX5105 | DUKHCONP2BZ4PLTC8005, DUKHCONP2BZ5SLEX5105, DUKHCONP2BZ4ACTC8000, DUKHCONP2BZ4SLEX5110, DUKHCONP2BZ4SLEX5110, DUKHCONP2BZ4ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP2BZ4SLEX5110 | Laying of Palm tree | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 21 | No | DUKHCONP2BZ4SLEX5105, DUKHCONP2BZ4SLEX5105 | DUKHCONP2BZ5SLEX5110, DUKHCONP2BZ4PLTC8005, DUKHCONP2BZ4ACTC8000, DUKHCONP2BZ4ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L45.25 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 23 |  |  |  | 0 | 0
DUKHCONP2BZ4ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 23 | No | DUKHCONP2BZ4HDEX5100, DUKHCONP2BZ4ARRF3660, DUKHCONP2BZ4SLEX5105, DUKHCONP2BZ4MSEX5005, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4ACRF4635, DUKHCONP2BZ4SLEX5110, DUKHCONP2BZ4AREL3680 | DUKHHANP2BGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2BZ4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 23 | No | DUKHCONP2BZ4MSEX5005, DUKHCONP2BZ4AREL3680, DUKHCONP2BZ4ELGF4025, DUKHCONP2BZ4ELGF4015, DUKHCONP2BZ4ELGF4030, DUKHCONP2BZ4SLEX5105, DUKHCONP2BZ4ELRF4075, DUKHCONP2BZ4ARRF3660, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4HDEX5100, DUKHCONP2BZ4SLEX5110 | DUKHHANP2BGNACTC9000, DUKHHANP2BGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2BZ4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 23 | No | DUKHCONP2BZ4SLEX5105, DUKHCONP2BZ4MSEX5005, DUKHCONP2BZ4HDEX5100, DUKHCONP2BZ4ARGF3095, DUKHCONP2BZ4PLGF4320, DUKHCONP2BZ4SLEX5110, DUKHCONP2BZ4WEEX5065, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ4AREL3680, DUKHCONP2BZ4ARRF3660 | DUKHHANP2BGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L45.30 ZONE - 5 (3 Twin Villas) |  | 338 | 338 | 0% | 2013-05-08 | 2014-06-14 | 2013-05-08 | 2014-06-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L45.30 .10 STRUCTURAL WORKS |  | 179 | 179 | 0% | 2013-05-08 | 2013-12-08 | 2013-05-08 | 2013-12-08 | 36 |  |  |  | 0 | 0
DHBL.K30.L45.30 .10 .10 SUB STRUCTURE |  | 105 | 105 | 0% | 2013-05-08 | 2013-09-10 | 2013-05-08 | 2013-09-10 | 2 |  |  |  | 0 | 0
DHBL.K30.L45.30 .10 .10 .10 UPTO GRADE SLAB |  | 105 | 105 | 0% | 2013-05-08 | 2013-09-10 | 2013-05-08 | 2013-09-10 | 2 |  |  |  | 0 | 0
DUKHCONP2BZ5STUG1035 | Backfilling Upto Grade Beam Bottom | 20 | 20 | 0% | 2013-07-07 | 2013-07-29 | 2013-07-07 | 2013-07-29 | 2 | No | DUKHCONP2BZ5STUG1030, DUKHCONP2BZ5STUG1030, DUKHCONP2BZ4STUG1035 | DUKHCONP2BZ5STUG1040, DUKHCONP2BZ5STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-06-06 | 2013-06-29 | 2013-06-06 | 2013-06-29 | 2 | No | DUKHCONP2BZ4STUG1020, DUKHCONP2BZ5STUG1015, DUKHCONP2BZ5STUG1015 | DUKHCONP2BZ5STUG1025, DUKHCONP2BZ5STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-07-18 | 2013-08-19 | 2013-07-18 | 2013-08-19 | 2 | No | DUKHCONP2BZ5STUG1035, DUKHCONP2BZ5STUG1035, DUKHCONP2BZ4STUG1040 | DUKHCONP2BZ5PLUG4300, DUKHCONP2BZ5STUG1045, DUKHCONP2BZ5STUG1045, DUKHCONP2BZ5PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1025 | Construction of neck of columns | 20 | 20 | 0% | 2013-06-16 | 2013-07-08 | 2013-06-16 | 2013-07-08 | 2 | No | DUKHCONP2BZ5STUG1020, DUKHCONP2BZ5STUG1020 | DUKHCONP2BZ5STUG1030, DUKHCONP2BZ5STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-08-13 | 2013-09-10 | 2013-08-13 | 2013-09-10 | 2 | No | DUKHCONP2BZ5STUG1040, DUKHCONP2BZ5STUG1040, DUKHCONP2BZ5PLUG4300, DUKHCONP2BZ5PLUG4300 | DUKHCONP2BZ5STGF2000, DUKHCONP2BZ5STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1005 | Footing Antitermite | 20 | 20 | 0% | 2013-05-20 | 2013-06-11 | 2013-05-20 | 2013-06-11 | 2 | No | DUKHCONP2BZ5STUG1000, DUKHCONP2BZ5STUG1000 | DUKHCONP2BZ5STUG1010, DUKHCONP2BZ5STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1010 | Footing Blinding | 20 | 20 | 0% | 2013-05-22 | 2013-06-13 | 2013-05-22 | 2013-06-13 | 2 | No | DUKHCONP2BZ5STUG1005, DUKHCONP2BZ5STUG1005 | DUKHCONP2BZ5STUG1015, DUKHCONP2BZ5STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-05-08 | 2013-06-05 | 2013-05-08 | 2013-06-05 | 2 | No | DUKHCONP2BZ4STUG1000 | DUKHCONP2BZ5STUG1005, DUKHCONP2BZ5STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1015 | Footing Waterproofing & Screed | 20 | 20 | 0% | 2013-05-28 | 2013-06-19 | 2013-05-28 | 2013-06-19 | 2 | No | DUKHCONP2BZ5STUG1010, DUKHCONP2BZ5STUG1010 | DUKHCONP2BZ5STUG1020, DUKHCONP2BZ5STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP2BZ5STUG1030 | Waterproofing Footing & Neck Column | 20 | 20 | 0% | 2013-06-25 | 2013-07-17 | 2013-06-25 | 2013-07-17 | 2 | No | DUKHCONP2BZ5STUG1025, DUKHCONP2BZ5STUG1025 | DUKHCONP2BZ5STUG1035, DUKHCONP2BZ5STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L45.30 .10 .15 SUPERSTRUCTURE |  | 84 | 84 | 0% | 2013-08-31 | 2013-12-08 | 2013-08-31 | 2013-12-08 | 36 |  |  |  | 0 | 0
DHBL.K30.L45.30 .10 .15 .10 GROUND FLOOR |  | 45 | 45 | 0% | 2013-08-31 | 2013-10-23 | 2013-08-31 | 2013-10-23 | 2 |  |  |  | 0 | 0
DUKHCONP2BZ5STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-10-05 | 2013-10-23 | 2013-10-05 | 2013-10-23 | 2 | No | DUKHCONP2BZ4STGF2015, DUKHCONP2BZ5STGF2010, DUKHCONP2BZ5STGF2010 | DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ5STRF2060, DUKHCONP2BZ5STRF2060 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-09-18 | 2013-10-16 | 2013-09-18 | 2013-10-16 | 2 | No | DUKHCONP2BZ5STGF2005, DUKHCONP2BZ5STGF2005 | DUKHCONP2BZ5STGF2015, DUKHCONP2BZ5STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5STGF2005 | Column-Concrete | 15 | 15 | 0% | 2013-09-10 | 2013-09-26 | 2013-09-10 | 2013-09-26 | 2 | No | DUKHCONP2BZ5STGF2000, DUKHCONP2BZ5STGF2000 | DUKHCONP2BZ5STGF2010, DUKHCONP2BZ5STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5STGF2000 | Column-Rebar & Formwork | 20 | 20 | 0% | 2013-08-31 | 2013-09-22 | 2013-08-31 | 2013-09-22 | 2 | No | DUKHCONP2BZ5STUG1045, DUKHCONP2BZ4STGF2000, DUKHCONP2BZ5STUG1045 | DUKHCONP2BZ5STGF2005, DUKHCONP2BZ5STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.30 .10 .15 .20 ROOF |  | 26 | 26 | 0% | 2013-11-09 | 2013-12-08 | 2013-11-09 | 2013-12-08 | 36 |  |  |  | 0 | 0
DUKHCONP2BZ5STRF2060 | Construction of Parapets | 20 | 20 | 0% | 2013-11-09 | 2013-12-01 | 2013-11-09 | 2013-12-01 | 19 | No | DUKHCONP2BZ4STRF2060, DUKHCONP2BZ5STGF2015, DUKHCONP2BZ5STGF2015 | DUKHCONI2BSBIWGL7400, DUKHCONP2BZ5STRF2065, DUKHCONP2BZ5STRF2065, DUKHCONP2BZ5ARRF3625, DUKHCONP2BZ5ARRF3625 | 0 | 0 | ROOF
DUKHCONP2BZ5STRF2065 | Construction of up stands/Plinth | 20 | 20 | 0% | 2013-11-16 | 2013-12-08 | 2013-11-16 | 2013-12-08 | 36 | No | DUKHCONP2BZ5STRF2060, DUKHCONP2BZ5STRF2060 | DUKHCONP2BZ5WEEX5030, DUKHCONP2BZ5MSEX5020, DUKHCONP2BZ5WEEX5030, DUKHCONP2BZ5MSEX5000, DUKHCONP2BZ5ARRF3625, DUKHCONP2BZ5AREL3665, DUKHCONP2BZ5MSEX5000, DUKHCONP2BZ5ARRF3625, DUKHCONP2BZ5MSEX5020, DUKHCONP2BZ5AREL3665 | 0 | 0 | ROOF
DHBL.K30.L45.30 .15 FINISHING WORKS |  | 165 | 165 | 0% | 2013-11-03 | 2014-05-15 | 2013-11-03 | 2014-05-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L45.30 .15 .10 INTERNAL FINISHES |  | 165 | 165 | 0% | 2013-11-03 | 2014-05-15 | 2013-11-03 | 2014-05-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L45.30 .15 .10 .10 GROUND FLOOR |  | 165 | 165 | 0% | 2013-11-03 | 2014-05-15 | 2013-11-03 | 2014-05-15 | 0 |  |  |  | 0 | 0
DUKHCONP2BZ5ARGF3080 | Aluminum windows | 18 | 18 | 0% | 2014-03-27 | 2014-04-16 | 2014-03-27 | 2014-04-16 | 10 | No | DUKHCONP2BZ5ARGF3065 | DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3000 | Block work | 25 | 25 | 0% | 2013-11-03 | 2013-12-01 | 2013-11-03 | 2013-12-01 | 0 | Yes | DUKHCONP2BZ5STGF2015, DUKHCONP2BZ5STGF2015, DUKHCONP2BZ4ARGF3000 | DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ5ELGF4000, DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5ELGF4000, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3075 | Carpentry & Joinery Works | 18 | 18 | 0% | 2014-03-16 | 2014-04-05 | 2014-03-16 | 2014-04-05 | 14 | No | DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ4ARGF3075 | DUKHCONP2BZ5ARGF3090, DUKHCONP2BZ5ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3020 | Ceramic Wall Tiling | 15 | 15 | 0% | 2014-01-01 | 2014-01-18 | 2014-01-01 | 2014-01-18 | 0 | Yes | DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5ARGF3015, DUKHCONP2BZ5ARGF3015, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5PLGF4310 | DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ5ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-03-13 | 2014-03-30 | 2014-03-13 | 2014-03-30 | 17 | No | DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3010, DUKHCONP2BZ4ARGF3040, DUKHCONP2BZ5ARGF3010, DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3025 | DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 0 | Yes | DUKHCONP2BZ5ARGF3030, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3080, DUKHCONP2BZ5ARGF3030, DUKHCONP2BZ5ARGF3040, DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ5ARGF3080, DUKHCONP2BZ5ARGF3040, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ARGF3090, DUKHCONP2BZ5ARGF3090, DUKHCONP2BZ5ACGF4610, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ACGF4610, DUKHCONP2BZ5ARGF3060 | DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5PLTC8005, DUKHCONP2BZ5ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3045 | Fixing of Suspension systems | 15 | 15 | 0% | 2014-02-09 | 2014-02-26 | 2014-02-09 | 2014-02-26 | 0 | Yes | DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ5ELGF4010, DUKHCONP2BZ5ARGF3030, DUKHCONP2BZ5ARGF3030, DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ5ELGF4010 | DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3010 | Flooring screed | 20 | 20 | 0% | 2013-12-08 | 2013-12-31 | 2013-12-08 | 2013-12-31 | 20 | No | DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ4ARGF3010, DUKHCONP2BZ5ARGF3005 | DUKHCONP2BZ5ARGF3040, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ5ARGF3040, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3060 | Gypsum board false ceiling | 20 | 20 | 0% | 2014-02-26 | 2014-03-20 | 2014-02-26 | 2014-03-20 | 0 | Yes | DUKHCONP2BZ4ARGF3060, DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ5ARGF3045, DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ5ARGF3045 | DUKHCONP2BZ5ELGF4025, DUKHCONP2BZ5PLGF4320, DUKHCONP2BZ5ELGF4020, DUKHCONP2BZ5ELGF4025, DUKHCONP2BZ5ELGF4015, DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ5PLGF4320, DUKHCONP2BZ5ELGF4030, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ACGF4605, DUKHCONP2BZ5ELGF4030, DUKHCONP2BZ5ELGF4015, DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ACGF4605, DUKHCONP2BZ5ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-04-02 | 2014-04-19 | 2014-04-02 | 2014-04-19 | 8 | No | DUKHCONP2BZ5ARGF3075, DUKHCONP2BZ5ARGF3075, DUKHCONP2BZ4ARGF3090 | DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3030 | Paint First coat | 20 | 20 | 0% | 2014-01-11 | 2014-02-02 | 2014-01-11 | 2014-02-02 | 6 | No | DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ4ARGF3030 | DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3045, DUKHCONP2BZ5ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-11-26 | 2013-12-25 | 2013-11-26 | 2013-12-25 | 0 | Yes | DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ4ARGF3005, DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5ELGF4000, DUKHCONP2BZ5ELGF4000, DUKHCONP2BZ5ARGF3000 | DUKHCONP2BZ5ARGF3030, DUKHCONP2BZ5ARGF3030, DUKHCONP2BZ5ARGF3010, DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ5ARGF3015, DUKHCONP2BZ5ARGF3015, DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ5ARGF3010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3025 | Porcelain Tile flooring | 20 | 20 | 0% | 2014-01-18 | 2014-02-09 | 2014-01-18 | 2014-02-09 | 0 | Yes | DUKHCONP2BZ5ARGF3020, DUKHCONP2BZ5ARGF3010, DUKHCONP2BZ4ARGF3025, DUKHCONP2BZ5ARGF3020, DUKHCONP2BZ5ARGF3010 | DUKHCONP2BZ5ARGF3045, DUKHCONP2BZ5ARGF3045, DUKHCONP2BZ5ARGF3040, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3035 | Slate Tile Flooring & Skirting | 18 | 18 | 0% | 2014-02-23 | 2014-03-15 | 2014-02-23 | 2014-03-15 | 13 | No | DUKHCONP2BZ4ARGF3035, DUKHCONP2BZ5ARGF3010, DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ5ARGF3025, DUKHCONP2BZ5ARGF3010 | DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3040, DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3015 | Wet area waterproofing & Protection Screed | 20 | 20 | 0% | 2013-12-12 | 2014-01-05 | 2013-12-12 | 2014-01-05 | 0 | Yes | DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ5ARGF3005 | DUKHCONP2BZ5ARGF3020, DUKHCONP2BZ5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ARGF3065 | Wooden door | 15 | 15 | 0% | 2014-03-10 | 2014-03-26 | 2014-03-10 | 2014-03-26 | 10 | No | DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3035, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ARGF3060 | DUKHCONP2BZ5PLGF4315, DUKHCONP2BZ5ARGF3080, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ARGF3075, DUKHCONP2BZ5ARGF3075, DUKHCONP2BZ5PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.30 .15 .15 EXTERNAL FINISHES |  | 77 | 77 | 0% | 2013-12-30 | 2014-03-30 | 2013-12-30 | 2014-03-30 | 40 |  |  |  | 0 | 0
DHBL.K30.L45.30 .15 .15 .10 ROOF |  | 53 | 53 | 0% | 2013-12-30 | 2014-03-02 | 2013-12-30 | 2014-03-02 | 54 |  |  |  | 0 | 0
DUKHCONP2BZ5ARRF3660 | Installation of Access Ladder | 20 | 20 | 0% | 2014-02-06 | 2014-03-02 | 2014-02-06 | 2014-03-02 | 54 | No | DUKHCONP2BZ4ARRF3660, DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5ARRF3645 | DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5AREL3680, DUKHCONP2BZ5PLTC8005, DUKHCONP2BZ5ACTC8000 | 0 | 0 | ROOF
DUKHCONP2BZ5ARRF3640 | Installation of Insulation & Protection | 18 | 18 | 0% | 2014-01-23 | 2014-02-13 | 2014-01-23 | 2014-02-13 | 30 | No | DUKHCONP2BZ5ARRF3635, DUKHCONP2BZ4ARRF3640, DUKHCONP2BZ5ARRF3635 | DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5ARRF3645 | 0 | 0 | ROOF
DUKHCONP2BZ5ARRF3625 | Laying of Pitched Roof | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 30 | No | DUKHCONP2BZ5STRF2065, DUKHCONP2BZ5STRF2060, DUKHCONP2BZ5STRF2060, DUKHCONP2BZ5STRF2065, DUKHCONP2BZ4ARRF3625 | DUKHCONP2BZ5ARRF3630, DUKHCONP2BZ5ARRF3630 | 0 | 0 | ROOF
DUKHCONP2BZ5ARRF3635 | Laying of Waterproofing Membrane | 18 | 18 | 0% | 2014-01-19 | 2014-02-08 | 2014-01-19 | 2014-02-08 | 30 | No | DUKHCONP2BZ5ARRF3630, DUKHCONP2BZ5ARRF3630 | DUKHCONP2BZ5ARRF3640, DUKHCONP2BZ5ARRF3640 | 0 | 0 | ROOF
DUKHCONP2BZ5ARRF3630 | Leveling Screed for Waterproofing | 18 | 18 | 0% | 2014-01-13 | 2014-02-02 | 2014-01-13 | 2014-02-02 | 30 | No | DUKHCONP2BZ5ARRF3625, DUKHCONP2BZ5ARRF3625 | DUKHCONP2BZ5ARRF3635, DUKHCONP2BZ5ARRF3635 | 0 | 0 | ROOF
DUKHCONP2BZ5ARRF3645 | Lime Stone Chips & Paving slab Installation | 18 | 18 | 0% | 2014-02-01 | 2014-02-22 | 2014-02-01 | 2014-02-22 | 30 | No | DUKHCONP2BZ5ARRF3640, DUKHCONP2BZ5ARRF3640 | DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5ELRF4070, DUKHCONP2BZ5AREL3665, DUKHCONP2BZ5ACRF4630, DUKHCONP2BZ5ACRF4630, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5ARRF3660, DUKHCONP2BZ5ARRF3660, DUKHCONP2BZ5ELRF4070, DUKHCONP2BZ5AREL3665 | 0 | 0 | ROOF
DHBL.K30.L45.30 .15 .15 .15 ELEVATION |  | 39 | 39 | 0% | 2014-02-13 | 2014-03-30 | 2014-02-13 | 2014-03-30 | 40 |  |  |  | 0 | 0
DUKHCONP2BZ5AREL3680 | External Painting | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 40 | No | DUKHCONP2BZ4AREL3680, DUKHCONP2BZ5AREL3665, DUKHCONP2BZ5AREL3665, DUKHCONP2BZ5ARRF3660 | DUKHCONP2BZ5PLTC8005, DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5ACTC8000 | 0 | 0 | ELEVATION
DUKHCONP2BZ5AREL3665 | External Plastering | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 30 | No | DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ4AREL3665, DUKHCONP2BZ5STRF2065, DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5STRF2065 | DUKHCONP2BZ5AREL3680, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5AREL3680, DUKHCONP2BZ5PLRF4350 | 0 | 0 | ELEVATION
DHBL.K30.L45.30 .20 MEP WORKS |  | 233 | 233 | 0% | 2013-08-01 | 2014-05-07 | 2013-08-01 | 2014-05-07 | 7 |  |  |  | 0 | 0
DHBL.K30.L45.30 .20 .10 ELECTRICAL WORKS |  | 144 | 144 | 0% | 2013-11-17 | 2014-05-05 | 2013-11-17 | 2014-05-05 | 9 |  |  |  | 0 | 0
DHBL.K30.L45.30 .20 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-11-17 | 2014-04-30 | 2013-11-17 | 2014-04-30 | 13 |  |  |  | 0 | 0
DUKHCONP2BZ5ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-25 | 2014-01-16 | 2013-12-25 | 2014-01-16 | 13 | No | DUKHCONP2BZ4ELGF4005, DUKHCONP2BZ5ELGF4000, DUKHCONP2BZ5ELGF4000 | DUKHCONP2BZ5ELGF4010, DUKHCONP2BZ5ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ELGF4000 | Fixing of wall conduits & switch socket boxes | 20 | 20 | 0% | 2013-11-17 | 2013-12-09 | 2013-11-17 | 2013-12-09 | 3 | No | DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ5ARGF3000 | DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ5ELGF4005, DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ5ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 20 | 20 | 0% | 2014-04-08 | 2014-04-30 | 2014-04-08 | 2014-04-30 | 13 | No | DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ4ELGF4015, DUKHCONP2BZ5ARGF3060 | DUKHCONP2BZ5ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 9 | No | DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ELGF4010, DUKHCONP2BZ5ELGF4010, DUKHCONP2BZ4ELGF4020, DUKHCONP2BZ5ARGF3060 | DUKHCONP2BZ5ELGF4030, DUKHCONP2BZ5ELGF4025, DUKHCONP2BZ5ELGF4030, DUKHCONP2BZ5ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ELGF4025 | Installation of Lighting fixtures & Accessories | 20 | 20 | 0% | 2014-03-18 | 2014-04-09 | 2014-03-18 | 2014-04-09 | 9 | No | DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ELGF4020, DUKHCONP2BZ5ELGF4020 | DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5ELRF4070, DUKHCONP2BZ5ELRF4070 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-03-18 | 2014-04-09 | 2014-03-18 | 2014-04-09 | 12 | No | DUKHCONP2BZ5ELGF4020, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ4ELGF4030, DUKHCONP2BZ5ELGF4020, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5MSEX5010 | DUKHCONP2BZ5ELRF4070, DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5ELRF4070 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ELGF4010 | Installation of wiring & Main Cabling | 20 | 20 | 0% | 2014-01-02 | 2014-01-25 | 2014-01-02 | 2014-01-25 | 13 | No | DUKHCONP2BZ5ELGF4005, DUKHCONP2BZ5ELGF4005 | DUKHCONP2BZ5ARGF3045, DUKHCONP2BZ5ELRF4070, DUKHCONP2BZ5ELGF4020, DUKHCONP2BZ5ELGF4020, DUKHCONP2BZ5ARGF3045, DUKHCONP2BZ5ELRF4070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.30 .20 .10 .20 ROOF |  | 30 | 30 | 0% | 2014-04-01 | 2014-05-05 | 2014-04-01 | 2014-05-05 | 9 |  |  |  | 0 | 0
DUKHCONP2BZ5ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-04-01 | 2014-04-21 | 2014-04-01 | 2014-04-21 | 9 | No | DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5ELGF4010, DUKHCONP2BZ5ELGF4030, DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5ELGF4010, DUKHCONP2BZ5ELGF4025, DUKHCONP2BZ5ELGF4025, DUKHCONP2BZ5ELGF4030 | DUKHCONP2BZ5ELRF4075, DUKHCONP2BZ5ELRF4075 | 0 | 0 | ROOF
DUKHCONP2BZ5ELRF4075 | Installation of TV Dish Antenna | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 9 | No | DUKHCONP2BZ5ELRF4070, DUKHCONP2BZ4ELRF4075, DUKHCONP2BZ5ELRF4070 | DUKHCONP2BZ5ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L45.30 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 233 | 233 | 0% | 2013-08-01 | 2014-05-07 | 2013-08-01 | 2014-05-07 | 7 |  |  |  | 0 | 0
DHBL.K30.L45.30 .20 .15 .10 GROUND FLOOR |  | 233 | 233 | 0% | 2013-08-01 | 2014-05-07 | 2013-08-01 | 2014-05-07 | 7 |  |  |  | 0 | 0
DUKHCONP2BZ5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-08-01 | 2013-08-27 | 2013-08-01 | 2013-08-27 | 2 | No | DUKHCONP2BZ5STUG1040, DUKHCONP2BZ5STUG1040 | DUKHCONP2BZ5STUG1045, DUKHCONP2BZ5STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-11-19 | 2013-12-09 | 2013-11-19 | 2013-12-09 | 28 | No | DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ4PLGF4310 | DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5MSEX5000, DUKHCONP2BZ5PLGF4315, DUKHCONP2BZ5PLGF4315, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5ARGF3020, DUKHCONP2BZ5MSEX5000, DUKHCONP2BZ5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5PLGF4305 | Installation of Plumbing pipes & testing | 20 | 20 | 0% | 2013-11-17 | 2013-12-09 | 2013-11-17 | 2013-12-09 | 0 | Yes | DUKHCONP2BZ5ARGF3000, DUKHCONP2BZ5ARGF3000 | DUKHCONP2BZ5ARGF3020, DUKHCONP2BZ5ARGF3020, DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5PLRF4350 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-04-21 | 2014-05-07 | 2014-04-21 | 2014-05-07 | 7 | No | DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5PLGF4315, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5PLGF4315 | DUKHCONP2BZ5PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-04-09 | 2014-05-01 | 2014-04-09 | 2014-05-01 | 7 | No | DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5ARGF3065, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ4PLGF4315, DUKHCONP2BZ5ARGF3065 | DUKHCONP2BZ5PLGF4320, DUKHCONP2BZ5PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.30 .20 .15 .20 ROOF |  | 15 | 15 | 0% | 2014-03-05 | 2014-03-22 | 2014-03-05 | 2014-03-22 | 30 |  |  |  | 0 | 0
DUKHCONP2BZ5PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-03-05 | 2014-03-22 | 2014-03-05 | 2014-03-22 | 30 | No | DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5AREL3665, DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5PLGF4305, DUKHCONP2BZ5AREL3665, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ4PLRF4350, DUKHCONP2BZ5PLGF4305 | DUKHCONP2BZ5WEEX5065, DUKHCONP2BZ5WEEX5065, DUKHCONP2BZ5PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L45.30 .20 .20 AC WORKS |  | 100 | 100 | 0% | 2014-01-07 | 2014-05-04 | 2014-01-07 | 2014-05-04 | 10 |  |  |  | 0 | 0
DHBL.K30.L45.30 .20 .20 .10 GROUND FLOOR |  | 95 | 95 | 0% | 2014-01-07 | 2014-04-28 | 2014-01-07 | 2014-04-28 | 0 |  |  |  | 0 | 0
DUKHCONP2BZ5ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-04-06 | 2014-04-28 | 2014-04-06 | 2014-04-28 | 0 | Yes | DUKHCONP2BZ5ACGF4605, DUKHCONP2BZ5ACGF4605 | DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ACRF4635, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 0 | Yes | DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ARGF3060 | DUKHCONP2BZ5ACGF4610, DUKHCONP2BZ5ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP2BZ5ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 28 | No | DUKHCONP2BZ5ARGF3005, DUKHCONP2BZ4ACGF4600, DUKHCONP2BZ5ARGF3005 | DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ACGF4605, DUKHCONP2BZ5ACGF4605, DUKHCONP2BZ5ACRF4630, DUKHCONP2BZ5ARGF3060, DUKHCONP2BZ5ACRF4630 | 0 | 0 | GROUND FLOOR
DHBL.K30.L45.30 .20 .20 .20 ROOF |  | 65 | 65 | 0% | 2014-02-18 | 2014-05-04 | 2014-02-18 | 2014-05-04 | 10 |  |  |  | 0 | 0
DUKHCONP2BZ5ACRF4635 | Installation of Condensing Unit | 20 | 20 | 0% | 2014-04-12 | 2014-05-04 | 2014-04-12 | 2014-05-04 | 10 | No | DUKHCONP2BZ5ACRF4630, DUKHCONP2BZ4ACRF4635, DUKHCONP2BZ5ACRF4630, DUKHCONP2BZ5ACGF4610, DUKHCONP2BZ5ACGF4610 | DUKHCONP2BZ5ACTC8000 | 0 | 0 | ROOF
DUKHCONP2BZ5ACRF4630 | Installation of Refrigerant Pipes | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 45 | No | DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5ARRF3645, DUKHCONP2BZ5ACGF4600, DUKHCONP2BZ4ACRF4630, DUKHCONP2BZ5ACGF4600 | DUKHCONP2BZ5ACRF4635, DUKHCONP2BZ5ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L45.30 .25 EXTERNAL WORKS |  | 138 | 138 | 0% | 2013-12-03 | 2014-05-14 | 2013-12-03 | 2014-05-14 | 26 |  |  |  | 0 | 0
DHBL.K30.L45.30 .25 .10 MISCELLANEOUS |  | 74 | 74 | 0% | 2013-12-03 | 2014-03-01 | 2013-12-03 | 2014-03-01 | 26 |  |  |  | 0 | 0
DUKHCONP2BZ5MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 26 | No | DUKHCONP2BZ5MSEX5000, DUKHCONP2BZ5MSEX5000 | DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5PLTC8005, DUKHCONP2BZ5MSEX5015, DUKHCONP2BZ5MSEX5015, DUKHCONP2BZ5ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ5MSEX5020 | Construction Entrance Ramp | 20 | 20 | 0% | 2013-12-26 | 2014-01-18 | 2013-12-26 | 2014-01-18 | 30 | No | DUKHCONP2BZ5STRF2065, DUKHCONP2BZ5STRF2065, DUKHCONP2BZ4MSEX5020 | DUKHCONP2BZ5HDEX5090, DUKHCONP2BZ5MSEX5025, DUKHCONP2BZ5MSEX5055, DUKHCONP2BZ5HDEX5090, DUKHCONP2BZ5MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ5MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 26 | No | DUKHCONP2BZ5MSEX5005, DUKHCONP2BZ5MSEX5005 | DUKHCONP2BZ5MSEX5010, DUKHCONP2BZ5WEEX5065, DUKHCONP2BZ5WEEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ5MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 26 | No | DUKHCONP2BZ4MSEX5000, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5STRF2065, DUKHCONP2BZ5PLGF4310, DUKHCONP2BZ5STRF2065 | DUKHCONP2BZ5MSEX5005, DUKHCONP2BZ5MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ5MSEX5055 | Installation Steel Door | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 30 | No | DUKHCONP2BZ5MSEX5020 | DUKHCONP2BZ5MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ5MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-01-19 | 2014-02-10 | 2014-01-19 | 2014-02-10 | 30 | No | DUKHCONP2BZ5MSEX5055, DUKHCONP2BZ5MSEX5020, DUKHCONP2BZ4MSEX5025, DUKHCONP2BZ5MSEX5020 | DUKHCONP2BZ5WEEX5050, DUKHCONP2BZ5WEEX5050, DUKHCONP2BZ5HDEX5090 | 0 | 0 | MISCELLANEOUS
DUKHCONP2BZ5MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 26 | No | DUKHCONP2BZ5MSEX5015 | DUKHCONP2BZ5ELGF4030 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L45.30 .25 .15 WATER TANK ENCLOSURE |  | 94 | 94 | 0% | 2014-01-25 | 2014-05-14 | 2014-01-25 | 2014-05-14 | 26 |  |  |  | 0 | 0
DUKHCONP2BZ5MSEX5335 | Aluminum Roll-up Shutter with 2m Wall | 25 | 25 | 0% | 2014-04-16 | 2014-05-14 | 2014-04-16 | 2014-05-14 | 26 | No | DUKHCONI2BZ2BWGL5325, DUKHCONP2BZ4MSEX5335 | DUKHHANP2BGNPLTC9005, DUKHHANP2BGNACTC9000, DUKHHANP2BGNELTC9010 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 15 | No | DUKHCONP2BZ5WEEX5035, DUKHCONP2BZ5WEEX5035 | DUKHCONP2BZ5WEEX5045, DUKHCONP2BZ5WEEX5045 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 15 | No | DUKHCONP2BZ5WEEX5030, DUKHCONP2BZ5WEEX5030 | DUKHCONP2BZ5WEEX5040, DUKHCONP2BZ5WEEX5040 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5030 | Excavation | 20 | 20 | 0% | 2014-01-25 | 2014-02-17 | 2014-01-25 | 2014-02-17 | 15 | No | DUKHCONP2BZ5STRF2065, DUKHCONP2BZ4WEEX5035, DUKHCONP2BZ5STRF2065 | DUKHCONP2BZ5WEEX5035, DUKHCONP2BZ5WEEX5035 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-02-22 | 2014-03-22 | 2014-02-22 | 2014-03-22 | 15 | No | DUKHCONP2BZ5WEEX5040, DUKHCONP2BZ5WEEX5040 | DUKHCONP2BZ5WEEX5050, DUKHCONP2BZ5WEEX5050 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-03-29 | 2014-04-26 | 2014-03-29 | 2014-04-26 | 15 | No | DUKHCONP2BZ5WEEX5060, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5MSEX5015, DUKHCONP2BZ5WEEX5060, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5MSEX5015, DUKHCONP2BZ4WEEX5065 | DUKHCONP2BZ5WEEX5070, DUKHCONP2BZ5PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5070 | Installation ladder for water Tank | 20 | 20 | 0% | 2014-04-12 | 2014-05-04 | 2014-04-12 | 2014-05-04 | 10 | No | DUKHCONP2BZ5WEEX5065, DUKHCONP2BZ4WEEX5070 | DUKHCONP2BZ5PLTC8005 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5050 | Installation of Steel | 20 | 20 | 0% | 2014-03-11 | 2014-04-02 | 2014-03-11 | 2014-04-02 | 15 | No | DUKHCONP2BZ5WEEX5045, DUKHCONP2BZ5MSEX5025, DUKHCONP2BZ5MSEX5025, DUKHCONP2BZ5WEEX5045, DUKHCONP2BZ4WEEX5050 | DUKHCONP2BZ5WEEX5060, DUKHCONP2BZ5WEEX5060 | 0 | 0 | WATER TANK ENCLOSURE
DUKHCONP2BZ5WEEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-03-17 | 2014-04-14 | 2014-03-17 | 2014-04-14 | 15 | No | DUKHCONP2BZ5WEEX5050, DUKHCONP2BZ5WEEX5050 | DUKHCONP2BZ5WEEX5065, DUKHCONP2BZ5WEEX5065 | 0 | 0 | WATER TANK ENCLOSURE
DHBL.K30.L45.30 .25 .20 HARD LANDSCAPING |  | 43 | 43 | 0% | 2014-01-27 | 2014-03-18 | 2014-01-27 | 2014-03-18 | 30 |  |  |  | 0 | 0
DUKHCONP2BZ5HDEX5095 | Cobble Stone Works | 20 | 20 | 0% | 2014-02-08 | 2014-03-03 | 2014-02-08 | 2014-03-03 | 30 | No | DUKHCONP2BZ5HDEX5090, DUKHCONP2BZ5HDEX5090 | DUKHCONP2BZ5HDEX5100, DUKHCONP2BZ5HDEX5100 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2BZ5HDEX5100 | Interlock works | 20 | 20 | 0% | 2014-02-24 | 2014-03-18 | 2014-02-24 | 2014-03-18 | 30 | No | DUKHCONP2BZ5HDEX5095, DUKHCONP2BZ5HDEX5095 | DUKHCONP2BZ5ACTC8000, DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5SLEX5105, DUKHCONP2BZ5SLEX5105, DUKHCONP2BZ5PLTC8005 | 0 | 0 | HARD LANDSCAPING
DUKHCONP2BZ5HDEX5090 | kerb works | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 30 | No | DUKHCONP2BZ5MSEX5020, DUKHCONP2BZ4HDEX5090, DUKHCONP2BZ5MSEX5025, DUKHCONP2BZ5MSEX5020 | DUKHCONP2BZ5HDEX5095, DUKHCONP2BZ5HDEX5095 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L45.30 .25 .25 SOFT LANDSCAPING |  | 30 | 30 | 0% | 2014-03-18 | 2014-04-21 | 2014-03-18 | 2014-04-21 | 21 |  |  |  | 0 | 0
DUKHCONP2BZ5SLEX5105 | Laying of Grass/ green area | 20 | 20 | 0% | 2014-03-18 | 2014-04-09 | 2014-03-18 | 2014-04-09 | 21 | No | DUKHCONP2BZ4SLEX5105, DUKHCONP2BZ5HDEX5100, DUKHCONP2BZ5HDEX5100 | DUKHCONP2BZ5PLTC8005, DUKHCONP2BZ5SLEX5110, DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5ACTC8000, DUKHCONP2BZ5SLEX5110 | 0 | 0 | SOFT LANDSCAPING
DUKHCONP2BZ5SLEX5110 | Laying of Palm tree | 20 | 20 | 0% | 2014-03-30 | 2014-04-21 | 2014-03-30 | 2014-04-21 | 21 | No | DUKHCONP2BZ5SLEX5105, DUKHCONP2BZ4SLEX5110, DUKHCONP2BZ5SLEX5105 | DUKHCONP2BZ5PLTC8005, DUKHCONP2BZ5ACTC8000, DUKHCONP2BZ5ELTC8010 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L45.30 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 |  |  |  | 0 | 0
DUKHCONP2BZ5ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 | Yes | DUKHCONP2BZ5HDEX5100, DUKHCONP2BZ5AREL3680, DUKHCONP2BZ5SLEX5110, DUKHMOBI2BPS00002275, DUKHCONP2BZ5SLEX5105, DUKHCONP2BZ5ACRF4635, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5MSEX5005, DUKHMOBP2BPS00002240, DUKHCONP2BZ5ARRF3660 | DUKHHANP2BGNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2BZ5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 | Yes | DUKHCONP2BZ5ELGF4025, DUKHMOBI2BPS00002275, DUKHCONP2BZ5ELGF4015, DUKHCONP2BZ5AREL3680, DUKHCONP2BZ5ARRF3660, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5MSEX5005, DUKHCONP2BZ5ELRF4075, DUKHCONP2BZ5HDEX5100, DUKHCONP2BZ5SLEX5105, DUKHMOBP2BPS00002240, DUKHCONP2BZ5ELGF4030, DUKHCONP2BZ5SLEX5110 | DUKHHANP2BGNACTC9000, DUKHHANP2BGNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP2BZ5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 | Yes | DUKHCONP2BZ5SLEX5105, DUKHCONP2BZ5AREL3680, DUKHCONP2BZ5MSEX5005, DUKHCONP2BZ5SLEX5110, DUKHCONP2BZ5ARGF3095, DUKHCONP2BZ5WEEX5070, DUKHCONP2BZ5ARRF3660, DUKHCONP2BZ5PLRF4350, DUKHCONP2BZ5WEEX5065, DUKHMOBP2BPS00002240, DUKHMOBI2BPS00002275, DUKHCONP2BZ5PLGF4320, DUKHCONP2BZ5HDEX5100 | DUKHHANP2BGNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L50 PACKAGE-2B INFRASTRUCTURE WORKS |  | 249 | 249 | 0% | 2013-07-31 | 2014-05-25 | 2013-07-31 | 2014-05-25 | 17 |  |  |  | 0 | 0
DHBL.K30.L50.10 ZONE- 1 |  | 207 | 207 | 0% | 2013-07-31 | 2014-04-06 | 2013-07-31 | 2014-04-06 | 49 |  |  |  | 0 | 0
DHBL.K30.L50.10 .10 INFRASTRUCTURE WORKS |  | 207 | 207 | 0% | 2013-07-31 | 2014-04-06 | 2013-07-31 | 2014-04-06 | 49 |  |  |  | 0 | 0
DHBL.K30.L50.10 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-07-31 | 2013-09-22 | 2013-07-31 | 2013-09-22 | 17 |  |  |  | 0 | 0
DUKHCONI2BZ1DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-09-05 | 2013-09-22 | 2013-09-05 | 2013-09-22 | 17 | No | DUKHCONI2BZ1DRGL5125, DUKHCONI2BZ1DRGL5125 | DUKHCONI2BZ2DRGL5115, DUKHCONI2BZ1WSGL5155, DUKHCONI2BZ1SAGL5140, DUKHCONI2BZ1SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI2BZ1DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-07-31 | 2013-09-01 | 2013-07-31 | 2013-09-01 | 17 | No | DUKHCONP2BZ4STGF2000, DUKHENGI2BDWDRAP5430 | DUKHCONI2BZ1SAGL5140, DUKHCONI2BZ1DRGL5120, DUKHCONI2BZ1SAGL5135, DUKHCONI2BZ1DRGL5120, DUKHMOBI2BPS00002275 | 0 | 0 | DRAINAGE LINES
DUKHCONI2BZ1DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-08-07 | 2013-09-08 | 2013-08-07 | 2013-09-08 | 17 | No | DUKHCONI2BZ1DRGL5115, DUKHCONI2BZ1DRGL5115 | DUKHCONI2BZ1DRGL5125, DUKHCONI2BZ1DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI2BZ1DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-08-19 | 2013-09-16 | 2013-08-19 | 2013-09-16 | 17 | No | DUKHCONI2BZ1DRGL5120, DUKHCONI2BZ1DRGL5120 | DUKHCONI2BZ1DRGL5130, DUKHCONI2BZ1DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L50.10 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-09-05 | 2013-11-27 | 2013-09-05 | 2013-11-27 | 43 |  |  |  | 0 | 0
DUKHCONI2BZ1SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2013-11-05 | 2013-11-27 | 2013-11-05 | 2013-11-27 | 43 | No | DUKHCONI2BZ1SAGL5135, DUKHCONI2BZ1SAGL5145 | DUKHCONI2BZ1RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2BZ1SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-09-05 | 2013-10-03 | 2013-09-05 | 2013-10-03 | 68 | No | DUKHCONI2BZ1DRGL5115, DUKHENGI2BDWDRAP5430, DUKHCONI2BZ1DRGL5130 | DUKHCONI2BZ2SAGL5135, DUKHCONI2BZ1SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2BZ1SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2013-10-05 | 2013-11-04 | 2013-10-05 | 2013-11-04 | 17 | No | DUKHCONI2BZ1SAGL5140 | DUKHCONI2BZ1WSGL5170, DUKHCONI2BZ2SAGL5145, DUKHCONI2BZ1SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2BZ1SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-09-05 | 2013-10-03 | 2013-09-05 | 2013-10-03 | 17 | No | DUKHCONI2BZ1DRGL5115, DUKHCONI2BZ1DRGL5130 | DUKHCONI2BZ1SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L50.10 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2013-09-17 | 2013-12-03 | 2013-09-17 | 2013-12-03 | 38 |  |  |  | 0 | 0
DUKHCONI2BZ1WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2013-10-05 | 2013-11-04 | 2013-10-05 | 2013-11-04 | 17 | No | DUKHCONI2BZ1SAGL5145, DUKHCONI2BZ1WSGL5165 | DUKHCONI2BZ2WSGL5155, DUKHCONI2BZ1WSGL5175, DUKHCONI2BZ1FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ1WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-10-10 | 2013-11-10 | 2013-10-10 | 2013-11-10 | 38 | No | DUKHCONI2BZ1WSGL5155, DUKHCONI2BZ1WSGL5170 | DUKHCONI2BZ1WSGL5180, DUKHCONI2BZ2WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ1WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-09-17 | 2013-10-15 | 2013-09-17 | 2013-10-15 | 17 | No | DUKHCONI2BZ1DRGL5130, DUKHENGI2BDWWSAP5450 | DUKHCONI2BZ1WSGL5160, DUKHCONI2BZ1WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ1WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2013-11-11 | 2013-12-03 | 2013-11-11 | 2013-12-03 | 38 | No | DUKHCONI2BZ1WSGL5175 | DUKHCONI2BZ2WSGL5180, DUKHCONI2BZ1FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ1WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-09-23 | 2013-10-23 | 2013-09-23 | 2013-10-23 | 17 | No | DUKHCONI2BZ1WSGL5155 | DUKHCONI2BZ1WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ1WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2013-09-29 | 2013-10-29 | 2013-09-29 | 2013-10-29 | 17 | No | DUKHCONI2BZ1WSGL5160 | DUKHCONI2BZ1WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L50.10 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2013-10-10 | 2013-12-11 | 2013-10-10 | 2013-12-11 | 31 |  |  |  | 0 | 0
DUKHCONI2BZ1FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2013-11-02 | 2013-11-30 | 2013-11-02 | 2013-11-30 | 17 | No | DUKHCONI2BZ1FFGL5195 | DUKHCONI2BZ1FFGL5205, DUKHCONI2BZ2FFGL5185, DUKHCONI2BZ1ELGL5215, DUKHCONI2BZ1RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ1FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2013-11-13 | 2013-12-11 | 2013-11-13 | 2013-12-11 | 31 | No | DUKHCONI2BZ1FFGL5205, DUKHCONI2BZ1WSGL5180 | DUKHCONI2BZ1RWGL6000, DUKHCONI2BZ2FFGL5210, DUKHCONI2BSBIWGL7440 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ1FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-11-07 | 2013-12-05 | 2013-11-07 | 2013-12-05 | 31 | No | DUKHCONI2BZ1FFGL5200, DUKHCONI2BZ1FFGL5185 | DUKHCONI2BZ2FFGL5205, DUKHCONI2BZ1FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ1FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2013-10-10 | 2013-11-10 | 2013-10-10 | 2013-11-10 | 17 | No | DUKHENGI2BDWFFAP5440, DUKHCONI2BZ1WSGL5170 | DUKHCONI2BZ1FFGL5190, DUKHCONI2BZ1FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ1FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2013-10-21 | 2013-11-18 | 2013-10-21 | 2013-11-18 | 17 | No | DUKHCONI2BZ1FFGL5185 | DUKHCONI2BZ1FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ1FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2013-10-27 | 2013-11-24 | 2013-10-27 | 2013-11-24 | 17 | No | DUKHCONI2BZ1FFGL5190 | DUKHCONI2BZ1FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L50.10 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2013-11-10 | 2014-01-04 | 2013-11-10 | 2014-01-04 | 62 |  |  |  | 0 | 0
DUKHCONI2BZ1ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2013-11-24 | 2013-12-23 | 2013-11-24 | 2013-12-23 | 22 | No | DUKHCONI2BZ1ELGL5215, DUKHCONI2BZ1ELGL5220 | DUKHCONI2BZ1RWGL6000, DUKHCONI2BZ1IRGL5285, DUKHCONI2BZ1IRGL5265, DUKHCONI2BZ1ELGL5230, DUKHCONI2BZ1ELGL5230, DUKHCONI2BZ2ELGL5215 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2BZ1ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 62 | No | DUKHCONI2BZ1ELGL5225, DUKHCONI2BZ1ELGL5225 | DUKHCONI2BZ1STGL5260, DUKHCONI2BZ2ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2BZ1ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 19 | No | DUKHENGI2BDWELAP5460, DUKHCONI2BZ1FFGL5200 | DUKHCONI2BZ1ELGL5225, DUKHCONI2BZ1STGL5235, DUKHCONI2BZ1ELGL5220 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2BZ1ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 22 | No | DUKHCONI2BZ1ELGL5215 | DUKHCONI2BZ1ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L50.10 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2013-11-10 | 2014-02-02 | 2013-11-10 | 2014-02-02 | 62 |  |  |  | 0 | 0
DUKHCONI2BZ1STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 19 | No | DUKHCONI2BZ1STGL5235, DUKHCONI2BZ1STGL5245 | DUKHCONI2BZ1BWGL5315, DUKHCONI2BZ2STGL5235, DUKHCONI2BZ1STGL5255, DUKHCONI2BZ1RWGL6000, DUKHCONI2BZ1TCGL5295 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ1STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 19 | No | DUKHCONI2BZ1STGL5235 | DUKHCONI2BZ1STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ1STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 19 | No | DUKHCONI2BZ1STGL5240 | DUKHCONI2BZ1STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ1STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 62 | No | DUKHCONI2BZ1ELGL5230, DUKHCONI2BZ1STGL5255 | DUKHCONI2BZ2STGL5260, DUKHCONI2BZ1PSGL7015 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ1STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 19 | No | DUKHCONI2BZ1ELGL5215, DUKHENGI2BDWSTAP5470 | DUKHCONI2BZ1STGL5250, DUKHCONI2BZ1STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ1STGL5255 | Installation of light Post | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 82 | No | DUKHCONI2BZ1STGL5250 | DUKHCONI2BZ2STGL5255, DUKHCONI2BZ1STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L50.10 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2013-12-24 | 2014-03-01 | 2013-12-24 | 2014-03-01 | 35 |  |  |  | 0 | 0
DUKHCONI2BZ1IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 30 | No | DUKHCONI2BZ1IRGL5275 | DUKHCONI2BZ1IRGL5290, DUKHCONI2BZ1IRGL5285, DUKHCONI2BZ2IRGL5265 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 35 | No | DUKHCONI2BZ1IRGL5280, DUKHCONI2BZ1ELGL5225 | DUKHCONI2BZ1IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ1IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 30 | No | DUKHCONI2BZ1ELGL5225, DUKHENGI2BDWIRAP5490 | DUKHCONI2BZ1IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 35 | No | DUKHCONI2BZ1IRGL5280, DUKHCONI2BZ1IRGL5285 | DUKHCONI2BZ1SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ1IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 30 | No | DUKHCONI2BZ1IRGL5265 | DUKHCONI2BZ1IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ1IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 30 | No | DUKHCONI2BZ1IRGL5270 | DUKHCONI2BZ1IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L50.10 .10 .45 TELECOMMUNICATION LINES |  | 44 | 44 | 0% | 2013-12-03 | 2014-01-23 | 2013-12-03 | 2014-01-23 | 60 |  |  |  | 0 | 0
DUKHCONI2BZ1TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2013-12-15 | 2014-01-07 | 2013-12-15 | 2014-01-07 | 19 | No | DUKHCONI2BZ1TCGL5300 | DUKHCONI2BZ1TCGL5310, DUKHCONI2BZ2TCGL5295, DUKHCONI2BZ1RWGL6000 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2BZ1TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-01-01 | 2014-01-23 | 2014-01-01 | 2014-01-23 | 60 | No | DUKHCONI2BZ1TCGL5305 | DUKHCONI2BZ2TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2BZ1TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2013-12-03 | 2013-12-26 | 2013-12-03 | 2013-12-26 | 19 | No | DUKHENGI2BDWTCAP5480, DUKHCONI2BZ1STGL5250 | DUKHCONI2BZ1TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2BZ1TCGL5300 | Laying of cables | 20 | 20 | 0% | 2013-12-09 | 2014-01-01 | 2013-12-09 | 2014-01-01 | 19 | No | DUKHCONI2BZ1TCGL5295 | DUKHCONI2BZ1TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L50.10 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2013-12-03 | 2014-03-01 | 2013-12-03 | 2014-03-01 | 60 |  |  |  | 0 | 0
DUKHCONI2BZ1BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 60 | No | DUKHCONI2BZ1BWGL5325 | DUKHCONI2BZ2BWGL5330, DUKHCONI2BZ1PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI2BZ1BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 43 | No | DUKHCONI2BZ1BWGL5320, DUKHCONI2BZ1BWGL5315 | DUKHCONP2BZ3MSEX5335, DUKHCONI2BZ1BWGL5330, DUKHCONI2BZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI2BZ1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 43 | No | DUKHCONI2BZ1STGL5250, DUKHENGI2BDWBWAP5510 | DUKHCONI2BZ2BWGL5315, DUKHCONI2BZ1BWGL5320, DUKHCONI2BZ1BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI2BZ1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 43 | No | DUKHCONI2BZ1BWGL5315 | DUKHCONI2BZ1BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L50.10 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2013-12-28 | 2014-03-13 | 2013-12-28 | 2014-03-13 | 49 |  |  |  | 0 | 0
DUKHCONI2BZ1RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2013-12-28 | 2014-01-07 | 2013-12-28 | 2014-01-07 | 19 | No | DUKHCONI2BZ1ELGL5225, DUKHCONI2BZ1FFGL5210, DUKHENGI2BDWBWAP5510, DUKHCONI2BZ1FFGL5200, DUKHCONI2BZ1STGL5250, DUKHCONI2BZ1SAGL5150, DUKHCONI2BZ1TCGL5305 | DUKHCONI2BZ1HDGL7020, DUKHCONI2BZ1RWGL6005 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ1RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-03-03 | 2014-03-08 | 2014-03-03 | 2014-03-08 | 49 | No | DUKHCONI2BZ1RWGL6020 | DUKHCONI2BZ2RWGL6025, DUKHCONI2BZ1RWGL6030, DUKHCONI2BZ1HDGL7040 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ1RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-02-01 | 2014-02-24 | 2014-02-01 | 2014-02-24 | 19 | No | DUKHCONI2BZ1RWGL6010 | DUKHCONI2BZ1PSGL7000, DUKHCONI2BZ1RWGL6020, DUKHCONI2BZ2RWGL6000, DUKHCONI2BZ1PSGL7005 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ1RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 19 | No | DUKHCONI2BZ1RWGL6005 | DUKHCONI2BZ1RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ1RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-02-25 | 2014-03-02 | 2014-02-25 | 2014-03-02 | 34 | No | DUKHCONI2BZ1RWGL6015 | DUKHCONI2BZ1PSGL7010, DUKHCONI2BZ1RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ1RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 19 | No | DUKHCONI2BZ1RWGL6000 | DUKHCONI2BZ1RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ1RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-03-09 | 2014-03-13 | 2014-03-09 | 2014-03-13 | 49 | No | DUKHCONI2BZ1RWGL6025 | DUKHCONI2BZ1PSGL7010, DUKHCONI2BZ2RWGL6030 | 0 | 0 | ROAD WORKS
DHBL.K30.L50.10 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-02-06 | 2014-04-06 | 2014-02-06 | 2014-04-06 | 34 |  |  |  | 0 | 0
DUKHCONI2BZ1PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 34 | No | DUKHCONI2BZ1PSGL7005, DUKHCONI2BZ1BWGL5330, DUKHCONI2BZ1RWGL6030, DUKHCONI2BZ1RWGL6020 | DUKHCONI2BZ1PSGL7015, DUKHCONI2BZ2PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI2BZ1PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 34 | No | DUKHCONI2BZ1PSGL7010, DUKHCONI2BZ1STGL5260 | DUKHCONI2BZ2PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI2BZ1PSGL7000 | Excavation | 15 | 15 | 0% | 2014-02-06 | 2014-02-24 | 2014-02-06 | 2014-02-24 | 39 | No | DUKHCONI2BZ1RWGL6015, DUKHENGI2BDWPSAP5520 | DUKHCONI2BZ1PSGL7005, DUKHCONI2BZ1PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI2BZ1PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-02-19 | 2014-03-08 | 2014-02-19 | 2014-03-08 | 34 | No | DUKHCONI2BZ1PSGL7000, DUKHCONI2BZ1RWGL6015, DUKHCONI2BZ1PSGL7000 | DUKHCONI2BZ1PSGL7010, DUKHCONI2BZ2PSGL7000 | 0 | 0 | PARKING SHED
DHBL.K30.L50.10 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2013-12-28 | 2014-03-19 | 2013-12-28 | 2014-03-19 | 64 |  |  |  | 0 | 0
DUKHCONI2BZ1HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 34 | No | DUKHCONI2BZ1HDGL7025 | DUKHCONI2BZ2HDGL7030, DUKHCONI2BZ1HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ1HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-03-09 | 2014-03-19 | 2014-03-09 | 2014-03-19 | 64 | No | DUKHCONI2BZ1HDGL7035, DUKHCONI2BZ1RWGL6025 | DUKHCONI2BZ2HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ1HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 34 | No | DUKHCONI2BZ1HDGL7030 | DUKHCONI2BZ1SLGL7200, DUKHCONI2BZ1HDGL7040, DUKHCONI2BZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ1HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 34 | No | DUKHCONI2BZ1HDGL7020 | DUKHCONI2BZ1HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ1HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2013-12-28 | 2014-01-19 | 2013-12-28 | 2014-01-19 | 34 | No | DUKHENGI2BDWSLAP5500, DUKHCONI2BZ1RWGL6000 | DUKHCONI2BZ1HDGL7025, DUKHCONI2BSBGZGL7900 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L50.10 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-02-01 | 2014-03-25 | 2014-02-01 | 2014-03-25 | 44 |  |  |  | 0 | 0
DUKHCONI2BZ1SLGL7200 | Excavation | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 34 | No | DUKHCONI2BZ1IRGL5290, DUKHCONI2BZ1HDGL7035, DUKHENGI2BDWSLAP5500 | DUKHCONI2BZ1SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2BZ1SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 44 | No | DUKHCONI2BZ1SLGL7205 | DUKHCONI2BZ2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2BZ1SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 34 | No | DUKHCONI2BZ1SLGL7200 | DUKHCONI2BZ1SLGL7210, DUKHCONI2BZ2SLGL7200 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L50.15 ZONE - 2 |  | 214 | 214 | 0% | 2013-09-14 | 2014-05-25 | 2013-09-14 | 2014-05-25 | 17 |  |  |  | 0 | 0
DHBL.K30.L50.15 .10 INFRASTRUCTURE WORKS |  | 214 | 214 | 0% | 2013-09-14 | 2014-05-25 | 2013-09-14 | 2014-05-25 | 17 |  |  |  | 0 | 0
DHBL.K30.L50.15 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-09-14 | 2013-11-04 | 2013-09-14 | 2013-11-04 | 24 |  |  |  | 0 | 0
DUKHCONI2BZ2DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-10-16 | 2013-11-04 | 2013-10-16 | 2013-11-04 | 24 | No | DUKHCONI2BZ2DRGL5125, DUKHCONI2BZ2DRGL5125 | DUKHCONI2BZ2WSGL5155, DUKHCONI2BZ2SAGL5135, DUKHCONI2BZ2SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI2BZ2DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-09-14 | 2013-10-12 | 2013-09-14 | 2013-10-12 | 24 | No | DUKHCONI2BZ1DRGL5130 | DUKHCONI2BZ2DRGL5120, DUKHCONI2BZ2SAGL5140, DUKHCONI2BZ2DRGL5120, DUKHCONI2BZ2SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI2BZ2DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-09-21 | 2013-10-21 | 2013-09-21 | 2013-10-21 | 24 | No | DUKHCONI2BZ2DRGL5115, DUKHCONI2BZ2DRGL5115 | DUKHCONI2BZ2DRGL5125, DUKHCONI2BZ2DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI2BZ2DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-09-29 | 2013-10-29 | 2013-09-29 | 2013-10-29 | 24 | No | DUKHCONI2BZ2DRGL5120, DUKHCONI2BZ2DRGL5120 | DUKHCONI2BZ2DRGL5130, DUKHCONI2BZ2DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L50.15 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-10-16 | 2014-01-08 | 2013-10-16 | 2014-01-08 | 48 |  |  |  | 0 | 0
DUKHCONI2BZ2SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2013-12-16 | 2014-01-08 | 2013-12-16 | 2014-01-08 | 48 | No | DUKHCONI2BZ2SAGL5135, DUKHCONI2BZ2SAGL5145 | DUKHCONI2BZ2RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2BZ2SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-10-16 | 2013-11-16 | 2013-10-16 | 2013-11-16 | 73 | No | DUKHCONI2BZ2DRGL5130, DUKHCONI2BZ1SAGL5135, DUKHCONI2BZ2DRGL5115 | DUKHCONI2BZ2SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2BZ2SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2013-11-17 | 2013-12-15 | 2013-11-17 | 2013-12-15 | 24 | No | DUKHCONI2BZ2SAGL5140, DUKHCONI2BZ1SAGL5145 | DUKHCONI2BZ2WSGL5170, DUKHCONI2BZ2SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI2BZ2SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-10-16 | 2013-11-16 | 2013-10-16 | 2013-11-16 | 24 | No | DUKHCONI2BZ2DRGL5115, DUKHCONI2BZ2DRGL5130 | DUKHCONI2BZ2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L50.15 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2013-11-05 | 2014-01-20 | 2013-11-05 | 2014-01-20 | 38 |  |  |  | 0 | 0
DUKHCONI2BZ2WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2013-11-23 | 2013-12-22 | 2013-11-23 | 2013-12-22 | 19 | No | DUKHCONI2BZ2SAGL5145, DUKHCONI2BZ2WSGL5165 | DUKHCONI2BZ2FFGL5185, DUKHCONI2BZ2WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ2WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-11-28 | 2013-12-28 | 2013-11-28 | 2013-12-28 | 38 | No | DUKHCONI2BZ2WSGL5170, DUKHCONI2BZ2WSGL5155, DUKHCONI2BZ1WSGL5175 | DUKHCONI2BZ2WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ2WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-11-05 | 2013-12-03 | 2013-11-05 | 2013-12-03 | 19 | No | DUKHCONI2BZ1WSGL5170, DUKHCONI2BZ2DRGL5130 | DUKHCONI2BZ2WSGL5175, DUKHCONI2BZ2WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ2WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2013-12-29 | 2014-01-20 | 2013-12-29 | 2014-01-20 | 38 | No | DUKHCONI2BZ1WSGL5180, DUKHCONI2BZ2WSGL5175 | DUKHHANP2BGNACTC9000, DUKHHANP2BGNPLTC9005, DUKHCONI2BZ2FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ2WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-11-11 | 2013-12-09 | 2013-11-11 | 2013-12-09 | 19 | No | DUKHCONI2BZ2WSGL5155 | DUKHCONI2BZ2WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI2BZ2WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2013-11-17 | 2013-12-15 | 2013-11-17 | 2013-12-15 | 19 | No | DUKHCONI2BZ2WSGL5160 | DUKHCONI2BZ2WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L50.15 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2013-12-01 | 2014-01-30 | 2013-12-01 | 2014-01-30 | 29 |  |  |  | 0 | 0
DUKHCONI2BZ2FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 17 | No | DUKHCONI2BZ2FFGL5195 | DUKHCONI2BZ2RWGL6000, DUKHCONI2BZ2FFGL5205, DUKHCONI2BZ2ELGL5215 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ2FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 29 | No | DUKHCONI2BZ2FFGL5205, DUKHCONI2BZ2WSGL5180, DUKHCONI2BZ1FFGL5210 | DUKHHANP2BGNELTC9010, DUKHCONI2BSBIWGL7440, DUKHHANP2BGNACTC9000, DUKHHANP2BGNPLTC9005, DUKHCONI2BZ2RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ2FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 29 | No | DUKHCONI2BZ1FFGL5205, DUKHCONI2BZ2FFGL5185, DUKHCONI2BZ2FFGL5200 | DUKHCONI2BZ2FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ2FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2013-12-01 | 2013-12-30 | 2013-12-01 | 2013-12-30 | 17 | No | DUKHCONI2BZ2WSGL5170, DUKHCONI2BZ1FFGL5200 | DUKHCONI2BZ2FFGL5205, DUKHCONI2BZ2FFGL5190 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ2FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2013-12-09 | 2014-01-07 | 2013-12-09 | 2014-01-07 | 17 | No | DUKHCONI2BZ2FFGL5185 | DUKHCONI2BZ2FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI2BZ2FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2013-12-15 | 2014-01-13 | 2013-12-15 | 2014-01-13 | 17 | No | DUKHCONI2BZ2FFGL5190 | DUKHCONI2BZ2FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L50.15 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2013-12-30 | 2014-02-23 | 2013-12-30 | 2014-02-23 | 45 |  |  |  | 0 | 0
DUKHCONI2BZ2ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 20 | No | DUKHCONI2BZ2ELGL5215, DUKHCONI2BZ2ELGL5220 | DUKHCONI2BZ2ELGL5230, DUKHCONI2BZ2ELGL5230, DUKHCONI2BZ2IRGL5265, DUKHCONI2BZ2RWGL6000, DUKHCONI2BZ2IRGL5285 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2BZ2ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 45 | No | DUKHCONI2BZ2ELGL5225, DUKHCONI2BZ2ELGL5225, DUKHCONI2BZ1ELGL5230 | DUKHCONI2BZ2STGL5260, DUKHCONI2BSBIWGL7450 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2BZ2ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 17 | No | DUKHCONI2BZ2FFGL5200, DUKHCONI2BZ1ELGL5225 | DUKHCONI2BZ2ELGL5225, DUKHCONI2BZ2ELGL5220, DUKHCONI2BZ2STGL5235 | 0 | 0 | ELECTRICAL LINES
DUKHCONI2BZ2ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 20 | No | DUKHCONI2BZ2ELGL5215 | DUKHCONI2BZ2ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L50.15 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2013-12-30 | 2014-03-24 | 2013-12-30 | 2014-03-24 | 45 |  |  |  | 0 | 0
DUKHCONI2BZ2STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 17 | No | DUKHCONI2BZ2STGL5235, DUKHCONI2BZ2STGL5245 | DUKHCONI2BZ2RWGL6000, DUKHCONI2BZ2TCGL5295, DUKHCONI2BZ2BWGL5315, DUKHCONI2BZ2STGL5255 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ2STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 17 | No | DUKHCONI2BZ2STGL5235 | DUKHCONI2BZ2STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ2STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 17 | No | DUKHCONI2BZ2STGL5240 | DUKHCONI2BZ2STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ2STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 45 | No | DUKHCONI2BZ1STGL5260, DUKHCONI2BZ2ELGL5230, DUKHCONI2BZ2STGL5255 | DUKHCONI2BZ2PSGL7015, DUKHHANP2BGNPLTC9005, DUKHHANP2BGNACTC9000, DUKHCONI2BSBIWGL7450, DUKHHANP2BGNELTC9010 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ2STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 17 | No | DUKHCONI2BZ1STGL5250, DUKHCONI2BZ2ELGL5215 | DUKHCONI2BZ2STGL5250, DUKHCONI2BZ2STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI2BZ2STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 65 | No | DUKHCONI2BZ1STGL5255, DUKHCONI2BZ2STGL5250 | DUKHCONI2BZ2STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L50.15 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-02-12 | 2014-04-19 | 2014-02-12 | 2014-04-19 | 28 |  |  |  | 0 | 0
DUKHCONI2BZ2IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 28 | No | DUKHCONI2BZ2IRGL5275 | DUKHCONI2BZ2IRGL5285, DUKHCONI2BZ2IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 28 | No | DUKHCONI2BZ2IRGL5280, DUKHCONI2BZ2ELGL5225 | DUKHCONI2BZ2IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ2IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 28 | No | DUKHCONI2BZ2ELGL5225, DUKHCONI2BZ1IRGL5280 | DUKHCONI2BZ2IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 28 | No | DUKHCONI2BZ2IRGL5280, DUKHCONI2BZ2IRGL5285 | DUKHCONI2BZ2SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ2IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 28 | No | DUKHCONI2BZ2IRGL5265 | DUKHCONI2BZ2IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI2BZ2IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 28 | No | DUKHCONI2BZ2IRGL5270 | DUKHCONI2BZ2IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L50.15 .10 .45 TELECOMMUNICATION LINES |  | 40 | 40 | 0% | 2014-01-22 | 2014-03-10 | 2014-01-22 | 2014-03-10 | 42 |  |  |  | 0 | 0
DUKHCONI2BZ2TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-02-03 | 2014-02-26 | 2014-02-03 | 2014-02-26 | 17 | No | DUKHCONI2BZ2TCGL5300 | DUKHCONI2BZ2TCGL5310, DUKHCONI2BZ2RWGL6000 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2BZ2TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 42 | No | DUKHCONI2BZ1TCGL5310, DUKHCONI2BZ2TCGL5305 | DUKHHANP2BGNACTC9000, DUKHHANP2BGNPLTC9005, DUKHCONI2BSBIWGL7450, DUKHHANP2BGNELTC9010 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2BZ2TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-01-22 | 2014-02-15 | 2014-01-22 | 2014-02-15 | 17 | No | DUKHCONI2BZ2STGL5250, DUKHCONI2BZ1TCGL5305 | DUKHCONI2BZ2TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI2BZ2TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-01-28 | 2014-02-20 | 2014-01-28 | 2014-02-20 | 17 | No | DUKHCONI2BZ2TCGL5295 | DUKHCONI2BZ2TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L50.15 .10 .50 BOUNDARY WALL |  | 74 | 74 | 0% | 2014-01-22 | 2014-04-19 | 2014-01-22 | 2014-04-19 | 43 |  |  |  | 0 | 0
DUKHCONI2BZ2BWGL5330 | Const. of Blockwork fence Wall (Ht-1.85m) | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 43 | No | DUKHCONI2BZ1BWGL5330, DUKHCONI2BZ2BWGL5325 | DUKHCONI2BZ2PSGL7010 | 0 | 0 | BOUNDARY WALL
DUKHCONI2BZ2BWGL5325 | Const. of Villa Front Boundary Wall (Ht-2m) | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 26 | No | DUKHCONI2BZ2BWGL5320, DUKHCONI2BZ1BWGL5325, DUKHCONI2BZ2BWGL5315 | DUKHCONP2BZ4MSEX5335, DUKHCONP2BZ5MSEX5335, DUKHCONI2BZ2BWGL5330 | 0 | 0 | BOUNDARY WALL
DUKHCONI2BZ2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 26 | No | DUKHCONI2BZ1BWGL5315, DUKHCONI2BZ2STGL5250 | DUKHCONI2BZ2BWGL5320, DUKHCONI2BZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DUKHCONI2BZ2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-02-08 | 2014-03-09 | 2014-02-08 | 2014-03-09 | 26 | No | DUKHCONI2BZ2BWGL5315 | DUKHCONI2BZ2BWGL5325 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L50.15 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-02-16 | 2014-05-01 | 2014-02-16 | 2014-05-01 | 32 |  |  |  | 0 | 0
DUKHCONI2BZ2RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-02-16 | 2014-02-26 | 2014-02-16 | 2014-02-26 | 17 | No | DUKHCONI2BZ2STGL5250, DUKHCONI2BZ2FFGL5200, DUKHCONI2BZ2ELGL5225, DUKHCONI2BZ2SAGL5150, DUKHCONI2BZ1RWGL6015, DUKHCONI2BZ2TCGL5305, DUKHCONI2BZ2FFGL5210 | DUKHCONI2BZ2RWGL6005, DUKHCONI2BZ2HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ2RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-04-21 | 2014-04-26 | 2014-04-21 | 2014-04-26 | 32 | No | DUKHCONI2BZ1RWGL6025, DUKHCONI2BZ2RWGL6020 | DUKHCONI2BZ2RWGL6030, DUKHCONI2BZ2HDGL7040 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ2RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-03-23 | 2014-04-14 | 2014-03-23 | 2014-04-14 | 17 | No | DUKHCONI2BZ2RWGL6010 | DUKHCONI2BZ2RWGL6020, DUKHCONI2BZ2PSGL7005, DUKHCONI2BZ2PSGL7000 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ2RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-03-11 | 2014-04-08 | 2014-03-11 | 2014-04-08 | 17 | No | DUKHCONI2BZ2RWGL6005 | DUKHCONI2BZ2RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ2RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-04-15 | 2014-04-20 | 2014-04-15 | 2014-04-20 | 17 | No | DUKHCONI2BZ2RWGL6015 | DUKHCONI2BZ2PSGL7010, DUKHCONI2BZ2RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ2RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 17 | No | DUKHCONI2BZ2RWGL6000 | DUKHCONI2BZ2RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI2BZ2RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-04-27 | 2014-05-01 | 2014-04-27 | 2014-05-01 | 32 | No | DUKHCONI2BZ2RWGL6025, DUKHCONI2BZ1RWGL6030 | DUKHCONI2BZ2PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L50.15 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-03-29 | 2014-05-25 | 2014-03-29 | 2014-05-25 | 17 |  |  |  | 0 | 0
DUKHCONI2BZ2PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-04-21 | 2014-05-19 | 2014-04-21 | 2014-05-19 | 17 | No | DUKHCONI2BZ2RWGL6030, DUKHCONI2BZ2RWGL6020, DUKHCONI2BZ2PSGL7005, DUKHCONI2BZ2BWGL5330, DUKHCONI2BZ1PSGL7010 | DUKHCONI2BZ2PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI2BZ2PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-04-27 | 2014-05-25 | 2014-04-27 | 2014-05-25 | 17 | No | DUKHCONI2BZ2STGL5260, DUKHCONI2BZ2PSGL7010, DUKHCONI2BZ1PSGL7015 | DUKHHANP2BGNELTC9010, DUKHHANP2BGNACTC9000, DUKHHANP2BGNPLTC9005 | 0 | 0 | PARKING SHED
DUKHCONI2BZ2PSGL7000 | Excavation | 15 | 15 | 0% | 2014-03-29 | 2014-04-14 | 2014-03-29 | 2014-04-14 | 22 | No | DUKHCONI2BZ1PSGL7005, DUKHCONI2BZ2RWGL6015 | DUKHCONI2BZ2PSGL7005, DUKHCONI2BZ2PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI2BZ2PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-04-09 | 2014-04-26 | 2014-04-09 | 2014-04-26 | 17 | No | DUKHCONI2BZ2PSGL7000, DUKHCONI2BZ2RWGL6015, DUKHCONI2BZ2PSGL7000 | DUKHCONI2BZ2PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L50.15 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-02-16 | 2014-05-07 | 2014-02-16 | 2014-05-07 | 32 |  |  |  | 0 | 0
DUKHCONI2BZ2HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-03-11 | 2014-04-08 | 2014-03-11 | 2014-04-08 | 27 | No | DUKHCONI2BZ1HDGL7030, DUKHCONI2BZ2HDGL7025 | DUKHCONI2BZ2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ2HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-04-27 | 2014-05-07 | 2014-04-27 | 2014-05-07 | 32 | No | DUKHCONI2BZ1HDGL7040, DUKHCONI2BZ2HDGL7035, DUKHCONI2BZ2RWGL6025 | DUKHHANP2BGNELTC9010, DUKHHANP2BGNPLTC9005 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ2HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-03-11 | 2014-04-08 | 2014-03-11 | 2014-04-08 | 27 | No | DUKHCONI2BZ2HDGL7030, DUKHCONI2BZ1HDGL7035 | DUKHCONI2BZ2SLGL7200, DUKHCONI2BZ2HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ2HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 27 | No | DUKHCONI2BZ2HDGL7020, DUKHCONI2BSBGZGL7910 | DUKHCONI2BZ2HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI2BZ2HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 27 | No | DUKHCONI2BZ2RWGL6000 | DUKHCONI2BZ2HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L50.15 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-03-23 | 2014-05-13 | 2014-03-23 | 2014-05-13 | 27 |  |  |  | 0 | 0
DUKHCONI2BZ2SLGL7200 | Excavation for Landscaping | 25 | 25 | 0% | 2014-03-23 | 2014-04-20 | 2014-03-23 | 2014-04-20 | 27 | No | DUKHCONI2BZ1SLGL7205, DUKHCONI2BZ2HDGL7035, DUKHCONI2BZ2IRGL5290 | DUKHCONI2BZ2SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2BZ2SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-04-15 | 2014-05-13 | 2014-04-15 | 2014-05-13 | 27 | No | DUKHCONI2BZ1SLGL7210, DUKHCONI2BZ2SLGL7205 | DUKHHANP2BGNACTC9000, DUKHHANP2BGNPLTC9005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI2BZ2SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 27 | No | DUKHCONI2BZ2SLGL7200 | DUKHCONI2BZ2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L50.25 SECONDARY BUILDINGS |  | 146 | 146 | 0% | 2013-12-02 | 2014-05-22 | 2013-12-02 | 2014-05-22 | 19 |  |  |  | 0 | 0
DHBL.K30.L50.25 .10 INFRASTRUCTURE WORKS |  | 146 | 146 | 0% | 2013-12-02 | 2014-05-22 | 2013-12-02 | 2014-05-22 | 19 |  |  |  | 0 | 0
DHBL.K30.L50.25 .10 .10 IRRIGATION WATER TANK & PUMP ROOM |  | 146 | 146 | 0% | 2013-12-02 | 2014-05-22 | 2013-12-02 | 2014-05-22 | 19 |  |  |  | 0 | 0
DUKHCONI2BSBIWGL7445 | AC Works | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 19 | No | DUKHCONI2BSBIWGL7440 | DUKHCONI2BSBIWGL7450 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7405 | Blinding & base waterproofing | 10 | 10 | 0% | 2013-12-21 | 2013-12-31 | 2013-12-21 | 2013-12-31 | 19 | No | DUKHCONI2BSBIWGL7400 | DUKHCONI2BSBIWGL7410 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7420 | Construction of Roof Slab | 20 | 20 | 0% | 2014-02-12 | 2014-03-06 | 2014-02-12 | 2014-03-06 | 19 | No | DUKHCONI2BSBIWGL7415 | DUKHCONI2BSBIWGL7425, DUKHCONI2BSBIWGL7430 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7410 | Construction of Raft slab | 10 | 10 | 0% | 2014-01-01 | 2014-01-12 | 2014-01-01 | 2014-01-12 | 19 | No | DUKHCONI2BSBIWGL7405 | DUKHCONI2BSBIWGL7415 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7415 | Construction of RCC Wall | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 19 | No | DUKHCONI2BSBIWGL7410 | DUKHCONI2BSBIWGL7420 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7450 | Electrical Works | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 19 | No | DUKHCONI2BSBIWGL7445, DUKHCONI2BZ2STGL5260, DUKHCONI2BZ2TCGL5310, DUKHCONI2BZ2ELGL5230 | DUKHCONI2BSBIWGL7455 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7400 | Excavation | 15 | 15 | 0% | 2013-12-02 | 2013-12-19 | 2013-12-02 | 2013-12-19 | 19 | No | DUKHCONP2BZ5STRF2060, DUKHENGI2BDWIWAP5540 | DUKHCONI2BSBIWGL7405 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7430 | Floor screed | 5 | 5 | 0% | 2014-04-01 | 2014-04-06 | 2014-04-01 | 2014-04-06 | 19 | No | DUKHCONI2BSBIWGL7425, DUKHCONI2BSBIWGL7420 | DUKHCONI2BSBIWGL7440 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7435 | Installation of Boundary Fences | 15 | 15 | 0% | 2014-04-06 | 2014-04-22 | 2014-04-06 | 2014-04-22 | 40 | No | DUKHCONI2BSBIWGL7950 | DUKHCONI2BSBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7465 | Installation of G.I Handrails | 5 | 5 | 0% | 2014-05-18 | 2014-05-22 | 2014-05-18 | 2014-05-22 | 19 | No | DUKHCONI2BSBIWGL7460, DUKHCONI2BSBIWGL7435 | DUKHHANP2BGNELTC9010, DUKHHANP2BGNPLTC9005, DUKHHANP2BGNACTC9000 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7460 | Installation of Steel Ladder | 5 | 5 | 0% | 2014-05-12 | 2014-05-17 | 2014-05-12 | 2014-05-17 | 19 | No | DUKHCONI2BSBIWGL7455 | DUKHCONI2BSBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7455 | Internal epoxy coating & Painting | 5 | 5 | 0% | 2014-05-06 | 2014-05-11 | 2014-05-06 | 2014-05-11 | 19 | No | DUKHCONI2BSBIWGL7450 | DUKHCONI2BSBIWGL7460 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7950 | Laying of Interlock | 10 | 10 | 0% | 2014-03-25 | 2014-04-05 | 2014-03-25 | 2014-04-05 | 40 | No | DUKHCONI2BSBIWGL7425 | DUKHCONI2BSBIWGL7435 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7440 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-04-07 | 2014-05-05 | 2014-04-07 | 2014-05-05 | 19 | No | DUKHCONI2BSBIWGL7430, DUKHCONI2BZ2FFGL5210, DUKHCONI2BZ1FFGL5210 | DUKHCONI2BSBIWGL7445 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI2BSBIWGL7425 | Waterproofing & Backfilling | 15 | 15 | 0% | 2014-03-08 | 2014-03-24 | 2014-03-08 | 2014-03-24 | 25 | No | DUKHCONI2BSBIWGL7420 | DUKHCONI2BSBIWGL7950, DUKHCONI2BSBIWGL7430 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DHBL.K30.L50.25 .10 .25 GAZEBO |  | 50 | 50 | 0% | 2014-01-20 | 2014-03-19 | 2014-01-20 | 2014-03-19 | 34 |  |  |  | 0 | 0
DUKHCONI2BSBGZGL7900 | Construction of Concrete structure | 20 | 20 | 0% | 2014-01-20 | 2014-02-12 | 2014-01-20 | 2014-02-12 | 34 | No | DUKHENGI2BDWGZAP5550, DUKHCONI2BZ1HDGL7020 | DUKHCONI2BSBGZGL7905 | 0 | 0 | GAZEBO
DUKHCONI2BSBGZGL7910 | Electrical Works-Gazebo | 15 | 15 | 0% | 2014-03-03 | 2014-03-19 | 2014-03-03 | 2014-03-19 | 34 | No | DUKHCONI2BSBGZGL7905, DUKHCONI2BSBGZGL7915 | DUKHCONI2BZ2HDGL7025 | 0 | 0 | GAZEBO
DUKHCONI2BSBGZGL7905 | Installation of Wooden Works | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 34 | No | DUKHCONI2BSBGZGL7900 | DUKHCONI2BSBGZGL7910, DUKHCONI2BSBGZGL7915 | 0 | 0 | GAZEBO
DUKHCONI2BSBGZGL7915 | Park Benches Installation | 15 | 15 | 0% | 2014-02-01 | 2014-02-18 | 2014-02-01 | 2014-02-18 | 44 | No | DUKHCONI2BSBGZGL7905 | DUKHCONI2BSBGZGL7910 | 0 | 0 | GAZEBO
DHBL.K30.L55 PACKAGE-3 |  | 522 | 522 | 0% | 2012-12-01 | 2014-08-14 | 2012-12-01 | 2014-08-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.03 SITE PREPARATORY WORKS |  | 69 | 69 | 0% | 2012-12-01 | 2013-02-20 | 2012-12-01 | 2013-02-20 | 0 |  |  |  | 0 | 0
DUKHCONP03GNSP002400 | Approval for new Layout for rerouting | 10 | 10 | 0% | 2013-01-10 | 2013-01-21 | 2013-01-10 | 2013-01-21 | 0 | Yes | DUKHCONP03GNSP002300 | DUKHCONP03GNSP002500 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP004000 | Demolition of Existing building & landscaping | 20 | 20 | 0% | 2012-12-13 | 2013-01-06 | 2012-12-13 | 2013-01-06 | 29 | No | DUKHCONP03GNSP003000 | DUKHCONP03GNSP005000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP005000 | Demolition of existing services works | 20 | 20 | 0% | 2012-12-20 | 2013-01-12 | 2012-12-20 | 2013-01-12 | 29 | No | DUKHCONP03GNSP004000 | DUKHCONP03Z1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP002200 | Information Required for Rerouting | 14 | 14 | 0% | 2012-12-19 | 2013-01-03 | 2012-12-19 | 2013-01-03 | 0 | Yes | DUKHCONP03GNSP002100 | DUKHCONP03GNSP002300 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP002300 | Preparation & Submission for New Layout | 5 | 5 | 0% | 2013-01-05 | 2013-01-09 | 2013-01-05 | 2013-01-09 | 0 | Yes | DUKHCONP03GNSP002200 | DUKHCONP03GNSP002400 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP002500 | Rerouting Works | 25 | 25 | 0% | 2013-01-22 | 2013-02-20 | 2013-01-22 | 2013-02-20 | 0 | Yes | DUKHCONP03GNSP002400 | DUKHCONP03Z1STUG1000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP002000 | Scanning for Existing Services for rerouting | 10 | 10 | 0% | 2012-12-01 | 2012-12-11 | 2012-12-01 | 2012-12-11 | 0 | Yes | DUKHCONP03GNSP001000 | DUKHCONP03GNSP003000, DUKHCONP03GNSP002100 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP003000 | Site stripping | 20 | 20 | 0% | 2012-12-08 | 2012-12-31 | 2012-12-08 | 2012-12-31 | 29 | No | DUKHCONP03GNSP002000 | DUKHCONP03GNSP004000 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP002100 | Submission of Scanning Reports | 5 | 5 | 0% | 2012-12-12 | 2012-12-17 | 2012-12-12 | 2012-12-17 | 0 | Yes | DUKHCONP03GNSP002000 | DUKHCONP03GNSP002200 | 0 | 0 | SITE PREPARATORY WORKS
DUKHCONP03GNSP001000 | Survey works, | 20 | 20 | 0% | 2012-12-01 | 2012-12-24 | 2012-12-01 | 2012-12-24 | 0 | Yes | DUKHMOBP030000004000 | DUKHCONP03GNSP002000 | 0 | 0 | SITE PREPARATORY WORKS
DHBL.K30.L55.05 MOCK UP |  | 124 | 124 | 0% | 2013-08-06 | 2014-01-04 | 2013-08-06 | 2014-01-04 | 47 |  |  |  | 0 | 0
DHBL.K30.L55.05 .15 FINISHING WORKS |  | 124 | 124 | 0% | 2013-08-06 | 2014-01-04 | 2013-08-06 | 2014-01-04 | 47 |  |  |  | 0 | 0
DHBL.K30.L55.05 .15 .10 INTERNAL FINISHES |  | 124 | 124 | 0% | 2013-08-06 | 2014-01-04 | 2013-08-06 | 2014-01-04 | 47 |  |  |  | 0 | 0
DHBL.K30.L55.05 .15 .10 .10 GROUND FLOOR |  | 103 | 103 | 0% | 2013-08-06 | 2013-12-09 | 2013-08-06 | 2013-12-09 | 58 |  |  |  | 0 | 0
DUKHCONP03MKARGF3070 | Aluminum doors | 5 | 5 | 0% | 2013-11-03 | 2013-11-07 | 2013-11-03 | 2013-11-07 | 56 | No | DUKHCONP03MKARGF3065, DUKHPROGEN00PRDV3440, DUKHPROGEN00PRDV3460 | DUKHCONP03Z1ARGF3070, DUKHCONP03MKARGF3075, DUKHCONP03MKARGF3080, DUKHCONP03MKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3055 | Aluminum tile false ceiling | 7 | 7 | 0% | 2013-10-20 | 2013-10-27 | 2013-10-20 | 2013-10-27 | 45 | No | DUKHCONP03MKACGF4600, DUKHCONP03MKARGF3045, DUKHPROGEN00PRDV3310 | DUKHCONP03MKELGF4025, DUKHCONP03MKELGF4020, DUKHCONP03MKELGF4015, DUKHCONP03MKARGF3065, DUKHCONP03Z1ARGF3055, DUKHCONP03MKELGF4030, DUKHCONP03MKPLGF4320, DUKHCONP03MKACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3080 | Aluminum windows | 5 | 5 | 0% | 2013-11-09 | 2013-11-13 | 2013-11-09 | 2013-11-13 | 72 | No | DUKHPROGEN00PRDV3470, DUKHCONP03MKARGF3070 | DUKHCONP03Z1ARGF3080, DUKHCONP03MKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3000 | Block work | 6 | 6 | 0% | 2013-08-06 | 2013-08-15 | 2013-08-06 | 2013-08-15 | 35 | No | DUKHCONP03Z1STGF2015 | DUKHCONP03Z1ARGF3000, DUKHCONP03MKPLGF4310, DUKHCONP03MKELGF4000, DUKHCONP03MKARGF3005, DUKHCONP03MKPLGF4305 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3075 | Carpentry & Joinery Works | 10 | 10 | 0% | 2013-11-12 | 2013-11-23 | 2013-11-12 | 2013-11-23 | 53 | No | DUKHCONP03MKARGF3070, DUKHPROGEN00PRDV3550, DUKHPROGEN00PRDV3560, DUKHPROGEN00PRDV3570 | DUKHCONP03MKARGF3090, DUKHCONP03Z1ARGF3075, DUKHCONP03MKARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3020 | Ceramic Wall Tiling | 6 | 6 | 0% | 2013-09-04 | 2013-09-10 | 2013-09-04 | 2013-09-10 | 51 | No | DUKHCONP03MKARGF3015, DUKHCONP03MKPLGF4310, DUKHPROGEN00PRDV3120 | DUKHCONP03MKARGF3025, DUKHCONP03Z1ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3040 | Cobble Tile flooring | 5 | 5 | 0% | 2013-09-18 | 2013-09-23 | 2013-09-18 | 2013-09-23 | 65 | No | DUKHPROGEN00PRDV3090, DUKHCONP03MKARGF3010, DUKHCONP03MKARGF3025 | DUKHCONP03MKARGF3050, DUKHCONP03MKARGF3035, DUKHCONP03Z1ARGF3040, DUKHCONP03MKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3095 | Final Painting | 7 | 7 | 0% | 2013-12-02 | 2013-12-09 | 2013-12-02 | 2013-12-09 | 58 | No | DUKHCONP03MKARGF3030, DUKHCONP03MKARGF3060, DUKHCONP03MKARGF3085, DUKHCONP03MKARGF3035, DUKHCONP03MKARGF3080, DUKHCONP03MKARGF3090, DUKHPROGEN00PRDV3420, DUKHCONP03MKARGF3040, DUKHCONP03MKARGF3070 | DUKHCONP03Z1ARGF3095, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3045 | Fixing of Suspension systems | 7 | 7 | 0% | 2013-10-01 | 2013-10-08 | 2013-10-01 | 2013-10-08 | 48 | No | DUKHCONP03MKELGF4010, DUKHCONP03MKARGF3030, DUKHCONP03MKARGF3025 | DUKHCONP03MKARGF3055, DUKHCONP03Z1ARGF3045, DUKHCONP03MKARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3010 | Flooring screed | 7 | 7 | 0% | 2013-08-26 | 2013-09-02 | 2013-08-26 | 2013-09-02 | 51 | No | DUKHCONP03MKARGF3005 | DUKHCONP03MKARGF3040, DUKHCONP03MKARGF3015, DUKHCONP03MKARGF3025, DUKHCONP03Z1ARGF3010, DUKHCONP03MKARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3050 | Granite - Stair case flooring & Skirting | 7 | 7 | 0% | 2013-10-20 | 2013-10-27 | 2013-10-20 | 2013-10-27 | 54 | No | DUKHPROGEN00PRDV3480, DUKHCONP03MKARGF3040, DUKHCONP03MKARGF3025 | DUKHCONP03MKARGF3065, DUKHCONP03MKARGF3085, DUKHCONP03Z1ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3060 | Gypsum board false ceiling | 7 | 7 | 0% | 2013-10-09 | 2013-10-16 | 2013-10-09 | 2013-10-16 | 51 | No | DUKHCONP03MKACGF4600, DUKHPROGEN00PRDV3300, DUKHCONP03MKARGF3045 | DUKHCONP03MKARGF3065, DUKHCONP03MKARGF3095, DUKHCONP03MKELGF4020, DUKHCONP03MKPLGF4320, DUKHCONP03MKACGF4605, DUKHCONP03MKELGF4015, DUKHCONP03Z1ARGF3060, DUKHCONP03MKELGF4025, DUKHCONP03MKELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3090 | Installation of Granite Counter Top | 7 | 7 | 0% | 2013-11-24 | 2013-12-01 | 2013-11-24 | 2013-12-01 | 57 | No | DUKHCONP03MKARGF3075 | DUKHCONP03MKARGF3095, DUKHCONP03Z1ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3030 | Paint First coat | 5 | 5 | 0% | 2013-09-25 | 2013-09-30 | 2013-09-25 | 2013-09-30 | 43 | No | DUKHPROGEN00PRDV3320, DUKHCONP03MKARGF3005 | DUKHCONP03MKARGF3095, DUKHCONP03Z1ARGF3030, DUKHCONP03MKARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3005 | Plastering work | 7 | 7 | 0% | 2013-08-22 | 2013-08-29 | 2013-08-22 | 2013-08-29 | 42 | No | DUKHPROGEN00PRDV3040, DUKHCONP03MKELGF4000, DUKHCONP03MKARGF3000 | DUKHCONP03Z1ARGF3005, DUKHCONP03MKARGF3010, DUKHCONP03MKARGF3015, DUKHCONP03MKACGF4600, DUKHCONP03MKELGF4005, DUKHCONP03MKARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3025 | Porcelain Tile flooring | 6 | 6 | 0% | 2013-09-11 | 2013-09-17 | 2013-09-11 | 2013-09-17 | 51 | No | DUKHPROGEN00PRDV3130, DUKHCONP03MKARGF3020, DUKHCONP03MKARGF3010 | DUKHCONP03MKARGF3040, DUKHCONP03Z1ARGF3025, DUKHCONP03MKARGF3045, DUKHCONP03MKARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3085 | S.S.Handrails & Balustrade | 7 | 7 | 0% | 2013-11-24 | 2013-12-01 | 2013-11-24 | 2013-12-01 | 58 | No | DUKHCONP03MKARGF3075, DUKHCONP03MKARGF3050 | DUKHCONP03MKARGF3095, DUKHCONP03Z1ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3035 | Slate Tile Flooring & Skirting | 5 | 5 | 0% | 2013-09-24 | 2013-09-29 | 2013-09-24 | 2013-09-29 | 65 | No | DUKHCONP03MKARGF3040, DUKHPROGEN00PRDV3100, DUKHCONP03MKARGF3010 | DUKHCONP03Z1ARGF3035, DUKHCONP03MKARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3015 | Wet area waterproofing & Protection Screed | 5 | 5 | 0% | 2013-08-29 | 2013-09-03 | 2013-08-29 | 2013-09-03 | 51 | No | DUKHCONP03MKARGF3010, DUKHCONP03MKARGF3005 | DUKHCONP03MKARGF3020, DUKHCONP03Z1ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKARGF3065 | Wooden door | 5 | 5 | 0% | 2013-10-28 | 2013-11-02 | 2013-10-28 | 2013-11-02 | 56 | No | DUKHCONP03MKARGF3060, DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3450, DUKHCONP03MKARGF3050, DUKHCONP03MKARGF3055 | DUKHCONP03Z1ARGF3065, DUKHCONP03MKARGF3070, DUKHCONP03MKPLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.05 .15 .10 .15 FIRST FLOORS |  | 82 | 82 | 0% | 2013-09-22 | 2013-12-29 | 2013-09-22 | 2013-12-29 | 37 |  |  |  | 0 | 0
DUKHCONP03MKARFF3370 | Aluminum doors | 5 | 5 | 0% | 2013-11-25 | 2013-11-30 | 2013-11-25 | 2013-11-30 | 36 | No | DUKHCONP03MKARFF3365, DUKHPROGEN00PRDV3460 | DUKHCONP03MKARFF3395, DUKHCONP03MKARFF3380, DUKHCONP03Z1ARFF3370, DUKHCONP03MKARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3355 | Aluminum tile false ceiling | 7 | 7 | 0% | 2013-11-11 | 2013-11-18 | 2013-11-11 | 2013-11-18 | 34 | No | DUKHCONP03MKACFF4615, DUKHCONP03MKARFF3345, DUKHPROGEN00PRDV3310 | DUKHCONP03MKARFF3395, DUKHCONP03MKELFF4055, DUKHCONP03MKELFF4060, DUKHCONP03MKPLFF4340, DUKHCONP03MKARFF3365, DUKHCONP03MKACFF4620, DUKHCONP03MKELFF4065, DUKHCONP03Z1ARFF3355, DUKHCONP03MKELFF4050 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3380 | Aluminum windows | 5 | 5 | 0% | 2013-12-01 | 2013-12-05 | 2013-12-01 | 2013-12-05 | 49 | No | DUKHPROGEN00PRDV3470, DUKHCONP03MKARFF3370 | DUKHCONP03Z1ARFF3380, DUKHCONP03MKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3300 | Block work | 6 | 6 | 0% | 2013-09-22 | 2013-09-28 | 2013-09-22 | 2013-09-28 | 0 | Yes | DUKHPROGEN00PRDV3010, DUKHCONP03Z1STFF2035, DUKHENGP03DWARAP5610 | DUKHCONP03MKPLFF4325, DUKHCONP03MKELFF4035, DUKHCONP03Z1ARFF3300, DUKHCONP03MKARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3375 | Carpentry & Joinery Works | 10 | 10 | 0% | 2013-12-01 | 2013-12-11 | 2013-12-01 | 2013-12-11 | 36 | No | DUKHPROGEN00PRDV3550, DUKHPROGEN00PRDV3560, DUKHCONP03MKARFF3370 | DUKHCONP03Z1ARFF3375, DUKHCONP03MKARFF3390, DUKHCONP03MKARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3320 | Ceramic Wall Tiling | 6 | 6 | 0% | 2013-10-20 | 2013-10-26 | 2013-10-20 | 2013-10-26 | 24 | No | DUKHCONP03MKPLFF4330, DUKHCONP03MKARFF3315, DUKHPROGEN00PRDV3120, DUKHCONP03MKPLFF4325 | DUKHCONP03MKARFF3325, DUKHCONP03Z1ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3395 | Final Painting | 7 | 7 | 0% | 2013-12-22 | 2013-12-29 | 2013-12-22 | 2013-12-29 | 37 | No | DUKHCONP03MKARFF3370, DUKHCONP03MKARFF3355, DUKHCONP03MKARFF3390, DUKHCONP03MKARFF3360, DUKHCONP03MKARFF3335, DUKHCONP03MKARFF3385, DUKHCONP03MKARFF3330, DUKHCONP03MKARFF3325, DUKHCONP03MKARFF3310, DUKHCONP03MKARFF3380 | DUKHCONP03Z1ACTC8000, DUKHCONP03MKARRF3695, DUKHCONP03MKARRF3620, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1PLTC8005 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3345 | Fixing of Suspension systems | 7 | 7 | 0% | 2013-11-03 | 2013-11-10 | 2013-11-03 | 2013-11-10 | 29 | No | DUKHCONP03MKELFF4045, DUKHCONP03MKARFF3325, DUKHCONP03MKARFF3330 | DUKHCONP03Z1ARFF3345, DUKHCONP03MKARFF3360, DUKHCONP03MKARFF3355 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3310 | Flooring screed | 7 | 7 | 0% | 2013-10-08 | 2013-10-15 | 2013-10-08 | 2013-10-15 | 22 | No | DUKHCONP03MKARFF3305 | DUKHCONP03MKARFF3315, DUKHCONP03MKARFF3325, DUKHCONP03MKARFF3350, DUKHCONP03Z1ARFF3310, DUKHCONP03MKARFF3335, DUKHCONP03MKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3350 | Granite - Stair case flooring & Skirting | 7 | 7 | 0% | 2013-11-03 | 2013-11-10 | 2013-11-03 | 2013-11-10 | 37 | No | DUKHPROGEN00PRDV3480, DUKHCONP03MKARFF3325, DUKHCONP03MKARFF3310 | DUKHCONP03MKARFF3385, DUKHCONP03Z1ARFF3350, DUKHCONP03MKARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3360 | Gypsum board false ceiling | 7 | 7 | 0% | 2013-11-11 | 2013-11-18 | 2013-11-11 | 2013-11-18 | 29 | No | DUKHCONP03MKACFF4615, DUKHCONP03MKARFF3345, DUKHPROGEN00PRDV3300 | DUKHCONP03MKACFF4620, DUKHCONP03MKELFF4055, DUKHCONP03MKPLFF4340, DUKHCONP03MKELFF4060, DUKHCONP03MKELFF4065, DUKHCONP03Z1ARFF3360, DUKHCONP03MKARFF3365, DUKHCONP03MKARFF3395, DUKHCONP03MKELFF4050 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3390 | Installation of Granite Counter Top | 7 | 7 | 0% | 2013-12-12 | 2013-12-21 | 2013-12-12 | 2013-12-21 | 37 | No | DUKHCONP03MKARFF3375 | DUKHCONP03MKARFF3395, DUKHCONP03Z1ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3330 | Paint First coat | 5 | 5 | 0% | 2013-10-23 | 2013-10-28 | 2013-10-23 | 2013-10-28 | 28 | No | DUKHCONP03MKARFF3305, DUKHPROGEN00PRDV3320 | DUKHCONP03MKARFF3345, DUKHCONP03Z1ARFF3330, DUKHCONP03MKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3305 | Plastering work | 7 | 7 | 0% | 2013-10-05 | 2013-10-12 | 2013-10-05 | 2013-10-12 | 8 | No | DUKHCONP03MKARFF3300, DUKHPROGEN00PRDV3040, DUKHCONP03MKELFF4035 | DUKHCONP03Z1ARFF3305, DUKHCONP03MKELFF4040, DUKHCONP03MKARFF3310, DUKHCONP03MKARFF3330, DUKHCONP03MKACFF4615, DUKHCONP03MKARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3325 | Porcelain Tile flooring | 6 | 6 | 0% | 2013-10-27 | 2013-11-02 | 2013-10-27 | 2013-11-02 | 24 | No | DUKHCONP03MKARFF3320, DUKHPROGEN00PRDV3130, DUKHCONP03MKARFF3310 | DUKHCONP03MKARFF3345, DUKHCONP03MKARFF3350, DUKHCONP03MKARFF3395, DUKHCONP03Z1ARFF3325, DUKHCONP03MKARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3385 | S.S.Handrails & Balustrade | 7 | 7 | 0% | 2013-12-12 | 2013-12-21 | 2013-12-12 | 2013-12-21 | 37 | No | DUKHCONP03MKARFF3350, DUKHPROGEN00PRDV3570, DUKHCONP03MKARFF3375, DUKHPROGEN00PRDV3580 | DUKHCONP03Z1ARFF3385, DUKHCONP03MKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3335 | Slate Tile Flooring & Skirting | 5 | 5 | 0% | 2013-11-03 | 2013-11-07 | 2013-11-03 | 2013-11-07 | 44 | No | DUKHCONP03MKARFF3310, DUKHCONP03MKARFF3325, DUKHPROGEN00PRDV3100 | DUKHCONP03Z1ARFF3335, DUKHCONP03MKARRF3610, DUKHCONP03MKARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3315 | Wet area waterproofing & Protection Screed | 5 | 5 | 0% | 2013-10-12 | 2013-10-16 | 2013-10-12 | 2013-10-16 | 22 | No | DUKHCONP03MKARFF3310, DUKHCONP03MKARFF3305 | DUKHCONP03MKARFF3320, DUKHCONP03Z1ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKARFF3365 | Wooden door | 5 | 5 | 0% | 2013-11-19 | 2013-11-24 | 2013-11-19 | 2013-11-24 | 36 | No | DUKHPROGEN00PRDV3490, DUKHPROGEN00PRDV3450, DUKHCONP03MKARFF3350, DUKHCONP03MKARFF3360, DUKHCONP03MKARFF3355 | DUKHCONP03MKARFF3370, DUKHCONP03Z1ARFF3365, DUKHCONP03MKPLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.05 .15 .10 .20 ROOF |  | 71 | 71 | 0% | 2013-10-10 | 2014-01-04 | 2013-10-10 | 2014-01-04 | 47 |  |  |  | 0 | 0
DUKHCONP03MKARRF3600 | Block work | 5 | 5 | 0% | 2013-10-10 | 2013-10-15 | 2013-10-10 | 2013-10-15 | 3 | No | DUKHCONP03Z1STRF2055 | DUKHCONP03Z1ARRF3600, DUKHCONP03MKARRF3605, DUKHCONP03MKARRF3605 | 0 | 0 | ROOF
DUKHCONP03MKARRF3620 | Epoxy Painting | 5 | 5 | 0% | 2013-12-30 | 2014-01-04 | 2013-12-30 | 2014-01-04 | 47 | No | DUKHCONP03MKARRF3695, DUKHCONP03MKARFF3395, DUKHPROGEN00PRDV3420 | DUKHCONP03Z1ARRF3620, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1PLTC8005 | 0 | 0 | ROOF
DUKHCONP03MKARRF3610 | Flooring screed | 6 | 6 | 0% | 2013-11-04 | 2013-11-10 | 2013-11-04 | 2013-11-10 | 73 | No | DUKHCONP03MKARFF3335, DUKHCONP03MKARRF3605 | DUKHCONP03MKARRF3695 | 0 | 0 | ROOF
DUKHCONP03MKARRF3695 | Painting | 5 | 5 | 0% | 2013-12-24 | 2013-12-29 | 2013-12-24 | 2013-12-29 | 37 | No | DUKHCONP03MKARRF3605, DUKHCONP03MKARFF3395, DUKHCONP03MKARRF3610 | DUKHCONP03MKARRF3620, DUKHCONP03Z1ARRF3695 | 0 | 0 | ROOF
DUKHCONP03MKARRF3605 | Plastering work | 5 | 5 | 0% | 2013-10-14 | 2013-10-21 | 2013-10-14 | 2013-10-21 | 3 | No | DUKHCONP03MKARRF3600, DUKHCONP03MKARRF3600 | DUKHCONP03MKARRF3630, DUKHCONP03MKARRF3695, DUKHCONP03MKAREL3665, DUKHCONP03Z1ARRF3605, DUKHCONP03MKPLRF4345, DUKHCONP03MKARRF3610 | 0 | 0 | ROOF
DHBL.K30.L55.05 .15 .15 EXTERNAL FINISHES |  | 39 | 39 | 0% | 2013-10-22 | 2013-12-05 | 2013-10-22 | 2013-12-05 | 71 |  |  |  | 0 | 0
DHBL.K30.L55.05 .15 .15 .10 ROOF |  | 32 | 32 | 0% | 2013-10-22 | 2013-11-27 | 2013-10-22 | 2013-11-27 | 78 |  |  |  | 0 | 0
DUKHCONP03MKARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 6 | 6 | 0% | 2013-11-09 | 2013-11-14 | 2013-11-09 | 2013-11-14 | 61 | No | DUKHPROGEN00PRDV3410, DUKHCONP03MKARRF3645 | DUKHCONP03Z1ARRF3650, DUKHCONP03MKARRF3655 | 0 | 0 | ROOF
DUKHCONP03MKARRF3660 | Installation of Access Ladder | 5 | 5 | 0% | 2013-11-23 | 2013-11-27 | 2013-11-23 | 2013-11-27 | 78 | No | DUKHCONP03MKARRF3655, DUKHPROGEN00PRDV3400 | DUKHCONP03Z1ARRF3660 | 0 | 0 | ROOF
DUKHCONP03MKARRF3640 | Installation of Insulation & Protection | 4 | 4 | 0% | 2013-10-30 | 2013-11-03 | 2013-10-30 | 2013-11-03 | 3 | No | DUKHCONP03MKARRF3635 | DUKHCONP03MKARRF3645, DUKHCONP03Z1ARRF3640 | 0 | 0 | ROOF
DUKHCONP03MKARRF3655 | Installation of Pumps Protection cabinets | 6 | 6 | 0% | 2013-11-16 | 2013-11-21 | 2013-11-16 | 2013-11-21 | 66 | No | DUKHCONP03MKARRF3645, DUKHCONP03MKARRF3650 | DUKHCONP03MKARRF3660, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ARRF3655, DUKHCONP03Z1ACTC8000, DUKHCONP03MKPLRF4355, DUKHCONP03Z1PLTC8005 | 0 | 0 | ROOF
DUKHCONP03MKARRF3635 | Laying of Waterproofing Membrane | 5 | 5 | 0% | 2013-10-24 | 2013-10-29 | 2013-10-24 | 2013-10-29 | 3 | No | DUKHCONP03MKARRF3630 | DUKHCONP03MKARRF3640, DUKHCONP03Z1ARRF3635 | 0 | 0 | ROOF
DUKHCONP03MKARRF3630 | Leveling Screed for Waterproofing | 2 | 2 | 0% | 2013-10-22 | 2013-10-23 | 2013-10-22 | 2013-10-23 | 3 | No | DUKHCONP03MKARRF3605, DUKHCONP03Z1STRF2060, DUKHCONP03Z1STRF2065, DUKHCONP03Z1STRF2055 | DUKHCONP03MKARRF3635, DUKHCONP03Z1ARRF3630 | 0 | 0 | ROOF
DUKHCONP03MKARRF3645 | Lime Stone Chips & Paving slab Installation | 4 | 4 | 0% | 2013-11-04 | 2013-11-07 | 2013-11-04 | 2013-11-07 | 3 | No | DUKHCONP03MKARRF3640 | DUKHCONP03MKELRF4070, DUKHCONP03MKACRF4630, DUKHCONP03MKAREL3665, DUKHCONP03MKPLRF4345, DUKHCONP03MKARRF3655, DUKHCONP03MKPLRF4355, DUKHCONP03MKACRF4635, DUKHCONP03MKARRF3650, DUKHCONP03Z1ARRF3645 | 0 | 0 | ROOF
DHBL.K30.L55.05 .15 .15 .15 ELEVATION |  | 24 | 24 | 0% | 2013-11-09 | 2013-12-05 | 2013-11-09 | 2013-12-05 | 66 |  |  |  | 0 | 0
DUKHCONP03MKAREL3680 | External Painting | 7 | 7 | 0% | 2013-11-28 | 2013-12-05 | 2013-11-28 | 2013-12-05 | 66 | No | DUKHCONP03MKAREL3675 | DUKHCONP03Z1ACTC8000, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1AREL3680 | 0 | 0 | ELEVATION
DUKHCONP03MKAREL3665 | External Plastering | 10 | 10 | 0% | 2013-11-09 | 2013-11-19 | 2013-11-09 | 2013-11-19 | 19 | No | DUKHCONP03MKARRF3645, DUKHCONP03MKARRF3605, DUKHCONP03Z1STRF2060 | DUKHCONP03Z1AREL3665, DUKHCONP03MKMSEX5020, DUKHCONP03MKAREL3675 | 0 | 0 | ELEVATION
DUKHCONP03MKAREL3675 | GRC Panel Works | 7 | 7 | 0% | 2013-11-20 | 2013-11-27 | 2013-11-20 | 2013-11-27 | 19 | No | DUKHPROGEN00PRDV3390, DUKHCONP03MKAREL3665 | DUKHCONP03Z1AREL3675, DUKHCONP03MKAREL3680, DUKHCONP03MKMSEX5020 | 0 | 0 | ELEVATION
DHBL.K30.L55.05 .20 MEP WORKS |  | 103 | 103 | 0% | 2013-08-17 | 2013-12-16 | 2013-08-17 | 2013-12-16 | 62 |  |  |  | 0 | 0
DHBL.K30.L55.05 .20 .10 ELECTRICAL WORKS |  | 101 | 101 | 0% | 2013-08-17 | 2013-12-14 | 2013-08-17 | 2013-12-14 | 56 |  |  |  | 0 | 0
DHBL.K30.L55.05 .20 .10 .10 GROUND FLOOR |  | 71 | 71 | 0% | 2013-08-17 | 2013-11-09 | 2013-08-17 | 2013-11-09 | 57 |  |  |  | 0 | 0
DUKHCONP03MKELGF4005 | Cable tray & trunking installation | 5 | 5 | 0% | 2013-08-31 | 2013-09-04 | 2013-08-31 | 2013-09-04 | 60 | No | DUKHCONP03MKELGF4000, DUKHCONP03MKARGF3005 | DUKHCONP03MKELGF4010, DUKHCONP03Z1ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKELGF4000 | Fixing of wall conduits & switch socket boxes | 5 | 5 | 0% | 2013-08-17 | 2013-08-21 | 2013-08-17 | 2013-08-21 | 42 | No | DUKHCONP03MKARGF3000 | DUKHCONP03Z1ELGF4000, DUKHCONP03MKELGF4005, DUKHCONP03MKARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKELGF4015 | Install. of CAMS & Fire Fighting Accessories | 7 | 7 | 0% | 2013-11-02 | 2013-11-09 | 2013-11-02 | 2013-11-09 | 52 | No | DUKHPROGEN00PRDV3260, DUKHPROGEN00PRDV3380, DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3360, DUKHCONP03MKARGF3055, DUKHPROGEN00PRDV3370, DUKHCONP03MKARGF3060 | DUKHCONP03Z1ACTC8000, DUKHCONP03MKELFF4055, DUKHCONP03Z1ELGF4015, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKELGF4020 | Installation of DBS,MCCB Accessories. | 5 | 5 | 0% | 2013-10-28 | 2013-11-02 | 2013-10-28 | 2013-11-02 | 52 | No | DUKHPROGEN00PRDV3170, DUKHCONP03MKELGF4010, DUKHCONP03MKARGF3055, DUKHCONP03MKARGF3060 | DUKHCONP03Z1ELGF4020, DUKHCONP03MKELGF4025, DUKHCONP03MKELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKELGF4025 | Installation of Lighting fixtures & Accessories | 5 | 5 | 0% | 2013-11-03 | 2013-11-07 | 2013-11-03 | 2013-11-07 | 58 | No | DUKHCONP03MKARGF3055, DUKHPROGEN00PRDV3190, DUKHCONP03MKELGF4020, DUKHCONP03MKARGF3060 | DUKHCONP03Z1ACTC8000, DUKHCONP03Z1ELGF4025, DUKHCONP03MKELFF4065, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKELGF4030 | Installation of Telephone System | 5 | 5 | 0% | 2013-11-03 | 2013-11-07 | 2013-11-03 | 2013-11-07 | 57 | No | DUKHPROGEN00PRDV3270, DUKHPROGEN00PRDV3280, DUKHCONP03MKELGF4020, DUKHCONP03MKARGF3055, DUKHCONP03MKARGF3060 | DUKHCONP03MKELFF4050, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ELGF4030, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKELGF4010 | Installation of wiring & Main Cabling | 5 | 5 | 0% | 2013-09-05 | 2013-09-10 | 2013-09-05 | 2013-09-10 | 62 | No | DUKHPROGEN00PRDV3180, DUKHCONP03MKELGF4005 | DUKHCONP03MKELGF4020, DUKHCONP03Z1ELGF4010, DUKHCONP03MKARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.05 .20 .10 .15 FIRST FLOORS |  | 52 | 52 | 0% | 2013-09-29 | 2013-11-30 | 2013-09-29 | 2013-11-30 | 48 |  |  |  | 0 | 0
DUKHCONP03MKELFF4040 | Cable tray & trunking installation | 5 | 5 | 0% | 2013-10-13 | 2013-10-20 | 2013-10-13 | 2013-10-20 | 30 | No | DUKHCONP03MKARFF3305, DUKHCONP03MKELFF4035 | DUKHCONP03Z1ELFF4040, DUKHCONP03MKELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKELFF4035 | Fixing of wall conduits & switch socket boxes | 5 | 5 | 0% | 2013-09-29 | 2013-10-03 | 2013-09-29 | 2013-10-03 | 8 | No | DUKHCONP03MKARFF3300 | DUKHCONP03MKELFF4040, DUKHCONP03Z1ELFF4035, DUKHCONP03MKARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKELFF4055 | Install. of CAMS & Fire Fighting Accessories | 7 | 7 | 0% | 2013-11-19 | 2013-11-26 | 2013-11-19 | 2013-11-26 | 44 | No | DUKHCONP03MKARFF3360, DUKHCONP03MKELGF4015, DUKHCONP03MKARFF3355, DUKHPROGEN00PRDV3210, DUKHPROGEN00PRDV3260, DUKHPROGEN00PRDV3360 | DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKELFF4060 | Installation of DBS,MCCB Accessories. | 5 | 5 | 0% | 2013-11-19 | 2013-11-24 | 2013-11-19 | 2013-11-24 | 38 | No | DUKHCONP03MKELFF4045, DUKHCONP03MKARFF3360, DUKHCONP03MKARFF3355, DUKHPROGEN00PRDV3170 | DUKHCONP03MKELFF4050, DUKHCONP03Z1ELFF4060, DUKHCONP03MKELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKELFF4065 | Installation of Lighting fixtures & Accessories | 5 | 5 | 0% | 2013-11-25 | 2013-11-30 | 2013-11-25 | 2013-11-30 | 44 | No | DUKHPROGEN00PRDV3190, DUKHCONP03MKARFF3360, DUKHCONP03MKELGF4025, DUKHCONP03MKARFF3355, DUKHCONP03MKELFF4060 | DUKHCONP03Z1ACTC8000, DUKHCONP03MKELRF4070, DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKELFF4050 | Installation of Telephone System | 5 | 5 | 0% | 2013-11-25 | 2013-11-30 | 2013-11-25 | 2013-11-30 | 48 | No | DUKHCONP03MKELGF4030, DUKHCONP03MKELFF4060, DUKHPROGEN00PRDV3280, DUKHCONP03MKARFF3360, DUKHPROGEN00PRDV3270, DUKHCONP03MKARFF3355 | DUKHCONP03Z1ACTC8000, DUKHCONP03Z1ELFF4050, DUKHCONP03MKELRF4070, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKELFF4045 | Installation of wiring & Main Cabling | 5 | 5 | 0% | 2013-10-21 | 2013-10-26 | 2013-10-21 | 2013-10-26 | 32 | No | DUKHPROGEN00PRDV3180, DUKHCONP03MKELFF4040 | DUKHCONP03MKELFF4060, DUKHCONP03Z1ELFF4045, DUKHCONP03MKARFF3345, DUKHCONP03MKELRF4070 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.05 .20 .10 .20 ROOF |  | 12 | 12 | 0% | 2013-12-01 | 2013-12-14 | 2013-12-01 | 2013-12-14 | 56 |  |  |  | 0 | 0
DUKHCONP03MKELRF4070 | Installation of Isolator | 5 | 5 | 0% | 2013-12-01 | 2013-12-05 | 2013-12-01 | 2013-12-05 | 56 | No | DUKHCONP03MKELFF4065, DUKHCONP03MKARRF3645, DUKHPROGEN00PRDV3200, DUKHCONP03MKELFF4045, DUKHCONP03MKELFF4050 | DUKHCONP03MKELRF4075, DUKHCONP03Z1ELRF4070 | 0 | 0 | ROOF
DUKHCONP03MKELRF4075 | Installation of TV Dish Antenna | 7 | 7 | 0% | 2013-12-07 | 2013-12-14 | 2013-12-07 | 2013-12-14 | 56 | No | DUKHCONP03MKELRF4070, DUKHPROGEN00PRDV3290 | DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELRF4075, DUKHCONP03Z1ACTC8000 | 0 | 0 | ROOF
DHBL.K30.L55.05 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 103 | 103 | 0% | 2013-08-17 | 2013-12-16 | 2013-08-17 | 2013-12-16 | 62 |  |  |  | 0 | 0
DHBL.K30.L55.05 .20 .15 .10 GROUND FLOOR |  | 88 | 88 | 0% | 2013-08-17 | 2013-11-28 | 2013-08-17 | 2013-11-28 | 77 |  |  |  | 0 | 0
DUKHCONP03MKPLGF4310 | Installation of Drainage pipes &testing | 5 | 5 | 0% | 2013-08-17 | 2013-08-21 | 2013-08-17 | 2013-08-21 | 62 | No | DUKHCONP03MKPLGF4305, DUKHCONP03MKARGF3000 | DUKHCONP03MKARGF3020, DUKHCONP03MKPLGF4315, DUKHCONP03Z1PLGF4310, DUKHCONP03MKMSEX5000 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKPLGF4305 | Installation of Plumbing pipes & testing | 5 | 5 | 0% | 2013-08-17 | 2013-08-21 | 2013-08-17 | 2013-08-21 | 44 | No | DUKHCONP03MKARGF3000 | DUKHCONP03MKPLGF4310, DUKHCONP03Z1PLGF4305 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKPLGF4320 | Installation of Water Heater | 5 | 5 | 0% | 2013-11-24 | 2013-11-28 | 2013-11-24 | 2013-11-28 | 77 | No | DUKHCONP03MKPLGF4315, DUKHCONP03MKARGF3060, DUKHCONP03MKARGF3055 | DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1PLGF4320, DUKHCONP03Z1ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKPLGF4315 | Sanitary Fittings & Accessories | 7 | 7 | 0% | 2013-11-16 | 2013-11-23 | 2013-11-16 | 2013-11-23 | 50 | No | DUKHPROGEN00PRDV3150, DUKHPROGEN00PRDV3230, DUKHCONP03MKPLGF4310, DUKHPROGEN00PRDV3770, DUKHCONP03MKARGF3065 | DUKHCONP03Z1PLGF4315, DUKHCONP03MKPLGF4320, DUKHCONP03MKPLFF4335 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.05 .20 .15 .15 FIRST FLOORS |  | 59 | 59 | 0% | 2013-09-29 | 2013-12-08 | 2013-09-29 | 2013-12-08 | 52 |  |  |  | 0 | 0
DUKHCONP03MKPLFF4330 | Installation of Drainage pipes & testing | 5 | 5 | 0% | 2013-09-29 | 2013-10-03 | 2013-09-29 | 2013-10-03 | 34 | No | DUKHCONP03MKPLFF4325 | DUKHCONP03MKPLFF4335, DUKHCONP03MKARFF3320, DUKHCONP03Z1PLFF4330, DUKHCONP03MKMSEX5000, DUKHCONP03MKPLRF4350 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKPLFF4325 | Installation of Plumbing pipes & testing | 5 | 5 | 0% | 2013-09-29 | 2013-10-03 | 2013-09-29 | 2013-10-03 | 9 | No | DUKHCONP03MKARFF3300, DUKHPROGEN00PRDV3080 | DUKHCONP03Z1PLFF4325, DUKHCONP03MKPLFF4330, DUKHCONP03MKARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKPLFF4340 | Installation of Water Heater | 5 | 5 | 0% | 2013-12-03 | 2013-12-08 | 2013-12-03 | 2013-12-08 | 52 | No | DUKHCONP03MKARFF3360, DUKHCONP03MKPLFF4335, DUKHCONP03MKARFF3355 | DUKHCONP03Z1PLFF4340, DUKHCONP03MKPLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKPLFF4335 | Sanitary Fittings & Accessories | 7 | 7 | 0% | 2013-11-25 | 2013-12-02 | 2013-11-25 | 2013-12-02 | 49 | No | DUKHCONP03MKPLFF4330, DUKHCONP03MKPLGF4315, DUKHCONP03MKARFF3365 | DUKHCONP03Z1PLFF4335, DUKHCONP03MKPLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.05 .20 .15 .20 ROOF |  | 33 | 33 | 0% | 2013-11-09 | 2013-12-16 | 2013-11-09 | 2013-12-16 | 52 |  |  |  | 0 | 0
DUKHCONP03MKPLRF4345 | Installation of Plumbing pipes & fittings | 5 | 5 | 0% | 2013-11-09 | 2013-11-13 | 2013-11-09 | 2013-11-13 | 3 | No | DUKHCONP03MKARRF3645, DUKHCONP03MKARRF3605 | DUKHCONP03Z1PLRF4345, DUKHCONP03MKPLRF4350, DUKHCONP03MKPLRF4355, DUKHCONP03MKMSEX5000 | 0 | 0 | ROOF
DUKHCONP03MKPLRF4350 | Installation of Rain water Pipes | 5 | 5 | 0% | 2013-11-14 | 2013-11-19 | 2013-11-14 | 2013-11-19 | 68 | No | DUKHCONP03MKPLRF4345, DUKHCONP03MKPLFF4330 | DUKHCONP03Z1ACTC8000, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLRF4350, DUKHCONP03MKPLRF4355 | 0 | 0 | ROOF
DUKHCONP03MKPLRF4355 | Roof Water Tank Installation & Connections | 7 | 7 | 0% | 2013-12-09 | 2013-12-16 | 2013-12-09 | 2013-12-16 | 52 | No | DUKHCONP03MKPLRF4345, DUKHCONP03MKPLRF4350, DUKHCONP03MKARRF3645, DUKHCONP03MKARRF3655, DUKHCONP03MKPLFF4340 | DUKHCONP03Z1PLRF4355, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L55.05 .20 .20 AC WORKS |  | 82 | 82 | 0% | 2013-08-31 | 2013-12-05 | 2013-08-31 | 2013-12-05 | 61 |  |  |  | 0 | 0
DHBL.K30.L55.05 .20 .20 .10 GROUND FLOOR |  | 58 | 58 | 0% | 2013-08-31 | 2013-11-07 | 2013-08-31 | 2013-11-07 | 70 |  |  |  | 0 | 0
DUKHCONP03MKACGF4610 | Fixing of Split AC | 5 | 5 | 0% | 2013-11-03 | 2013-11-07 | 2013-11-03 | 2013-11-07 | 70 | No | DUKHPROGEN00PRDV3240, DUKHCONP03MKACGF4605 | DUKHCONP03MKACRF4635, DUKHCONP03MKACFF4625, DUKHCONP03Z1ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKACGF4605 | Fixing of Ventilation Equipments | 5 | 5 | 0% | 2013-10-28 | 2013-11-02 | 2013-10-28 | 2013-11-02 | 57 | No | DUKHPROGEN00PRDV3340, DUKHCONP03MKACGF4600, DUKHCONP03MKARGF3060, DUKHPROGEN00PRDV3530, DUKHCONP03MKARGF3055 | DUKHCONP03MKACFF4620, DUKHCONP03Z1ACGF4605, DUKHCONP03MKACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP03MKACGF4600 | Installation AC Pipes | 5 | 5 | 0% | 2013-08-31 | 2013-09-04 | 2013-08-31 | 2013-09-04 | 79 | No | DUKHCONP03MKARGF3005, DUKHPROGEN00PRDV3160 | DUKHCONP03MKACRF4630, DUKHCONP03MKACFF4615, DUKHCONP03MKARGF3055, DUKHCONP03MKACGF4605, DUKHCONP03MKARGF3060, DUKHCONP03Z1ACGF4600 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.05 .20 .20 .15 FIRST FLOORS |  | 40 | 40 | 0% | 2013-10-13 | 2013-11-30 | 2013-10-13 | 2013-11-30 | 56 |  |  |  | 0 | 0
DUKHCONP03MKACFF4625 | Fixing of Split AC | 5 | 5 | 0% | 2013-11-25 | 2013-11-30 | 2013-11-25 | 2013-11-30 | 56 | No | DUKHCONP03MKACGF4610, DUKHCONP03MKACFF4620, DUKHPROGEN00PRDV3240 | DUKHCONP03MKACRF4635, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1ACFF4625, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKACFF4620 | Fixing of Ventilation Equipments | 5 | 5 | 0% | 2013-11-19 | 2013-11-24 | 2013-11-19 | 2013-11-24 | 43 | No | DUKHCONP03MKARFF3360, DUKHCONP03MKACGF4605, DUKHCONP03MKACFF4615, DUKHCONP03MKARFF3355, DUKHPROGEN00PRDV3340 | DUKHCONP03MKACFF4625, DUKHCONP03Z1ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP03MKACFF4615 | Installation AC Pipes | 5 | 5 | 0% | 2013-10-13 | 2013-10-20 | 2013-10-13 | 2013-10-20 | 47 | No | DUKHPROGEN00PRDV3160, DUKHCONP03MKACGF4600, DUKHCONP03MKARFF3305 | DUKHCONP03Z1ACFF4615, DUKHCONP03MKARFF3355, DUKHCONP03MKARFF3360, DUKHCONP03MKACFF4620, DUKHCONP03MKACRF4630 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.05 .20 .20 .20 ROOF |  | 24 | 24 | 0% | 2013-11-09 | 2013-12-05 | 2013-11-09 | 2013-12-05 | 61 |  |  |  | 0 | 0
DUKHCONP03MKACRF4635 | Installation of Condensing Unit | 5 | 5 | 0% | 2013-12-01 | 2013-12-05 | 2013-12-01 | 2013-12-05 | 61 | No | DUKHCONP03MKACGF4610, DUKHCONP03MKACRF4630, DUKHCONP03MKACFF4625, DUKHCONP03MKARRF3645 | DUKHCONP03Z1ACTC8000, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ACRF4635 | 0 | 0 | ROOF
DUKHCONP03MKACRF4630 | Installation of Refrigerant Pipes | 7 | 7 | 0% | 2013-11-09 | 2013-11-16 | 2013-11-09 | 2013-11-16 | 73 | No | DUKHCONP03MKARRF3645, DUKHCONP03MKACGF4600, DUKHCONP03MKACFF4615 | DUKHCONP03Z1ACRF4630, DUKHCONP03MKACRF4635 | 0 | 0 | ROOF
DHBL.K30.L55.05 .25 EXTERNAL WORKS |  | 24 | 24 | 0% | 2013-11-14 | 2013-12-11 | 2013-11-14 | 2013-12-11 | 51 |  |  |  | 0 | 0
DHBL.K30.L55.05 .25 .10 MISCELLANEOUS |  | 24 | 24 | 0% | 2013-11-14 | 2013-12-11 | 2013-11-14 | 2013-12-11 | 51 |  |  |  | 0 | 0
DUKHCONP03MKMSEX5005 | Construction of Soak pit, Chambers | 7 | 7 | 0% | 2013-11-23 | 2013-11-30 | 2013-11-23 | 2013-11-30 | 23 | No | DUKHCONP03MKMSEX5000 | DUKHCONP03MKMSEX5015, DUKHCONP03Z1MSEX5005, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP03MKMSEX5020 | Construction Entrance Ramp | 7 | 7 | 0% | 2013-11-28 | 2013-12-05 | 2013-11-28 | 2013-12-05 | 19 | No | DUKHCONP03MKAREL3665, DUKHCONP03MKAREL3675 | DUKHCONP03Z1MSEX5020, DUKHCONP03MKMSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP03MKMSEX5015 | Construction of grease Trap | 7 | 7 | 0% | 2013-12-01 | 2013-12-08 | 2013-12-01 | 2013-12-08 | 54 | No | DUKHCONP03MKMSEX5005 | DUKHCONP03Z1MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP03MKMSEX5000 | Construction of Manholes | 7 | 7 | 0% | 2013-11-14 | 2013-11-21 | 2013-11-14 | 2013-11-21 | 3 | No | DUKHCONP03MKPLFF4330, DUKHCONP03MKPLGF4310, DUKHCONP03MKPLRF4345 | DUKHCONP03Z1MSEX5000, DUKHCONP03MKMSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP03MKMSEX5025 | SS.Handrails and Balustrades | 5 | 5 | 0% | 2013-12-07 | 2013-12-11 | 2013-12-07 | 2013-12-11 | 31 | No | DUKHCONP03MKMSEX5020 | DUKHCONP03Z1MSEX5025 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L55.10 ZONE - 1 (3 Apartments) |  | 372 | 372 | 0% | 2013-01-29 | 2014-04-16 | 2013-01-29 | 2014-04-16 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.10 .10 STRUCTURAL WORKS |  | 225 | 225 | 0% | 2013-01-29 | 2013-10-24 | 2013-01-29 | 2013-10-24 | 18 |  |  |  | 0 | 0
DHBL.K30.L55.10 .10 .10 SUB STRUCTURE |  | 117 | 117 | 0% | 2013-01-29 | 2013-06-15 | 2013-01-29 | 2013-06-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.10 .10 .10 .10 UPTO GRADE SLAB |  | 117 | 117 | 0% | 2013-01-29 | 2013-06-15 | 2013-01-29 | 2013-06-15 | 0 |  |  |  | 0 | 0
DUKHCONP03Z1STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-04-04 | 2013-05-02 | 2013-04-04 | 2013-05-02 | 0 | Yes | DUKHCONP03Z1STUG1030, DUKHCONP03Z1STUG1030 | DUKHCONP03Z2STUG1035, DUKHCONP03Z1STUG1040, DUKHCONP03Z1STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-03-06 | 2013-03-28 | 2013-03-06 | 2013-03-28 | 0 | Yes | DUKHMOBP030000004060, DUKHMOBP030000004080, DUKHMOBP030000004070, DUKHMOBP030000004090, DUKHCONP03Z1STUG1015, DUKHCONP03Z1STUG1015 | DUKHCONP03Z1STUG1025, DUKHCONP03Z1STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-04-21 | 2013-05-19 | 2013-04-21 | 2013-05-19 | 0 | Yes | DUKHENGP03DWSTAP5570, DUKHCONP03Z1STUG1035, DUKHCONP03Z1STUG1035 | DUKHCONP03Z1PLUG4300, DUKHCONP03Z1STUG1045, DUKHCONP03Z1PLUG4300, DUKHCONP03Z1STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-03-16 | 2013-04-13 | 2013-03-16 | 2013-04-13 | 0 | Yes | DUKHCONP03Z1STUG1020, DUKHCONP03Z1STUG1020 | DUKHCONP03Z1STUG1030, DUKHCONP03Z1STUG1030, DUKHCONP03Z2STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-05-18 | 2013-06-15 | 2013-05-18 | 2013-06-15 | 0 | Yes | DUKHENGP03DWSTAP5570, DUKHCONP03Z1PLUG4300, DUKHCONP03Z1STUG1040, DUKHCONP03Z1PLUG4300, DUKHCONP03Z1STUG1040 | DUKHCONP03Z1STGF2000, DUKHCONP03Z2STUG1045, DUKHCONP03Z1STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-02-09 | 2013-03-07 | 2013-02-09 | 2013-03-07 | 0 | Yes | DUKHCONP03Z1STUG1000, DUKHCONP03Z1STUG1000 | DUKHCONP03Z1STUG1010, DUKHCONP03Z1STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-02-13 | 2013-03-11 | 2013-02-13 | 2013-03-11 | 0 | Yes | DUKHCONP03Z1STUG1005, DUKHCONP03Z1STUG1005 | DUKHCONP03Z1STUG1015, DUKHCONP03Z1STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-01-29 | 2013-02-27 | 2013-01-29 | 2013-02-27 | 0 | Yes | DUKHMOBP030000004050, DUKHCONP03GNSP005000, DUKHCONP03GNSP002500 | DUKHCONP03Z2STUG1000, DUKHCONP03Z1STUG1005, DUKHCONP03Z1STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-02-19 | 2013-03-19 | 2013-02-19 | 2013-03-19 | 0 | Yes | DUKHENGP03DWSTAP5560, DUKHPROGEN00PRDV3020, DUKHCONP03Z1STUG1010, DUKHCONP03Z1STUG1010 | DUKHCONP03Z1STUG1020, DUKHCONP03Z1STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z1STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-03-25 | 2013-04-22 | 2013-03-25 | 2013-04-22 | 0 | Yes | DUKHCONP03Z1STUG1025, DUKHCONP03Z1STUG1025 | DUKHCONP03Z1STUG1035, DUKHCONP03Z1STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L55.10 .10 .15 SUPERSTRUCTURE |  | 119 | 119 | 0% | 2013-06-03 | 2013-10-24 | 2013-06-03 | 2013-10-24 | 18 |  |  |  | 0 | 0
DHBL.K30.L55.10 .10 .15 .10 GROUND FLOOR |  | 49 | 49 | 0% | 2013-06-03 | 2013-07-29 | 2013-06-03 | 2013-07-29 | 0 |  |  |  | 0 | 0
DUKHCONP03Z1STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-07-13 | 2013-07-29 | 2013-07-13 | 2013-07-29 | 0 | Yes | DUKHCONP03Z1STGF2010, DUKHCONP03Z1STGF2010 | DUKHCONP03MKARGF3000, DUKHCONP03Z1ARGF3000, DUKHCONP03Z1STFF2020, DUKHCONP03Z2STGF2015, DUKHCONP03Z1STFF2020, DUKHCONP03Z1ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-06-27 | 2013-07-25 | 2013-06-27 | 2013-07-25 | 0 | Yes | DUKHCONP03Z1STGF2005, DUKHCONP03Z1STGF2005, DUKHENGP03DWSTAP5590 | DUKHCONP03Z1STGF2015, DUKHCONP03Z1STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-06-12 | 2013-07-09 | 2013-06-12 | 2013-07-09 | 0 | Yes | DUKHCONP03Z1STGF2000, DUKHCONP03Z1STGF2000 | DUKHCONP03Z1STGF2010, DUKHCONP03Z1STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-06-03 | 2013-07-01 | 2013-06-03 | 2013-07-01 | 0 | Yes | DUKHENGP03DWSTAP5580, DUKHCONP03Z1STUG1045, DUKHCONP03Z1STUG1045 | DUKHCONP03Z1STGF2005, DUKHCONP03Z2STGF2000, DUKHCONP03Z1STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.10 .10 .15 .15 FIRST FLOORS |  | 50 | 50 | 0% | 2013-07-15 | 2013-09-14 | 2013-07-15 | 2013-09-14 | 0 |  |  |  | 0 | 0
DUKHCONP03Z1STFF2035 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-08-28 | 2013-09-14 | 2013-08-28 | 2013-09-14 | 0 | Yes | DUKHCONP03Z1STFF2030, DUKHCONP03Z1STFF2030 | DUKHCONP03Z2STFF2035, DUKHCONP03Z1ARFF3300, DUKHCONP03Z1STRF2040, DUKHCONP03Z1STRF2040, DUKHCONP03MKARFF3300, DUKHCONP03Z1ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-08-13 | 2013-09-10 | 2013-08-13 | 2013-09-10 | 0 | Yes | DUKHCONP03Z1STFF2025, DUKHCONP03Z1STFF2025 | DUKHCONP03Z1STFF2035, DUKHCONP03Z1STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-07-25 | 2013-08-25 | 2013-07-25 | 2013-08-25 | 0 | Yes | DUKHCONP03Z1STFF2020, DUKHCONP03Z1STFF2020 | DUKHCONP03Z1STFF2030, DUKHCONP03Z1STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-07-15 | 2013-08-15 | 2013-07-15 | 2013-08-15 | 0 | Yes | DUKHCONP03Z1STGF2015, DUKHCONP03Z1STGF2015, DUKHENGP03DWSTAP5600 | DUKHCONP03Z1STFF2025, DUKHCONP03Z1STFF2025, DUKHCONP03Z1ARFF3300, DUKHCONP03Z2STFF2020, DUKHCONP03Z1ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.10 .10 .15 .20 ROOF |  | 46 | 46 | 0% | 2013-08-31 | 2013-10-24 | 2013-08-31 | 2013-10-24 | 18 |  |  |  | 0 | 0
DUKHCONP03Z1STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-09-03 | 2013-09-22 | 2013-09-03 | 2013-09-22 | 3 | No | DUKHCONP03Z1STRF2040, DUKHCONP03Z1STRF2040 | DUKHCONP03Z1STRF2050, DUKHCONP03Z1STRF2050 | 0 | 0 | ROOF
DUKHCONP03Z1STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-08-31 | 2013-09-19 | 2013-08-31 | 2013-09-19 | 3 | No | DUKHCONP03Z1STFF2035, DUKHCONP03Z1STFF2035 | DUKHCONP03Z1STRF2045, DUKHCONP03Z2STRF2040, DUKHCONP03Z1STRF2045 | 0 | 0 | ROOF
DUKHCONP03Z1STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-09-18 | 2013-10-16 | 2013-09-18 | 2013-10-16 | 18 | No | DUKHCONP03Z1STRF2055, DUKHCONP03Z1STRF2055 | DUKHCONP03MKARRF3630, DUKHCONP03Z1STRF2065, DUKHCONP03Z1ARRF3630, DUKHCONP03MKAREL3665, DUKHCONP03Z1ARRF3630, DUKHCONP03Z1STRF2065 | 0 | 0 | ROOF
DUKHCONP03Z1STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-09-24 | 2013-10-24 | 2013-09-24 | 2013-10-24 | 18 | No | DUKHCONP03Z1STRF2060, DUKHCONP03Z1STRF2060 | DUKHCONP03Z1ARRF3630, DUKHCONP03Z1WTEX5030, DUKHCONP03Z1AREL3665, DUKHCONP03Z1ARRF3630, DUKHCONP03Z2STRF2065, DUKHCONP03MKARRF3630, DUKHCONP03Z1AREL3665 | 0 | 0 | ROOF
DUKHCONP03Z1STRF2055 | Slab-Concrete | 13 | 13 | 0% | 2013-09-16 | 2013-09-30 | 2013-09-16 | 2013-09-30 | 3 | No | DUKHCONP03Z1STRF2050, DUKHCONP03Z1STRF2050 | DUKHCONP03Z1ARRF3600, DUKHCONP03Z1MSEX5020, DUKHCONP03Z1WTEX5030, DUKHCONP03Z1STRF2060, DUKHCONP03Z2STRF2055, DUKHCONP03MKARRF3600, DUKHCONP03Z1MSEX5000, DUKHCONP03Z1MSEX5020, DUKHCONP03Z1WTEX5030, DUKHCONP03Z1ARRF3600, DUKHCONP03Z1STRF2060, DUKHCONP03Z1MSEX5000, DUKHCONP03MKARRF3630 | 0 | 0 | ROOF
DUKHCONP03Z1STRF2050 | Slab-Rebar & Formwork | 20 | 20 | 0% | 2013-09-05 | 2013-09-28 | 2013-09-05 | 2013-09-28 | 3 | No | DUKHCONP03Z1STRF2045, DUKHCONP03Z1STRF2045 | DUKHCONP03Z1STRF2055, DUKHCONP03Z1STRF2055 | 0 | 0 | ROOF
DHBL.K30.L55.10 .15 FINISHING WORKS |  | 180 | 180 | 0% | 2013-08-17 | 2014-03-18 | 2013-08-17 | 2014-03-18 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.10 .15 .10 INTERNAL FINISHES |  | 180 | 180 | 0% | 2013-08-17 | 2014-03-18 | 2013-08-17 | 2014-03-18 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.10 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-08-17 | 2014-01-29 | 2013-08-17 | 2014-01-29 | 40 |  |  |  | 0 | 0
DUKHCONP03Z1ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2013-12-03 | 2013-12-21 | 2013-12-03 | 2013-12-21 | 40 | No | DUKHCONP03MKARGF3070, DUKHCONP03Z1ARGF3065, DUKHCONP03Z1ARGF3065 | DUKHCONP03Z1ARGF3075, DUKHCONP03Z1ARGF3075, DUKHCONP03Z1ARGF3095, DUKHCONP03Z2ARGF3070, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3080, DUKHCONP03Z1ARGF3080 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 39 | No | DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ARGF3045, DUKHCONP03MKARGF3055, DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ARGF3045 | DUKHCONP03Z1ELGF4015, DUKHCONP03Z1ACGF4605, DUKHCONP03Z1ELGF4025, DUKHCONP03Z1ELGF4015, DUKHCONP03Z1ELGF4025, DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ACGF4605, DUKHCONP03Z1ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2013-12-10 | 2014-01-02 | 2013-12-10 | 2014-01-02 | 50 | No | DUKHCONP03MKARGF3080, DUKHCONP03Z1ARGF3070, DUKHCONP03Z1ARGF3070 | DUKHCONP03Z1ARGF3095, DUKHCONP03Z2ARGF3080, DUKHCONP03Z1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3000 | Block work | 25 | 25 | 0% | 2013-08-17 | 2013-09-14 | 2013-08-17 | 2013-09-14 | 35 | No | DUKHCONP03MKARGF3000, DUKHCONP03Z1STGF2015, DUKHCONP03Z1STGF2015 | DUKHCONP03Z1PLGF4305, DUKHCONP03Z1PLGF4310, DUKHCONP03Z2ARGF3000, DUKHCONP03Z1ARGF3005, DUKHCONP03Z1PLGF4305, DUKHCONP03Z1ELGF4000, DUKHCONP03Z1ELGF4000, DUKHCONP03Z1PLGF4310, DUKHCONP03Z1ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2013-12-09 | 2014-01-01 | 2013-12-09 | 2014-01-01 | 40 | No | DUKHCONP03Z1ARGF3070, DUKHCONP03Z1ARGF3070, DUKHCONP03MKARGF3075 | DUKHCONP03Z1ARGF3090, DUKHCONP03Z1ARGF3085, DUKHCONP03Z1ARGF3090, DUKHCONP03Z2ARGF3075, DUKHCONP03Z1ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-10-01 | 2013-10-31 | 2013-10-01 | 2013-10-31 | 35 | No | DUKHCONP03Z1PLGF4310, DUKHCONP03Z1PLGF4305, DUKHCONP03Z1PLGF4305, DUKHCONP03Z1ARGF3015, DUKHCONP03MKARGF3020, DUKHCONP03Z1PLGF4310, DUKHCONP03Z1ARGF3015 | DUKHCONP03Z1ARGF3025, DUKHCONP03Z2ARGF3020, DUKHCONP03Z1ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2013-11-05 | 2013-11-21 | 2013-11-05 | 2013-11-21 | 40 | No | DUKHCONP03Z1ARGF3035, DUKHCONP03Z1ARGF3010, DUKHCONP03Z1ARGF3025, DUKHCONP03MKARGF3040, DUKHCONP03Z1ARGF3010, DUKHCONP03Z1ARGF3025, DUKHCONP03Z1ARGF3035 | DUKHCONP03Z1ARGF3050, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3050, DUKHCONP03Z1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-01-01 | 2014-01-29 | 2014-01-01 | 2014-01-29 | 40 | No | DUKHCONP03Z1ARGF3090, DUKHCONP03MKARGF3095, DUKHCONP03Z1ACGF4610, DUKHCONP03Z1ARGF3080, DUKHCONP03Z1ARGF3085, DUKHCONP03Z1ARGF3040, DUKHCONP03Z1ARGF3035, DUKHCONP03Z1ARGF3080, DUKHCONP03Z1ARGF3085, DUKHCONP03Z1ACGF4610, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ARGF3070, DUKHCONP03Z1ARGF3030, DUKHCONP03Z1ARGF3090, DUKHCONP03Z1ARGF3030, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ARGF3070, DUKHCONP03Z1ARGF3040, DUKHCONP03Z1ARGF3035 | DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELTC8010, DUKHCONP03Z2ARGF3095, DUKHCONP03Z1ACTC8000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2013-10-27 | 2013-11-18 | 2013-10-27 | 2013-11-18 | 35 | No | DUKHCONP03Z1ARGF3030, DUKHCONP03Z1ARGF3025, DUKHCONP03Z1ARGF3030, DUKHCONP03Z1ELGF4010, DUKHCONP03MKARGF3045, DUKHCONP03Z1ARGF3025, DUKHCONP03Z1ELGF4010 | DUKHCONP03Z2ARGF3045, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ARGF3055, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ARGF3055 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-09-16 | 2013-10-09 | 2013-09-16 | 2013-10-09 | 43 | No | DUKHCONP03Z1ARGF3005, DUKHCONP03Z1ARGF3005, DUKHCONP03MKARGF3010 | DUKHCONP03Z1ARGF3025, DUKHCONP03Z1ARGF3035, DUKHCONP03Z1ARGF3035, DUKHCONP03Z1ARGF3025, DUKHCONP03Z1ARGF3040, DUKHCONP03Z1ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2013-11-13 | 2013-12-05 | 2013-11-13 | 2013-12-05 | 40 | No | DUKHCONP03Z1ARGF3025, DUKHCONP03Z1ARGF3040, DUKHCONP03Z1ARGF3040, DUKHCONP03Z1ARGF3025, DUKHCONP03MKARGF3050 | DUKHCONP03Z1ARGF3065, DUKHCONP03Z1ARGF3085, DUKHCONP03Z1ARGF3085, DUKHCONP03Z1ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2013-11-07 | 2013-12-05 | 2013-11-07 | 2013-12-05 | 35 | No | DUKHCONP03Z1ARGF3045, DUKHCONP03MKARGF3060, DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ARGF3045, DUKHCONP03Z1ACGF4600 | DUKHCONP03Z1ELGF4015, DUKHCONP03Z1ACGF4605, DUKHCONP03Z1ELGF4030, DUKHCONP03Z1PLGF4320, DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1PLGF4320, DUKHCONP03Z2ARGF3060, DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ELGF4025, DUKHCONP03Z1ACGF4605, DUKHCONP03Z1ELGF4015, DUKHCONP03Z1ELGF4030, DUKHCONP03Z1ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2013-12-23 | 2014-01-08 | 2013-12-23 | 2014-01-08 | 40 | No | DUKHCONP03Z1ARGF3075, DUKHCONP03Z1ARGF3075, DUKHCONP03MKARGF3090 | DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-10-01 | 2013-10-31 | 2013-10-01 | 2013-10-31 | 43 | No | DUKHCONP03MKARGF3030, DUKHCONP03Z1ARGF3005, DUKHCONP03Z1ARGF3005 | DUKHCONP03Z1ARGF3045, DUKHCONP03Z2ARGF3030, DUKHCONP03Z1ARGF3045, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-09-08 | 2013-10-06 | 2013-09-08 | 2013-10-06 | 35 | No | DUKHCONP03MKARGF3005, DUKHCONP03Z1ELGF4000, DUKHCONP03Z1PLGF4305, DUKHCONP03Z1ARGF3000, DUKHCONP03Z1ELGF4000, DUKHCONP03Z1PLGF4305, DUKHCONP03Z1ARGF3000 | DUKHCONP03Z1ARGF3010, DUKHCONP03Z1ARGF3015, DUKHCONP03Z1ARGF3015, DUKHCONP03Z1ARGF3030, DUKHCONP03Z1ARGF3010, DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ARGF3030, DUKHCONP03Z1ACGF4600, DUKHCONP03Z2ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-10-07 | 2013-11-06 | 2013-10-07 | 2013-11-06 | 35 | No | DUKHCONP03Z1ARGF3010, DUKHCONP03MKARGF3025, DUKHCONP03Z1ARGF3020, DUKHCONP03Z1ARGF3020, DUKHCONP03Z1ARGF3010 | DUKHCONP03Z1ARGF3050, DUKHCONP03Z1ARGF3045, DUKHCONP03Z1ARGF3035, DUKHCONP03Z1ARGF3045, DUKHCONP03Z2ARGF3025, DUKHCONP03Z1ARGF3040, DUKHCONP03Z1ARGF3035, DUKHCONP03Z1ARGF3050, DUKHCONP03Z1ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2013-12-17 | 2014-01-09 | 2013-12-17 | 2014-01-09 | 45 | No | DUKHCONP03Z1ARGF3050, DUKHCONP03Z1ARGF3050, DUKHCONP03Z1ARGF3075, DUKHCONP03MKARGF3085, DUKHCONP03Z1ARGF3075 | DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2013-10-29 | 2013-11-14 | 2013-10-29 | 2013-11-14 | 42 | No | DUKHCONP03Z1ARGF3025, DUKHCONP03MKARGF3035, DUKHCONP03Z1ARGF3010, DUKHCONP03Z1ARGF3010, DUKHCONP03Z1ARGF3025 | DUKHCONP03Z1ARGF3040, DUKHCONP03Z1ARGF3065, DUKHCONP03Z1ARGF3065, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-09-25 | 2013-10-12 | 2013-09-25 | 2013-10-12 | 35 | No | DUKHCONP03Z1ARGF3005, DUKHCONP03Z1ARGF3005, DUKHCONP03MKARGF3015 | DUKHCONP03Z1ARGF3020, DUKHCONP03Z1ARGF3020, DUKHCONP03Z2ARGF3015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ARGF3065 | Wooden door | 15 | 15 | 0% | 2013-11-27 | 2013-12-14 | 2013-11-27 | 2013-12-14 | 40 | No | DUKHCONP03Z1ARGF3035, DUKHCONP03Z1ARGF3050, DUKHCONP03Z1ARGF3035, DUKHCONP03MKARGF3065, DUKHCONP03Z1ARGF3050 | DUKHCONP03Z1PLGF4315, DUKHCONP03Z1ARGF3070, DUKHCONP03Z2ARGF3065, DUKHCONP03Z1PLGF4315, DUKHCONP03Z1ARGF3070 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.10 .15 .10 .15 FIRST FLOORS |  | 143 | 143 | 0% | 2013-09-29 | 2014-03-18 | 2013-09-29 | 2014-03-18 | 0 |  |  |  | 0 | 0
DUKHCONP03Z1ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-01-16 | 2014-02-08 | 2014-01-16 | 2014-02-08 | 0 | Yes | DUKHCONP03MKARFF3370, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3365 | DUKHCONP03Z1ARFF3380, DUKHCONP03Z1ARFF3375, DUKHCONP03Z1ARFF3380, DUKHCONP03Z2ARFF3370, DUKHCONP03Z1ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3355 | Aluminum tile false ceiling | 20 | 20 | 0% | 2013-12-28 | 2014-01-19 | 2013-12-28 | 2014-01-19 | 2 | No | DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ACFF4615, DUKHCONP03MKARFF3355, DUKHCONP03Z1ARFF3345, DUKHCONP03Z1ARFF3345 | DUKHCONP03Z1PLFF4340, DUKHCONP03Z1ACFF4620, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ELFF4055, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ELFF4050, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ACFF4620, DUKHCONP03Z1PLFF4340, DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ELFF4050, DUKHCONP03Z2ARFF3355, DUKHCONP03Z1ELFF4060, DUKHCONP03Z1ELFF4055, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ELFF4060, DUKHCONP03Z1ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-01-23 | 2014-02-16 | 2014-01-23 | 2014-02-16 | 11 | No | DUKHCONP03Z1ARFF3370, DUKHCONP03Z1ARFF3370, DUKHCONP03MKARFF3380 | DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3300 | Block work | 24 | 24 | 0% | 2013-09-29 | 2013-10-28 | 2013-09-29 | 2013-10-28 | 0 | Yes | DUKHCONP03Z1STFF2035, DUKHCONP03Z1STFF2020, DUKHCONP03Z1STFF2035, DUKHCONP03Z1STFF2020, DUKHCONP03MKARFF3300 | DUKHCONP03Z1PLFF4325, DUKHCONP03Z1PLFF4330, DUKHCONP03Z1ELFF4035, DUKHCONP03Z1PLFF4330, DUKHCONP03Z1ARFF3305, DUKHCONP03Z1ARFF3305, DUKHCONP03Z1ELFF4035, DUKHCONP03Z2ARFF3300, DUKHCONP03Z1PLFF4325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 0 | Yes | DUKHCONP03Z1ARFF3370, DUKHCONP03MKARFF3375, DUKHCONP03Z1ARFF3370 | DUKHCONP03Z1ARFF3390, DUKHCONP03Z1ARFF3385, DUKHCONP03Z2ARFF3375, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3385, DUKHCONP03Z1ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-11-24 | 2013-12-23 | 2013-11-24 | 2013-12-23 | 0 | Yes | DUKHCONP03Z1PLFF4330, DUKHCONP03Z1PLFF4325, DUKHCONP03Z1ARFF3315, DUKHCONP03Z1PLFF4325, DUKHCONP03MKARFF3320, DUKHCONP03Z1PLFF4330, DUKHCONP03Z1ARFF3315 | DUKHCONP03Z1ARFF3325, DUKHCONP03Z2ARFF3320, DUKHCONP03Z1ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 0 | Yes | DUKHCONP03Z1ARFF3380, DUKHCONP03Z1ACFF4625, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3385, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3330, DUKHCONP03Z1ARFF3330, DUKHCONP03Z1ACFF4625, DUKHCONP03Z1ARFF3380, DUKHCONP03Z1ARFF3375, DUKHCONP03Z1ARFF3390, DUKHCONP03Z1ARFF3385, DUKHCONP03Z1ARFF3335, DUKHCONP03Z1ARFF3350, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3375, DUKHCONP03Z1ARFF3335, DUKHCONP03MKARFF3395, DUKHCONP03Z1ARFF3350, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3390 | DUKHCONP03Z2ARFF3395, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2013-12-15 | 2014-01-07 | 2013-12-15 | 2014-01-07 | 0 | Yes | DUKHCONP03Z1ARFF3325, DUKHCONP03MKARFF3345, DUKHCONP03Z1ARFF3330, DUKHCONP03Z1ELFF4045, DUKHCONP03Z1ARFF3325, DUKHCONP03Z1ARFF3330, DUKHCONP03Z1ELFF4045 | DUKHCONP03Z2ARFF3345, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3355 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3310 | Flooring screed | 21 | 21 | 0% | 2013-11-02 | 2013-11-25 | 2013-11-02 | 2013-11-25 | 15 | No | DUKHCONP03Z1ARFF3305, DUKHCONP03MKARFF3310, DUKHCONP03Z1ARFF3305 | DUKHCONP03Z1ARFF3325, DUKHCONP03Z1ARFF3335, DUKHCONP03Z1ARFF3325, DUKHCONP03Z1ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2013-12-23 | 2014-01-14 | 2013-12-23 | 2014-01-14 | 2 | No | DUKHCONP03Z1ARFF3325, DUKHCONP03MKARFF3350, DUKHCONP03Z1ARFF3325 | DUKHCONP03Z1ARFF3385, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3385, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 0 | Yes | DUKHCONP03Z1ARFF3345, DUKHCONP03MKARFF3360, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ARFF3345 | DUKHCONP03Z1ELFF4060, DUKHCONP03Z1ELFF4060, DUKHCONP03Z1PLFF4340, DUKHCONP03Z1ELFF4050, DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ELFF4050, DUKHCONP03Z1ELFF4055, DUKHCONP03Z1ACFF4620, DUKHCONP03Z2ARFF3355, DUKHCONP03Z1ELFF4055, DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1PLFF4340, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ACFF4620, DUKHCONP03Z1ARFF3395, DUKHCONP03Z2ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-02-05 | 2014-03-01 | 2014-02-05 | 2014-03-01 | 1 | No | DUKHCONP03Z1ARFF3350, DUKHCONP03Z1ARFF3350, DUKHCONP03Z1ARFF3375, DUKHCONP03MKARFF3385, DUKHCONP03Z1ARFF3375 | DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-02-08 | 2014-03-03 | 2014-02-08 | 2014-03-03 | 0 | Yes | DUKHCONP03Z1ARFF3375, DUKHCONP03MKARFF3390, DUKHCONP03Z1ARFF3375 | DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3330 | Paint First coat | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 18 | No | DUKHCONP03Z1ARFF3305, DUKHCONP03MKARFF3330, DUKHCONP03Z1ARFF3305 | DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3345, DUKHCONP03Z1ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3305 | Plastering work | 25 | 25 | 0% | 2013-10-24 | 2013-11-21 | 2013-10-24 | 2013-11-21 | 0 | Yes | DUKHCONP03MKARFF3305, DUKHCONP03Z1ELFF4035, DUKHCONP03Z1PLFF4325, DUKHCONP03Z1ELFF4035, DUKHCONP03Z1ARFF3300, DUKHCONP03Z1ARFF3300, DUKHCONP03Z1PLFF4325 | DUKHCONP03Z1ARFF3315, DUKHCONP03Z1ARFF3315, DUKHCONP03Z1AREL3665, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ARFF3330, DUKHCONP03Z1ARFF3310, DUKHCONP03Z1ARFF3310, DUKHCONP03Z1AREL3665, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ARFF3330, DUKHCONP03Z2ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-12-01 | 2013-12-30 | 2013-12-01 | 2013-12-30 | 0 | Yes | DUKHCONP03Z1ARFF3320, DUKHCONP03Z1ARFF3310, DUKHCONP03Z1ARFF3310, DUKHCONP03MKARFF3325, DUKHCONP03Z1ARFF3320 | DUKHCONP03Z2ARFF3325, DUKHCONP03Z1ARFF3350, DUKHCONP03Z1ARFF3345, DUKHCONP03Z1ARFF3335, DUKHCONP03Z1ARFF3335, DUKHCONP03Z1ARFF3345, DUKHCONP03Z1ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2013-12-19 | 2014-01-05 | 2013-12-19 | 2014-01-05 | 10 | No | DUKHCONP03Z1ARFF3310, DUKHCONP03MKARFF3335, DUKHCONP03Z1ARFF3325, DUKHCONP03Z1ARFF3325, DUKHCONP03Z1ARFF3310 | DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2013-11-14 | 2013-12-01 | 2013-11-14 | 2013-12-01 | 0 | Yes | DUKHCONP03Z1ARFF3305, DUKHCONP03Z1ARFF3305, DUKHCONP03MKARFF3315 | DUKHCONP03Z2ARFF3315, DUKHCONP03Z1ARFF3320, DUKHCONP03Z1ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-01-08 | 2014-01-25 | 2014-01-08 | 2014-01-25 | 0 | Yes | DUKHCONP03Z1ARFF3350, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3335, DUKHCONP03Z1ARFF3350, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3360, DUKHCONP03MKARFF3365, DUKHCONP03Z1ARFF3335, DUKHCONP03Z1ARFF3355 | DUKHCONP03Z1ARFF3395, DUKHCONP03Z2ARFF3365, DUKHCONP03Z1PLFF4335, DUKHCONP03Z1PLFF4335, DUKHCONP03Z1ARFF3370, DUKHCONP03Z1ARFF3370, DUKHCONP03Z1ARFF3395 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.10 .15 .10 .20 ROOF |  | 91 | 91 | 0% | 2013-10-16 | 2014-02-02 | 2013-10-16 | 2014-02-02 | 37 |  |  |  | 0 | 0
DUKHCONP03Z1ARRF3600 | Block work | 20 | 20 | 0% | 2013-10-16 | 2013-11-10 | 2013-10-16 | 2013-11-10 | 67 | No | DUKHCONP03Z1STRF2055, DUKHCONP03MKARRF3600, DUKHCONP03Z1STRF2055 | DUKHCONP03Z2ARRF3600, DUKHCONP03Z1ARRF3605, DUKHCONP03Z1ARRF3605 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3620 | Epoxy Painting | 15 | 15 | 0% | 2014-01-16 | 2014-02-02 | 2014-01-16 | 2014-02-02 | 37 | No | DUKHCONP03MKARRF3620, DUKHCONP03Z1ARRF3695, DUKHCONP03Z1ARRF3695 | DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ACTC8000 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3610 | Flooring screed | 15 | 15 | 0% | 2013-11-10 | 2013-11-26 | 2013-11-10 | 2013-11-26 | 72 | No | DUKHCONP03Z1ARRF3605, DUKHCONP03Z1ARRF3605 | DUKHCONP03Z1ARRF3695, DUKHCONP03Z1ARRF3695 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3695 | Painting | 20 | 20 | 0% | 2013-12-30 | 2014-01-21 | 2013-12-30 | 2014-01-21 | 37 | No | DUKHCONP03Z1ARRF3610, DUKHCONP03Z1ARRF3610, DUKHCONP03MKARRF3695 | DUKHCONP03Z1ARRF3620, DUKHCONP03Z1AREL3680, DUKHCONP03Z1ARRF3620, DUKHCONP03Z1AREL3680 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3605 | Plastering work | 20 | 20 | 0% | 2013-10-27 | 2013-11-18 | 2013-10-27 | 2013-11-18 | 67 | No | DUKHCONP03MKARRF3605, DUKHCONP03Z1ARRF3600, DUKHCONP03Z1ARRF3600 | DUKHCONP03Z1PLRF4345, DUKHCONP03Z1ARRF3610, DUKHCONP03Z1PLRF4345, DUKHCONP03Z1AREL3665, DUKHCONP03Z1ARRF3610 | 0 | 0 | ROOF
DHBL.K30.L55.10 .15 .15 EXTERNAL FINISHES |  | 80 | 80 | 0% | 2013-10-24 | 2014-01-26 | 2013-10-24 | 2014-01-26 | 43 |  |  |  | 0 | 0
DHBL.K30.L55.10 .15 .15 .10 ROOF |  | 58 | 58 | 0% | 2013-10-24 | 2013-12-31 | 2013-10-24 | 2013-12-31 | 65 |  |  |  | 0 | 0
DUKHCONP03Z1ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2013-11-17 | 2013-12-15 | 2013-11-17 | 2013-12-15 | 60 | No | DUKHCONP03MKARRF3650, DUKHCONP03Z1ARRF3645, DUKHCONP03Z1ARRF3645 | DUKHCONP03Z1ARRF3655, DUKHCONP03Z1ARRF3655 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2013-12-14 | 2013-12-31 | 2013-12-14 | 2013-12-31 | 65 | No | DUKHCONP03MKARRF3660, DUKHCONP03Z1ARRF3655, DUKHCONP03Z1ARRF3655 | DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 60 | No | DUKHCONP03Z1ARRF3635, DUKHCONP03Z1ARRF3635, DUKHCONP03MKARRF3640 | DUKHCONP03Z1ARRF3645, DUKHCONP03Z1ARRF3645 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2013-12-02 | 2013-12-25 | 2013-12-02 | 2013-12-25 | 60 | No | DUKHCONP03Z1ARRF3645, DUKHCONP03Z1ARRF3650, DUKHCONP03Z1ARRF3650, DUKHCONP03MKARRF3655, DUKHCONP03Z1ARRF3645 | DUKHCONP03Z1PLRF4355, DUKHCONP03Z2ARRF3655, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1PLRF4355, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ARRF3660, DUKHCONP03Z1ARRF3660 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2013-10-30 | 2013-11-27 | 2013-10-30 | 2013-11-27 | 60 | No | DUKHPROGEN00PRDV3050, DUKHCONP03Z1ARRF3630, DUKHCONP03MKARRF3635, DUKHCONP03Z1ARRF3630 | DUKHCONP03Z1ARRF3640, DUKHCONP03Z1ARRF3640 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2013-10-24 | 2013-11-21 | 2013-10-24 | 2013-11-21 | 62 | No | DUKHCONP03Z1STRF2065, DUKHCONP03Z1STRF2065, DUKHCONP03Z1STRF2060, DUKHCONP03Z1STRF2060, DUKHCONP03MKARRF3630 | DUKHCONP03Z2ARRF3630, DUKHCONP03Z1ARRF3635, DUKHCONP03Z1ARRF3635 | 0 | 0 | ROOF
DUKHCONP03Z1ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2013-11-09 | 2013-12-07 | 2013-11-09 | 2013-12-07 | 60 | No | DUKHCONP03Z1ARRF3640, DUKHCONP03Z1ARRF3640, DUKHCONP03MKARRF3645 | DUKHCONP03Z1ARRF3655, DUKHCONP03Z1ELRF4070, DUKHCONP03Z1ACRF4630, DUKHCONP03Z1ARRF3650, DUKHCONP03Z1ELRF4070, DUKHCONP03Z1ACRF4630, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1ARRF3650, DUKHCONP03Z1ARRF3655 | 0 | 0 | ROOF
DHBL.K30.L55.10 .15 .15 .15 ELEVATION |  | 57 | 57 | 0% | 2013-11-20 | 2014-01-26 | 2013-11-20 | 2014-01-26 | 43 |  |  |  | 0 | 0
DUKHCONP03Z1AREL3680 | External Painting | 20 | 20 | 0% | 2014-01-04 | 2014-01-26 | 2014-01-04 | 2014-01-26 | 43 | No | DUKHCONP03Z1ARRF3695, DUKHCONP03MKAREL3680, DUKHCONP03Z1ARRF3695, DUKHCONP03Z1AREL3675, DUKHCONP03Z1AREL3675 | DUKHCONP03Z2AREL3680, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1ACTC8000 | 0 | 0 | ELEVATION
DUKHCONP03Z1AREL3665 | External Plastering | 25 | 25 | 0% | 2013-11-20 | 2013-12-19 | 2013-11-20 | 2013-12-19 | 53 | No | DUKHCONP03Z1STRF2065, DUKHCONP03Z1ARFF3305, DUKHCONP03MKAREL3665, DUKHCONP03Z1STRF2065, DUKHCONP03Z1ARFF3305, DUKHCONP03Z1ARRF3605 | DUKHCONP03Z2AREL3665, DUKHCONP03Z1AREL3675, DUKHCONP03Z1AREL3675, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP03Z1AREL3675 | GRC Panel Works | 20 | 20 | 0% | 2013-12-08 | 2013-12-31 | 2013-12-08 | 2013-12-31 | 55 | No | DUKHPROGEN00PRDV3390, DUKHCONP03Z1AREL3665, DUKHCONP03Z1AREL3665, DUKHCONP03MKAREL3675 | DUKHCONP03Z1AREL3680, DUKHCONP03Z1AREL3680, DUKHCONP03Z2AREL3675 | 0 | 0 | ELEVATION
DHBL.K30.L55.10 .20 MEP WORKS |  | 261 | 261 | 0% | 2013-05-08 | 2014-03-16 | 2013-05-08 | 2014-03-16 | 2 |  |  |  | 0 | 0
DHBL.K30.L55.10 .20 .10 ELECTRICAL WORKS |  | 173 | 173 | 0% | 2013-08-22 | 2014-03-16 | 2013-08-22 | 2014-03-16 | 2 |  |  |  | 0 | 0
DHBL.K30.L55.10 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-08-22 | 2014-01-01 | 2013-08-22 | 2014-01-01 | 37 |  |  |  | 0 | 0
DUKHCONP03Z1ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-09-05 | 2013-09-28 | 2013-09-05 | 2013-09-28 | 60 | No | DUKHCONP03MKELGF4005, DUKHCONP03Z1ELGF4000, DUKHCONP03Z1ELGF4000 | DUKHCONP03Z2ELGF4005, DUKHCONP03Z1ELGF4010, DUKHCONP03Z1ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-08-22 | 2013-09-19 | 2013-08-22 | 2013-09-19 | 44 | No | DUKHCONP03MKELGF4000, DUKHCONP03Z1ARGF3000, DUKHCONP03Z1ARGF3000 | DUKHCONP03Z1ARGF3005, DUKHCONP03Z1ELGF4005, DUKHCONP03Z1ELGF4005, DUKHCONP03Z1ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 49 | No | DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ARGF3055, DUKHCONP03MKELGF4015, DUKHCONP03Z1ARGF3055, DUKHCONP03Z1ARGF3060 | DUKHCONP03Z1ELFF4055, DUKHCONP03Z1ELFF4055, DUKHCONP03Z1ELTC8010, DUKHCONP03Z2ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2013-11-21 | 2013-12-14 | 2013-11-21 | 2013-12-14 | 36 | No | DUKHCONP03MKELGF4020, DUKHCONP03Z1ELGF4010, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ELGF4010, DUKHCONP03Z1ARGF3055, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ARGF3055 | DUKHCONP03Z1ELGF4025, DUKHCONP03Z1ELGF4030, DUKHCONP03Z1ELGF4030, DUKHCONP03Z1ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 37 | No | DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ARGF3055, DUKHCONP03MKELGF4025, DUKHCONP03Z1ARGF3055, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ARGF3060 | DUKHCONP03Z2ELGF4025, DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2013-12-03 | 2013-12-26 | 2013-12-03 | 2013-12-26 | 36 | No | DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ARGF3060, DUKHCONP03MKELGF4030, DUKHCONP03Z1ARGF3060 | DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ELFF4050, DUKHCONP03Z1ELFF4050, DUKHCONP03Z2ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-09-14 | 2013-10-12 | 2013-09-14 | 2013-10-12 | 60 | No | DUKHCONP03Z1ELGF4005, DUKHCONP03Z1ELGF4005, DUKHCONP03MKELGF4010 | DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ARGF3045, DUKHCONP03Z1ELGF4020, DUKHCONP03Z1ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.10 .20 .10 .15 FIRST FLOORS |  | 115 | 115 | 0% | 2013-10-05 | 2014-02-19 | 2013-10-05 | 2014-02-19 | 5 |  |  |  | 0 | 0
DUKHCONP03Z1ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-10-21 | 2013-11-12 | 2013-10-21 | 2013-11-12 | 30 | No | DUKHCONP03Z1ELFF4035, DUKHCONP03MKELFF4040, DUKHCONP03Z1ELFF4035 | DUKHCONP03Z1ELFF4045, DUKHCONP03Z1ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-10-05 | 2013-11-04 | 2013-10-05 | 2013-11-04 | 10 | No | DUKHCONP03Z1ARFF3300, DUKHCONP03MKELFF4035, DUKHCONP03Z1ARFF3300 | DUKHCONP03Z1ARFF3305, DUKHCONP03Z1ELFF4040, DUKHCONP03Z1ARFF3305, DUKHCONP03Z1ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 12 | No | DUKHCONP03Z1ELGF4015, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ELGF4015, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3360, DUKHCONP03MKELFF4055, DUKHCONP03Z1ARFF3355 | DUKHCONP03Z1ELTC8010, DUKHCONP03Z2ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-01-08 | 2014-01-30 | 2014-01-08 | 2014-01-30 | 1 | No | DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ELFF4045, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ELFF4045, DUKHCONP03Z1ARFF3355, DUKHCONP03MKELFF4060, DUKHCONP03Z1ARFF3355 | DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ELFF4065, DUKHCONP03Z2ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 1 | No | DUKHCONP03MKELFF4065, DUKHCONP03Z1ELFF4060, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ELGF4025, DUKHCONP03Z1ELFF4060, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ELGF4025, DUKHCONP03Z1ARFF3355 | DUKHCONP03Z1ELRF4070, DUKHCONP03Z2ELFF4065, DUKHCONP03Z1ELRF4070, DUKHCONP03Z1ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 18 | No | DUKHCONP03Z1ELGF4030, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3360, DUKHCONP03MKELFF4050, DUKHCONP03Z1ELGF4030, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1MSEX5010 | DUKHCONP03Z1ELRF4070, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-10-29 | 2013-11-26 | 2013-10-29 | 2013-11-26 | 30 | No | DUKHCONP03MKELFF4045, DUKHCONP03Z1ELFF4040, DUKHCONP03Z1ELFF4040 | DUKHCONP03Z1ELRF4070, DUKHCONP03Z1ELFF4060, DUKHCONP03Z1ELFF4060, DUKHCONP03Z1ARFF3345, DUKHCONP03Z1ELRF4070, DUKHCONP03Z1ARFF3345, DUKHCONP03Z2ELFF4045 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.10 .20 .10 .20 ROOF |  | 29 | 29 | 0% | 2014-02-10 | 2014-03-16 | 2014-02-10 | 2014-03-16 | 2 |  |  |  | 0 | 0
DUKHCONP03Z1ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-02-10 | 2014-03-03 | 2014-02-10 | 2014-03-03 | 2 | No | DUKHCONP03Z1ELFF4045, DUKHCONP03Z1ELFF4050, DUKHCONP03Z1ARRF3645, DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ARRF3645, DUKHCONP03MKELRF4070, DUKHCONP03Z1ELFF4065, DUKHCONP03Z1ELFF4045, DUKHCONP03Z1ELFF4050 | DUKHCONP03Z1ELRF4075, DUKHCONP03Z1ELRF4075 | 0 | 0 | ROOF
DUKHCONP03Z1ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-02-18 | 2014-03-16 | 2014-02-18 | 2014-03-16 | 2 | No | DUKHCONP03Z1ELRF4070, DUKHCONP03MKELRF4075, DUKHCONP03Z1ELRF4070 | DUKHCONP03Z1ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L55.10 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 249 | 249 | 0% | 2013-05-08 | 2014-03-02 | 2013-05-08 | 2014-03-02 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.10 .20 .15 .10 GROUND FLOOR |  | 199 | 199 | 0% | 2013-05-08 | 2014-01-01 | 2013-05-08 | 2014-01-01 | 64 |  |  |  | 0 | 0
DUKHCONP03Z1PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-05-08 | 2013-05-30 | 2013-05-08 | 2013-05-30 | 0 | Yes | DUKHCONP03Z1STUG1040, DUKHPROGEN00PRDV3060, DUKHPROGEN00PRDV3070, DUKHCONP03Z1STUG1040 | DUKHCONP03Z1STUG1045, DUKHCONP03Z1STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-09-02 | 2013-09-22 | 2013-09-02 | 2013-09-22 | 56 | No | DUKHCONP03MKPLGF4310, DUKHCONP03Z1ARGF3000, DUKHCONP03Z1ARGF3000, DUKHCONP03Z1PLGF4305, DUKHCONP03Z1PLGF4305 | DUKHCONP03Z1ARGF3020, DUKHCONP03Z1MSEX5000, DUKHCONP03Z1ARGF3020, DUKHCONP03Z1PLGF4315, DUKHCONP03Z1MSEX5000, DUKHCONP03Z1PLGF4315 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-09-02 | 2013-09-22 | 2013-09-02 | 2013-09-22 | 35 | No | DUKHCONP03Z1ARGF3000, DUKHCONP03Z1ARGF3000, DUKHCONP03MKPLGF4305 | DUKHCONP03Z2PLGF4305, DUKHCONP03Z1ARGF3020, DUKHCONP03Z1ARGF3020, DUKHCONP03Z1ARGF3005, DUKHCONP03Z1ARGF3005, DUKHCONP03Z1PLGF4310, DUKHCONP03Z1PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2013-12-15 | 2014-01-01 | 2013-12-15 | 2014-01-01 | 64 | No | DUKHCONP03Z1PLGF4315, DUKHCONP03Z1ARGF3060, DUKHCONP03MKPLGF4320, DUKHCONP03Z1ARGF3060, DUKHCONP03Z1PLGF4315 | DUKHCONP03Z1PLTC8005, DUKHCONP03Z2PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2013-12-03 | 2013-12-26 | 2013-12-03 | 2013-12-26 | 64 | No | DUKHCONP03MKPLGF4315, DUKHCONP03Z1ARGF3065, DUKHCONP03Z1ARGF3065, DUKHCONP03Z1PLGF4310, DUKHCONP03Z1PLGF4310 | DUKHCONP03Z1PLGF4320, DUKHCONP03Z1PLGF4320, DUKHCONP03Z2PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.10 .20 .15 .15 FIRST FLOORS |  | 100 | 100 | 0% | 2013-10-15 | 2014-02-12 | 2013-10-15 | 2014-02-12 | 14 |  |  |  | 0 | 0
DUKHCONP03Z1PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2013-10-15 | 2013-11-06 | 2013-10-15 | 2013-11-06 | 25 | No | DUKHCONP03Z1ARFF3300, DUKHCONP03Z1ARFF3300, DUKHCONP03MKPLFF4330, DUKHCONP03Z1PLFF4325, DUKHCONP03Z1PLFF4325 | DUKHCONP03Z1PLRF4350, DUKHCONP03Z1ARFF3320, DUKHCONP03Z1PLFF4335, DUKHCONP03Z2PLFF4330, DUKHCONP03Z1PLFF4335, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-10-15 | 2013-11-06 | 2013-10-15 | 2013-11-06 | 0 | Yes | DUKHCONP03MKPLFF4325, DUKHCONP03Z1ARFF3300, DUKHCONP03Z1ARFF3300 | DUKHCONP03Z1ARFF3305, DUKHCONP03Z1PLFF4330, DUKHCONP03Z1ARFF3320, DUKHCONP03Z1ARFF3320, DUKHCONP03Z1ARFF3305, DUKHCONP03Z1PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-01-26 | 2014-02-12 | 2014-01-26 | 2014-02-12 | 14 | No | DUKHCONP03MKPLFF4340, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1PLFF4335, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1PLFF4335, DUKHCONP03Z1ARFF3360 | DUKHCONP03Z2PLFF4340, DUKHCONP03Z1PLRF4355, DUKHCONP03Z1PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-01-14 | 2014-02-05 | 2014-01-14 | 2014-02-05 | 14 | No | DUKHCONP03MKPLFF4335, DUKHCONP03Z1PLFF4330, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1ARFF3365, DUKHCONP03Z1PLFF4330 | DUKHCONP03Z1PLFF4340, DUKHCONP03Z1PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.10 .20 .15 .20 ROOF |  | 91 | 91 | 0% | 2013-11-14 | 2014-03-02 | 2013-11-14 | 2014-03-02 | 14 |  |  |  | 0 | 0
DUKHCONP03Z1PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2013-11-14 | 2013-12-01 | 2013-11-14 | 2013-12-01 | 67 | No | DUKHCONP03MKPLRF4345, DUKHCONP03Z1ARRF3605, DUKHCONP03Z1ARRF3605 | DUKHCONP03Z1PLRF4355, DUKHCONP03Z1PLRF4355, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1PLRF4350 | 0 | 0 | ROOF
DUKHCONP03Z1PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2013-12-10 | 2013-12-28 | 2013-12-10 | 2013-12-28 | 53 | No | DUKHCONP03Z1PLFF4330, DUKHCONP03Z1PLRF4345, DUKHCONP03Z1PLRF4345, DUKHCONP03MKPLRF4350, DUKHCONP03Z1ARRF3645, DUKHCONP03Z1AREL3665, DUKHCONP03Z1PLFF4330, DUKHCONP03Z1ARRF3645, DUKHCONP03Z1AREL3665 | DUKHCONP03Z1PLRF4355, DUKHCONP03Z1WTEX5065, DUKHCONP03Z2PLRF4350, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1WTEX5065, DUKHCONP03Z1PLRF4355 | 0 | 0 | ROOF
DUKHCONP03Z1PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 14 | No | DUKHCONP03Z1PLRF4345, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1ARRF3655, DUKHCONP03MKPLRF4355, DUKHCONP03Z1PLRF4345, DUKHCONP03Z1PLFF4340, DUKHCONP03Z1ARRF3655, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1PLFF4340 | DUKHCONP03Z2PLRF4355, DUKHCONP03Z1PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L55.10 .20 .20 AC WORKS |  | 135 | 135 | 0% | 2013-09-22 | 2014-03-02 | 2013-09-22 | 2014-03-02 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.10 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-09-22 | 2013-12-30 | 2013-09-22 | 2013-12-30 | 51 |  |  |  | 0 | 0
DUKHCONP03Z1ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2013-12-07 | 2013-12-30 | 2013-12-07 | 2013-12-30 | 51 | No | DUKHCONP03Z1ACGF4605, DUKHCONP03Z1ACGF4605, DUKHCONP03MKACGF4610 | DUKHCONP03Z2ACGF4610, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ACRF4635, DUKHCONP03Z1ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 51 | No | DUKHCONP03Z1ARGF3060, DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ARGF3055, DUKHCONP03MKACGF4605, DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ARGF3055, DUKHCONP03Z1ARGF3060 | DUKHCONP03Z1ACGF4610, DUKHCONP03Z1ACGF4610, DUKHCONP03Z2ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z1ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-09-22 | 2013-10-14 | 2013-09-22 | 2013-10-14 | 66 | No | DUKHCONP03Z1ARGF3005, DUKHCONP03Z1ARGF3005, DUKHCONP03MKACGF4600 | DUKHCONP03Z1ACRF4630, DUKHCONP03Z1ACGF4605, DUKHCONP03Z1ARGF3055, DUKHCONP03Z1ACGF4605, DUKHCONP03Z1ACRF4630, DUKHCONP03Z1ARGF3060, DUKHCONP03Z2ACGF4600, DUKHCONP03Z1ARGF3055, DUKHCONP03Z1ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.10 .20 .20 .15 FIRST FLOORS |  | 87 | 87 | 0% | 2013-11-07 | 2014-02-18 | 2013-11-07 | 2014-02-18 | 9 |  |  |  | 0 | 0
DUKHCONP03Z1ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-01-26 | 2014-02-18 | 2014-01-26 | 2014-02-18 | 9 | No | DUKHCONP03MKACFF4625, DUKHCONP03Z1ACFF4620, DUKHCONP03Z1ACFF4620 | DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ACRF4635, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ACTC8000, DUKHCONP03Z1ACRF4635, DUKHCONP03Z2ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 9 | No | DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3355, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ARFF3360, DUKHCONP03MKACFF4620 | DUKHCONP03Z1ACFF4625, DUKHCONP03Z1ACFF4625, DUKHCONP03Z2ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z1ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2013-11-07 | 2013-11-30 | 2013-11-07 | 2013-11-30 | 32 | No | DUKHCONP03MKACFF4615, DUKHCONP03Z1ARFF3305, DUKHCONP03Z1ARFF3305 | DUKHCONP03Z1ACRF4630, DUKHCONP03Z1ACRF4630, DUKHCONP03Z1ARFF3355, DUKHCONP03Z2ACFF4615, DUKHCONP03Z1ACFF4620, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ACFF4620, DUKHCONP03Z1ARFF3355 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.10 .20 .20 .20 ROOF |  | 89 | 89 | 0% | 2013-11-17 | 2014-03-02 | 2013-11-17 | 2014-03-02 | 14 |  |  |  | 0 | 0
DUKHCONP03Z1ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 14 | No | DUKHCONP03Z1ACFF4625, DUKHCONP03Z1ACGF4610, DUKHCONP03Z1ACFF4625, DUKHCONP03MKACRF4635, DUKHCONP03Z1ACRF4630, DUKHCONP03Z1ACRF4630, DUKHCONP03Z1ACGF4610 | DUKHCONP03Z2ACRF4635, DUKHCONP03Z1ACTC8000 | 0 | 0 | ROOF
DUKHCONP03Z1ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2013-11-17 | 2013-12-15 | 2013-11-17 | 2013-12-15 | 73 | No | DUKHCONP03MKACRF4630, DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ACFF4615, DUKHCONP03Z1ARRF3645, DUKHCONP03Z1ACGF4600, DUKHCONP03Z1ARRF3645 | DUKHCONP03Z1ACRF4635, DUKHCONP03Z2ACRF4630, DUKHCONP03Z1ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L55.10 .25 EXTERNAL WORKS |  | 123 | 123 | 0% | 2013-09-30 | 2014-02-24 | 2013-09-30 | 2014-02-24 | 19 |  |  |  | 0 | 0
DHBL.K30.L55.10 .25 .10 MISCELLANEOUS |  | 62 | 62 | 0% | 2013-11-23 | 2014-02-03 | 2013-11-23 | 2014-02-03 | 26 |  |  |  | 0 | 0
DUKHCONP03Z1MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-12-07 | 2014-01-05 | 2013-12-07 | 2014-01-05 | 18 | No | DUKHCONP03Z1MSEX5000, DUKHCONP03Z1MSEX5000, DUKHCONP03MKMSEX5005 | DUKHCONP03Z1ACTC8000, DUKHCONP03Z1MSEX5015, DUKHCONP03Z1ELTC8010, DUKHCONP03Z1PLTC8005, DUKHCONP03Z1MSEX5010, DUKHCONP03Z1MSEX5015 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z1MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2013-12-07 | 2014-01-05 | 2013-12-07 | 2014-01-05 | 19 | No | DUKHCONP03Z1STRF2055, DUKHCONP03Z1STRF2055, DUKHCONP03MKMSEX5020 | DUKHCONP03Z2MSEX5020, DUKHCONP03Z1MSEX5025, DUKHCONP03Z1MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z1MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2013-12-28 | 2014-01-19 | 2013-12-28 | 2014-01-19 | 39 | No | DUKHCONP03Z1MSEX5005, DUKHCONP03MKMSEX5015, DUKHCONP03Z1MSEX5005 | DUKHCONP03Z1WTEX5065, DUKHCONP03Z1WTEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z1MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-11-23 | 2013-12-22 | 2013-11-23 | 2013-12-22 | 3 | No | DUKHCONP03Z1PLGF4310, DUKHCONP03Z1STRF2055, DUKHCONP03MKMSEX5000, DUKHCONP03Z1STRF2055, DUKHCONP03Z1PLGF4310 | DUKHMOBP03PS00002310, DUKHCONP03Z1MSEX5005, DUKHCONP03Z1MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z1MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2013-12-28 | 2014-01-19 | 2013-12-28 | 2014-01-19 | 19 | No | DUKHCONP03MKMSEX5025, DUKHCONP03Z1MSEX5020, DUKHCONP03Z1MSEX5020 | DUKHCONP03Z1WTEX5060, DUKHCONP03Z1WTEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z1MSEX5010 | Telephone Cable laying | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 18 | No | DUKHCONP03Z1MSEX5005 | DUKHCONP03Z1ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L55.10 .25 .15 DOMESTIC WATER TANK & PUMP ROOM |  | 123 | 123 | 0% | 2013-09-30 | 2014-02-24 | 2013-09-30 | 2014-02-24 | 19 |  |  |  | 0 | 0
DUKHCONP03Z1WTEX5040 | Block works & Plastering | 25 | 25 | 0% | 2013-10-15 | 2013-11-14 | 2013-10-15 | 2013-11-14 | 63 | No | DUKHCONP03Z1WTEX5035, DUKHCONP03Z1WTEX5035 | DUKHCONP03Z1WTEX5080, DUKHCONP03Z1WTEX5045, DUKHCONP03Z1WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5035 | Construction of Raft & slab | 25 | 25 | 0% | 2013-10-06 | 2013-11-05 | 2013-10-06 | 2013-11-05 | 63 | No | DUKHCONP03Z1WTEX5030, DUKHCONP03Z1WTEX5030 | DUKHCONP03Z1WTEX5040, DUKHCONP03Z1WTEX5040 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5075 | Domestic Water Tank AC works | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 63 | No | DUKHCONP03Z1WTEX5070 | DUKHCONP03Z1WTEX5085 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5080 | Domestic Water Tank Electrical works | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 63 | No | DUKHCONP03Z1WTEX5040 | DUKHCONP03Z1WTEX5070 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5085 | Domestic Water Tank Firefighting works | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 63 | No | DUKHCONP03Z1WTEX5075 | DUKHCONP03Z1WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5070 | Domestic Water Tank Plumbings works | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 63 | No | DUKHCONP03Z1WTEX5080 | DUKHCONP03Z1WTEX5075 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5030 | Excavation | 20 | 20 | 0% | 2013-09-30 | 2013-10-24 | 2013-09-30 | 2013-10-24 | 63 | No | DUKHCONP03Z1STRF2065, DUKHCONP03Z1STRF2055, DUKHCONP03Z1STRF2055 | DUKHCONP03Z1WTEX5035, DUKHCONP03Z1WTEX5035, DUKHCONP03Z2WTEX5030 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5045 | Flooring & Painting | 25 | 25 | 0% | 2013-10-30 | 2013-11-27 | 2013-10-30 | 2013-11-27 | 63 | No | DUKHCONP03Z1WTEX5040, DUKHCONP03Z1WTEX5085, DUKHCONP03Z1WTEX5040 | DUKHCONP03Z1WTEX5050, DUKHCONP03Z1WTEX5050 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 19 | No | DUKHCONP03Z1PLRF4350, DUKHCONP03Z1WTEX5060, DUKHCONP03Z1WTEX5060, DUKHPROGEN00PRDV3330, DUKHCONP03Z1MSEX5015, DUKHCONP03Z1MSEX5015, DUKHCONP03Z1PLRF4350, DUKHPROGEN00PRDV3220 | DUKHCONP03Z2WTEX5065, DUKHCONP03Z1PLTC8005 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-01-08 | 2014-01-30 | 2014-01-08 | 2014-01-30 | 19 | No | DUKHPROGEN00PRDV3500, DUKHCONP03Z1WTEX5045, DUKHCONP03Z1WTEX5045, DUKHCONP03Z1MSEX5025 | DUKHCONP03Z1WTEX5060, DUKHCONP03Z1WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z1WTEX5060 | SS Shed cover installation | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 19 | No | DUKHCONP03Z1MSEX5025, DUKHCONP03Z1WTEX5050, DUKHCONP03Z1WTEX5050, DUKHPROGEN00PRDV3610 | DUKHCONP03Z1WTEX5065, DUKHCONP03Z1WTEX5065, DUKHCONP03Z2WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DHBL.K30.L55.10 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 0 |  |  |  | 0 | 0
DUKHCONP03Z1ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 0 | Yes | DUKHMOBP03PS00002310, DUKHCONP03MKELFF4065, DUKHCONP03MKACRF4635, DUKHCONP03MKACFF4625, DUKHCONP03MKELGF4015, DUKHCONP03MKELFF4050, DUKHCONP03Z1MSEX5005, DUKHCONP03MKARFF3395, DUKHMOBI03PS00002345, DUKHCONP03MKELGF4025, DUKHCONP03MKELFF4055, DUKHCONP03MKPLRF4350, DUKHCONP03MKARRF3620, DUKHCONP03MKAREL3680, DUKHCONP03MKPLRF4355, DUKHCONP03MKPLGF4320, DUKHCONP03Z1ACFF4625, DUKHCONP03MKELGF4030, DUKHCONP03Z1ACRF4635, DUKHCONP03MKARRF3655, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARFF3395, DUKHCONP03MKELRF4075, DUKHCONP03Z1ARRF3620, DUKHCONP03MKMSEX5005, DUKHCONP03Z1AREL3680, DUKHCONP03MKARGF3095 | DUKHCONP03Z2ACTC8000, DUKHHANP03GNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z1ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 0 | Yes | DUKHCONP03Z1ELGF4030, DUKHCONP03Z1ARRF3660, DUKHCONP03MKELFF4055, DUKHCONP03MKARRF3620, DUKHMOBP03PS00002310, DUKHCONP03MKACRF4635, DUKHCONP03Z1ELRF4075, DUKHCONP03Z1AREL3680, DUKHCONP03MKARGF3095, DUKHCONP03MKELGF4015, DUKHCONP03MKELGF4030, DUKHCONP03MKELFF4065, DUKHCONP03Z1ELFF4055, DUKHCONP03Z1ELFF4050, DUKHCONP03Z1ARFF3395, DUKHCONP03Z1ARRF3620, DUKHCONP03Z1ARRF3655, DUKHCONP03MKMSEX5005, DUKHCONP03MKARFF3395, DUKHCONP03MKARRF3655, DUKHCONP03MKELRF4075, DUKHCONP03MKPLRF4350, DUKHCONP03Z1MSEX5005, DUKHCONP03Z1ARGF3095, DUKHCONP03MKAREL3680, DUKHCONP03MKELGF4025, DUKHCONP03MKPLRF4355, DUKHCONP03MKPLGF4320, DUKHCONP03Z1ELFF4065, DUKHMOBI03PS00002345, DUKHCONP03MKELFF4050, DUKHCONP03Z1ELGF4025, DUKHCONP03Z1ELGF4015, DUKHCONP03MKACFF4625 | DUKHCONP03Z2ELTC8010, DUKHHANP03GNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z1PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 0 | Yes | DUKHCONP03Z1ARRF3655, DUKHMOBI03PS00002345, DUKHCONP03Z1PLRF4350, DUKHCONP03Z1PLGF4320, DUKHCONP03Z1ARRF3620, DUKHCONP03MKARGF3095, DUKHCONP03Z1ARGF3095, DUKHCONP03Z1ARRF3660, DUKHMOBP03PS00002310, DUKHCONP03MKPLRF4350, DUKHCONP03MKPLRF4355, DUKHCONP03MKPLGF4320, DUKHCONP03MKAREL3680, DUKHCONP03MKELFF4065, DUKHCONP03MKELFF4055, DUKHCONP03MKACRF4635, DUKHCONP03Z1MSEX5005, DUKHCONP03MKELRF4075, DUKHCONP03Z1ARFF3395, DUKHCONP03MKMSEX5005, DUKHCONP03MKELGF4025, DUKHCONP03MKELGF4015, DUKHCONP03MKELGF4030, DUKHCONP03MKACFF4625, DUKHCONP03Z1WTEX5065, DUKHCONP03Z1PLRF4355, DUKHCONP03MKARRF3655, DUKHCONP03MKELFF4050, DUKHCONP03Z1AREL3680, DUKHCONP03MKARFF3395, DUKHCONP03MKARRF3620 | DUKHHANP03GNPLTC9005, DUKHCONP03Z2PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L55.15 ZONE - 2 (3 Apartments) |  | 372 | 372 | 0% | 2013-02-28 | 2014-05-15 | 2013-02-28 | 2014-05-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.15 .10 STRUCTURAL WORKS |  | 230 | 230 | 0% | 2013-02-28 | 2013-11-28 | 2013-02-28 | 2013-11-28 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.15 .10 .10 SUB STRUCTURE |  | 117 | 117 | 0% | 2013-02-28 | 2013-07-14 | 2013-02-28 | 2013-07-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.15 .10 .10 .10 UPTO GRADE SLAB |  | 117 | 117 | 0% | 2013-02-28 | 2013-07-14 | 2013-02-28 | 2013-07-14 | 0 |  |  |  | 0 | 0
DUKHCONP03Z2STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-05-04 | 2013-06-01 | 2013-05-04 | 2013-06-01 | 0 | Yes | DUKHCONP03Z2STUG1030, DUKHCONP03Z1STUG1035, DUKHCONP03Z2STUG1030 | DUKHCONP03Z3STUG1035, DUKHCONP03Z2STUG1040, DUKHCONP03Z2STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-04-04 | 2013-04-27 | 2013-04-04 | 2013-04-27 | 0 | Yes | DUKHCONP03Z2STUG1015, DUKHCONP03Z2STUG1015 | DUKHCONP03Z2STUG1025, DUKHCONP03Z2STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-05-20 | 2013-06-17 | 2013-05-20 | 2013-06-17 | 0 | Yes | DUKHCONP03Z2STUG1035, DUKHCONP03Z2STUG1035 | DUKHCONP03Z2PLUG4300, DUKHCONP03Z2STUG1045, DUKHCONP03Z2PLUG4300, DUKHCONP03Z2STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-04-14 | 2013-05-12 | 2013-04-14 | 2013-05-12 | 0 | Yes | DUKHCONP03Z2STUG1020, DUKHCONP03Z2STUG1020, DUKHCONP03Z1STUG1025 | DUKHCONP03Z3STUG1025, DUKHCONP03Z2STUG1030, DUKHCONP03Z2STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-06-16 | 2013-07-14 | 2013-06-16 | 2013-07-14 | 0 | Yes | DUKHCONP03Z1STUG1045, DUKHCONP03Z2STUG1040, DUKHCONP03Z2PLUG4300, DUKHCONP03Z2PLUG4300, DUKHCONP03Z2STUG1040 | DUKHCONP03Z2STGF2000, DUKHCONP03Z2STGF2000, DUKHCONP03Z3STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-03-11 | 2013-04-06 | 2013-03-11 | 2013-04-06 | 0 | Yes | DUKHCONP03Z2STUG1000, DUKHCONP03Z2STUG1000 | DUKHCONP03Z2STUG1010, DUKHCONP03Z2STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-03-14 | 2013-04-09 | 2013-03-14 | 2013-04-09 | 0 | Yes | DUKHCONP03Z2STUG1005, DUKHCONP03Z2STUG1005 | DUKHCONP03Z2STUG1015, DUKHCONP03Z2STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-02-28 | 2013-03-28 | 2013-02-28 | 2013-03-28 | 0 | Yes | DUKHCONP03Z1STUG1000 | DUKHCONP03Z2STUG1005, DUKHCONP03Z3STUG1000, DUKHCONP03Z2STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-03-20 | 2013-04-17 | 2013-03-20 | 2013-04-17 | 0 | Yes | DUKHCONP03Z2STUG1010, DUKHCONP03Z2STUG1010 | DUKHCONP03Z2STUG1020, DUKHCONP03Z2STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z2STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-04-23 | 2013-05-21 | 2013-04-23 | 2013-05-21 | 0 | Yes | DUKHCONP03Z2STUG1025, DUKHCONP03Z2STUG1025 | DUKHCONP03Z2STUG1035, DUKHCONP03Z2STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L55.15 .10 .15 SUPERSTRUCTURE |  | 124 | 124 | 0% | 2013-07-02 | 2013-11-28 | 2013-07-02 | 2013-11-28 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.15 .10 .15 .10 GROUND FLOOR |  | 49 | 49 | 0% | 2013-07-02 | 2013-08-31 | 2013-07-02 | 2013-08-31 | 0 |  |  |  | 0 | 0
DUKHCONP03Z2STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-08-14 | 2013-08-31 | 2013-08-14 | 2013-08-31 | 0 | Yes | DUKHCONP03Z2STGF2010, DUKHCONP03Z1STGF2015, DUKHCONP03Z2STGF2010 | DUKHCONP03Z2ARGF3000, DUKHCONP03Z2STFF2020, DUKHCONP03Z2ARGF3000, DUKHCONP03Z2STFF2020, DUKHCONP03Z3STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-07-27 | 2013-08-27 | 2013-07-27 | 2013-08-27 | 0 | Yes | DUKHCONP03Z2STGF2005, DUKHCONP03Z2STGF2005 | DUKHCONP03Z2STGF2015, DUKHCONP03Z2STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-07-11 | 2013-08-07 | 2013-07-11 | 2013-08-07 | 0 | Yes | DUKHCONP03Z2STGF2000, DUKHCONP03Z2STGF2000 | DUKHCONP03Z2STGF2010, DUKHCONP03Z2STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-07-02 | 2013-07-30 | 2013-07-02 | 2013-07-30 | 0 | Yes | DUKHCONP03Z2STUG1045, DUKHCONP03Z1STGF2000, DUKHCONP03Z2STUG1045 | DUKHCONP03Z2STGF2005, DUKHCONP03Z3STGF2000, DUKHCONP03Z2STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.15 .10 .15 .15 FIRST FLOORS |  | 55 | 55 | 0% | 2013-08-17 | 2013-10-21 | 2013-08-17 | 2013-10-21 | 0 |  |  |  | 0 | 0
DUKHCONP03Z2STFF2035 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-10-02 | 2013-10-21 | 2013-10-02 | 2013-10-21 | 0 | Yes | DUKHCONP03Z1STFF2035, DUKHCONP03Z2STFF2030, DUKHCONP03Z2STFF2030 | DUKHCONP03Z2STRF2040, DUKHCONP03Z2ARFF3300, DUKHCONP03Z2ARFF3300, DUKHCONP03Z2STRF2040, DUKHCONP03Z3STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-09-11 | 2013-10-09 | 2013-09-11 | 2013-10-09 | 0 | Yes | DUKHCONP03Z2STFF2025, DUKHCONP03Z2STFF2025 | DUKHCONP03Z2STFF2035, DUKHCONP03Z2STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-08-27 | 2013-09-23 | 2013-08-27 | 2013-09-23 | 0 | Yes | DUKHCONP03Z2STFF2020, DUKHCONP03Z2STFF2020 | DUKHCONP03Z2STFF2030, DUKHCONP03Z2STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-08-17 | 2013-09-14 | 2013-08-17 | 2013-09-14 | 0 | Yes | DUKHCONP03Z2STGF2015, DUKHCONP03Z2STGF2015, DUKHCONP03Z1STFF2020 | DUKHCONI03Z1DRGL5115, DUKHCONP03Z2STFF2025, DUKHCONP03Z3STFF2020, DUKHCONP03Z2STFF2025, DUKHCONP03Z2ARFF3300, DUKHCONP03Z2ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.15 .10 .15 .20 ROOF |  | 46 | 46 | 0% | 2013-10-05 | 2013-11-28 | 2013-10-05 | 2013-11-28 | 58 |  |  |  | 0 | 0
DUKHCONP03Z2STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-10-08 | 2013-10-29 | 2013-10-08 | 2013-10-29 | 51 | No | DUKHCONP03Z2STRF2040, DUKHCONP03Z2STRF2040 | DUKHCONP03Z2STRF2050, DUKHCONP03Z2STRF2050 | 0 | 0 | ROOF
DUKHCONP03Z2STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-10-05 | 2013-10-27 | 2013-10-05 | 2013-10-27 | 36 | No | DUKHCONP03Z2STFF2035, DUKHCONP03Z1STRF2040, DUKHCONP03Z2STFF2035 | DUKHCONP03Z2STRF2045, DUKHCONP03Z3STRF2040, DUKHCONP03Z2STRF2045 | 0 | 0 | ROOF
DUKHCONP03Z2STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 58 | No | DUKHCONP03Z2STRF2055, DUKHCONP03Z2STRF2055 | DUKHCONP03Z2ARRF3630, DUKHCONP03Z2ARRF3630, DUKHCONP03Z2STRF2065, DUKHCONP03Z2STRF2065 | 0 | 0 | ROOF
DUKHCONP03Z2STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-10-31 | 2013-11-28 | 2013-10-31 | 2013-11-28 | 58 | No | DUKHCONP03Z1STRF2065, DUKHCONP03Z2STRF2060, DUKHCONP03Z2STRF2060 | DUKHCONP03Z2WTEX5030, DUKHCONP03Z2ARRF3630, DUKHCONP03Z3STRF2065, DUKHCONP03Z2AREL3665, DUKHCONP03Z2AREL3665, DUKHCONP03Z2ARRF3630 | 0 | 0 | ROOF
DUKHCONP03Z2STRF2055 | Slab-Concrete | 13 | 13 | 0% | 2013-10-23 | 2013-11-06 | 2013-10-23 | 2013-11-06 | 51 | No | DUKHCONP03Z2STRF2050, DUKHCONP03Z2STRF2050, DUKHCONP03Z1STRF2055 | DUKHCONP03Z2WTEX5030, DUKHCONP03Z2WTEX5030, DUKHCONP03Z2MSEX5020, DUKHCONP03Z2ARRF3600, DUKHCONP03Z2MSEX5000, DUKHCONP03Z2MSEX5020, DUKHCONP03Z2STRF2060, DUKHCONP03Z3STRF2055, DUKHCONP03Z2ARRF3600, DUKHCONP03Z2STRF2060, DUKHCONP03Z2MSEX5000 | 0 | 0 | ROOF
DUKHCONP03Z2STRF2050 | Slab-Rebar & Formwork | 20 | 20 | 0% | 2013-10-10 | 2013-11-04 | 2013-10-10 | 2013-11-04 | 51 | No | DUKHCONP03Z2STRF2045, DUKHCONP03Z2STRF2045 | DUKHCONP03Z2STRF2055, DUKHCONP03Z2STRF2055 | 0 | 0 | ROOF
DHBL.K30.L55.15 .15 FINISHING WORKS |  | 180 | 180 | 0% | 2013-09-15 | 2014-04-16 | 2013-09-15 | 2014-04-16 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.15 .15 .10 INTERNAL FINISHES |  | 180 | 180 | 0% | 2013-09-15 | 2014-04-16 | 2013-09-15 | 2014-04-16 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.15 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-09-15 | 2014-03-01 | 2013-09-15 | 2014-03-01 | 40 |  |  |  | 0 | 0
DUKHCONP03Z2ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-01-02 | 2014-01-19 | 2014-01-02 | 2014-01-19 | 40 | No | DUKHCONP03Z2ARGF3065, DUKHCONP03Z2ARGF3065, DUKHCONP03Z1ARGF3070 | DUKHCONP03Z2ARGF3080, DUKHCONP03Z2ARGF3075, DUKHCONP03Z3ARGF3070, DUKHCONP03Z2ARGF3080, DUKHCONP03Z2ARGF3075, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 39 | No | DUKHCONP03Z2ARGF3045, DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ARGF3045, DUKHCONP03Z2ACGF4600 | DUKHCONP03Z2ACGF4605, DUKHCONP03Z2ELGF4025, DUKHCONP03Z2ACGF4605, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ELGF4015, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ELGF4015, DUKHCONP03Z2ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-01-09 | 2014-02-01 | 2014-01-09 | 2014-02-01 | 50 | No | DUKHCONP03Z2ARGF3070, DUKHCONP03Z2ARGF3070, DUKHCONP03Z1ARGF3080 | DUKHCONP03Z2ARGF3095, DUKHCONP03Z3ARGF3080, DUKHCONP03Z2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3000 | Block work | 25 | 25 | 0% | 2013-09-15 | 2013-10-13 | 2013-09-15 | 2013-10-13 | 35 | No | DUKHCONP03Z2STGF2015, DUKHCONP03Z2STGF2015, DUKHCONP03Z1ARGF3000 | DUKHCONP03Z2PLGF4310, DUKHCONP03Z3ARGF3000, DUKHCONP03Z2PLGF4305, DUKHCONP03Z2ELGF4000, DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ARGF3005, DUKHCONP03Z2PLGF4310, DUKHCONP03Z2PLGF4305, DUKHCONP03Z2ELGF4000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-01-08 | 2014-01-30 | 2014-01-08 | 2014-01-30 | 40 | No | DUKHCONP03Z2ARGF3070, DUKHCONP03Z1ARGF3075, DUKHCONP03Z2ARGF3070 | DUKHCONP03Z2ARGF3090, DUKHCONP03Z2ARGF3085, DUKHCONP03Z2ARGF3085, DUKHCONP03Z2ARGF3090, DUKHCONP03Z3ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-11-02 | 2013-11-30 | 2013-11-02 | 2013-11-30 | 35 | No | DUKHCONP03Z2ARGF3015, DUKHCONP03Z2PLGF4305, DUKHCONP03Z2PLGF4310, DUKHCONP03Z2PLGF4310, DUKHCONP03Z1ARGF3020, DUKHCONP03Z2PLGF4305, DUKHCONP03Z2ARGF3015 | DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3025, DUKHCONP03Z3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2013-12-04 | 2013-12-22 | 2013-12-04 | 2013-12-22 | 40 | No | DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3010, DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3010 | DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3050, DUKHCONP03Z2ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 40 | No | DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ARGF3080, DUKHCONP03Z2ARGF3090, DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3085, DUKHCONP03Z2ARGF3085, DUKHCONP03Z2ACGF4610, DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3070, DUKHCONP03Z2ARGF3070, DUKHCONP03Z2ARGF3030, DUKHCONP03Z1ARGF3095, DUKHCONP03Z2ARGF3030, DUKHCONP03Z2ARGF3080, DUKHCONP03Z2ARGF3090, DUKHCONP03Z2ACGF4610 | DUKHCONP03Z3ARGF3095, DUKHCONP03Z2PLTC8005, DUKHCONP03Z2ACTC8000, DUKHCONP03Z2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2013-11-25 | 2013-12-17 | 2013-11-25 | 2013-12-17 | 35 | No | DUKHCONP03Z2ARGF3030, DUKHCONP03Z1ARGF3045, DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ELGF4010, DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3030, DUKHCONP03Z2ELGF4010 | DUKHCONP03Z2ARGF3055, DUKHCONP03Z3ARGF3045, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-10-15 | 2013-11-10 | 2013-10-15 | 2013-11-10 | 43 | No | DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ARGF3005 | DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2013-12-12 | 2014-01-05 | 2013-12-12 | 2014-01-05 | 40 | No | DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3040 | DUKHCONP03Z2ARGF3065, DUKHCONP03Z2ARGF3065, DUKHCONP03Z2ARGF3085, DUKHCONP03Z2ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2013-12-07 | 2014-01-05 | 2013-12-07 | 2014-01-05 | 35 | No | DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ARGF3045, DUKHCONP03Z1ARGF3060, DUKHCONP03Z2ARGF3045 | DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ACGF4605, DUKHCONP03Z2ELGF4025, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ELGF4030, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ELGF4025, DUKHCONP03Z2ELGF4015, DUKHCONP03Z2PLGF4320, DUKHCONP03Z2ELGF4015, DUKHCONP03Z2PLGF4320, DUKHCONP03Z2ACGF4605, DUKHCONP03Z3ARGF3060, DUKHCONP03Z2ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-01-21 | 2014-02-06 | 2014-01-21 | 2014-02-06 | 40 | No | DUKHCONP03Z2ARGF3075, DUKHCONP03Z2ARGF3075 | DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-11-02 | 2013-11-30 | 2013-11-02 | 2013-11-30 | 43 | No | DUKHCONP03Z1ARGF3030, DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ARGF3005 | DUKHCONP03Z2ARGF3045, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3045, DUKHCONP03Z3ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-10-07 | 2013-11-06 | 2013-10-07 | 2013-11-06 | 35 | No | DUKHCONP03Z2ELGF4000, DUKHCONP03Z2PLGF4305, DUKHCONP03Z2PLGF4305, DUKHCONP03Z2ARGF3000, DUKHCONP03Z2ARGF3000, DUKHCONP03Z1ARGF3005, DUKHCONP03Z2ELGF4000 | DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ARGF3015, DUKHCONP03Z2ARGF3010, DUKHCONP03Z2ARGF3015, DUKHCONP03Z2ARGF3030, DUKHCONP03Z2ARGF3030, DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ARGF3010, DUKHCONP03Z3ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-11-07 | 2013-12-05 | 2013-11-07 | 2013-12-05 | 35 | No | DUKHCONP03Z2ARGF3010, DUKHCONP03Z2ARGF3020, DUKHCONP03Z2ARGF3020, DUKHCONP03Z1ARGF3025, DUKHCONP03Z2ARGF3010 | DUKHCONP03Z2ARGF3045, DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3045, DUKHCONP03Z2ARGF3040, DUKHCONP03Z3ARGF3025, DUKHCONP03Z2ARGF3050, DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-01-16 | 2014-02-08 | 2014-01-16 | 2014-02-08 | 45 | No | DUKHCONP03Z2ARGF3075, DUKHCONP03Z2ARGF3075, DUKHCONP03Z2ARGF3050, DUKHCONP03Z2ARGF3050 | DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2013-11-27 | 2013-12-14 | 2013-11-27 | 2013-12-14 | 42 | No | DUKHCONP03Z2ARGF3010, DUKHCONP03Z2ARGF3010, DUKHCONP03Z2ARGF3025, DUKHCONP03Z2ARGF3025 | DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3040, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARGF3065, DUKHCONP03Z2ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-10-27 | 2013-11-12 | 2013-10-27 | 2013-11-12 | 35 | No | DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ARGF3005, DUKHCONP03Z1ARGF3015 | DUKHCONP03Z2ARGF3020, DUKHCONP03Z3ARGF3015, DUKHCONP03Z2ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ARGF3065 | Wooden door | 15 | 15 | 0% | 2013-12-28 | 2014-01-13 | 2013-12-28 | 2014-01-13 | 40 | No | DUKHCONP03Z2ARGF3050, DUKHCONP03Z1ARGF3065, DUKHCONP03Z2ARGF3050, DUKHCONP03Z2ARGF3035, DUKHCONP03Z2ARGF3035 | DUKHCONP03Z2PLGF4315, DUKHCONP03Z2PLGF4315, DUKHCONP03Z2ARGF3070, DUKHCONP03Z2ARGF3070, DUKHCONP03Z3ARGF3065 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.15 .15 .10 .15 FIRST FLOORS |  | 144 | 144 | 0% | 2013-10-29 | 2014-04-16 | 2013-10-29 | 2014-04-16 | 0 |  |  |  | 0 | 0
DUKHCONP03Z2ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 0 | Yes | DUKHCONP03Z1ARFF3370, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ARFF3365 | DUKHCONP03Z2ARFF3375, DUKHCONP03Z2ARFF3380, DUKHCONP03Z2ARFF3380, DUKHCONP03Z2ARFF3375, DUKHCONP03Z3ARFF3370 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3355 | Aluminum tile false ceiling | 20 | 20 | 0% | 2014-01-26 | 2014-02-18 | 2014-01-26 | 2014-02-18 | 2 | No | DUKHCONP03Z2ACFF4615, DUKHCONP03Z2ACFF4615, DUKHCONP03Z2ARFF3345, DUKHCONP03Z2ARFF3345, DUKHCONP03Z1ARFF3360, DUKHCONP03Z1ARFF3355 | DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELFF4055, DUKHCONP03Z2ARFF3365, DUKHCONP03Z3ARFF3355, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2PLFF4340, DUKHCONP03Z2ACFF4620, DUKHCONP03Z2ELFF4050, DUKHCONP03Z2PLFF4340, DUKHCONP03Z2ACFF4620, DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ELFF4055, DUKHCONP03Z2ELFF4050 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-02-23 | 2014-03-17 | 2014-02-23 | 2014-03-17 | 11 | No | DUKHCONP03Z2ARFF3370, DUKHCONP03Z2ARFF3370 | DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3300 | Block work | 25 | 25 | 0% | 2013-10-29 | 2013-11-26 | 2013-10-29 | 2013-11-26 | 0 | Yes | DUKHCONP03Z2STFF2035, DUKHCONP03Z2STFF2035, DUKHCONP03Z1ARFF3300, DUKHCONP03Z2STFF2020, DUKHCONP03Z2STFF2020 | DUKHCONP03Z3ARFF3300, DUKHCONP03Z2PLFF4330, DUKHCONP03Z2ARFF3305, DUKHCONP03Z2PLFF4325, DUKHCONP03Z2PLFF4330, DUKHCONP03Z2ELFF4035, DUKHCONP03Z2ARFF3305, DUKHCONP03Z2PLFF4325, DUKHCONP03Z2ELFF4035 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 0 | Yes | DUKHCONP03Z2ARFF3370, DUKHCONP03Z1ARFF3375, DUKHCONP03Z2ARFF3370 | DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3385, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3385, DUKHCONP03Z2ARFF3390, DUKHCONP03Z3ARFF3375, DUKHCONP03Z2ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 0 | Yes | DUKHCONP03Z2ARFF3315, DUKHCONP03Z2PLFF4325, DUKHCONP03Z2PLFF4325, DUKHCONP03Z2PLFF4330, DUKHCONP03Z1ARFF3320, DUKHCONP03Z2ARFF3315, DUKHCONP03Z2PLFF4330 | DUKHCONP03Z2ARFF3325, DUKHCONP03Z3ARFF3320, DUKHCONP03Z2ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 0 | Yes | DUKHCONP03Z2ARFF3330, DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3375, DUKHCONP03Z2ARFF3330, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3375, DUKHCONP03Z2ARFF3390, DUKHCONP03Z2ARFF3385, DUKHCONP03Z2ACFF4625, DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3350, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3380, DUKHCONP03Z2ARFF3385, DUKHCONP03Z1ARFF3395, DUKHCONP03Z2ACFF4625, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ARFF3380, DUKHCONP03Z2ARFF3350, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ARFF3390 | DUKHCONP03Z2ELTC8010, DUKHCONP03Z3ARFF3395, DUKHCONP03Z2PLTC8005, DUKHCONP03Z2ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-01-14 | 2014-02-05 | 2014-01-14 | 2014-02-05 | 0 | Yes | DUKHCONP03Z2ELFF4045, DUKHCONP03Z2ARFF3330, DUKHCONP03Z2ARFF3330, DUKHCONP03Z1ARFF3345, DUKHCONP03Z2ELFF4045, DUKHCONP03Z2ARFF3325, DUKHCONP03Z2ARFF3325 | DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3355, DUKHCONP03Z3ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3310 | Flooring screed | 21 | 21 | 0% | 2013-12-01 | 2013-12-25 | 2013-12-01 | 2013-12-25 | 15 | No | DUKHCONP03Z2ARFF3305, DUKHCONP03Z2ARFF3305 | DUKHCONP03Z2ARFF3325, DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-01-21 | 2014-02-13 | 2014-01-21 | 2014-02-13 | 2 | No | DUKHCONP03Z2ARFF3325, DUKHCONP03Z2ARFF3325 | DUKHCONP03Z2ARFF3385, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 0 | Yes | DUKHCONP03Z2ARFF3345, DUKHCONP03Z2ARFF3345, DUKHCONP03Z2ACFF4615, DUKHCONP03Z2ACFF4615, DUKHCONP03Z1ARFF3360 | DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELFF4055, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ELFF4050, DUKHCONP03Z2ELFF4065, DUKHCONP03Z3ARFF3360, DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ACFF4620, DUKHCONP03Z2ELFF4050, DUKHCONP03Z2ELFF4055, DUKHCONP03Z2PLFF4340, DUKHCONP03Z2PLFF4340, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 0 | Yes | DUKHCONP03Z2ARFF3350, DUKHCONP03Z2ARFF3375, DUKHCONP03Z2ARFF3375, DUKHCONP03Z2ARFF3350 | DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-03-10 | 2014-04-01 | 2014-03-10 | 2014-04-01 | 0 | Yes | DUKHCONP03Z2ARFF3375, DUKHCONP03Z2ARFF3375 | DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3330 | Paint First coat | 25 | 25 | 0% | 2013-12-09 | 2014-01-07 | 2013-12-09 | 2014-01-07 | 18 | No | DUKHCONP03Z2ARFF3305, DUKHCONP03Z2ARFF3305 | DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3345, DUKHCONP03Z2ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3305 | Plastering work | 25 | 25 | 0% | 2013-11-23 | 2013-12-22 | 2013-11-23 | 2013-12-22 | 0 | Yes | DUKHCONP03Z2PLFF4325, DUKHCONP03Z2ELFF4035, DUKHCONP03Z2ARFF3300, DUKHCONP03Z2ARFF3300, DUKHCONP03Z2PLFF4325, DUKHCONP03Z2ELFF4035, DUKHCONP03Z1ARFF3305 | DUKHCONP03Z2AREL3665, DUKHCONP03Z2ARFF3315, DUKHCONP03Z2ACFF4615, DUKHCONP03Z2ARFF3330, DUKHCONP03Z2ARFF3330, DUKHCONP03Z2ACFF4615, DUKHCONP03Z3ARFF3305, DUKHCONP03Z2ARFF3310, DUKHCONP03Z2AREL3665, DUKHCONP03Z2ARFF3310, DUKHCONP03Z2ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-12-31 | 2014-01-28 | 2013-12-31 | 2014-01-28 | 0 | Yes | DUKHCONP03Z2ARFF3310, DUKHCONP03Z1ARFF3325, DUKHCONP03Z2ARFF3320, DUKHCONP03Z2ARFF3310, DUKHCONP03Z2ARFF3320 | DUKHCONP03Z2ARFF3350, DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3350, DUKHCONP03Z2ARFF3345, DUKHCONP03Z3ARFF3325, DUKHCONP03Z2ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-01-18 | 2014-02-03 | 2014-01-18 | 2014-02-03 | 10 | No | DUKHCONP03Z2ARFF3310, DUKHCONP03Z2ARFF3325, DUKHCONP03Z2ARFF3325, DUKHCONP03Z2ARFF3310 | DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2013-12-14 | 2013-12-31 | 2013-12-14 | 2013-12-31 | 0 | Yes | DUKHCONP03Z2ARFF3305, DUKHCONP03Z1ARFF3315, DUKHCONP03Z2ARFF3305 | DUKHCONP03Z2ARFF3320, DUKHCONP03Z3ARFF3315, DUKHCONP03Z2ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-02-06 | 2014-02-24 | 2014-02-06 | 2014-02-24 | 0 | Yes | DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3350, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3355, DUKHCONP03Z1ARFF3365, DUKHCONP03Z2ARFF3350, DUKHCONP03Z2ARFF3335, DUKHCONP03Z2ARFF3360 | DUKHCONP03Z3ARFF3365, DUKHCONP03Z2PLFF4335, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3370, DUKHCONP03Z2ARFF3370, DUKHCONP03Z2PLFF4335, DUKHCONP03Z2ARFF3395 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.15 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2013-11-17 | 2014-01-21 | 2013-11-17 | 2014-01-21 | 72 |  |  |  | 0 | 0
DUKHCONP03Z2ARRF3600 | Block work | 20 | 20 | 0% | 2013-11-17 | 2013-12-09 | 2013-11-17 | 2013-12-09 | 67 | No | DUKHCONP03Z1ARRF3600, DUKHCONP03Z2STRF2055, DUKHCONP03Z2STRF2055 | DUKHCONP03Z3ARRF3600, DUKHCONP03Z2ARRF3605, DUKHCONP03Z2ARRF3605 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3620 | Epoxy Painting | 15 | 15 | 0% | 2014-01-05 | 2014-01-21 | 2014-01-05 | 2014-01-21 | 72 | No | DUKHCONP03Z2ARRF3695, DUKHCONP03Z2ARRF3695 | DUKHCONP03Z2ACTC8000, DUKHCONP03Z2ELTC8010, DUKHCONP03Z2PLTC8005 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3610 | Flooring screed | 15 | 15 | 0% | 2013-12-09 | 2013-12-26 | 2013-12-09 | 2013-12-26 | 72 | No | DUKHCONP03Z2ARRF3605, DUKHCONP03Z2ARRF3605 | DUKHCONP03Z2ARRF3695, DUKHCONP03Z2ARRF3695 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3695 | Painting | 20 | 20 | 0% | 2013-12-17 | 2014-01-09 | 2013-12-17 | 2014-01-09 | 72 | No | DUKHCONP03Z2ARRF3610, DUKHCONP03Z2ARRF3610 | DUKHCONP03Z2AREL3680, DUKHCONP03Z2AREL3680, DUKHCONP03Z2ARRF3620, DUKHCONP03Z2ARRF3620 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3605 | Plastering work | 20 | 20 | 0% | 2013-11-25 | 2013-12-17 | 2013-11-25 | 2013-12-17 | 67 | No | DUKHCONP03Z2ARRF3600, DUKHCONP03Z2ARRF3600 | DUKHCONP03Z2ARRF3610, DUKHCONP03Z2AREL3665, DUKHCONP03Z2PLRF4345, DUKHCONP03Z2PLRF4345, DUKHCONP03Z2ARRF3610 | 0 | 0 | ROOF
DHBL.K30.L55.15 .15 .15 EXTERNAL FINISHES |  | 75 | 75 | 0% | 2013-11-23 | 2014-02-19 | 2013-11-23 | 2014-02-19 | 48 |  |  |  | 0 | 0
DHBL.K30.L55.15 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2013-11-23 | 2014-01-27 | 2013-11-23 | 2014-01-27 | 67 |  |  |  | 0 | 0
DUKHCONP03Z2ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 62 | No | DUKHCONP03Z2ARRF3645, DUKHCONP03Z2ARRF3645 | DUKHCONP03Z2ARRF3655, DUKHCONP03Z2ARRF3655 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-01-11 | 2014-01-27 | 2014-01-11 | 2014-01-27 | 67 | No | DUKHCONP03Z2ARRF3655, DUKHCONP03Z2ARRF3655 | DUKHCONP03Z2ELTC8010, DUKHCONP03Z2ACTC8000, DUKHCONP03Z2PLTC8005 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2013-12-01 | 2013-12-30 | 2013-12-01 | 2013-12-30 | 62 | No | DUKHCONP03Z2ARRF3635, DUKHCONP03Z2ARRF3635 | DUKHCONP03Z2ARRF3645, DUKHCONP03Z2ARRF3645 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2013-12-30 | 2014-01-21 | 2013-12-30 | 2014-01-21 | 62 | No | DUKHCONP03Z1ARRF3655, DUKHCONP03Z2ARRF3650, DUKHCONP03Z2ARRF3650, DUKHCONP03Z2ARRF3645, DUKHCONP03Z2ARRF3645 | DUKHCONP03Z2ARRF3660, DUKHCONP03Z3ARRF3655, DUKHCONP03Z2PLRF4355, DUKHCONP03Z2PLRF4355, DUKHCONP03Z2ARRF3660, DUKHCONP03Z2ELTC8010, DUKHCONP03Z2PLTC8005 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2013-11-26 | 2013-12-25 | 2013-11-26 | 2013-12-25 | 62 | No | DUKHCONP03Z2ARRF3630, DUKHCONP03Z2ARRF3630 | DUKHCONP03Z2ARRF3640, DUKHCONP03Z2ARRF3640 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2013-11-23 | 2013-12-22 | 2013-11-23 | 2013-12-22 | 62 | No | DUKHCONP03Z2STRF2065, DUKHCONP03Z2STRF2060, DUKHCONP03Z1ARRF3630, DUKHCONP03Z2STRF2060, DUKHCONP03Z2STRF2065 | DUKHCONP03Z3ARRF3630, DUKHCONP03Z2ARRF3635, DUKHCONP03Z2ARRF3635 | 0 | 0 | ROOF
DUKHCONP03Z2ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 62 | No | DUKHCONP03Z2ARRF3640, DUKHCONP03Z2ARRF3640 | DUKHCONP03Z2ARRF3650, DUKHCONP03Z2ACRF4630, DUKHCONP03Z2ELRF4070, DUKHCONP03Z2PLRF4350, DUKHCONP03Z2ACRF4630, DUKHCONP03Z2ELRF4070, DUKHCONP03Z2ARRF3655, DUKHCONP03Z2PLRF4350, DUKHCONP03Z2ARRF3650, DUKHCONP03Z2ARRF3655 | 0 | 0 | ROOF
DHBL.K30.L55.15 .15 .15 .15 ELEVATION |  | 52 | 52 | 0% | 2013-12-21 | 2014-02-19 | 2013-12-21 | 2014-02-19 | 48 |  |  |  | 0 | 0
DUKHCONP03Z2AREL3680 | External Painting | 20 | 20 | 0% | 2014-01-27 | 2014-02-19 | 2014-01-27 | 2014-02-19 | 48 | No | DUKHCONP03Z2AREL3675, DUKHCONP03Z1AREL3680, DUKHCONP03Z2AREL3675, DUKHCONP03Z2ARRF3695, DUKHCONP03Z2ARRF3695 | DUKHCONP03Z2PLTC8005, DUKHCONP03Z3AREL3680, DUKHCONP03Z2ACTC8000, DUKHCONP03Z2ELTC8010 | 0 | 0 | ELEVATION
DUKHCONP03Z2AREL3665 | External Plastering | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 53 | No | DUKHCONP03Z2ARFF3305, DUKHCONP03Z1AREL3665, DUKHCONP03Z2ARRF3605, DUKHCONP03Z2STRF2065, DUKHCONP03Z2STRF2065, DUKHCONP03Z2ARFF3305 | DUKHCONP03Z2AREL3675, DUKHCONP03Z2PLRF4350, DUKHCONP03Z2PLRF4350, DUKHCONP03Z3AREL3665, DUKHCONP03Z2AREL3675 | 0 | 0 | ELEVATION
DUKHCONP03Z2AREL3675 | GRC Panel Works | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 55 | No | DUKHCONP03Z2AREL3665, DUKHCONP03Z2AREL3665, DUKHCONP03Z1AREL3675 | DUKHCONP03Z2AREL3680, DUKHCONP03Z3AREL3675, DUKHCONP03Z2AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L55.15 .20 MEP WORKS |  | 261 | 261 | 0% | 2013-06-06 | 2014-04-14 | 2013-06-06 | 2014-04-14 | 2 |  |  |  | 0 | 0
DHBL.K30.L55.15 .20 .10 ELECTRICAL WORKS |  | 173 | 173 | 0% | 2013-09-21 | 2014-04-14 | 2013-09-21 | 2014-04-14 | 2 |  |  |  | 0 | 0
DHBL.K30.L55.15 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-09-21 | 2014-01-30 | 2013-09-21 | 2014-01-30 | 37 |  |  |  | 0 | 0
DUKHCONP03Z2ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-10-02 | 2013-10-27 | 2013-10-02 | 2013-10-27 | 62 | No | DUKHCONP03Z1ELGF4005, DUKHCONP03Z2ELGF4000, DUKHCONP03Z2ELGF4000 | DUKHCONP03Z3ELGF4005, DUKHCONP03Z2ELGF4010, DUKHCONP03Z2ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-09-21 | 2013-10-21 | 2013-09-21 | 2013-10-21 | 44 | No | DUKHCONP03Z2ARGF3000, DUKHCONP03Z2ARGF3000 | DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ELGF4005, DUKHCONP03Z2ELGF4005, DUKHCONP03Z2ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2013-12-15 | 2014-01-13 | 2013-12-15 | 2014-01-13 | 49 | No | DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ARGF3060, DUKHCONP03Z1ELGF4015 | DUKHCONP03Z2ELFF4055, DUKHCONP03Z3ELGF4015, DUKHCONP03Z2ELFF4055, DUKHCONP03Z2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2013-12-22 | 2014-01-13 | 2013-12-22 | 2014-01-13 | 36 | No | DUKHCONP03Z2ELGF4010, DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ELGF4010, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ARGF3055 | DUKHCONP03Z2ELGF4030, DUKHCONP03Z2ELGF4030, DUKHCONP03Z2ELGF4025, DUKHCONP03Z2ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 37 | No | DUKHCONP03Z1ELGF4025, DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ARGF3055 | DUKHCONP03Z3ELGF4025, DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-01-02 | 2014-01-25 | 2014-01-02 | 2014-01-25 | 36 | No | DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ARGF3060, DUKHCONP03Z1ELGF4030 | DUKHCONP03Z2ELFF4050, DUKHCONP03Z2ELTC8010, DUKHCONP03Z2ELFF4050, DUKHCONP03Z3ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-10-10 | 2013-11-10 | 2013-10-10 | 2013-11-10 | 62 | No | DUKHCONP03Z2ELGF4005, DUKHCONP03Z2ELGF4005 | DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ELGF4020, DUKHCONP03Z2ARGF3045, DUKHCONP03Z2ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.15 .20 .10 .15 FIRST FLOORS |  | 116 | 116 | 0% | 2013-11-04 | 2014-03-20 | 2013-11-04 | 2014-03-20 | 5 |  |  |  | 0 | 0
DUKHCONP03Z2ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-11-16 | 2013-12-08 | 2013-11-16 | 2013-12-08 | 33 | No | DUKHCONP03Z2ELFF4035, DUKHCONP03Z2ELFF4035 | DUKHCONP03Z2ELFF4045, DUKHCONP03Z2ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-11-04 | 2013-12-02 | 2013-11-04 | 2013-12-02 | 11 | No | DUKHCONP03Z2ARFF3300, DUKHCONP03Z2ARFF3300 | DUKHCONP03Z2ARFF3305, DUKHCONP03Z2ELFF4040, DUKHCONP03Z2ARFF3305, DUKHCONP03Z2ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 12 | No | DUKHCONP03Z2ELGF4015, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ELGF4015, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z1ELFF4055 | DUKHCONP03Z3ELFF4055, DUKHCONP03Z2ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-02-06 | 2014-03-02 | 2014-02-06 | 2014-03-02 | 1 | No | DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ELFF4045, DUKHCONP03Z2ELFF4045, DUKHCONP03Z2ARFF3360, DUKHCONP03Z1ELFF4060, DUKHCONP03Z2ARFF3355 | DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELFF4065, DUKHCONP03Z3ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 1 | No | DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ELGF4025, DUKHCONP03Z2ARFF3360, DUKHCONP03Z1ELFF4065, DUKHCONP03Z2ELGF4025 | DUKHCONP03Z2ELRF4070, DUKHCONP03Z2ELTC8010, DUKHCONP03Z3ELFF4065, DUKHCONP03Z2ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 21 | No | DUKHCONP03Z2ELGF4030, DUKHCONP03Z2MSEX5010, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ELGF4030, DUKHCONP03Z2ARFF3355 | DUKHCONP03Z2ELTC8010, DUKHCONP03Z2ELRF4070, DUKHCONP03Z2ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-11-27 | 2013-12-26 | 2013-11-27 | 2013-12-26 | 30 | No | DUKHCONP03Z2ELFF4040, DUKHCONP03Z2ELFF4040, DUKHCONP03Z1ELFF4045 | DUKHCONP03Z2ARFF3345, DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ELFF4060, DUKHCONP03Z2ELRF4070, DUKHCONP03Z2ELRF4070, DUKHCONP03Z3ELFF4045, DUKHCONP03Z2ARFF3345 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.15 .20 .10 .20 ROOF |  | 29 | 29 | 0% | 2014-03-12 | 2014-04-14 | 2014-03-12 | 2014-04-14 | 2 |  |  |  | 0 | 0
DUKHCONP03Z2ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-03-12 | 2014-04-01 | 2014-03-12 | 2014-04-01 | 2 | No | DUKHCONP03Z2ARRF3645, DUKHCONP03Z2ELFF4045, DUKHCONP03Z2ELFF4050, DUKHCONP03Z2ARRF3645, DUKHCONP03Z2ELFF4045, DUKHCONP03Z2ELFF4050, DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELFF4065 | DUKHCONP03Z2ELRF4075, DUKHCONP03Z2ELRF4075 | 0 | 0 | ROOF
DUKHCONP03Z2ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-03-19 | 2014-04-14 | 2014-03-19 | 2014-04-14 | 2 | No | DUKHCONP03Z2ELRF4070, DUKHCONP03Z2ELRF4070 | DUKHCONP03Z2ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L55.15 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 249 | 249 | 0% | 2013-06-06 | 2014-03-31 | 2013-06-06 | 2014-03-31 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.15 .20 .15 .10 GROUND FLOOR |  | 199 | 199 | 0% | 2013-06-06 | 2014-01-30 | 2013-06-06 | 2014-01-30 | 64 |  |  |  | 0 | 0
DUKHCONP03Z2PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-06-06 | 2013-06-29 | 2013-06-06 | 2013-06-29 | 0 | Yes | DUKHCONP03Z2STUG1040, DUKHCONP03Z2STUG1040 | DUKHCONP03Z2STUG1045, DUKHCONP03Z2STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-10-01 | 2013-10-23 | 2013-10-01 | 2013-10-23 | 56 | No | DUKHCONP03Z2PLGF4305, DUKHCONP03Z2ARGF3000, DUKHCONP03Z2ARGF3000, DUKHCONP03Z2PLGF4305 | DUKHCONP03Z2PLGF4315, DUKHCONP03Z2ARGF3020, DUKHCONP03Z2ARGF3020, DUKHCONP03Z2PLGF4315, DUKHCONP03Z2MSEX5000, DUKHCONP03Z2MSEX5000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-10-01 | 2013-10-23 | 2013-10-01 | 2013-10-23 | 35 | No | DUKHCONP03Z1PLGF4305, DUKHCONP03Z2ARGF3000, DUKHCONP03Z2ARGF3000 | DUKHCONP03Z2PLGF4310, DUKHCONP03Z2ARGF3020, DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ARGF3020, DUKHCONP03Z3PLGF4305, DUKHCONP03Z2PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-01-14 | 2014-01-30 | 2014-01-14 | 2014-01-30 | 64 | No | DUKHCONP03Z2ARGF3060, DUKHCONP03Z2PLGF4315, DUKHCONP03Z1PLGF4320, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2PLGF4315 | DUKHCONP03Z2PLTC8005, DUKHCONP03Z3PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-01-02 | 2014-01-25 | 2014-01-02 | 2014-01-25 | 64 | No | DUKHCONP03Z2ARGF3065, DUKHCONP03Z2ARGF3065, DUKHCONP03Z2PLGF4310, DUKHCONP03Z2PLGF4310, DUKHCONP03Z1PLGF4315 | DUKHCONP03Z2PLGF4320, DUKHCONP03Z2PLGF4320, DUKHCONP03Z3PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.15 .20 .15 .15 FIRST FLOORS |  | 102 | 102 | 0% | 2013-11-13 | 2014-03-13 | 2013-11-13 | 2014-03-13 | 14 |  |  |  | 0 | 0
DUKHCONP03Z2PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2013-11-14 | 2013-12-04 | 2013-11-14 | 2013-12-04 | 26 | No | DUKHCONP03Z2ARFF3300, DUKHCONP03Z2PLFF4325, DUKHCONP03Z2ARFF3300, DUKHCONP03Z2PLFF4325, DUKHCONP03Z1PLFF4330 | DUKHCONP03Z2PLFF4335, DUKHCONP03Z2PLFF4335, DUKHCONP03Z2PLRF4350, DUKHCONP03Z2ARFF3320, DUKHCONP03Z2PLRF4350, DUKHCONP03Z3PLFF4330, DUKHCONP03Z2ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-11-13 | 2013-12-03 | 2013-11-13 | 2013-12-03 | 0 | Yes | DUKHCONP03Z2ARFF3300, DUKHCONP03Z2ARFF3300 | DUKHCONP03Z2ARFF3305, DUKHCONP03Z2PLFF4330, DUKHCONP03Z2PLFF4330, DUKHCONP03Z2ARFF3320, DUKHCONP03Z2ARFF3320, DUKHCONP03Z2ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-02-25 | 2014-03-13 | 2014-02-25 | 2014-03-13 | 14 | No | DUKHCONP03Z1PLFF4340, DUKHCONP03Z2PLFF4335, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2PLFF4335 | DUKHCONP03Z3PLFF4340, DUKHCONP03Z2PLRF4355, DUKHCONP03Z2PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-02-13 | 2014-03-08 | 2014-02-13 | 2014-03-08 | 14 | No | DUKHCONP03Z2PLFF4330, DUKHCONP03Z2PLFF4330, DUKHCONP03Z2ARFF3365, DUKHCONP03Z2ARFF3365 | DUKHCONP03Z2PLFF4340, DUKHCONP03Z2PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.15 .20 .15 .20 ROOF |  | 95 | 95 | 0% | 2013-12-09 | 2014-03-31 | 2013-12-09 | 2014-03-31 | 14 |  |  |  | 0 | 0
DUKHCONP03Z2PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2013-12-09 | 2013-12-26 | 2013-12-09 | 2013-12-26 | 71 | No | DUKHCONP03Z2ARRF3605, DUKHCONP03Z2ARRF3605 | DUKHCONP03Z2PLRF4350, DUKHCONP03Z2PLRF4350, DUKHCONP03Z2PLRF4355, DUKHCONP03Z2PLRF4355 | 0 | 0 | ROOF
DUKHCONP03Z2PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-01-09 | 2014-01-26 | 2014-01-09 | 2014-01-26 | 53 | No | DUKHCONP03Z1PLRF4350, DUKHCONP03Z2PLFF4330, DUKHCONP03Z2PLFF4330, DUKHCONP03Z2AREL3665, DUKHCONP03Z2AREL3665, DUKHCONP03Z2ARRF3645, DUKHCONP03Z2PLRF4345, DUKHCONP03Z2PLRF4345, DUKHCONP03Z2ARRF3645 | DUKHCONP03Z2WTEX5065, DUKHCONP03Z2PLRF4355, DUKHCONP03Z2PLRF4355, DUKHCONP03Z3PLRF4350, DUKHCONP03Z2PLTC8005, DUKHCONP03Z2WTEX5065 | 0 | 0 | ROOF
DUKHCONP03Z2PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 14 | No | DUKHCONP03Z2PLFF4340, DUKHCONP03Z1PLRF4355, DUKHCONP03Z2ARRF3655, DUKHCONP03Z2ARRF3655, DUKHCONP03Z2PLRF4350, DUKHCONP03Z2PLRF4350, DUKHCONP03Z2PLRF4345, DUKHCONP03Z2PLRF4345, DUKHCONP03Z2PLFF4340 | DUKHCONP03Z3PLRF4355, DUKHCONP03Z2PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L55.15 .20 .20 AC WORKS |  | 135 | 135 | 0% | 2013-10-23 | 2014-03-31 | 2013-10-23 | 2014-03-31 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.15 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-10-23 | 2014-01-28 | 2013-10-23 | 2014-01-28 | 51 |  |  |  | 0 | 0
DUKHCONP03Z2ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-01-06 | 2014-01-28 | 2014-01-06 | 2014-01-28 | 51 | No | DUKHCONP03Z1ACGF4610, DUKHCONP03Z2ACGF4605, DUKHCONP03Z2ACGF4605 | DUKHCONP03Z2ACRF4635, DUKHCONP03Z3ACGF4610, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ACRF4635, DUKHCONP03Z2ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2013-12-15 | 2014-01-13 | 2013-12-15 | 2014-01-13 | 51 | No | DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ARGF3060, DUKHCONP03Z1ACGF4605 | DUKHCONP03Z2ACGF4610, DUKHCONP03Z3ACGF4605, DUKHCONP03Z2ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z2ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-10-23 | 2013-11-14 | 2013-10-23 | 2013-11-14 | 66 | No | DUKHCONP03Z2ARGF3005, DUKHCONP03Z2ARGF3005, DUKHCONP03Z1ACGF4600 | DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ACRF4630, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ACGF4605, DUKHCONP03Z2ARGF3060, DUKHCONP03Z2ACGF4605, DUKHCONP03Z2ARGF3055, DUKHCONP03Z2ACRF4630, DUKHCONP03Z3ACGF4600 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.15 .20 .20 .15 FIRST FLOORS |  | 87 | 87 | 0% | 2013-12-07 | 2014-03-19 | 2013-12-07 | 2014-03-19 | 9 |  |  |  | 0 | 0
DUKHCONP03Z2ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-02-25 | 2014-03-19 | 2014-02-25 | 2014-03-19 | 9 | No | DUKHCONP03Z2ACFF4620, DUKHCONP03Z2ACFF4620, DUKHCONP03Z1ACFF4625 | DUKHCONP03Z3ACFF4625, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ACTC8000, DUKHCONP03Z2ACRF4635, DUKHCONP03Z2ACRF4635 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 9 | No | DUKHCONP03Z2ACFF4615, DUKHCONP03Z1ACFF4620, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ACFF4615, DUKHCONP03Z2ARFF3360 | DUKHCONP03Z3ACFF4620, DUKHCONP03Z2ACFF4625, DUKHCONP03Z2ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z2ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2013-12-07 | 2013-12-30 | 2013-12-07 | 2013-12-30 | 32 | No | DUKHCONP03Z2ARFF3305, DUKHCONP03Z1ACFF4615, DUKHCONP03Z2ARFF3305 | DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ACRF4630, DUKHCONP03Z3ACFF4615, DUKHCONP03Z2ARFF3355, DUKHCONP03Z2ACFF4620, DUKHCONP03Z2ACRF4630, DUKHCONP03Z2ARFF3360, DUKHCONP03Z2ACFF4620, DUKHCONP03Z2ARFF3360 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.15 .20 .20 .20 ROOF |  | 89 | 89 | 0% | 2013-12-16 | 2014-03-31 | 2013-12-16 | 2014-03-31 | 14 |  |  |  | 0 | 0
DUKHCONP03Z2ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 14 | No | DUKHCONP03Z1ACRF4635, DUKHCONP03Z2ACGF4610, DUKHCONP03Z2ACRF4630, DUKHCONP03Z2ACFF4625, DUKHCONP03Z2ACFF4625, DUKHCONP03Z2ACRF4630, DUKHCONP03Z2ACGF4610 | DUKHCONP03Z3ACRF4635, DUKHCONP03Z2ACTC8000 | 0 | 0 | ROOF
DUKHCONP03Z2ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2013-12-16 | 2014-01-14 | 2013-12-16 | 2014-01-14 | 73 | No | DUKHCONP03Z2ACFF4615, DUKHCONP03Z2ACGF4600, DUKHCONP03Z2ARRF3645, DUKHCONP03Z2ACFF4615, DUKHCONP03Z2ARRF3645, DUKHCONP03Z2ACGF4600, DUKHCONP03Z1ACRF4630 | DUKHCONP03Z2ACRF4635, DUKHCONP03Z3ACRF4630, DUKHCONP03Z2ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L55.15 .25 EXTERNAL WORKS |  | 125 | 125 | 0% | 2013-10-29 | 2014-03-25 | 2013-10-29 | 2014-03-25 | 19 |  |  |  | 0 | 0
DHBL.K30.L55.15 .25 .10 MISCELLANEOUS |  | 93 | 93 | 0% | 2013-10-29 | 2014-02-16 | 2013-10-29 | 2014-02-16 | 33 |  |  |  | 0 | 0
DUKHCONP03Z2MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-11-12 | 2013-12-10 | 2013-11-12 | 2013-12-10 | 52 | No | DUKHCONP03Z2MSEX5000, DUKHCONP03Z2MSEX5000 | DUKHCONP03Z2PLTC8005, DUKHCONP03Z2MSEX5015, DUKHCONP03Z2ELTC8010, DUKHCONP03Z2MSEX5015, DUKHCONP03Z2ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z2MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 21 | No | DUKHCONP03Z2STRF2055, DUKHCONP03Z2STRF2055, DUKHCONP03Z1MSEX5020 | DUKHCONP03Z3MSEX5020, DUKHCONP03Z2MSEX5025, DUKHCONP03Z2MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z2MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2013-12-02 | 2013-12-25 | 2013-12-02 | 2013-12-25 | 52 | No | DUKHCONP03Z2MSEX5005, DUKHCONP03Z2MSEX5005 | DUKHCONP03Z2WTEX5065, DUKHCONP03Z2WTEX5065, DUKHCONP03Z2MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z2MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-10-29 | 2013-11-26 | 2013-10-29 | 2013-11-26 | 52 | No | DUKHCONP03Z2STRF2055, DUKHCONP03Z2PLGF4310, DUKHCONP03Z2PLGF4310, DUKHCONP03Z2STRF2055 | DUKHCONP03Z2MSEX5005, DUKHCONP03Z2MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z2MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-01-23 | 2014-02-16 | 2014-01-23 | 2014-02-16 | 21 | No | DUKHCONP03Z2MSEX5020, DUKHCONP03Z2MSEX5020 | DUKHCONP03Z2WTEX5060, DUKHCONP03Z2WTEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z2MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2013-12-26 | 2014-01-23 | 2013-12-26 | 2014-01-23 | 52 | No | DUKHCONP03Z2MSEX5015 | DUKHCONP03Z2ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L55.15 .25 .15 DOMESTIC WATER TANK & PUMP ROOM |  | 118 | 118 | 0% | 2013-11-06 | 2014-03-25 | 2013-11-06 | 2014-03-25 | 19 |  |  |  | 0 | 0
DUKHCONP03Z2WTEX5040 | Block works & Plastering | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 58 | No | DUKHCONP03Z2WTEX5035, DUKHCONP03Z2WTEX5035 | DUKHCONP03Z2WTEX5080, DUKHCONP03Z2WTEX5045, DUKHCONP03Z2WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5035 | Construction of Raft | 25 | 25 | 0% | 2013-11-12 | 2013-12-10 | 2013-11-12 | 2013-12-10 | 58 | No | DUKHCONP03Z2WTEX5030, DUKHCONP03Z2WTEX5030 | DUKHCONP03Z2WTEX5040, DUKHCONP03Z2WTEX5040 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5075 | Domestic Water Tank AC works | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 58 | No | DUKHCONP03Z2WTEX5070 | DUKHCONP03Z2WTEX5085 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5080 | Domestic Water Tank Electrical works | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 58 | No | DUKHCONP03Z2WTEX5040 | DUKHCONP03Z2WTEX5070 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5085 | Domestic Water Tank Firefighting works | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 58 | No | DUKHCONP03Z2WTEX5075 | DUKHCONP03Z2WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5070 | Domestic Water Tank Plumbings works | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 58 | No | DUKHCONP03Z2WTEX5080 | DUKHCONP03Z2WTEX5075 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5030 | Excavation | 20 | 20 | 0% | 2013-11-06 | 2013-11-28 | 2013-11-06 | 2013-11-28 | 58 | No | DUKHCONP03Z2STRF2055, DUKHCONP03Z2STRF2055, DUKHCONP03Z2STRF2065, DUKHCONP03Z1WTEX5030 | DUKHCONP03Z3WTEX5030, DUKHCONP03Z2WTEX5035, DUKHCONP03Z2WTEX5035 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5045 | Flooring & Painting | 25 | 25 | 0% | 2013-12-04 | 2014-01-02 | 2013-12-04 | 2014-01-02 | 58 | No | DUKHCONP03Z2WTEX5040, DUKHCONP03Z2WTEX5040, DUKHCONP03Z2WTEX5085 | DUKHCONP03Z2WTEX5050, DUKHCONP03Z2WTEX5050 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 19 | No | DUKHCONP03Z2WTEX5060, DUKHCONP03Z2PLRF4350, DUKHCONP03Z1WTEX5065, DUKHCONP03Z2WTEX5060, DUKHCONP03Z2MSEX5015, DUKHCONP03Z2MSEX5015, DUKHCONP03Z2PLRF4350 | DUKHCONP03Z2PLTC8005, DUKHCONP03Z3WTEX5065 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-02-04 | 2014-02-27 | 2014-02-04 | 2014-02-27 | 21 | No | DUKHCONP03Z2WTEX5045, DUKHCONP03Z2MSEX5025, DUKHCONP03Z2WTEX5045 | DUKHCONP03Z2WTEX5060, DUKHCONP03Z2WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z2WTEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 19 | No | DUKHCONP03Z2WTEX5050, DUKHCONP03Z2WTEX5050, DUKHCONP03Z2MSEX5025, DUKHCONP03Z1WTEX5060 | DUKHCONP03Z2WTEX5065, DUKHCONP03Z2WTEX5065, DUKHCONP03Z3WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DHBL.K30.L55.15 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 0 |  |  |  | 0 | 0
DUKHCONP03Z2ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 0 | Yes | DUKHCONP03Z2ARRF3620, DUKHCONP03Z1ACTC8000, DUKHCONP03Z2AREL3680, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ACFF4625, DUKHCONP03Z2ARRF3660, DUKHCONP03Z2ACRF4635, DUKHCONP03Z2MSEX5005 | DUKHHANP03GNACTC9000, DUKHCONP03Z3ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z2ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 0 | Yes | DUKHCONP03Z2ARFF3395, DUKHCONP03Z2ELFF4050, DUKHCONP03Z2ELRF4075, DUKHCONP03Z2MSEX5005, DUKHCONP03Z2ELGF4030, DUKHCONP03Z1ELTC8010, DUKHCONP03Z2ARRF3620, DUKHCONP03Z2AREL3680, DUKHCONP03Z2ELGF4015, DUKHCONP03Z2ARRF3660, DUKHCONP03Z2ARRF3655, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2ELFF4065, DUKHCONP03Z2ELFF4055, DUKHCONP03Z2ELGF4025 | DUKHCONP03Z3ELTC8010, DUKHHANP03GNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z2PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 0 | Yes | DUKHCONP03Z2MSEX5005, DUKHCONP03Z2AREL3680, DUKHCONP03Z2ARGF3095, DUKHCONP03Z2WTEX5065, DUKHCONP03Z2PLRF4355, DUKHCONP03Z2PLGF4320, DUKHCONP03Z2ARRF3620, DUKHCONP03Z2ARFF3395, DUKHCONP03Z1PLTC8005, DUKHCONP03Z2ARRF3655, DUKHCONP03Z2ARRF3660, DUKHCONP03Z2PLRF4350 | DUKHHANP03GNPLTC9005, DUKHCONP03Z3PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L55.20 ZONE - 3 (3 Apartments) |  | 372 | 372 | 0% | 2013-03-30 | 2014-06-14 | 2013-03-30 | 2014-06-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.20 .10 STRUCTURAL WORKS |  | 230 | 230 | 0% | 2013-03-30 | 2013-12-29 | 2013-03-30 | 2013-12-29 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.20 .10 .10 SUB STRUCTURE |  | 117 | 117 | 0% | 2013-03-30 | 2013-08-15 | 2013-03-30 | 2013-08-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.20 .10 .10 .10 UPTO GRADE SLAB |  | 117 | 117 | 0% | 2013-03-30 | 2013-08-15 | 2013-03-30 | 2013-08-15 | 0 |  |  |  | 0 | 0
DUKHCONP03Z3STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-06-02 | 2013-06-30 | 2013-06-02 | 2013-06-30 | 0 | Yes | DUKHCONP03Z2STUG1035, DUKHCONP03Z3STUG1030, DUKHCONP03Z3STUG1030 | DUKHCONP03Z3STUG1040, DUKHCONP03Z3STUG1040, DUKHCONP03Z4STUG1035 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-05-04 | 2013-05-26 | 2013-05-04 | 2013-05-26 | 0 | Yes | DUKHCONP03Z3STUG1015, DUKHCONP03Z3STUG1015 | DUKHCONP03Z3STUG1025, DUKHCONP03Z3STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-06-18 | 2013-07-16 | 2013-06-18 | 2013-07-16 | 0 | Yes | DUKHCONP03Z3STUG1035, DUKHCONP03Z3STUG1035 | DUKHCONP03Z3PLUG4300, DUKHCONP03Z3STUG1045, DUKHCONP03Z3PLUG4300, DUKHCONP03Z3STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-05-13 | 2013-06-10 | 2013-05-13 | 2013-06-10 | 0 | Yes | DUKHCONP03Z2STUG1025, DUKHCONP03Z3STUG1020, DUKHCONP03Z3STUG1020 | DUKHCONP03Z3STUG1030, DUKHCONP03Z4STUG1025, DUKHCONP03Z3STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-07-15 | 2013-08-15 | 2013-07-15 | 2013-08-15 | 0 | Yes | DUKHCONP03Z3PLUG4300, DUKHCONP03Z3PLUG4300, DUKHCONP03Z3STUG1040, DUKHCONP03Z2STUG1045, DUKHCONP03Z3STUG1040 | DUKHCONP03Z4STUG1045, DUKHCONP03Z3STGF2000, DUKHCONP03Z3STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-04-09 | 2013-05-05 | 2013-04-09 | 2013-05-05 | 0 | Yes | DUKHCONP03Z3STUG1000, DUKHCONP03Z3STUG1000 | DUKHCONP03Z3STUG1010, DUKHCONP03Z3STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-04-13 | 2013-05-08 | 2013-04-13 | 2013-05-08 | 0 | Yes | DUKHCONP03Z3STUG1005, DUKHCONP03Z3STUG1005 | DUKHCONP03Z3STUG1015, DUKHCONP03Z3STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-03-30 | 2013-04-27 | 2013-03-30 | 2013-04-27 | 0 | Yes | DUKHCONP03Z2STUG1000 | DUKHCONP03Z4STUG1000, DUKHCONP03Z3STUG1005, DUKHCONP03Z3STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-04-18 | 2013-05-16 | 2013-04-18 | 2013-05-16 | 0 | Yes | DUKHCONP03Z3STUG1010, DUKHCONP03Z3STUG1010 | DUKHCONP03Z3STUG1020, DUKHCONP03Z3STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z3STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-05-22 | 2013-06-19 | 2013-05-22 | 2013-06-19 | 0 | Yes | DUKHCONP03Z3STUG1025, DUKHCONP03Z3STUG1025 | DUKHCONP03Z3STUG1035, DUKHCONP03Z3STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L55.20 .10 .15 SUPERSTRUCTURE |  | 124 | 124 | 0% | 2013-07-31 | 2013-12-29 | 2013-07-31 | 2013-12-29 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.20 .10 .15 .10 GROUND FLOOR |  | 49 | 49 | 0% | 2013-07-31 | 2013-09-29 | 2013-07-31 | 2013-09-29 | 0 |  |  |  | 0 | 0
DUKHCONP03Z3STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-09-12 | 2013-09-29 | 2013-09-12 | 2013-09-29 | 0 | Yes | DUKHCONP03Z3STGF2010, DUKHCONP03Z3STGF2010, DUKHCONP03Z2STGF2015 | DUKHCONP03Z3STFF2020, DUKHCONP03Z3STFF2020, DUKHCONP03Z3ARGF3000, DUKHCONP03Z3ARGF3000, DUKHCONP03Z4STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-08-28 | 2013-09-25 | 2013-08-28 | 2013-09-25 | 0 | Yes | DUKHCONP03Z3STGF2005, DUKHCONP03Z3STGF2005 | DUKHCONP03Z3STGF2015, DUKHCONP03Z3STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-08-13 | 2013-09-09 | 2013-08-13 | 2013-09-09 | 0 | Yes | DUKHCONP03Z3STGF2000, DUKHCONP03Z3STGF2000 | DUKHCONP03Z3STGF2010, DUKHCONP03Z3STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-07-31 | 2013-09-01 | 2013-07-31 | 2013-09-01 | 0 | Yes | DUKHCONP03Z3STUG1045, DUKHCONP03Z2STGF2000, DUKHCONP03Z3STUG1045 | DUKHCONP03Z3STGF2005, DUKHCONP03Z4STGF2000, DUKHCONP03Z3STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.20 .10 .15 .15 FIRST FLOORS |  | 55 | 55 | 0% | 2013-09-15 | 2013-11-19 | 2013-09-15 | 2013-11-19 | 0 |  |  |  | 0 | 0
DUKHCONP03Z3STFF2035 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-11-03 | 2013-11-19 | 2013-11-03 | 2013-11-19 | 0 | Yes | DUKHCONP03Z3STFF2030, DUKHCONP03Z3STFF2030, DUKHCONP03Z2STFF2035 | DUKHCONP03Z3ARFF3300, DUKHCONP03Z3ARFF3300, DUKHCONP03Z4STFF2035, DUKHCONP03Z3STRF2040, DUKHCONP03Z3STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-10-10 | 2013-11-10 | 2013-10-10 | 2013-11-10 | 0 | Yes | DUKHCONP03Z3STFF2025, DUKHCONP03Z3STFF2025 | DUKHCONP03Z3STFF2035, DUKHCONP03Z3STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-09-25 | 2013-10-24 | 2013-09-25 | 2013-10-24 | 0 | Yes | DUKHCONP03Z3STFF2020, DUKHCONP03Z3STFF2020 | DUKHCONP03Z3STFF2030, DUKHCONP03Z3STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-09-15 | 2013-10-13 | 2013-09-15 | 2013-10-13 | 0 | Yes | DUKHCONP03Z3STGF2015, DUKHCONP03Z3STGF2015, DUKHCONP03Z2STFF2020 | DUKHCONP03Z3STFF2025, DUKHCONP03Z3ARFF3300, DUKHCONP03Z4STFF2020, DUKHCONP03Z3STFF2025, DUKHCONP03Z3ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.20 .10 .15 .20 ROOF |  | 46 | 46 | 0% | 2013-11-05 | 2013-12-29 | 2013-11-05 | 2013-12-29 | 58 |  |  |  | 0 | 0
DUKHCONP03Z3STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-11-09 | 2013-11-27 | 2013-11-09 | 2013-11-27 | 39 | No | DUKHCONP03Z3STRF2040, DUKHCONP03Z3STRF2040 | DUKHCONP03Z3STRF2050, DUKHCONP03Z3STRF2050 | 0 | 0 | ROOF
DUKHCONP03Z3STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-11-05 | 2013-11-25 | 2013-11-05 | 2013-11-25 | 29 | No | DUKHCONP03Z2STRF2040, DUKHCONP03Z3STFF2035, DUKHCONP03Z3STFF2035 | DUKHCONP03Z3STRF2045, DUKHCONP03Z3STRF2045, DUKHCONP03Z4STRF2040 | 0 | 0 | ROOF
DUKHCONP03Z3STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-11-24 | 2013-12-23 | 2013-11-24 | 2013-12-23 | 58 | No | DUKHCONP03Z3STRF2055, DUKHCONP03Z3STRF2055 | DUKHCONP03Z3STRF2065, DUKHCONP03Z3ARRF3630, DUKHCONP03Z3STRF2065, DUKHCONP03Z3ARRF3630 | 0 | 0 | ROOF
DUKHCONP03Z3STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 58 | No | DUKHCONP03Z3STRF2060, DUKHCONP03Z2STRF2065, DUKHCONP03Z3STRF2060 | DUKHCONP03Z3ARRF3630, DUKHCONP03Z4STRF2065, DUKHCONP03Z3WTEX5030, DUKHCONP03Z3AREL3665, DUKHCONP03Z3AREL3665, DUKHCONP03Z3ARRF3630 | 0 | 0 | ROOF
DUKHCONP03Z3STRF2055 | Slab-Concrete | 13 | 13 | 0% | 2013-11-21 | 2013-12-05 | 2013-11-21 | 2013-12-05 | 39 | No | DUKHCONP03Z2STRF2055, DUKHCONP03Z3STRF2050, DUKHCONP03Z3STRF2050 | DUKHCONP03Z3MSEX5000, DUKHCONP03Z4STRF2055, DUKHCONP03Z3MSEX5020, DUKHCONP03Z3WTEX5030, DUKHCONP03Z3ARRF3600, DUKHCONP03Z3STRF2060, DUKHCONP03Z3MSEX5000, DUKHCONP03Z3ARRF3600, DUKHCONP03Z3MSEX5020, DUKHCONP03Z3STRF2060, DUKHCONP03Z3WTEX5030 | 0 | 0 | ROOF
DUKHCONP03Z3STRF2050 | Slab-Rebar & Formwork | 20 | 20 | 0% | 2013-11-11 | 2013-12-03 | 2013-11-11 | 2013-12-03 | 39 | No | DUKHCONP03Z3STRF2045, DUKHCONP03Z3STRF2045 | DUKHCONP03Z3STRF2055, DUKHCONP03Z3STRF2055 | 0 | 0 | ROOF
DHBL.K30.L55.20 .15 FINISHING WORKS |  | 180 | 180 | 0% | 2013-10-14 | 2014-05-15 | 2013-10-14 | 2014-05-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.20 .15 .10 INTERNAL FINISHES |  | 180 | 180 | 0% | 2013-10-14 | 2014-05-15 | 2013-10-14 | 2014-05-15 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.20 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-10-14 | 2014-03-30 | 2013-10-14 | 2014-03-30 | 40 |  |  |  | 0 | 0
DUKHCONP03Z3ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-02-01 | 2014-02-18 | 2014-02-01 | 2014-02-18 | 40 | No | DUKHCONP03Z2ARGF3070, DUKHCONP03Z3ARGF3065, DUKHCONP03Z3ARGF3065 | DUKHCONP03Z3ARGF3075, DUKHCONP03Z3ARGF3080, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3080, DUKHCONP03Z3ARGF3075, DUKHCONP03Z3ARGF3095, DUKHCONP03Z4ARGF3070 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 38 | No | DUKHCONP03Z3ARGF3045, DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ARGF3045 | DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ACGF4605, DUKHCONP03Z3ELGF4015, DUKHCONP03Z3ELGF4025, DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ELGF4015, DUKHCONP03Z3ACGF4605, DUKHCONP03Z3ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-02-08 | 2014-03-03 | 2014-02-08 | 2014-03-03 | 50 | No | DUKHCONP03Z3ARGF3070, DUKHCONP03Z2ARGF3080, DUKHCONP03Z3ARGF3070 | DUKHCONP03Z4ARGF3080, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3000 | Block work | 25 | 25 | 0% | 2013-10-14 | 2013-11-13 | 2013-10-14 | 2013-11-13 | 35 | No | DUKHCONP03Z2ARGF3000, DUKHCONP03Z3STGF2015, DUKHCONP03Z3STGF2015 | DUKHCONP03Z4ARGF3000, DUKHCONP03Z3ARGF3005, DUKHCONP03Z3PLGF4305, DUKHCONP03Z3ARGF3005, DUKHCONP03Z3PLGF4310, DUKHCONP03Z3PLGF4310, DUKHCONP03Z3PLGF4305, DUKHCONP03Z3ELGF4000, DUKHCONP03Z3ELGF4000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-02-06 | 2014-03-02 | 2014-02-06 | 2014-03-02 | 40 | No | DUKHCONP03Z3ARGF3070, DUKHCONP03Z3ARGF3070, DUKHCONP03Z2ARGF3075 | DUKHCONP03Z3ARGF3090, DUKHCONP03Z3ARGF3090, DUKHCONP03Z3ARGF3085, DUKHCONP03Z4ARGF3075, DUKHCONP03Z3ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-12-01 | 2013-12-30 | 2013-12-01 | 2013-12-30 | 35 | No | DUKHCONP03Z3PLGF4305, DUKHCONP03Z2ARGF3020, DUKHCONP03Z3ARGF3015, DUKHCONP03Z3PLGF4305, DUKHCONP03Z3PLGF4310, DUKHCONP03Z3PLGF4310, DUKHCONP03Z3ARGF3015 | DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3025, DUKHCONP03Z4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-01-04 | 2014-01-20 | 2014-01-04 | 2014-01-20 | 40 | No | DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3010, DUKHCONP03Z3ARGF3010, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3035 | DUKHCONP03Z3ARGF3050, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 40 | No | DUKHCONP03Z2ARGF3095, DUKHCONP03Z3ACGF4610, DUKHCONP03Z3ARGF3070, DUKHCONP03Z3ACGF4610, DUKHCONP03Z3ARGF3030, DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3070, DUKHCONP03Z3ARGF3090, DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ARGF3030, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3080, DUKHCONP03Z3ARGF3085, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ARGF3080, DUKHCONP03Z3ARGF3090, DUKHCONP03Z3ARGF3085 | DUKHCONP03Z3ELTC8010, DUKHCONP03Z3ACTC8000, DUKHCONP03Z4ARGF3095, DUKHCONP03Z3PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2013-12-25 | 2014-01-16 | 2013-12-25 | 2014-01-16 | 35 | No | DUKHCONP03Z3ARGF3025, DUKHCONP03Z2ARGF3045, DUKHCONP03Z3ARGF3030, DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ELGF4010, DUKHCONP03Z3ELGF4010, DUKHCONP03Z3ARGF3030 | DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ARGF3060, DUKHCONP03Z4ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-11-16 | 2013-12-09 | 2013-11-16 | 2013-12-09 | 43 | No | DUKHCONP03Z3ARGF3005, DUKHCONP03Z3ARGF3005 | DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3035 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-01-12 | 2014-02-03 | 2014-01-12 | 2014-02-03 | 40 | No | DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3040 | DUKHCONP03Z3ARGF3085, DUKHCONP03Z3ARGF3065, DUKHCONP03Z3ARGF3065, DUKHCONP03Z3ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 35 | No | DUKHCONP03Z3ARGF3045, DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ACGF4600, DUKHCONP03Z2ARGF3060, DUKHCONP03Z3ARGF3045 | DUKHCONP03Z3PLGF4320, DUKHCONP03Z3ELGF4025, DUKHCONP03Z3ELGF4015, DUKHCONP03Z3ELGF4030, DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ELGF4030, DUKHCONP03Z4ARGF3060, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ELGF4025, DUKHCONP03Z3PLGF4320, DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ELGF4015, DUKHCONP03Z3ACGF4605, DUKHCONP03Z3ACGF4605, DUKHCONP03Z3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-02-20 | 2014-03-09 | 2014-02-20 | 2014-03-09 | 40 | No | DUKHCONP03Z3ARGF3075, DUKHCONP03Z3ARGF3075 | DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-12-01 | 2013-12-30 | 2013-12-01 | 2013-12-30 | 43 | No | DUKHCONP03Z3ARGF3005, DUKHCONP03Z2ARGF3030, DUKHCONP03Z3ARGF3005 | DUKHCONP03Z4ARGF3030, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3045, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-11-07 | 2013-12-05 | 2013-11-07 | 2013-12-05 | 35 | No | DUKHCONP03Z3ARGF3000, DUKHCONP03Z3ELGF4000, DUKHCONP03Z3PLGF4305, DUKHCONP03Z3ARGF3000, DUKHCONP03Z3ELGF4000, DUKHCONP03Z2ARGF3005, DUKHCONP03Z3PLGF4305 | DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ARGF3015, DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ARGF3010, DUKHCONP03Z3ARGF3010, DUKHCONP03Z3ARGF3030, DUKHCONP03Z4ARGF3005, DUKHCONP03Z3ARGF3015, DUKHCONP03Z3ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2013-12-07 | 2014-01-05 | 2013-12-07 | 2014-01-05 | 35 | No | DUKHCONP03Z3ARGF3020, DUKHCONP03Z3ARGF3020, DUKHCONP03Z3ARGF3010, DUKHCONP03Z2ARGF3025, DUKHCONP03Z3ARGF3010 | DUKHCONP03Z3ARGF3045, DUKHCONP03Z3ARGF3050, DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3040, DUKHCONP03Z4ARGF3025, DUKHCONP03Z3ARGF3050, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 45 | No | DUKHCONP03Z3ARGF3050, DUKHCONP03Z3ARGF3075, DUKHCONP03Z3ARGF3050, DUKHCONP03Z3ARGF3075 | DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2013-12-28 | 2014-01-13 | 2013-12-28 | 2014-01-13 | 42 | No | DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3025, DUKHCONP03Z3ARGF3010, DUKHCONP03Z3ARGF3010 | DUKHCONP03Z3ARGF3065, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3040, DUKHCONP03Z3ARGF3065, DUKHCONP03Z3ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-11-25 | 2013-12-11 | 2013-11-25 | 2013-12-11 | 35 | No | DUKHCONP03Z3ARGF3005, DUKHCONP03Z2ARGF3015, DUKHCONP03Z3ARGF3005 | DUKHCONP03Z3ARGF3020, DUKHCONP03Z4ARGF3015, DUKHCONP03Z3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ARGF3065 | Wooden door | 15 | 15 | 0% | 2014-01-26 | 2014-02-12 | 2014-01-26 | 2014-02-12 | 40 | No | DUKHCONP03Z3ARGF3050, DUKHCONP03Z2ARGF3065, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3035, DUKHCONP03Z3ARGF3050 | DUKHCONP03Z3PLGF4315, DUKHCONP03Z3ARGF3070, DUKHCONP03Z3ARGF3070, DUKHCONP03Z4ARGF3065, DUKHCONP03Z3PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.20 .15 .10 .15 FIRST FLOORS |  | 144 | 144 | 0% | 2013-11-27 | 2014-05-15 | 2013-11-27 | 2014-05-15 | 0 |  |  |  | 0 | 0
DUKHCONP03Z3ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 0 | Yes | DUKHCONP03Z3ARFF3365, DUKHCONP03Z2ARFF3370, DUKHCONP03Z3ARFF3365 | DUKHCONP03Z4ARFF3370, DUKHCONP03Z3ARFF3375, DUKHCONP03Z3ARFF3380, DUKHCONP03Z3ARFF3375, DUKHCONP03Z3ARFF3380 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3355 | Aluminum tile false ceiling | 20 | 20 | 0% | 2014-02-25 | 2014-03-19 | 2014-02-25 | 2014-03-19 | 2 | No | DUKHCONP03Z3ACFF4615, DUKHCONP03Z2ARFF3355, DUKHCONP03Z3ARFF3345, DUKHCONP03Z3ACFF4615, DUKHCONP03Z3ARFF3345 | DUKHCONP03Z3PLFF4340, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ELFF4055, DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ELFF4055, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3PLFF4340, DUKHCONP03Z3ACFF4620, DUKHCONP03Z3ELFF4060, DUKHCONP03Z3ELFF4060, DUKHCONP03Z3ARFF3395, DUKHCONP03Z4ARFF3355, DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-03-24 | 2014-04-15 | 2014-03-24 | 2014-04-15 | 11 | No | DUKHCONP03Z3ARFF3370, DUKHCONP03Z3ARFF3370 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3300 | Block work | 25 | 25 | 0% | 2013-11-27 | 2013-12-26 | 2013-11-27 | 2013-12-26 | 0 | Yes | DUKHCONP03Z2ARFF3300, DUKHCONP03Z3STFF2035, DUKHCONP03Z3STFF2035, DUKHCONP03Z3STFF2020, DUKHCONP03Z3STFF2020 | DUKHCONP03Z3ARFF3305, DUKHCONP03Z3PLFF4325, DUKHCONP03Z3PLFF4330, DUKHCONP03Z3PLFF4330, DUKHCONP03Z3ELFF4035, DUKHCONP03Z3PLFF4325, DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ELFF4035, DUKHCONP03Z4ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-03-25 | 2014-04-22 | 2014-03-25 | 2014-04-22 | 0 | Yes | DUKHCONP03Z3ARFF3370, DUKHCONP03Z3ARFF3370, DUKHCONP03Z2ARFF3375 | DUKHCONP03Z3ARFF3385, DUKHCONP03Z3ARFF3390, DUKHCONP03Z3ARFF3385, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3390, DUKHCONP03Z4ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 0 | Yes | DUKHCONP03Z3ARFF3315, DUKHCONP03Z3PLFF4330, DUKHCONP03Z3PLFF4330, DUKHCONP03Z3PLFF4325, DUKHCONP03Z3PLFF4325, DUKHCONP03Z2ARFF3320, DUKHCONP03Z3ARFF3315 | DUKHCONP03Z3ARFF3325, DUKHCONP03Z3ARFF3325, DUKHCONP03Z4ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-04-17 | 2014-05-15 | 2014-04-17 | 2014-05-15 | 0 | Yes | DUKHCONP03Z2ARFF3395, DUKHCONP03Z3ARFF3385, DUKHCONP03Z3ARFF3330, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3350, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3390, DUKHCONP03Z3ARFF3390, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3375, DUKHCONP03Z3ACFF4625, DUKHCONP03Z3ARFF3330, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ARFF3350, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3385, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ARFF3375, DUKHCONP03Z3ARFF3380, DUKHCONP03Z3ACFF4625, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3380 | DUKHCONP03Z3ELTC8010, DUKHCONP03Z3ACTC8000, DUKHCONP03Z3PLTC8005, DUKHCONP03Z4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-02-13 | 2014-03-08 | 2014-02-13 | 2014-03-08 | 0 | Yes | DUKHCONP03Z3ELFF4045, DUKHCONP03Z3ARFF3330, DUKHCONP03Z3ARFF3325, DUKHCONP03Z3ARFF3325, DUKHCONP03Z3ELFF4045, DUKHCONP03Z3ARFF3330, DUKHCONP03Z2ARFF3345 | DUKHCONP03Z4ARFF3345, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3355 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3310 | Flooring screed | 21 | 21 | 0% | 2013-12-31 | 2014-01-23 | 2013-12-31 | 2014-01-23 | 15 | No | DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ARFF3305 | DUKHCONP03Z3ARFF3325, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-02-20 | 2014-03-15 | 2014-02-20 | 2014-03-15 | 2 | No | DUKHCONP03Z3ARFF3325, DUKHCONP03Z3ARFF3325 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3385, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3385, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-02-22 | 2014-03-22 | 2014-02-22 | 2014-03-22 | 0 | Yes | DUKHCONP03Z3ACFF4615, DUKHCONP03Z3ARFF3345, DUKHCONP03Z3ARFF3345, DUKHCONP03Z3ACFF4615, DUKHCONP03Z2ARFF3360 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ELFF4060, DUKHCONP03Z3ACFF4620, DUKHCONP03Z3ELFF4055, DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3PLFF4340, DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ELFF4060, DUKHCONP03Z3ACFF4620, DUKHCONP03Z3PLFF4340, DUKHCONP03Z3ARFF3365, DUKHCONP03Z4ARFF3360, DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-04-06 | 2014-04-28 | 2014-04-06 | 2014-04-28 | 0 | Yes | DUKHCONP03Z3ARFF3375, DUKHCONP03Z3ARFF3350, DUKHCONP03Z3ARFF3375, DUKHCONP03Z3ARFF3350 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-04-08 | 2014-04-30 | 2014-04-08 | 2014-04-30 | 0 | Yes | DUKHCONP03Z3ARFF3375, DUKHCONP03Z3ARFF3375 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-01-08 | 2014-02-05 | 2014-01-08 | 2014-02-05 | 18 | No | DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ARFF3305 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3345, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3305 | Plastering work | 25 | 25 | 0% | 2013-12-23 | 2014-01-20 | 2013-12-23 | 2014-01-20 | 0 | Yes | DUKHCONP03Z3ELFF4035, DUKHCONP03Z3ARFF3300, DUKHCONP03Z3PLFF4325, DUKHCONP03Z2ARFF3305, DUKHCONP03Z3ELFF4035, DUKHCONP03Z3PLFF4325, DUKHCONP03Z3ARFF3300 | DUKHCONP03Z3ARFF3330, DUKHCONP03Z3ACFF4615, DUKHCONP03Z3ACFF4615, DUKHCONP03Z3ARFF3315, DUKHCONP03Z3AREL3665, DUKHCONP03Z3ARFF3315, DUKHCONP03Z3ARFF3310, DUKHCONP03Z4ARFF3305, DUKHCONP03Z3AREL3665, DUKHCONP03Z3ARFF3330, DUKHCONP03Z3ARFF3310 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 0 | Yes | DUKHCONP03Z3ARFF3320, DUKHCONP03Z3ARFF3310, DUKHCONP03Z3ARFF3320, DUKHCONP03Z2ARFF3325, DUKHCONP03Z3ARFF3310 | DUKHCONP03Z3ARFF3345, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3345, DUKHCONP03Z4ARFF3325, DUKHCONP03Z3ARFF3350, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-02-17 | 2014-03-05 | 2014-02-17 | 2014-03-05 | 10 | No | DUKHCONP03Z3ARFF3310, DUKHCONP03Z3ARFF3310, DUKHCONP03Z3ARFF3325, DUKHCONP03Z3ARFF3325 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-01-13 | 2014-01-29 | 2014-01-13 | 2014-01-29 | 0 | Yes | DUKHCONP03Z2ARFF3315, DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ARFF3305 | DUKHCONP03Z4ARFF3315, DUKHCONP03Z3ARFF3320, DUKHCONP03Z3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-03-09 | 2014-03-25 | 2014-03-09 | 2014-03-25 | 0 | Yes | DUKHCONP03Z2ARFF3365, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3335, DUKHCONP03Z3ARFF3350, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3350 | DUKHCONP03Z4ARFF3365, DUKHCONP03Z3ARFF3370, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARFF3370, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3PLFF4335, DUKHCONP03Z3PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.20 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2013-12-16 | 2014-02-20 | 2013-12-16 | 2014-02-20 | 72 |  |  |  | 0 | 0
DUKHCONP03Z3ARRF3600 | Block work | 20 | 20 | 0% | 2013-12-16 | 2014-01-08 | 2013-12-16 | 2014-01-08 | 67 | No | DUKHCONP03Z3STRF2055, DUKHCONP03Z2ARRF3600, DUKHCONP03Z3STRF2055 | DUKHCONP03Z4ARRF3600, DUKHCONP03Z3ARRF3605, DUKHCONP03Z3ARRF3605 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3620 | Epoxy Painting | 15 | 15 | 0% | 2014-02-03 | 2014-02-20 | 2014-02-03 | 2014-02-20 | 72 | No | DUKHCONP03Z3ARRF3695, DUKHCONP03Z3ARRF3695 | DUKHCONP03Z3ELTC8010, DUKHCONP03Z3ACTC8000, DUKHCONP03Z3PLTC8005 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-01-08 | 2014-01-25 | 2014-01-08 | 2014-01-25 | 72 | No | DUKHCONP03Z3ARRF3605, DUKHCONP03Z3ARRF3605 | DUKHCONP03Z3ARRF3695, DUKHCONP03Z3ARRF3695 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3695 | Painting | 20 | 20 | 0% | 2014-01-16 | 2014-02-08 | 2014-01-16 | 2014-02-08 | 72 | No | DUKHCONP03Z3ARRF3610, DUKHCONP03Z3ARRF3610 | DUKHCONP03Z3AREL3680, DUKHCONP03Z3ARRF3620, DUKHCONP03Z3ARRF3620, DUKHCONP03Z3AREL3680 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3605 | Plastering work | 20 | 20 | 0% | 2013-12-25 | 2014-01-16 | 2013-12-25 | 2014-01-16 | 67 | No | DUKHCONP03Z3ARRF3600, DUKHCONP03Z3ARRF3600 | DUKHCONP03Z3PLRF4345, DUKHCONP03Z3ARRF3610, DUKHCONP03Z3ARRF3610, DUKHCONP03Z3AREL3665, DUKHCONP03Z3PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L55.20 .15 .15 EXTERNAL FINISHES |  | 70 | 70 | 0% | 2013-12-23 | 2014-03-15 | 2013-12-23 | 2014-03-15 | 53 |  |  |  | 0 | 0
DHBL.K30.L55.20 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2013-12-23 | 2014-02-26 | 2013-12-23 | 2014-02-26 | 67 |  |  |  | 0 | 0
DUKHCONP03Z3ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 62 | No | DUKHCONP03Z3ARRF3645, DUKHCONP03Z3ARRF3645 | DUKHCONP03Z3ARRF3655, DUKHCONP03Z3ARRF3655 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-02-09 | 2014-02-26 | 2014-02-09 | 2014-02-26 | 67 | No | DUKHCONP03Z3ARRF3655, DUKHCONP03Z3ARRF3655 | DUKHCONP03Z3ACTC8000, DUKHCONP03Z3PLTC8005, DUKHCONP03Z3ELTC8010 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2013-12-31 | 2014-01-28 | 2013-12-31 | 2014-01-28 | 62 | No | DUKHCONP03Z3ARRF3635, DUKHCONP03Z3ARRF3635 | DUKHCONP03Z3ARRF3645, DUKHCONP03Z3ARRF3645 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-01-28 | 2014-02-20 | 2014-01-28 | 2014-02-20 | 62 | No | DUKHCONP03Z3ARRF3645, DUKHCONP03Z2ARRF3655, DUKHCONP03Z3ARRF3645, DUKHCONP03Z3ARRF3650, DUKHCONP03Z3ARRF3650 | DUKHCONP03Z3ELTC8010, DUKHCONP03Z4ARRF3655, DUKHCONP03Z3PLRF4355, DUKHCONP03Z3ARRF3660, DUKHCONP03Z3PLTC8005, DUKHCONP03Z3ACTC8000, DUKHCONP03Z3PLRF4355, DUKHCONP03Z3ARRF3660 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2013-12-26 | 2014-01-23 | 2013-12-26 | 2014-01-23 | 62 | No | DUKHCONP03Z3ARRF3630, DUKHCONP03Z3ARRF3630 | DUKHCONP03Z3ARRF3640, DUKHCONP03Z3ARRF3640 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2013-12-23 | 2014-01-20 | 2013-12-23 | 2014-01-20 | 62 | No | DUKHCONP03Z2ARRF3630, DUKHCONP03Z3STRF2065, DUKHCONP03Z3STRF2060, DUKHCONP03Z3STRF2060, DUKHCONP03Z3STRF2065 | DUKHCONP03Z3ARRF3635, DUKHCONP03Z4ARRF3630, DUKHCONP03Z3ARRF3635 | 0 | 0 | ROOF
DUKHCONP03Z3ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 62 | No | DUKHCONP03Z3ARRF3640, DUKHCONP03Z3ARRF3640 | DUKHCONP03Z3ARRF3655, DUKHCONP03Z3PLRF4350, DUKHCONP03Z3ARRF3650, DUKHCONP03Z3ARRF3655, DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ELRF4070, DUKHCONP03Z3ARRF3650, DUKHCONP03Z3ELRF4070, DUKHCONP03Z3PLRF4350 | 0 | 0 | ROOF
DHBL.K30.L55.20 .15 .15 .15 ELEVATION |  | 47 | 47 | 0% | 2014-01-19 | 2014-03-15 | 2014-01-19 | 2014-03-15 | 53 |  |  |  | 0 | 0
DUKHCONP03Z3AREL3680 | External Painting | 20 | 20 | 0% | 2014-02-20 | 2014-03-15 | 2014-02-20 | 2014-03-15 | 53 | No | DUKHCONP03Z3ARRF3695, DUKHCONP03Z2AREL3680, DUKHCONP03Z3ARRF3695, DUKHCONP03Z3AREL3675, DUKHCONP03Z3AREL3675 | DUKHCONP03Z3ELTC8010, DUKHCONP03Z3PLTC8005, DUKHCONP03Z3ACTC8000, DUKHCONP03Z4AREL3680 | 0 | 0 | ELEVATION
DUKHCONP03Z3AREL3665 | External Plastering | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 53 | No | DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ARRF3605, DUKHCONP03Z3STRF2065, DUKHCONP03Z3ARFF3305, DUKHCONP03Z2AREL3665, DUKHCONP03Z3STRF2065 | DUKHCONP03Z4AREL3665, DUKHCONP03Z3AREL3675, DUKHCONP03Z3PLRF4350, DUKHCONP03Z3AREL3675, DUKHCONP03Z3PLRF4350 | 0 | 0 | ELEVATION
DUKHCONP03Z3AREL3675 | GRC Panel Works | 20 | 20 | 0% | 2014-02-05 | 2014-03-01 | 2014-02-05 | 2014-03-01 | 55 | No | DUKHCONP03Z2AREL3675, DUKHCONP03Z3AREL3665, DUKHCONP03Z3AREL3665 | DUKHCONP03Z3AREL3680, DUKHCONP03Z3AREL3680, DUKHCONP03Z4AREL3675 | 0 | 0 | ELEVATION
DHBL.K30.L55.20 .20 MEP WORKS |  | 262 | 262 | 0% | 2013-07-06 | 2014-05-14 | 2013-07-06 | 2014-05-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L55.20 .20 .10 ELECTRICAL WORKS |  | 174 | 174 | 0% | 2013-10-22 | 2014-05-14 | 2013-10-22 | 2014-05-14 | 1 |  |  |  | 0 | 0
DHBL.K30.L55.20 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-10-22 | 2014-03-02 | 2013-10-22 | 2014-03-02 | 37 |  |  |  | 0 | 0
DUKHCONP03Z3ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-11-03 | 2013-11-25 | 2013-11-03 | 2013-11-25 | 62 | No | DUKHCONP03Z2ELGF4005, DUKHCONP03Z3ELGF4000, DUKHCONP03Z3ELGF4000 | DUKHCONP03Z3ELGF4010, DUKHCONP03Z3ELGF4010, DUKHCONP03Z4ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-10-22 | 2013-11-19 | 2013-10-22 | 2013-11-19 | 44 | No | DUKHCONP03Z3ARGF3000, DUKHCONP03Z3ARGF3000 | DUKHCONP03Z3ARGF3005, DUKHCONP03Z3ELGF4005, DUKHCONP03Z3ARGF3005, DUKHCONP03Z3ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 49 | No | DUKHCONP03Z2ELGF4015, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ARGF3060 | DUKHCONP03Z3ELFF4055, DUKHCONP03Z3ELTC8010, DUKHCONP03Z4ELGF4015, DUKHCONP03Z3ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-01-20 | 2014-02-12 | 2014-01-20 | 2014-02-12 | 35 | No | DUKHCONP03Z3ELGF4010, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ELGF4010, DUKHCONP03Z3ARGF3060 | DUKHCONP03Z3ELGF4030, DUKHCONP03Z3ELGF4025, DUKHCONP03Z3ELGF4030, DUKHCONP03Z3ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 37 | No | DUKHCONP03Z3ARGF3060, DUKHCONP03Z2ELGF4025, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ELGF4020 | DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ELTC8010, DUKHCONP03Z4ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-02-01 | 2014-02-24 | 2014-02-01 | 2014-02-24 | 35 | No | DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ARGF3060, DUKHCONP03Z2ELGF4030, DUKHCONP03Z3ELGF4020 | DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ELTC8010, DUKHCONP03Z4ELGF4030, DUKHCONP03Z3ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-11-11 | 2013-12-09 | 2013-11-11 | 2013-12-09 | 62 | No | DUKHCONP03Z3ELGF4005, DUKHCONP03Z3ELGF4005 | DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ELGF4020, DUKHCONP03Z3ARGF3045, DUKHCONP03Z3ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.20 .20 .10 .15 FIRST FLOORS |  | 116 | 116 | 0% | 2013-12-03 | 2014-04-19 | 2013-12-03 | 2014-04-19 | 4 |  |  |  | 0 | 0
DUKHCONP03Z3ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-15 | 2014-01-07 | 2013-12-15 | 2014-01-07 | 33 | No | DUKHCONP03Z3ELFF4035, DUKHCONP03Z3ELFF4035 | DUKHCONP03Z3ELFF4045, DUKHCONP03Z3ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 11 | No | DUKHCONP03Z3ARFF3300, DUKHCONP03Z3ARFF3300 | DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ELFF4040, DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 12 | No | DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ELGF4015, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ELGF4015, DUKHCONP03Z2ELFF4055, DUKHCONP03Z3ARFF3360 | DUKHCONP03Z3ELTC8010, DUKHCONP03Z4ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-03-09 | 2014-03-31 | 2014-03-09 | 2014-03-31 | 1 | No | DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z2ELFF4060, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ELFF4045, DUKHCONP03Z3ELFF4045 | DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ELFF4065, DUKHCONP03Z4ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 1 | No | DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ELFF4060, DUKHCONP03Z3ELFF4060, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ELGF4025, DUKHCONP03Z3ELGF4025, DUKHCONP03Z2ELFF4065, DUKHCONP03Z3ARFF3355 | DUKHCONP03Z3ELTC8010, DUKHCONP03Z3ELRF4070, DUKHCONP03Z4ELFF4065, DUKHCONP03Z3ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 20 | No | DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ELGF4030, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3MSEX5010, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ELGF4030 | DUKHCONP03Z3ELRF4070, DUKHCONP03Z3ELTC8010, DUKHCONP03Z3ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 30 | No | DUKHCONP03Z3ELFF4040, DUKHCONP03Z3ELFF4040, DUKHCONP03Z2ELFF4045 | DUKHCONP03Z3ARFF3345, DUKHCONP03Z4ELFF4045, DUKHCONP03Z3ELRF4070, DUKHCONP03Z3ARFF3345, DUKHCONP03Z3ELRF4070, DUKHCONP03Z3ELFF4060, DUKHCONP03Z3ELFF4060 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.20 .20 .10 .20 ROOF |  | 30 | 30 | 0% | 2014-04-10 | 2014-05-14 | 2014-04-10 | 2014-05-14 | 1 |  |  |  | 0 | 0
DUKHCONP03Z3ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-04-10 | 2014-04-30 | 2014-04-10 | 2014-04-30 | 1 | No | DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ELFF4045, DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ELFF4045, DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ARRF3645, DUKHCONP03Z3ARRF3645, DUKHCONP03Z3ELFF4065 | DUKHCONP03Z3ELRF4075, DUKHCONP03Z3ELRF4075 | 0 | 0 | ROOF
DUKHCONP03Z3ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-04-19 | 2014-05-14 | 2014-04-19 | 2014-05-14 | 1 | No | DUKHCONP03Z3ELRF4070, DUKHCONP03Z3ELRF4070 | DUKHCONP03Z3ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L55.20 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 249 | 249 | 0% | 2013-07-06 | 2014-04-29 | 2013-07-06 | 2014-04-29 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.20 .20 .15 .10 GROUND FLOOR |  | 199 | 199 | 0% | 2013-07-06 | 2014-03-02 | 2013-07-06 | 2014-03-02 | 64 |  |  |  | 0 | 0
DUKHCONP03Z3PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-07-06 | 2013-07-28 | 2013-07-06 | 2013-07-28 | 0 | Yes | DUKHCONP03Z3STUG1040, DUKHCONP03Z3STUG1040 | DUKHCONP03Z3STUG1045, DUKHCONP03Z3STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-11-02 | 2013-11-21 | 2013-11-02 | 2013-11-21 | 56 | No | DUKHCONP03Z3ARGF3000, DUKHCONP03Z3PLGF4305, DUKHCONP03Z3PLGF4305, DUKHCONP03Z3ARGF3000 | DUKHCONP03Z3MSEX5000, DUKHCONP03Z3PLGF4315, DUKHCONP03Z3PLGF4315, DUKHCONP03Z3MSEX5000, DUKHCONP03Z3ARGF3020, DUKHCONP03Z3ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-11-02 | 2013-11-21 | 2013-11-02 | 2013-11-21 | 35 | No | DUKHCONP03Z3ARGF3000, DUKHCONP03Z3ARGF3000, DUKHCONP03Z2PLGF4305 | DUKHCONP03Z3ARGF3020, DUKHCONP03Z3ARGF3005, DUKHCONP03Z3ARGF3020, DUKHCONP03Z3PLGF4310, DUKHCONP03Z3PLGF4310, DUKHCONP03Z4PLGF4305, DUKHCONP03Z3ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-02-13 | 2014-03-02 | 2014-02-13 | 2014-03-02 | 64 | No | DUKHCONP03Z3ARGF3060, DUKHCONP03Z3PLGF4315, DUKHCONP03Z2PLGF4320, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3PLGF4315 | DUKHCONP03Z4PLGF4320, DUKHCONP03Z3PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-02-01 | 2014-02-24 | 2014-02-01 | 2014-02-24 | 64 | No | DUKHCONP03Z3ARGF3065, DUKHCONP03Z3PLGF4310, DUKHCONP03Z3PLGF4310, DUKHCONP03Z2PLGF4315, DUKHCONP03Z3ARGF3065 | DUKHCONP03Z3PLGF4320, DUKHCONP03Z4PLGF4315, DUKHCONP03Z3PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.20 .20 .15 .15 FIRST FLOORS |  | 102 | 102 | 0% | 2013-12-12 | 2014-04-12 | 2013-12-12 | 2014-04-12 | 14 |  |  |  | 0 | 0
DUKHCONP03Z3PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2013-12-14 | 2014-01-04 | 2013-12-14 | 2014-01-04 | 26 | No | DUKHCONP03Z3PLFF4325, DUKHCONP03Z3ARFF3300, DUKHCONP03Z3ARFF3300, DUKHCONP03Z2PLFF4330, DUKHCONP03Z3PLFF4325 | DUKHCONP03Z3PLFF4335, DUKHCONP03Z4PLFF4330, DUKHCONP03Z3PLRF4350, DUKHCONP03Z3PLRF4350, DUKHCONP03Z3ARFF3320, DUKHCONP03Z3ARFF3320, DUKHCONP03Z3PLFF4335 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-12-12 | 2014-01-02 | 2013-12-12 | 2014-01-02 | 0 | Yes | DUKHCONP03Z3ARFF3300, DUKHCONP03Z3ARFF3300 | DUKHCONP03Z3PLFF4330, DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ARFF3320, DUKHCONP03Z3PLFF4330, DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-03-26 | 2014-04-12 | 2014-03-26 | 2014-04-12 | 14 | No | DUKHCONP03Z2PLFF4340, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3PLFF4335, DUKHCONP03Z3PLFF4335, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3360 | DUKHCONP03Z3PLRF4355, DUKHCONP03Z3PLRF4355, DUKHCONP03Z4PLFF4340 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-03-15 | 2014-04-06 | 2014-03-15 | 2014-04-06 | 14 | No | DUKHCONP03Z3PLFF4330, DUKHCONP03Z3PLFF4330, DUKHCONP03Z3ARFF3365, DUKHCONP03Z3ARFF3365 | DUKHCONP03Z3PLFF4340, DUKHCONP03Z3PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.20 .20 .15 .20 ROOF |  | 95 | 95 | 0% | 2014-01-08 | 2014-04-29 | 2014-01-08 | 2014-04-29 | 14 |  |  |  | 0 | 0
DUKHCONP03Z3PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-01-08 | 2014-01-25 | 2014-01-08 | 2014-01-25 | 71 | No | DUKHCONP03Z3ARRF3605, DUKHCONP03Z3ARRF3605 | DUKHCONP03Z3PLRF4350, DUKHCONP03Z3PLRF4355, DUKHCONP03Z3PLRF4355, DUKHCONP03Z3PLRF4350 | 0 | 0 | ROOF
DUKHCONP03Z3PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-02-08 | 2014-02-25 | 2014-02-08 | 2014-02-25 | 53 | No | DUKHCONP03Z3PLFF4330, DUKHCONP03Z3PLRF4345, DUKHCONP03Z3ARRF3645, DUKHCONP03Z3PLFF4330, DUKHCONP03Z3AREL3665, DUKHCONP03Z2PLRF4350, DUKHCONP03Z3AREL3665, DUKHCONP03Z3ARRF3645, DUKHCONP03Z3PLRF4345 | DUKHCONP03Z4PLRF4350, DUKHCONP03Z3WTEX5065, DUKHCONP03Z3WTEX5065, DUKHCONP03Z3PLRF4355, DUKHCONP03Z3PLTC8005, DUKHCONP03Z3PLRF4355 | 0 | 0 | ROOF
DUKHCONP03Z3PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 14 | No | DUKHCONP03Z2PLRF4355, DUKHCONP03Z3ARRF3655, DUKHCONP03Z3PLFF4340, DUKHCONP03Z3PLFF4340, DUKHCONP03Z3PLRF4345, DUKHCONP03Z3PLRF4345, DUKHCONP03Z3PLRF4350, DUKHCONP03Z3ARRF3655, DUKHCONP03Z3PLRF4350 | DUKHCONP03Z3PLTC8005, DUKHCONP03Z4PLRF4355 | 0 | 0 | ROOF
DHBL.K30.L55.20 .20 .20 AC WORKS |  | 135 | 135 | 0% | 2013-11-21 | 2014-04-29 | 2013-11-21 | 2014-04-29 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.20 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-11-21 | 2014-02-27 | 2013-11-21 | 2014-02-27 | 51 |  |  |  | 0 | 0
DUKHCONP03Z3ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-02-04 | 2014-02-27 | 2014-02-04 | 2014-02-27 | 51 | No | DUKHCONP03Z3ACGF4605, DUKHCONP03Z3ACGF4605, DUKHCONP03Z2ACGF4610 | DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ACRF4635, DUKHCONP03Z4ACGF4610, DUKHCONP03Z3ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-01-14 | 2014-02-12 | 2014-01-14 | 2014-02-12 | 51 | No | DUKHCONP03Z3ARGF3055, DUKHCONP03Z2ACGF4605, DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ARGF3060 | DUKHCONP03Z3ACGF4610, DUKHCONP03Z3ACGF4610, DUKHCONP03Z4ACGF4605 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z3ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-11-21 | 2013-12-14 | 2013-11-21 | 2013-12-14 | 66 | No | DUKHCONP03Z3ARGF3005, DUKHCONP03Z3ARGF3005, DUKHCONP03Z2ACGF4600 | DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ARGF3055, DUKHCONP03Z3ACGF4605, DUKHCONP03Z3ARGF3055, DUKHCONP03Z4ACGF4600, DUKHCONP03Z3ACGF4605, DUKHCONP03Z3ARGF3060, DUKHCONP03Z3ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.20 .20 .20 .15 FIRST FLOORS |  | 87 | 87 | 0% | 2014-01-06 | 2014-04-17 | 2014-01-06 | 2014-04-17 | 9 |  |  |  | 0 | 0
DUKHCONP03Z3ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-03-26 | 2014-04-17 | 2014-03-26 | 2014-04-17 | 9 | No | DUKHCONP03Z2ACFF4625, DUKHCONP03Z3ACFF4620, DUKHCONP03Z3ACFF4620 | DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ACRF4635, DUKHCONP03Z4ACFF4625, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ACRF4635, DUKHCONP03Z3ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 9 | No | DUKHCONP03Z2ACFF4620, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3355, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ACFF4615, DUKHCONP03Z3ACFF4615, DUKHCONP03Z3ARFF3355 | DUKHCONP03Z3ACFF4625, DUKHCONP03Z3ACFF4625, DUKHCONP03Z4ACFF4620 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z3ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-06 | 2014-01-28 | 2014-01-06 | 2014-01-28 | 32 | No | DUKHCONP03Z2ACFF4615, DUKHCONP03Z3ARFF3305, DUKHCONP03Z3ARFF3305 | DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ARFF3355, DUKHCONP03Z4ACFF4615, DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ARFF3360, DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ACFF4620, DUKHCONP03Z3ACFF4620, DUKHCONP03Z3ARFF3355 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.20 .20 .20 .20 ROOF |  | 89 | 89 | 0% | 2014-01-15 | 2014-04-29 | 2014-01-15 | 2014-04-29 | 14 |  |  |  | 0 | 0
DUKHCONP03Z3ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 14 | No | DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ACRF4630, DUKHCONP03Z3ACGF4610, DUKHCONP03Z3ACFF4625, DUKHCONP03Z2ACRF4635, DUKHCONP03Z3ACGF4610, DUKHCONP03Z3ACFF4625 | DUKHCONP03Z4ACRF4635, DUKHCONP03Z3ACTC8000 | 0 | 0 | ROOF
DUKHCONP03Z3ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-01-15 | 2014-02-13 | 2014-01-15 | 2014-02-13 | 73 | No | DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ACGF4600, DUKHCONP03Z3ARRF3645, DUKHCONP03Z3ARRF3645, DUKHCONP03Z3ACFF4615, DUKHCONP03Z3ACFF4615, DUKHCONP03Z2ACRF4630 | DUKHCONP03Z3ACRF4635, DUKHCONP03Z3ACRF4635, DUKHCONP03Z4ACRF4630 | 0 | 0 | ROOF
DHBL.K30.L55.20 .25 EXTERNAL WORKS |  | 120 | 120 | 0% | 2013-12-03 | 2014-04-23 | 2013-12-03 | 2014-04-23 | 19 |  |  |  | 0 | 0
DHBL.K30.L55.20 .25 .10 MISCELLANEOUS |  | 88 | 88 | 0% | 2013-12-03 | 2014-03-17 | 2013-12-03 | 2014-03-17 | 32 |  |  |  | 0 | 0
DUKHCONP03Z3MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2013-12-17 | 2014-01-15 | 2013-12-17 | 2014-01-15 | 46 | No | DUKHCONP03Z3MSEX5000, DUKHCONP03Z3MSEX5000 | DUKHCONP03Z3MSEX5015, DUKHCONP03Z3PLTC8005, DUKHCONP03Z3ELTC8010, DUKHCONP03Z3MSEX5015, DUKHCONP03Z3ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z3MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-02-04 | 2014-03-05 | 2014-02-04 | 2014-03-05 | 21 | No | DUKHCONP03Z3STRF2055, DUKHCONP03Z2MSEX5020, DUKHCONP03Z3STRF2055 | DUKHCONP03Z3MSEX5025, DUKHCONP03Z4MSEX5020, DUKHCONP03Z3MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z3MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-01-07 | 2014-01-29 | 2014-01-07 | 2014-01-29 | 46 | No | DUKHCONP03Z3MSEX5005, DUKHCONP03Z3MSEX5005 | DUKHCONP03Z3MSEX5010, DUKHCONP03Z3WTEX5065, DUKHCONP03Z3WTEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z3MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 46 | No | DUKHCONP03Z3STRF2055, DUKHCONP03Z3PLGF4310, DUKHCONP03Z3STRF2055, DUKHCONP03Z3PLGF4310 | DUKHCONP03Z3MSEX5005, DUKHCONP03Z3MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z3MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-02-23 | 2014-03-17 | 2014-02-23 | 2014-03-17 | 21 | No | DUKHCONP03Z3MSEX5020, DUKHCONP03Z3MSEX5020 | DUKHCONP03Z3WTEX5050, DUKHCONP03Z3WTEX5060 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z3MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 46 | No | DUKHCONP03Z3MSEX5015 | DUKHCONP03Z3ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L55.20 .25 .15 DOMESTIC WATER TANK & PUMP ROOM |  | 118 | 118 | 0% | 2013-12-05 | 2014-04-23 | 2013-12-05 | 2014-04-23 | 19 |  |  |  | 0 | 0
DUKHCONP03Z3WTEX5040 | Block works & Plastering | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 58 | No | DUKHCONP03Z3WTEX5035, DUKHCONP03Z3WTEX5035 | DUKHCONP03Z3WTEX5045, DUKHCONP03Z3WTEX5080, DUKHCONP03Z3WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5035 | Construction of Raft | 25 | 25 | 0% | 2013-12-11 | 2014-01-09 | 2013-12-11 | 2014-01-09 | 58 | No | DUKHCONP03Z3WTEX5030, DUKHCONP03Z3WTEX5030 | DUKHCONP03Z3WTEX5040, DUKHCONP03Z3WTEX5040 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5075 | Domestic Water Tank AC works | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 58 | No | DUKHCONP03Z3WTEX5070 | DUKHCONP03Z3WTEX5085 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5080 | Domestic Water Tank Electrical works | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 58 | No | DUKHCONP03Z3WTEX5040 | DUKHCONP03Z3WTEX5070 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5085 | Domestic Water Tank Firefighting works | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 58 | No | DUKHCONP03Z3WTEX5075 | DUKHCONP03Z3WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5070 | Domestic Water Tank Plumbings works | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 58 | No | DUKHCONP03Z3WTEX5080 | DUKHCONP03Z3WTEX5075 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5030 | Excavation | 20 | 20 | 0% | 2013-12-05 | 2013-12-29 | 2013-12-05 | 2013-12-29 | 58 | No | DUKHCONP03Z3STRF2055, DUKHCONP03Z3STRF2065, DUKHCONP03Z2WTEX5030, DUKHCONP03Z3STRF2055 | DUKHCONP03Z3WTEX5035, DUKHCONP03Z4WTEX5030, DUKHCONP03Z3WTEX5035 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-01-04 | 2014-02-01 | 2014-01-04 | 2014-02-01 | 58 | No | DUKHCONP03Z3WTEX5040, DUKHCONP03Z3WTEX5040, DUKHCONP03Z3WTEX5085 | DUKHCONP03Z3WTEX5050, DUKHCONP03Z3WTEX5050 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-03-26 | 2014-04-23 | 2014-03-26 | 2014-04-23 | 19 | No | DUKHCONP03Z3WTEX5060, DUKHCONP03Z3PLRF4350, DUKHCONP03Z3PLRF4350, DUKHCONP03Z3MSEX5015, DUKHCONP03Z2WTEX5065, DUKHCONP03Z3MSEX5015, DUKHCONP03Z3WTEX5060 | DUKHCONP03Z3PLTC8005, DUKHCONP03Z4WTEX5065 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 21 | No | DUKHCONP03Z3WTEX5045, DUKHCONP03Z3WTEX5045, DUKHCONP03Z3MSEX5025 | DUKHCONP03Z3WTEX5060, DUKHCONP03Z3WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z3WTEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 19 | No | DUKHCONP03Z3WTEX5050, DUKHCONP03Z2WTEX5060, DUKHCONP03Z3WTEX5050, DUKHCONP03Z3MSEX5025 | DUKHCONP03Z3WTEX5065, DUKHCONP03Z4WTEX5060, DUKHCONP03Z3WTEX5065 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DHBL.K30.L55.20 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 |  |  |  | 0 | 0
DUKHCONP03Z3ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 | Yes | DUKHCONP03Z3ARRF3620, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARRF3660, DUKHCONP03Z3MSEX5005, DUKHCONP03Z2ACTC8000, DUKHCONP03Z3AREL3680, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ACRF4635, DUKHCONP03Z3ARRF3655, DUKHCONP03Z3ACFF4625 | DUKHCONP03Z4ACTC8000, DUKHHANP03GNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z3ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 | Yes | DUKHCONP03Z3ARRF3620, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARRF3655, DUKHCONP03Z2ELTC8010, DUKHCONP03Z3AREL3680, DUKHCONP03Z3ARRF3660, DUKHCONP03Z3ELFF4065, DUKHCONP03Z3ELRF4075, DUKHCONP03Z3MSEX5005, DUKHCONP03Z3ELGF4030, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3ELFF4050, DUKHCONP03Z3ELFF4055, DUKHCONP03Z3ELGF4015, DUKHCONP03Z3ELGF4025 | DUKHHANP03GNELTC9010, DUKHHANP03GNACTC9000, DUKHCONP03Z4ELTC8010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z3PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 | Yes | DUKHCONP03Z3ARRF3620, DUKHCONP03Z3ARRF3660, DUKHCONP03Z3PLRF4355, DUKHCONP03Z3MSEX5005, DUKHCONP03Z3AREL3680, DUKHCONP03Z2PLTC8005, DUKHCONP03Z3ARFF3395, DUKHCONP03Z3ARRF3655, DUKHCONP03Z3PLGF4320, DUKHCONP03Z3WTEX5065, DUKHCONP03Z3ARGF3095, DUKHCONP03Z3PLRF4350 | DUKHHANP03GNPLTC9005, DUKHCONP03Z4PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L55.25 ZONE - 4 (3 Apartments) |  | 372 | 372 | 0% | 2013-04-28 | 2014-07-13 | 2013-04-28 | 2014-07-13 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.25 .10 STRUCTURAL WORKS |  | 230 | 230 | 0% | 2013-04-28 | 2014-01-27 | 2013-04-28 | 2014-01-27 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.25 .10 .10 SUB STRUCTURE |  | 117 | 117 | 0% | 2013-04-28 | 2013-09-14 | 2013-04-28 | 2013-09-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.25 .10 .10 .10 UPTO GRADE SLAB |  | 117 | 117 | 0% | 2013-04-28 | 2013-09-14 | 2013-04-28 | 2013-09-14 | 0 |  |  |  | 0 | 0
DUKHCONP03Z4STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-07-01 | 2013-07-29 | 2013-07-01 | 2013-07-29 | 0 | Yes | DUKHCONP03Z4STUG1030, DUKHCONP03Z3STUG1035, DUKHCONP03Z4STUG1030 | DUKHCONP03Z4STUG1040, DUKHCONP03Z4STUG1040, DUKHCONP03Z5STUG1035 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-06-02 | 2013-06-24 | 2013-06-02 | 2013-06-24 | 0 | Yes | DUKHCONP03Z4STUG1015, DUKHCONP03Z4STUG1015 | DUKHCONP03Z4STUG1025, DUKHCONP03Z4STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-07-17 | 2013-08-18 | 2013-07-17 | 2013-08-18 | 0 | Yes | DUKHCONP03Z4STUG1035, DUKHCONP03Z4STUG1035 | DUKHCONP03Z4STUG1045, DUKHCONP03Z4PLUG4300, DUKHCONP03Z4STUG1045, DUKHCONP03Z4PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-06-11 | 2013-07-09 | 2013-06-11 | 2013-07-09 | 0 | Yes | DUKHCONP03Z3STUG1025, DUKHCONP03Z4STUG1020, DUKHCONP03Z4STUG1020 | DUKHCONP03Z4STUG1030, DUKHCONP03Z4STUG1030, DUKHCONP03Z5STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-08-17 | 2013-09-14 | 2013-08-17 | 2013-09-14 | 0 | Yes | DUKHCONP03Z4PLUG4300, DUKHCONP03Z3STUG1045, DUKHCONP03Z4STUG1040, DUKHCONP03Z4STUG1040, DUKHCONP03Z4PLUG4300 | DUKHCONP03Z4STGF2000, DUKHCONP03Z4STGF2000, DUKHCONP03Z5STUG1045 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-05-08 | 2013-06-03 | 2013-05-08 | 2013-06-03 | 0 | Yes | DUKHCONP03Z4STUG1000, DUKHCONP03Z4STUG1000 | DUKHCONP03Z4STUG1010, DUKHCONP03Z4STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-05-12 | 2013-06-06 | 2013-05-12 | 2013-06-06 | 0 | Yes | DUKHCONP03Z4STUG1005, DUKHCONP03Z4STUG1005 | DUKHCONP03Z4STUG1015, DUKHCONP03Z4STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-04-28 | 2013-05-26 | 2013-04-28 | 2013-05-26 | 0 | Yes | DUKHCONP03Z3STUG1000 | DUKHCONP03Z4STUG1005, DUKHCONP03Z4STUG1005, DUKHCONP03Z5STUG1000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-05-18 | 2013-06-15 | 2013-05-18 | 2013-06-15 | 0 | Yes | DUKHCONP03Z4STUG1010, DUKHCONP03Z4STUG1010 | DUKHCONP03Z4STUG1020, DUKHCONP03Z4STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z4STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-06-20 | 2013-07-18 | 2013-06-20 | 2013-07-18 | 0 | Yes | DUKHCONP03Z4STUG1025, DUKHCONP03Z4STUG1025 | DUKHCONP03Z4STUG1035, DUKHCONP03Z4STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L55.25 .10 .15 SUPERSTRUCTURE |  | 124 | 124 | 0% | 2013-09-02 | 2014-01-27 | 2013-09-02 | 2014-01-27 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.25 .10 .15 .10 GROUND FLOOR |  | 49 | 49 | 0% | 2013-09-02 | 2013-10-30 | 2013-09-02 | 2013-10-30 | 0 |  |  |  | 0 | 0
DUKHCONP03Z4STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-10-12 | 2013-10-30 | 2013-10-12 | 2013-10-30 | 0 | Yes | DUKHCONP03Z4STGF2010, DUKHCONP03Z4STGF2010, DUKHCONP03Z3STGF2015 | DUKHCONP03Z4ARGF3000, DUKHCONP03Z5STGF2015, DUKHCONP03Z4STFF2020, DUKHCONP03Z4STFF2020, DUKHCONP03Z4ARGF3000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-09-26 | 2013-10-27 | 2013-09-26 | 2013-10-27 | 0 | Yes | DUKHCONP03Z4STGF2005, DUKHCONP03Z4STGF2005 | DUKHCONP03Z4STGF2015, DUKHCONP03Z4STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-09-11 | 2013-10-08 | 2013-09-11 | 2013-10-08 | 0 | Yes | DUKHCONP03Z4STGF2000, DUKHCONP03Z4STGF2000 | DUKHCONP03Z4STGF2010, DUKHCONP03Z4STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-09-02 | 2013-09-30 | 2013-09-02 | 2013-09-30 | 0 | Yes | DUKHCONP03Z3STGF2000, DUKHCONP03Z4STUG1045, DUKHCONP03Z4STUG1045 | DUKHCONP03Z4STGF2005, DUKHCONP03Z5STGF2000, DUKHCONP03Z4STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.25 .10 .15 .15 FIRST FLOORS |  | 55 | 55 | 0% | 2013-10-14 | 2013-12-19 | 2013-10-14 | 2013-12-19 | 0 |  |  |  | 0 | 0
DUKHCONP03Z4STFF2035 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-12-02 | 2013-12-19 | 2013-12-02 | 2013-12-19 | 0 | Yes | DUKHCONP03Z3STFF2035, DUKHCONP03Z4STFF2030, DUKHCONP03Z4STFF2030 | DUKHCONP03Z4ARFF3300, DUKHCONP03Z4ARFF3300, DUKHCONP03Z4STRF2040, DUKHCONP03Z5STFF2035, DUKHCONP03Z4STRF2040 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-11-11 | 2013-12-09 | 2013-11-11 | 2013-12-09 | 0 | Yes | DUKHCONP03Z4STFF2025, DUKHCONP03Z4STFF2025 | DUKHCONP03Z4STFF2035, DUKHCONP03Z4STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-10-27 | 2013-11-23 | 2013-10-27 | 2013-11-23 | 0 | Yes | DUKHCONP03Z4STFF2020, DUKHCONP03Z4STFF2020 | DUKHCONP03Z4STFF2030, DUKHCONP03Z4STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-10-14 | 2013-11-13 | 2013-10-14 | 2013-11-13 | 0 | Yes | DUKHCONP03Z4STGF2015, DUKHCONP03Z3STFF2020, DUKHCONP03Z4STGF2015 | DUKHCONP03Z4ARFF3300, DUKHCONP03Z4ARFF3300, DUKHCONP03Z4STFF2025, DUKHCONP03Z5STFF2020, DUKHCONP03Z4STFF2025 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.25 .10 .15 .20 ROOF |  | 46 | 46 | 0% | 2013-12-04 | 2014-01-27 | 2013-12-04 | 2014-01-27 | 58 |  |  |  | 0 | 0
DUKHCONP03Z4STRF2045 | Column-Concrete | 17 | 17 | 0% | 2013-12-08 | 2013-12-28 | 2013-12-08 | 2013-12-28 | 27 | No | DUKHCONP03Z4STRF2040, DUKHCONP03Z4STRF2040 | DUKHCONP03Z4STRF2050, DUKHCONP03Z4STRF2050 | 0 | 0 | ROOF
DUKHCONP03Z4STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2013-12-04 | 2013-12-25 | 2013-12-04 | 2013-12-25 | 22 | No | DUKHCONP03Z4STFF2035, DUKHCONP03Z4STFF2035, DUKHCONP03Z3STRF2040 | DUKHCONP03Z5STRF2040, DUKHCONP03Z4STRF2045, DUKHCONP03Z4STRF2045 | 0 | 0 | ROOF
DUKHCONP03Z4STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 58 | No | DUKHCONP03Z4STRF2055, DUKHCONP03Z4STRF2055 | DUKHCONP03Z4ARRF3630, DUKHCONP03Z4STRF2065, DUKHCONP03Z4ARRF3630, DUKHCONP03Z4STRF2065 | 0 | 0 | ROOF
DUKHCONP03Z4STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 58 | No | DUKHCONP03Z3STRF2065, DUKHCONP03Z4STRF2060, DUKHCONP03Z4STRF2060 | DUKHCONP03Z4AREL3665, DUKHCONP03Z5STRF2065, DUKHCONP03Z4AREL3665, DUKHCONP03Z4ARRF3630, DUKHCONP03Z4ARRF3630, DUKHCONP03Z4WTEX5030 | 0 | 0 | ROOF
DUKHCONP03Z4STRF2055 | Slab-Concrete | 13 | 13 | 0% | 2013-12-22 | 2014-01-05 | 2013-12-22 | 2014-01-05 | 27 | No | DUKHCONP03Z3STRF2055, DUKHCONP03Z4STRF2050, DUKHCONP03Z4STRF2050 | DUKHCONP03Z4MSEX5020, DUKHCONP03Z4ARRF3600, DUKHCONP03Z4MSEX5020, DUKHCONP03Z4MSEX5000, DUKHCONP03Z5STRF2055, DUKHCONP03Z4STRF2060, DUKHCONP03Z4WTEX5030, DUKHCONP03Z4ARRF3600, DUKHCONP03Z4STRF2060, DUKHCONP03Z4WTEX5030, DUKHCONP03Z4MSEX5000 | 0 | 0 | ROOF
DUKHCONP03Z4STRF2050 | Slab-Rebar & Formwork | 20 | 20 | 0% | 2013-12-10 | 2014-01-02 | 2013-12-10 | 2014-01-02 | 27 | No | DUKHCONP03Z4STRF2045, DUKHCONP03Z4STRF2045 | DUKHCONP03Z4STRF2055, DUKHCONP03Z4STRF2055 | 0 | 0 | ROOF
DHBL.K30.L55.25 .15 FINISHING WORKS |  | 180 | 180 | 0% | 2013-11-14 | 2014-06-14 | 2013-11-14 | 2014-06-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.25 .15 .10 INTERNAL FINISHES |  | 180 | 180 | 0% | 2013-11-14 | 2014-06-14 | 2013-11-14 | 2014-06-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.25 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-11-14 | 2014-04-28 | 2013-11-14 | 2014-04-28 | 40 |  |  |  | 0 | 0
DUKHCONP03Z4ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-03-03 | 2014-03-19 | 2014-03-03 | 2014-03-19 | 40 | No | DUKHCONP03Z4ARGF3065, DUKHCONP03Z4ARGF3065, DUKHCONP03Z3ARGF3070 | DUKHCONP03Z4ARGF3080, DUKHCONP03Z4ARGF3095, DUKHCONP03Z5ARGF3070, DUKHCONP03Z4ARGF3080, DUKHCONP03Z4ARGF3075, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 39 | No | DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ACGF4600, DUKHCONP03Z4ACGF4600 | DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ACGF4605, DUKHCONP03Z4ELGF4015, DUKHCONP03Z4ELGF4020, DUKHCONP03Z4ACGF4605, DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ELGF4015, DUKHCONP03Z4ELGF4020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-03-10 | 2014-04-01 | 2014-03-10 | 2014-04-01 | 50 | No | DUKHCONP03Z4ARGF3070, DUKHCONP03Z3ARGF3080, DUKHCONP03Z4ARGF3070 | DUKHCONP03Z5ARGF3080, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3000 | Block work | 25 | 25 | 0% | 2013-11-14 | 2013-12-12 | 2013-11-14 | 2013-12-12 | 36 | No | DUKHCONP03Z3ARGF3000, DUKHCONP03Z4STGF2015, DUKHCONP03Z4STGF2015 | DUKHCONP03Z4PLGF4310, DUKHCONP03Z4ELGF4000, DUKHCONP03Z4ARGF3005, DUKHCONP03Z4ARGF3005, DUKHCONP03Z4PLGF4305, DUKHCONP03Z5ARGF3000, DUKHCONP03Z4PLGF4305, DUKHCONP03Z4ELGF4000, DUKHCONP03Z4PLGF4310 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-03-09 | 2014-03-31 | 2014-03-09 | 2014-03-31 | 40 | No | DUKHCONP03Z4ARGF3070, DUKHCONP03Z3ARGF3075, DUKHCONP03Z4ARGF3070 | DUKHCONP03Z5ARGF3075, DUKHCONP03Z4ARGF3090, DUKHCONP03Z4ARGF3085, DUKHCONP03Z4ARGF3085, DUKHCONP03Z4ARGF3090 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2013-12-31 | 2014-01-28 | 2013-12-31 | 2014-01-28 | 36 | No | DUKHCONP03Z4ARGF3015, DUKHCONP03Z4PLGF4305, DUKHCONP03Z4PLGF4310, DUKHCONP03Z4ARGF3015, DUKHCONP03Z3ARGF3020, DUKHCONP03Z4PLGF4305, DUKHCONP03Z4PLGF4310 | DUKHCONP03Z4ARGF3025, DUKHCONP03Z5ARGF3020, DUKHCONP03Z4ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-02-02 | 2014-02-19 | 2014-02-02 | 2014-02-19 | 40 | No | DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ARGF3025, DUKHCONP03Z4ARGF3025 | DUKHCONP03Z4ARGF3050, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3050 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 40 | No | DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3070, DUKHCONP03Z4ARGF3080, DUKHCONP03Z4ARGF3085, DUKHCONP03Z4ACGF4610, DUKHCONP03Z4ARGF3030, DUKHCONP03Z4ARGF3040, DUKHCONP03Z3ARGF3095, DUKHCONP03Z4ARGF3040, DUKHCONP03Z4ARGF3090, DUKHCONP03Z4ARGF3085, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3070, DUKHCONP03Z4ARGF3080, DUKHCONP03Z4ACGF4610, DUKHCONP03Z4ARGF3030, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3090 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z5ARGF3095, DUKHCONP03Z4ACTC8000, DUKHCONP03Z4ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-01-23 | 2014-02-16 | 2014-01-23 | 2014-02-16 | 36 | No | DUKHCONP03Z4ARGF3025, DUKHCONP03Z4ELGF4010, DUKHCONP03Z4ARGF3030, DUKHCONP03Z4ARGF3030, DUKHCONP03Z4ARGF3025, DUKHCONP03Z3ARGF3045, DUKHCONP03Z4ELGF4010 | DUKHCONP03Z4ARGF3055, DUKHCONP03Z4ARGF3055, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3060, DUKHCONP03Z5ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3010 | Flooring screed | 21 | 21 | 0% | 2013-12-15 | 2014-01-08 | 2013-12-15 | 2014-01-08 | 44 | No | DUKHCONP03Z4ARGF3005, DUKHCONP03Z4ARGF3005 | DUKHCONP03Z4ARGF3040, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3025, DUKHCONP03Z4ARGF3040, DUKHCONP03Z4ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-02-10 | 2014-03-05 | 2014-02-10 | 2014-03-05 | 40 | No | DUKHCONP03Z4ARGF3040, DUKHCONP03Z4ARGF3025, DUKHCONP03Z4ARGF3025, DUKHCONP03Z4ARGF3040 | DUKHCONP03Z4ARGF3065, DUKHCONP03Z4ARGF3085, DUKHCONP03Z4ARGF3065, DUKHCONP03Z4ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-02-04 | 2014-03-05 | 2014-02-04 | 2014-03-05 | 36 | No | DUKHCONP03Z4ACGF4600, DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ARGF3045, DUKHCONP03Z3ARGF3060, DUKHCONP03Z4ACGF4600 | DUKHCONP03Z4ELGF4030, DUKHCONP03Z4ARGF3095, DUKHCONP03Z5ARGF3060, DUKHCONP03Z4ELGF4020, DUKHCONP03Z4ELGF4030, DUKHCONP03Z4ELGF4020, DUKHCONP03Z4PLGF4320, DUKHCONP03Z4ELGF4015, DUKHCONP03Z4ELGF4015, DUKHCONP03Z4ACGF4605, DUKHCONP03Z4PLGF4320, DUKHCONP03Z4ACGF4605, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-03-22 | 2014-04-07 | 2014-03-22 | 2014-04-07 | 40 | No | DUKHCONP03Z4ARGF3075, DUKHCONP03Z4ARGF3075 | DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3030 | Paint First coat | 25 | 25 | 0% | 2013-12-31 | 2014-01-28 | 2013-12-31 | 2014-01-28 | 44 | No | DUKHCONP03Z4ARGF3005, DUKHCONP03Z3ARGF3030, DUKHCONP03Z4ARGF3005 | DUKHCONP03Z5ARGF3030, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3005 | Plastering work | 25 | 25 | 0% | 2013-12-07 | 2014-01-05 | 2013-12-07 | 2014-01-05 | 36 | No | DUKHCONP03Z4PLGF4305, DUKHCONP03Z4PLGF4305, DUKHCONP03Z4ARGF3000, DUKHCONP03Z4ELGF4000, DUKHCONP03Z4ELGF4000, DUKHCONP03Z4ARGF3000, DUKHCONP03Z3ARGF3005 | DUKHCONP03Z4ARGF3030, DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ARGF3015, DUKHCONP03Z4ACGF4600, DUKHCONP03Z5ARGF3005, DUKHCONP03Z4ARGF3015, DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ACGF4600, DUKHCONP03Z4ARGF3030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 36 | No | DUKHCONP03Z3ARGF3025, DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ARGF3020, DUKHCONP03Z4ARGF3020 | DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3035, DUKHCONP03Z5ARGF3025, DUKHCONP03Z4ARGF3050, DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ARGF3040, DUKHCONP03Z4ARGF3050, DUKHCONP03Z4ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 45 | No | DUKHCONP03Z4ARGF3075, DUKHCONP03Z4ARGF3050, DUKHCONP03Z4ARGF3075, DUKHCONP03Z4ARGF3050 | DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-01-26 | 2014-02-12 | 2014-01-26 | 2014-02-12 | 42 | No | DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ARGF3010, DUKHCONP03Z4ARGF3025, DUKHCONP03Z4ARGF3025 | DUKHCONP03Z4ARGF3040, DUKHCONP03Z4ARGF3040, DUKHCONP03Z4ARGF3065, DUKHCONP03Z4ARGF3065, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2013-12-25 | 2014-01-11 | 2013-12-25 | 2014-01-11 | 36 | No | DUKHCONP03Z4ARGF3005, DUKHCONP03Z4ARGF3005, DUKHCONP03Z3ARGF3015 | DUKHCONP03Z4ARGF3020, DUKHCONP03Z5ARGF3015, DUKHCONP03Z4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ARGF3065 | Wooden door | 15 | 15 | 0% | 2014-02-25 | 2014-03-13 | 2014-02-25 | 2014-03-13 | 40 | No | DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3050, DUKHCONP03Z4ARGF3035, DUKHCONP03Z4ARGF3050, DUKHCONP03Z3ARGF3065 | DUKHCONP03Z4PLGF4315, DUKHCONP03Z5ARGF3065, DUKHCONP03Z4ARGF3070, DUKHCONP03Z4ARGF3070, DUKHCONP03Z4PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.25 .15 .10 .15 FIRST FLOORS |  | 144 | 144 | 0% | 2013-12-28 | 2014-06-14 | 2013-12-28 | 2014-06-14 | 0 |  |  |  | 0 | 0
DUKHCONP03Z4ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-04-15 | 2014-05-07 | 2014-04-15 | 2014-05-07 | 0 | Yes | DUKHCONP03Z3ARFF3370, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ARFF3365 | DUKHCONP03Z4ARFF3380, DUKHCONP03Z5ARFF3370, DUKHCONP03Z4ARFF3375, DUKHCONP03Z4ARFF3380, DUKHCONP03Z4ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3355 | Aluminum tile false ceiling | 20 | 20 | 0% | 2014-03-26 | 2014-04-17 | 2014-03-26 | 2014-04-17 | 2 | No | DUKHCONP03Z4ARFF3345, DUKHCONP03Z4ACFF4615, DUKHCONP03Z4ARFF3345, DUKHCONP03Z3ARFF3355, DUKHCONP03Z4ACFF4615 | DUKHCONP03Z4PLFF4340, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ELFF4060, DUKHCONP03Z4ELFF4055, DUKHCONP03Z4ACFF4620, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4PLFF4340, DUKHCONP03Z4ELFF4050, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ACFF4620, DUKHCONP03Z5ARFF3355, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ELFF4055, DUKHCONP03Z4ELFF4050, DUKHCONP03Z4ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-04-22 | 2014-05-14 | 2014-04-22 | 2014-05-14 | 11 | No | DUKHCONP03Z4ARFF3370, DUKHCONP03Z4ARFF3370 | DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3300 | Block work | 25 | 25 | 0% | 2013-12-28 | 2014-01-25 | 2013-12-28 | 2014-01-25 | 0 | Yes | DUKHCONP03Z4STFF2020, DUKHCONP03Z4STFF2020, DUKHCONP03Z4STFF2035, DUKHCONP03Z4STFF2035, DUKHCONP03Z3ARFF3300 | DUKHCONP03Z4ELFF4035, DUKHCONP03Z4ARFF3305, DUKHCONP03Z4ARFF3305, DUKHCONP03Z4PLFF4325, DUKHCONP03Z4PLFF4330, DUKHCONP03Z5ARFF3300, DUKHCONP03Z4PLFF4325, DUKHCONP03Z4ELFF4035, DUKHCONP03Z4PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 0 | Yes | DUKHCONP03Z4ARFF3370, DUKHCONP03Z3ARFF3375, DUKHCONP03Z4ARFF3370 | DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3385, DUKHCONP03Z4ARFF3390, DUKHCONP03Z4ARFF3395, DUKHCONP03Z5ARFF3375, DUKHCONP03Z4ARFF3385, DUKHCONP03Z4ARFF3390 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-02-22 | 2014-03-22 | 2014-02-22 | 2014-03-22 | 0 | Yes | DUKHCONP03Z4PLFF4325, DUKHCONP03Z4PLFF4330, DUKHCONP03Z4ARFF3315, DUKHCONP03Z3ARFF3320, DUKHCONP03Z4PLFF4325, DUKHCONP03Z4PLFF4330, DUKHCONP03Z4ARFF3315 | DUKHCONP03Z5ARFF3320, DUKHCONP03Z4ARFF3325, DUKHCONP03Z4ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 0 | Yes | DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3380, DUKHCONP03Z4ARFF3380, DUKHCONP03Z4ARFF3375, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ARFF3375, DUKHCONP03Z4ACFF4625, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3385, DUKHCONP03Z4ARFF3350, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3350, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3385, DUKHCONP03Z3ARFF3395, DUKHCONP03Z4ARFF3330, DUKHCONP03Z4ARFF3390, DUKHCONP03Z4ACFF4625, DUKHCONP03Z4ARFF3330, DUKHCONP03Z4ARFF3390 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z4ELTC8010, DUKHCONP03Z5ARFF3395, DUKHCONP03Z4ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-03-15 | 2014-04-06 | 2014-03-15 | 2014-04-06 | 0 | Yes | DUKHCONP03Z3ARFF3345, DUKHCONP03Z4ARFF3330, DUKHCONP03Z4ELFF4045, DUKHCONP03Z4ARFF3325, DUKHCONP03Z4ELFF4045, DUKHCONP03Z4ARFF3325, DUKHCONP03Z4ARFF3330 | DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3360, DUKHCONP03Z5ARFF3345, DUKHCONP03Z4ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-01-29 | 2014-02-23 | 2014-01-29 | 2014-02-23 | 15 | No | DUKHCONP03Z4ARFF3305, DUKHCONP03Z4ARFF3305 | DUKHCONP03Z4ARFF3325, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-03-22 | 2014-04-13 | 2014-03-22 | 2014-04-13 | 2 | No | DUKHCONP03Z4ARFF3325, DUKHCONP03Z4ARFF3325 | DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3385, DUKHCONP03Z4ARFF3385, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-03-23 | 2014-04-20 | 2014-03-23 | 2014-04-20 | 0 | Yes | DUKHCONP03Z4ACFF4615, DUKHCONP03Z4ARFF3345, DUKHCONP03Z4ACFF4615, DUKHCONP03Z3ARFF3360, DUKHCONP03Z4ARFF3345 | DUKHCONP03Z4PLFF4340, DUKHCONP03Z4PLFF4340, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ELFF4060, DUKHCONP03Z4ELFF4050, DUKHCONP03Z4ACFF4620, DUKHCONP03Z4ELFF4060, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ELFF4050, DUKHCONP03Z5ARFF3360, DUKHCONP03Z4ELFF4055, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ACFF4620, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-05-05 | 2014-05-27 | 2014-05-05 | 2014-05-27 | 0 | Yes | DUKHCONP03Z4ARFF3375, DUKHCONP03Z4ARFF3350, DUKHCONP03Z4ARFF3350, DUKHCONP03Z4ARFF3375 | DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-05-07 | 2014-05-29 | 2014-05-07 | 2014-05-29 | 0 | Yes | DUKHCONP03Z4ARFF3375, DUKHCONP03Z4ARFF3375 | DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-02-06 | 2014-03-08 | 2014-02-06 | 2014-03-08 | 18 | No | DUKHCONP03Z4ARFF3305, DUKHCONP03Z4ARFF3305 | DUKHCONP03Z4ARFF3345, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3345, DUKHCONP03Z4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 0 | Yes | DUKHCONP03Z4PLFF4325, DUKHCONP03Z4ARFF3300, DUKHCONP03Z4ARFF3300, DUKHCONP03Z4ELFF4035, DUKHCONP03Z4ELFF4035, DUKHCONP03Z3ARFF3305, DUKHCONP03Z4PLFF4325 | DUKHCONP03Z4ARFF3310, DUKHCONP03Z4AREL3665, DUKHCONP03Z4ARFF3315, DUKHCONP03Z4ARFF3330, DUKHCONP03Z4ACFF4615, DUKHCONP03Z4ARFF3315, DUKHCONP03Z5ARFF3305, DUKHCONP03Z4ARFF3310, DUKHCONP03Z4ACFF4615, DUKHCONP03Z4ARFF3330, DUKHCONP03Z4AREL3665 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-03-01 | 2014-03-29 | 2014-03-01 | 2014-03-29 | 0 | Yes | DUKHCONP03Z3ARFF3325, DUKHCONP03Z4ARFF3310, DUKHCONP03Z4ARFF3310, DUKHCONP03Z4ARFF3320, DUKHCONP03Z4ARFF3320 | DUKHCONP03Z4ARFF3350, DUKHCONP03Z5ARFF3325, DUKHCONP03Z4ARFF3350, DUKHCONP03Z4ARFF3345, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3345 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-03-18 | 2014-04-03 | 2014-03-18 | 2014-04-03 | 10 | No | DUKHCONP03Z4ARFF3310, DUKHCONP03Z4ARFF3325, DUKHCONP03Z4ARFF3310, DUKHCONP03Z4ARFF3325 | DUKHCONP03Z4ARFF3365, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-02-12 | 2014-03-01 | 2014-02-12 | 2014-03-01 | 0 | Yes | DUKHCONP03Z3ARFF3315, DUKHCONP03Z4ARFF3305, DUKHCONP03Z4ARFF3305 | DUKHCONP03Z4ARFF3320, DUKHCONP03Z4ARFF3320, DUKHCONP03Z5ARFF3315 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-04-07 | 2014-04-23 | 2014-04-07 | 2014-04-23 | 0 | Yes | DUKHCONP03Z3ARFF3365, DUKHCONP03Z4ARFF3350, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3350, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3335, DUKHCONP03Z4ARFF3355 | DUKHCONP03Z4ARFF3370, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4PLFF4335, DUKHCONP03Z4ARFF3370, DUKHCONP03Z5ARFF3365, DUKHCONP03Z4PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.25 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-01-15 | 2014-03-22 | 2014-01-15 | 2014-03-22 | 72 |  |  |  | 0 | 0
DUKHCONP03Z4ARRF3600 | Block work | 20 | 20 | 0% | 2014-01-15 | 2014-02-06 | 2014-01-15 | 2014-02-06 | 67 | No | DUKHCONP03Z3ARRF3600, DUKHCONP03Z4STRF2055, DUKHCONP03Z4STRF2055 | DUKHCONP03Z4ARRF3605, DUKHCONP03Z5ARRF3600, DUKHCONP03Z4ARRF3605 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3620 | Epoxy Painting | 15 | 15 | 0% | 2014-03-05 | 2014-03-22 | 2014-03-05 | 2014-03-22 | 72 | No | DUKHCONP03Z4ARRF3695, DUKHCONP03Z4ARRF3695 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z4ELTC8010, DUKHCONP03Z4ACTC8000 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-02-06 | 2014-02-24 | 2014-02-06 | 2014-02-24 | 72 | No | DUKHCONP03Z4ARRF3605, DUKHCONP03Z4ARRF3605 | DUKHCONP03Z4ARRF3695, DUKHCONP03Z4ARRF3695 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3695 | Painting | 20 | 20 | 0% | 2014-02-16 | 2014-03-10 | 2014-02-16 | 2014-03-10 | 72 | No | DUKHCONP03Z4ARRF3610, DUKHCONP03Z4ARRF3610 | DUKHCONP03Z4AREL3680, DUKHCONP03Z4ARRF3620, DUKHCONP03Z4AREL3680, DUKHCONP03Z4ARRF3620 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-01-23 | 2014-02-16 | 2014-01-23 | 2014-02-16 | 67 | No | DUKHCONP03Z4ARRF3600, DUKHCONP03Z4ARRF3600 | DUKHCONP03Z4PLRF4345, DUKHCONP03Z4ARRF3610, DUKHCONP03Z4AREL3665, DUKHCONP03Z4PLRF4345, DUKHCONP03Z4ARRF3610 | 0 | 0 | ROOF
DHBL.K30.L55.25 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-01-21 | 2014-04-10 | 2014-01-21 | 2014-04-10 | 55 |  |  |  | 0 | 0
DHBL.K30.L55.25 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-01-21 | 2014-03-27 | 2014-01-21 | 2014-03-27 | 67 |  |  |  | 0 | 0
DUKHCONP03Z4ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 62 | No | DUKHCONP03Z4ARRF3645, DUKHCONP03Z4ARRF3645 | DUKHCONP03Z4ARRF3655, DUKHCONP03Z4ARRF3655 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-03-11 | 2014-03-27 | 2014-03-11 | 2014-03-27 | 67 | No | DUKHCONP03Z4ARRF3655, DUKHCONP03Z4ARRF3655 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z4ACTC8000, DUKHCONP03Z4ELTC8010 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 62 | No | DUKHCONP03Z4ARRF3635, DUKHCONP03Z4ARRF3635 | DUKHCONP03Z4ARRF3645, DUKHCONP03Z4ARRF3645 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-02-27 | 2014-03-22 | 2014-02-27 | 2014-03-22 | 62 | No | DUKHCONP03Z4ARRF3650, DUKHCONP03Z3ARRF3655, DUKHCONP03Z4ARRF3650, DUKHCONP03Z4ARRF3645, DUKHCONP03Z4ARRF3645 | DUKHCONP03Z4ELTC8010, DUKHCONP03Z4ARRF3660, DUKHCONP03Z4PLTC8005, DUKHCONP03Z5ARRF3655, DUKHCONP03Z4PLRF4355, DUKHCONP03Z4ARRF3660, DUKHCONP03Z4PLRF4355 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 62 | No | DUKHCONP03Z4ARRF3630, DUKHCONP03Z4ARRF3630 | DUKHCONP03Z4ARRF3640, DUKHCONP03Z4ARRF3640 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 62 | No | DUKHCONP03Z4STRF2060, DUKHCONP03Z3ARRF3630, DUKHCONP03Z4STRF2065, DUKHCONP03Z4STRF2060, DUKHCONP03Z4STRF2065 | DUKHCONP03Z4ARRF3635, DUKHCONP03Z5ARRF3630, DUKHCONP03Z4ARRF3635 | 0 | 0 | ROOF
DUKHCONP03Z4ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-02-03 | 2014-03-04 | 2014-02-03 | 2014-03-04 | 62 | No | DUKHCONP03Z4ARRF3640, DUKHCONP03Z4ARRF3640 | DUKHCONP03Z4ARRF3650, DUKHCONP03Z4PLRF4350, DUKHCONP03Z4ARRF3655, DUKHCONP03Z4PLRF4350, DUKHCONP03Z4ACRF4630, DUKHCONP03Z4ACRF4630, DUKHCONP03Z4ARRF3655, DUKHCONP03Z4ELRF4070, DUKHCONP03Z4ARRF3650, DUKHCONP03Z4ELRF4070 | 0 | 0 | ROOF
DHBL.K30.L55.25 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-02-18 | 2014-04-10 | 2014-02-18 | 2014-04-10 | 55 |  |  |  | 0 | 0
DUKHCONP03Z4AREL3680 | External Painting | 20 | 20 | 0% | 2014-03-19 | 2014-04-10 | 2014-03-19 | 2014-04-10 | 55 | No | DUKHCONP03Z4ARRF3695, DUKHCONP03Z4AREL3675, DUKHCONP03Z3AREL3680, DUKHCONP03Z4ARRF3695, DUKHCONP03Z4AREL3675 | DUKHCONP03Z4ELTC8010, DUKHCONP03Z4PLTC8005, DUKHCONP03Z4ACTC8000, DUKHCONP03Z5AREL3680 | 0 | 0 | ELEVATION
DUKHCONP03Z4AREL3665 | External Plastering | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 53 | No | DUKHCONP03Z3AREL3665, DUKHCONP03Z4ARFF3305, DUKHCONP03Z4STRF2065, DUKHCONP03Z4STRF2065, DUKHCONP03Z4ARRF3605, DUKHCONP03Z4ARFF3305 | DUKHCONP03Z4PLRF4350, DUKHCONP03Z4AREL3675, DUKHCONP03Z4PLRF4350, DUKHCONP03Z4AREL3675, DUKHCONP03Z5AREL3665 | 0 | 0 | ELEVATION
DUKHCONP03Z4AREL3675 | GRC Panel Works | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 55 | No | DUKHCONP03Z4AREL3665, DUKHCONP03Z4AREL3665, DUKHCONP03Z3AREL3675 | DUKHCONP03Z4AREL3680, DUKHCONP03Z5AREL3675, DUKHCONP03Z4AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L55.25 .20 MEP WORKS |  | 261 | 261 | 0% | 2013-08-04 | 2014-06-11 | 2013-08-04 | 2014-06-11 | 2 |  |  |  | 0 | 0
DHBL.K30.L55.25 .20 .10 ELECTRICAL WORKS |  | 173 | 173 | 0% | 2013-11-20 | 2014-06-11 | 2013-11-20 | 2014-06-11 | 2 |  |  |  | 0 | 0
DHBL.K30.L55.25 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-11-20 | 2014-03-31 | 2013-11-20 | 2014-03-31 | 38 |  |  |  | 0 | 0
DUKHCONP03Z4ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2013-12-02 | 2013-12-25 | 2013-12-02 | 2013-12-25 | 63 | No | DUKHCONP03Z4ELGF4000, DUKHCONP03Z4ELGF4000, DUKHCONP03Z3ELGF4005 | DUKHCONP03Z4ELGF4010, DUKHCONP03Z4ELGF4010, DUKHCONP03Z5ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-11-20 | 2013-12-19 | 2013-11-20 | 2013-12-19 | 45 | No | DUKHCONP03Z4ARGF3000, DUKHCONP03Z4ARGF3000 | DUKHCONP03Z4ELGF4005, DUKHCONP03Z4ARGF3005, DUKHCONP03Z4ARGF3005, DUKHCONP03Z4ELGF4005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 49 | No | DUKHCONP03Z4ARGF3055, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3055, DUKHCONP03Z3ELGF4015 | DUKHCONP03Z4ELFF4055, DUKHCONP03Z4ELFF4055, DUKHCONP03Z4ELTC8010, DUKHCONP03Z5ELGF4015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-02-19 | 2014-03-13 | 2014-02-19 | 2014-03-13 | 36 | No | DUKHCONP03Z4ELGF4010, DUKHCONP03Z4ARGF3055, DUKHCONP03Z4ELGF4010, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3055 | DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ELGF4030, DUKHCONP03Z4ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 38 | No | DUKHCONP03Z4ELGF4020, DUKHCONP03Z4ARGF3055, DUKHCONP03Z4ELGF4020, DUKHCONP03Z4ARGF3055, DUKHCONP03Z3ELGF4025, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3060 | DUKHCONP03Z4ELFF4065, DUKHCONP03Z5ELGF4025, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-03-03 | 2014-03-25 | 2014-03-03 | 2014-03-25 | 36 | No | DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3060, DUKHCONP03Z3ELGF4030, DUKHCONP03Z4ELGF4020, DUKHCONP03Z4ELGF4020 | DUKHCONP03Z5ELGF4030, DUKHCONP03Z4ELTC8010, DUKHCONP03Z4ELFF4050, DUKHCONP03Z4ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 63 | No | DUKHCONP03Z4ELGF4005, DUKHCONP03Z4ELGF4005 | DUKHCONP03Z4ELGF4020, DUKHCONP03Z4ELGF4020, DUKHCONP03Z4ARGF3045, DUKHCONP03Z4ARGF3045 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.25 .20 .10 .15 FIRST FLOORS |  | 116 | 116 | 0% | 2014-01-02 | 2014-05-18 | 2014-01-02 | 2014-05-18 | 5 |  |  |  | 0 | 0
DUKHCONP03Z4ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-01-14 | 2014-02-05 | 2014-01-14 | 2014-02-05 | 33 | No | DUKHCONP03Z4ELFF4035, DUKHCONP03Z4ELFF4035 | DUKHCONP03Z4ELFF4045, DUKHCONP03Z4ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 11 | No | DUKHCONP03Z4ARFF3300, DUKHCONP03Z4ARFF3300 | DUKHCONP03Z4ARFF3305, DUKHCONP03Z4ARFF3305, DUKHCONP03Z4ELFF4040, DUKHCONP03Z4ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 12 | No | DUKHCONP03Z4ELGF4015, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ELGF4015, DUKHCONP03Z4ARFF3360, DUKHCONP03Z3ELFF4055, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3360 | DUKHCONP03Z4ELTC8010, DUKHCONP03Z5ELFF4055 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-04-07 | 2014-04-29 | 2014-04-07 | 2014-04-29 | 2 | No | DUKHCONP03Z4ELFF4045, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3360, DUKHCONP03Z3ELFF4060, DUKHCONP03Z4ELFF4045, DUKHCONP03Z4ARFF3355 | DUKHCONP03Z5ELFF4060, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-04-20 | 2014-05-18 | 2014-04-20 | 2014-05-18 | 2 | No | DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ELFF4060, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ARFF3360, DUKHCONP03Z3ELFF4065, DUKHCONP03Z4ELFF4060, DUKHCONP03Z4ARFF3360 | DUKHCONP03Z4ELRF4070, DUKHCONP03Z5ELFF4065, DUKHCONP03Z4ELTC8010, DUKHCONP03Z4ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 21 | No | DUKHCONP03Z4ARFF3360, DUKHCONP03Z4MSEX5010, DUKHCONP03Z4ELGF4030, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ELGF4030, DUKHCONP03Z4ARFF3355 | DUKHCONP03Z4ELRF4070, DUKHCONP03Z4ELTC8010, DUKHCONP03Z4ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 30 | No | DUKHCONP03Z4ELFF4040, DUKHCONP03Z3ELFF4045, DUKHCONP03Z4ELFF4040 | DUKHCONP03Z4ELFF4060, DUKHCONP03Z4ELRF4070, DUKHCONP03Z4ARFF3345, DUKHCONP03Z4ARFF3345, DUKHCONP03Z4ELRF4070, DUKHCONP03Z4ELFF4060, DUKHCONP03Z5ELFF4045 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.25 .20 .10 .20 ROOF |  | 29 | 29 | 0% | 2014-05-10 | 2014-06-11 | 2014-05-10 | 2014-06-11 | 2 |  |  |  | 0 | 0
DUKHCONP03Z4ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-05-10 | 2014-05-29 | 2014-05-10 | 2014-05-29 | 2 | No | DUKHCONP03Z4ELFF4050, DUKHCONP03Z4ELFF4045, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ARRF3645, DUKHCONP03Z4ELFF4045, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ELFF4050, DUKHCONP03Z4ARRF3645 | DUKHCONP03Z4ELRF4075, DUKHCONP03Z4ELRF4075 | 0 | 0 | ROOF
DUKHCONP03Z4ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-05-17 | 2014-06-11 | 2014-05-17 | 2014-06-11 | 2 | No | DUKHCONP03Z4ELRF4070, DUKHCONP03Z4ELRF4070 | DUKHCONP03Z4ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L55.25 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 249 | 249 | 0% | 2013-08-04 | 2014-05-28 | 2013-08-04 | 2014-05-28 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.25 .20 .15 .10 GROUND FLOOR |  | 199 | 199 | 0% | 2013-08-04 | 2014-03-31 | 2013-08-04 | 2014-03-31 | 64 |  |  |  | 0 | 0
DUKHCONP03Z4PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-08-04 | 2013-08-29 | 2013-08-04 | 2013-08-29 | 0 | Yes | DUKHCONP03Z4STUG1040, DUKHCONP03Z4STUG1040 | DUKHCONP03Z4STUG1045, DUKHCONP03Z4STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-12-01 | 2013-12-22 | 2013-12-01 | 2013-12-22 | 57 | No | DUKHCONP03Z4ARGF3000, DUKHCONP03Z4PLGF4305, DUKHCONP03Z4PLGF4305, DUKHCONP03Z4ARGF3000 | DUKHCONP03Z4ARGF3020, DUKHCONP03Z4PLGF4315, DUKHCONP03Z4MSEX5000, DUKHCONP03Z4MSEX5000, DUKHCONP03Z4PLGF4315, DUKHCONP03Z4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-12-01 | 2013-12-22 | 2013-12-01 | 2013-12-22 | 36 | No | DUKHCONP03Z4ARGF3000, DUKHCONP03Z3PLGF4305, DUKHCONP03Z4ARGF3000 | DUKHCONP03Z5PLGF4305, DUKHCONP03Z4ARGF3005, DUKHCONP03Z4ARGF3005, DUKHCONP03Z4ARGF3020, DUKHCONP03Z4PLGF4310, DUKHCONP03Z4PLGF4310, DUKHCONP03Z4ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-03-15 | 2014-03-31 | 2014-03-15 | 2014-03-31 | 64 | No | DUKHCONP03Z3PLGF4320, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4PLGF4315, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4PLGF4315 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z5PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-03-03 | 2014-03-25 | 2014-03-03 | 2014-03-25 | 64 | No | DUKHCONP03Z4ARGF3065, DUKHCONP03Z3PLGF4315, DUKHCONP03Z4PLGF4310, DUKHCONP03Z4PLGF4310, DUKHCONP03Z4ARGF3065 | DUKHCONP03Z4PLGF4320, DUKHCONP03Z5PLGF4315, DUKHCONP03Z4PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.25 .20 .15 .15 FIRST FLOORS |  | 102 | 102 | 0% | 2014-01-12 | 2014-05-11 | 2014-01-12 | 2014-05-11 | 14 |  |  |  | 0 | 0
DUKHCONP03Z4PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-01-13 | 2014-02-02 | 2014-01-13 | 2014-02-02 | 26 | No | DUKHCONP03Z3PLFF4330, DUKHCONP03Z4PLFF4325, DUKHCONP03Z4ARFF3300, DUKHCONP03Z4PLFF4325, DUKHCONP03Z4ARFF3300 | DUKHCONP03Z4PLRF4350, DUKHCONP03Z4PLFF4335, DUKHCONP03Z4PLRF4350, DUKHCONP03Z5PLFF4330, DUKHCONP03Z4ARFF3320, DUKHCONP03Z4ARFF3320, DUKHCONP03Z4PLFF4335 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-01-12 | 2014-02-01 | 2014-01-12 | 2014-02-01 | 0 | Yes | DUKHCONP03Z4ARFF3300, DUKHCONP03Z4ARFF3300 | DUKHCONP03Z4ARFF3305, DUKHCONP03Z4PLFF4330, DUKHCONP03Z4ARFF3320, DUKHCONP03Z4PLFF4330, DUKHCONP03Z4ARFF3320, DUKHCONP03Z4ARFF3305 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-04-24 | 2014-05-11 | 2014-04-24 | 2014-05-11 | 14 | No | DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3355, DUKHCONP03Z3PLFF4340, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4PLFF4335, DUKHCONP03Z4PLFF4335 | DUKHCONP03Z4PLRF4355, DUKHCONP03Z5PLFF4340, DUKHCONP03Z4PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 14 | No | DUKHCONP03Z4PLFF4330, DUKHCONP03Z4ARFF3365, DUKHCONP03Z4PLFF4330, DUKHCONP03Z4ARFF3365 | DUKHCONP03Z4PLFF4340, DUKHCONP03Z4PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.25 .20 .15 .20 ROOF |  | 95 | 95 | 0% | 2014-02-06 | 2014-05-28 | 2014-02-06 | 2014-05-28 | 14 |  |  |  | 0 | 0
DUKHCONP03Z4PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-02-06 | 2014-02-24 | 2014-02-06 | 2014-02-24 | 71 | No | DUKHCONP03Z4ARRF3605, DUKHCONP03Z4ARRF3605 | DUKHCONP03Z4PLRF4355, DUKHCONP03Z4PLRF4355, DUKHCONP03Z4PLRF4350, DUKHCONP03Z4PLRF4350 | 0 | 0 | ROOF
DUKHCONP03Z4PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-03-10 | 2014-03-26 | 2014-03-10 | 2014-03-26 | 53 | No | DUKHCONP03Z4PLFF4330, DUKHCONP03Z4AREL3665, DUKHCONP03Z4PLFF4330, DUKHCONP03Z4ARRF3645, DUKHCONP03Z4ARRF3645, DUKHCONP03Z4AREL3665, DUKHCONP03Z3PLRF4350, DUKHCONP03Z4PLRF4345, DUKHCONP03Z4PLRF4345 | DUKHCONP03Z4WTEX5065, DUKHCONP03Z4PLRF4355, DUKHCONP03Z4PLRF4355, DUKHCONP03Z4PLTC8005, DUKHCONP03Z5PLRF4350, DUKHCONP03Z4WTEX5065 | 0 | 0 | ROOF
DUKHCONP03Z4PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 14 | No | DUKHCONP03Z4PLRF4345, DUKHCONP03Z4PLRF4345, DUKHCONP03Z4PLFF4340, DUKHCONP03Z4PLRF4350, DUKHCONP03Z4PLRF4350, DUKHCONP03Z4ARRF3655, DUKHCONP03Z3PLRF4355, DUKHCONP03Z4PLFF4340, DUKHCONP03Z4ARRF3655 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z5PLRF4355 | 0 | 0 | ROOF
DHBL.K30.L55.25 .20 .20 AC WORKS |  | 135 | 135 | 0% | 2013-12-22 | 2014-05-28 | 2013-12-22 | 2014-05-28 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.25 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2013-12-22 | 2014-03-29 | 2013-12-22 | 2014-03-29 | 51 |  |  |  | 0 | 0
DUKHCONP03Z4ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 51 | No | DUKHCONP03Z4ACGF4605, DUKHCONP03Z3ACGF4610, DUKHCONP03Z4ACGF4605 | DUKHCONP03Z4ACRF4635, DUKHCONP03Z4ACRF4635, DUKHCONP03Z4ARGF3095, DUKHCONP03Z5ACGF4610, DUKHCONP03Z4ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-02-13 | 2014-03-13 | 2014-02-13 | 2014-03-13 | 51 | No | DUKHCONP03Z4ARGF3055, DUKHCONP03Z4ACGF4600, DUKHCONP03Z4ACGF4600, DUKHCONP03Z4ARGF3055, DUKHCONP03Z3ACGF4605, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ARGF3060 | DUKHCONP03Z4ACGF4610, DUKHCONP03Z5ACGF4605, DUKHCONP03Z4ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z4ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2013-12-22 | 2014-01-13 | 2013-12-22 | 2014-01-13 | 67 | No | DUKHCONP03Z4ARGF3005, DUKHCONP03Z3ACGF4600, DUKHCONP03Z4ARGF3005 | DUKHCONP03Z4ACGF4605, DUKHCONP03Z4ACGF4605, DUKHCONP03Z4ARGF3060, DUKHCONP03Z5ACGF4600, DUKHCONP03Z4ARGF3055, DUKHCONP03Z4ARGF3060, DUKHCONP03Z4ACRF4630, DUKHCONP03Z4ACRF4630, DUKHCONP03Z4ARGF3055 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.25 .20 .20 .15 FIRST FLOORS |  | 87 | 87 | 0% | 2014-02-04 | 2014-05-17 | 2014-02-04 | 2014-05-17 | 9 |  |  |  | 0 | 0
DUKHCONP03Z4ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-04-24 | 2014-05-17 | 2014-04-24 | 2014-05-17 | 9 | No | DUKHCONP03Z4ACFF4620, DUKHCONP03Z3ACFF4625, DUKHCONP03Z4ACFF4620 | DUKHCONP03Z4ACRF4635, DUKHCONP03Z4ACRF4635, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ACTC8000, DUKHCONP03Z5ACFF4625, DUKHCONP03Z4ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-04-03 | 2014-05-01 | 2014-04-03 | 2014-05-01 | 9 | No | DUKHCONP03Z4ACFF4615, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3355, DUKHCONP03Z4ARFF3360, DUKHCONP03Z3ACFF4620, DUKHCONP03Z4ACFF4615 | DUKHCONP03Z4ACFF4625, DUKHCONP03Z5ACFF4620, DUKHCONP03Z4ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z4ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-02-04 | 2014-02-27 | 2014-02-04 | 2014-02-27 | 32 | No | DUKHCONP03Z3ACFF4615, DUKHCONP03Z4ARFF3305, DUKHCONP03Z4ARFF3305 | DUKHCONP03Z4ACFF4620, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ARFF3355, DUKHCONP03Z5ACFF4615, DUKHCONP03Z4ARFF3360, DUKHCONP03Z4ACRF4630, DUKHCONP03Z4ACRF4630, DUKHCONP03Z4ACFF4620, DUKHCONP03Z4ARFF3355 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.25 .20 .20 .20 ROOF |  | 89 | 89 | 0% | 2014-02-15 | 2014-05-28 | 2014-02-15 | 2014-05-28 | 14 |  |  |  | 0 | 0
DUKHCONP03Z4ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 14 | No | DUKHCONP03Z4ACFF4625, DUKHCONP03Z4ACGF4610, DUKHCONP03Z3ACRF4635, DUKHCONP03Z4ACGF4610, DUKHCONP03Z4ACFF4625, DUKHCONP03Z4ACRF4630, DUKHCONP03Z4ACRF4630 | DUKHCONP03Z4ACTC8000, DUKHCONP03Z5ACRF4635 | 0 | 0 | ROOF
DUKHCONP03Z4ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 73 | No | DUKHCONP03Z3ACRF4630, DUKHCONP03Z4ACFF4615, DUKHCONP03Z4ARRF3645, DUKHCONP03Z4ARRF3645, DUKHCONP03Z4ACGF4600, DUKHCONP03Z4ACGF4600, DUKHCONP03Z4ACFF4615 | DUKHCONP03Z5ACRF4630, DUKHCONP03Z4ACRF4635, DUKHCONP03Z4ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L55.25 .25 EXTERNAL WORKS |  | 120 | 120 | 0% | 2014-01-02 | 2014-05-22 | 2014-01-02 | 2014-05-22 | 19 |  |  |  | 0 | 0
DHBL.K30.L55.25 .25 .10 MISCELLANEOUS |  | 88 | 88 | 0% | 2014-01-02 | 2014-04-15 | 2014-01-02 | 2014-04-15 | 33 |  |  |  | 0 | 0
DUKHCONP03Z4MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 47 | No | DUKHCONP03Z4MSEX5000, DUKHCONP03Z4MSEX5000 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z4MSEX5015, DUKHCONP03Z4MSEX5015, DUKHCONP03Z4ELTC8010, DUKHCONP03Z4ACTC8000 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z4MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 21 | No | DUKHCONP03Z4STRF2055, DUKHCONP03Z4STRF2055, DUKHCONP03Z3MSEX5020 | DUKHCONP03Z4MSEX5025, DUKHCONP03Z4MSEX5025, DUKHCONP03Z5MSEX5020 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z4MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-02-05 | 2014-03-01 | 2014-02-05 | 2014-03-01 | 47 | No | DUKHCONP03Z4MSEX5005, DUKHCONP03Z4MSEX5005 | DUKHCONP03Z4WTEX5065, DUKHCONP03Z4WTEX5065, DUKHCONP03Z4MSEX5010 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z4MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-01-02 | 2014-01-30 | 2014-01-02 | 2014-01-30 | 47 | No | DUKHCONP03Z4STRF2055, DUKHCONP03Z4PLGF4310, DUKHCONP03Z4PLGF4310, DUKHCONP03Z4STRF2055 | DUKHCONP03Z4MSEX5005, DUKHCONP03Z4MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z4MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-03-24 | 2014-04-15 | 2014-03-24 | 2014-04-15 | 21 | No | DUKHCONP03Z4MSEX5020, DUKHCONP03Z4MSEX5020 | DUKHCONP03Z4WTEX5060, DUKHCONP03Z4WTEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z4MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 47 | No | DUKHCONP03Z4MSEX5015 | DUKHCONP03Z4ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L55.25 .25 .15 DOMESTIC WATER TANK & PUMP ROOM |  | 118 | 118 | 0% | 2014-01-05 | 2014-05-22 | 2014-01-05 | 2014-05-22 | 19 |  |  |  | 0 | 0
DUKHCONP03Z4WTEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-01-20 | 2014-02-18 | 2014-01-20 | 2014-02-18 | 58 | No | DUKHCONP03Z4WTEX5035, DUKHCONP03Z4WTEX5035 | DUKHCONP03Z4WTEX5045, DUKHCONP03Z4WTEX5080, DUKHCONP03Z4WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 58 | No | DUKHCONP03Z4WTEX5030, DUKHCONP03Z4WTEX5030 | DUKHCONP03Z4WTEX5040, DUKHCONP03Z4WTEX5040 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5075 | Domestic Water Tank AC works | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 58 | No | DUKHCONP03Z4WTEX5070 | DUKHCONP03Z4WTEX5085 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5080 | Domestic Water Tank Electrical works | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 58 | No | DUKHCONP03Z4WTEX5040 | DUKHCONP03Z4WTEX5070 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5085 | Domestic Water Tank Firefighting works | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 58 | No | DUKHCONP03Z4WTEX5075 | DUKHCONP03Z4WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5070 | Domestic Water Tank Plumbings works | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 58 | No | DUKHCONP03Z4WTEX5080 | DUKHCONP03Z4WTEX5075 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5030 | Excavation | 20 | 20 | 0% | 2014-01-05 | 2014-01-27 | 2014-01-05 | 2014-01-27 | 58 | No | DUKHCONP03Z4STRF2055, DUKHCONP03Z3WTEX5030, DUKHCONP03Z4STRF2065, DUKHCONP03Z4STRF2055 | DUKHCONP03Z4WTEX5035, DUKHCONP03Z4WTEX5035, DUKHCONP03Z5WTEX5030 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 58 | No | DUKHCONP03Z4WTEX5040, DUKHCONP03Z4WTEX5085, DUKHCONP03Z4WTEX5040 | DUKHCONP03Z4WTEX5050, DUKHCONP03Z4WTEX5050 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-04-24 | 2014-05-22 | 2014-04-24 | 2014-05-22 | 19 | No | DUKHCONP03Z4PLRF4350, DUKHCONP03Z4WTEX5060, DUKHCONP03Z4WTEX5060, DUKHCONP03Z4MSEX5015, DUKHCONP03Z3WTEX5065, DUKHCONP03Z4PLRF4350, DUKHCONP03Z4MSEX5015 | DUKHCONP03Z4PLTC8005, DUKHCONP03Z5WTEX5065 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-04-05 | 2014-04-27 | 2014-04-05 | 2014-04-27 | 21 | No | DUKHCONP03Z4WTEX5045, DUKHCONP03Z4WTEX5045, DUKHCONP03Z4MSEX5025 | DUKHCONP03Z4WTEX5060, DUKHCONP03Z4WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z4WTEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-04-13 | 2014-05-11 | 2014-04-13 | 2014-05-11 | 19 | No | DUKHCONP03Z4MSEX5025, DUKHCONP03Z4WTEX5050, DUKHCONP03Z4WTEX5050, DUKHCONP03Z3WTEX5060 | DUKHCONP03Z4WTEX5065, DUKHCONP03Z4WTEX5065, DUKHCONP03Z5WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DHBL.K30.L55.25 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 0 |  |  |  | 0 | 0
DUKHCONP03Z4ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 0 | Yes | DUKHCONP03Z3ACTC8000, DUKHCONP03Z4ARRF3620, DUKHCONP03Z4AREL3680, DUKHCONP03Z4ACFF4625, DUKHCONP03Z4ACRF4635, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ARRF3660, DUKHCONP03Z4MSEX5005 | DUKHHANP03GNACTC9000, DUKHCONP03Z5ACTC8000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z4ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 0 | Yes | DUKHCONP03Z4ARRF3655, DUKHCONP03Z4ELFF4055, DUKHCONP03Z4AREL3680, DUKHCONP03Z3ELTC8010, DUKHCONP03Z4ARRF3620, DUKHCONP03Z4ELGF4030, DUKHCONP03Z4ELGF4015, DUKHCONP03Z4ELGF4025, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4ELRF4075, DUKHCONP03Z4ELFF4065, DUKHCONP03Z4ELFF4050, DUKHCONP03Z4MSEX5005, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARRF3660 | DUKHHANP03GNACTC9000, DUKHCONP03Z5ELTC8010, DUKHHANP03GNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z4PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 0 | Yes | DUKHCONP03Z4ARRF3620, DUKHCONP03Z4ARFF3395, DUKHCONP03Z4PLRF4355, DUKHCONP03Z4ARGF3095, DUKHCONP03Z4ARRF3655, DUKHCONP03Z4MSEX5005, DUKHCONP03Z4PLGF4320, DUKHCONP03Z4AREL3680, DUKHCONP03Z4WTEX5065, DUKHCONP03Z4PLRF4350, DUKHCONP03Z3PLTC8005, DUKHCONP03Z4ARRF3660 | DUKHHANP03GNPLTC9005, DUKHCONP03Z5PLTC8005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L55.30 ZONE - 5 (3 Apartments) |  | 372 | 372 | 0% | 2013-05-27 | 2014-08-14 | 2013-05-27 | 2014-08-14 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.30 .10 STRUCTURAL WORKS |  | 230 | 230 | 0% | 2013-05-27 | 2014-02-26 | 2013-05-27 | 2014-02-26 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.30 .10 .10 SUB STRUCTURE |  | 117 | 117 | 0% | 2013-05-27 | 2013-10-13 | 2013-05-27 | 2013-10-13 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.30 .10 .10 .10 UPTO GRADE SLAB |  | 117 | 117 | 0% | 2013-05-27 | 2013-10-13 | 2013-05-27 | 2013-10-13 | 0 |  |  |  | 0 | 0
DUKHCONP03Z5STUG1035 | Backfilling Upto Grade Beam Bottom | 25 | 25 | 0% | 2013-07-30 | 2013-08-31 | 2013-07-30 | 2013-08-31 | 0 | Yes | DUKHCONP03Z5STUG1030, DUKHCONP03Z5STUG1030, DUKHCONP03Z4STUG1035 | DUKHCONP03Z5STUG1040, DUKHCONP03Z5STUG1040 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1020 | Construction of foundations | 20 | 20 | 0% | 2013-07-01 | 2013-07-23 | 2013-07-01 | 2013-07-23 | 0 | Yes | DUKHCONP03Z5STUG1015, DUKHCONP03Z5STUG1015 | DUKHCONP03Z5STUG1025, DUKHCONP03Z5STUG1025 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1040 | Construction of Grade Beams | 25 | 25 | 0% | 2013-08-19 | 2013-09-16 | 2013-08-19 | 2013-09-16 | 0 | Yes | DUKHCONP03Z5STUG1035, DUKHCONP03Z5STUG1035 | DUKHCONP03Z5STUG1045, DUKHCONP03Z5STUG1045, DUKHCONP03Z5PLUG4300, DUKHCONP03Z5PLUG4300 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1025 | Construction of neck of columns | 25 | 25 | 0% | 2013-07-10 | 2013-08-07 | 2013-07-10 | 2013-08-07 | 0 | Yes | DUKHCONP03Z5STUG1020, DUKHCONP03Z4STUG1025, DUKHCONP03Z5STUG1020 | DUKHCONP03Z5STUG1030, DUKHCONP03Z5STUG1030 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1045 | Construction of slab on grade | 25 | 25 | 0% | 2013-09-15 | 2013-10-13 | 2013-09-15 | 2013-10-13 | 0 | Yes | DUKHCONP03Z5STUG1040, DUKHCONP03Z5STUG1040, DUKHCONP03Z5PLUG4300, DUKHCONP03Z5PLUG4300, DUKHCONP03Z4STUG1045 | DUKHCONP03Z5STGF2000, DUKHCONP03Z5STGF2000 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1005 | Footing Antitermite | 23 | 23 | 0% | 2013-06-06 | 2013-07-02 | 2013-06-06 | 2013-07-02 | 0 | Yes | DUKHCONP03Z5STUG1000, DUKHCONP03Z5STUG1000 | DUKHCONP03Z5STUG1010, DUKHCONP03Z5STUG1010 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1010 | Footing Blinding | 23 | 23 | 0% | 2013-06-10 | 2013-07-06 | 2013-06-10 | 2013-07-06 | 0 | Yes | DUKHCONP03Z5STUG1005, DUKHCONP03Z5STUG1005 | DUKHCONP03Z5STUG1015, DUKHCONP03Z5STUG1015 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1000 | Footing Excavation | 25 | 25 | 0% | 2013-05-27 | 2013-06-24 | 2013-05-27 | 2013-06-24 | 0 | Yes | DUKHCONP03Z4STUG1000 | DUKHCONP03Z5STUG1005, DUKHCONP03Z5STUG1005 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1015 | Footing Waterproofing & Screed | 25 | 25 | 0% | 2013-06-16 | 2013-07-14 | 2013-06-16 | 2013-07-14 | 0 | Yes | DUKHCONP03Z5STUG1010, DUKHCONP03Z5STUG1010 | DUKHCONP03Z5STUG1020, DUKHCONP03Z5STUG1020 | 0 | 0 | UPTO GRADE SLAB
DUKHCONP03Z5STUG1030 | Waterproofing Footing & Neck Column | 25 | 25 | 0% | 2013-07-20 | 2013-08-20 | 2013-07-20 | 2013-08-20 | 0 | Yes | DUKHCONP03Z5STUG1025, DUKHCONP03Z5STUG1025 | DUKHCONP03Z5STUG1035, DUKHCONP03Z5STUG1035 | 0 | 0 | UPTO GRADE SLAB
DHBL.K30.L55.30 .10 .15 SUPERSTRUCTURE |  | 124 | 124 | 0% | 2013-10-01 | 2014-02-26 | 2013-10-01 | 2014-02-26 | 58 |  |  |  | 0 | 0
DHBL.K30.L55.30 .10 .15 .10 GROUND FLOOR |  | 49 | 49 | 0% | 2013-10-01 | 2013-11-28 | 2013-10-01 | 2013-11-28 | 0 |  |  |  | 0 | 0
DUKHCONP03Z5STGF2015 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2013-11-12 | 2013-11-28 | 2013-11-12 | 2013-11-28 | 0 | Yes | DUKHCONP03Z5STGF2010, DUKHCONP03Z4STGF2015, DUKHCONP03Z5STGF2010 | DUKHCONP03Z5ARGF3000, DUKHCONP03Z5STFF2020, DUKHCONP03Z5ARGF3000, DUKHCONP03Z5STFF2020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5STGF2010 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-10-28 | 2013-11-25 | 2013-10-28 | 2013-11-25 | 0 | Yes | DUKHCONP03Z5STGF2005, DUKHCONP03Z5STGF2005 | DUKHCONP03Z5STGF2015, DUKHCONP03Z5STGF2015 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5STGF2005 | Column-Concrete | 24 | 24 | 0% | 2013-10-10 | 2013-11-09 | 2013-10-10 | 2013-11-09 | 0 | Yes | DUKHCONP03Z5STGF2000, DUKHCONP03Z5STGF2000 | DUKHCONP03Z5STGF2010, DUKHCONP03Z5STGF2010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5STGF2000 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-10-01 | 2013-10-31 | 2013-10-01 | 2013-10-31 | 0 | Yes | DUKHCONP03Z5STUG1045, DUKHCONP03Z5STUG1045, DUKHCONP03Z4STGF2000 | DUKHCONP03Z5STGF2005, DUKHCONP03Z5STGF2005 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.30 .10 .15 .15 FIRST FLOORS |  | 55 | 55 | 0% | 2013-11-14 | 2014-01-18 | 2013-11-14 | 2014-01-18 | 0 |  |  |  | 0 | 0
DUKHCONP03Z5STFF2035 | Beam, Stairs ,Slab-Concrete | 15 | 15 | 0% | 2014-01-01 | 2014-01-18 | 2014-01-01 | 2014-01-18 | 0 | Yes | DUKHCONP03Z4STFF2035, DUKHCONP03Z5STFF2030, DUKHCONP03Z5STFF2030 | DUKHCONP03Z5ARFF3300, DUKHCONP03Z5STRF2040, DUKHCONP03Z5STRF2040, DUKHCONP03Z5ARFF3300 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5STFF2030 | Beam, Stairs ,Slab-Rebar & Formwork | 25 | 25 | 0% | 2013-12-10 | 2014-01-08 | 2013-12-10 | 2014-01-08 | 0 | Yes | DUKHCONP03Z5STFF2025, DUKHCONP03Z5STFF2025 | DUKHCONP03Z5STFF2035, DUKHCONP03Z5STFF2035 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5STFF2025 | Column-Concrete | 24 | 24 | 0% | 2013-11-25 | 2013-12-23 | 2013-11-25 | 2013-12-23 | 0 | Yes | DUKHCONP03Z5STFF2020, DUKHCONP03Z5STFF2020 | DUKHCONP03Z5STFF2030, DUKHCONP03Z5STFF2030 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5STFF2020 | Column-Rebar & Formwork | 25 | 25 | 0% | 2013-11-14 | 2013-12-12 | 2013-11-14 | 2013-12-12 | 0 | Yes | DUKHCONP03Z5STGF2015, DUKHCONP03Z4STFF2020, DUKHCONP03Z5STGF2015 | DUKHCONP03Z5STFF2025, DUKHCONP03Z5STFF2025, DUKHCONP03Z5ARFF3300, DUKHCONP03Z5ARFF3300 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.30 .10 .15 .20 ROOF |  | 46 | 46 | 0% | 2014-01-04 | 2014-02-26 | 2014-01-04 | 2014-02-26 | 58 |  |  |  | 0 | 0
DUKHCONP03Z5STRF2045 | Column-Concrete | 17 | 17 | 0% | 2014-01-07 | 2014-01-26 | 2014-01-07 | 2014-01-26 | 15 | No | DUKHCONP03Z5STRF2040, DUKHCONP03Z5STRF2040 | DUKHCONP03Z5STRF2050, DUKHCONP03Z5STRF2050 | 0 | 0 | ROOF
DUKHCONP03Z5STRF2040 | Column-Rebar & Formwork | 18 | 18 | 0% | 2014-01-04 | 2014-01-23 | 2014-01-04 | 2014-01-23 | 15 | No | DUKHCONP03Z4STRF2040, DUKHCONP03Z5STFF2035, DUKHCONP03Z5STFF2035 | DUKHCONP03Z5STRF2045, DUKHCONP03Z5STRF2045 | 0 | 0 | ROOF
DUKHCONP03Z5STRF2060 | Construction of Parapets | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 58 | No | DUKHCONP03Z5STRF2055, DUKHCONP03Z5STRF2055 | DUKHCONP03Z5STRF2065, DUKHCONP03Z5ARRF3630, DUKHCONP03Z5STRF2065, DUKHCONP03Z5ARRF3630 | 0 | 0 | ROOF
DUKHCONP03Z5STRF2065 | Construction of up stands/Plinth | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 58 | No | DUKHCONP03Z5STRF2060, DUKHCONP03Z4STRF2065, DUKHCONP03Z5STRF2060 | DUKHCONP03Z5AREL3665, DUKHCONP03Z5AREL3665, DUKHCONP03Z5WTEX5030, DUKHCONP03Z5ARRF3630, DUKHCONP03Z5ARRF3630 | 0 | 0 | ROOF
DUKHCONP03Z5STRF2055 | Slab-Concrete | 13 | 13 | 0% | 2014-01-20 | 2014-02-03 | 2014-01-20 | 2014-02-03 | 15 | No | DUKHCONP03Z5STRF2050, DUKHCONP03Z5STRF2050, DUKHCONP03Z4STRF2055 | DUKHCONP03Z5MSEX5020, DUKHCONP03Z5ARRF3600, DUKHCONP03Z5MSEX5000, DUKHCONP03Z5WTEX5030, DUKHCONP03Z5ARRF3600, DUKHCONP03Z5MSEX5000, DUKHCONP03Z5STRF2060, DUKHCONI03SBIWGL7400, DUKHCONP03Z5WTEX5030, DUKHCONP03Z5MSEX5020, DUKHCONP03Z5STRF2060 | 0 | 0 | ROOF
DUKHCONP03Z5STRF2050 | Slab-Rebar & Formwork | 20 | 20 | 0% | 2014-01-09 | 2014-02-01 | 2014-01-09 | 2014-02-01 | 15 | No | DUKHCONP03Z5STRF2045, DUKHCONP03Z5STRF2045 | DUKHCONP03Z5STRF2055, DUKHCONP03Z5STRF2055 | 0 | 0 | ROOF
DHBL.K30.L55.30 .15 FINISHING WORKS |  | 180 | 180 | 0% | 2013-12-14 | 2014-07-13 | 2013-12-14 | 2014-07-13 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.30 .15 .10 INTERNAL FINISHES |  | 180 | 180 | 0% | 2013-12-14 | 2014-07-13 | 2013-12-14 | 2014-07-13 | 0 |  |  |  | 0 | 0
DHBL.K30.L55.30 .15 .10 .10 GROUND FLOOR |  | 140 | 140 | 0% | 2013-12-14 | 2014-05-27 | 2013-12-14 | 2014-05-27 | 40 |  |  |  | 0 | 0
DUKHCONP03Z5ARGF3070 | Aluminum doors | 15 | 15 | 0% | 2014-04-01 | 2014-04-17 | 2014-04-01 | 2014-04-17 | 40 | No | DUKHCONP03Z5ARGF3065, DUKHCONP03Z5ARGF3065, DUKHCONP03Z4ARGF3070 | DUKHCONP03Z5ARGF3075, DUKHCONP03Z5ARGF3080, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3080, DUKHCONP03Z5ARGF3075 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3055 | Aluminum tile false ceiling | 25 | 25 | 0% | 2014-03-03 | 2014-03-31 | 2014-03-03 | 2014-03-31 | 45 | No | DUKHCONP03Z5ACGF4600, DUKHCONP03Z5ACGF4600, DUKHCONP03Z5ARGF3045, DUKHCONP03Z5ARGF3045 | DUKHCONP03Z5ACGF4605, DUKHCONP03Z5ACGF4605, DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ELGF4015, DUKHCONP03Z5ELGF4015, DUKHCONP03Z5ELGF4025, DUKHCONP03Z5ELGF4025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3080 | Aluminum windows | 20 | 20 | 0% | 2014-04-08 | 2014-04-30 | 2014-04-08 | 2014-04-30 | 50 | No | DUKHCONP03Z5ARGF3070, DUKHCONP03Z4ARGF3080, DUKHCONP03Z5ARGF3070 | DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3000 | Block work | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 40 | No | DUKHCONP03Z5STGF2015, DUKHCONP03Z4ARGF3000, DUKHCONP03Z5STGF2015 | DUKHCONP03Z5PLGF4310, DUKHCONP03Z5ARGF3005, DUKHCONP03Z5ARGF3005, DUKHCONP03Z5PLGF4310, DUKHCONP03Z5PLGF4305, DUKHCONP03Z5PLGF4305, DUKHCONP03Z5ELGF4000, DUKHCONP03Z5ELGF4000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3075 | Carpentry & Joinery Works | 20 | 20 | 0% | 2014-04-07 | 2014-04-29 | 2014-04-07 | 2014-04-29 | 40 | No | DUKHCONP03Z5ARGF3070, DUKHCONP03Z4ARGF3075, DUKHCONP03Z5ARGF3070 | DUKHCONP03Z5ARGF3090, DUKHCONP03Z5ARGF3090, DUKHCONP03Z5ARGF3085, DUKHCONP03Z5ARGF3085 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3020 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 40 | No | DUKHCONP03Z5ARGF3015, DUKHCONP03Z5PLGF4305, DUKHCONP03Z5PLGF4310, DUKHCONP03Z5PLGF4310, DUKHCONP03Z5ARGF3015, DUKHCONP03Z5PLGF4305, DUKHCONP03Z4ARGF3020 | DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3040 | Cobble Tile flooring | 15 | 15 | 0% | 2014-03-04 | 2014-03-20 | 2014-03-04 | 2014-03-20 | 40 | No | DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3010, DUKHCONP03Z5ARGF3010, DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3035 | DUKHCONP03Z5ARGF3050, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3050, DUKHCONP03Z5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3095 | Final Painting | 25 | 25 | 0% | 2014-04-29 | 2014-05-27 | 2014-04-29 | 2014-05-27 | 40 | No | DUKHCONP03Z5ACGF4610, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ARGF3030, DUKHCONP03Z5ARGF3030, DUKHCONP03Z4ARGF3095, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3070, DUKHCONP03Z5ARGF3090, DUKHCONP03Z5ARGF3070, DUKHCONP03Z5ARGF3080, DUKHCONP03Z5ARGF3085, DUKHCONP03Z5ACGF4610, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ARGF3080, DUKHCONP03Z5ARGF3090, DUKHCONP03Z5ARGF3085, DUKHCONP03Z5ARGF3040, DUKHCONP03Z5ARGF3040 | DUKHCONP03Z5ACTC8000, DUKHCONP03Z5PLTC8005, DUKHCONP03Z5ELTC8010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3045 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-02-23 | 2014-03-17 | 2014-02-23 | 2014-03-17 | 42 | No | DUKHCONP03Z5ARGF3030, DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ELGF4010, DUKHCONP03Z5ELGF4010, DUKHCONP03Z5ARGF3030, DUKHCONP03Z4ARGF3045, DUKHCONP03Z5ARGF3025 | DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ARGF3060 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3010 | Flooring screed | 21 | 21 | 0% | 2014-01-14 | 2014-02-06 | 2014-01-14 | 2014-02-06 | 48 | No | DUKHCONP03Z5ARGF3005, DUKHCONP03Z5ARGF3005 | DUKHCONP03Z5ARGF3040, DUKHCONP03Z5ARGF3040, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3025 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3050 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-03-12 | 2014-04-03 | 2014-03-12 | 2014-04-03 | 40 | No | DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3040, DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3040 | DUKHCONP03Z5ARGF3085, DUKHCONP03Z5ARGF3065, DUKHCONP03Z5ARGF3085, DUKHCONP03Z5ARGF3065 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3060 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 42 | No | DUKHCONP03Z5ACGF4600, DUKHCONP03Z4ARGF3060, DUKHCONP03Z5ARGF3045, DUKHCONP03Z5ACGF4600, DUKHCONP03Z5ARGF3045 | DUKHCONP03Z5ARGF3095, DUKHCONP03Z5PLGF4320, DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ACGF4605, DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ELGF4015, DUKHCONP03Z5ELGF4025, DUKHCONP03Z5ELGF4030, DUKHCONP03Z5ELGF4030, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ELGF4015, DUKHCONP03Z5ACGF4605, DUKHCONP03Z5ELGF4025, DUKHCONP03Z5PLGF4320 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3090 | Installation of Granite Counter Top | 15 | 15 | 0% | 2014-04-20 | 2014-05-06 | 2014-04-20 | 2014-05-06 | 40 | No | DUKHCONP03Z5ARGF3075, DUKHCONP03Z5ARGF3075 | DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3030 | Paint First coat | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 50 | No | DUKHCONP03Z5ARGF3005, DUKHCONP03Z4ARGF3030, DUKHCONP03Z5ARGF3005 | DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3045, DUKHCONP03Z5ARGF3045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3005 | Plastering work | 25 | 25 | 0% | 2014-01-06 | 2014-02-03 | 2014-01-06 | 2014-02-03 | 40 | No | DUKHCONP03Z5PLGF4305, DUKHCONP03Z5ARGF3000, DUKHCONP03Z5ARGF3000, DUKHCONP03Z4ARGF3005, DUKHCONP03Z5ELGF4000, DUKHCONP03Z5ELGF4000, DUKHCONP03Z5PLGF4305 | DUKHCONP03Z5ARGF3015, DUKHCONP03Z5ARGF3030, DUKHCONP03Z5ARGF3010, DUKHCONP03Z5ARGF3010, DUKHCONP03Z5ACGF4600, DUKHCONP03Z5ARGF3030, DUKHCONP03Z5ARGF3015, DUKHCONP03Z5ACGF4600 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3025 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-02-04 | 2014-03-05 | 2014-02-04 | 2014-03-05 | 40 | No | DUKHCONP03Z4ARGF3025, DUKHCONP03Z5ARGF3020, DUKHCONP03Z5ARGF3020, DUKHCONP03Z5ARGF3010, DUKHCONP03Z5ARGF3010 | DUKHCONP03Z5ARGF3045, DUKHCONP03Z5ARGF3040, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3050, DUKHCONP03Z5ARGF3050, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3045, DUKHCONP03Z5ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3085 | S.S.Balustrade | 20 | 20 | 0% | 2014-04-15 | 2014-05-07 | 2014-04-15 | 2014-05-07 | 45 | No | DUKHCONP03Z5ARGF3050, DUKHCONP03Z5ARGF3050, DUKHCONP03Z5ARGF3075, DUKHCONP03Z5ARGF3075 | DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3095 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3035 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-02-25 | 2014-03-13 | 2014-02-25 | 2014-03-13 | 42 | No | DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3010, DUKHCONP03Z5ARGF3025, DUKHCONP03Z5ARGF3010 | DUKHCONP03Z5ARGF3065, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARGF3065, DUKHCONP03Z5ARGF3040, DUKHCONP03Z5ARGF3040 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3015 | Wet area waterproofing & Protection Screed | 15 | 15 | 0% | 2014-01-23 | 2014-02-09 | 2014-01-23 | 2014-02-09 | 40 | No | DUKHCONP03Z5ARGF3005, DUKHCONP03Z4ARGF3015, DUKHCONP03Z5ARGF3005 | DUKHCONP03Z5ARGF3020, DUKHCONP03Z5ARGF3020 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ARGF3065 | Wooden door | 15 | 15 | 0% | 2014-03-26 | 2014-04-12 | 2014-03-26 | 2014-04-12 | 40 | No | DUKHCONP03Z5ARGF3035, DUKHCONP03Z4ARGF3065, DUKHCONP03Z5ARGF3035, DUKHCONP03Z5ARGF3050, DUKHCONP03Z5ARGF3050 | DUKHCONP03Z5ARGF3070, DUKHCONP03Z5ARGF3070, DUKHCONP03Z5PLGF4315, DUKHCONP03Z5PLGF4315 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.30 .15 .10 .15 FIRST FLOORS |  | 144 | 144 | 0% | 2014-01-26 | 2014-07-13 | 2014-01-26 | 2014-07-13 | 0 |  |  |  | 0 | 0
DUKHCONP03Z5ARFF3370 | Aluminum Door | 20 | 20 | 0% | 2014-05-14 | 2014-06-05 | 2014-05-14 | 2014-06-05 | 0 | Yes | DUKHCONP03Z4ARFF3370, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3365 | DUKHCONP03Z5ARFF3375, DUKHCONP03Z5ARFF3380, DUKHCONP03Z5ARFF3380, DUKHCONP03Z5ARFF3375 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3355 | Aluminum tile false ceiling | 20 | 20 | 0% | 2014-04-24 | 2014-05-17 | 2014-04-24 | 2014-05-17 | 4 | No | DUKHCONP03Z5ARFF3345, DUKHCONP03Z5ACFF4615, DUKHCONP03Z5ACFF4615, DUKHCONP03Z4ARFF3355, DUKHCONP03Z5ARFF3345 | DUKHCONP03Z5ELFF4060, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ELFF4050, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ELFF4060, DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ELFF4050, DUKHCONP03Z5PLFF4340, DUKHCONP03Z5PLFF4340, DUKHCONP03Z5ELFF4055, DUKHCONP03Z5ACFF4620, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ELFF4055, DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ACFF4620, DUKHCONP03Z5ARFF3365 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3380 | Aluminum windows | 20 | 20 | 0% | 2014-05-21 | 2014-06-12 | 2014-05-21 | 2014-06-12 | 11 | No | DUKHCONP03Z5ARFF3370, DUKHCONP03Z5ARFF3370 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3300 | Block work | 25 | 25 | 0% | 2014-01-26 | 2014-02-24 | 2014-01-26 | 2014-02-24 | 0 | Yes | DUKHCONP03Z5STFF2035, DUKHCONP03Z5STFF2020, DUKHCONP03Z5STFF2020, DUKHCONP03Z5STFF2035, DUKHCONP03Z4ARFF3300 | DUKHCONP03Z5ARFF3305, DUKHCONP03Z5PLFF4325, DUKHCONP03Z5PLFF4325, DUKHCONP03Z5ELFF4035, DUKHCONP03Z5ELFF4035, DUKHCONP03Z5PLFF4330, DUKHCONP03Z5ARFF3305, DUKHCONP03Z5PLFF4330 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3375 | Carpentry & Joinery Works | 25 | 25 | 0% | 2014-05-22 | 2014-06-19 | 2014-05-22 | 2014-06-19 | 0 | Yes | DUKHCONP03Z5ARFF3370, DUKHCONP03Z5ARFF3370, DUKHCONP03Z4ARFF3375 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3390, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3390, DUKHCONP03Z5ARFF3385, DUKHCONP03Z5ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3320 | Ceramic Wall Tiling | 25 | 25 | 0% | 2014-03-23 | 2014-04-20 | 2014-03-23 | 2014-04-20 | 0 | Yes | DUKHCONP03Z4ARFF3320, DUKHCONP03Z5PLFF4330, DUKHCONP03Z5ARFF3315, DUKHCONP03Z5PLFF4325, DUKHCONP03Z5PLFF4325, DUKHCONP03Z5PLFF4330, DUKHCONP03Z5ARFF3315 | DUKHCONP03Z5ARFF3325, DUKHCONP03Z5ARFF3325 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3395 | Final Painting | 25 | 25 | 0% | 2014-06-15 | 2014-07-13 | 2014-06-15 | 2014-07-13 | 0 | Yes | DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3375, DUKHCONP03Z5ARFF3390, DUKHCONP03Z5ARFF3350, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ELFF4055, DUKHCONP03Z5ACFF4625, DUKHCONP03Z5ARFF3330, DUKHCONP03Z5ARFF3380, DUKHCONP03Z5ARFF3335, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3380, DUKHCONP03Z5ACFF4625, DUKHCONP03Z5ARFF3350, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3335, DUKHCONP03Z5ARFF3375, DUKHCONP03Z5ARFF3390, DUKHCONP03Z5ARFF3385, DUKHCONP03Z4ARFF3395, DUKHCONP03Z5ARFF3330, DUKHCONP03Z5ARFF3385 | DUKHCONP03Z5PLTC8005, DUKHCONP03Z5ELTC8010, DUKHCONP03Z5ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3345 | Fixing of Suspension systems | 20 | 20 | 0% | 2014-04-13 | 2014-05-05 | 2014-04-13 | 2014-05-05 | 0 | Yes | DUKHCONP03Z5ARFF3330, DUKHCONP03Z4ARFF3345, DUKHCONP03Z5ELFF4045, DUKHCONP03Z5ELFF4045, DUKHCONP03Z5ARFF3330, DUKHCONP03Z5ARFF3325, DUKHCONP03Z5ARFF3325 | DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3360 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3310 | Flooring screed | 21 | 21 | 0% | 2014-03-01 | 2014-03-24 | 2014-03-01 | 2014-03-24 | 15 | No | DUKHCONP03Z5ARFF3305, DUKHCONP03Z5ARFF3305 | DUKHCONP03Z5ARFF3335, DUKHCONP03Z5ARFF3325, DUKHCONP03Z5ARFF3325, DUKHCONP03Z5ARFF3335 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3350 | Granite - Stair case flooring & Skirting | 20 | 20 | 0% | 2014-04-20 | 2014-05-12 | 2014-04-20 | 2014-05-12 | 4 | No | DUKHCONP03Z5ARFF3325, DUKHCONP03Z5ARFF3325 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3385, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3385 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3360 | Gypsum board false ceiling | 25 | 25 | 0% | 2014-04-21 | 2014-05-19 | 2014-04-21 | 2014-05-19 | 0 | Yes | DUKHCONP03Z5ACFF4615, DUKHCONP03Z5ACFF4615, DUKHCONP03Z4ARFF3360, DUKHCONP03Z5ARFF3345, DUKHCONP03Z5ARFF3345 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ELFF4055, DUKHCONP03Z5ELFF4055, DUKHCONP03Z5ELFF4050, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ELFF4060, DUKHCONP03Z5PLFF4340, DUKHCONP03Z5ACFF4620, DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ACFF4620, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5PLFF4340, DUKHCONP03Z5ELFF4050, DUKHCONP03Z5ELFF4060 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3385 | Handrail & Balustrade | 20 | 20 | 0% | 2014-06-03 | 2014-06-25 | 2014-06-03 | 2014-06-25 | 0 | Yes | DUKHCONP03Z5ARFF3350, DUKHCONP03Z5ARFF3350, DUKHCONP03Z5ARFF3375, DUKHCONP03Z5ARFF3375 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3390 | Installation of Granite Counter Top | 20 | 20 | 0% | 2014-06-07 | 2014-06-29 | 2014-06-07 | 2014-06-29 | 2 | No | DUKHCONP03Z5ARFF3375, DUKHCONP03Z5ARFF3375 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3330 | Paint First coat | 25 | 25 | 0% | 2014-03-09 | 2014-04-06 | 2014-03-09 | 2014-04-06 | 18 | No | DUKHCONP03Z5ARFF3305, DUKHCONP03Z5ARFF3305 | DUKHCONP03Z5ARFF3345, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3345, DUKHCONP03Z5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3305 | Plastering work | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 0 | Yes | DUKHCONP03Z5PLFF4325, DUKHCONP03Z5ARFF3300, DUKHCONP03Z5PLFF4325, DUKHCONP03Z5ELFF4035, DUKHCONP03Z5ELFF4035, DUKHCONP03Z4ARFF3305, DUKHCONP03Z5ARFF3300 | DUKHCONP03Z5ARFF3330, DUKHCONP03Z5ARFF3315, DUKHCONP03Z5ACFF4615, DUKHCONP03Z5ARFF3310, DUKHCONP03Z5ARFF3330, DUKHCONP03Z5ACFF4615, DUKHCONP03Z5AREL3665, DUKHCONP03Z5ARFF3315, DUKHCONP03Z5AREL3665, DUKHCONP03Z5ARFF3310 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3325 | Porcelain Tile flooring | 25 | 25 | 0% | 2014-03-30 | 2014-04-27 | 2014-03-30 | 2014-04-27 | 0 | Yes | DUKHCONP03Z4ARFF3325, DUKHCONP03Z5ARFF3310, DUKHCONP03Z5ARFF3320, DUKHCONP03Z5ARFF3310, DUKHCONP03Z5ARFF3320 | DUKHCONP03Z5ARFF3350, DUKHCONP03Z5ARFF3335, DUKHCONP03Z5ARFF3335, DUKHCONP03Z5ARFF3345, DUKHCONP03Z5ARFF3345, DUKHCONP03Z5ARFF3350 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3335 | Slate Tile Flooring & Skirting | 15 | 15 | 0% | 2014-04-16 | 2014-05-03 | 2014-04-16 | 2014-05-03 | 12 | No | DUKHCONP03Z5ARFF3310, DUKHCONP03Z5ARFF3325, DUKHCONP03Z5ARFF3310, DUKHCONP03Z5ARFF3325 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3315 | Wet area waterproofing | 15 | 15 | 0% | 2014-03-13 | 2014-03-30 | 2014-03-13 | 2014-03-30 | 0 | Yes | DUKHCONP03Z5ARFF3305, DUKHCONP03Z5ARFF3305, DUKHCONP03Z4ARFF3315 | DUKHCONP03Z5ARFF3320, DUKHCONP03Z5ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ARFF3365 | Wooden door | 15 | 15 | 0% | 2014-05-08 | 2014-05-25 | 2014-05-08 | 2014-05-25 | 0 | Yes | DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3350, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3350, DUKHCONP03Z5ARFF3335, DUKHCONP03Z5ARFF3335, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3355, DUKHCONP03Z4ARFF3365 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ARFF3370, DUKHCONP03Z5ARFF3370, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5PLFF4335, DUKHCONP03Z5PLFF4335 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.30 .15 .10 .20 ROOF |  | 56 | 56 | 0% | 2014-02-15 | 2014-04-20 | 2014-02-15 | 2014-04-20 | 72 |  |  |  | 0 | 0
DUKHCONP03Z5ARRF3600 | Block work | 20 | 20 | 0% | 2014-02-15 | 2014-03-09 | 2014-02-15 | 2014-03-09 | 67 | No | DUKHCONP03Z5STRF2055, DUKHCONP03Z5STRF2055, DUKHCONP03Z4ARRF3600 | DUKHCONP03Z5ARRF3605, DUKHCONP03Z5ARRF3605 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3620 | Epoxy Painting | 15 | 15 | 0% | 2014-04-03 | 2014-04-20 | 2014-04-03 | 2014-04-20 | 72 | No | DUKHCONP03Z5ARRF3695, DUKHCONP03Z5ARRF3695 | DUKHCONP03Z5ACTC8000, DUKHCONP03Z5PLTC8005, DUKHCONP03Z5ELTC8010 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3610 | Flooring screed | 15 | 15 | 0% | 2014-03-09 | 2014-03-25 | 2014-03-09 | 2014-03-25 | 72 | No | DUKHCONP03Z5ARRF3605, DUKHCONP03Z5ARRF3605 | DUKHCONP03Z5ARRF3695, DUKHCONP03Z5ARRF3695 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3695 | Painting | 20 | 20 | 0% | 2014-03-17 | 2014-04-08 | 2014-03-17 | 2014-04-08 | 72 | No | DUKHCONP03Z5ARRF3610, DUKHCONP03Z5ARRF3610 | DUKHCONP03Z5AREL3680, DUKHCONP03Z5ARRF3620, DUKHCONP03Z5ARRF3620, DUKHCONP03Z5AREL3680 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3605 | Plastering work | 20 | 20 | 0% | 2014-02-23 | 2014-03-17 | 2014-02-23 | 2014-03-17 | 67 | No | DUKHCONP03Z5ARRF3600, DUKHCONP03Z5ARRF3600 | DUKHCONP03Z5ARRF3610, DUKHCONP03Z5AREL3665, DUKHCONP03Z5ARRF3610, DUKHCONP03Z5PLRF4345, DUKHCONP03Z5PLRF4345 | 0 | 0 | ROOF
DHBL.K30.L55.30 .15 .15 EXTERNAL FINISHES |  | 68 | 68 | 0% | 2014-02-20 | 2014-05-10 | 2014-02-20 | 2014-05-10 | 55 |  |  |  | 0 | 0
DHBL.K30.L55.30 .15 .15 .10 ROOF |  | 56 | 56 | 0% | 2014-02-20 | 2014-04-26 | 2014-02-20 | 2014-04-26 | 67 |  |  |  | 0 | 0
DUKHCONP03Z5ARRF3650 | Install. of Gal. Frame & Aluminum Slat Screen | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 62 | No | DUKHCONP03Z5ARRF3645, DUKHCONP03Z5ARRF3645 | DUKHCONP03Z5ARRF3655, DUKHCONP03Z5ARRF3655 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3660 | Installation of Access Ladder | 15 | 15 | 0% | 2014-04-09 | 2014-04-26 | 2014-04-09 | 2014-04-26 | 67 | No | DUKHCONP03Z5ARRF3655, DUKHCONP03Z5ARRF3655 | DUKHCONP03Z5ELTC8010, DUKHCONP03Z5ACTC8000, DUKHCONP03Z5PLTC8005 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3640 | Installation of Insulation & Protection | 25 | 25 | 0% | 2014-03-01 | 2014-03-29 | 2014-03-01 | 2014-03-29 | 62 | No | DUKHCONP03Z5ARRF3635, DUKHCONP03Z5ARRF3635 | DUKHCONP03Z5ARRF3645, DUKHCONP03Z5ARRF3645 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3655 | Installation of Pumps Protection cabinets | 20 | 20 | 0% | 2014-03-29 | 2014-04-20 | 2014-03-29 | 2014-04-20 | 62 | No | DUKHCONP03Z4ARRF3655, DUKHCONP03Z5ARRF3645, DUKHCONP03Z5ARRF3650, DUKHCONP03Z5ARRF3650, DUKHCONP03Z5ARRF3645 | DUKHCONP03Z5PLRF4355, DUKHCONP03Z5ELTC8010, DUKHCONP03Z5PLTC8005, DUKHCONP03Z5ARRF3660, DUKHCONP03Z5ARRF3660, DUKHCONP03Z5PLRF4355 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3635 | Laying of Waterproofing Membrane | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 62 | No | DUKHCONP03Z5ARRF3630, DUKHCONP03Z5ARRF3630 | DUKHCONP03Z5ARRF3640, DUKHCONP03Z5ARRF3640 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3630 | Leveling Screed for Waterproofing | 25 | 25 | 0% | 2014-02-20 | 2014-03-20 | 2014-02-20 | 2014-03-20 | 62 | No | DUKHCONP03Z5STRF2065, DUKHCONP03Z5STRF2060, DUKHCONP03Z5STRF2065, DUKHCONP03Z4ARRF3630, DUKHCONP03Z5STRF2060 | DUKHCONP03Z5ARRF3635, DUKHCONP03Z5ARRF3635 | 0 | 0 | ROOF
DUKHCONP03Z5ARRF3645 | Lime Stone Chips & Paving slab Installation | 25 | 25 | 0% | 2014-03-05 | 2014-04-02 | 2014-03-05 | 2014-04-02 | 62 | No | DUKHCONP03Z5ARRF3640, DUKHCONP03Z5ARRF3640 | DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ACRF4630, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5ACRF4630, DUKHCONP03Z5ARRF3655, DUKHCONP03Z5ARRF3650, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5ARRF3650, DUKHCONP03Z5ARRF3655 | 0 | 0 | ROOF
DHBL.K30.L55.30 .15 .15 .15 ELEVATION |  | 45 | 45 | 0% | 2014-03-19 | 2014-05-10 | 2014-03-19 | 2014-05-10 | 55 |  |  |  | 0 | 0
DUKHCONP03Z5AREL3680 | External Painting | 20 | 20 | 0% | 2014-04-17 | 2014-05-10 | 2014-04-17 | 2014-05-10 | 55 | No | DUKHCONP03Z5AREL3675, DUKHCONP03Z5ARRF3695, DUKHCONP03Z4AREL3680, DUKHCONP03Z5AREL3675, DUKHCONP03Z5ARRF3695 | DUKHCONP03Z5ACTC8000, DUKHCONP03Z5PLTC8005, DUKHCONP03Z5ELTC8010 | 0 | 0 | ELEVATION
DUKHCONP03Z5AREL3665 | External Plastering | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 53 | No | DUKHCONP03Z5STRF2065, DUKHCONP03Z5STRF2065, DUKHCONP03Z5ARRF3605, DUKHCONP03Z5ARFF3305, DUKHCONP03Z5ARFF3305, DUKHCONP03Z4AREL3665 | DUKHCONP03Z5PLRF4350, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5AREL3675, DUKHCONP03Z5AREL3675 | 0 | 0 | ELEVATION
DUKHCONP03Z5AREL3675 | GRC Panel Works | 20 | 20 | 0% | 2014-04-06 | 2014-04-28 | 2014-04-06 | 2014-04-28 | 55 | No | DUKHCONP03Z5AREL3665, DUKHCONP03Z4AREL3675, DUKHCONP03Z5AREL3665 | DUKHCONP03Z5AREL3680, DUKHCONP03Z5AREL3680 | 0 | 0 | ELEVATION
DHBL.K30.L55.30 .20 MEP WORKS |  | 265 | 265 | 0% | 2013-09-05 | 2014-07-15 | 2013-09-05 | 2014-07-15 | 8 |  |  |  | 0 | 0
DHBL.K30.L55.30 .20 .10 ELECTRICAL WORKS |  | 177 | 177 | 0% | 2013-12-21 | 2014-07-15 | 2013-12-21 | 2014-07-15 | 8 |  |  |  | 0 | 0
DHBL.K30.L55.30 .20 .10 .10 GROUND FLOOR |  | 111 | 111 | 0% | 2013-12-21 | 2014-04-29 | 2013-12-21 | 2014-04-29 | 44 |  |  |  | 0 | 0
DUKHCONP03Z5ELGF4005 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-01-01 | 2014-01-23 | 2014-01-01 | 2014-01-23 | 69 | No | DUKHCONP03Z5ELGF4000, DUKHCONP03Z4ELGF4005, DUKHCONP03Z5ELGF4000 | DUKHCONP03Z5ELGF4010, DUKHCONP03Z5ELGF4010 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ELGF4000 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2013-12-21 | 2014-01-18 | 2013-12-21 | 2014-01-18 | 49 | No | DUKHCONP03Z5ARGF3000, DUKHCONP03Z5ARGF3000 | DUKHCONP03Z5ELGF4005, DUKHCONP03Z5ARGF3005, DUKHCONP03Z5ELGF4005, DUKHCONP03Z5ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ELGF4015 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 49 | No | DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3060, DUKHCONP03Z4ELGF4015 | DUKHCONP03Z5ELFF4055, DUKHCONP03Z5ELTC8010, DUKHCONP03Z5ELFF4055 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ELGF4020 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-03-20 | 2014-04-12 | 2014-03-20 | 2014-04-12 | 42 | No | DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ELGF4010, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ELGF4010 | DUKHCONP03Z5ELGF4025, DUKHCONP03Z5ELGF4025, DUKHCONP03Z5ELGF4030, DUKHCONP03Z5ELGF4030 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ELGF4025 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-04-01 | 2014-04-29 | 2014-04-01 | 2014-04-29 | 44 | No | DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ELGF4020, DUKHCONP03Z4ELGF4025, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3060 | DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ELTC8010, DUKHCONP03Z5ELFF4065 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ELGF4030 | Installation of Telephone System | 20 | 20 | 0% | 2014-04-01 | 2014-04-23 | 2014-04-01 | 2014-04-23 | 42 | No | DUKHCONP03Z4ELGF4030, DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ARGF3060 | DUKHCONP03Z5ELFF4050, DUKHCONP03Z5ELTC8010, DUKHCONP03Z5ELFF4050 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ELGF4010 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-01-09 | 2014-02-06 | 2014-01-09 | 2014-02-06 | 69 | No | DUKHCONP03Z5ELGF4005, DUKHCONP03Z5ELGF4005 | DUKHCONP03Z5ELGF4020, DUKHCONP03Z5ARGF3045, DUKHCONP03Z5ARGF3045, DUKHCONP03Z5ELGF4020 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.30 .20 .10 .15 FIRST FLOORS |  | 116 | 116 | 0% | 2014-02-01 | 2014-06-16 | 2014-02-01 | 2014-06-16 | 11 |  |  |  | 0 | 0
DUKHCONP03Z5ELFF4040 | Cable tray & trunking installation | 20 | 20 | 0% | 2014-02-13 | 2014-03-08 | 2014-02-13 | 2014-03-08 | 33 | No | DUKHCONP03Z5ELFF4035, DUKHCONP03Z5ELFF4035 | DUKHCONP03Z5ELFF4045, DUKHCONP03Z5ELFF4045 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ELFF4035 | Fixing of wall conduits & switch socket boxes | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 11 | No | DUKHCONP03Z5ARFF3300, DUKHCONP03Z5ARFF3300 | DUKHCONP03Z5ARFF3305, DUKHCONP03Z5ELFF4040, DUKHCONP03Z5ARFF3305, DUKHCONP03Z5ELFF4040 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ELFF4055 | Install. of CAMS & Fire Fighting Accessories | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 12 | No | DUKHCONP03Z5ELGF4015, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3355, DUKHCONP03Z4ELFF4055, DUKHCONP03Z5ELGF4015 | DUKHCONP03Z5ELTC8010, DUKHCONP03Z5ARFF3395 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ELFF4060 | Installation of DBS,MCCB Accessories. | 20 | 20 | 0% | 2014-05-06 | 2014-05-28 | 2014-05-06 | 2014-05-28 | 8 | No | DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ELFF4045, DUKHCONP03Z5ELFF4045, DUKHCONP03Z5ARFF3355, DUKHCONP03Z4ELFF4060, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3360 | DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ELFF4065 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ELFF4065 | Installation of Lighting fixtures & Accessories | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 8 | No | DUKHCONP03Z5ELGF4025, DUKHCONP03Z5ELFF4060, DUKHCONP03Z5ARFF3355, DUKHCONP03Z4ELFF4065, DUKHCONP03Z5ELFF4060, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ELGF4025, DUKHCONP03Z5ARFF3355 | DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ELTC8010, DUKHCONP03Z5ELRF4070 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ELFF4050 | Installation of Telephone System | 25 | 25 | 0% | 2014-04-30 | 2014-05-28 | 2014-04-30 | 2014-05-28 | 27 | No | DUKHCONP03Z5MSEX5010, DUKHCONP03Z5ELGF4030, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ELGF4030, DUKHCONP03Z5ARFF3360 | DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ELTC8010 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ELFF4045 | Installation of wiring & Main Cabling | 25 | 25 | 0% | 2014-02-25 | 2014-03-25 | 2014-02-25 | 2014-03-25 | 30 | No | DUKHCONP03Z5ELFF4040, DUKHCONP03Z5ELFF4040, DUKHCONP03Z4ELFF4045 | DUKHCONP03Z5ELFF4060, DUKHCONP03Z5ELFF4060, DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ARFF3345, DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ARFF3345 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.30 .20 .10 .20 ROOF |  | 33 | 33 | 0% | 2014-06-08 | 2014-07-15 | 2014-06-08 | 2014-07-15 | 8 |  |  |  | 0 | 0
DUKHCONP03Z5ELRF4070 | Installation of Isolator | 18 | 18 | 0% | 2014-06-08 | 2014-06-28 | 2014-06-08 | 2014-06-28 | 8 | No | DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ELFF4050, DUKHCONP03Z5ARRF3645, DUKHCONP03Z5ARRF3645, DUKHCONP03Z5ELFF4045, DUKHCONP03Z5ELFF4050, DUKHCONP03Z5ELFF4045, DUKHCONP03Z5ELFF4065 | DUKHCONP03Z5ELRF4075, DUKHCONP03Z5ELRF4075 | 0 | 0 | ROOF
DUKHCONP03Z5ELRF4075 | Installation of TV Dish Antenna | 23 | 23 | 0% | 2014-06-19 | 2014-07-15 | 2014-06-19 | 2014-07-15 | 8 | No | DUKHCONP03Z5ELRF4070, DUKHCONP03Z5ELRF4070 | DUKHCONP03Z5ELTC8010 | 0 | 0 | ROOF
DHBL.K30.L55.30 .20 .15 PLUMBING, DRAINAGE & FIRE FIGHTING WORKS |  | 251 | 251 | 0% | 2013-09-05 | 2014-06-29 | 2013-09-05 | 2014-06-29 | 12 |  |  |  | 0 | 0
DHBL.K30.L55.30 .20 .15 .10 GROUND FLOOR |  | 199 | 199 | 0% | 2013-09-05 | 2014-04-29 | 2013-09-05 | 2014-04-29 | 64 |  |  |  | 0 | 0
DUKHCONP03Z5PLUG4300 | Drainage / Storm Pipes in Grade Slab | 20 | 20 | 0% | 2013-09-05 | 2013-09-28 | 2013-09-05 | 2013-09-28 | 0 | Yes | DUKHCONP03Z5STUG1040, DUKHCONP03Z5STUG1040 | DUKHCONP03Z5STUG1045, DUKHCONP03Z5STUG1045 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5PLGF4310 | Installation of Drainage pipes &testing | 18 | 18 | 0% | 2013-12-31 | 2014-01-20 | 2013-12-31 | 2014-01-20 | 61 | No | DUKHCONP03Z5ARGF3000, DUKHCONP03Z5ARGF3000, DUKHCONP03Z5PLGF4305, DUKHCONP03Z5PLGF4305 | DUKHCONP03Z5MSEX5000, DUKHCONP03Z5ARGF3020, DUKHCONP03Z5PLGF4315, DUKHCONP03Z5ARGF3020, DUKHCONP03Z5PLGF4315, DUKHCONP03Z5MSEX5000 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5PLGF4305 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2013-12-31 | 2014-01-20 | 2013-12-31 | 2014-01-20 | 40 | No | DUKHCONP03Z4PLGF4305, DUKHCONP03Z5ARGF3000, DUKHCONP03Z5ARGF3000 | DUKHCONP03Z5ARGF3005, DUKHCONP03Z5ARGF3020, DUKHCONP03Z5PLGF4310, DUKHCONP03Z5PLGF4310, DUKHCONP03Z5ARGF3020, DUKHCONP03Z5ARGF3005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5PLGF4320 | Installation of Water Heater | 15 | 15 | 0% | 2014-04-13 | 2014-04-29 | 2014-04-13 | 2014-04-29 | 64 | No | DUKHCONP03Z5ARGF3060, DUKHCONP03Z5PLGF4315, DUKHCONP03Z5PLGF4315, DUKHCONP03Z5ARGF3060, DUKHCONP03Z4PLGF4320 | DUKHCONP03Z5PLTC8005 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5PLGF4315 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-04-01 | 2014-04-23 | 2014-04-01 | 2014-04-23 | 64 | No | DUKHCONP03Z5PLGF4310, DUKHCONP03Z5ARGF3065, DUKHCONP03Z4PLGF4315, DUKHCONP03Z5ARGF3065, DUKHCONP03Z5PLGF4310 | DUKHCONP03Z5PLGF4320, DUKHCONP03Z5PLGF4320 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.30 .20 .15 .15 FIRST FLOORS |  | 104 | 104 | 0% | 2014-02-10 | 2014-06-11 | 2014-02-10 | 2014-06-11 | 12 |  |  |  | 0 | 0
DUKHCONP03Z5PLFF4330 | Installation of Drainage pipes & testing | 18 | 18 | 0% | 2014-02-12 | 2014-03-04 | 2014-02-12 | 2014-03-04 | 26 | No | DUKHCONP03Z5PLFF4325, DUKHCONP03Z4PLFF4330, DUKHCONP03Z5PLFF4325, DUKHCONP03Z5ARFF3300, DUKHCONP03Z5ARFF3300 | DUKHCONP03Z5ARFF3320, DUKHCONP03Z5PLFF4335, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5PLFF4335, DUKHCONP03Z5ARFF3320, DUKHCONP03Z5PLRF4350 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5PLFF4325 | Installation of Plumbing pipes & testing | 18 | 18 | 0% | 2014-02-10 | 2014-03-03 | 2014-02-10 | 2014-03-03 | 0 | Yes | DUKHCONP03Z5ARFF3300, DUKHCONP03Z5ARFF3300 | DUKHCONP03Z5ARFF3305, DUKHCONP03Z5ARFF3305, DUKHCONP03Z5PLFF4330, DUKHCONP03Z5PLFF4330, DUKHCONP03Z5ARFF3320, DUKHCONP03Z5ARFF3320 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5PLFF4340 | Installation of Water Heater | 15 | 15 | 0% | 2014-05-26 | 2014-06-11 | 2014-05-26 | 2014-06-11 | 12 | No | DUKHCONP03Z5PLFF4335, DUKHCONP03Z5PLFF4335, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3360, DUKHCONP03Z4PLFF4340 | DUKHCONP03Z5PLRF4355, DUKHCONP03Z5PLRF4355 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5PLFF4335 | Sanitary Fittings & Accessories | 20 | 20 | 0% | 2014-05-14 | 2014-06-05 | 2014-05-14 | 2014-06-05 | 12 | No | DUKHCONP03Z5PLFF4330, DUKHCONP03Z5PLFF4330, DUKHCONP03Z5ARFF3365, DUKHCONP03Z5ARFF3365 | DUKHCONP03Z5PLFF4340, DUKHCONP03Z5PLFF4340 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.30 .20 .15 .20 ROOF |  | 97 | 97 | 0% | 2014-03-09 | 2014-06-29 | 2014-03-09 | 2014-06-29 | 12 |  |  |  | 0 | 0
DUKHCONP03Z5PLRF4345 | Installation of Plumbing pipes & fittings | 15 | 15 | 0% | 2014-03-09 | 2014-03-25 | 2014-03-09 | 2014-03-25 | 71 | No | DUKHCONP03Z5ARRF3605, DUKHCONP03Z5ARRF3605 | DUKHCONP03Z5PLRF4355, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5PLRF4355, DUKHCONP03Z5PLRF4350 | 0 | 0 | ROOF
DUKHCONP03Z5PLRF4350 | Installation of Rain water Pipes | 15 | 15 | 0% | 2014-04-08 | 2014-04-24 | 2014-04-08 | 2014-04-24 | 53 | No | DUKHCONP03Z5PLFF4330, DUKHCONP03Z5PLRF4345, DUKHCONP03Z5PLRF4345, DUKHCONP03Z5ARRF3645, DUKHCONP03Z5AREL3665, DUKHCONP03Z5AREL3665, DUKHCONP03Z5ARRF3645, DUKHCONP03Z4PLRF4350, DUKHCONP03Z5PLFF4330 | DUKHCONP03Z5WTEX5065, DUKHCONP03Z5WTEX5065, DUKHCONP03Z5PLRF4355, DUKHCONP03Z5PLRF4355, DUKHCONP03Z5PLTC8005 | 0 | 0 | ROOF
DUKHCONP03Z5PLRF4355 | Roof Water Tank Installation & Connections | 25 | 25 | 0% | 2014-06-01 | 2014-06-29 | 2014-06-01 | 2014-06-29 | 12 | No | DUKHCONP03Z5PLFF4340, DUKHCONP03Z5PLRF4345, DUKHCONP03Z5PLRF4345, DUKHCONP03Z5ARRF3655, DUKHCONP03Z4PLRF4355, DUKHCONP03Z5PLFF4340, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5ARRF3655 | DUKHCONP03Z5PLTC8005 | 0 | 0 | ROOF
DHBL.K30.L55.30 .20 .20 AC WORKS |  | 135 | 135 | 0% | 2014-01-20 | 2014-06-26 | 2014-01-20 | 2014-06-26 | 14 |  |  |  | 0 | 0
DHBL.K30.L55.30 .20 .20 .10 GROUND FLOOR |  | 83 | 83 | 0% | 2014-01-20 | 2014-04-27 | 2014-01-20 | 2014-04-27 | 51 |  |  |  | 0 | 0
DUKHCONP03Z5ACGF4610 | Fixing of Split AC | 20 | 20 | 0% | 2014-04-05 | 2014-04-27 | 2014-04-05 | 2014-04-27 | 51 | No | DUKHCONP03Z4ACGF4610, DUKHCONP03Z5ACGF4605, DUKHCONP03Z5ACGF4605 | DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ACRF4635, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ACRF4635 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ACGF4605 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-03-15 | 2014-04-12 | 2014-03-15 | 2014-04-12 | 51 | No | DUKHCONP03Z5ACGF4600, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ACGF4600, DUKHCONP03Z5ARGF3060, DUKHCONP03Z4ACGF4605 | DUKHCONP03Z5ACGF4610, DUKHCONP03Z5ACGF4610 | 0 | 0 | GROUND FLOOR
DUKHCONP03Z5ACGF4600 | Installation AC Pipes | 20 | 20 | 0% | 2014-01-20 | 2014-02-12 | 2014-01-20 | 2014-02-12 | 73 | No | DUKHCONP03Z5ARGF3005, DUKHCONP03Z4ACGF4600, DUKHCONP03Z5ARGF3005 | DUKHCONP03Z5ACRF4630, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ACGF4605, DUKHCONP03Z5ARGF3055, DUKHCONP03Z5ARGF3060, DUKHCONP03Z5ACGF4605, DUKHCONP03Z5ACRF4630, DUKHCONP03Z5ARGF3060 | 0 | 0 | GROUND FLOOR
DHBL.K30.L55.30 .20 .20 .15 FIRST FLOORS |  | 87 | 87 | 0% | 2014-03-06 | 2014-06-15 | 2014-03-06 | 2014-06-15 | 9 |  |  |  | 0 | 0
DUKHCONP03Z5ACFF4625 | Fixing of Split AC | 20 | 20 | 0% | 2014-05-24 | 2014-06-15 | 2014-05-24 | 2014-06-15 | 9 | No | DUKHCONP03Z5ACFF4620, DUKHCONP03Z5ACFF4620, DUKHCONP03Z4ACFF4625 | DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ACRF4635, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5ACRF4635, DUKHCONP03Z5ACTC8000 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ACFF4620 | Fixing of Ventilation Equipments | 25 | 25 | 0% | 2014-05-03 | 2014-05-31 | 2014-05-03 | 2014-05-31 | 9 | No | DUKHCONP03Z5ACFF4615, DUKHCONP03Z5ARFF3360, DUKHCONP03Z4ACFF4620, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ACFF4615, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ARFF3360 | DUKHCONP03Z5ACFF4625, DUKHCONP03Z5ACFF4625 | 0 | 0 | FIRST FLOORS
DUKHCONP03Z5ACFF4615 | Installation AC Pipes | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 32 | No | DUKHCONP03Z5ARFF3305, DUKHCONP03Z4ACFF4615, DUKHCONP03Z5ARFF3305 | DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ACRF4630, DUKHCONP03Z5ACFF4620, DUKHCONP03Z5ARFF3360, DUKHCONP03Z5ACRF4630, DUKHCONP03Z5ARFF3355, DUKHCONP03Z5ACFF4620 | 0 | 0 | FIRST FLOORS
DHBL.K30.L55.30 .20 .20 .20 ROOF |  | 89 | 89 | 0% | 2014-03-16 | 2014-06-26 | 2014-03-16 | 2014-06-26 | 14 |  |  |  | 0 | 0
DUKHCONP03Z5ACRF4635 | Installation of Condensing Unit | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 14 | No | DUKHCONP03Z5ACGF4610, DUKHCONP03Z5ACRF4630, DUKHCONP03Z5ACFF4625, DUKHCONP03Z5ACGF4610, DUKHCONP03Z5ACFF4625, DUKHCONP03Z5ACRF4630, DUKHCONP03Z4ACRF4635 | DUKHCONP03Z5ACTC8000 | 0 | 0 | ROOF
DUKHCONP03Z5ACRF4630 | Installation of Refrigerant Pipes | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 73 | No | DUKHCONP03Z5ACGF4600, DUKHCONP03Z4ACRF4630, DUKHCONP03Z5ACFF4615, DUKHCONP03Z5ARRF3645, DUKHCONP03Z5ARRF3645, DUKHCONP03Z5ACFF4615, DUKHCONP03Z5ACGF4600 | DUKHCONP03Z5ACRF4635, DUKHCONP03Z5ACRF4635 | 0 | 0 | ROOF
DHBL.K30.L55.30 .25 EXTERNAL WORKS |  | 120 | 120 | 0% | 2014-02-01 | 2014-06-21 | 2014-02-01 | 2014-06-21 | 19 |  |  |  | 0 | 0
DHBL.K30.L55.30 .25 .10 MISCELLANEOUS |  | 88 | 88 | 0% | 2014-02-01 | 2014-05-14 | 2014-02-01 | 2014-05-14 | 39 |  |  |  | 0 | 0
DUKHCONP03Z5MSEX5005 | Construction of Soak pit, Chambers | 25 | 25 | 0% | 2014-02-16 | 2014-03-16 | 2014-02-16 | 2014-03-16 | 53 | No | DUKHCONP03Z5MSEX5000, DUKHCONP03Z5MSEX5000 | DUKHCONP03Z5MSEX5015, DUKHCONP03Z5PLTC8005, DUKHCONP03Z5ACTC8000, DUKHCONP03Z5MSEX5015, DUKHCONP03Z5ELTC8010 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z5MSEX5020 | Construction Entrance Ramp | 25 | 25 | 0% | 2014-04-05 | 2014-05-03 | 2014-04-05 | 2014-05-03 | 21 | No | DUKHCONP03Z5STRF2055, DUKHCONP03Z4MSEX5020, DUKHCONP03Z5STRF2055 | DUKHCONP03Z5MSEX5025, DUKHCONP03Z5MSEX5025 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z5MSEX5015 | Construction of grease Trap | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 53 | No | DUKHCONP03Z5MSEX5005, DUKHCONP03Z5MSEX5005 | DUKHCONP03Z5MSEX5010, DUKHCONP03Z5WTEX5065, DUKHCONP03Z5WTEX5065 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z5MSEX5000 | Construction of Manholes | 25 | 25 | 0% | 2014-02-01 | 2014-03-02 | 2014-02-01 | 2014-03-02 | 53 | No | DUKHCONP03Z5STRF2055, DUKHCONP03Z5PLGF4310, DUKHCONP03Z5STRF2055, DUKHCONP03Z5PLGF4310 | DUKHCONP03Z5MSEX5005, DUKHCONP03Z5MSEX5005 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z5MSEX5025 | SS.Handrails and Balustrades | 20 | 20 | 0% | 2014-04-22 | 2014-05-14 | 2014-04-22 | 2014-05-14 | 21 | No | DUKHCONP03Z5MSEX5020, DUKHCONP03Z5MSEX5020 | DUKHCONP03Z5WTEX5060, DUKHCONP03Z5WTEX5050 | 0 | 0 | MISCELLANEOUS
DUKHCONP03Z5MSEX5010 | Telephone cable laying | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 53 | No | DUKHCONP03Z5MSEX5015 | DUKHCONP03Z5ELFF4050 | 0 | 0 | MISCELLANEOUS
DHBL.K30.L55.30 .25 .15 DOMESTIC WATER TANK & PUMP ROOM |  | 118 | 118 | 0% | 2014-02-03 | 2014-06-21 | 2014-02-03 | 2014-06-21 | 19 |  |  |  | 0 | 0
DUKHCONP03Z5WTEX5040 | Block works & Plastering | 25 | 25 | 0% | 2014-02-19 | 2014-03-19 | 2014-02-19 | 2014-03-19 | 58 | No | DUKHCONP03Z5WTEX5035, DUKHCONP03Z5WTEX5035 | DUKHCONP03Z5WTEX5080, DUKHCONP03Z5WTEX5045, DUKHCONP03Z5WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5035 | Construction of Raft | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 58 | No | DUKHCONP03Z5WTEX5030, DUKHCONP03Z5WTEX5030 | DUKHCONP03Z5WTEX5040, DUKHCONP03Z5WTEX5040 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5075 | Domestic Water Tank AC works | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 58 | No | DUKHCONP03Z5WTEX5070 | DUKHCONP03Z5WTEX5085 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5080 | Domestic Water Tank Electrical works | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 58 | No | DUKHCONP03Z5WTEX5040 | DUKHCONP03Z5WTEX5070 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5085 | Domestic Water Tank Firefighting works | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 58 | No | DUKHCONP03Z5WTEX5075 | DUKHCONP03Z5WTEX5045 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5070 | Domestic Water Tank Plumbings works | 25 | 25 | 0% | 2014-02-27 | 2014-03-27 | 2014-02-27 | 2014-03-27 | 58 | No | DUKHCONP03Z5WTEX5080 | DUKHCONP03Z5WTEX5075 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5030 | Excavation | 20 | 20 | 0% | 2014-02-03 | 2014-02-26 | 2014-02-03 | 2014-02-26 | 58 | No | DUKHCONP03Z5STRF2055, DUKHCONP03Z5STRF2065, DUKHCONP03Z5STRF2055, DUKHCONP03Z4WTEX5030 | DUKHCONP03Z5WTEX5035, DUKHCONP03Z5WTEX5035 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5045 | Flooring & Painting | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 58 | No | DUKHCONP03Z5WTEX5085, DUKHCONP03Z5WTEX5040, DUKHCONP03Z5WTEX5040 | DUKHCONP03Z5WTEX5050, DUKHCONP03Z5WTEX5050 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5065 | Install. of Water Tank,Chiller,Pump & Meter | 25 | 25 | 0% | 2014-05-24 | 2014-06-21 | 2014-05-24 | 2014-06-21 | 19 | No | DUKHCONP03Z5WTEX5060, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5PLRF4350, DUKHCONP03Z4WTEX5065, DUKHCONP03Z5MSEX5015, DUKHCONP03Z5WTEX5060, DUKHCONP03Z5MSEX5015 | DUKHCONP03Z5PLTC8005 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5050 | Installation of Steel Gate | 20 | 20 | 0% | 2014-05-04 | 2014-05-26 | 2014-05-04 | 2014-05-26 | 21 | No | DUKHCONP03Z5WTEX5045, DUKHCONP03Z5WTEX5045, DUKHCONP03Z5MSEX5025 | DUKHCONP03Z5WTEX5060, DUKHCONP03Z5WTEX5060 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DUKHCONP03Z5WTEX5060 | Structural steel & SS Shed cover installation | 25 | 25 | 0% | 2014-05-12 | 2014-06-09 | 2014-05-12 | 2014-06-09 | 19 | No | DUKHCONP03Z5WTEX5050, DUKHCONP03Z4WTEX5060, DUKHCONP03Z5WTEX5050, DUKHCONP03Z5MSEX5025 | DUKHCONP03Z5WTEX5065, DUKHCONP03Z5WTEX5065 | 0 | 0 | DOMESTIC WATER TANK & PUMP ROOM
DHBL.K30.L55.30 .30 TESTING AND COMMISSIONING |  | 25 | 25 | 0% | 2014-07-14 | 2014-08-14 | 2014-07-14 | 2014-08-14 | 0 |  |  |  | 0 | 0
DUKHCONP03Z5ACTC8000 | Pre-Commissioning & Testing of AC Works | 25 | 25 | 0% | 2014-07-14 | 2014-08-14 | 2014-07-14 | 2014-08-14 | 0 | Yes | DUKHCONP03Z5AREL3680, DUKHCONP03Z5ARRF3620, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ACRF4635, DUKHCONP03Z5ARRF3660, DUKHCONP03Z5MSEX5005, DUKHCONP03Z5ACFF4625, DUKHCONP03Z5ARFF3395, DUKHCONP03Z4ACTC8000 | DUKHHANP03GNACTC9000 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z5ELTC8010 | Pre-Commissioning & Testing of Electrical Works | 25 | 25 | 0% | 2014-07-14 | 2014-08-14 | 2014-07-14 | 2014-08-14 | 0 | Yes | DUKHCONP03Z5ELFF4055, DUKHCONP03Z5ARRF3660, DUKHCONP03Z5ELGF4015, DUKHCONP03Z5ELRF4075, DUKHCONP03Z4ELTC8010, DUKHCONP03Z5ELFF4065, DUKHCONP03Z5ELGF4025, DUKHCONP03Z5ARRF3620, DUKHCONP03Z5ELFF4050, DUKHCONP03Z5ELGF4030, DUKHCONP03Z5ARRF3655, DUKHCONP03Z5AREL3680, DUKHCONP03Z5ARGF3095, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5MSEX5005 | DUKHHANP03GNELTC9010 | 0 | 0 | TESTING AND COMMISSIONING
DUKHCONP03Z5PLTC8005 | Pre-Commissioning & Testing of Plumbing Works | 25 | 25 | 0% | 2014-07-14 | 2014-08-14 | 2014-07-14 | 2014-08-14 | 0 | Yes | DUKHCONP03Z5PLRF4355, DUKHCONP03Z5ARRF3620, DUKHCONP03Z5ARFF3395, DUKHCONP03Z5AREL3680, DUKHCONP03Z5ARGF3095, DUKHCONP03Z4PLTC8005, DUKHCONP03Z5MSEX5005, DUKHCONP03Z5ARRF3655, DUKHCONP03Z5WTEX5065, DUKHCONP03Z5PLRF4350, DUKHCONP03Z5PLGF4320, DUKHCONP03Z5ARRF3660 | DUKHHANP03GNPLTC9005 | 0 | 0 | TESTING AND COMMISSIONING
DHBL.K30.L60 PACKAGE-3 INFRASTRUCTURE WORKS |  | 297 | 297 | 0% | 2013-08-17 | 2014-08-05 | 2013-08-17 | 2014-08-05 | 8 |  |  |  | 0 | 0
DHBL.K30.L60.10 ZONE - 1 |  | 213 | 213 | 0% | 2013-08-17 | 2014-04-26 | 2013-08-17 | 2014-04-26 | 42 |  |  |  | 0 | 0
DHBL.K30.L60.10 .10 INFRASTRUCTURE WORKS |  | 213 | 213 | 0% | 2013-08-17 | 2014-04-26 | 2013-08-17 | 2014-04-26 | 42 |  |  |  | 0 | 0
DHBL.K30.L60.10 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-08-17 | 2013-10-05 | 2013-08-17 | 2013-10-05 | 12 |  |  |  | 0 | 0
DUKHCONI03Z1DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-09-18 | 2013-10-05 | 2013-09-18 | 2013-10-05 | 12 | No | DUKHCONI03Z1DRGL5125, DUKHCONI03Z1DRGL5125 | DUKHCONI03Z2DRGL5115, DUKHCONI03Z1SAGL5140, DUKHCONI03Z1SAGL5135, DUKHCONI03Z1WSGL5155 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z1DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-08-17 | 2013-09-14 | 2013-08-17 | 2013-09-14 | 5 | No | DUKHCONP03Z2STFF2020, DUKHENGI03DWDRAP5810 | DUKHMOBI03PS00002345, DUKHCONI03Z1DRGL5120, DUKHCONI03Z1SAGL5140, DUKHCONI03Z1SAGL5135, DUKHCONI03Z1DRGL5120 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z1DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-08-24 | 2013-09-21 | 2013-08-24 | 2013-09-21 | 12 | No | DUKHCONI03Z1DRGL5115, DUKHCONI03Z1DRGL5115 | DUKHCONI03Z1DRGL5125, DUKHCONI03Z1DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z1DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-09-01 | 2013-09-29 | 2013-09-01 | 2013-09-29 | 12 | No | DUKHCONI03Z1DRGL5120, DUKHCONI03Z1DRGL5120 | DUKHCONI03Z1DRGL5130, DUKHCONI03Z1DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L60.10 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-09-18 | 2013-12-10 | 2013-09-18 | 2013-12-10 | 42 |  |  |  | 0 | 0
DUKHCONI03Z1SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2013-11-18 | 2013-12-10 | 2013-11-18 | 2013-12-10 | 42 | No | DUKHCONI03Z1SAGL5145, DUKHCONI03Z1SAGL5135 | DUKHCONI03Z1RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z1SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-09-18 | 2013-10-16 | 2013-09-18 | 2013-10-16 | 67 | No | DUKHCONI03Z1DRGL5115, DUKHCONI03Z1DRGL5130 | DUKHCONI03Z2SAGL5135, DUKHCONI03Z1SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z1SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2013-10-20 | 2013-11-17 | 2013-10-20 | 2013-11-17 | 14 | No | DUKHCONI03Z1SAGL5140 | DUKHCONI03Z2SAGL5145, DUKHCONI03Z1SAGL5150, DUKHCONI03Z1WSGL5170 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z1SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-09-18 | 2013-10-16 | 2013-09-18 | 2013-10-16 | 14 | No | DUKHCONI03Z1DRGL5115, DUKHCONI03Z1DRGL5130 | DUKHCONI03Z1SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L60.10 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2013-09-30 | 2013-12-16 | 2013-09-30 | 2013-12-16 | 37 |  |  |  | 0 | 0
DUKHCONI03Z1WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2013-10-20 | 2013-11-17 | 2013-10-20 | 2013-11-17 | 14 | No | DUKHCONI03Z1SAGL5145, DUKHCONI03Z1WSGL5165 | DUKHCONI03Z2WSGL5155, DUKHCONI03Z1FFGL5185, DUKHCONI03Z1WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z1WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 37 | No | DUKHCONI03Z1WSGL5170, DUKHCONI03Z1WSGL5155 | DUKHCONI03Z2WSGL5175, DUKHCONI03Z1WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z1WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-09-30 | 2013-10-30 | 2013-09-30 | 2013-10-30 | 14 | No | DUKHENGI03DWWSAP5830, DUKHCONI03Z1DRGL5130 | DUKHCONI03Z1WSGL5160, DUKHCONI03Z1WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z1WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2013-11-24 | 2013-12-16 | 2013-11-24 | 2013-12-16 | 37 | No | DUKHCONI03Z1WSGL5175 | DUKHCONI03Z1FFGL5210, DUKHCONI03Z2WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z1WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-10-06 | 2013-11-05 | 2013-10-06 | 2013-11-05 | 14 | No | DUKHCONI03Z1WSGL5155 | DUKHCONI03Z1WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z1WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2013-10-12 | 2013-11-11 | 2013-10-12 | 2013-11-11 | 14 | No | DUKHCONI03Z1WSGL5160 | DUKHCONI03Z1WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L60.10 .10 .25 FIREFIGHTING LINES |  | 67 | 67 | 0% | 2013-10-26 | 2014-01-12 | 2013-10-26 | 2014-01-12 | 15 |  |  |  | 0 | 0
DUKHCONI03Z1FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 8 | No | DUKHCONI03Z1FFGL5195 | DUKHCONI03Z2FFGL5185, DUKHCONI03Z1FFGL5205, DUKHCONI03Z1RWGL6000, DUKHCONI03Z1ELGL5215 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z1FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2013-12-14 | 2014-01-12 | 2013-12-14 | 2014-01-12 | 15 | No | DUKHCONI03Z1WSGL5180, DUKHCONI03Z1FFGL5205 | DUKHCONI03Z2FFGL5210, DUKHCONI03Z1RWGL6000, DUKHCONI03SBIWGL7440 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z1FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-12-08 | 2014-01-06 | 2013-12-08 | 2014-01-06 | 15 | No | DUKHCONI03Z1FFGL5185, DUKHCONI03Z1FFGL5200, DUKHPROGEN00PRDV3690 | DUKHCONI03Z2FFGL5205, DUKHCONI03Z1FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z1FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2013-10-26 | 2013-11-23 | 2013-10-26 | 2013-11-23 | 14 | No | DUKHENGI03DWFFAP5820, DUKHCONI03Z1WSGL5170 | DUKHCONI03Z1FFGL5205, DUKHCONI03Z1FFGL5190 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z1FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 8 | No | DUKHCONI03Z1FFGL5185, DUKHPROGEN00PRDV3540, DUKHPROGEN00PRDV3650 | DUKHCONI03Z1FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z1FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2013-11-16 | 2013-12-14 | 2013-11-16 | 2013-12-14 | 8 | No | DUKHCONI03Z1FFGL5190 | DUKHCONI03Z1FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L60.10 .10 .30 ELECTRICAL LINES |  | 49 | 49 | 0% | 2013-11-30 | 2014-01-26 | 2013-11-30 | 2014-01-26 | 48 |  |  |  | 0 | 0
DUKHCONI03Z1ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2013-12-16 | 2014-01-14 | 2013-12-16 | 2014-01-14 | 13 | No | DUKHCONI03Z1ELGL5215, DUKHCONI03Z1ELGL5220 | DUKHCONI03Z1IRGL5265, DUKHCONI03Z1RWGL6000, DUKHCONI03Z1ELGL5230, DUKHCONI03Z2ELGL5215, DUKHCONI03Z1ELGL5230, DUKHCONI03Z1IRGL5285 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z1ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2013-12-29 | 2014-01-26 | 2013-12-29 | 2014-01-26 | 48 | No | DUKHCONI03Z1ELGL5225, DUKHCONI03Z1ELGL5225 | DUKHCONI03Z1STGL5260, DUKHCONI03Z2ELGL5230, DUKHCONI03Z1STGL5255 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z1ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 12 | No | DUKHENGI03DWELAP5840, DUKHCONI03Z1FFGL5200 | DUKHCONI03Z1ELGL5220, DUKHCONI03Z1STGL5235, DUKHCONI03Z1ELGL5225 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z1ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 13 | No | DUKHCONI03Z1ELGL5215 | DUKHCONI03Z1ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L60.10 .10 .35 STREET LIGHTING |  | 74 | 74 | 0% | 2013-11-30 | 2014-02-25 | 2013-11-30 | 2014-02-25 | 48 |  |  |  | 0 | 0
DUKHCONI03Z1STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2013-12-11 | 2014-01-09 | 2013-12-11 | 2014-01-09 | 12 | No | DUKHCONI03Z1STGL5245, DUKHCONI03Z1STGL5235 | DUKHCONI03Z1STGL5255, DUKHCONI03Z1RWGL6000, DUKHCONI03Z1TCGL5295, DUKHCONI03Z2STGL5235, DUKHCONI03Z1BWGL5315 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z1STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 12 | No | DUKHCONI03Z1STGL5235 | DUKHCONI03Z1STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z1STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2013-12-05 | 2014-01-04 | 2013-12-05 | 2014-01-04 | 12 | No | DUKHCONI03Z1STGL5240 | DUKHCONI03Z1STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z1STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 48 | No | DUKHCONI03Z1ELGL5230, DUKHCONI03Z1STGL5255 | DUKHCONI03Z1PSGL7015, DUKHCONI03Z2STGL5260 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z1STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2013-11-30 | 2013-12-29 | 2013-11-30 | 2013-12-29 | 12 | No | DUKHENGI03DWSTAP5850, DUKHCONI03Z1ELGL5215 | DUKHCONI03Z1STGL5240, DUKHCONI03Z1STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z1STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-01-13 | 2014-02-10 | 2014-01-13 | 2014-02-10 | 53 | No | DUKHPROGEN00PRDV3350, DUKHPROGEN00PRDV3250, DUKHCONI03Z1STGL5250, DUKHCONI03Z1ELGL5230 | DUKHCONI03Z1STGL5260, DUKHCONI03Z2STGL5255 | 0 | 0 | STREET LIGHTING
DHBL.K30.L60.10 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-01-15 | 2014-03-23 | 2014-01-15 | 2014-03-23 | 31 |  |  |  | 0 | 0
DUKHCONI03Z1IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 21 | No | DUKHCONI03Z1IRGL5275 | DUKHCONI03Z1IRGL5285, DUKHCONI03Z2IRGL5265, DUKHCONI03Z1IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z1IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 31 | No | DUKHCONI03Z1IRGL5280, DUKHCONI03Z1ELGL5225 | DUKHCONI03Z1IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z1IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-01-15 | 2014-02-13 | 2014-01-15 | 2014-02-13 | 21 | No | DUKHCONI03Z1ELGL5225, DUKHENGI03DWIRAP5870 | DUKHCONI03Z1IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z1IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-02-23 | 2014-03-23 | 2014-02-23 | 2014-03-23 | 31 | No | DUKHPROGEN00PRDV3870, DUKHPROGEN00PRDV3760, DUKHPROGEN00PRDV3840, DUKHPROGEN00PRDV3860, DUKHCONI03Z1IRGL5280, DUKHCONI03Z1IRGL5285, DUKHPROGEN00PRDV3810, DUKHPROGEN00PRDV3830 | DUKHCONI03Z1SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z1IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-01-21 | 2014-02-19 | 2014-01-21 | 2014-02-19 | 21 | No | DUKHCONI03Z1IRGL5265 | DUKHCONI03Z1IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z1IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-01-27 | 2014-02-25 | 2014-01-27 | 2014-02-25 | 21 | No | DUKHCONI03Z1IRGL5270 | DUKHCONI03Z1IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L60.10 .10 .45 TELECOMMUNICATION LINES |  | 105 | 105 | 0% | 2013-12-24 | 2014-04-26 | 2013-12-24 | 2014-04-26 | 22 |  |  |  | 0 | 0
DUKHCONI03Z1TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-01-05 | 2014-01-27 | 2014-01-05 | 2014-01-27 | 12 | No | DUKHCONI03Z1TCGL5300 | DUKHCONI03Z1RWGL6000, DUKHCONI03Z2TCGL5295, DUKHCONI03Z1TCGL5310, DUKHCONI03Z1TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z1TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-04-03 | 2014-04-26 | 2014-04-03 | 2014-04-26 | 22 | No | DUKHCONI03Z1PSGL7015, DUKHCONI03Z1TCGL5305, DUKHCONI03Z1TCGL5305 | DUKHCONI03SBTRGL7630, DUKHCONI03Z2TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z1TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2013-12-24 | 2014-01-15 | 2013-12-24 | 2014-01-15 | 12 | No | DUKHCONI03Z1STGL5250, DUKHENGI03DWTCAP5860 | DUKHCONI03Z1TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z1TCGL5300 | Laying of cables | 20 | 20 | 0% | 2013-12-30 | 2014-01-21 | 2013-12-30 | 2014-01-21 | 12 | No | DUKHCONI03Z1TCGL5295 | DUKHCONI03Z1TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L60.10 .10 .50 BOUNDARY WALL |  | 39 | 39 | 0% | 2013-12-24 | 2014-02-06 | 2013-12-24 | 2014-02-06 | 53 |  |  |  | 0 | 0
DUKHCONI03Z1BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2013-12-24 | 2014-01-21 | 2013-12-24 | 2014-01-21 | 53 | No | DUKHENGI03DWBWAP5890, DUKHCONI03Z1STGL5250, DUKHPROGEN00PRDV3820 | DUKHCONI03Z2BWGL5315, DUKHCONI03Z1BWGL5320 | 0 | 0 | BOUNDARY WALL
DUKHCONI03Z1BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-01-09 | 2014-02-06 | 2014-01-09 | 2014-02-06 | 53 | No | DUKHPROGEN00PRDV3800, DUKHCONI03Z1BWGL5315 | DUKHCONI03Z2BWGL5320 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L60.10 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-01-16 | 2014-04-02 | 2014-01-16 | 2014-04-02 | 37 |  |  |  | 0 | 0
DUKHCONI03Z1RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-01-16 | 2014-01-27 | 2014-01-16 | 2014-01-27 | 12 | No | DUKHCONI03Z1FFGL5210, DUKHCONI03Z1TCGL5305, DUKHCONI03Z1ELGL5225, DUKHENGI03DWBWAP5890, DUKHCONI03Z1STGL5250, DUKHCONI03Z1SAGL5150, DUKHCONI03Z1FFGL5200 | DUKHCONI03Z1RWGL6005, DUKHCONI03Z1HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI03Z1RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-03-23 | 2014-03-27 | 2014-03-23 | 2014-03-27 | 37 | No | DUKHCONI03Z1RWGL6020 | DUKHCONI03Z1RWGL6030, DUKHCONI03Z2RWGL6025, DUKHCONI03Z1HDGL7040 | 0 | 0 | ROAD WORKS
DUKHCONI03Z1RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-02-22 | 2014-03-16 | 2014-02-22 | 2014-03-16 | 12 | No | DUKHCONI03Z1RWGL6010 | DUKHCONI03Z2RWGL6000, DUKHCONI03Z1PSGL7005, DUKHCONI03Z1RWGL6020, DUKHCONI03Z1PSGL7000 | 0 | 0 | ROAD WORKS
DUKHCONI03Z1RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 12 | No | DUKHCONI03Z1RWGL6005 | DUKHCONI03Z1RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI03Z1RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-03-17 | 2014-03-22 | 2014-03-17 | 2014-03-22 | 22 | No | DUKHCONI03Z1RWGL6015 | DUKHCONI03Z1RWGL6025, DUKHCONI03Z1PSGL7010 | 0 | 0 | ROAD WORKS
DUKHCONI03Z1RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 12 | No | DUKHCONI03Z1RWGL6000 | DUKHCONI03Z1RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI03Z1RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-03-29 | 2014-04-02 | 2014-03-29 | 2014-04-02 | 37 | No | DUKHCONI03Z1RWGL6025, DUKHPROGEN00PRDV3700, DUKHPROGEN00PRDV3710, DUKHPROGEN00PRDV3720 | DUKHCONI03Z2RWGL6030, DUKHCONI03Z1PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L60.10 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-02-27 | 2014-04-26 | 2014-02-27 | 2014-04-26 | 22 |  |  |  | 0 | 0
DUKHCONI03Z1PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-03-23 | 2014-04-20 | 2014-03-23 | 2014-04-20 | 22 | No | DUKHCONI03Z1RWGL6020, DUKHPROGEN00PRDV3730, DUKHCONI03Z1RWGL6030, DUKHCONI03Z1PSGL7005 | DUKHCONI03Z2PSGL7010, DUKHCONI03Z1PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI03Z1PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-03-29 | 2014-04-26 | 2014-03-29 | 2014-04-26 | 22 | No | DUKHCONI03Z1STGL5260, DUKHCONI03Z1PSGL7010 | DUKHCONI03Z2PSGL7015, DUKHCONI03Z1TCGL5310 | 0 | 0 | PARKING SHED
DUKHCONI03Z1PSGL7000 | Excavation | 15 | 15 | 0% | 2014-02-27 | 2014-03-16 | 2014-02-27 | 2014-03-16 | 27 | No | DUKHENGI03DWPSAP5900, DUKHCONI03Z1RWGL6015 | DUKHCONI03Z1PSGL7005, DUKHCONI03Z1PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI03Z1PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-03-11 | 2014-03-27 | 2014-03-11 | 2014-03-27 | 22 | No | DUKHCONI03Z1PSGL7000, DUKHCONI03Z1RWGL6015, DUKHCONI03Z1PSGL7000 | DUKHCONI03Z2PSGL7000, DUKHCONI03Z1PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L60.10 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-01-16 | 2014-04-08 | 2014-01-16 | 2014-04-08 | 57 |  |  |  | 0 | 0
DUKHCONI03Z1HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 32 | No | DUKHCONI03Z1HDGL7025 | DUKHCONI03Z2HDGL7030, DUKHCONI03Z1HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z1HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-03-29 | 2014-04-08 | 2014-03-29 | 2014-04-08 | 57 | No | DUKHCONI03Z1HDGL7035, DUKHCONI03Z1RWGL6025, DUKHPROGEN00PRDV3750 | DUKHCONI03Z2HDGL7040, DUKHCONI03Z1SLGL7210 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z1HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 32 | No | DUKHPROGEN00PRDV3740, DUKHCONI03Z1HDGL7030 | DUKHCONI03Z1SLGL7200, DUKHCONI03Z1HDGL7040, DUKHCONI03Z2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z1HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-01-28 | 2014-02-26 | 2014-01-28 | 2014-02-26 | 32 | No | DUKHCONI03Z1HDGL7020, DUKHPROGEN00PRDV3600 | DUKHCONI03Z1HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z1HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-01-16 | 2014-02-08 | 2014-01-16 | 2014-02-08 | 32 | No | DUKHCONI03Z1RWGL6000, DUKHENGI03DWSLAP5880 | DUKHCONI03Z1HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L60.10 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-02-23 | 2014-04-15 | 2014-02-23 | 2014-04-15 | 51 |  |  |  | 0 | 0
DUKHCONI03Z1SLGL7200 | Excavation | 25 | 25 | 0% | 2014-02-23 | 2014-03-23 | 2014-02-23 | 2014-03-23 | 31 | No | DUKHCONI03Z1IRGL5290, DUKHCONI03Z1HDGL7035, DUKHENGI03DWSLAP5880 | DUKHCONI03Z1SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI03Z1SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 51 | No | DUKHCONI03Z1HDGL7040, DUKHCONI03Z1SLGL7205 | DUKHCONI03Z2SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI03Z1SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-03-06 | 2014-04-03 | 2014-03-06 | 2014-04-03 | 31 | No | DUKHCONI03Z1SLGL7200 | DUKHCONI03Z2SLGL7200, DUKHCONI03Z1SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L60.15 ZONE- 2 |  | 212 | 212 | 0% | 2013-10-06 | 2014-06-14 | 2013-10-06 | 2014-06-14 | 40 |  |  |  | 0 | 0
DHBL.K30.L60.15 .10 INFRASTRUCTURE WORKS |  | 212 | 212 | 0% | 2013-10-06 | 2014-06-14 | 2013-10-06 | 2014-06-14 | 40 |  |  |  | 0 | 0
DHBL.K30.L60.15 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-10-06 | 2013-11-26 | 2013-10-06 | 2013-11-26 | 12 |  |  |  | 0 | 0
DUKHCONI03Z2DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-11-10 | 2013-11-26 | 2013-11-10 | 2013-11-26 | 12 | No | DUKHCONI03Z2DRGL5125, DUKHCONI03Z2DRGL5125 | DUKHCONI03Z2SAGL5135, DUKHCONI03Z2SAGL5140, DUKHCONI03Z3DRGL5115, DUKHCONI03Z2WSGL5155 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z2DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-10-06 | 2013-11-05 | 2013-10-06 | 2013-11-05 | 12 | No | DUKHCONI03Z1DRGL5130 | DUKHCONI03Z2DRGL5120, DUKHCONI03Z2DRGL5120, DUKHCONI03Z2SAGL5135, DUKHCONI03Z2SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z2DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-10-13 | 2013-11-12 | 2013-10-13 | 2013-11-12 | 12 | No | DUKHCONI03Z2DRGL5115, DUKHCONI03Z2DRGL5115 | DUKHCONI03Z2DRGL5125, DUKHCONI03Z2DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z2DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-10-23 | 2013-11-20 | 2013-10-23 | 2013-11-20 | 12 | No | DUKHCONI03Z2DRGL5120, DUKHCONI03Z2DRGL5120 | DUKHCONI03Z2DRGL5130, DUKHCONI03Z2DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L60.15 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-11-10 | 2014-01-30 | 2013-11-10 | 2014-01-30 | 39 |  |  |  | 0 | 0
DUKHCONI03Z2SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-01-08 | 2014-01-30 | 2014-01-08 | 2014-01-30 | 39 | No | DUKHCONI03Z2SAGL5135, DUKHCONI03Z2SAGL5145 | DUKHCONI03Z2RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z2SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 64 | No | DUKHCONI03Z2DRGL5130, DUKHCONI03Z1SAGL5135, DUKHCONI03Z2DRGL5115 | DUKHCONI03Z2SAGL5150, DUKHCONI03Z3SAGL5135 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z2SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2013-12-09 | 2014-01-07 | 2013-12-09 | 2014-01-07 | 13 | No | DUKHCONI03Z1SAGL5145, DUKHCONI03Z2SAGL5140 | DUKHCONI03Z2WSGL5170, DUKHCONI03Z3SAGL5145, DUKHCONI03Z2SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z2SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-11-10 | 2013-12-08 | 2013-11-10 | 2013-12-08 | 13 | No | DUKHCONI03Z2DRGL5130, DUKHCONI03Z2DRGL5115 | DUKHCONI03Z2SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L60.15 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2013-11-21 | 2014-02-05 | 2013-11-21 | 2014-02-05 | 34 |  |  |  | 0 | 0
DUKHCONI03Z2WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2013-12-09 | 2014-01-07 | 2013-12-09 | 2014-01-07 | 13 | No | DUKHCONI03Z2SAGL5145, DUKHCONI03Z2WSGL5165 | DUKHCONI03Z3WSGL5155, DUKHCONI03Z2WSGL5175, DUKHCONI03Z2FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z2WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2013-12-15 | 2014-01-13 | 2013-12-15 | 2014-01-13 | 34 | No | DUKHCONI03Z1WSGL5175, DUKHCONI03Z2WSGL5155, DUKHCONI03Z2WSGL5170 | DUKHCONI03Z2WSGL5180, DUKHCONI03Z3WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z2WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2013-11-21 | 2013-12-21 | 2013-11-21 | 2013-12-21 | 13 | No | DUKHCONI03Z1WSGL5170, DUKHCONI03Z2DRGL5130 | DUKHCONI03Z2WSGL5175, DUKHCONI03Z2WSGL5160 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z2WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-01-14 | 2014-02-05 | 2014-01-14 | 2014-02-05 | 34 | No | DUKHCONI03Z2WSGL5175, DUKHCONI03Z1WSGL5180 | DUKHCONI03Z3WSGL5180, DUKHCONI03Z2FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z2WSGL5160 | Laying of water line | 25 | 25 | 0% | 2013-11-27 | 2013-12-26 | 2013-11-27 | 2013-12-26 | 13 | No | DUKHCONI03Z2WSGL5155 | DUKHCONI03Z2WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z2WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2013-12-03 | 2014-01-01 | 2013-12-03 | 2014-01-01 | 13 | No | DUKHCONI03Z2WSGL5160 | DUKHCONI03Z2WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L60.15 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2013-12-22 | 2014-02-20 | 2013-12-22 | 2014-02-20 | 22 |  |  |  | 0 | 0
DUKHCONI03Z2FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-01-11 | 2014-02-08 | 2014-01-11 | 2014-02-08 | 8 | No | DUKHCONI03Z2FFGL5195 | DUKHCONI03Z2RWGL6000, DUKHCONI03Z2ELGL5215, DUKHCONI03Z2FFGL5205, DUKHCONI03Z3FFGL5185 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z2FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-01-22 | 2014-02-20 | 2014-01-22 | 2014-02-20 | 22 | No | DUKHCONI03Z1FFGL5210, DUKHCONI03Z2WSGL5180, DUKHCONI03Z2FFGL5205 | DUKHCONI03SBIWGL7440, DUKHCONI03Z3FFGL5210, DUKHCONI03Z2RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z2FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-01-16 | 2014-02-15 | 2014-01-16 | 2014-02-15 | 22 | No | DUKHCONI03Z2FFGL5185, DUKHCONI03Z1FFGL5205, DUKHCONI03Z2FFGL5200 | DUKHCONI03Z3FFGL5205, DUKHCONI03Z2FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z2FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2013-12-22 | 2014-01-19 | 2013-12-22 | 2014-01-19 | 8 | No | DUKHCONI03Z1FFGL5200, DUKHCONI03Z2WSGL5170 | DUKHCONI03Z2FFGL5205, DUKHCONI03Z2FFGL5190 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z2FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2013-12-30 | 2014-01-27 | 2013-12-30 | 2014-01-27 | 8 | No | DUKHCONI03Z2FFGL5185 | DUKHCONI03Z2FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z2FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-01-05 | 2014-02-02 | 2014-01-05 | 2014-02-02 | 8 | No | DUKHCONI03Z2FFGL5190 | DUKHCONI03Z2FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L60.15 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-01-19 | 2014-03-15 | 2014-01-19 | 2014-03-15 | 53 |  |  |  | 0 | 0
DUKHCONI03Z2ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-02-02 | 2014-03-03 | 2014-02-02 | 2014-03-03 | 13 | No | DUKHCONI03Z2ELGL5215, DUKHCONI03Z2ELGL5220 | DUKHCONI03Z2RWGL6000, DUKHCONI03Z3ELGL5215, DUKHCONI03Z2IRGL5265, DUKHCONI03Z2IRGL5285, DUKHCONI03Z2ELGL5230, DUKHCONI03Z2ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z2ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-02-15 | 2014-03-15 | 2014-02-15 | 2014-03-15 | 53 | No | DUKHCONI03Z1ELGL5230, DUKHCONI03Z2ELGL5225, DUKHCONI03Z2ELGL5225 | DUKHCONI03Z3ELGL5230, DUKHCONI03Z2STGL5260 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z2ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 10 | No | DUKHCONI03Z2FFGL5200, DUKHCONI03Z1ELGL5225 | DUKHCONI03Z2ELGL5225, DUKHCONI03Z2ELGL5220, DUKHCONI03Z2STGL5235 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z2ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 13 | No | DUKHCONI03Z2ELGL5215 | DUKHCONI03Z2ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L60.15 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-01-19 | 2014-04-13 | 2014-01-19 | 2014-04-13 | 53 |  |  |  | 0 | 0
DUKHCONI03Z2STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-01-30 | 2014-03-01 | 2014-01-30 | 2014-03-01 | 10 | No | DUKHCONI03Z2STGL5245, DUKHCONI03Z2STGL5235 | DUKHCONI03Z2BWGL5315, DUKHCONI03Z2RWGL6000, DUKHCONI03Z2TCGL5295, DUKHCONI03Z3STGL5235, DUKHCONI03Z2STGL5255 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z2STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 10 | No | DUKHCONI03Z2STGL5235 | DUKHCONI03Z2STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z2STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-01-25 | 2014-02-23 | 2014-01-25 | 2014-02-23 | 10 | No | DUKHCONI03Z2STGL5240 | DUKHCONI03Z2STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z2STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 53 | No | DUKHCONI03Z2STGL5255, DUKHCONI03Z1STGL5260, DUKHCONI03Z2ELGL5230 | DUKHCONI03Z3STGL5260, DUKHCONI03Z2PSGL7015 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z2STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-01-19 | 2014-02-17 | 2014-01-19 | 2014-02-17 | 10 | No | DUKHCONI03Z1STGL5250, DUKHCONI03Z2ELGL5215 | DUKHCONI03Z2STGL5250, DUKHCONI03Z2STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z2STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 73 | No | DUKHCONI03Z1STGL5255, DUKHCONI03Z2STGL5250 | DUKHCONI03Z2STGL5260, DUKHCONI03Z3STGL5255 | 0 | 0 | STREET LIGHTING
DHBL.K30.L60.15 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-03-04 | 2014-05-08 | 2014-03-04 | 2014-05-08 | 26 |  |  |  | 0 | 0
DUKHCONI03Z2IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 21 | No | DUKHCONI03Z2IRGL5275 | DUKHCONI03Z2IRGL5290, DUKHCONI03Z3IRGL5265, DUKHCONI03Z2IRGL5285 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z2IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 26 | No | DUKHCONI03Z2ELGL5225, DUKHCONI03Z2IRGL5280 | DUKHCONI03Z2IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z2IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-03-04 | 2014-04-01 | 2014-03-04 | 2014-04-01 | 21 | No | DUKHCONI03Z1IRGL5280, DUKHCONI03Z2ELGL5225 | DUKHCONI03Z2IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z2IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-04-10 | 2014-05-08 | 2014-04-10 | 2014-05-08 | 26 | No | DUKHCONI03Z2IRGL5285, DUKHCONI03Z2IRGL5280 | DUKHCONI03Z2SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z2IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 21 | No | DUKHCONI03Z2IRGL5265 | DUKHCONI03Z2IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z2IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 21 | No | DUKHCONI03Z2IRGL5270 | DUKHCONI03Z2IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L60.15 .10 .45 TELECOMMUNICATION LINES |  | 83 | 83 | 0% | 2014-02-12 | 2014-05-19 | 2014-02-12 | 2014-05-19 | 22 |  |  |  | 0 | 0
DUKHCONI03Z2TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-02-24 | 2014-03-18 | 2014-02-24 | 2014-03-18 | 10 | No | DUKHCONI03Z2TCGL5300 | DUKHCONI03Z2RWGL6000, DUKHCONI03Z2TCGL5310, DUKHCONI03Z3TCGL5295 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z2TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-04-27 | 2014-05-19 | 2014-04-27 | 2014-05-19 | 22 | No | DUKHCONI03Z1TCGL5310, DUKHCONI03Z2TCGL5305 | DUKHCONI03SBTRGL7630, DUKHCONI03Z3TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z2TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-02-12 | 2014-03-06 | 2014-02-12 | 2014-03-06 | 10 | No | DUKHCONI03Z1TCGL5305, DUKHCONI03Z2STGL5250 | DUKHCONI03Z2TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z2TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-02-18 | 2014-03-12 | 2014-02-18 | 2014-03-12 | 10 | No | DUKHCONI03Z2TCGL5295 | DUKHCONI03Z2TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L60.15 .10 .50 BOUNDARY WALL |  | 39 | 39 | 0% | 2014-02-12 | 2014-03-29 | 2014-02-12 | 2014-03-29 | 36 |  |  |  | 0 | 0
DUKHCONI03Z2BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-02-12 | 2014-03-12 | 2014-02-12 | 2014-03-12 | 36 | No | DUKHCONI03Z2STGL5250, DUKHCONI03Z1BWGL5315 | DUKHCONI03Z2BWGL5320, DUKHCONI03Z3BWGL5315 | 0 | 0 | BOUNDARY WALL
DUKHCONI03Z2BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-03-01 | 2014-03-29 | 2014-03-01 | 2014-03-29 | 36 | No | DUKHCONI03Z2BWGL5315, DUKHCONI03Z1BWGL5320 | DUKHCONI03Z3BWGL5320 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L60.15 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-03-08 | 2014-05-21 | 2014-03-08 | 2014-05-21 | 40 |  |  |  | 0 | 0
DUKHCONI03Z2RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-03-08 | 2014-03-18 | 2014-03-08 | 2014-03-18 | 10 | No | DUKHCONI03Z2ELGL5225, DUKHCONI03Z1RWGL6015, DUKHCONI03Z2STGL5250, DUKHCONI03Z2FFGL5200, DUKHCONI03Z2TCGL5305, DUKHCONI03Z2FFGL5210, DUKHCONI03Z2SAGL5150 | DUKHCONI03Z2RWGL6005, DUKHCONI03Z2HDGL7020 | 0 | 0 | ROAD WORKS
DUKHCONI03Z2RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-05-11 | 2014-05-15 | 2014-05-11 | 2014-05-15 | 40 | No | DUKHCONI03Z1RWGL6025, DUKHCONI03Z2RWGL6020 | DUKHCONI03Z3RWGL6025, DUKHCONI03Z2HDGL7040, DUKHCONI03Z2RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI03Z2RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-04-12 | 2014-05-04 | 2014-04-12 | 2014-05-04 | 10 | No | DUKHCONI03Z2RWGL6010 | DUKHCONI03Z2PSGL7005, DUKHCONI03Z2PSGL7000, DUKHCONI03Z3RWGL6000, DUKHCONI03Z2RWGL6020 | 0 | 0 | ROAD WORKS
DUKHCONI03Z2RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 10 | No | DUKHCONI03Z2RWGL6005 | DUKHCONI03Z2RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI03Z2RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-05-05 | 2014-05-10 | 2014-05-05 | 2014-05-10 | 25 | No | DUKHCONI03Z2RWGL6015 | DUKHCONI03Z2PSGL7010, DUKHCONI03Z2RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI03Z2RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 10 | No | DUKHCONI03Z2RWGL6000 | DUKHCONI03Z2RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI03Z2RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-05-17 | 2014-05-21 | 2014-05-17 | 2014-05-21 | 40 | No | DUKHCONI03Z1RWGL6030, DUKHCONI03Z2RWGL6025 | DUKHCONI03Z3RWGL6030, DUKHCONI03Z2PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L60.15 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-04-17 | 2014-06-14 | 2014-04-17 | 2014-06-14 | 25 |  |  |  | 0 | 0
DUKHCONI03Z2PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-05-11 | 2014-06-08 | 2014-05-11 | 2014-06-08 | 25 | No | DUKHCONI03Z1PSGL7010, DUKHCONI03Z2PSGL7005, DUKHCONI03Z2RWGL6020, DUKHCONI03Z2RWGL6030 | DUKHCONI03Z2PSGL7015, DUKHCONI03Z3PSGL7010 | 0 | 0 | PARKING SHED
DUKHCONI03Z2PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 25 | No | DUKHCONI03Z1PSGL7015, DUKHCONI03Z2PSGL7010, DUKHCONI03Z2STGL5260 | DUKHCONI03Z3PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI03Z2PSGL7000 | Excavation | 15 | 15 | 0% | 2014-04-17 | 2014-05-04 | 2014-04-17 | 2014-05-04 | 30 | No | DUKHCONI03Z2RWGL6015, DUKHCONI03Z1PSGL7005 | DUKHCONI03Z2PSGL7005, DUKHCONI03Z2PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI03Z2PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-04-29 | 2014-05-15 | 2014-04-29 | 2014-05-15 | 25 | No | DUKHCONI03Z2PSGL7000, DUKHCONI03Z2RWGL6015, DUKHCONI03Z2PSGL7000 | DUKHCONI03Z3PSGL7000, DUKHCONI03Z2PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L60.15 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-03-08 | 2014-05-27 | 2014-03-08 | 2014-05-27 | 55 |  |  |  | 0 | 0
DUKHCONI03Z2HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 25 | No | DUKHCONI03Z2HDGL7025, DUKHCONI03Z1HDGL7030 | DUKHCONI03Z3HDGL7030, DUKHCONI03Z2HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z2HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-05-17 | 2014-05-27 | 2014-05-17 | 2014-05-27 | 55 | No | DUKHCONI03Z1HDGL7040, DUKHCONI03Z2RWGL6025, DUKHCONI03Z2HDGL7035 | DUKHCONI03Z3HDGL7040 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z2HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-03-31 | 2014-04-28 | 2014-03-31 | 2014-04-28 | 25 | No | DUKHCONI03Z1HDGL7035, DUKHCONI03Z2HDGL7030 | DUKHCONI03Z2SLGL7200, DUKHCONI03Z2HDGL7040, DUKHCONI03Z3HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z2HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-03-19 | 2014-04-16 | 2014-03-19 | 2014-04-16 | 25 | No | DUKHCONI03Z2HDGL7020 | DUKHCONI03Z2HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z2HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-03-08 | 2014-03-30 | 2014-03-08 | 2014-03-30 | 25 | No | DUKHCONI03Z2RWGL6000 | DUKHCONI03Z2HDGL7025, DUKHCONI03SBGZGL7900 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L60.15 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-04-12 | 2014-06-02 | 2014-04-12 | 2014-06-02 | 35 |  |  |  | 0 | 0
DUKHCONI03Z2SLGL7200 | Excavation | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 25 | No | DUKHCONI03Z2HDGL7035, DUKHCONI03Z2IRGL5290, DUKHCONI03Z1SLGL7205 | DUKHCONI03Z2SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI03Z2SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-05-05 | 2014-06-02 | 2014-05-05 | 2014-06-02 | 35 | No | DUKHCONI03Z2SLGL7205, DUKHCONI03Z1SLGL7210 | DUKHCONI03Z3SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI03Z2SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-04-23 | 2014-05-21 | 2014-04-23 | 2014-05-21 | 25 | No | DUKHCONI03Z2SLGL7200 | DUKHCONI03Z2SLGL7210, DUKHCONI03Z3SLGL7200 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L60.20 ZONE - 3 |  | 211 | 211 | 0% | 2013-11-27 | 2014-08-05 | 2013-11-27 | 2014-08-05 | 8 |  |  |  | 0 | 0
DHBL.K30.L60.20 .10 INFRASTRUCTURE WORKS |  | 211 | 211 | 0% | 2013-11-27 | 2014-08-05 | 2013-11-27 | 2014-08-05 | 8 |  |  |  | 0 | 0
DHBL.K30.L60.20 .10 .10 DRAINAGE LINES |  | 43 | 43 | 0% | 2013-11-27 | 2014-01-16 | 2013-11-27 | 2014-01-16 | 12 |  |  |  | 0 | 0
DUKHCONI03Z3DRGL5130 | Backfilling Drainage line | 15 | 15 | 0% | 2013-12-31 | 2014-01-16 | 2013-12-31 | 2014-01-16 | 12 | No | DUKHCONI03Z3DRGL5125, DUKHCONI03Z3DRGL5125 | DUKHCONI03Z3WSGL5155, DUKHCONI03Z3SAGL5140, DUKHCONI03Z3SAGL5135 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z3DRGL5115 | Excavation for Drainage line | 25 | 25 | 0% | 2013-11-27 | 2013-12-26 | 2013-11-27 | 2013-12-26 | 12 | No | DUKHCONI03Z2DRGL5130 | DUKHCONI03Z3SAGL5135, DUKHCONI03Z3DRGL5120, DUKHCONI03Z3DRGL5120, DUKHCONI03Z3SAGL5140 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z3DRGL5120 | Laying of Drainage line | 25 | 25 | 0% | 2013-12-04 | 2014-01-02 | 2013-12-04 | 2014-01-02 | 12 | No | DUKHCONI03Z3DRGL5115, DUKHCONI03Z3DRGL5115 | DUKHCONI03Z3DRGL5125, DUKHCONI03Z3DRGL5125 | 0 | 0 | DRAINAGE LINES
DUKHCONI03Z3DRGL5125 | Testing of Drainage line | 25 | 25 | 0% | 2013-12-12 | 2014-01-11 | 2013-12-12 | 2014-01-11 | 12 | No | DUKHCONI03Z3DRGL5120, DUKHCONI03Z3DRGL5120 | DUKHCONI03Z3DRGL5130, DUKHCONI03Z3DRGL5130 | 0 | 0 | DRAINAGE LINES
DHBL.K30.L60.20 .10 .15 MANHOLES & SOAKAWAY |  | 70 | 70 | 0% | 2013-12-31 | 2014-03-23 | 2013-12-31 | 2014-03-23 | 36 |  |  |  | 0 | 0
DUKHCONI03Z3SAGL5150 | Connection with existing sewer manhole | 20 | 20 | 0% | 2014-03-01 | 2014-03-23 | 2014-03-01 | 2014-03-23 | 36 | No | DUKHCONI03Z3SAGL5145, DUKHCONI03Z3SAGL5135 | DUKHCONI03Z3RWGL6000 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z3SAGL5135 | Construction of manholes Drainage | 25 | 25 | 0% | 2013-12-31 | 2014-01-28 | 2013-12-31 | 2014-01-28 | 61 | No | DUKHCONI03Z3DRGL5115, DUKHCONI03Z3DRGL5130, DUKHCONI03Z2SAGL5135 | DUKHCONI03Z3SAGL5150 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z3SAGL5145 | Construction of Road gullies | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 12 | No | DUKHCONI03Z3SAGL5140, DUKHCONI03Z2SAGL5145 | DUKHCONI03Z3SAGL5150, DUKHCONI03Z3WSGL5170 | 0 | 0 | MANHOLES & SOAKAWAY
DUKHCONI03Z3SAGL5140 | Construction of soakaways | 25 | 25 | 0% | 2013-12-31 | 2014-01-28 | 2013-12-31 | 2014-01-28 | 12 | No | DUKHCONI03Z3DRGL5130, DUKHCONI03Z3DRGL5115 | DUKHCONI03Z3SAGL5145 | 0 | 0 | MANHOLES & SOAKAWAY
DHBL.K30.L60.20 .10 .20 WATER SUPPLY SYSTEM |  | 65 | 65 | 0% | 2014-01-12 | 2014-03-29 | 2014-01-12 | 2014-03-29 | 31 |  |  |  | 0 | 0
DUKHCONI03Z3WSGL5170 | Backfilling potable water line | 25 | 25 | 0% | 2014-01-29 | 2014-02-27 | 2014-01-29 | 2014-02-27 | 12 | No | DUKHCONI03Z3SAGL5145, DUKHCONI03Z3WSGL5165 | DUKHCONI03Z3WSGL5175, DUKHCONI03Z3FFGL5185 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z3WSGL5175 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-02-04 | 2014-03-05 | 2014-02-04 | 2014-03-05 | 31 | No | DUKHCONI03Z3WSGL5170, DUKHCONI03Z3WSGL5155, DUKHCONI03Z2WSGL5175 | DUKHCONI03Z3WSGL5180 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z3WSGL5155 | Excavation for water line | 25 | 25 | 0% | 2014-01-12 | 2014-02-09 | 2014-01-12 | 2014-02-09 | 12 | No | DUKHCONI03Z3DRGL5130, DUKHCONI03Z2WSGL5170 | DUKHCONI03Z3WSGL5160, DUKHCONI03Z3WSGL5175 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z3WSGL5180 | Installation of meter ,Accessories & Connection | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 31 | No | DUKHCONI03Z3WSGL5175, DUKHCONI03Z2WSGL5180 | DUKHHANP03GNELTC9010, DUKHHANP03GNPLTC9005, DUKHCONI03Z3FFGL5210 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z3WSGL5160 | Laying of water line | 25 | 25 | 0% | 2014-01-18 | 2014-02-16 | 2014-01-18 | 2014-02-16 | 12 | No | DUKHCONI03Z3WSGL5155 | DUKHCONI03Z3WSGL5165 | 0 | 0 | WATER SUPPLY SYSTEM
DUKHCONI03Z3WSGL5165 | Testing of potable water line | 25 | 25 | 0% | 2014-01-23 | 2014-02-22 | 2014-01-23 | 2014-02-22 | 12 | No | DUKHCONI03Z3WSGL5160 | DUKHCONI03Z3WSGL5170 | 0 | 0 | WATER SUPPLY SYSTEM
DHBL.K30.L60.20 .10 .25 FIREFIGHTING LINES |  | 52 | 52 | 0% | 2014-02-09 | 2014-04-10 | 2014-02-09 | 2014-04-10 | 20 |  |  |  | 0 | 0
DUKHCONI03Z3FFGL5200 | Backfilling firefighting line | 25 | 25 | 0% | 2014-03-02 | 2014-03-30 | 2014-03-02 | 2014-03-30 | 8 | No | DUKHCONI03Z3FFGL5195 | DUKHCONI03Z3RWGL6000, DUKHCONI03Z3FFGL5205, DUKHCONI03Z3ELGL5215 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z3FFGL5210 | Connection with existing Firewater System | 25 | 25 | 0% | 2014-03-13 | 2014-04-10 | 2014-03-13 | 2014-04-10 | 20 | No | DUKHCONI03Z3FFGL5205, DUKHCONI03Z2FFGL5210, DUKHCONI03Z3WSGL5180 | DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000, DUKHCONI03SBIWGL7440, DUKHHANP03GNELTC9010, DUKHCONI03Z3RWGL6000 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z3FFGL5205 | Construction of valve chambers & Thrust Blocks | 25 | 25 | 0% | 2014-03-08 | 2014-04-05 | 2014-03-08 | 2014-04-05 | 20 | No | DUKHCONI03Z3FFGL5200, DUKHCONI03Z2FFGL5205, DUKHCONI03Z3FFGL5185 | DUKHCONI03Z3FFGL5210 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z3FFGL5185 | Excavation for firefighting line | 25 | 25 | 0% | 2014-02-09 | 2014-03-10 | 2014-02-09 | 2014-03-10 | 8 | No | DUKHCONI03Z3WSGL5170, DUKHCONI03Z2FFGL5200 | DUKHCONI03Z3FFGL5190, DUKHCONI03Z3FFGL5205 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z3FFGL5190 | Laying of firefighting line | 25 | 25 | 0% | 2014-02-18 | 2014-03-18 | 2014-02-18 | 2014-03-18 | 8 | No | DUKHCONI03Z3FFGL5185 | DUKHCONI03Z3FFGL5195 | 0 | 0 | FIREFIGHTING LINES
DUKHCONI03Z3FFGL5195 | Testing of firefighting line | 25 | 25 | 0% | 2014-02-24 | 2014-03-24 | 2014-02-24 | 2014-03-24 | 8 | No | DUKHCONI03Z3FFGL5190 | DUKHCONI03Z3FFGL5200 | 0 | 0 | FIREFIGHTING LINES
DHBL.K30.L60.20 .10 .30 ELECTRICAL LINES |  | 47 | 47 | 0% | 2014-03-10 | 2014-05-03 | 2014-03-10 | 2014-05-03 | 36 |  |  |  | 0 | 0
DUKHCONI03Z3ELGL5225 | Backfilling Electrical trench | 25 | 25 | 0% | 2014-03-24 | 2014-04-21 | 2014-03-24 | 2014-04-21 | 11 | No | DUKHCONI03Z3ELGL5215, DUKHCONI03Z3ELGL5220 | DUKHCONI03Z3ELGL5230, DUKHCONI03Z3IRGL5285, DUKHCONI03Z3IRGL5265, DUKHCONI03Z3RWGL6000, DUKHCONI03Z3ELGL5230 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z3ELGL5230 | Construction of Submain Board & Feeder Pillar | 25 | 25 | 0% | 2014-04-05 | 2014-05-03 | 2014-04-05 | 2014-05-03 | 36 | No | DUKHCONI03Z3ELGL5225, DUKHCONI03Z2ELGL5230, DUKHCONI03Z3ELGL5225 | DUKHCONI03Z3STGL5260, DUKHCONI03SBIWGL7450 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z3ELGL5215 | Excavation Cable Trenches & Duct Banks | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 8 | No | DUKHCONI03Z2ELGL5225, DUKHCONI03Z3FFGL5200 | DUKHCONI03Z3ELGL5225, DUKHCONI03Z3STGL5235, DUKHCONI03Z3ELGL5220 | 0 | 0 | ELECTRICAL LINES
DUKHCONI03Z3ELGL5220 | Laying of electrical cables | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 11 | No | DUKHCONI03Z3ELGL5215 | DUKHCONI03Z3ELGL5225 | 0 | 0 | ELECTRICAL LINES
DHBL.K30.L60.20 .10 .35 STREET LIGHTING |  | 72 | 72 | 0% | 2014-03-10 | 2014-06-01 | 2014-03-10 | 2014-06-01 | 36 |  |  |  | 0 | 0
DUKHCONI03Z3STGL5250 | Backfilling Street Lighting | 25 | 25 | 0% | 2014-03-22 | 2014-04-19 | 2014-03-22 | 2014-04-19 | 8 | No | DUKHCONI03Z3STGL5235, DUKHCONI03Z3STGL5245 | DUKHCONI03Z3STGL5255, DUKHCONI03Z3RWGL6000, DUKHCONI03Z3TCGL5295, DUKHCONI03Z3BWGL5315 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z3STGL5240 | Construction of Duct Banks | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 8 | No | DUKHCONI03Z3STGL5235 | DUKHCONI03Z3STGL5245 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z3STGL5245 | Construction of Foundation | 25 | 25 | 0% | 2014-03-16 | 2014-04-13 | 2014-03-16 | 2014-04-13 | 8 | No | DUKHCONI03Z3STGL5240 | DUKHCONI03Z3STGL5250 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z3STGL5260 | Electrical Works | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 36 | No | DUKHCONI03Z3ELGL5230, DUKHCONI03Z2STGL5260, DUKHCONI03Z3STGL5255 | DUKHHANP03GNELTC9010, DUKHCONI03Z3PSGL7015, DUKHHANP03GNACTC9000, DUKHCONI03SBIWGL7450 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z3STGL5235 | Excavation for Street lighting | 25 | 25 | 0% | 2014-03-10 | 2014-04-07 | 2014-03-10 | 2014-04-07 | 8 | No | DUKHCONI03Z3ELGL5215, DUKHCONI03Z2STGL5250 | DUKHCONI03Z3STGL5250, DUKHCONI03Z3STGL5240 | 0 | 0 | STREET LIGHTING
DUKHCONI03Z3STGL5255 | Installation of light Post | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 56 | No | DUKHCONI03Z3STGL5250, DUKHCONI03Z2STGL5255 | DUKHCONI03Z3STGL5260 | 0 | 0 | STREET LIGHTING
DHBL.K30.L60.20 .10 .40 IRRIGATION LINES |  | 57 | 57 | 0% | 2014-04-22 | 2014-06-26 | 2014-04-22 | 2014-06-26 | 19 |  |  |  | 0 | 0
DUKHCONI03Z3IRGL5280 | Backfilling irrigation line | 25 | 25 | 0% | 2014-05-10 | 2014-06-07 | 2014-05-10 | 2014-06-07 | 19 | No | DUKHCONI03Z3IRGL5275 | DUKHCONI03Z3IRGL5285, DUKHCONI03Z3IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z3IRGL5285 | Construction of Thrust Blocks,Pull boxes | 25 | 25 | 0% | 2014-05-21 | 2014-06-18 | 2014-05-21 | 2014-06-18 | 19 | No | DUKHCONI03Z3IRGL5280, DUKHCONI03Z3ELGL5225 | DUKHCONI03Z3IRGL5290 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z3IRGL5265 | Excavation for irrigation line | 25 | 25 | 0% | 2014-04-22 | 2014-05-20 | 2014-04-22 | 2014-05-20 | 19 | No | DUKHCONI03Z2IRGL5280, DUKHCONI03Z3ELGL5225 | DUKHCONI03Z3IRGL5270 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z3IRGL5290 | Irrigation Fittings (Nozzle,Values) | 25 | 25 | 0% | 2014-05-29 | 2014-06-26 | 2014-05-29 | 2014-06-26 | 19 | No | DUKHCONI03Z3IRGL5280, DUKHCONI03Z3IRGL5285 | DUKHCONI03Z3SLGL7200 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z3IRGL5270 | Laying of irrigationline | 25 | 25 | 0% | 2014-04-28 | 2014-05-26 | 2014-04-28 | 2014-05-26 | 19 | No | DUKHCONI03Z3IRGL5265 | DUKHCONI03Z3IRGL5275 | 0 | 0 | IRRIGATION LINES
DUKHCONI03Z3IRGL5275 | Testing of irrigation line | 25 | 25 | 0% | 2014-05-04 | 2014-06-01 | 2014-05-04 | 2014-06-01 | 19 | No | DUKHCONI03Z3IRGL5270 | DUKHCONI03Z3IRGL5280 | 0 | 0 | IRRIGATION LINES
DHBL.K30.L60.20 .10 .45 TELECOMMUNICATION LINES |  | 61 | 61 | 0% | 2014-04-02 | 2014-06-11 | 2014-04-02 | 2014-06-11 | 22 |  |  |  | 0 | 0
DUKHCONI03Z3TCGL5305 | Backfilling telecommunication trench | 20 | 20 | 0% | 2014-04-14 | 2014-05-06 | 2014-04-14 | 2014-05-06 | 8 | No | DUKHCONI03Z3TCGL5300 | DUKHCONI03Z3RWGL6000, DUKHCONI03Z3TCGL5310 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z3TCGL5310 | Connection & Installation | 20 | 20 | 0% | 2014-05-20 | 2014-06-11 | 2014-05-20 | 2014-06-11 | 22 | No | DUKHCONI03Z3TCGL5305, DUKHCONI03Z2TCGL5310 | DUKHHANP03GNPLTC9005, DUKHHANP03GNELTC9010, DUKHHANP03GNACTC9000, DUKHCONI03SBTRGL7630 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z3TCGL5295 | Excavation Telecommunication trenches | 20 | 20 | 0% | 2014-04-02 | 2014-04-24 | 2014-04-02 | 2014-04-24 | 8 | No | DUKHCONI03Z3STGL5250, DUKHCONI03Z2TCGL5305 | DUKHCONI03Z3TCGL5300 | 0 | 0 | TELECOMMUNICATION LINES
DUKHCONI03Z3TCGL5300 | Laying of cables | 20 | 20 | 0% | 2014-04-08 | 2014-04-30 | 2014-04-08 | 2014-04-30 | 8 | No | DUKHCONI03Z3TCGL5295 | DUKHCONI03Z3TCGL5305 | 0 | 0 | TELECOMMUNICATION LINES
DHBL.K30.L60.20 .10 .50 BOUNDARY WALL |  | 39 | 39 | 0% | 2014-04-02 | 2014-05-17 | 2014-04-02 | 2014-05-17 | 19 |  |  |  | 0 | 0
DUKHCONI03Z3BWGL5315 | Construction of Boundary Wall (Ht-3m) | 25 | 25 | 0% | 2014-04-02 | 2014-04-30 | 2014-04-02 | 2014-04-30 | 19 | No | DUKHCONI03Z2BWGL5315, DUKHCONI03Z3STGL5250 | DUKHCONI03Z3BWGL5320 | 0 | 0 | BOUNDARY WALL
DUKHCONI03Z3BWGL5320 | Install.Steel Gate,Entance Barrier (3m Wall) | 25 | 25 | 0% | 2014-04-19 | 2014-05-17 | 2014-04-19 | 2014-05-17 | 19 | No | DUKHCONI03Z2BWGL5320, DUKHCONI03Z3BWGL5315 | DUKHCONI03Z3HDGL7030 | 0 | 0 | BOUNDARY WALL
DHBL.K30.L60.20 .10 .55 ROAD WORKS |  | 65 | 65 | 0% | 2014-04-26 | 2014-07-09 | 2014-04-26 | 2014-07-09 | 23 |  |  |  | 0 | 0
DUKHCONI03Z3RWGL6000 | Excavation & Earth Filling | 10 | 10 | 0% | 2014-04-26 | 2014-05-06 | 2014-04-26 | 2014-05-06 | 8 | No | DUKHCONI03Z3STGL5250, DUKHCONI03Z3SAGL5150, DUKHCONI03Z3FFGL5200, DUKHCONI03Z3TCGL5305, DUKHCONI03Z2RWGL6015, DUKHCONI03Z3FFGL5210, DUKHCONI03Z3ELGL5225 | DUKHCONI03Z3HDGL7020, DUKHCONI03Z3RWGL6005 | 0 | 0 | ROAD WORKS
DUKHCONI03Z3RWGL6025 | Laying of Asphalt Wearing Coarse | 5 | 5 | 0% | 2014-06-29 | 2014-07-03 | 2014-06-29 | 2014-07-03 | 23 | No | DUKHCONI03Z2RWGL6025, DUKHCONI03Z3RWGL6020 | DUKHCONI03Z3HDGL7040, DUKHCONI03Z3RWGL6030 | 0 | 0 | ROAD WORKS
DUKHCONI03Z3RWGL6015 | Laying of Granular Sub Base Coarse | 20 | 20 | 0% | 2014-05-31 | 2014-06-22 | 2014-05-31 | 2014-06-22 | 8 | No | DUKHCONI03Z3RWGL6010 | DUKHCONI03Z3PSGL7000, DUKHCONI03Z3PSGL7005, DUKHCONI03Z3RWGL6020 | 0 | 0 | ROAD WORKS
DUKHCONI03Z3RWGL6010 | Laying of Precast Kerbs | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 8 | No | DUKHCONI03Z3RWGL6005 | DUKHCONI03Z3RWGL6015 | 0 | 0 | ROAD WORKS
DUKHCONI03Z3RWGL6020 | Laying of Road Base Asphalt Concrete | 5 | 5 | 0% | 2014-06-23 | 2014-06-28 | 2014-06-23 | 2014-06-28 | 8 | No | DUKHCONI03Z3RWGL6015 | DUKHCONI03Z3PSGL7010, DUKHCONI03Z3RWGL6025 | 0 | 0 | ROAD WORKS
DUKHCONI03Z3RWGL6005 | Laying of Sub Grade | 25 | 25 | 0% | 2014-05-07 | 2014-06-04 | 2014-05-07 | 2014-06-04 | 8 | No | DUKHCONI03Z3RWGL6000 | DUKHCONI03Z3RWGL6010 | 0 | 0 | ROAD WORKS
DUKHCONI03Z3RWGL6030 | Traffic Signage & Road Marking | 5 | 5 | 0% | 2014-07-05 | 2014-07-09 | 2014-07-05 | 2014-07-09 | 23 | No | DUKHCONI03Z2RWGL6030, DUKHCONI03Z3RWGL6025 | DUKHCONI03Z3PSGL7010 | 0 | 0 | ROAD WORKS
DHBL.K30.L60.20 .10 .60 PARKING SHED |  | 50 | 50 | 0% | 2014-06-05 | 2014-08-05 | 2014-06-05 | 2014-08-05 | 8 |  |  |  | 0 | 0
DUKHCONI03Z3PSGL7010 | Column, Frame& Fabrics Erection | 25 | 25 | 0% | 2014-06-29 | 2014-07-27 | 2014-06-29 | 2014-07-27 | 8 | No | DUKHCONI03Z3PSGL7005, DUKHCONI03Z3RWGL6020, DUKHCONI03Z3RWGL6030, DUKHCONI03Z2PSGL7010 | DUKHCONI03Z3PSGL7015 | 0 | 0 | PARKING SHED
DUKHCONI03Z3PSGL7015 | Electrical Works-Parking Shed | 25 | 25 | 0% | 2014-07-05 | 2014-08-05 | 2014-07-05 | 2014-08-05 | 8 | No | DUKHCONI03Z3STGL5260, DUKHCONI03Z2PSGL7015, DUKHCONI03Z3PSGL7010 | DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000, DUKHHANP03GNELTC9010 | 0 | 0 | PARKING SHED
DUKHCONI03Z3PSGL7000 | Excavation | 15 | 15 | 0% | 2014-06-05 | 2014-06-22 | 2014-06-05 | 2014-06-22 | 13 | No | DUKHCONI03Z2PSGL7005, DUKHCONI03Z3RWGL6015 | DUKHCONI03Z3PSGL7005, DUKHCONI03Z3PSGL7005 | 0 | 0 | PARKING SHED
DUKHCONI03Z3PSGL7005 | Foundation casting | 15 | 15 | 0% | 2014-06-17 | 2014-07-03 | 2014-06-17 | 2014-07-03 | 8 | No | DUKHCONI03Z3RWGL6015, DUKHCONI03Z3PSGL7000, DUKHCONI03Z3PSGL7000 | DUKHCONI03Z3PSGL7010 | 0 | 0 | PARKING SHED
DHBL.K30.L60.20 .10 .65 HARD LANDSCAPING |  | 70 | 70 | 0% | 2014-04-26 | 2014-07-15 | 2014-04-26 | 2014-07-15 | 23 |  |  |  | 0 | 0
DUKHCONI03Z3HDGL7030 | Construction of Retaining wall | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 18 | No | DUKHCONI03Z2HDGL7030, DUKHCONI03Z3BWGL5320, DUKHCONI03Z3HDGL7025 | DUKHCONI03Z3HDGL7035 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z3HDGL7040 | Construction of Speed Humps | 10 | 10 | 0% | 2014-07-05 | 2014-07-15 | 2014-07-05 | 2014-07-15 | 23 | No | DUKHCONI03Z3RWGL6025, DUKHCONI03Z3HDGL7035, DUKHCONI03Z2HDGL7040 | DUKHHANP03GNELTC9010, DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z3HDGL7035 | Construction of Wash Stone Boulders | 25 | 25 | 0% | 2014-05-19 | 2014-06-16 | 2014-05-19 | 2014-06-16 | 18 | No | DUKHCONI03Z3HDGL7030, DUKHCONI03Z2HDGL7035 | DUKHCONI03Z3HDGL7040, DUKHCONI03Z3SLGL7200 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z3HDGL7025 | Interlocking for Walkways | 25 | 25 | 0% | 2014-05-07 | 2014-06-04 | 2014-05-07 | 2014-06-04 | 18 | No | DUKHCONI03SBGZGL7910, DUKHCONI03Z3HDGL7020 | DUKHCONI03Z3HDGL7030 | 0 | 0 | HARD LANDSCAPING
DUKHCONI03Z3HDGL7020 | Precast Concrete Kerbs works | 20 | 20 | 0% | 2014-04-26 | 2014-05-18 | 2014-04-26 | 2014-05-18 | 18 | No | DUKHCONI03Z3RWGL6000 | DUKHCONI03Z3HDGL7025 | 0 | 0 | HARD LANDSCAPING
DHBL.K30.L60.20 .10 .70 SOFT LANDSCAPING |  | 45 | 45 | 0% | 2014-05-31 | 2014-07-21 | 2014-05-31 | 2014-07-21 | 18 |  |  |  | 0 | 0
DUKHCONI03Z3SLGL7200 | Excavation for Landscaping | 25 | 25 | 0% | 2014-05-31 | 2014-06-28 | 2014-05-31 | 2014-06-28 | 18 | No | DUKHCONI03Z3IRGL5290, DUKHCONI03Z2SLGL7205, DUKHCONI03Z3HDGL7035 | DUKHCONI03Z3SLGL7205 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI03Z3SLGL7210 | Plantation works | 25 | 25 | 0% | 2014-06-23 | 2014-07-21 | 2014-06-23 | 2014-07-21 | 18 | No | DUKHCONI03Z2SLGL7210, DUKHCONI03Z3SLGL7205 | DUKHHANP03GNELTC9010, DUKHHANP03GNPLTC9005 | 0 | 0 | SOFT LANDSCAPING
DUKHCONI03Z3SLGL7205 | Sweet Soil Laying | 25 | 25 | 0% | 2014-06-11 | 2014-07-09 | 2014-06-11 | 2014-07-09 | 18 | No | DUKHCONI03Z3SLGL7200 | DUKHCONI03Z3SLGL7210 | 0 | 0 | SOFT LANDSCAPING
DHBL.K30.L60.25 SECONDARY BUILDINGS |  | 146 | 146 | 0% | 2014-02-04 | 2014-07-24 | 2014-02-04 | 2014-07-24 | 15 |  |  |  | 0 | 0
DHBL.K30.L60.25 .10 INFRASTRUCTURE WORKS |  | 146 | 146 | 0% | 2014-02-04 | 2014-07-24 | 2014-02-04 | 2014-07-24 | 15 |  |  |  | 0 | 0
DHBL.K30.L60.25 .10 .10 IRRIGATION WATER TANK & PUMP ROOM |  | 146 | 146 | 0% | 2014-02-04 | 2014-07-24 | 2014-02-04 | 2014-07-24 | 15 |  |  |  | 0 | 0
DUKHCONI03SBIWGL7445 | AC Works | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 15 | No | DUKHCONI03SBIWGL7440 | DUKHCONI03SBIWGL7450 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7405 | Blinding & base waterproofing | 10 | 10 | 0% | 2014-02-23 | 2014-03-05 | 2014-02-23 | 2014-03-05 | 15 | No | DUKHCONI03SBIWGL7400 | DUKHCONI03SBIWGL7410 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7420 | Construction of Roof Slab | 20 | 20 | 0% | 2014-04-16 | 2014-05-08 | 2014-04-16 | 2014-05-08 | 15 | No | DUKHCONI03SBIWGL7415 | DUKHCONI03SBIWGL7430, DUKHCONI03SBIWGL7425 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7410 | Construction of Raft slab | 10 | 10 | 0% | 2014-03-06 | 2014-03-17 | 2014-03-06 | 2014-03-17 | 15 | No | DUKHCONI03SBIWGL7405 | DUKHCONI03SBIWGL7415 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7415 | Construction of RCC Wall | 25 | 25 | 0% | 2014-03-18 | 2014-04-15 | 2014-03-18 | 2014-04-15 | 15 | No | DUKHCONI03SBIWGL7410 | DUKHCONI03SBIWGL7420 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7450 | Electrical Works | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 15 | No | DUKHCONI03Z3STGL5260, DUKHCONI03Z3ELGL5230, DUKHCONI03SBIWGL7445 | DUKHCONI03SBIWGL7455 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7400 | Excavation | 15 | 15 | 0% | 2014-02-04 | 2014-02-22 | 2014-02-04 | 2014-02-22 | 15 | No | DUKHCONP03Z5STRF2055, DUKHENGI03DWIWAP5920 | DUKHCONI03SBIWGL7405, DUKHCONI03SBTRGL7600 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7430 | Floor screed | 5 | 5 | 0% | 2014-06-03 | 2014-06-08 | 2014-06-03 | 2014-06-08 | 15 | No | DUKHCONI03SBIWGL7420, DUKHCONI03SBIWGL7425 | DUKHCONI03SBIWGL7440 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7435 | Installation of Boundary Fences | 15 | 15 | 0% | 2014-06-08 | 2014-06-24 | 2014-06-08 | 2014-06-24 | 36 | No | DUKHCONI03SBIWGL7950, DUKHPROGEN00PRDV3850 | DUKHCONI03SBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7465 | Installation of G.I Handrails | 5 | 5 | 0% | 2014-07-20 | 2014-07-24 | 2014-07-20 | 2014-07-24 | 15 | No | DUKHCONI03SBIWGL7435, DUKHCONI03SBIWGL7460 | DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000, DUKHHANP03GNELTC9010 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7460 | Installation of Steel Ladder | 5 | 5 | 0% | 2014-07-14 | 2014-07-19 | 2014-07-14 | 2014-07-19 | 15 | No | DUKHCONI03SBIWGL7455 | DUKHCONI03SBIWGL7465 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7455 | Internal epoxy coating & Painting | 5 | 5 | 0% | 2014-07-08 | 2014-07-13 | 2014-07-08 | 2014-07-13 | 15 | No | DUKHCONI03SBIWGL7450 | DUKHCONI03SBIWGL7460 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7950 | Laying of Interlock | 10 | 10 | 0% | 2014-05-27 | 2014-06-07 | 2014-05-27 | 2014-06-07 | 36 | No | DUKHCONI03SBIWGL7425 | DUKHCONI03SBIWGL7435 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7440 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 15 | No | DUKHCONI03Z2FFGL5210, DUKHCONI03Z1FFGL5210, DUKHCONI03Z3FFGL5210, DUKHCONI03SBIWGL7430 | DUKHCONI03SBIWGL7445 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DUKHCONI03SBIWGL7425 | Waterproofing & Backfilling | 15 | 15 | 0% | 2014-05-10 | 2014-05-26 | 2014-05-10 | 2014-05-26 | 21 | No | DUKHCONI03SBIWGL7420 | DUKHCONI03SBIWGL7950, DUKHCONI03SBIWGL7430 | 0 | 0 | IRRIGATION WATER TANK & PUMP ROOM
DHBL.K30.L60.25 .10 .15 TELECOMMUNICATION ROOM |  | 124 | 124 | 0% | 2014-02-23 | 2014-07-16 | 2014-02-23 | 2014-07-16 | 22 |  |  |  | 0 | 0
DUKHCONI03SBTRGL7625 | AC Works | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 35 | No | DUKHCONI03SBTRGL7620 | DUKHCONI03SBTRGL7635, DUKHCONI03SBTRGL7630 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI03SBTRGL7610 | Construction Column,Beams & Roof Slab | 20 | 20 | 0% | 2014-03-30 | 2014-04-21 | 2014-03-30 | 2014-04-21 | 35 | No | DUKHCONI03SBTRGL7605 | DUKHCONI03SBTRGL7615 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI03SBTRGL7605 | Construction of foundation & Grade slab | 20 | 20 | 0% | 2014-03-06 | 2014-03-29 | 2014-03-06 | 2014-03-29 | 35 | No | DUKHCONI03SBTRGL7600 | DUKHCONI03SBTRGL7610 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI03SBTRGL7630 | Electrical Works-Telecom Room | 25 | 25 | 0% | 2014-06-12 | 2014-07-10 | 2014-06-12 | 2014-07-10 | 22 | No | DUKHCONI03Z1TCGL5310, DUKHCONI03SBTRGL7625, DUKHCONI03Z2TCGL5310, DUKHCONI03Z3TCGL5310 | DUKHCONI03SBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI03SBTRGL7600 | Excavation | 10 | 10 | 0% | 2014-02-23 | 2014-03-05 | 2014-02-23 | 2014-03-05 | 25 | No | DUKHCONI03SBIWGL7400, DUKHENGI03DWTRAP5930 | DUKHCONI03SBTRGL7605, DUKHCONI03SBGHGL7800 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI03SBTRGL7635 | Final Paintings | 5 | 5 | 0% | 2014-07-12 | 2014-07-16 | 2014-07-12 | 2014-07-16 | 22 | No | DUKHCONI03SBTRGL7625, DUKHCONI03SBTRGL7630, DUKHCONI03SBTRGL7620, DUKHCONI03SBTRGL7615 | DUKHHANP03GNACTC9000, DUKHHANP03GNELTC9010, DUKHHANP03GNPLTC9005 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI03SBTRGL7615 | Finishing Works | 25 | 25 | 0% | 2014-05-17 | 2014-06-14 | 2014-05-17 | 2014-06-14 | 35 | No | DUKHCONI03SBTRGL7610 | DUKHCONI03SBTRGL7620, DUKHCONI03SBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DUKHCONI03SBTRGL7620 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 35 | No | DUKHCONI03SBTRGL7615 | DUKHCONI03SBTRGL7625, DUKHCONI03SBTRGL7635 | 0 | 0 | TELECOMMUNICATION ROOM
DHBL.K30.L60.25 .10 .20 GUARD HOUSE |  | 111 | 111 | 0% | 2014-03-06 | 2014-07-13 | 2014-03-06 | 2014-07-13 | 25 |  |  |  | 0 | 0
DUKHCONI03SBGHGL7825 | AC Works | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 25 | No | DUKHCONI03SBGHGL7820 | DUKHCONI03SBGHGL7835, DUKHCONI03SBGHGL7830 | 0 | 0 | GUARD HOUSE
DUKHCONI03SBGHGL7810 | Construction Column,Beams & Roof Slab | 20 | 20 | 0% | 2014-04-10 | 2014-05-03 | 2014-04-10 | 2014-05-03 | 25 | No | DUKHCONI03SBGHGL7805 | DUKHCONI03SBGHGL7815 | 0 | 0 | GUARD HOUSE
DUKHCONI03SBGHGL7805 | Construction of foundation & Grade slab | 20 | 20 | 0% | 2014-03-18 | 2014-04-09 | 2014-03-18 | 2014-04-09 | 25 | No | DUKHCONI03SBGHGL7800 | DUKHCONI03SBGHGL7810 | 0 | 0 | GUARD HOUSE
DUKHCONI03SBGHGL7830 | Electrical Works-Telecom Room | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 25 | No | DUKHCONI03SBGHGL7825 | DUKHCONI03SBGHGL7835 | 0 | 0 | GUARD HOUSE
DUKHCONI03SBGHGL7800 | Excavation | 10 | 10 | 0% | 2014-03-06 | 2014-03-17 | 2014-03-06 | 2014-03-17 | 25 | No | DUKHCONI03SBTRGL7600, DUKHENGI03DWGHAP5950 | DUKHCONI03SBGHGL7805 | 0 | 0 | GUARD HOUSE
DUKHCONI03SBGHGL7835 | Final Paintings | 5 | 5 | 0% | 2014-07-08 | 2014-07-13 | 2014-07-08 | 2014-07-13 | 25 | No | DUKHCONI03SBGHGL7830, DUKHCONI03SBGHGL7815, DUKHCONI03SBGHGL7820, DUKHCONI03SBGHGL7825 | DUKHHANP03GNELTC9010, DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000 | 0 | 0 | GUARD HOUSE
DUKHCONI03SBGHGL7815 | Finishing Works | 25 | 25 | 0% | 2014-05-28 | 2014-06-25 | 2014-05-28 | 2014-06-25 | 25 | No | DUKHCONI03SBGHGL7810 | DUKHCONI03SBGHGL7820, DUKHCONI03SBGHGL7835 | 0 | 0 | GUARD HOUSE
DUKHCONI03SBGHGL7820 | Plumbing , Drainage & Firefighting works | 25 | 25 | 0% | 2014-06-09 | 2014-07-07 | 2014-06-09 | 2014-07-07 | 25 | No | DUKHCONI03SBGHGL7815 | DUKHCONI03SBGHGL7825, DUKHCONI03SBGHGL7835 | 0 | 0 | GUARD HOUSE
DHBL.K30.L60.25 .10 .25 GAZEBO |  | 50 | 50 | 0% | 2014-03-31 | 2014-05-27 | 2014-03-31 | 2014-05-27 | 25 |  |  |  | 0 | 0
DUKHCONI03SBGZGL7900 | Construction of Concrete structure | 20 | 20 | 0% | 2014-03-31 | 2014-04-22 | 2014-03-31 | 2014-04-22 | 25 | No | DUKHCONI03Z2HDGL7020, DUKHENGI03DWGZAP5940, DUKHPROGEN00PRDV3780 | DUKHCONI03SBPGGL7940, DUKHCONI03SBGZGL7905 | 0 | 0 | GAZEBO
DUKHCONI03SBGZGL7910 | Electrical Works-Gazebo | 15 | 15 | 0% | 2014-05-11 | 2014-05-27 | 2014-05-11 | 2014-05-27 | 25 | No | DUKHCONI03SBGZGL7905, DUKHCONI03SBGZGL7915 | DUKHCONI03Z3HDGL7025 | 0 | 0 | GAZEBO
DUKHCONI03SBGZGL7905 | Installation of Wooden Works | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 25 | No | DUKHCONI03SBGZGL7900 | DUKHCONI03SBGZGL7910, DUKHCONI03SBGZGL7915 | 0 | 0 | GAZEBO
DUKHCONI03SBGZGL7915 | Park Benches Installation | 25 | 25 | 0% | 2014-04-12 | 2014-05-10 | 2014-04-12 | 2014-05-10 | 25 | No | DUKHCONI03SBGZGL7905 | DUKHCONI03SBGZGL7910 | 0 | 0 | GAZEBO
DHBL.K30.L60.25 .10 .30 PLAY GROUND |  | 60 | 60 | 0% | 2014-04-23 | 2014-07-01 | 2014-04-23 | 2014-07-01 | 35 |  |  |  | 0 | 0
DUKHCONI03SBPGGL7945 | Final Work Play Ground Works | 30 | 30 | 0% | 2014-05-28 | 2014-07-01 | 2014-05-28 | 2014-07-01 | 35 | No | DUKHCONI03SBPGGL7940 | DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000, DUKHHANP03GNELTC9010 | 0 | 0 | PLAY GROUND
DUKHCONI03SBPGGL7940 | Intial Work Play Ground Works | 30 | 30 | 0% | 2014-04-23 | 2014-05-27 | 2014-04-23 | 2014-05-27 | 35 | No | DUKHCONI03SBGZGL7900 | DUKHCONI03SBPGGL7945 | 0 | 0 | PLAY GROUND
DHBL.K35 COMMISSIONING & HANDING OVER |  | 242 | 242 | 0% | 2014-06-15 | 2015-03-31 | 2014-06-15 | 2015-03-31 | 0 |  |  |  | 0 | 0
DHBL.K35.L20 PACKAGE-1A |  | 90 | 90 | 0% | 2014-12-15 | 2015-03-31 | 2014-12-15 | 2015-03-31 | 0 |  |  |  | 0 | 0
DUKHHANP1AGNDM009020 | Demobilization & Handing Over | 60 | 60 | 0% | 2015-01-20 | 2015-03-31 | 2015-01-20 | 2015-03-31 | 0 | Yes | DUKHHANP1AGNELTC9010, DUKHHANP1AGNACTC9000, DUKHHANP1AGNPLTC9005, DUKHHANP1AGNAB009015, DUKHHANP1AGNAB009015 | DUKHKYDP010000001000 | 0 | 0 | PACKAGE-1A
DUKHHANP1AGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 30 | 30 | 0% | 2014-12-15 | 2015-01-19 | 2014-12-15 | 2015-01-19 | 0 | Yes | DUKHCONP1AZ8ELTC8010, DUKHCONP1AZ1PLTC8005, DUKHCONI1AZ5SLGL7210, DUKHCONI1AZ5TCGL5310, DUKHCONP1AZ1ELTC8010, DUKHCONP1AZ4PLTC8005, DUKHCONP1AZ5PLTC8005, DUKHCONP1AZ9MSEX5335, DUKHCONP1AZ6ELTC8010, DUKHCONI1AZ5HDGL7040, DUKHCONI1ASBIWGL7465, DUKHCONP1AZ8PLTC8005, DUKHCONP1AZ4ELTC8010, DUKHCONI1AZ5STGL5260, DUKHCONI1AZ5PSGL7015, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ9PLTC8005, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ2PLTC8005, DUKHCONI1AZ5WSGL5180, DUKHCONP1AZ3PLTC8005, DUKHCONP1AZ2ELTC8010, DUKHCONP1AZ9ELTC8010, DUKHCONP1AZ6PLTC8005, DUKHCONP1AZ7PLTC8005, DUKHCONI1AZ5FFGL5210, DUKHCONI1ASBGHGL7835, DUKHCONI1ASBTRGL7635 | DUKHHANP1AGNAB009015, DUKHHANP1AGNAB009015, DUKHHANP1AGNDM009020 | 0 | 0 | PACKAGE-1A
DUKHHANP1AGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 30 | 30 | 0% | 2014-12-15 | 2015-01-19 | 2014-12-15 | 2015-01-19 | 0 | Yes | DUKHCONP1AZ6ACTC8000, DUKHCONP1AZ7ACTC8000, DUKHCONP1AZ1ACTC8000, DUKHCONP1AZ4ACTC8000, DUKHCONP1AZ2ACTC8000, DUKHCONP1AZ5ACTC8000, DUKHCONI1ASBIWGL7465, DUKHCONI1ASBGHGL7835, DUKHCONI1ASBTRGL7635, DUKHCONP1AZ9ACTC8000, DUKHCONP1AZ3ACTC8000, DUKHCONP1AZ8ACTC8000 | DUKHHANP1AGNAB009015, DUKHHANP1AGNAB009015, DUKHHANP1AGNDM009020 | 0 | 0 | PACKAGE-1A
DUKHHANP1AGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 30 | 30 | 0% | 2014-12-15 | 2015-01-19 | 2014-12-15 | 2015-01-19 | 0 | Yes | DUKHCONP1AZ2ELTC8010, DUKHCONI1AZ5HDGL7040, DUKHCONP1AZ9MSEX5335, DUKHCONP1AZ9ELTC8010, DUKHCONI1AZ5PSGL7015, DUKHCONP1AZ8ELTC8010, DUKHCONI1AZ5FFGL5210, DUKHCONI1AZ5WSGL5180, DUKHCONI1ASBGHGL7835, DUKHCONP1AZ3ELTC8010, DUKHCONP1AZ6ELTC8010, DUKHCONP1AZ7ELTC8010, DUKHCONP1AZ4ELTC8010, DUKHCONI1AZ5SLGL7210, DUKHCONI1AZ5STGL5260, DUKHCONI1AZ5TCGL5310, DUKHCONI1ASBTRGL7635, DUKHCONI1ASBIWGL7465, DUKHCONP1AZ5ELTC8010, DUKHCONP1AZ1ELTC8010 | DUKHHANP1AGNDM009020, DUKHHANP1AGNAB009015, DUKHHANP1AGNAB009015 | 0 | 0 | PACKAGE-1A
DUKHHANP1AGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 20 | 20 | 0% | 2015-01-08 | 2015-01-31 | 2015-01-08 | 2015-01-31 | 0 | Yes | DUKHHANP1AGNACTC9000, DUKHHANP1AGNPLTC9005, DUKHHANP1AGNACTC9000, DUKHHANP1AGNPLTC9005, DUKHHANP1AGNELTC9010, DUKHHANP1AGNELTC9010 | DUKHHANP1AGNDM009020, DUKHHANP1AGNDM009020 | 0 | 0 | PACKAGE-1A
DHBL.K35.L25 PACKAGE-1B |  | 90 | 90 | 0% | 2014-12-15 | 2015-03-31 | 2014-12-15 | 2015-03-31 | 0 |  |  |  | 0 | 0
DUKHHANP1BGNDM009020 | Demobilization & Handing Over | 60 | 60 | 0% | 2015-01-20 | 2015-03-31 | 2015-01-20 | 2015-03-31 | 0 | Yes | DUKHHANP1BGNACTC9000, DUKHHANP1BGNPLTC9005, DUKHHANP1BGNAB009015, DUKHHANP1BGNAB009015, DUKHHANP1BGNELTC9010 | DUKHKYDP010000001000 | 0 | 0 | PACKAGE-1B
DUKHHANP1BGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 30 | 30 | 0% | 2014-12-15 | 2015-01-19 | 2014-12-15 | 2015-01-19 | 0 | Yes | DUKHCONI1BSBIWGL7465, DUKHCONP1BZ5MSEX5335, DUKHCONP1BZ5ELTC8010, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ1PLTC8005, DUKHCONP1BZ4PLTC8005, DUKHCONP1BZ6ELTC8010, DUKHCONI1BZ4HDGL7040, DUKHCONP1BZ4MSEX5335, DUKHCONP1BZ6PLTC8005, DUKHCONI1BSBGHGL7835, DUKHCONI1BZ4STGL5260, DUKHCONI1BZ4PSGL7015, DUKHCONP1BZ5PLTC8005, DUKHCONP1BZ4ELTC8010, DUKHCONI1BZ4SLGL7210, DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ6MSEX5335, DUKHCONI1BSBTRGL7635, DUKHCONI1BZ4TCGL5310, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ2PLTC8005, DUKHCONP1BZ3PLTC8005, DUKHCONI1BZ4FFGL5210, DUKHCONI1BZ4WSGL5180 | DUKHHANP1BGNAB009015, DUKHHANP1BGNAB009015, DUKHHANP1BGNDM009020 | 0 | 0 | PACKAGE-1B
DUKHHANP1BGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 30 | 30 | 0% | 2014-12-15 | 2015-01-19 | 2014-12-15 | 2015-01-19 | 0 | Yes | DUKHCONP1BZ5ACTC8000, DUKHCONP1BZ3ACTC8000, DUKHCONI1BZ4PSGL7015, DUKHCONP1BZ4ACTC8000, DUKHCONI1BSBIWGL7465, DUKHCONP1BZ6ACTC8000, DUKHCONI1BSBTRGL7635, DUKHCONP1BZ1ACTC8000, DUKHCONI1BZ4HDGL7040, DUKHCONP1BZ2ACTC8000, DUKHCONI1BSBGHGL7835 | DUKHHANP1BGNDM009020, DUKHHANP1BGNAB009015, DUKHHANP1BGNAB009015 | 0 | 0 | PACKAGE-1B
DUKHHANP1BGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 30 | 30 | 0% | 2014-12-15 | 2015-01-19 | 2014-12-15 | 2015-01-19 | 0 | Yes | DUKHCONP1BZ2ELTC8010, DUKHCONP1BZ3ELTC8010, DUKHCONP1BZ4MSEX5335, DUKHCONI1BZ4FFGL5210, DUKHCONI1BZ4PSGL7015, DUKHCONI1BSBIWGL7465, DUKHCONI1BZ4HDGL7040, DUKHCONI1BZ4WSGL5180, DUKHCONP1BZ1ELTC8010, DUKHCONP1BZ4ELTC8010, DUKHCONP1BZ6MSEX5335, DUKHCONP1BZ6ELTC8010, DUKHCONI1BZ4STGL5260, DUKHCONP1BZ5ELTC8010, DUKHCONI1BSBTRGL7635, DUKHCONP1BZ5MSEX5335, DUKHCONI1BSBGHGL7835, DUKHCONI1BZ4TCGL5310 | DUKHHANP1BGNDM009020, DUKHHANP1BGNAB009015, DUKHHANP1BGNAB009015 | 0 | 0 | PACKAGE-1B
DUKHHANP1BGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 20 | 20 | 0% | 2015-01-08 | 2015-01-31 | 2015-01-08 | 2015-01-31 | 0 | Yes | DUKHHANP1BGNPLTC9005, DUKHHANP1BGNPLTC9005, DUKHHANP1BGNACTC9000, DUKHHANP1BGNELTC9010, DUKHHANP1BGNACTC9000, DUKHHANP1BGNELTC9010 | DUKHHANP1BGNDM009020, DUKHHANP1BGNDM009020 | 0 | 0 | PACKAGE-1B
DHBL.K35.L35 PACKAGE-2A |  | 90 | 90 | 0% | 2014-06-15 | 2014-09-30 | 2014-06-15 | 2014-09-30 | 0 |  |  |  | 0 | 0
DUKHHANP2AGNDM009020 | Demobilization & Handing Over | 60 | 60 | 0% | 2014-07-20 | 2014-09-30 | 2014-07-20 | 2014-09-30 | 0 | Yes | DUKHHANP2AGNAB009015, DUKHHANP2AGNAB009015, DUKHHANP2AGNACTC9000, DUKHHANP2AGNELTC9010, DUKHHANP2AGNPLTC9005 | DUKHKYDP020000002000 | 0 | 0 | PACKAGE-2A
DUKHHANP2AGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 30 | 30 | 0% | 2014-06-15 | 2014-07-19 | 2014-06-15 | 2014-07-19 | 0 | Yes | DUKHCONP2AZ1PLTC8005, DUKHHANP2AGNELTC9010, DUKHCONI2AZ2HDGL7040, DUKHCONI2AZ2STGL5260, DUKHCONI2AZ2WSGL5180, DUKHCONP2AZ2MSEX5335, DUKHCONP2AZ2PLTC8005, DUKHCONI2ASBIWGL7465, DUKHCONI2AZ2SLGL7210, DUKHCONI2AZ2TCGL5310, DUKHCONI2AZ2FFGL5210 | DUKHHANP2AGNAB009015, DUKHHANP2AGNDM009020, DUKHHANP2AGNAB009015 | 0 | 0 | PACKAGE-2A
DUKHHANP2AGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 30 | 30 | 0% | 2014-06-15 | 2014-07-19 | 2014-06-15 | 2014-07-19 | 0 | Yes | DUKHCONI2AZ2TCGL5310, DUKHCONI2AZ2STGL5260, DUKHCONP2AZ1ACTC8000, DUKHCONI2AZ2WSGL5180, DUKHCONP2AZ2MSEX5335, DUKHCONP2AZ2ACTC8000, DUKHCONI2ASBIWGL7465, DUKHCONI2AZ2FFGL5210, DUKHCONP2AZ2ELTC8010, DUKHHANP2AGNELTC9010, DUKHCONP2AZ1ELTC8010 | DUKHHANP2AGNAB009015, DUKHHANP2AGNDM009020, DUKHHANP2AGNAB009015 | 0 | 0 | PACKAGE-2A
DUKHHANP2AGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 30 | 30 | 0% | 2014-06-15 | 2014-07-19 | 2014-06-15 | 2014-07-19 | 0 | Yes | DUKHCONI2AZ2WSGL5180, DUKHCONI2AZ2TCGL5310, DUKHCONI2AZ2PSGL7015, DUKHCONP2AZ2ELTC8010, DUKHCONI2AZ2FFGL5210, DUKHCONI2AZ2HDGL7040, DUKHCONP2AZ1ELTC8010, DUKHCONI2ASBIWGL7465, DUKHCONI2AZ2STGL5260, DUKHCONP2AZ2MSEX5335 | DUKHHANP2AGNAB009015, DUKHHANP2AGNPLTC9005, DUKHHANP2AGNAB009015, DUKHHANP2AGNDM009020, DUKHHANP2AGNACTC9000 | 0 | 0 | PACKAGE-2A
DUKHHANP2AGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 20 | 20 | 0% | 2014-07-08 | 2014-07-30 | 2014-07-08 | 2014-07-30 | 0 | Yes | DUKHHANP2AGNELTC9010, DUKHHANP2AGNACTC9000, DUKHHANP2AGNPLTC9005, DUKHHANP2AGNELTC9010, DUKHHANP2AGNACTC9000, DUKHHANP2AGNPLTC9005 | DUKHHANP2AGNDM009020, DUKHHANP2AGNDM009020 | 0 | 0 | PACKAGE-2A
DHBL.K35.L40 PACKAGE-2B |  | 90 | 90 | 0% | 2014-06-15 | 2014-09-30 | 2014-06-15 | 2014-09-30 | 0 |  |  |  | 0 | 0
DUKHHANP2BGNDM009020 | Demobilization & Handing Over | 60 | 60 | 0% | 2014-07-20 | 2014-09-30 | 2014-07-20 | 2014-09-30 | 0 | Yes | DUKHHANP2BGNAB009015, DUKHHANP2BGNPLTC9005, DUKHHANP2BGNACTC9000, DUKHHANP2BGNELTC9010, DUKHHANP2BGNAB009015 | DUKHKYDP020000002000 | 0 | 0 | PACKAGE-2B
DUKHHANP2BGNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 30 | 30 | 0% | 2014-06-15 | 2014-07-19 | 2014-06-15 | 2014-07-19 | 0 | Yes | DUKHCONP2BZ3PLTC8005, DUKHCONP2BZ5MSEX5335, DUKHCONI2BZ2STGL5260, DUKHCONP2BZ4PLTC8005, DUKHCONI2BZ2HDGL7040, DUKHCONI2BSBIWGL7465, DUKHCONI2BZ2TCGL5310, DUKHCONI2BZ2FFGL5210, DUKHCONP2BZ5PLTC8005, DUKHCONI2BZ2PSGL7015, DUKHCONI2BZ2SLGL7210, DUKHCONI2BZ2WSGL5180 | DUKHHANP2BGNAB009015, DUKHHANP2BGNAB009015, DUKHHANP2BGNDM009020 | 0 | 0 | PACKAGE-2B
DUKHHANP2BGNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 30 | 30 | 0% | 2014-06-15 | 2014-07-19 | 2014-06-15 | 2014-07-19 | 0 | Yes | DUKHCONI2BZ2TCGL5310, DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5MSEX5335, DUKHCONI2BZ2WSGL5180, DUKHCONP2BZ4ELTC8010, DUKHCONP2BZ3ELTC8010, DUKHCONP2BZ4ACTC8000, DUKHCONP2BZ5ACTC8000, DUKHCONI2BZ2SLGL7210, DUKHCONI2BZ2FFGL5210, DUKHCONI2BZ2STGL5260, DUKHCONI2BSBIWGL7465, DUKHCONP2BZ3ACTC8000, DUKHCONI2BZ2PSGL7015 | DUKHHANP2BGNAB009015, DUKHHANP2BGNAB009015, DUKHHANP2BGNDM009020 | 0 | 0 | PACKAGE-2B
DUKHHANP2BGNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 30 | 30 | 0% | 2014-06-15 | 2014-07-19 | 2014-06-15 | 2014-07-19 | 0 | Yes | DUKHCONI2BZ2HDGL7040, DUKHCONI2BSBIWGL7465, DUKHCONP2BZ4MSEX5335, DUKHCONI2BZ2PSGL7015, DUKHCONI2BZ2FFGL5210, DUKHCONP2BZ5ELTC8010, DUKHCONP2BZ5MSEX5335, DUKHCONP2BZ4ELTC8010, DUKHCONI2BZ2STGL5260, DUKHCONP2BZ3ELTC8010, DUKHCONI2BZ2TCGL5310 | DUKHHANP2BGNDM009020, DUKHHANP2BGNAB009015, DUKHHANP2BGNAB009015 | 0 | 0 | PACKAGE-2B
DUKHHANP2BGNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 20 | 20 | 0% | 2014-07-08 | 2014-07-30 | 2014-07-08 | 2014-07-30 | 0 | Yes | DUKHHANP2BGNPLTC9005, DUKHHANP2BGNPLTC9005, DUKHHANP2BGNACTC9000, DUKHHANP2BGNACTC9000, DUKHHANP2BGNELTC9010, DUKHHANP2BGNELTC9010 | DUKHHANP2BGNDM009020, DUKHHANP2BGNDM009020 | 0 | 0 | PACKAGE-2B
DHBL.K35.L45 PACKAGE-3 |  | 90 | 90 | 0% | 2014-08-16 | 2014-11-30 | 2014-08-16 | 2014-11-30 | 0 |  |  |  | 0 | 0
DUKHHANP03GNDM009020 | Demobilization & Handing Over | 60 | 60 | 0% | 2014-09-20 | 2014-11-30 | 2014-09-20 | 2014-11-30 | 0 | Yes | DUKHHANP03GNAB009015, DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000, DUKHHANP03GNAB009015, DUKHHANP03GNELTC9010 | DUKHKYDP030000003000 | 0 | 0 | PACKAGE-3
DUKHHANP03GNPLTC9005 | Submission & Clearance of Punch list, Final Testing &Commissioning of Plumbing/Drainage | 30 | 30 | 0% | 2014-08-16 | 2014-09-18 | 2014-08-16 | 2014-09-18 | 0 | Yes | DUKHCONI03Z3FFGL5210, DUKHCONI03Z3TCGL5310, DUKHCONI03SBIWGL7465, DUKHCONI03SBPGGL7945, DUKHCONP03Z4PLTC8005, DUKHCONI03Z3WSGL5180, DUKHCONP03Z2PLTC8005, DUKHCONI03SBGHGL7835, DUKHCONP03Z1PLTC8005, DUKHCONP03Z5PLTC8005, DUKHCONP03Z3PLTC8005, DUKHCONI03Z3PSGL7015, DUKHCONI03Z3SLGL7210, DUKHCONI03Z3HDGL7040, DUKHCONI03SBTRGL7635 | DUKHHANP03GNAB009015, DUKHHANP03GNDM009020, DUKHHANP03GNAB009015 | 0 | 0 | PACKAGE-3
DUKHHANP03GNACTC9000 | Submission & Clearance of Punch list,Final Testing & Commissioning of AC Works | 30 | 30 | 0% | 2014-08-16 | 2014-09-18 | 2014-08-16 | 2014-09-18 | 0 | Yes | DUKHCONP03Z4ELTC8010, DUKHCONP03Z3ELTC8010, DUKHCONI03Z3FFGL5210, DUKHCONP03Z2ACTC8000, DUKHCONI03SBTRGL7635, DUKHCONI03Z3TCGL5310, DUKHCONP03Z1ACTC8000, DUKHCONI03Z3STGL5260, DUKHCONI03Z3PSGL7015, DUKHCONI03SBIWGL7465, DUKHCONI03SBGHGL7835, DUKHCONP03Z5ACTC8000, DUKHCONI03SBPGGL7945, DUKHCONP03Z3ACTC8000, DUKHCONP03Z4ACTC8000, DUKHCONI03Z3HDGL7040 | DUKHHANP03GNAB009015, DUKHHANP03GNDM009020, DUKHHANP03GNAB009015 | 0 | 0 | PACKAGE-3
DUKHHANP03GNELTC9010 | Submission & Clearance Punch list,Final Testing & Commissioning of Electrical Works | 30 | 30 | 0% | 2014-08-16 | 2014-09-18 | 2014-08-16 | 2014-09-18 | 0 | Yes | DUKHCONI03Z3WSGL5180, DUKHCONI03SBGHGL7835, DUKHCONI03Z3STGL5260, DUKHCONI03Z3TCGL5310, DUKHCONP03Z3ELTC8010, DUKHCONI03Z3FFGL5210, DUKHCONI03Z3SLGL7210, DUKHCONI03Z3HDGL7040, DUKHCONI03SBTRGL7635, DUKHCONP03Z4ELTC8010, DUKHCONI03Z3PSGL7015, DUKHCONP03Z2ELTC8010, DUKHCONP03Z5ELTC8010, DUKHCONI03SBIWGL7465, DUKHCONI03SBPGGL7945, DUKHCONP03Z1ELTC8010 | DUKHHANP03GNAB009015, DUKHHANP03GNAB009015, DUKHHANP03GNDM009020 | 0 | 0 | PACKAGE-3
DUKHHANP03GNAB009015 | Submission & Approval of As-Built Drawings & O&M Manuals | 20 | 20 | 0% | 2014-09-08 | 2014-09-30 | 2014-09-08 | 2014-09-30 | 0 | Yes | DUKHHANP03GNPLTC9005, DUKHHANP03GNACTC9000, DUKHHANP03GNELTC9010, DUKHHANP03GNACTC9000, DUKHHANP03GNELTC9010, DUKHHANP03GNPLTC9005 | DUKHHANP03GNDM009020, DUKHHANP03GNDM009020 | 0 | 0 | PACKAGE-3