## Includes Material
RR Expenditure Type ID | Resource ID Name | Total Hours per resource from 2012- AP10 - 2025- AP04 period | RR Expenditure Type | Resource ID Name | 2012-AP10 | 2012-AP11 | 2012-AP12 | 2013-AP01 | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 | 2014-AP05 | 2014-AP06 | 2014-AP07 | 2014-AP08 | 2014-AP09 | 2014-AP10 | 2014-AP11 | 2014-AP12 | 2015-AP01 | 2015-AP02 | 2015-AP03 | 2015-AP04 | Total Hours
EQOP | EQUIP OPERATORS | 162108 | Resource ID: EQOP | EQOP.EQUIP OPERATORS |  | 956 | 5040 | 6466 | 1030 | 1573 | 5349 | 5714 | 6609 | 7097 | 4995 | 4183 | 6205 | 5781 | 8007 | 12985 | 12964 | 11141 | 13853 | 9183 | 9799 | 7887 | 5933 | 4846 | 2579 | 1843 | 90 |  |  |  |  | 162108
J302 | BLINDING MASON SK | 38273 | Resource ID: J302 | J302.BLINDING MASON SK |  |  |  |  | 239 | 777 | 1217 | 1975 | 4130 | 5335 | 4460 | 4604 | 4673 | 2982 | 2657 | 3606 | 1162 | 328 |  | 64 | 64 | [10 empty] | 38273
J303 | SCREED MASON SK | 96090 | Resource ID: J303 | J303.SCREED MASON SK | [5 empty] | 568 | 1330 | 1932 | 3175 | 4116 | 4123 | 5032 | 8365 | 7723 | 8531 | 13715 | 8002 | 7168 | 7605 | 5522 | 5121 | 2323 | 1309 | 254 | 162 | 14 | [5 empty] | 96090
J304 | STEEL FIXERS SK | 325360 | Resource ID: J304 | J304.STEEL FIXERS SK |  |  |  | 161 | 64 | 2878 | 7522 | 8959 | 13290 | 23418 | 19882 | 27934 | 38001 | 35142 | 27341 | 38624 | 25092 | 22983 | 17411 | 6307 | 4313 | 2266 | 1062 | 961 | 947 | 789 | 13 |  |  |  |  | 325360
J305 | CARPENTERS SK | 430942 | Resource ID: J305 | J305.CARPENTERS SK |  |  | 40 | 630 | 80 | 1512 | 5789 | 8235 | 13031 | 29778 | 28382 | 39094 | 52262 | 47555 | 36787 | 52816 | 34102 | 31263 | 24794 | 10050 | 6644 | 3731 | 1229 | 1489 | 981 | 661 | 7 |  |  |  |  | 430942
J306 | CONCRETE MASON SK | 86203 | Resource ID: J306 | J306.CONCRETE MASON SK | [5 empty] | 564 | 1493 | 1944 | 3471 | 5588 | 6293 | 6933 | 9365 | 7708 | 6985 | 9857 | 6210 | 6342 | 5663 | 2432 | 2100 | 1324 | 703 | 695 | 394 | 125 | 14 |  |  |  |  | 86203
J307 | BLOCK MASON SK | 261061 | Resource ID: J307 | J307.BLOCK MASON SK |  |  | 50 | 770 | 80 | [5 empty] | 4068 | 17559 | 25891 | 29645 | 26889 | 40665 | 27470 | 24650 | 28061 | 20387 | 9879 | 4933 | 64 | [8 empty] | 261061
J308 | PLASTER MASON SK | 482981 | Resource ID: J308 | J308.PLASTER MASON SK |  |  | 45 | 700 | 80 | [5 empty] | 1338 | 4903 | 21867 | 31416 | 40853 | 75542 | 58192 | 57026 | 60428 | 45248 | 46852 | 26750 | 10141 | 320 | 1136 | 144 | [5 empty] | 482981
J309 | TILE MASON SK | 172303 | Resource ID: J309 | J309.TILE MASON SK | [11 empty] | 1187 | 4863 | 9933 | 13192 | 27401 | 21477 | 19639 | 21807 | 16528 | 15913 | 13715 | 4613 | 1939 | 81 | 15 | [5 empty] | 172303
J310 | GRANITE MASON SK | 23811 | Resource ID: J310 | J310.GRANITE MASON SK | [12 empty] | 176 | 255 | 678 | 2099 | 2203 | 3005 | 3276 | 2721 | 2950 | 2945 | 2231 | 961 | 303 | 8 | [5 empty] | 23811
J311 | MANHOLES SK | 25888 | Resource ID: J311 | J311.MANHOLES SK | [11 empty] | 311 | 1139 | 2086 | 2740 | 5059 | 2977 | 2889 | 2880 | 2146 | 1982 | 1073 | 606 | [8 empty] | 25888
J312 | KERBSTONE MASON SK | 27257 | Resource ID: J312 | J312.KERBSTONE MASON SK | [12 empty] | 113 | 130 | 193 | 2209 | 3169 | 3273 | 3731 | 2940 | 3366 | 2043 | 1559 | 2192 | 1401 | 938 | [5 empty] | 27257
J313 | INTERLOCK MASON SK | 19348 | Resource ID: J313 | J313.INTERLOCK MASON SK | [10 empty] | 62 | 185 | 417 | 462 | 695 | 1936 | 2234 | 2502 | 2139 | 2208 | 1487 | 1526 | 1107 | 762 | 1626 | [6 empty] | 19348
J315 | SURVEYOR SK | 250 | Resource ID: J315 | J315.SURVEYOR SK |  | 40 | 210 | [28 empty] | 250
J320 | DRAFTMAN SK | 9319 | Resource ID: J320 | J320.DRAFTMAN SK |  | 324 | 670 | 637 | 532 | 919 | 1126 | 808 | 720 | 144 | [11 empty] | 816 | 368 | 712 | 312 | 192 |  | 707 | 161 | 161 | 10 | 9319
LC30 | LABOR - CIVIL | 1242744 | Resource ID: LC30 | LC30.LABOR - CIVIL |  | 901 | 4531 | 6005 | 2111 | 6348 | 15785 | 19484 | 29814 | 52531 | 51250 | 76104 | 111868 | 111143 | 103960 | 160983 | 111468 | 103814 | 100578 | 58990 | 50940 | 31232 | 16481 | 9444 | 4240 | 2114 | 25 | 101 | 242 | 242 | 15 | 1242744
LS30 | LABOR- SUBCONTRACTOR | 823891 | Resource ID: LS30 | LS30.LABOR- SUBCONTRACTOR |  |  |  |  | 317 | 1259 | 2248 | 1754 | 2136 | 1879 | 1531 | 5445 | 15430 | 24195 | 35137 | 77609 | 73989 | 83578 | 104759 | 78197 | 82390 | 80280 | 48629 | 39004 | 28694 | 14119 | 5103 | 6209 | 4800 | 4800 | 400 | 823891
M301 | AC TECHNICIAN SK | 124145 | Resource ID: M301 | M301.AC TECHNICIAN SK | [10 empty] | 4 | 247 | 1350 | 2139 | 4248 | 7592 | 8448 | 10523 | 16258 | 12656 | 13922 | 13111 | 8144 | 8128 | 5994 | 3261 | 1640 | 2480 | 1920 | 1920 | 160 | 124145
M302 | ELECTRICIANS SK | 474315 | Resource ID: M302 | M302.ELECTRICIANS SK |  | 74 | 295 | 672 | 264 | 25 |  |  |  |  | 428 | 4731 | 11607 | 18356 | 27024 | 47790 | 41020 | 45747 | 62854 | 42438 | 43717 | 40274 | 26105 | 21703 | 15711 | 7181 | 3331 | 4968 | 3840 | 3840 | 320 | 474315
M303 | MECHANICALS SK | 264273 | Resource ID: M303 | M303.MECHANICALS SK |  | 71 | 290 | 744 | 256 | 24 |  | 165 | 495 | 442 | 936 | 5425 | 10407 | 11830 | 12333 | 21302 | 18539 | 19601 | 30485 | 20746 | 22625 | 24014 | 15770 | 15578 | 9676 | 6279 | 3280 | 4960 | 3840 | 3840 | 320 | 264273
M304 | MATERIAL ENGG | 4376 | Resource ID: M304 | M304.MATERIAL ENGG | 8 | 144 | 348 | 497 | 353 | 734 | 775 | 708 | 403 | 293 | 77 | 21 | 15 | [18 empty] | 4376
M305 | QUANTITY SURVEYOUR | 1140 | Resource ID: M305 | M305.QUANTITY SURVEYOUR | 16 | 329 | 397 | 398 | [27 empty] | 1140
M306 | SAFETY OFFICER | 801 | Resource ID: M306 | M306.SAFETY OFFICER | 24 | 358 | 237 | 182 | [27 empty] | 801
S301 | WATERPROOFING SPECIALIST SK | 79257 | Resource ID: S301 | S301.WATERPROOFING SPECIALIST SK |  |  |  |  | 263 | 947 | 2080 | 1408 | 1821 | 1519 | 853 | 1326 | 3251 | 4528 | 5413 | 10858 | 8740 | 8225 | 6740 | 6162 | 6546 | 4420 | 2954 | 1203 | [7 empty] | 79257
S302 | PAINTERS SK | 405365 | Resource ID: S302 | S302.PAINTERS SK | [11 empty] | 904 | 7244 | 11561 | 19297 | 40502 | 39031 | 46764 | 55019 | 43034 | 42163 | 41132 | 24245 | 15828 | 14139 | 4502 | [5 empty] | 405365
S303 | FALSE CEILING SKILLED SK | 80233 | Resource ID: S303 | S303.FALSE CEILING SKILLED SK | [12 empty] | 1173 | 2211 | 4231 | 13160 | 10019 | 9841 | 10504 | 7805 | 7332 | 6905 | 4308 | 2452 | 292 | [6 empty] | 80233
S304 | DOOR ERECTOR SK | 32351 | Resource ID: S304 | S304.DOOR ERECTOR SK | [12 empty] | 135 | 605 | 695 | 2924 | 3689 | 4520 | 4856 | 3216 | 3404 | 3598 | 1752 | 2027 | 818 | 112 | [5 empty] | 32351
S305 | WINDOW ERECTOR SK | 6925 | Resource ID: S305 | S305.WINDOW ERECTOR SK | [12 empty] | 9 | 75 | 137 | 426 | 802 | 847 | 1062 | 763 | 789 | 791 | 468 | 499 | 257 | [6 empty] | 6925
S306 | JOINERY WORK SK | 28424 | Resource ID: S306 | S306.JOINERY WORK SK | [12 empty] | 15 | 529 | 526 | 2162 | 3503 | 3262 | 3750 | 2602 | 3006 | 3441 | 1875 | 2158 | 1546 | 49 | [5 empty] | 28424
S307 | COUNTER SK | 2015 | Resource ID: S307 | S307.COUNTER SK | [13 empty] | 4 | 1 | 42 | 145 | 177 | 246 | 241 | 269 | 320 | 195 | 207 | 168 | [6 empty] | 2015
S308 | HANDRAIL ERECTOR SKILLED | 14195 | Resource ID: S308 | S308.HANDRAIL ERECTOR SKILLED | [11 empty] | 20 | 88 | 325 | 587 | 1144 | 1274 | 1594 | 2065 | 1636 | 1687 | 1183 | 820 | 854 | 855 | 63 | [5 empty] | 14195
S309 | EPOXY SK | 1494 | Resource ID: S309 | S309.EPOXY SK | [12 empty] | 5 |  |  | 120 | 131 | 142 | 221 | 169 | 194 | 257 | 63 | 51 | 100 | 41 | [5 empty] | 1494
S310 | PRE CAST CONCRETE SK | 9841 | Resource ID: S310 | S310.PRE CAST CONCRETE SK | [11 empty] | 27 | 98 | 555 | 514 | 1415 | 1358 | 1257 | 1097 | 863 | 1031 | 785 | 432 | 409 | [7 empty] | 9841
S311 | LADDER ERECTOR SK | 4949 | Resource ID: S311 | S311.LADDER ERECTOR SK | [11 empty] | 16 | 88 | 169 | 208 | 518 | 575 | 694 | 765 | 392 | 388 | 576 | 273 | 122 | 157 | 8 | [5 empty] | 4949
S312 | LANDSCAPING SK | 72416 | Resource ID: S312 | S312.LANDSCAPING SK | [14 empty] | 830 | 2921 | 4946 | 8269 | 10437 | 6992 | 9043 | 10158 | 5936 | 3719 | 4691 | 3842 | 632 |  |  |  |  | 72416
S313 | GATE ERECTOR SK | 1764 | Resource ID: S313 | S313.GATE ERECTOR SK | [11 empty] | 10 | 123 | 152 | 155 | 268 | 201 | 191 | 148 | 110 | 122 | 124 | 93 | 56 | 11 | [6 empty] | 1764
S314 | STEEL ERECTOR SK | 16062 | Resource ID: S314 | S314.STEEL ERECTOR SK | [13 empty] | 166 | 295 | 692 | 896 | 1607 | 2571 | 1437 | 1561 | 1908 | 1367 | 667 | 1457 | 751 | 679 | 8 |  |  |  | 16062
S315 | PULL BOX SK | 1166 | Resource ID: S315 | S315.PULL BOX SK | [15 empty] | 55 | 154 | 204 | 174 | 110 | 69 | 113 | 83 | 63 | 135 | 6 | [5 empty] | 1166
S316 | ASPHALT SK | 2472 | Resource ID: S316 | S316.ASPHALT SK | [17 empty] | 190 | 570 | 192 | 264 | 320 | 221 | 91 | 312 | 160 | 152 |  |  |  |  | 2472
S317 | EXPANSION JOINT SKILLED SK | 2656 | Resource ID: S317 | S317.EXPANSION JOINT SKILLED SK | [14 empty] | 152 | 719 | 423 | 363 | 393 | 153 | 85 | 168 | 105 | 95 | [7 empty] | 2656
S318 | DOOR WORK SK | 1000 | Resource ID: S318 | S318.DOOR WORK SK | [15 empty] | 8 | 192 | 136 | 200 | 64 |  |  | 16 | 312 | 72 | [6 empty] | 1000
S319 | GRC SK | 4800 | Resource ID: S319 | S319.GRC SK | [13 empty] | 400 | 300 | 500 | 680 | 760 | 880 | 380 | 420 | 480 | [9 empty] | 4800
S320 | ANTITERMITE SK | 25041 | Resource ID: S320 | S320.ANTITERMITE SK |  |  |  |  | 580 | 2409 | 3910 | 3138 | 3457 | 3112 | 2173 | 2720 | 2666 | 876 | [17 empty] | 25041
|  | 0 | [33 empty] | 0

## Sheet1 (3)
RR Expenditure Type ID | Resource ID Name | Total Hours per resource from 2012- AP10 - 2025- AP04 period | RR Expenditure Type | Resource ID Name | 2012-AP10 | 2012-AP11 | 2012-AP12 | 2013-AP01 | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 | 2014-AP05 | 2014-AP06 | 2014-AP07 | 2014-AP08 | 2014-AP09 | 2014-AP10 | 2014-AP11 | 2014-AP12 | 2015-AP01 | 2015-AP02 | 2015-AP03 | 2015-AP04 | Total Hours
EQOP | EQUIP OPERATORS | 162108 | Resource ID: EQOP | EQOP.EQUIP OPERATORS |  | 956 | 5040 | 6466 | 1030 | 1573 | 5349 | 5714 | 6609 | 7097 | 4995 | 4183 | 6205 | 5781 | 8007 | 12985 | 12964 | 11141 | 13853 | 9183 | 9799 | 7887 | 5933 | 4846 | 2579 | 1843 | 90 |  |  |  |  | 162108
J302 | BLINDING MASON SK | 38273 | Resource ID: J302 | J302.BLINDING MASON SK |  |  |  |  | 239 | 777 | 1217 | 1975 | 4130 | 5335 | 4460 | 4604 | 4673 | 2982 | 2657 | 3606 | 1162 | 328 |  | 64 | 64 | [10 empty] | 38273
J303 | SCREED MASON SK | 96090 | Resource ID: J303 | J303.SCREED MASON SK | [5 empty] | 568 | 1330 | 1932 | 3175 | 4116 | 4123 | 5032 | 8365 | 7723 | 8531 | 13715 | 8002 | 7168 | 7605 | 5522 | 5121 | 2323 | 1309 | 254 | 162 | 14 | [5 empty] | 96090
J304 | STEEL FIXERS SK | 325360 | Resource ID: J304 | J304.STEEL FIXERS SK |  |  |  | 161 | 64 | 2878 | 7522 | 8959 | 13290 | 23418 | 19882 | 27934 | 38001 | 35142 | 27341 | 38624 | 25092 | 22983 | 17411 | 6307 | 4313 | 2266 | 1062 | 961 | 947 | 789 | 13 |  |  |  |  | 325360
J305 | CARPENTERS SK | 430942 | Resource ID: J305 | J305.CARPENTERS SK |  |  | 40 | 630 | 80 | 1512 | 5789 | 8235 | 13031 | 29778 | 28382 | 39094 | 52262 | 47555 | 36787 | 52816 | 34102 | 31263 | 24794 | 10050 | 6644 | 3731 | 1229 | 1489 | 981 | 661 | 7 |  |  |  |  | 430942
J306 | CONCRETE MASON SK | 86203 | Resource ID: J306 | J306.CONCRETE MASON SK | [5 empty] | 564 | 1493 | 1944 | 3471 | 5588 | 6293 | 6933 | 9365 | 7708 | 6985 | 9857 | 6210 | 6342 | 5663 | 2432 | 2100 | 1324 | 703 | 695 | 394 | 125 | 14 |  |  |  |  | 86203
J307 | BLOCK MASON SK | 261061 | Resource ID: J307 | J307.BLOCK MASON SK |  |  | 50 | 770 | 80 | [5 empty] | 4068 | 17559 | 25891 | 29645 | 26889 | 40665 | 27470 | 24650 | 28061 | 20387 | 9879 | 4933 | 64 | [8 empty] | 261061
J308 | PLASTER MASON SK | 482981 | Resource ID: J308 | J308.PLASTER MASON SK |  |  | 45 | 700 | 80 | [5 empty] | 1338 | 4903 | 21867 | 31416 | 40853 | 75542 | 58192 | 57026 | 60428 | 45248 | 46852 | 26750 | 10141 | 320 | 1136 | 144 | [5 empty] | 482981
J309 | TILE MASON SK | 172303 | Resource ID: J309 | J309.TILE MASON SK | [11 empty] | 1187 | 4863 | 9933 | 13192 | 27401 | 21477 | 19639 | 21807 | 16528 | 15913 | 13715 | 4613 | 1939 | 81 | 15 | [5 empty] | 172303
J310 | GRANITE MASON SK | 23811 | Resource ID: J310 | J310.GRANITE MASON SK | [12 empty] | 176 | 255 | 678 | 2099 | 2203 | 3005 | 3276 | 2721 | 2950 | 2945 | 2231 | 961 | 303 | 8 | [5 empty] | 23811
J311 | MANHOLES SK | 25888 | Resource ID: J311 | J311.MANHOLES SK | [11 empty] | 311 | 1139 | 2086 | 2740 | 5059 | 2977 | 2889 | 2880 | 2146 | 1982 | 1073 | 606 | [8 empty] | 25888
J312 | KERBSTONE MASON SK | 27257 | Resource ID: J312 | J312.KERBSTONE MASON SK | [12 empty] | 113 | 130 | 193 | 2209 | 3169 | 3273 | 3731 | 2940 | 3366 | 2043 | 1559 | 2192 | 1401 | 938 | [5 empty] | 27257
J313 | INTERLOCK MASON SK | 19348 | Resource ID: J313 | J313.INTERLOCK MASON SK | [10 empty] | 62 | 185 | 417 | 462 | 695 | 1936 | 2234 | 2502 | 2139 | 2208 | 1487 | 1526 | 1107 | 762 | 1626 | [6 empty] | 19348
J315 | SURVEYOR SK | 250 | Resource ID: J315 | J315.SURVEYOR SK |  | 40 | 210 | [28 empty] | 250
J320 | DRAFTMAN SK | 9319 | Resource ID: J320 | J320.DRAFTMAN SK |  | 324 | 670 | 637 | 532 | 919 | 1126 | 808 | 720 | 144 | [11 empty] | 816 | 368 | 712 | 312 | 192 |  | 707 | 161 | 161 | 10 | 9319
LC30 | LABOR - CIVIL | 1242744 | Resource ID: LC30 | LC30.LABOR - CIVIL |  | 901 | 4531 | 6005 | 2111 | 6348 | 15785 | 19484 | 29814 | 52531 | 51250 | 76104 | 111868 | 111143 | 103960 | 160983 | 111468 | 103814 | 100578 | 58990 | 50940 | 31232 | 16481 | 9444 | 4240 | 2114 | 25 | 101 | 242 | 242 | 15 | 1242744
LS30 | LABOR- SUBCONTRACTOR | 823891 | Resource ID: LS30 | LS30.LABOR- SUBCONTRACTOR |  |  |  |  | 317 | 1259 | 2248 | 1754 | 2136 | 1879 | 1531 | 5445 | 15430 | 24195 | 35137 | 77609 | 73989 | 83578 | 104759 | 78197 | 82390 | 80280 | 48629 | 39004 | 28694 | 14119 | 5103 | 6209 | 4800 | 4800 | 400 | 823891
M301 | AC TECHNICIAN SK | 124145 | Resource ID: M301 | M301.AC TECHNICIAN SK | [10 empty] | 4 | 247 | 1350 | 2139 | 4248 | 7592 | 8448 | 10523 | 16258 | 12656 | 13922 | 13111 | 8144 | 8128 | 5994 | 3261 | 1640 | 2480 | 1920 | 1920 | 160 | 124145
M302 | ELECTRICIANS SK | 474315 | Resource ID: M302 | M302.ELECTRICIANS SK |  | 74 | 295 | 672 | 264 | 25 |  |  |  |  | 428 | 4731 | 11607 | 18356 | 27024 | 47790 | 41020 | 45747 | 62854 | 42438 | 43717 | 40274 | 26105 | 21703 | 15711 | 7181 | 3331 | 4968 | 3840 | 3840 | 320 | 474315
M303 | MECHANICALS SK | 264273 | Resource ID: M303 | M303.MECHANICALS SK |  | 71 | 290 | 744 | 256 | 24 |  | 165 | 495 | 442 | 936 | 5425 | 10407 | 11830 | 12333 | 21302 | 18539 | 19601 | 30485 | 20746 | 22625 | 24014 | 15770 | 15578 | 9676 | 6279 | 3280 | 4960 | 3840 | 3840 | 320 | 264273
M304 | MATERIAL ENGG | 4376 | Resource ID: M304 | M304.MATERIAL ENGG | 8 | 144 | 348 | 497 | 353 | 734 | 775 | 708 | 403 | 293 | 77 | 21 | 15 | [18 empty] | 4376
M305 | QUANTITY SURVEYOUR | 1140 | Resource ID: M305 | M305.QUANTITY SURVEYOUR | 16 | 329 | 397 | 398 | [27 empty] | 1140
M306 | SAFETY OFFICER | 801 | Resource ID: M306 | M306.SAFETY OFFICER | 24 | 358 | 237 | 182 | [27 empty] | 801
S301 | WATERPROOFING SPECIALIST SK | 79257 | Resource ID: S301 | S301.WATERPROOFING SPECIALIST SK |  |  |  |  | 263 | 947 | 2080 | 1408 | 1821 | 1519 | 853 | 1326 | 3251 | 4528 | 5413 | 10858 | 8740 | 8225 | 6740 | 6162 | 6546 | 4420 | 2954 | 1203 | [7 empty] | 79257
S302 | PAINTERS SK | 405365 | Resource ID: S302 | S302.PAINTERS SK | [11 empty] | 904 | 7244 | 11561 | 19297 | 40502 | 39031 | 46764 | 55019 | 43034 | 42163 | 41132 | 24245 | 15828 | 14139 | 4502 | [5 empty] | 405365
S303 | FALSE CEILING SKILLED SK | 80233 | Resource ID: S303 | S303.FALSE CEILING SKILLED SK | [12 empty] | 1173 | 2211 | 4231 | 13160 | 10019 | 9841 | 10504 | 7805 | 7332 | 6905 | 4308 | 2452 | 292 | [6 empty] | 80233
S304 | DOOR ERECTOR SK | 32351 | Resource ID: S304 | S304.DOOR ERECTOR SK | [12 empty] | 135 | 605 | 695 | 2924 | 3689 | 4520 | 4856 | 3216 | 3404 | 3598 | 1752 | 2027 | 818 | 112 | [5 empty] | 32351
S305 | WINDOW ERECTOR SK | 6925 | Resource ID: S305 | S305.WINDOW ERECTOR SK | [12 empty] | 9 | 75 | 137 | 426 | 802 | 847 | 1062 | 763 | 789 | 791 | 468 | 499 | 257 | [6 empty] | 6925
S306 | JOINERY WORK SK | 28424 | Resource ID: S306 | S306.JOINERY WORK SK | [12 empty] | 15 | 529 | 526 | 2162 | 3503 | 3262 | 3750 | 2602 | 3006 | 3441 | 1875 | 2158 | 1546 | 49 | [5 empty] | 28424
S307 | COUNTER SK | 2015 | Resource ID: S307 | S307.COUNTER SK | [13 empty] | 4 | 1 | 42 | 145 | 177 | 246 | 241 | 269 | 320 | 195 | 207 | 168 | [6 empty] | 2015
S308 | HANDRAIL ERECTOR SKILLED | 14195 | Resource ID: S308 | S308.HANDRAIL ERECTOR SKILLED | [11 empty] | 20 | 88 | 325 | 587 | 1144 | 1274 | 1594 | 2065 | 1636 | 1687 | 1183 | 820 | 854 | 855 | 63 | [5 empty] | 14195
S309 | EPOXY SK | 1494 | Resource ID: S309 | S309.EPOXY SK | [12 empty] | 5 |  |  | 120 | 131 | 142 | 221 | 169 | 194 | 257 | 63 | 51 | 100 | 41 | [5 empty] | 1494
S310 | PRE CAST CONCRETE SK | 9841 | Resource ID: S310 | S310.PRE CAST CONCRETE SK | [11 empty] | 27 | 98 | 555 | 514 | 1415 | 1358 | 1257 | 1097 | 863 | 1031 | 785 | 432 | 409 | [7 empty] | 9841
S311 | LADDER ERECTOR SK | 4949 | Resource ID: S311 | S311.LADDER ERECTOR SK | [11 empty] | 16 | 88 | 169 | 208 | 518 | 575 | 694 | 765 | 392 | 388 | 576 | 273 | 122 | 157 | 8 | [5 empty] | 4949
S312 | LANDSCAPING SK | 72416 | Resource ID: S312 | S312.LANDSCAPING SK | [14 empty] | 830 | 2921 | 4946 | 8269 | 10437 | 6992 | 9043 | 10158 | 5936 | 3719 | 4691 | 3842 | 632 |  |  |  |  | 72416
S313 | GATE ERECTOR SK | 1764 | Resource ID: S313 | S313.GATE ERECTOR SK | [11 empty] | 10 | 123 | 152 | 155 | 268 | 201 | 191 | 148 | 110 | 122 | 124 | 93 | 56 | 11 | [6 empty] | 1764
S314 | STEEL ERECTOR SK | 16062 | Resource ID: S314 | S314.STEEL ERECTOR SK | [13 empty] | 166 | 295 | 692 | 896 | 1607 | 2571 | 1437 | 1561 | 1908 | 1367 | 667 | 1457 | 751 | 679 | 8 |  |  |  | 16062
S315 | PULL BOX SK | 1166 | Resource ID: S315 | S315.PULL BOX SK | [15 empty] | 55 | 154 | 204 | 174 | 110 | 69 | 113 | 83 | 63 | 135 | 6 | [5 empty] | 1166
S316 | ASPHALT SK | 2472 | Resource ID: S316 | S316.ASPHALT SK | [17 empty] | 190 | 570 | 192 | 264 | 320 | 221 | 91 | 312 | 160 | 152 |  |  |  |  | 2472
S317 | EXPANSION JOINT SKILLED SK | 2656 | Resource ID: S317 | S317.EXPANSION JOINT SKILLED SK | [14 empty] | 152 | 719 | 423 | 363 | 393 | 153 | 85 | 168 | 105 | 95 | [7 empty] | 2656
S318 | DOOR WORK SK | 1000 | Resource ID: S318 | S318.DOOR WORK SK | [15 empty] | 8 | 192 | 136 | 200 | 64 |  |  | 16 | 312 | 72 | [6 empty] | 1000
S319 | GRC SK | 4800 | Resource ID: S319 | S319.GRC SK | [13 empty] | 400 | 300 | 500 | 680 | 760 | 880 | 380 | 420 | 480 | [9 empty] | 4800
S320 | ANTITERMITE SK | 25041 | Resource ID: S320 | S320.ANTITERMITE SK |  |  |  |  | 580 | 2409 | 3910 | 3138 | 3457 | 3112 | 2173 | 2720 | 2666 | 876 | [17 empty] | 25041
|  | 0 | [33 empty] | 0

## Sheet3
RR Expenditure Type ID | Resource ID Name | Total Hours per resource from 2012- AP10 - 2025- AP04 period
EQOP | EQUIP OPERATORS | 162108
J302 | BLINDING MASON SK | 38273
J303 | SCREED MASON SK | 96090
J304 | STEEL FIXERS SK | 325360
J305 | CARPENTERS SK | 430942
J306 | CONCRETE MASON SK | 86203
J307 | BLOCK MASON SK | 261061
J308 | PLASTER MASON SK | 482981
J309 | TILE MASON SK | 172303
J310 | GRANITE MASON SK | 23811
J311 | MANHOLES SK | 25888
J312 | KERBSTONE MASON SK | 27257
J313 | INTERLOCK MASON SK | 19348
J315 | SURVEYOR SK | 250
J320 | DRAFTMAN SK | 9319
LC30 | LABOR - CIVIL | 1242744
LS30 | LABOR- SUBCONTRACTOR | 823891
M301 | AC TECHNICIAN SK | 124145
M302 | ELECTRICIANS SK | 474315
M303 | MECHANICALS SK | 264273
M304 | MATERIAL ENGG | 4376
M305 | QUANTITY SURVEYOUR | 1140
M306 | SAFETY OFFICER | 801
S301 | WATERPROOFING SPECIALIST SK | 79257
S302 | PAINTERS SK | 405365
S303 | FALSE CEILING SKILLED SK | 80233
S304 | DOOR ERECTOR SK | 32351
S305 | WINDOW ERECTOR SK | 6925
S306 | JOINERY WORK SK | 28424
S307 | COUNTER SK | 2015
S308 | HANDRAIL ERECTOR SKILLED | 14195
S309 | EPOXY SK | 1494
S310 | PRE CAST CONCRETE SK | 9841
S311 | LADDER ERECTOR SK | 4949
S312 | LANDSCAPING SK | 72416
S313 | GATE ERECTOR SK | 1764
S314 | STEEL ERECTOR SK | 16062
S315 | PULL BOX SK | 1166
S316 | ASPHALT SK | 2472
S317 | EXPANSION JOINT SKILLED SK | 2656
S318 | DOOR WORK SK | 1000
S319 | GRC SK | 4800
S320 | ANTITERMITE SK | 25041

## Sheet1 (2)
RR Expenditure Type ID | Resource ID Name | RR Expenditure Type | Resource ID Name | 2012-AP10 | 2012-AP11 | 2012-AP12 | 2013-AP01 | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 | 2014-AP05 | 2014-AP06 | 2014-AP07 | 2014-AP08 | 2014-AP09 | 2014-AP10 | 2014-AP11 | 2014-AP12 | 2015-AP01 | 2015-AP02 | 2015-AP03 | 2015-AP04 | Total Hours
|  | Total |  | 48 | 3197 | 12153 | 17862 | 6249 | 20537 | 48624 | 56224 | 82552 | 135252 | 130855 | 208921 | 338909 | 370637 | 391591 | 680224 | 535477 | 544515 | 608280 | 415084 | 402437 | 336922 | 191260 | 139801 | 99247 | 47217 | 14966 | 19433 | 14803 | 14803 | 1225 | 5889305
EQOP | EQUIP OPERATORS | Resource ID: EQOP | EQOP.EQUIP OPERATORS |  | 956 | 5040 | 6466 | 1030 | 1573 | 5349 | 5714 | 6609 | 7097 | 4995 | 4183 | 6205 | 5781 | 8007 | 12985 | 12964 | 11141 | 13853 | 9183 | 9799 | 7887 | 5933 | 4846 | 2579 | 1843 | 90 |  |  |  |  | 162108
J302 | BLINDING MASON SK | Resource ID: J302 | J302.BLINDING MASON SK |  |  |  |  | 239 | 777 | 1217 | 1975 | 4130 | 5335 | 4460 | 4604 | 4673 | 2982 | 2657 | 3606 | 1162 | 328 |  | 64 | 64 | [10 empty] | 38273
J303 | SCREED MASON SK | Resource ID: J303 | J303.SCREED MASON SK | [5 empty] | 568 | 1330 | 1932 | 3175 | 4116 | 4123 | 5032 | 8365 | 7723 | 8531 | 13715 | 8002 | 7168 | 7605 | 5522 | 5121 | 2323 | 1309 | 254 | 162 | 14 | [5 empty] | 96090
J304 | STEEL FIXERS SK | Resource ID: J304 | J304.STEEL FIXERS SK |  |  |  | 161 | 64 | 2878 | 7522 | 8959 | 13290 | 23418 | 19882 | 27934 | 38001 | 35142 | 27341 | 38624 | 25092 | 22983 | 17411 | 6307 | 4313 | 2266 | 1062 | 961 | 947 | 789 | 13 |  |  |  |  | 325360
J305 | CARPENTERS SK | Resource ID: J305 | J305.CARPENTERS SK |  |  | 40 | 630 | 80 | 1512 | 5789 | 8235 | 13031 | 29778 | 28382 | 39094 | 52262 | 47555 | 36787 | 52816 | 34102 | 31263 | 24794 | 10050 | 6644 | 3731 | 1229 | 1489 | 981 | 661 | 7 |  |  |  |  | 430942
J306 | CONCRETE MASON SK | Resource ID: J306 | J306.CONCRETE MASON SK | [5 empty] | 564 | 1493 | 1944 | 3471 | 5588 | 6293 | 6933 | 9365 | 7708 | 6985 | 9857 | 6210 | 6342 | 5663 | 2432 | 2100 | 1324 | 703 | 695 | 394 | 125 | 14 |  |  |  |  | 86203
J307 | BLOCK MASON SK | Resource ID: J307 | J307.BLOCK MASON SK |  |  | 50 | 770 | 80 | [5 empty] | 4068 | 17559 | 25891 | 29645 | 26889 | 40665 | 27470 | 24650 | 28061 | 20387 | 9879 | 4933 | 64 | [8 empty] | 261061
J308 | PLASTER MASON SK | Resource ID: J308 | J308.PLASTER MASON SK |  |  | 45 | 700 | 80 | [5 empty] | 1338 | 4903 | 21867 | 31416 | 40853 | 75542 | 58192 | 57026 | 60428 | 45248 | 46852 | 26750 | 10141 | 320 | 1136 | 144 | [5 empty] | 482981
J309 | TILE MASON SK | Resource ID: J309 | J309.TILE MASON SK | [11 empty] | 1187 | 4863 | 9933 | 13192 | 27401 | 21477 | 19639 | 21807 | 16528 | 15913 | 13715 | 4613 | 1939 | 81 | 15 | [5 empty] | 172303
J310 | GRANITE MASON SK | Resource ID: J310 | J310.GRANITE MASON SK | [12 empty] | 176 | 255 | 678 | 2099 | 2203 | 3005 | 3276 | 2721 | 2950 | 2945 | 2231 | 961 | 303 | 8 | [5 empty] | 23811
J311 | MANHOLES SK | Resource ID: J311 | J311.MANHOLES SK | [11 empty] | 311 | 1139 | 2086 | 2740 | 5059 | 2977 | 2889 | 2880 | 2146 | 1982 | 1073 | 606 | [8 empty] | 25888
J312 | KERBSTONE MASON SK | Resource ID: J312 | J312.KERBSTONE MASON SK | [12 empty] | 113 | 130 | 193 | 2209 | 3169 | 3273 | 3731 | 2940 | 3366 | 2043 | 1559 | 2192 | 1401 | 938 | [5 empty] | 27257
J313 | INTERLOCK MASON SK | Resource ID: J313 | J313.INTERLOCK MASON SK | [10 empty] | 62 | 185 | 417 | 462 | 695 | 1936 | 2234 | 2502 | 2139 | 2208 | 1487 | 1526 | 1107 | 762 | 1626 | [6 empty] | 19348
J315 | SURVEYOR SK | Resource ID: J315 | J315.SURVEYOR SK |  | 40 | 210 | [28 empty] | 250
J320 | DRAFTMAN SK | Resource ID: J320 | J320.DRAFTMAN SK |  | 324 | 670 | 637 | 532 | 919 | 1126 | 808 | 720 | 144 | [11 empty] | 816 | 368 | 712 | 312 | 192 |  | 707 | 161 | 161 | 10 | 9319
LC30 | LABOR - CIVIL | Resource ID: LC30 | LC30.LABOR - CIVIL |  | 901 | 4531 | 6005 | 2111 | 6348 | 15785 | 19484 | 29814 | 52531 | 51250 | 76104 | 111868 | 111143 | 103960 | 160983 | 111468 | 103814 | 100578 | 58990 | 50940 | 31232 | 16481 | 9444 | 4240 | 2114 | 25 | 101 | 242 | 242 | 15 | 1242744
LS30 | LABOR- SUBCONTRACTOR | Resource ID: LS30 | LS30.LABOR- SUBCONTRACTOR |  |  |  |  | 317 | 1259 | 2248 | 1754 | 2136 | 1879 | 1531 | 5445 | 15430 | 24195 | 35137 | 77609 | 73989 | 83578 | 104759 | 78197 | 82390 | 80280 | 48629 | 39004 | 28694 | 14119 | 5103 | 6209 | 4800 | 4800 | 400 | 823891
M301 | AC TECHNICIAN SK | Resource ID: M301 | M301.AC TECHNICIAN SK | [10 empty] | 4 | 247 | 1350 | 2139 | 4248 | 7592 | 8448 | 10523 | 16258 | 12656 | 13922 | 13111 | 8144 | 8128 | 5994 | 3261 | 1640 | 2480 | 1920 | 1920 | 160 | 124145
M302 | ELECTRICIANS SK | Resource ID: M302 | M302.ELECTRICIANS SK |  | 74 | 295 | 672 | 264 | 25 |  |  |  |  | 428 | 4731 | 11607 | 18356 | 27024 | 47790 | 41020 | 45747 | 62854 | 42438 | 43717 | 40274 | 26105 | 21703 | 15711 | 7181 | 3331 | 4968 | 3840 | 3840 | 320 | 474315
M303 | MECHANICALS SK | Resource ID: M303 | M303.MECHANICALS SK |  | 71 | 290 | 744 | 256 | 24 |  | 165 | 495 | 442 | 936 | 5425 | 10407 | 11830 | 12333 | 21302 | 18539 | 19601 | 30485 | 20746 | 22625 | 24014 | 15770 | 15578 | 9676 | 6279 | 3280 | 4960 | 3840 | 3840 | 320 | 264273
M304 | MATERIAL ENGG | Resource ID: M304 | M304.MATERIAL ENGG | 8 | 144 | 348 | 497 | 353 | 734 | 775 | 708 | 403 | 293 | 77 | 21 | 15 | [18 empty] | 4376
M305 | QUANTITY SURVEYOUR | Resource ID: M305 | M305.QUANTITY SURVEYOUR | 16 | 329 | 397 | 398 | [27 empty] | 1140
M306 | SAFETY OFFICER | Resource ID: M306 | M306.SAFETY OFFICER | 24 | 358 | 237 | 182 | [27 empty] | 801
S301 | WATERPROOFING SPECIALIST SK | Resource ID: S301 | S301.WATERPROOFING SPECIALIST SK |  |  |  |  | 263 | 947 | 2080 | 1408 | 1821 | 1519 | 853 | 1326 | 3251 | 4528 | 5413 | 10858 | 8740 | 8225 | 6740 | 6162 | 6546 | 4420 | 2954 | 1203 | [7 empty] | 79257
S302 | PAINTERS SK | Resource ID: S302 | S302.PAINTERS SK | [11 empty] | 904 | 7244 | 11561 | 19297 | 40502 | 39031 | 46764 | 55019 | 43034 | 42163 | 41132 | 24245 | 15828 | 14139 | 4502 | [5 empty] | 405365
S303 | FALSE CEILING SKILLED SK | Resource ID: S303 | S303.FALSE CEILING SKILLED SK | [12 empty] | 1173 | 2211 | 4231 | 13160 | 10019 | 9841 | 10504 | 7805 | 7332 | 6905 | 4308 | 2452 | 292 | [6 empty] | 80233
S304 | DOOR ERECTOR SK | Resource ID: S304 | S304.DOOR ERECTOR SK | [12 empty] | 135 | 605 | 695 | 2924 | 3689 | 4520 | 4856 | 3216 | 3404 | 3598 | 1752 | 2027 | 818 | 112 | [5 empty] | 32351
S305 | WINDOW ERECTOR SK | Resource ID: S305 | S305.WINDOW ERECTOR SK | [12 empty] | 9 | 75 | 137 | 426 | 802 | 847 | 1062 | 763 | 789 | 791 | 468 | 499 | 257 | [6 empty] | 6925
S306 | JOINERY WORK SK | Resource ID: S306 | S306.JOINERY WORK SK | [12 empty] | 15 | 529 | 526 | 2162 | 3503 | 3262 | 3750 | 2602 | 3006 | 3441 | 1875 | 2158 | 1546 | 49 | [5 empty] | 28424
S307 | COUNTER SK | Resource ID: S307 | S307.COUNTER SK | [13 empty] | 4 | 1 | 42 | 145 | 177 | 246 | 241 | 269 | 320 | 195 | 207 | 168 | [6 empty] | 2015
S308 | HANDRAIL ERECTOR SKILLED | Resource ID: S308 | S308.HANDRAIL ERECTOR SKILLED | [11 empty] | 20 | 88 | 325 | 587 | 1144 | 1274 | 1594 | 2065 | 1636 | 1687 | 1183 | 820 | 854 | 855 | 63 | [5 empty] | 14195
S309 | EPOXY SK | Resource ID: S309 | S309.EPOXY SK | [12 empty] | 5 |  |  | 120 | 131 | 142 | 221 | 169 | 194 | 257 | 63 | 51 | 100 | 41 | [5 empty] | 1494
S310 | PRE CAST CONCRETE SK | Resource ID: S310 | S310.PRE CAST CONCRETE SK | [11 empty] | 27 | 98 | 555 | 514 | 1415 | 1358 | 1257 | 1097 | 863 | 1031 | 785 | 432 | 409 | [7 empty] | 9841
S311 | LADDER ERECTOR SK | Resource ID: S311 | S311.LADDER ERECTOR SK | [11 empty] | 16 | 88 | 169 | 208 | 518 | 575 | 694 | 765 | 392 | 388 | 576 | 273 | 122 | 157 | 8 | [5 empty] | 4949
S312 | LANDSCAPING SK | Resource ID: S312 | S312.LANDSCAPING SK | [14 empty] | 830 | 2921 | 4946 | 8269 | 10437 | 6992 | 9043 | 10158 | 5936 | 3719 | 4691 | 3842 | 632 |  |  |  |  | 72416
S313 | GATE ERECTOR SK | Resource ID: S313 | S313.GATE ERECTOR SK | [11 empty] | 10 | 123 | 152 | 155 | 268 | 201 | 191 | 148 | 110 | 122 | 124 | 93 | 56 | 11 | [6 empty] | 1764
S314 | STEEL ERECTOR SK | Resource ID: S314 | S314.STEEL ERECTOR SK | [13 empty] | 166 | 295 | 692 | 896 | 1607 | 2571 | 1437 | 1561 | 1908 | 1367 | 667 | 1457 | 751 | 679 | 8 |  |  |  | 16062
S315 | PULL BOX SK | Resource ID: S315 | S315.PULL BOX SK | [15 empty] | 55 | 154 | 204 | 174 | 110 | 69 | 113 | 83 | 63 | 135 | 6 | [5 empty] | 1166
S316 | ASPHALT SK | Resource ID: S316 | S316.ASPHALT SK | [17 empty] | 190 | 570 | 192 | 264 | 320 | 221 | 91 | 312 | 160 | 152 |  |  |  |  | 2472
S317 | EXPANSION JOINT SKILLED SK | Resource ID: S317 | S317.EXPANSION JOINT SKILLED SK | [14 empty] | 152 | 719 | 423 | 363 | 393 | 153 | 85 | 168 | 105 | 95 | [7 empty] | 2656
S318 | DOOR WORK SK | Resource ID: S318 | S318.DOOR WORK SK | [15 empty] | 8 | 192 | 136 | 200 | 64 |  |  | 16 | 312 | 72 | [6 empty] | 1000
S319 | GRC SK | Resource ID: S319 | S319.GRC SK | [13 empty] | 400 | 300 | 500 | 680 | 760 | 880 | 380 | 420 | 480 | [9 empty] | 4800
S320 | ANTITERMITE SK | Resource ID: S320 | S320.ANTITERMITE SK |  |  |  |  | 580 | 2409 | 3910 | 3138 | 3457 | 3112 | 2173 | 2720 | 2666 | 876 | [17 empty] | 25041
0

## Sheet2
RR Expenditure Type ID | Resource ID Name | 2012-AP10 | 2012-AP11 | 2012-AP12 | 2013-AP01 | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 | 2014-AP05 | 2014-AP06 | 2014-AP07 | 2014-AP08 | 2014-AP09 | 2014-AP10 | 2014-AP11 | 2014-AP12 | 2015-AP01 | 2015-AP02 | 2015-AP03 | 2015-AP04
EQOP | EQUIP OPERATORS
J302 | BLINDING MASON SK
J303 | SCREED MASON SK
J304 | STEEL FIXERS SK
J305 | CARPENTERS SK
J306 | CONCRETE MASON SK
J307 | BLOCK MASON SK
J308 | PLASTER MASON SK
J309 | TILE MASON SK
J310 | GRANITE MASON SK
J311 | MANHOLES SK
J312 | KERBSTONE MASON SK
J313 | INTERLOCK MASON SK
J315 | SURVEYOR SK
J320 | DRAFTMAN SK
LC30 | LABOR - CIVIL
LS30 | LABOR- SUBCONTRACTOR
M301 | AC TECHNICIAN SK
M302 | ELECTRICIANS SK
M303 | MECHANICALS SK
M304 | MATERIAL ENGG
M305 | QUANTITY SURVEYOUR
M306 | SAFETY OFFICER
S301 | WATERPROOFING SPECIALIST SK
S302 | PAINTERS SK
S303 | FALSE CEILING SKILLED SK
S304 | DOOR ERECTOR SK
S305 | WINDOW ERECTOR SK
S306 | JOINERY WORK SK
S307 | COUNTER SK
S308 | HANDRAIL ERECTOR SKILLED
S309 | EPOXY SK
S310 | PRE CAST CONCRETE SK
S311 | LADDER ERECTOR SK
S312 | LANDSCAPING SK
S313 | GATE ERECTOR SK
S314 | STEEL ERECTOR SK
S315 | PULL BOX SK
S316 | ASPHALT SK
S317 | EXPANSION JOINT SKILLED SK
S318 | DOOR WORK SK
S319 | GRC SK
S320 | ANTITERMITE SK

## Sheet4
I have created a PivotTable based on your columns. For example, the sum of total hours for "M301" is 124145 and for "S320" is 25041. See the PivotTable above for more details.

## Sheet5
Resource ID Name | Sum of Total Hours per resource from 2012- AP10 - 2025- AP04 period
AC TECHNICIAN SK | 124145
ANTITERMITE SK | 25041
ASPHALT SK | 2472
BLINDING MASON SK | 38273
BLOCK MASON SK | 261061
CARPENTERS SK | 430942
CONCRETE MASON SK | 86203
COUNTER SK | 2015
DOOR ERECTOR SK | 32351
DOOR WORK SK | 1000
DRAFTMAN SK | 9319
ELECTRICIANS SK | 474315
EPOXY SK | 1494
EQUIP OPERATORS | 162108
EXPANSION JOINT SKILLED SK | 2656
FALSE CEILING SKILLED SK | 80233
GATE ERECTOR SK | 1764
GRANITE MASON SK | 23811
GRC SK | 4800
HANDRAIL ERECTOR SKILLED | 14195
INTERLOCK MASON SK | 19348
JOINERY WORK SK | 28424
KERBSTONE MASON SK | 27257
LABOR - CIVIL | 1242744
LABOR- SUBCONTRACTOR | 823891
LADDER ERECTOR SK | 4949
LANDSCAPING SK | 72416
MANHOLES SK | 25888
MATERIAL ENGG | 4376
MECHANICALS SK | 264273
PAINTERS SK | 405365
PLASTER MASON SK | 482981
PRE CAST CONCRETE SK | 9841
PULL BOX SK | 1166
QUANTITY SURVEYOUR | 1140
SAFETY OFFICER | 801
SCREED MASON SK | 96090
STEEL ERECTOR SK | 16062
STEEL FIXERS SK | 325360
SURVEYOR SK | 250
TILE MASON SK | 172303
WATERPROOFING SPECIALIST SK | 79257
WINDOW ERECTOR SK | 6925
Grand Total | 5889305

## Sheet1
RR Expenditure Type | Resource ID Name | 2012-AP10 | 2012-AP11 | 2012-AP12 | 2013-AP01 | 2013-AP02 | 2013-AP03 | 2013-AP04 | 2013-AP05 | 2013-AP06 | 2013-AP07 | 2013-AP08 | 2013-AP09 | 2013-AP10 | 2013-AP11 | 2013-AP12 | 2014-AP01 | 2014-AP02 | 2014-AP03 | 2014-AP04 | 2014-AP05 | 2014-AP06 | 2014-AP07 | 2014-AP08 | 2014-AP09 | 2014-AP10 | 2014-AP11 | 2014-AP12 | 2015-AP01 | 2015-AP02 | 2015-AP03 | 2015-AP04 | Total hours
Total |  | 48 | 3197 | 12153 | 17862 | 6249 | 20537 | 48624 | 56224 | 82552 | 135252 | 130855 | 208921 | 338909 | 370637 | 391591 | 680224 | 535477 | 544515 | 608280 | 415084 | 402437 | 336922 | 191260 | 139801 | 99247 | 47217 | 14966 | 19433 | 14803 | 14803 | 1225 | 5889305
Resource ID: EQOP | EQOP.EQUIP OPERATORS |  | 956 | 5040 | 6466 | 1030 | 1573 | 5349 | 5714 | 6609 | 7097 | 4995 | 4183 | 6205 | 5781 | 8007 | 12985 | 12964 | 11141 | 13853 | 9183 | 9799 | 7887 | 5933 | 4846 | 2579 | 1843 | 90 |  |  |  |  | 162108
Resource ID: J302 | J302.BLINDING MASON SK |  |  |  |  | 239 | 777 | 1217 | 1975 | 4130 | 5335 | 4460 | 4604 | 4673 | 2982 | 2657 | 3606 | 1162 | 328 |  | 64 | 64 | [10 empty] | 38273
Resource ID: J303 | J303.SCREED MASON SK | [5 empty] | 568 | 1330 | 1932 | 3175 | 4116 | 4123 | 5032 | 8365 | 7723 | 8531 | 13715 | 8002 | 7168 | 7605 | 5522 | 5121 | 2323 | 1309 | 254 | 162 | 14 | [5 empty] | 96090
Resource ID: J304 | J304.STEEL FIXERS SK |  |  |  | 161 | 64 | 2878 | 7522 | 8959 | 13290 | 23418 | 19882 | 27934 | 38001 | 35142 | 27341 | 38624 | 25092 | 22983 | 17411 | 6307 | 4313 | 2266 | 1062 | 961 | 947 | 789 | 13 |  |  |  |  | 325360
Resource ID: J305 | J305.CARPENTERS SK |  |  | 40 | 630 | 80 | 1512 | 5789 | 8235 | 13031 | 29778 | 28382 | 39094 | 52262 | 47555 | 36787 | 52816 | 34102 | 31263 | 24794 | 10050 | 6644 | 3731 | 1229 | 1489 | 981 | 661 | 7 |  |  |  |  | 430942
Resource ID: J306 | J306.CONCRETE MASON SK | [5 empty] | 564 | 1493 | 1944 | 3471 | 5588 | 6293 | 6933 | 9365 | 7708 | 6985 | 9857 | 6210 | 6342 | 5663 | 2432 | 2100 | 1324 | 703 | 695 | 394 | 125 | 14 |  |  |  |  | 86203
Resource ID: J307 | J307.BLOCK MASON SK |  |  | 50 | 770 | 80 | [5 empty] | 4068 | 17559 | 25891 | 29645 | 26889 | 40665 | 27470 | 24650 | 28061 | 20387 | 9879 | 4933 | 64 | [8 empty] | 261061
Resource ID: J308 | J308.PLASTER MASON SK |  |  | 45 | 700 | 80 | [5 empty] | 1338 | 4903 | 21867 | 31416 | 40853 | 75542 | 58192 | 57026 | 60428 | 45248 | 46852 | 26750 | 10141 | 320 | 1136 | 144 | [5 empty] | 482981
Resource ID: J309 | J309.TILE MASON SK | [11 empty] | 1187 | 4863 | 9933 | 13192 | 27401 | 21477 | 19639 | 21807 | 16528 | 15913 | 13715 | 4613 | 1939 | 81 | 15 | [5 empty] | 172303
Resource ID: J310 | J310.GRANITE MASON SK | [12 empty] | 176 | 255 | 678 | 2099 | 2203 | 3005 | 3276 | 2721 | 2950 | 2945 | 2231 | 961 | 303 | 8 | [5 empty] | 23811
Resource ID: J311 | J311.MANHOLES SK | [11 empty] | 311 | 1139 | 2086 | 2740 | 5059 | 2977 | 2889 | 2880 | 2146 | 1982 | 1073 | 606 | [8 empty] | 25888
Resource ID: J312 | J312.KERBSTONE MASON SK | [12 empty] | 113 | 130 | 193 | 2209 | 3169 | 3273 | 3731 | 2940 | 3366 | 2043 | 1559 | 2192 | 1401 | 938 | [5 empty] | 27257
Resource ID: J313 | J313.INTERLOCK MASON SK | [10 empty] | 62 | 185 | 417 | 462 | 695 | 1936 | 2234 | 2502 | 2139 | 2208 | 1487 | 1526 | 1107 | 762 | 1626 | [6 empty] | 19348
Resource ID: J315 | J315.SURVEYOR SK |  | 40 | 210 | [28 empty] | 250
Resource ID: J320 | J320.DRAFTMAN SK |  | 324 | 670 | 637 | 532 | 919 | 1126 | 808 | 720 | 144 | [11 empty] | 816 | 368 | 712 | 312 | 192 |  | 707 | 161 | 161 | 10 | 9319
Resource ID: LC30 | LC30.LABOR - CIVIL |  | 901 | 4531 | 6005 | 2111 | 6348 | 15785 | 19484 | 29814 | 52531 | 51250 | 76104 | 111868 | 111143 | 103960 | 160983 | 111468 | 103814 | 100578 | 58990 | 50940 | 31232 | 16481 | 9444 | 4240 | 2114 | 25 | 101 | 242 | 242 | 15 | 1242744
Resource ID: LS30 | LS30.LABOR- SUBCONTRACTOR |  |  |  |  | 317 | 1259 | 2248 | 1754 | 2136 | 1879 | 1531 | 5445 | 15430 | 24195 | 35137 | 77609 | 73989 | 83578 | 104759 | 78197 | 82390 | 80280 | 48629 | 39004 | 28694 | 14119 | 5103 | 6209 | 4800 | 4800 | 400 | 823891
Resource ID: M301 | M301.AC TECHNICIAN SK | [10 empty] | 4 | 247 | 1350 | 2139 | 4248 | 7592 | 8448 | 10523 | 16258 | 12656 | 13922 | 13111 | 8144 | 8128 | 5994 | 3261 | 1640 | 2480 | 1920 | 1920 | 160 | 124145
Resource ID: M302 | M302.ELECTRICIANS SK |  | 74 | 295 | 672 | 264 | 25 |  |  |  |  | 428 | 4731 | 11607 | 18356 | 27024 | 47790 | 41020 | 45747 | 62854 | 42438 | 43717 | 40274 | 26105 | 21703 | 15711 | 7181 | 3331 | 4968 | 3840 | 3840 | 320 | 474315
Resource ID: M303 | M303.MECHANICALS SK |  | 71 | 290 | 744 | 256 | 24 |  | 165 | 495 | 442 | 936 | 5425 | 10407 | 11830 | 12333 | 21302 | 18539 | 19601 | 30485 | 20746 | 22625 | 24014 | 15770 | 15578 | 9676 | 6279 | 3280 | 4960 | 3840 | 3840 | 320 | 264273
Resource ID: M304 | M304.MATERIAL ENGG | 8 | 144 | 348 | 497 | 353 | 734 | 775 | 708 | 403 | 293 | 77 | 21 | 15 | [18 empty] | 4376
Resource ID: M305 | M305.QUANTITY SURVEYOUR | 16 | 329 | 397 | 398 | [27 empty] | 1140
Resource ID: M306 | M306.SAFETY OFFICER | 24 | 358 | 237 | 182 | [27 empty] | 801
Resource ID: S301 | S301.WATERPROOFING SPECIALIST SK |  |  |  |  | 263 | 947 | 2080 | 1408 | 1821 | 1519 | 853 | 1326 | 3251 | 4528 | 5413 | 10858 | 8740 | 8225 | 6740 | 6162 | 6546 | 4420 | 2954 | 1203 | [7 empty] | 79257
Resource ID: S302 | S302.PAINTERS SK | [11 empty] | 904 | 7244 | 11561 | 19297 | 40502 | 39031 | 46764 | 55019 | 43034 | 42163 | 41132 | 24245 | 15828 | 14139 | 4502 | [5 empty] | 405365
Resource ID: S303 | S303.FALSE CEILING SKILLED SK | [12 empty] | 1173 | 2211 | 4231 | 13160 | 10019 | 9841 | 10504 | 7805 | 7332 | 6905 | 4308 | 2452 | 292 | [6 empty] | 80233
Resource ID: S304 | S304.DOOR ERECTOR SK | [12 empty] | 135 | 605 | 695 | 2924 | 3689 | 4520 | 4856 | 3216 | 3404 | 3598 | 1752 | 2027 | 818 | 112 | [5 empty] | 32351
Resource ID: S305 | S305.WINDOW ERECTOR SK | [12 empty] | 9 | 75 | 137 | 426 | 802 | 847 | 1062 | 763 | 789 | 791 | 468 | 499 | 257 | [6 empty] | 6925
Resource ID: S306 | S306.JOINERY WORK SK | [12 empty] | 15 | 529 | 526 | 2162 | 3503 | 3262 | 3750 | 2602 | 3006 | 3441 | 1875 | 2158 | 1546 | 49 | [5 empty] | 28424
Resource ID: S307 | S307.COUNTER SK | [13 empty] | 4 | 1 | 42 | 145 | 177 | 246 | 241 | 269 | 320 | 195 | 207 | 168 | [6 empty] | 2015
Resource ID: S308 | S308.HANDRAIL ERECTOR SKILLED | [11 empty] | 20 | 88 | 325 | 587 | 1144 | 1274 | 1594 | 2065 | 1636 | 1687 | 1183 | 820 | 854 | 855 | 63 | [5 empty] | 14195
Resource ID: S309 | S309.EPOXY SK | [12 empty] | 5 |  |  | 120 | 131 | 142 | 221 | 169 | 194 | 257 | 63 | 51 | 100 | 41 | [5 empty] | 1494
Resource ID: S310 | S310.PRE CAST CONCRETE SK | [11 empty] | 27 | 98 | 555 | 514 | 1415 | 1358 | 1257 | 1097 | 863 | 1031 | 785 | 432 | 409 | [7 empty] | 9841
Resource ID: S311 | S311.LADDER ERECTOR SK | [11 empty] | 16 | 88 | 169 | 208 | 518 | 575 | 694 | 765 | 392 | 388 | 576 | 273 | 122 | 157 | 8 | [5 empty] | 4949
Resource ID: S312 | S312.LANDSCAPING SK | [14 empty] | 830 | 2921 | 4946 | 8269 | 10437 | 6992 | 9043 | 10158 | 5936 | 3719 | 4691 | 3842 | 632 |  |  |  |  | 72416
Resource ID: S313 | S313.GATE ERECTOR SK | [11 empty] | 10 | 123 | 152 | 155 | 268 | 201 | 191 | 148 | 110 | 122 | 124 | 93 | 56 | 11 | [6 empty] | 1764
Resource ID: S314 | S314.STEEL ERECTOR SK | [13 empty] | 166 | 295 | 692 | 896 | 1607 | 2571 | 1437 | 1561 | 1908 | 1367 | 667 | 1457 | 751 | 679 | 8 |  |  |  | 16062
Resource ID: S315 | S315.PULL BOX SK | [15 empty] | 55 | 154 | 204 | 174 | 110 | 69 | 113 | 83 | 63 | 135 | 6 | [5 empty] | 1166
Resource ID: S316 | S316.ASPHALT SK | [17 empty] | 190 | 570 | 192 | 264 | 320 | 221 | 91 | 312 | 160 | 152 |  |  |  |  | 2472
Resource ID: S317 | S317.EXPANSION JOINT SKILLED SK | [14 empty] | 152 | 719 | 423 | 363 | 393 | 153 | 85 | 168 | 105 | 95 | [7 empty] | 2656
Resource ID: S318 | S318.DOOR WORK SK | [15 empty] | 8 | 192 | 136 | 200 | 64 |  |  | 16 | 312 | 72 | [6 empty] | 1000
Resource ID: S319 | S319.GRC SK | [13 empty] | 400 | 300 | 500 | 680 | 760 | 880 | 380 | 420 | 480 | [9 empty] | 4800
Resource ID: S320 | S320.ANTITERMITE SK |  |  |  |  | 580 | 2409 | 3910 | 3138 | 3457 | 3112 | 2173 | 2720 | 2666 | 876